## Sheet1
Count | ID | Short Description1 | Cpvs | Cpvs Designation | Environmental criteria (T/F) | Publication Year | Close Year | Country | Municipality | District | District Code | Submission deadline (days) | Signing date | Closing date | Diference between close and signing dates | Execution deadline (days) | Base Bid Price (€) | Initial price (€) | I. price Class | Effective Price (€) | Difference between the effective and initial price (€) | Proportion between the effective and initial price (%) | Award criteria | Award criteria class | Classification of the multifactor criteria (%) | Collateral | Published in the EU journal | Contract end type | Number of bidders | Involves joint procurement (with several entities) (T/F) | Awarded by a central purchasing body (T/F) | Conclusion of a framework agreement (T/F) | Electronic auction (T/F) | Negotiation phase (T/F) | Contracting by lots (T/F) | Justification for deadline change | Justification for price change
0 | 9347658 | Construction of the domestic and rainwater drainage network at street of Benvindos à Quintinhas and street Fernão Seco - Charneca de Caparica | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Almada | Setúbal | 17 | 30 | 11-01-2021 | 31-05-2022 | 505 | 210 | 183000 | 179951 | 1 | 210227.16 | -30276.16 | 85.5984 | Best value for money: No Criterion related to quality Name: - Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project was finished ahead of schedule, evidencing the good rhythm of the projects and the absence of circumstances that hindered the progress of the projects. | price review
1 | 9331053 | Repairs to Municipal Swimming Pools | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2020 | 2022 | Portugal | Viseu | Viseu | 20 | N/A | 28-08-2020 | 14-03-2022 | 563 | 30 | 43600 | 43196.8 | 1 | 43196.8 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 2 | FALSE | N/A | N/A | N/A | N/A | FALSE
2 | 9328338 | Rehabilitation contract for the beachside ramp at the fishing port of Quarteira: Phase 2 - vertical joints | 45262330-3 | Concrete repair work | FALSE | 2022 | 2022 | Portugal | Loulé | Faro | 8 | 28 | 16-03-2022 | 11-06-2022 | 87 | 60 | 31410 | 19725 | 1 | 19725 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | completion of work carried out before the deadline.
3 | 9305186 | Rehabilitation of the Cavalo Bridge in Travassos de Baixo | 45000000-7, 45221119-9 | Construction work, Bridge renewal construction work | FALSE | 2020 | 2022 | Portugal | Viseu | Viseu | 20 | 19 | 08-02-2021 | 03-05-2022 | 449 | 90 | 57900 | 42715.76 | 1 | 42715.76 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | from 05/10/2021 to 06/15/2021 (37 days), due to bad weather conditions that caused an increase in flow in the stream; from 9/2/2021 to 10/13/2021 (41 days), as an additional contract for the replacement of the water pipe is under development. were there any changes in the execution time of the project? extension of 15 days, 7 days regarding the project contained in the additional contract and 8 days regarding the contractual work that cannot be carried out until the water pipe is replaced. | complementary work
4 | 9286914 | Replacement of the bridge in Moure de Madalena in the parish of Abraveses | 45221119-9 | Bridge renewal construction work | FALSE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 15 | 20-05-2021 | 29-04-2022 | 344 | 90 | 137030 | 41480 | 1 | 41480 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period | price review
5 | 9269183 | Rehabilitation of the Bridge in Casal de Torredeita | 45221119-9 | Bridge renewal construction work | FALSE | 2020 | 2022 | Portugal | Viseu | Viseu | 20 | 18 | 08-09-2020 | 20-04-2022 | 589 | 30 | 33378 | 24967.75 | 1 | 22605.25 | 2362.5 | 110.4511 | Best value for money: No Criterion related to quality Name: Weighting Weighting: 0% Criterion related to cost Name: Weighting Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | underwork
6 | 9250937 | Reconstruction of wall and hydraulic passage at street Quinta da Longra - S.Salvador" | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 18 | 08-03-2021 | 29-04-2022 | 417 | 90 | 40050 | 37849.69 | 1 | 22605.25 | 15244.44 | 167.4376 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 | 9248436 | streets in Rio Torto | 45233252-0 | Surface work for streets | FALSE | 2022 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-05-2022 | 09-08-2022 | 91 | 30 | 19692.66 | 18970 | 1 | 18970 | 0 | 100 | If yes in point 5, is the award criterion differentiated by batch? No Multifactor? No Monofactor Factor - Name: Price | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | early completion | provisional ordinary price review due to the non-existence of indices
8 | 9201504 | Construction / Conservation of Sports, Recreational and Leisure Infrastructures in the Parishes. Contract: Remodeling of the Playgrounds of elementary school and JI de Tocha and elementary school de Gesteira | 45113000-2 | Siteworks | FALSE | 2022 | 2022 | Portugal | Cantanhede | Coimbra | 6 | 14 | 27-04-2022 | 23-06-2022 | 57 | 120 | 36000 | 32472 | 1 | 32472 | 0 | 100 | If yes in point 5, is the award criterion differentiated by batch? No Multifactor? No Monofactor Factor - Name: Price | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | completion of works.
9 | 9194199 | Contract for "Improvement of EM 553 from Rio Bom to Seixedo" | 45233252-0 | Surface work for streets | FALSE | 2022 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-04-2022 | 03-08-2022 | 105 | 60 | 75471.7 | 71658.8 | 1 | 71658.8 | 0 | 100 | If yes in point 5, is the award criterion differentiated by batch? No Multifactor? No Monofactor Factor - Name: Price | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | term extension, determined by the difficulty of acquiring and delivering raw materials.
10 | 9191389 | Maintenance dredging of the NW sector of the port basin of Póvoa de Varzim fishing port. | 45240000-1 | Construction work for water projects | FALSE | 2021 | 2022 | Portugal | Póvoa de Varzim | Porto | 13 | 14 | 28-09-2021 | 30-06-2022 | 275 | 60 | 111000 | 101373.5 | 1 | 101373.5 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | work suspension notice: 10.27.2021 and suspension notice: 04.04.2022
11 | 9189304 | Construction of Rainwater Drainage Infrastructure at street of Intermunicipal - Vilarinho | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Santo Tirso | Porto | 13 | 14 | 10-02-2022 | 23-05-2022 | 102 | 60 | 14137.5 | 13925 | 1 | 6306.65 | 7618.35 | 220.7987 | Best value for money: No Criterion related to quality Name: None Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | the non-execution of some contractual works as well as the existence of more works
12 | 9144908 | Energy rehabilitation of the school of the S. João de lourosa | 45000000-7 | Construction work | FALSE | 2020 | 2022 | Portugal | Viseu | Viseu | 20 | 21 | 15-07-2020 | 21-01-2022 | 555 | 70 | 129880 | 111977.14 | 1 | 118174.98 | -6197.84 | 94.7554 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
13 | 9142634 | Rehabilitation and replacement of walkways inside the fishermen's dock | 45241500-3 | Wharf construction work | FALSE | 2020 | 2022 | Portugal | Setúbal | Setúbal | 17 | 15 | 26-11-2020 | 24-03-2022 | 483 | 90 | 90000 | 89560 | 1 | 89560 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Factor B - Work Methodology and Planning Weighting: 30% Criterion related to cost Name: Factor A - Price; Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1 day
14 | 9116880 | 2020.116.06.C1 - SFP Setúbal - Replacement of fiber cement roof | 45262660-5 | Asbestos-removal work | TRUE | 2020 | 2022 | Portugal | Setúbal | Setúbal | 17 | 20 | 21-12-2020 | 19-05-2022 | 514 | 90 | 123155 | 84481.33 | 1 | 84481.33 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
15 | 9056685 | Urgent Public Tender No. 83/2021/GRM - General Repair of Roof Gutters - Alfeite Social Neighborhood - Espadarte, Fataça and Dentão Blocks. | 45000000-7 | Construction work | FALSE | 2021 | 2022 | Portugal | Almada | Setúbal | 17 | N/A | 04-10-2021 | 27-01-2022 | 115 | 75 | 58375.41 | 58357.04 | 1 | 58357.04 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | the project delayed
16 | 8962999 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro Elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 20-01-2022 | 279 | 90 | 1733000 | 79700 | 1 | 145249.27 | -65549.27 | 54.8712 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
17 | 8920361 | Improvement of the rainwater network at R. Quinta de Calvelhe, Lavra | 45240000-1 | Construction work for water projects | FALSE | 2021 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 16-02-2022 | 06-06-2022 | 110 | 75 | 134000 | 98488 | 1 | 98488 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
18 | 8911358 | Extension of water supply networks in Carvalho Mesuras and Ruival - Parish of Várzea, Aliviada and Folhada | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 19 | 14-02-2022 | 29-06-2022 | 135 | 90 | 53000 | 52385.5 | 1 | 55245.42 | -2859.92 | 94.8232 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the project ended and days before the deadline. | positive interim pricing revision.
19 | 8895843 | residential home APPACDM-fundão | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2022 | Portugal | Fundão | Castelo Branco | 5 | 20 | 07-03-2019 | 21-01-2022 | 1051 | 183 | 301847.36 | 277775.22 | 2 | 278040.18 | -264.96 | 99.9047 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of material by suppliers | extra work
20 | 8842410 | Lot 1 - remodeling of the interior garden according to the project lot 2 - waterproofing of the head office gutters, according to technical specification lot 3 - painting and maintenance of railings and gates | 45261320-3 | Guttering work | FALSE | 2021 | 2022 | Portugal | Porto | Porto | 13 | 14 | 04-01-2022 | 03-02-2022 | 30 | 40 | 74151 | 3053 | 1 | 3053 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: PRICE Weighting: 100% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the contractor completed the project within the deadline.
21 | 8835989 | Contract 65/gebalis/2021 - bairro padre cruz - rehabilitation of municipal housing - carnide - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 20-01-2022 | 19-07-2022 | 180 | 90 | 186000 | 35100 | 1 | 35100 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | in accordance
22 | 8823922 | Contract 53/gebalis/2021 - Bairro Alta de Lisboa - Rehabilitation of municipal housing - Santa Clara - Lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 12 | 19-01-2022 | 15-03-2022 | 55 | 90 | 473550 | 71379.15 | 1 | 71379.15 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | in accordance
23 | 8822411 | Contract 65/gebalis/2021 - bairro padre cruz - rehabilitation of municipal housing - carnide - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 20-01-2022 | 09-05-2022 | 109 | 90 | 186000 | 37566 | 1 | 37566 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
24 | 8822160 | Contract 65/gebalis/2021 - bairro padre cruz - rehabilitation of municipal housing - carnide - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 20-01-2022 | 23-05-2022 | 123 | 90 | 186000 | 39083 | 1 | 39083 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
25 | 8779624 | Contract 66/gebalis/2021 - rehabilitation of municipal buildings - western lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 20 | 19-01-2022 | 30-06-2022 | 162 | 90 | 154000 | 49960 | 1 | 49960 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
26 | 8778723 | Contract 102/gebalis/2021 - municipal housing rehabilitation works - beato / marvila / penha de frança / s. Vicente - Lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 28 | 17-01-2022 | 10-05-2022 | 113 | 45 | 265000 | 34500 | 1 | 34500 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
27 | 8777897 | Contract 94/gebalis/2021 - municipal housing rehabilitation works - marvila / olivais / parque Nações / - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 17-01-2022 | 24-06-2022 | 158 | 60 | 548000 | 36000 | 1 | 36721.92 | -721.92 | 98.0341 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
28 | 8777693 | Contract 94/gebalis/2021 - municipal housing rehabilitation works - marvila / olivais / parque Nações / - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 17-01-2022 | 04-07-2022 | 168 | 45 | 548000 | 36000 | 1 | 36000 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
29 | 8777277 | Contract 232/gebalis/2021 - north east lisbon - rehabilitation of municipal housing | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 14 | 17-01-2022 | 24-06-2022 | 158 | 45 | 96000 | 35850 | 1 | 35850 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
30 | 8776454 | Contract 53/gebalis/2021 - Bairro Alta de Lisboa - Rehabilitation of municipal housing - Santa Clara - Lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 12 | 17-01-2022 | 12-05-2022 | 115 | 45 | 473550 | 39632 | 1 | 39632 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
31 | 8757622 | Contract 94/gebalis/2021 - municipal housing rehabilitation works - marvila / olivais / parque Nações / - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 18-01-2022 | 25-05-2022 | 127 | 90 | 548000 | 57532.47 | 1 | 39089.99 | 18442.48 | 147.1795 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
32 | 8757416 | Contract 94/gebalis/2021 - municipal housing rehabilitation works - marvila / olivais / parque Nações / - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 18-01-2022 | 22-04-2022 | 94 | 90 | 548000 | 56170.24 | 1 | 56170.24 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
33 | 8720146 | Contract for the Conservation of the Modern Walls of the city of Moura | 45454100-5 | Restoration work | FALSE | 2018 | 2022 | Portugal | Moura | Beja | 2 | 30 | 09-01-2019 | 12-01-2022 | 1099 | 180 | 331927.4 | 278827.33 | 2 | 284814.89 | -5987.56 | 97.8977 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension requests | price review
34 | 8579833 | Michel Giacometti Elementary and High school - Roof replacement | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Sesimbra | Setúbal | 17 | 30 | 08-10-2021 | 24-05-2022 | 228 | 100 | 197064 | 155230 | 1 | 171622.91 | -16392.91 | 90.4483 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the execution period was 100 days starting on 11/18/2021 and ending on 02/26/2022. | the value of the contract was €155,230.00 + the price review in the amount of €16,392.91 makes the value €171,622.91
35 | 8575205 | Louredo Multisport Requalification | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2021 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-12-2021 | 21-07-2022 | 205 | 60 | 64330 | 60843.6 | 1 | 58577.6 | 2266 | 103.8684 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | 20-day extension of the deadline and 6 days for scheduling an inspection for the purpose of provisional acceptance | underwork
36 | 8574982 | Multi-sport center rehabilitation of the Outeiro Leisure Zone - Milheirós de Poiares | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2021 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-12-2021 | 13-06-2022 | 178 | 60 | 47000 | 37750 | 1 | 37516.35 | 233.65 | 100.6228 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | 7 days in the inspection appointment for provisional reception purposes | underwork
37 | 8551393 | Replacement of Electrical Panels (Pole A and C) and Intervention in Emergency Lighting (Pole A, B and C) | 45453100-8 | Refurbishment work | TRUE | 2021 | 2022 | Portugal | Coimbra | Coimbra | 6 | 9 | 07-12-2021 | 07-01-2022 | 31 | 60 | 82800 | 61683.82 | 1 | 61683.82 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes
38 | 8530980 | CP 236/DGADR/2020 - Contract to Repair Damage Caused by Bad Weather in December 2019 in the Infrastructures of A.H. From Baixo Mondego - 2nd Phase: Paths and Flowmeter | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Soure | Coimbra | 6 | 21 | 11-11-2020 | 06-05-2022 | 541 | 180 | 465000 | 408126.84 | 2 | 408126.84 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Proposal value Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work was carried out within the deadlines | price review
39 | 8530138 | 2019/40-DGEP - Restructuring of access to street São João Bosco, Queijas | 45233142-6 | Road-repair works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 19-07-2019 | 26-01-2022 | 922 | 45 | 23760 | 21820.8 | 1 | 24407.14 | -2586.34 | 89.4033 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | value extra work
40 | 8529796 | 1775/DOM - : Municipal Installation at street Ilha do Pico, nº2, in Mealhada - Remodeling for the New UIC Facilities (Citizenship Inclusion Unit) - | 45215000-7 | Construction work for buildings relating to health and social services, for crematoriums and public conveniences | FALSE | 2021 | 2022 | Portugal | Loures | Lisboa | 11 | 30 | 29-11-2021 | 23-06-2022 | 206 | 88 | 160935.41 | 159623.11 | 1 | 159623.11 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valuation of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty in acquiring materials
41 | 8465049 | Public works contract for the requalification of building nº 53 on street António Nobre, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 15 | 03-11-2021 | 21-04-2022 | 169 | 120 | 455000 | 454002.96 | 2 | 484411.9 | -30408.94 | 93.7225 | Best value for money: Yes Criterion related to quality Name: Deadline for execution of the work Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the change in deadlines was due to complementary work and the delay of some materials, namely aluminium. | the alteration in the value of the project was exclusively due to the complementary works that were not foreseen, and it was difficult to detect them before the execution of the contract.
42 | 8400159 | Construction of a wastewater drainage network in Portela do Monte - Penafiel Parish | 45232460-4 | Sanitary works | FALSE | 2020 | 2022 | Portugal | Penafiel | Porto | 13 | 21 | 01-10-2020 | 05-04-2022 | 551 | 300 | 293428.55 | 233728.01 | 1 | 245902.07 | -12174.06 | 95.0492 | Best value for money: No Criterion related to quality Name: NA Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work | price review
43 | 8399712 | Refurbishment of the EB 2,3 José dos Anjos de Carrazedo de Montenegro School - 3rd Phase | 45454000-4 | Restructuring work | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 21 | 19-11-2021 | 17-03-2022 | 118 | 90 | 281392.93 | 257966.66 | 2 | 257966.66 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of materials to complete the project caused by the current covid 19 pandemic situation
44 | 8377307 | 2019.126.02.C1 - SFP Sintra - replacement of fiber cement roofing | 45261213-0 | Metal roof-covering work | TRUE | 2021 | 2022 | Portugal | Sintra | Lisboa | 11 | 15 | 30-06-2021 | 07-07-2022 | 372 | 60 | 69000 | 57909.99 | 1 | 59983.24 | -2073.25 | 96.5436 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data | price review
45 | 8368972 | Cp 13/2018 - remodeling and expansion of the stª eufémia de prazins treatment capture system - uv disinfection system | 45252120-5 | Water-treatment plant construction work | FALSE | 2018 | 2022 | Portugal | Guimarães | Braga | 3 | 20 | 07-02-2019 | 15-02-2022 | 1104 | 120 | 400000 | 394896.33 | 2 | 437675.81 | -42779.48 | 90.2258 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extensions | underwork
46 | 8349165 | Contract for Rehabilitation of Buildings in the Municipal Housing Park in the Olival de Fora Municipal District (street Bernardo Santareno) and Other Buildings - Vialonga | 45454100-5 | Restoration work | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 01-09-2020 | 25-05-2022 | 631 | 210 | 122637 | 90837.5 | 1 | 92613.09 | -1775.59 | 98.0828 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
47 | 8292337 | 2021.180.01.C1 - SEFP Portimão - Refurbishment and installation of equipment for the sports center | 45259900-6 | Plant upgrade work | TRUE | 2021 | 2022 | Portugal | Portimão | Faro | 8 | 20 | 01-10-2021 | 26-02-2022 | 148 | 120 | 240000 | 229512.15 | 1 | 217152.49 | 12359.66 | 105.6917 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work and underwork | additional work and underwork
48 | 8240999 | Enlargement and Requalification of Avenida 25 de Abril (Requalification of the Space next to the Alijó Tourist Office) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 15-10-2021 | 02-05-2022 | 199 | 120 | 38500 | 33740 | 1 | 33740 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
49 | 8233321 | Remodeling of the Water Supply and Sanitation Network at street Antero de Quental - Forte da Casa | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 15 | 19-11-2019 | 22-03-2022 | 854 | 120 | 132892 | 108249 | 1 | 108249 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of the technical compilation by the contractor
50 | 8182776 | Improvement of Energy Efficiency in the Municipal Library Bento de Jesus Caraça, Moita | 45331200-8 | Ventilation and air-conditioning installation work | FALSE | 2021 | 2022 | Portugal | Moita | Setúbal | 17 | 24 | 12-10-2021 | 14-07-2022 | 275 | 180 | 203784.68 | 201814.38 | 1 | 214648.92 | -12834.54 | 94.0207 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a 35-day extension of the deadline due to additional work. | additional work, underwork and price revisions
51 | 8179362 | Street layouts in various places in the municipality - (Barreiros) | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 02-11-2021 | 22-07-2022 | 262 | 120 | 63037.22 | 61915.8 | 1 | 61915.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects and delay in the delivery of materials due to the current pandemic situation related to covid-19 | ordinary provisional price review
52 | 8091388 | Renovation of the water supply and sanitation network on street of Juventude (part) in Alverca do Ribatejo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 10-09-2020 | 21-02-2022 | 529 | 120 | 161771.5 | 127777.5 | 1 | 140064.85 | -12287.35 | 91.2274 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: The award will be made on the basis of the lowest price Weighting: 100% Diário da República, 2nd series No. 7404 July 10, 2020 Page 4 | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of the technical compilation by the contractor | approval of complementary works
53 | 8090773 | Refurbishment of the sanitation network on streetAlmirante Gago Coutinho (part) in Povoa de Santa Iria | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 21-07-2020 | 16-03-2022 | 603 | 45 | 66350 | 49329.25 | 1 | 54127.05 | -4797.8 | 91.136 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: The award will be made on the basis of the lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of the technical compilation by the contractor | additional works worth €4,797.80 approved by board of directors resolution of 8/4/2021
54 | 8083478 | Contract 198/gebalis/2021 - public tender - modernization and repair of elevators | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 32 | 12-10-2021 | 26-04-2022 | 196 | 90 | 71500 | 64395.98 | 1 | 64395.98 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | complexity in the execution of work
55 | 8072434 | Contract 80/gebalis/2021 - Liberdade neighborhood and Alcântara valley - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 21-10-2021 | 29-03-2022 | 159 | 90 | 111000 | 76308.5 | 1 | 77098.5 | -790 | 98.9753 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
56 | 8044605 | Contract 51/gebalis/2021 - telheiras north neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 14-10-2021 | 21-02-2022 | 130 | 180 | 250000 | 174000 | 1 | 176970 | -2970 | 98.3217 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
57 | 8035794 | Refurbishment of the sanitation network on street Batista Pereira (part), street gas Moniz and Praça Eça de Queirós in Fort da Casa | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2021 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 29-03-2021 | 25-07-2022 | 483 | 90 | 148844.5 | 118987.52 | 1 | 118987.52 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: The award will be made on the basis of the lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of the final screens by the contractor.
58 | 8027770 | 2019.039.01.C1 - SFP Viana do Castelo - Remodeling and Accessibility | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 15 | 12-07-2021 | 31-01-2022 | 203 | 120 | 110566.79 | 105818.72 | 1 | 103535.16 | 2283.56 | 102.2056 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data | underwork and additional work
59 | 7993184 | Replacement of synthetic turf - Multifunctional Pitches (Soccer Pitch) | 45236119-7 | Repair work on sports fields | FALSE | 2021 | 2022 | Portugal | Lousada | Porto | 13 | 21 | 15-10-2021 | 20-04-2022 | 187 | 90 | 158510 | 149566.6 | 1 | 153086.6 | -3520 | 97.7006 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions | complementary works
60 | 7982303 | Intervention to underpin the foundations of the Austral Quarteira building - Loulé | 45262211-3 | Pile driving | FALSE | 2020 | 2022 | Portugal | Loulé | Faro | 8 | 30 | 17-06-2021 | 04-04-2022 | 291 | 150 | 347716.29 | 337916.58 | 2 | 371320.65 | -33404.07 | 91.004 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in the course of the limitations of the useful height, with different heights throughout the project area, there was a consequent drop in expected yields, namely in the use of mechanical means to carry out the project. the normal progress of the projects was also affected by the problem of the covid 19 pandemic, which induced a decrease in the human resources present at the project and other supplies of materials.
61 | 7981994 | Recovery and maintenance of buildings and municipal sports equipment - Demolition and partial construction of the supporting wall of the Municipal Stadium of Loulé | 45262310-7 | Reinforced-concrete work | FALSE | 2021 | 2022 | Portugal | Loulé | Faro | 8 | 15 | 02-09-2021 | 17-02-2022 | 168 | 90 | 77000 | 72896.68 | 1 | 72896.68 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes in the execution period of the contract.
62 | 7978942 | Santiago elementary School - Rehabilitation of the Multipurpose Area | 45400000-1 | Building completion work | FALSE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 15 | 24-08-2021 | 08-04-2022 | 227 | 63 | 44088 | 42638.23 | 1 | 44979.42 | -2341.19 | 94.795 | Best value for money: No Criterion related to quality name: price Weighting: 100% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | price review- information no. 055/2022be of 03.29.2022
63 | 7967771 | Municipal Dog Park (Sara Moreira Urban Park) | 45112710-5 | Landscaping work for green areas | FALSE | 2021 | 2022 | Portugal | Santo Tirso | Porto | 13 | 14 | 22-09-2021 | 28-03-2022 | 187 | 30 | 55333.85 | 51307.02 | 1 | 58913.42 | -7606.4 | 87.0889 | Best value for money: No Criterion related to quality Name: None Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration of some works foreseen in the project of the project proposed to the competition. | the existence of complementary works during the contract.
64 | 7950846 | Widening of street of Castelinho - Phase 1 | 45233120-6 | Road construction works | FALSE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 30 | 12-10-2021 | 01-07-2022 | 262 | 120 | 100030.39 | 90795.49 | 1 | 98249.38 | -7453.89 | 92.4133 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had 77 days of suspension and 30 days of extension | the project had complementary works in the amount of € 12 309.26 the project had underwork in the amount of € 8 568.00 provisional positive receipt in the amount of € 3 712.63 total contract: € 98,249.39
65 | 7911827 | Repaving contract for a section on Avenida João Bosco Mota Amaral, between Clube Naval and Rotunda de Belém, São Pedro | 45000000-7 | Construction work | FALSE | 2021 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 17 | 08-10-2021 | 22-06-2022 | 257 | 120 | 350000 | 344987.53 | 2 | 341610.95 | 3376.58 | 100.9884 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of term. | underwork and price revision.
66 | 7911581 | Renovation of the Pavilion of the Professor Ribeirinha Machado School (Remodeling of the Window Frames) | 45454000-4 | Restructuring work | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 21 | 20-09-2021 | 04-07-2022 | 287 | 90 | 133947.53 | 131369.08 | 1 | 135320.16 | -3951.08 | 97.0802 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of raw materials to complete the project caused by the current pandemic situation | ordinary price review
67 | 7886394 | Paving of streets in the village of Reigadinha - Pala | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Pinhel | Guarda | 9 | 7 | 22-09-2021 | 22-01-2022 | 122 | 122 | 35250 | 35190 | 1 | 35190 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
68 | 7885880 | CPN 69/2021/DICP- T - 82/2021 Requalification and Improvement of street of Calçada - Raposeira - Colmeias | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Leiria | Leiria | 10 | 18 | 12-08-2021 | 14-02-2022 | 186 | 90 | 230141 | 187906.32 | 1 | 187906.32 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
69 | 7871833 | Ribeira da Levandeira | 45232450-1 | Drainage construction works | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 29-09-2021 | 26-07-2022 | 300 | 150 | 97815.5 | 84542.5 | 1 | 84542.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological conditions not favorable to the execution of the projects and delays in the delivery of materials for the execution of the projects due to the current covid-19 pandemic | ordinary provisional price review
70 | 7870285 | Paving of streets in Fornos | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 27-09-2021 | 18-04-2022 | 203 | 60 | 15872.16 | 14845 | 1 | 14845 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unavailability of labor to carry out paver work and unavailability of markets for supplies of materials necessary for carrying out the project | ordinary price review
71 | 7870106 | Cp 03/2021 - repair of bituminous pavements in the parish of santa eulália - vizela | 45233142-6 | Road-repair works | FALSE | 2021 | 2022 | Portugal | Vizela | Braga | 3 | 14 | 05-07-2021 | 11-01-2022 | 190 | 30 | 110702.75 | 94829.37 | 1 | 94829.37 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
72 | 7866338 | Contract for the remodeling of the sanitary facilities in the central atrium of Building 01 on the Azurém Campus, in Guimarães. (Cp/eop usgci-16/20209) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 14-09-2021 | 17-03-2022 | 184 | 60 | 50000 | 43282.41 | 1 | 38217.22 | 5065.19 | 113.2537 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the time of completion of the contractual work, it was not in a position to be received | articles 2.6, 2.8 and 4.1 were partially executed and articles 2.7, 2.9, 4.2, 5.3.6 and 5.3.7 of the unit price list were not executed.
73 | 7864336 | Bituminous carpet paving in Bairro Novo in Pala. | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Pinhel | Guarda | 9 | 6 | 22-09-2021 | 22-01-2022 | 122 | 122 | 54000 | 53640 | 1 | 53640 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
74 | 7864167 | Paving in bituminous carpet on the branch line between Argomil - Ribeira dos Carinhos - Pomares. | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Pinhel | Guarda | 9 | 14 | 22-09-2021 | 22-01-2022 | 122 | 122 | 64321.25 | 64055 | 1 | 64055 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
75 | 7861028 | Restoration of Pavements and Drainage Organs on Estrada dos 4 Marcos | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Montijo | Setúbal | 17 | 20 | 31-08-2021 | 29-07-2022 | 332 | 180 | 357000 | 286276.17 | 2 | 306293.45 | -20017.28 | 93.4647 | Best value for money: Yes Criterion related to quality Name: most economically advantageous proposal Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of changes to the design of the parking lots, reformulation of the order of materials and delay in their delivery | there was a price revision
76 | 7857699 | Contract contract for the "photovoltaic installation of self-consumption with storage in the warehouses of provisions of the fishing port of Povoa de Varzim" | 45261215-4 | Solar panel roof-covering work | FALSE | 2021 | 2022 | Portugal | Póvoa de Varzim | Porto | 13 | 19 | 09-06-2021 | 23-03-2022 | 287 | 59 | 112000 | 109253.22 | 1 | 109253.22 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A
77 | 7856602 | Contract for the repair and improvement of the roof and façade of cimlt. | 45261900-3 | Roof repair and maintenance work | FALSE | 2021 | 2022 | Portugal | Santarém | Santarém | 16 | 14 | 16-09-2021 | 28-02-2022 | 165 | 60 | 61716.55 | 59588.37 | 1 | 62578.37 | -2990 | 95.222 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological conditions and the need to fill in additional work that could not be detected during the tender phase. | need for sanitation of brick masonry support.
78 | 7843210 | Connecting road between the Urbanization of Arrochela II and crossstreet ofAssento - School of Blacksmiths - Arões S. Romão | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 9 | 16-09-2021 | 30-06-2022 | 287 | 150 | 240177.32 | 203235.62 | 1 | 203235.62 | 0 | 100 | Best value for money: No Criterion related to quality Name: QUALITY Weighting: 0% Criterion related to cost Name: PRICE Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were changes to the contract project | there was complementary work and underwork
79 | 7840345 | Contract for repaving and horizontal signaling of ravine roads, pear cuts, wood, mains, peach trees and heels year 2021 | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Alcoutim | Faro | 8 | 12 | 23-07-2021 | 10-05-2022 | 291 | 30 | 522100.29 | 521157.61 | 2 | 535518.61 | -14361 | 97.3183 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the suspension of work and deadline extensions | due to underwork and definitive price revision.
80 | 7839254 | Cp 42/2020 - Extension of wastewater drainage networks and replacement of water supply networks in the parishes of Caldelas, Pencelo Ponte and UF de Sande Vila Nova and Sande São Clemente | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 20 | 01-03-2021 | 21-07-2022 | 507 | 150 | 390000 | 385738.32 | 2 | 385726.83 | 11.49 | 100.003 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions | underwork
81 | 7838434 | Exterior Arrangement Contract on Av. Amália rodrigues, tires | 45112710-5 | Landscaping work for green areas | FALSE | 2021 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 30-08-2021 | 14-03-2022 | 196 | 60 | 68243.9 | 37777.5 | 1 | 37777.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect subject to competition Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | correct deadline
82 | 7836313 | Construction of infrastructure (rainwater, wastewater and water supply) on a section of street ofs Laginhas, street of Valinhas and Viela do Ribeiro - Vilarinho | 45232452-5 | Drainage works | FALSE | 2021 | 2022 | Portugal | Santo Tirso | Porto | 13 | 14 | 08-09-2021 | 29-04-2022 | 233 | 90 | 89449.95 | 88519.69 | 1 | 103834.84 | -15315.15 | 85.2505 | Best value for money: No Criterion related to quality Name: None Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | definition and execution of complementary work on site. | complementary work and the non-execution of underwork.
83 | 7835958 | Contract for the Decontamination of Soils in the Former Radioactive Mining Areas | 45112340-0 | Soil-decontamination work | TRUE | 2021 | 2022 | Portugal | Nelas | Guarda | 9 | 14 | 01-09-2021 | 14-06-2022 | 286 | 85 | 320000 | 288244 | 2 | 288244.01 | -0.01 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline was not changed, but there was a need to suspend the contract | rounding of € 0.01
84 | 7835128 | Public Tender for the contract for "Improvement Works for the kitchen and dining hall of the elementary School of Abelheira and EB of Lanheses, Children's Park and Playground of the Centro Escolar de Lanheses | 45113000-2 | Siteworks | FALSE | 2021 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 09-09-2021 | 06-01-2022 | 119 | 60 | 411061.15 | 35010.8 | 1 | 35010.8 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delays in the delivery of material due to the existing pandemic state.
85 | 7835116 | Public Tender for the contract for "Improvement Works for the kitchen and dining hall of the elementary School of Abelheira and EB of Lanheses, Children's Park and Playground of the Centro Escolar de Lanheses | 45113000-2 | Siteworks | FALSE | 2021 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 09-09-2021 | 01-06-2022 | 265 | 60 | 411061.15 | 60530.48 | 1 | 60530.48 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | need to suspend work due to unstable weather conditions preventing concreting.
86 | 7833051 | streets in Lebução | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-09-2021 | 05-01-2022 | 117 | 90 | 49160.39 | 48900 | 1 | 50400.16 | -1500.16 | 97.0235 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
87 | 7833012 | Urban arrangements in Ferrugende | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-09-2021 | 13-06-2022 | 276 | 150 | 90198.48 | 89499.35 | 1 | 84779.35 | 4720 | 105.5674 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty in delivering materials to complete work caused by the current covid-19 pandemic situation | there was no need to carry out the planned quantities for certain works since it was not necessary to carry out the entirety
88 | 7830361 | Contract for "Qualification of Public Space - Green Spaces - Arrangement of Vila Jardim Squares and Camélias" | 45112712-9 | Landscaping work for gardens | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 18 | 07-09-2021 | 26-05-2022 | 261 | 90 | 127070.76 | 120188.5 | 1 | 109028.5 | 11160 | 110.2359 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork worth €11,160.00 + vat
89 | 7823020 | Refurbishment of the Outer Space at elementary school da Atalaia | 45236290-9 | Repair work on recreational areas | FALSE | 2021 | 2022 | Portugal | Montijo | Setúbal | 17 | 20 | 07-07-2021 | 04-04-2022 | 271 | 90 | 212578.31 | 179888.67 | 1 | 179888.67 | 0 | 100 | Best value for money: No Quality criteriaDiary of the Republic, 2nd series No. 4572 April 08, 2021 Page 4 Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the contract term | there were no changes in the value of the contract
90 | 7818051 | Cpn 59/2021/dicp - t-59/2021 - requalification of a-do-magro street, Casal Novo and execution of ditches on the street of the rat nest, in Amor | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Leiria | Leiria | 10 | 14 | 23-08-2021 | 22-03-2022 | 211 | 90 | 115462.5 | 112117.5 | 1 | 98493.42 | 13624.08 | 113.8325 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension associated with complementary work (art.º 374.º) and deadline extension under n.º 73/2021. | underwork (art.º 379.º n.º 2) and complementary works (art.º 373.º)
91 | 7817996 | NPD-3021009030-AMN - Contract for Energy Efficiency in the Captaincy of Sines | 45320000-6 | Insulation work | FALSE | 2021 | 2022 | Portugal | Sines | Setúbal | 17 | 14 | 24-08-2021 | 31-01-2022 | 160 | 60 | 60000 | 44444.43 | 1 | 44444.43 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contractor requested a request for an extension of the contractual term, due to alleging difficulties in obtaining labor, proposing a new work plan adjusted for the conclusion of the projects for january 31, 2022 | difficulties in obtaining labor and materials
92 | 7815907 | 2021/139 - DGEP - Replacement of the Guardrails of the Espargal Viaduct, in Paço-de-Arcos. | 45340000-2 | Fencing, railing and safety equipment installation work | FALSE | 2021 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 26-08-2021 | 03-06-2022 | 281 | 45 | 155560 | 153277 | 1 | 164319.1 | -11042.1 | 93.2801 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
93 | 7815876 | Anticipatory work contract for the garridas intergenerational center_x000D_ | 45262310-7 | Reinforced-concrete work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 6 | 12-08-2021 | 08-06-2022 | 300 | 120 | 286066.82 | 285977.14 | 2 | 304944.93 | -18967.79 | 93.7799 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project. | the alteration of the contractual value of the contract was due to the need to issue the complementary work in order to eliminate the errors and omissions of the execution project. the same was duly framed in accordance with the legislation in force
94 | 7814138 | Diversion of the Domestic Wastewater Collector - Quinta do André | 45000000-7 | Construction work | FALSE | 2021 | 2022 | Portugal | Grandola | Setúbal | 17 | 30 | 12-05-2021 | 13-05-2022 | 366 | 90 | 29196.62 | 22871.62 | 1 | 27312.08 | -4440.46 | 83.7418 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | since the location of the project is at rua 22 de junho, which is perpendicularly connected with rua 1.º de maio (bairro da esperança) and that currently there is another work underway on that same street, it was not feasible to begin. | during the project, it was verified that the difference in the connection levels to the manorbox between the collector to be executed and the existing domestic wastewater collector is 6 cm making a deviation.with the dutch dropping, it was verified that the clay soils could not be considered for background due to their characteristics, and it was necessary to use loan land to perform the project.
95 | 7811736 | Construction work on the Sanitation Branch to the Municipal Garden | 45232460-4 | Sanitary works | FALSE | 2021 | 2022 | Portugal | Porto | Porto | 13 | 15 | 25-08-2021 | 30-06-2022 | 309 | 90 | 115000 | 114556.28 | 1 | 114326 | 230.28 | 100.2014 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractual provisions. | works not performed
96 | 7808415 | Repaving of Municipal Road 523, from the intersection of Lagos and Relvas to the boundary of the municipality | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 15 | 18-08-2021 | 30-05-2022 | 285 | 90 | 193515 | 127206 | 1 | 127206 | 0 | 100 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Prices Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
97 | 7807229 | Contract 231/GEBALIS/2020 - Neighborhood Vale de Alcântara / Estrela - Rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 19-08-2021 | 21-01-2022 | 155 | 90 | 102000 | 84630 | 1 | 62820 | 21810 | 134.7182 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
98 | 7806866 | Paving of street Clemente Vercial, Vilar de Nantes | 45432112-2 | Laying of paving | FALSE | 2021 | 2022 | Portugal | Chaves | Vila Real | 19 | 15 | 18-08-2021 | 12-07-2022 | 328 | 60 | 106000 | 102455.7 | 1 | 89660.06 | 12795.64 | 114.2713 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension for 90 days | underwork worth €17,489.94 and definitive price revision, worth €4,694.30
99 | 7806741 | Repaving of EM 516-1 and CM 1316 (street of Outeiro) | 45432110-8 | Floor-laying work | FALSE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 15 | 18-08-2021 | 14-06-2022 | 300 | 90 | 412800 | 310991 | 2 | 338238.87 | -27247.87 | 91.9442 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
100 | 7806265 | Sanitation works in the Municipality - connection of the residual effluent from Argemil and Ribas to Argeriz | 45232460-4 | Sanitary works | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-08-2021 | 25-05-2022 | 278 | 90 | 58368.48 | 58268.48 | 1 | 58268.48 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to lack of weather conditions for carrying out the project, and recommendation to apply the definitive wear layer for a minimum period of 60 days
101 | 7804840 | 2021/93 - DGEP - Reorganization of the parking lot next to street João Alves de Carvalho in Caxias | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Oeiras | Lisboa | 11 | 21 | 12-08-2021 | 28-07-2022 | 350 | 120 | 83761.46 | 67000 | 1 | 100952.97 | -33952.97 | 66.3675 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
102 | 7804294 | Conservation and repair (Cemeteries) - Alijó Cemetery | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 02-08-2021 | 29-08-2022 | 392 | 60 | 48997.15 | 46000 | 1 | 46000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | missing material
103 | 7804228 | Various Paving and Street Layouts - Requalification/Paving - Parish of Alijó | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 02-08-2021 | 10-06-2022 | 312 | 150 | 134370.18 | 126000 | 1 | 126000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of the material by the supplier
104 | 7798733 | Construction of two benches on the football field of Vila Boa do Bispo | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 13-08-2021 | 02-03-2022 | 201 | 91 | 83459.04 | 78018.23 | 1 | 79380.89 | -1362.66 | 98.2834 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended from 01/04/2022 to 02/09/2022 | positive price review
105 | 7797103 | Urban Arrangement of the Largo in Canaveses | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 21 | 16-08-2021 | 08-04-2022 | 235 | 60 | 37951 | 37540 | 1 | 38730.86 | -1190.86 | 96.9253 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays caused by the current covid-19 pandemic situation with regard to locksmith work | ordinary price review
106 | 7794786 | CP 06/2021_DEGA - Expansion of the RDA and RDAR on Avenida Central _IC2_Branca_Albergaria-a-Velha | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2021 | 2022 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 40 | 17-06-2021 | 01-08-2022 | 410 | 90 | 420000 | 319905.63 | 2 | 318627.34 | 1278.29 | 100.4012 | Best value for money: Yes Criterion related to quality Name: VALIA TÉCNICA Weighting: 45% Criterion related to cost Name: PRICE Weighting: 55% | 1 | 55 | 5 | TRUE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
107 | 7794650 | Repaving of Municipal Path 1312 and EM 2011 (Espargueira to Azinhal and Amendoeira). | 45432110-8 | Floor-laying work | TRUE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 14 | 03-08-2021 | 05-07-2022 | 336 | 60 | 162146 | 95754.5 | 1 | 107637.84 | -11883.34 | 88.9599 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
108 | 7792136 | Bituminous paving of the street between Tresmundes and Carvela | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Chaves | Vila Real | 19 | 15 | 29-07-2021 | 31-03-2022 | 245 | 90 | 111495 | 98500 | 1 | 101144.5 | -2644.5 | 97.3854 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | underwork worth €1,848.60 and price revision worth €4,493.10
109 | 7789056 | Cpn 29/2021/dicp - t60/2021 - connection from arnal street (arrabal) to main street - vale Maior - santa catarina da serra | 45233141-9 | Road-maintenance works | FALSE | 2021 | 2022 | Portugal | Leiria | Leiria | 10 | 15 | 21-07-2021 | 24-03-2022 | 246 | 30 | 55775 | 49607 | 1 | 40928 | 8679 | 121.2055 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork (art.º 379.º n.º 2)
110 | 7787051 | Portalegre District Centre_refurbishment works for the WC, rehabilitation of the roof and interior spaces in the Local Service of Crato | 45113000-2 | Siteworks | FALSE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 15 | 04-08-2021 | 07-02-2022 | 187 | 90 | 133030 | 118404.51 | 1 | 118404.51 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without changes
111 | 7785101 | Repaving contract for street of Lucena (lot 1) and street of Valado (lot 2), Santo António | 45233223-8 | Carriageway resurfacing works | FALSE | 2021 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 9 | 29-07-2021 | 20-06-2022 | 326 | 120 | 210000 | 207500 | 1 | 217137.78 | -9637.78 | 95.5614 | Lower price If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | pricing review.
112 | 7783053 | Contract for Requalification and Adaptation of the Composting Center for Green Waste at Ecoparque de Trajouce | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2022 | Portugal | Cascais | Lisboa | 11 | 8 | 16-06-2021 | 04-07-2022 | 383 | 239 | 4550000 | 3525364.14 | 3 | 37781111.94 | -34255747.8 | 9.331 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the period stipulated in the contract. | complementary work resulting from errors in quantities and omissions in the project considered essential to ensure the normal development of the contract works under the appropriate technical conditions and underwork corresponding to a set of works that prove to be unnecessary in view of the concrete circumstances of the project in progress
113 | 7781963 | Contract for requalification of spaces in Building 05 for the Higher School of Nursing on the Gualtar campus of the University of Minho, in Braga. (Cp/eop usgci-02/2021) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Braga | Braga | 3 | 14 | 28-06-2021 | 11-02-2022 | 228 | 60 | 76000 | 68313.23 | 1 | 62061.23 | 6252 | 110.0739 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the time of completion of the contractual work, it was not in a position to be received | underwork on articles 7.7.1.2 and 7.7.1.3 of the unit price list
114 | 7780259 | Repaving of Teófilo Carvalho dos Santos and 1º de Maio streets in Tunes | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 30 | 16-04-2021 | 02-08-2022 | 473 | 60 | 68014 | 53205.92 | 1 | 64066.73 | -10860.81 | 83.0477 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | additional work, price revision, work less
115 | 7779756 | Requalification of the Road Network in the Parishes of Cadima, Tocha and Sanguinheira, by Contract - 2nd Phase - CP-CCP-EMP n.º 11/2021 | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Cantanhede | Coimbra | 6 | 14 | 30-07-2021 | 13-06-2022 | 318 | 180 | 539299.5 | 512827.49 | 2 | 560101.58 | -47274.09 | 91.5597 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
116 | 7778759 | Monstros collection park (Almagreira, Carriço, Louriçal, Mata Mourisca and Pelariga) - Proc. No. 27/2021 | 45222110-3 | Waste disposal site construction work | FALSE | 2021 | 2022 | Portugal | Pombal | Leiria | 10 | 15 | 23-07-2021 | 29-06-2022 | 341 | 120 | 136521.75 | 131481.7 | 1 | 150341.41 | -18859.71 | 87.4554 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project finished within the deadline. | existence of complementary work and value of price revision.
117 | 7778022 | Public Tender for the contract for the execution of sewage and rainwater collectors and branches. | 45232411-6 | Foul-water piping construction work | FALSE | 2021 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 21-07-2021 | 30-03-2022 | 252 | 152 | 40000 | 35395 | 1 | 35395 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
118 | 7777344 | Repaving of CM 1312 (Espargueira to Azinheiro) | 45432110-8 | Floor-laying work | TRUE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 14 | 20-07-2021 | 30-06-2022 | 345 | 60 | 188839 | 188839 | 1 | 137971.71 | 50867.29 | 136.8679 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
119 | 7777171 | Repair of Play and Recreation Spaces in Public Space - Municipality | 45236290-9 | Repair work on recreational areas | FALSE | 2021 | 2022 | Portugal | Loures | Lisboa | 11 | 20 | 21-05-2021 | 02-05-2022 | 346 | 150 | 173500 | 164495 | 1 | 166105 | -1610 | 99.0307 | Best value for money: Yes Criterion related to quality Name: Unweighted Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of complementary work and difficulties arising from covid 19 | execution of additional work and underwork
120 | 7775948 | CP nº 22/2021_DEGA - "Expansion of the RDA and RDAR on street and crossstreet ofs Areias - Ovar" | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2021 | 2022 | Portugal | Ovar | Aveiro | 1 | 40 | 20-07-2021 | 03-08-2022 | 379 | 90 | 95000 | 65813.94 | 1 | 63143.54 | 2670.4 | 104.2291 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | No | TRUE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
121 | 7775045 | Contract for the Improvement and Paving of Several streets in the Municipality of Ponta Delgada | 45233223-8 | Carriageway resurfacing works | FALSE | 2021 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 12 | 26-07-2021 | 19-04-2022 | 267 | 90 | 556000 | 503596.02 | 2 | 516516.84 | -12920.82 | 97.4985 | Lower price PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 119 MONDAY, JUNE 21, 2021 If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | underwork and price revisions.
122 | 7774667 | Remodeling and upgrading of the Luciano Cordeiro elementary school - Removal of asbestos cement from school buildings | 45262660-5 | Asbestos-removal work | FALSE | 2021 | 2022 | Portugal | Mirandela | Bragança | 4 | 21 | 20-07-2021 | 23-05-2022 | 307 | 90 | 185000 | 158594.82 | 1 | 160507.24 | -1912.42 | 98.8085 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the rules imposed by covid-19, the supply of materials is experiencing significant delays, a shortage of metal products, and a limitation on the period for removing fiber cement. | underwork and price revision.
123 | 7774379 | Repaving of Rural Path 4132-1 (Est. From Vida Verde to Outeiro). | 45432110-8 | Floor-laying work | TRUE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 14 | 23-07-2021 | 27-06-2022 | 339 | 60 | 67820 | 42772.5 | 1 | 42772.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
124 | 7774210 | Requalification of the Manhôce Housing Cooperative Sports Complex - Arrifana | 45210000-2 | Building construction work | FALSE | 2021 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 21-07-2021 | 06-01-2022 | 169 | 30 | 20000 | 19854.5 | 1 | 19254.5 | 600 | 103.1162 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 9 days in the inspection appointment for the provisional rectification | underwork
125 | 7773843 | Adaptation of school buildings to support nature sports | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2021 | 2022 | Portugal | Amarante | Porto | 13 | 8 | 16-07-2021 | 15-06-2022 | 334 | 180 | 390500 | 62191.54 | 1 | 65165.37 | -2973.83 | 95.4365 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | delay in inspection for provisional acceptance | price review
126 | 7773239 | EP-2021(5001)/10002 Improvement of the Sheltering House Santa Isabel Pre-Autonomy Project | 45113000-2 | Siteworks | TRUE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 15 | 23-07-2021 | 18-01-2022 | 179 | 120 | 200000 | 199405.14 | 1 | 199405.14 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 70% Criterion related to cost Name: Technical Value of the Proposal Weighting: 30% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of complementary work | no change
127 | 7773037 | Contract "Minho Line - Superstructure rehabilitation of track between km 5,050 and 7,750 VA". Desco 10005341 | 45234100-7 | Railway construction works | FALSE | 2021 | 2022 | Portugal | Maia | Porto | 13 | 11 | 06-07-2021 | 06-04-2022 | 274 | 150 | 950000 | 938781.75 | 2 | 938781.75 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
128 | 7772913 | Street layouts in various places in the municipality - (Valpaços and Valverde) | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 15-07-2021 | 19-01-2022 | 188 | 90 | 50671.21 | 50670 | 1 | 52028.16 | -1358.16 | 97.3896 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unavailability of equipment and materials for completing walkways, namely granite guides and concrete floor stone | non-execution of stop bars in thermoplastic paint
129 | 7771035 | Requalification of the Public Space of Veiros - Largo 25 de Abril | 45112700-2 | Landscaping work | FALSE | 2021 | 2022 | Portugal | Estremoz | Évora | 7 | 15 | 22-07-2021 | 13-04-2022 | 265 | 90 | 365437.74 | 365430 | 2 | 361120.05 | 4309.95 | 101.1935 | Best value for money: Yes Criterion related to quality Name: Technical Value and Deadline (20% and 30% respectively) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work and underwork. | additional work and underwork.
130 | 7770620 | Different Schools - School of Fijós - Sobrado | 45262650-2 | Cladding works | FALSE | 2021 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 20-07-2021 | 20-05-2022 | 304 | 70 | 170000 | 138488.77 | 1 | 161388.8 | -22900.03 | 85.8106 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the execution period - 31 days - 1st addendum to the initial contract on 12.15.2021 allocation of 15 days to carry out the complementary work (1st additional contract of 12.15.2021) | approval of complementary work - €15,902.26 - additional contract approval of the provisional calculation of the price revision - €6,997.77
131 | 7769606 | Recovery of traditional buildings for country houses | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 10 | 23-03-2020 | 29-04-2022 | 767 | 240 | 250061.52 | 244514.07 | 1 | 244514.07 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
132 | 7768885 | Lot 1-Paving and Roads - Requalification/Paving -street of Calvário in Sanfins do Douro; lot 2- Conservation and Requalification of the N323 Road between N15 and N323-1 (Vilar de Maçada Ferry) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 12-07-2021 | 07-02-2022 | 210 | 120 | 439845 | 80425 | 1 | 80425 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
133 | 7768874 | Lot 1-Paving and Roads - Requalification/Paving -street of Calvário in Sanfins do Douro; lot 2- Conservation and Requalification of the N323 Road between N15 and N323-1 (Vilar de Maçada Ferry) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 12-07-2021 | 07-02-2022 | 210 | 120 | 439845 | 80391 | 1 | 80391 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
134 | 7768865 | Lot 1-Paving and Roads - Requalification/Paving -street of Calvário in Sanfins do Douro; lot 2- Conservation and Requalification of the N323 Road between N15 and N323-1 (Vilar de Maçada Ferry) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 12-07-2021 | 07-02-2022 | 210 | 120 | 439845 | 208397.5 | 1 | 228001.25 | -19603.75 | 91.4019 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | support wall to the road that felled and paving
135 | 7768841 | Lot 1-Paving and Roads - Requalification/Paving -street of Calvário in Sanfins do Douro; lot 2- Conservation and Requalification of the N323 Road between N15 and N323-1 (Vilar de Maçada Ferry) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 12-07-2021 | 07-02-2022 | 210 | 60 | 439845 | 31289.5 | 1 | 31289.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
136 | 7766864 | Rectification and Paving of street of Cerdeirinhas (Regadas) and Paving of the Loteamento do Passal (S. Gens), street of Cimo de Vila (Golães) and crossstreet of Bairro de Antime | 45233140-2 | Roadworks | FALSE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 9 | 19-07-2021 | 21-04-2022 | 276 | 90 | 197386.2 | 190554.2 | 1 | 175421.2 | 15133 | 108.6267 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was an extension of the contract period. | not all quantities were executed for some items.
137 | 7763620 | Paving and streets - Requalification/Paving - street of Cemitério in Cheires | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 12-07-2021 | 13-01-2022 | 185 | 120 | 61808 | 61000 | 1 | 61000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
138 | 7761938 | 2020.011.01.C1 - SFP de Chaves - Replacement of HVAC and AQS system | 45331000-6 | Heating, ventilation and air-conditioning installation work | TRUE | 2021 | 2022 | Portugal | Chaves | Vila Real | 19 | 25 | 13-05-2021 | 30-05-2022 | 382 | 210 | 400000 | 311441.23 | 2 | 357783.21 | -46341.98 | 87.0475 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data | complementary work, underwork and price revision
139 | 7760515 | Connection of the Esperança Distribution Network to the Lugar do Marco Reservoir/Extension of the Water Supply Pipeline to Várzea Grande (Marco)" | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Arronches | Portalegre | 12 | 30 | 26-04-2021 | 21-02-2022 | 301 | 150 | 160503.37 | 154247.37 | 1 | 154147.37 | 100 | 100.0649 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was verified the need for additional clarifications by the designer, for the proper execution of the electrical part of the pumping station | it was found that there was an article that was in duplicate
140 | 7760128 | Pavement rehabilitation of the EN 238, between Sertã and Faleiros | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Sertã | Castelo Branco | 5 | 15 | 07-07-2021 | 04-03-2022 | 240 | 60 | 406500 | 308262.26 | 2 | 317715.43 | -9453.17 | 97.0246 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the stipulated time frame. | change in the value of the project due to price revision
141 | 7760066 | Repaving of CM 1321 (Estrada do Guelhim) | 45432110-8 | Floor-laying work | TRUE | 2021 | 2022 | Portugal | Faro | Faro | 8 | 14 | 09-07-2021 | 07-07-2022 | 363 | 60 | 93848.5 | 60924.6 | 1 | 66565 | -5640.4 | 91.5265 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
142 | 7759085 | 2017.070.04.C1 - Viseu Training Services - Replacement of the HVAC system and the water network | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 20 | 24-05-2021 | 28-02-2022 | 280 | 200 | 605000 | 557592.6 | 2 | 563925.04 | -6332.44 | 98.8771 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work | additional work
143 | 7758096 | 5-Emp/20 - Contract for the conservation and improvement of the municipality's road network - Municipal Roads in the Parish of Santa Catarina da Fonte do Bispo | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 08-07-2021 | 06-07-2022 | 363 | 150 | 414672.73 | 392610.15 | 2 | 438015.95 | -45405.8 | 89.6338 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of deadline and delivery of the technical compilation of the contract | complementary works worth €9,597.98 and definitive price review worth €35,807.82 (positive).
144 | 7757953 | Repair works in the school building and exterior arrangements - E. B. 1st cycle of Vale S. Martinho | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2021 | 2022 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 23-06-2021 | 03-01-2022 | 194 | 75 | 134032.3 | 128476 | 1 | 128476 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work for a period of 100 days.
145 | 7757617 | Contract nº 66/2020 - Monte da Galega Sports Park - Requalification of the Track | 45236119-7 | Repair work on sports fields | FALSE | 2021 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 12-07-2021 | 08-04-2022 | 270 | 180 | 169808.5 | 169054.89 | 1 | 169054.89 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - as a result of the covid19 pandemic, there were delays in the delivery of materials, difficulties in transport and in the delivery of raw materials. - as a result of the pandemic, there was still a lack of labour, difficulties in hiring workers, aggravated by the fact that many workers (including the construction management) were forced to isolate themselves, as they had contracted covid 19.
146 | 7757553 | PRC_0119/2021_GAE - AR0663 - FSC installation contract in Canedo and execution of Box-Culvert to cross the water line (Celorico de Basto) | 45232400-6 | Sewer construction work | TRUE | 2021 | 2022 | Portugal | Celorico de Basto | Braga | 3 | 21 | 25-06-2021 | 26-07-2022 | 396 | 180 | 170000 | 168874.04 | 1 | 179891.16 | -11017.12 | 93.8757 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | delays in completing work due to shortages of raw materials and lack of labor | excess related to price revision
147 | 7757315 | Moinho da Palmeira Road Requalification – Faro Urban Cycle Path | 45233252-0 | Surface work for streets | TRUE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 20 | 09-07-2021 | 31-05-2022 | 326 | 120 | 381416.5 | 337970 | 2 | 337970 | 0 | 100 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
148 | 7753211 | Campo de Ourique Pavilion - Demolition Contract | 45262310-7 | Reinforced-concrete work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 6 | 09-07-2021 | 05-04-2022 | 270 | 100 | 435000 | 307500 | 2 | 341705.08 | -34205.08 | 89.9899 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the project took place during the pandemic period caused by covid-19. | "the change in the contractual value of the contract was due to the need to issue additional works in order to overcome an undetectable omission in the contract formation phase, with the detection occurring within a period of 60 days after the assignment of the contract, in accordance with paragraph 4 of art.378a, with the value of the projects related to the supply of omissions being the responsibility of the client. they were duly framed in accordance with the legislation in force and submitted to the court of auditors for appreciation."
149 | 7752280 | Urban Arrangements in Rio Torto | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 21 | 09-07-2021 | 11-04-2022 | 276 | 90 | 64021.48 | 62643.5 | 1 | 53696.52 | 8946.98 | 116.6621 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of raw material on the market to carry out the project | it was not necessary to carry out all the project
150 | 7752104 | Proximity works 2021 - hub paving - lot 1 and 4 | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 06-07-2021 | 08-04-2022 | 276 | 180 | 318759.75 | 159744.53 | 1 | 151318.6 | 8425.93 | 105.5683 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension | underwork, price review.
151 | 7750721 | Minho Line - PK 67.234 to 68.437 - Renewal of the track platform of Line I at Barroselas Station | 45234100-7 | Railway construction works | FALSE | 2021 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 17 | 06-07-2021 | 02-05-2022 | 300 | 90 | 450000 | 411910.6 | 2 | 411206.6 | 704 | 100.1712 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
152 | 7750250 | Contract No. 9/2021 - elementary school Alfragide - Execution of Conservation and Improvement Works | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 05-07-2021 | 14-03-2022 | 252 | 90 | 338161.55 | 304345.41 | 2 | 268420.13 | 35925.28 | 113.384 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in the movement of equipment and in the delivery of the necessary materials for the intervention of the external walls and railing. | due to the provisional price revision in the amount of €10,207.41 and underworks in the amount of €46,132.69
153 | 7747639 | Contract for Public Works for the Maintenance and Occasional Repairs of Sidewalks and Paves in the Municipality of Cascais | 45233253-7 | Surface work for footpaths | FALSE | 2021 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 05-07-2021 | 27-05-2022 | 326 | 365 | 426811.1 | 168080 | 1 | 168080 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect subject to competition Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the work finished ahead of schedule
154 | 7746622 | Improvement and Conservation of other Basic Education Buildings (CE da Redinha) - Proc. No. 21/2021 | 45454100-5 | Restoration work | FALSE | 2021 | 2022 | Portugal | Pombal | Leiria | 10 | 18 | 28-06-2021 | 21-03-2022 | 266 | 75 | 149991 | 131661.84 | 1 | 141597.28 | -9935.44 | 92.9833 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the initial deadline for the project ended on september 25, 2021, however, for the execution of the complementary works, another 4 days were granted until september 29, 2021 since it was the delivery date of the waste plan for the project. | existence of complementary work and value of price revision.
155 | 7744814 | Contract 377/gebalis/2020 - rehabilitation of municipal buildings - parish marvila - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 26 | 28-06-2021 | 30-03-2022 | 275 | 60 | 471000 | 61282.32 | 1 | 61282.32 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 30 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
156 | 7744775 | Contract 377/gebalis/2020 - rehabilitation of municipal buildings - parish marvila - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 26 | 28-06-2021 | 10-01-2022 | 196 | 90 | 471000 | 77867.03 | 1 | 58310.97 | 19556.06 | 133.5375 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 30 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
157 | 7743921 | Contract No. 8/2021 - elementary school Alice Vieira - Work Execution | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 30-06-2021 | 12-05-2022 | 316 | 120 | 320750.72 | 288675.66 | 2 | 305604.65 | -16928.99 | 94.4605 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the contractual term. the deviation of less than 12 days is due to the speed with which the contractor complied with all procedural situations, namely the delivery of the waste management plan at work, which allowed to speed up the respective provisional acceptance. | due to the 1st provisional price review - €11,411.64; 2nd provisional price revision - €5,517.35.
158 | 7739914 | Contract 378/gebalis/2020 - rehabilitation of municipal housing - parishes areeiro / beato / penha frança / s. Vicente - Lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 22 | 29-06-2021 | 15-02-2022 | 231 | 60 | 366000 | 57153.34 | 1 | 57153.34 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 24 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
159 | 7739361 | Execution of the Work to Increase the Capacity of the Tuning Line of the Anaerobic Digestion Center (CDA) | 45220000-5 | Engineering works and construction works | FALSE | 2020 | 2022 | Portugal | Mafra | Lisboa | 11 | 30 | 16-03-2021 | 08-06-2022 | 449 | 120 | 380000 | 332286.72 | 2 | 369856.89 | -37570.17 | 89.842 | Best value for money: Yes Criterion related to quality Name: Contract deadline Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulties in mobilizing qualified teams to carry out disassembly and assembly work on electromechanical equipment, due to constraints caused by the covid-19 pandemic | increase in the price of materials to be used as well as an increase in the price of labor
160 | 7737885 | AA and AR Network - Small Extensions 2021 - 2nd Phase | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2021 | 2022 | Portugal | N/A | N/A | N/A | 40 | 28-06-2021 | 06-06-2022 | 343 | 730 | 245000 | 226229.65 | 1 | 225023.43 | 1206.22 | 100.536 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: PRICE Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
161 | 7737808 | EP-2021(5001)/10001 Replacement of windows and blinds in Central Services | 45421132-8 | Installation of windows | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 14 | 22-06-2021 | 21-01-2022 | 213 | 120 | 90000 | 73444.61 | 1 | 73444.61 | 0 | 100 | Best value for money: No Criterion related to quality Name: (Does not have) Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
162 | 7732343 | Contract 288/gebalis/2020 - county district / flamenco / quinta das laranjeiras / - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 20 | 23-06-2021 | 02-02-2022 | 224 | 90 | 165000 | 108251 | 1 | 108251 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
163 | 7729922 | Viseu District Center - Replacement of Elevators E19816 and Deep Refurbishment of Elevators E19817 and E19818 in the headquarters building | 45113000-2 | Siteworks | FALSE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 30 | 21-05-2021 | 01-02-2022 | 256 | 90 | 184500 | 168050 | 1 | 168050 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the covid-19 epidemic is an unpredictable event, with the shortage of labor available on the market, in the face of disease outbreaks and mandatory confinements, the difficulty in the delivery of equipment by suppliers, due to serious shortages in supply. of electronic components and raw material for the manufacture of such equipment, as well as the difficulty in international transport, affected the fulfillment of the provision in question and created a true objective impossibility of meeting the deadline for the contract initially contracted, which directly affected the projectforce , as well as the supply of essential equipment for the completion of the contract.
164 | 7726172 | Requalification of the banks of the Ribeira de Santa Apolónia, execution of draining bituminous concrete sidewalks, demolition and reconstruction of the pontoon, construction of walls, plantations | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Coimbra | Coimbra | 6 | 33 | 24-03-2021 | 30-03-2022 | 371 | 150 | 207050 | 204947.55 | 1 | 221059.95 | -16112.4 | 92.7113 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work without deadline extension | value related to price review
165 | 7722745 | Requalification of the Auditorium Multisport - Santa Maria de Lamas | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2021 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 15-06-2021 | 06-01-2022 | 205 | 30 | 44000.15 | 42601.5 | 1 | 42601.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 15 days grace period extension 7 days when booking inspection for provisional acceptance
166 | 7721857 | Contract No. 5/2021 - elementary school Venteira - Implementation of Improvement Works | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Amadora | Lisboa | 11 | 21 | 17-06-2021 | 26-05-2022 | 343 | 120 | 559851.77 | 503866.61 | 2 | 536489.98 | -32623.37 | 93.9191 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within its contractual term. the deviation from the execution deadline is exclusively due to the delay in the delivery of the waste management plan on site. | due to the 1st provisional price review - €22,674.50; 2nd provisional price revision - €9,948.87
167 | 7720799 | Contract 385/gebalis/2020 - boavista neighborhood / good pastor - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 18 | 16-06-2021 | 04-02-2022 | 233 | 90 | 97000 | 66157 | 1 | 66157 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
168 | 7720569 | Sports and Leisure Equipment next to the Olaia School Center | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2021 | 2022 | Portugal | Torres Novas | Santarém | 16 | 20 | 25-05-2021 | 05-07-2022 | 406 | 180 | 273781.85 | 272046.22 | 2 | 310577.73 | -38531.51 | 87.5936 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or Cost Evaluation Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | additional work and underwork
169 | 7717629 | CP 44 /2020_DEGA - Rehabilitation of the Carregal Reserve System – Ovar | 45259000-7 | Repair and maintenance of plant | TRUE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 40 | 28-05-2021 | 28-03-2022 | 304 | 150 | 150000 | 148000 | 1 | 148000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: VALIA TÉCNICA Weighting: 45% Criterion related to cost Name: PRICE Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
170 | 7714281 | Urban Arrangement of Largo das Festas in Argeriz | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 21 | 09-06-2021 | 21-04-2022 | 316 | 120 | 142467.5 | 142347.5 | 1 | 150509.63 | -8162.13 | 94.577 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of materials and lack of labour to carry out the project, caused by the current covid-19 pandemic situation | ordinary price review
171 | 7702978 | Paving of municipal road 1159 – silves | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 30 | 24-05-2021 | 26-05-2022 | 367 | 60 | 197840 | 196900.38 | 1 | 231145.3 | -34244.92 | 85.1847 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to describe | price review
172 | 7697475 | Paving of the path connecting Ponte Velha and EM 528 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 30 | 26-03-2021 | 25-05-2022 | 425 | 30 | 64130 | 63946.88 | 1 | 73391.77 | -9444.89 | 87.1309 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | price review and adjustment of 0.01€
173 | 7693882 | Recovery and Improvement of the Mother Church of Aljustrel | 45261900-3 | Roof repair and maintenance work | FALSE | 2021 | 2022 | Portugal | Aljustrel | Beja | 2 | 9 | 02-06-2021 | 08-06-2022 | 371 | 150 | 198860.87 | 169850.85 | 1 | 179110.71 | -9259.86 | 94.8301 | Best value for money: No Criterion related to quality Name: - Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse atmospheric conditions to the execution of the projects | final calculation of the price revision
174 | 7693070 | Beira Baixa Line - Contract for Anticorrosive Protection of Metallic Bridges, Phase 3 (Desco 10002920) | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2020 | 2022 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 29 | 26-05-2021 | 22-07-2022 | 422 | 210 | 900000 | 784997.75 | 2 | 832858.46 | -47860.71 | 94.2534 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Diário da República, 2nd series No. 11874 October 22, 2020 Page 4 Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation of 91 days in the execution period
175 | 7690730 | Contract 70/gebalis/2021 - shipowner neighborhood - rehabilitation works in common areas with roof replacement | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 31-05-2021 | 06-05-2022 | 340 | 180 | 330000 | 286470 | 2 | 275428.23 | 11041.77 | 104.0089 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complexity in the execution of work
176 | 7689919 | Preservation of Municipal Roads | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Mértola | Beja | 2 | 18 | 25-05-2021 | 16-03-2022 | 295 | 90 | 362850 | 287106.45 | 2 | 283926.46 | 3179.99 | 101.12 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by price assessment. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | underwork
177 | 7689560 | Requalification of the Road Network in the Parish of Febres, by Contract - 2nd Phase - CP-CCP-EMP n.º 06/2021 | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Cantanhede | Coimbra | 6 | 14 | 31-05-2021 | 04-05-2022 | 338 | 120 | 381496.76 | 350287.17 | 2 | 334422.73 | 15864.44 | 104.7438 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works and underwork.
178 | 7685979 | Linha do minho - stripping and replacement of tbb pk 96,245 to 97,200 | 45234100-7 | Railway construction works | FALSE | 2021 | 2022 | Portugal | Caminha | Viana do Castelo | 18 | 15 | 28-05-2021 | 05-04-2022 | 312 | 90 | 430000 | 422280 | 2 | 403681.43 | 18598.57 | 104.6072 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price: Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | nothing to register
179 | 7682608 | Roof Renovation - Aljustrel High school | 45261210-9 | Roof-covering work | FALSE | 2020 | 2022 | Portugal | Aljustrel | Beja | 2 | 156 | 25-05-2021 | 23-05-2022 | 363 | 90 | 166330.91 | 144334.58 | 1 | 152870.72 | -8536.14 | 94.4161 | Best value for money: No Criterion related to quality Name: - Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | the final calculation of the price revision
180 | 7680727 | Water supply network to S. Domingos e Bouça - Parish of Vila Boa do Bispo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 25-05-2021 | 21-04-2022 | 331 | 150 | 109638.5 | 103550 | 1 | 120113.64 | -16563.64 | 86.21 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time. | definitive, positive price revision in the amount of 9,764.76
181 | 7679241 | Renovation of Municipal Road 1119 - Rio de Moinhos | 45233142-6 | Road-repair works | FALSE | 2021 | 2022 | Portugal | Alcácer do Sal | Setúbal | 17 | 30 | 21-05-2021 | 10-02-2022 | 265 | 60 | 236000 | 206984.33 | 1 | 236357.75 | -29373.42 | 87.5725 | Best value for money: Yes Criterion related to quality Name: Value and feasibility of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | price revision calculations were carried out in january and february/2022, with the respective final account being drawn up on 02/10/2022 and accepted by the contractor through official letter, received on 03/11/2022. | addition - due to complementary work and final price review.
182 | 7678907 | Contract 382/gebalis/2020 - rehabilitation and conservation works at Quinta do Cabrinha | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 4 | 24-05-2021 | 25-03-2022 | 305 | 180 | 176428.4 | 171196.65 | 1 | 174166.65 | -2970 | 98.2947 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | complexity in the execution of work
183 | 7678727 | Construction of sidewalks - street Professor Mota e Costa - Eiró | 45233253-7 | Surface work for footpaths | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 17-05-2021 | 30-03-2022 | 317 | 60 | 49546.05 | 45895.93 | 1 | 48758.41 | -2862.48 | 94.1293 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended for 7 days and suspended for 180 days | the project involved complementary works worth €575.00 and a positive provisional price review worth €2,287.48.
184 | 7676503 | Hot bituminous concrete paving of various roads in the Municipality, including the replacement of horizontal signage and, occasionally, the execution of drainage and correction of sidewalks. | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Coimbra | Coimbra | 6 | 15 | 28-04-2021 | 22-03-2022 | 328 | 120 | 447733 | 379643.21 | 2 | 437456.97 | -57813.76 | 86.7841 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work without deadline extension | value related to price revision
185 | 7675344 | Proximity works 2021 - hub paving | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 14-05-2021 | 16-05-2022 | 367 | 180 | 666339.75 | 177153.48 | 1 | 160050.38 | 17103.1 | 110.6861 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension | underwork, price review
186 | 7675315 | Proximity works 2021 - hub paving | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 14-05-2021 | 14-02-2022 | 276 | 180 | 666339.75 | 198218.5 | 1 | 196956.77 | 1261.73 | 100.6406 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was completed on time. | underwork, price review
187 | 7675172 | streets in Vilarandelo | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 18 | 12-05-2021 | 24-01-2022 | 257 | 180 | 185026.99 | 174000 | 1 | 183897.81 | -9897.81 | 94.6178 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | forwarding of rainwater and surface water in a granite cube saving half pipes
188 | 7673136 | Contract for the "Tamar Branch - between PK 8.730 and PK 9.985 - Replacement of TM/TBB and changeover from BC to BLS - Phase 4" (Process no. 10004445) | 45234100-7 | Railway construction works | FALSE | 2020 | 2022 | Portugal | Tomar | Santarém | 16 | 25 | 04-05-2021 | 07-04-2022 | 338 | 120 | 800000 | 715000 | 2 | 674032.2 | 40967.8 | 106.078 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
189 | 7672752 | PRC 0192/2020_GAE - AA0581-Contract work for paving municipal roads affected by the installation of water supply infrastructure. | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Vieira do Minho | Braga | 3 | 21 | 06-05-2021 | 21-01-2022 | 260 | 14 | 260000 | 196985 | 1 | 220392.73 | -23407.73 | 89.3791 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the term for execution of the contract was not changed, with the successful tenderer complied with the contractual provisions within the period stipulated in the contract | value with price revision
190 | 7668766 | "Túnel do Marão: Installation of a reactor system at each electrical energy input_x000D_" Desco nº 10002642 | 45310000-3 | Electrical installation work | FALSE | 2021 | 2022 | Portugal | Vila Real | Porto | 13 | 17 | 18-05-2021 | 15-02-2022 | 273 | 120 | 25500 | 19587.5 | 1 | 21161.41 | -1573.91 | 92.5624 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Diário da República, 2nd series No. 2904 March 5, 2021 Page 4 Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
191 | 7664188 | The work includes the execution of AP, ARD, AA, ITUR and IP networks. Construction of sidewalks and parking bays and paving of streets in bituminous concrete | 45233251-3 | Resurfacing works | FALSE | 2021 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 11-05-2021 | 16-07-2022 | 431 | 180 | 450000 | 367400 | 2 | 402950.22 | -35550.22 | 91.1775 | Best value for money: Yes Criterion related to quality name: quality Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline. | approval of price revision (provisional and definitive calculation) approval of underwork
192 | 7663903 | Refurbishment contract for Beco de Santana, Chapels (Lot 1) and construction of a car park in the drawer on streetProfessor Manuel Moniz Morgado and the Regional Road, Fenais da Luz (Lot 2) | 45233220-7 | Surface work for roads | FALSE | 2021 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 11 | 12-05-2021 | 31-03-2022 | 323 | 120 | 156500 | 152855.36 | 1 | 155629.06 | -2773.7 | 98.2177 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | underwork and price revisions
193 | 7661891 | Cpn 03/2021/dicp - t-122/2020 - reformulation of the rain collector in the street of the initiative commission - leiria | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Leiria | Leiria | 10 | 21 | 26-03-2021 | 17-02-2022 | 328 | 70 | 36000 | 35500 | 1 | 33012.7 | 2487.3 | 107.5344 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork (art.º 379.º n.º 2)
194 | 7658025 | EP-2021(5001)/10000 Rehabilitation of the 2nd and 3rd cycle buildings | 45113000-2 | Siteworks | TRUE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 16 | 13-05-2021 | 13-01-2022 | 245 | 120 | 260000 | 227314 | 1 | 227314 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 30% | 1 | 30 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
195 | 7654884 | Contract work for earthmoving and drainage systems | 45112500-0 | Earthmoving work | FALSE | 2021 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 11-05-2021 | 28-03-2022 | 321 | 365 | 608971.23 | 418000 | 2 | 418000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project finished ahead of schedule
196 | 7654315 | Contract 416/gebalis/2020 - rehabilitation and conservation works in the 2 de Maio neighborhood | 45453100-8 | Refurbishment work | FALSE | 2021 | 2022 | Portugal | Lisboa | Lisboa | 11 | 14 | 10-05-2021 | 25-02-2022 | 291 | 120 | 202060 | 150000 | 1 | 123264.98 | 26735.02 | 121.6891 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complexity in the execution of the project and adverse weather conditions during the course of the project
197 | 7652574 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro Elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 02-02-2022 | 292 | 90 | 1733000 | 165700 | 1 | 183121.53 | -17421.53 | 90.4864 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
198 | 7652530 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro Elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 02-02-2022 | 292 | 90 | 1733000 | 79700 | 1 | 79700 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
199 | 7652106 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro Elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 27-06-2022 | 437 | 90 | 1733000 | 208640 | 1 | 223561.16 | -14921.16 | 93.3257 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
200 | 7651837 | Cpn 9/2021/dicp - t - 20/21 - rehabilitation and improvement of street of Pinhal - Ponte da Pedra - Regueira de Pontes | 45233141-9 | Road-maintenance works | FALSE | 2021 | 2022 | Portugal | Leiria | Leiria | 10 | 15 | 09-04-2021 | 22-03-2022 | 347 | 60 | 176265 | 175507.7 | 1 | 251807.13 | -76299.43 | 69.6993 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (by the owner of the project) due to the need to study changes to the project (art. 365, paragraph b) | underwork (art.º 379.º n.º 2) and complementary works (art.º 373.º)
201 | 7647771 | street of Eira / Cimo da Fonte, Vila Chã - Requalification / Execution | 45231000-5 | Construction work for pipelines, communication and power lines | FALSE | 2021 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 05-05-2021 | 07-04-2022 | 337 | 180 | 182156.9 | 181980.5 | 1 | 209047.5 | -27067 | 87.0522 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | “lack of material to complete the project. this fact is due to the high demand in the market for raw materials, which led to a shortage of various products, one of which is granite, which, in addition to the strong demand at a national level, also has high exports.” | 1 - sanitation network with the development of the project, it was identified that during the contract, three houses were left without connection to the public wastewater drainage network, these three houses have septic tanks. 2 - water supply network with the development of the project, it was identified that during the contract the pipe of the water supply network is made of fiber cement and is in an advanced state of degradation, this type of material results in risks to public health. 1 - drainage of rainwater with the development of the projects, it was identified that during the contract with the vila chã day center it is necessary to drain the rainwater since there will be water infiltrations both from the day center and in an existing building there.
202 | 7644798 | PRC_0359/2020_GAE-EB0599 - Repaving of E.M. 754, And urban wastewater supply and sanitation in E.M. 754 (Vila Chã do Marão) and at E.M. 750 (Frydon) | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Amarante | Porto | 13 | 30 | 01-04-2021 | 28-03-2022 | 361 | 210 | 1261200 | 580720.54 | 2 | 609514.06 | -28793.52 | 95.276 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty in hiring labor and delays in the delivery of materials. | some sections of the water supply pipeline and wastewater drainage network, provided for in this project, had already been executed as part of another contract.
203 | 7644469 | Conservation and Rehabilitation of Municipal Buildings-Maintenance and Rehabilitation of Town Hall Buildings-General Maintenance Works and Rehabilitation of Window Frames | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Loulé | Faro | 8 | 15 | 22-07-2020 | 23-05-2022 | 670 | 180 | 186000 | 140283.2 | 1 | 140283.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of materials
204 | 7642429 | Public tender for awarding the contract for "Removal of asbestos cement in school buildings" | 45262660-5 | Asbestos-removal work | TRUE | 2020 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 29-04-2021 | 11-04-2022 | 347 | 120 | 749681 | 598091.5 | 2 | 598091.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 measures
205 | 7640570 | Wastewater drainage network in Lagarelha - parish of Vila Boa de Quires and Maureles | 45232460-4 | Sanitary works | FALSE | 2021 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 29-04-2021 | 16-05-2022 | 382 | 120 | 178933.12 | 173375.44 | 1 | 188381.38 | -15005.94 | 92.0343 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work | price review
206 | 7640158 | Lifting of bituminous carpet and guides, execution of infrastructure, supply and placement of concrete, granite curbs and replacement of pavement | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 28-04-2021 | 01-04-2022 | 338 | 90 | 138000 | 120427.15 | 1 | 118670.33 | 1756.82 | 101.4804 | Best value for money: Yes Criterion related to quality Name: technical value 30% + deadline 10% Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the deadline for carrying out the project. the project was completed on 15.09.2021, it was only awaiting the delivery of the necessary documentation for the preparation of the final report. it should also be mentioned some delay in scheduling the inspection for the purposes of provisional acceptance. | approval of underwork - €9,256.99 price revision approval (provisional + final) - €7,500.18
207 | 7631431 | CP 018/2021 - Construction contract for the parking lot for towed vehicles II | 45233200-1 | Various surface works | TRUE | 2021 | 2022 | Portugal | Portimão | Faro | 8 | 30 | 26-04-2021 | 21-03-2022 | 329 | 70 | 75000 | 65500 | 1 | 68119.99 | -2619.99 | 96.1539 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the initial deadline for the contract was 70 days, stipulated in the ec, having been complied with, the provisional reception was on 08/13/2022. | the price fixed in the contract for the execution of the project is mandatorily revised under the contractually established terms and in accordance with the provisions of the law.
208 | 7630732 | Implementation of lighting and electrical installation projects in Funchal Cathedral | 45310000-3 | Electrical installation work | FALSE | 2020 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 12 | 11-03-2021 | 11-02-2022 | 337 | 240 | 215000 | 185152.71 | 1 | 185152.71 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
209 | 7627369 | Contract for "Bituminous Paving of the streets between Sanjurge and Soutelo, between Bobadela and Vilar de Izeu and between Sesmil and R314" | 45233142-6 | Road-repair works | FALSE | 2021 | 2022 | Portugal | Chaves | Vila Real | 19 | 24 | 23-04-2021 | 17-01-2022 | 269 | 120 | 367922.45 | 336000 | 2 | 330429.2 | 5570.8 | 101.6859 | Best value for money: No Criterion related to quality name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% Diário da República, 2nd series No. 2269 February 23, 2021 Page 4 | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | works not done.
210 | 7627083 | Demolition of screed sidewalks, lifting of bituminous carpet and guides, execution of infrastructure, supply and placement of concrete, curbs and granite brick, bituminous carpet, signage | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Valongo | Porto | 13 | 22 | 20-04-2021 | 08-03-2022 | 322 | 100 | 240000 | 226917.89 | 1 | 244084.41 | -17166.52 | 92.967 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal 30% + deadline 10% Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allocation of 20 days for carrying out the complementary work. note: there was some delay in scheduling the provisional reception. | approval of: additional work + underwork + price review (prov. + defin.)
211 | 7626186 | Valorization of the Mother Church of Atalaia | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2020 | 2022 | Portugal | Vila Nova da Barquinha | Santarém | 16 | 33 | 15-04-2021 | 14-06-2022 | 425 | 140 | 234562.01 | 229914.57 | 1 | 225240.47 | 4674.1 | 102.0752 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | the extensions of the execution period were motivated by the lack of materials and equipment for the execution of the project. | complementary work to repair the fence walls of the churchyard
212 | 7623798 | Replacement of the roof and exterior spans, reformulation of interior spaces and painting of the facades of the old building of the headquarters of the District Center of Guarda | 45113000-2 | Siteworks | FALSE | 2021 | 2022 | Portugal | Guarda | Guarda | 9 | 20 | 20-04-2021 | 23-01-2022 | 278 | 120 | 355200 | 334814.82 | 2 | 334814.82 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | due to the pandemic, many workers were in confinement and there was a delay in the delivery of the material.
213 | 7618778 | 2020/190 - DGEP - Parking next to Av. Duque de Loulé and streetManuel da Silva Gaio, in Linda-a-Velha | 45233120-6 | Road construction works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 15-04-2021 | 26-04-2022 | 376 | 180 | 412841.75 | 387704.44 | 2 | 414494.38 | -26789.94 | 93.5367 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
214 | 7617328 | Cp 30/2020 - extension of water supply networks and wastewater sanitation networks at the uf de arosa and castelões - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 16-12-2020 | 18-01-2022 | 398 | 120 | 125000 | 116465.49 | 1 | 116465.42 | 0.07 | 100.0001 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
215 | 7612074 | Paving with granite brick in several places in the Municipality. | 45432110-8 | Floor-laying work | FALSE | 2021 | 2022 | Portugal | Amarante | Porto | 13 | 15 | 13-04-2021 | 14-04-2022 | 366 | 90 | 308091 | 12224 | 1 | 13609.65 | -1385.65 | 89.8186 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was completed before the end of the contractual term | price review
216 | 7612036 | 3rd - Phase of the Energy Efficiency Requalification Project of 6 Social Neighborhoods: Social Neighborhood of Reguengo Grande | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Lourinhã | Lisboa | 11 | 15 | 14-04-2021 | 07-04-2022 | 358 | 120 | 278782.17 | 249000 | 1 | 273588.87 | -24588.87 | 91.0125 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Award criterion is price assessment Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | errors and omissions complementary work | errors and omissions complementary work
217 | 7611923 | 2nd Phase of the Energy Efficiency Requalification Project of 6 Social Neighborhoods: Social Neighborhood of São Bartolomeu dos Galegos | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2022 | Portugal | Lourinhã | Lisboa | 11 | 15 | 14-04-2021 | 18-01-2022 | 279 | 122 | 240850.51 | 229000 | 1 | 245436.21 | -16436.21 | 93.3033 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Award criterion is price evaluation. Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | acceptance of complementary works, for supplies of errors and omissions and considerable delay in the approval of the removal of asbestos in the roof, by the external entity act | acceptance of complementary works, for supplies of errors and omissions.
218 | 7611848 | Contract for "Remodeling of the Patio/São João Baptista de Ajudá Children's Park" | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 20 | 06-04-2021 | 07-03-2022 | 335 | 120 | 230000 | 219818.58 | 1 | 244731.25 | -24912.67 | 89.8204 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 50% Criterion related to cost Name: Cost 40% and deadline 10% which makes the total of 50% Weighting: 50% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
219 | 7611295 | Replacement of Fiber Cement Roofing at elementary School n.7 of Barreiro | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 60 | 18-03-2021 | 14-01-2022 | 302 | 60 | 285000 | 277151.64 | 2 | 297497.92 | -20346.28 | 93.1609 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension and extensions | minor and additional work
220 | 7610960 | Reservoir Rehabilitation Contract - Phase 3 (Alentejo) | 45247270-3 | Reservoir construction works | FALSE | 2020 | 2022 | Portugal | Castelo de Vide | Portalegre | 12 | 30 | 22-03-2021 | 18-05-2022 | 422 | 240 | 450000 | 335277.69 | 2 | 367900.13 | -32622.44 | 91.1328 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0 % Diário da República, 2nd series No. 12626 November 04, 2020 Page 4 Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | replacement of the financial balance of the contract in the form of a term extension (60 days). | change in the value of the project due to contractual works not carried out and due to the price review carried out.
221 | 7610878 | Requalification and energy efficiency works at the Centro Escolar da Ordem | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2022 | Portugal | Lousada | Porto | 13 | 21 | 05-04-2021 | 05-04-2022 | 365 | 90 | 89600 | 78980.55 | 1 | 81880.29 | -2899.74 | 96.4586 | Best value for money: No Criterion related to quality Name: No discretion Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic | price review
222 | 7608402 | Rehabilitation of street of Jovens - section between street of Trabalhador and Praça da Sociedade Filarmónica Recreio Alverquense - Alverca do Ribatejo | 45233251-3 | Resurfacing works | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 18 | 03-02-2021 | 06-01-2022 | 337 | 120 | 317400 | 302023.14 | 2 | 315103.45 | -13080.31 | 95.8489 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | approval of price revision in the amount of €13,080.31
223 | 7603000 | Contract n.º 71/2020 - Central Park - Development of Park Requalification Actions, Replacement of Pavements, Recovery of the Irrigation Network and Lake Cleaning - North Zone | 45233200-1 | Various surface works | FALSE | 2021 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 05-04-2021 | 08-04-2022 | 368 | 120 | 179028 | 164999.3 | 1 | 164999.3 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reasons for changing the execution period: - as a result of the covid19 pandemic, there were delays in the delivery of materials, difficulties in transport and in the delivery of raw materials. - as a result of the pandemic, there was still a lack of labour, which was aggravated by the fact that many workers were forced to isolate themselves.
224 | 7602209 | Requalification of the Ecopista do Dão | 45233142-6 | Road-repair works | FALSE | 2021 | 2022 | Portugal | Viseu | Viseu | 20 | 21 | 05-04-2021 | 30-03-2022 | 359 | 120 | 276200 | 235986.3 | 1 | 256104.2 | -20117.9 | 92.1446 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | " verified the need to carry out work that was not foreseen, requiring the conclusion of the additional contract to the contract for the execution of the projects" | 120 days (29.04.2021 to 27.08.2021) / suspension between 08.23.2021 and 10.11.2021 with execution period up to 10.17.2021
225 | 7600618 | Advanced Civil Protection Unit - Vale Maria Dias - Refurbishment and expansion of the old house of the councilors of Vale Maria Dias | 45262800-9 | Building extension work | FALSE | 2020 | 2022 | Portugal | Loulé | Faro | 8 | 30 | 03-03-2021 | 29-03-2022 | 391 | 240 | 348346.98 | 330543.22 | 2 | 330543.22 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension
226 | 7596806 | Improvement of the Estrada do Viso (EM 546) | 45233141-9, 45000000-7 | Road-maintenance works, Construction work | FALSE | 2020 | 2022 | Portugal | Grandola | Setúbal | 17 | 30 | 17-03-2021 | 16-05-2022 | 425 | 150 | 761901.26 | 527043.13 | 2 | 559203.97 | -32160.84 | 94.2488 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: 1. The award will be made according to the criterion of the economically most advantageous Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the item for application of the price review had to be reinforced by the finance division, verifying a delay in the development of the process | the contract had a provisional price review and a definitive price review, verifying the increase of 32,160.84 included in vat
227 | 7596421 | Paving, in bituminous concrete, of streets - 9th Phase, in the parishes of Santa Maria de Lamas and Rio Meão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 12-03-2021 | 16-02-2022 | 341 | 120 | 311392 | 202935.6 | 1 | 194592.7 | 8342.9 | 104.2874 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 60 days of graceful extension 75 days of delay in the conclusion of the projects by the contractor 5 days in the scheduling of inspections | underwork
228 | 7593521 | Public works contract for the introduction of traffic lights for pedestrians on Av.ª Francisco Costa Gomes | 45113000-2 | Siteworks | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 18 | 01-03-2021 | 12-04-2022 | 407 | 49 | 52000 | 44447.08 | 1 | 44447.08 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration of the execution period of the contract was due to the delay in carrying out the electrical works and assembly of the meter by the energy trader.
229 | 7592409 | River rehabilitation of the Avelames River in Cidadelhe de Aguiar | 45246000-3 | River regulation and flood control works | FALSE | 2021 | 2022 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 18 | 22-03-2021 | 18-05-2022 | 422 | 180 | 185470 | 145805 | 1 | 152777.55 | -6972.55 | 95.4361 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | prior inspection of the good execution of the projects by the "apa". | pricing review.
230 | 7583287 | Contract nº 55/2020 - Execution of the Parking Marking Plan - 2021/2022 | 45233221-4 | Road-surface painting work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 31 | 23-03-2021 | 24-02-2022 | 338 | 560 | 181640 | 178000 | 1 | 193529.2 | -15529.2 | 91.9758 | Best value for money: Yes Criterion related to quality Name: Quality in work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion was anticipated due to weather conditions being very favorable for the application of paints with specific chemical components. the profitability of the teams was higher than estimated, because they were not conditioned to weather conditions, namely the rain. rain, humidity and heat influence the project carried out in the execution of horizontal signage. | due to the definitive price revision in the amount of €15,529.20, an addendum was made to the project bill on 07/04/2022.
231 | 7583109 | Contract nº 56/20 - Horizontal Signage 2021 - Lot 1 - North Zone and Lot 2 - South Zone | 45233221-4 | Road-surface painting work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 23-03-2021 | 18-01-2022 | 301 | 240 | 330000 | 264000.1 | 2 | 281886.42 | -17886.32 | 93.6548 | Best value for money: Yes Criterion related to quality Name: Quality of work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | completion was anticipated due to weather conditions being very favorable for the application of paints with specific chemical components. the profitability of the teams was higher than estimated because they were not conditioned to weather conditions, namely rain. rain, humidity and heat influence the project carried out in the execution of horizontal signage. | due to the final price revision in the amount of €17,886.32 (lot 1 - €8,819.65) (lot 2 - €9,066.67), an addendum was made to the project bill on 07/04/2022.
232 | 7581711 | Urban Requalification of street of Hibiscos / street ofs Palmeiras | 45000000-7 | Construction work | FALSE | 2020 | 2022 | Portugal | Anadia | Aveiro | 1 | 15 | 18-12-2020 | 05-01-2022 | 383 | 150 | 147416 | 117315.5 | 1 | 117315.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
233 | 7581170 | Construction of the Parish Council of Água Longa - Exterior Arrangements | 45233262-3 | Pedestrian zone construction work | FALSE | 2021 | 2022 | Portugal | Santo Tirso | Porto | 13 | 14 | 19-03-2021 | 09-05-2022 | 416 | 60 | 63320.45 | 56761.7 | 1 | 57850.51 | -1088.81 | 98.1179 | Best value for money: No Criterion related to quality Name: None Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | definition of new works not initially contracted. | the existence of additional work, as well as underwork.
234 | 7580967 | Public Tender for the contract "Execution of the Viana do Castelo incubator - Lot 59" | 45262700-8 | Building alteration work | TRUE | 2021 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 7 | 22-03-2021 | 13-01-2022 | 297 | 120 | 254007.63 | 252052.69 | 2 | 256642.41 | -4589.72 | 98.2116 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | but weather conditions and measures imposed by covid-19. | more work and underwork.
235 | 7580879 | Refurbishment of Roofs at elementary Schools No. 5 in Chaves, Vila Verde da Raia and Dr. Francisco Goncalves Carneiro | 45261210-9 | Roof-covering work | FALSE | 2020 | 2022 | Portugal | Chaves | Vila Real | 19 | 18 | 17-03-2021 | 15-02-2022 | 335 | 60 | 108357.25 | 95883 | 1 | 102905.95 | -7022.95 | 93.1754 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension for 118 days | definitive price review worth €7,672.95
236 | 7578223 | Requalification and paving of streets and public space, adjacent to Bairro da Chentuada | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Amarante | Porto | 13 | 15 | 12-03-2021 | 08-06-2022 | 453 | 180 | 235400 | 226030.78 | 1 | 245896.59 | -19865.81 | 91.9211 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the execution period | underwork and price revision
237 | 7575763 | Contract for "Structural Consolidation of the Wall Section of the City of Lagos, between Porta de S. Gonçalo and Castelo dos Governadores" | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lagos | Faro | 8 | 30 | 08-03-2021 | 25-01-2022 | 323 | 120 | 178000 | 175950.6 | 1 | 182304.92 | -6354.32 | 96.5145 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, no. | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for carrying out the project was extended for another 30 days by order of mr. president of 07/22/2021 | determined the final value of the price revision, the amount of €6,354.32, plus vat
238 | 7568623 | streets in Frutuoso | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-03-2021 | 20-01-2022 | 316 | 90 | 19563.21 | 18846 | 1 | 19235.13 | -389.13 | 97.977 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conditions caused by the pandemic situation and delay in the delivery of materials and specialized labor | ordinary provisional price review
239 | 7568493 | streets in Tinhela | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-03-2021 | 24-05-2022 | 440 | 120 | 52171.88 | 50744 | 1 | 50744 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation caused by covid-19 and lack of material and labor to complete the project | ordinary price review
240 | 7568323 | streets in Seixedo | 45233252-0 | Surface work for streets | FALSE | 2021 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-03-2021 | 12-07-2022 | 489 | 90 | 22431.15 | 21190 | 1 | 21190 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of raw materials to complete the project and lack of skilled labor caused by the current covid-19 pandemic situation | provisional ordinary price revision
241 | 7567245 | Paving, in bituminous concrete, of streets - 9th Phase, in the parishes of Lourosa and S. João de Ver | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 12-03-2021 | 20-07-2022 | 495 | 120 | 319285 | 191969.9 | 1 | 191834.4 | 135.5 | 100.0706 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 181 days for non-compliance by the contractor, 106 days for correcting physical and documental defects | underwork
242 | 7541588 | PRC_0293/2020_GAE-AR0600 - Construction contract for the execution of the Redondelo Pumping Station and Complementary Works of the Terras de Bouro Interceptor System | 45232423-3 | Sewage pumping stations construction work | TRUE | 2020 | 2022 | Portugal | N/A | N/A | N/A | 17 | 02-03-2021 | 26-01-2022 | 330 | 210 | 400000 | 349097.46 | 2 | 400439.19 | -51341.73 | 87.1786 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | complementary works that resulted, fundamentally, from the omission of the articles related to the construction of the emergency discharge and the final section of connection to the redondelo pumping station, which, by mistake, were not included in the lpu of the variant proposal, patented in the tender.
243 | 7539689 | 2019/35 - DGEP - Refurbishment of floors in the Caxias prison | 45316110-9, 45233200-1 | Installation of road lighting equipment, Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 21 | 12-07-2019 | 04-05-2022 | 1027 | 90 | 158609.44 | 142541.09 | 1 | 142378.93 | 162.16 | 100.1139 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
244 | 7538328 | Rehabilitation of the EM581 between Carregal and Cruzamento da Lapa - 1st Phase and construction of a roundabout. | 45233120-6 | Road construction works | FALSE | 2020 | 2022 | Portugal | Sernancelhe | Viseu | 20 | 30 | 24-02-2021 | 28-04-2022 | 428 | 180 | 326763 | 299443.32 | 2 | 445706.72 | -146263.4 | 67.1839 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work and underwork | additional work and underwork
245 | 7537475 | Construction of Infrastructures for Drainage of Wastewater-ASAAST | 45232451-8 | Drainage and surface works | FALSE | 2021 | 2022 | Portugal | Santo Tirso | Porto | 13 | 14 | 18-02-2021 | 25-07-2022 | 522 | 45 | 23139.74 | 23095 | 1 | 28858.27 | -5763.27 | 80.0291 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the execution of complementary works. | complementary works and price revision.
246 | 7535967 | PRC_0168/2020_GAE - AR0561 - Rehabilitation of the Pelhe Interceptor - Section between streetD. Sancho and EE de Queimados (former EN14) - (V.N. Famalicão) | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2020 | 2022 | Portugal | Vila Nova de Famalicão | Braga | 3 | 42 | 05-03-2021 | 31-01-2022 | 332 | 300 | 700000 | 634533.29 | 2 | 760136.4 | -125603.11 | 83.4762 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | the interceptor was located in a garden area with large trees. the city council of famalicão requested that the trees not be removed for reasons of public interest, so a new route was recommended. errors and omissions derive from issues not safeguarded in the execution project - errors and omissions supply works (art. 377, nº 1 of the "public procurement code") in the amount of 9,405.68 eur.
247 | 7534259 | Public tender for the execution of the contract to repair ruptures in pipes and branches of the water supply network in the municipality of Albufeira-2020/20201 | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 26-02-2021 | 15-02-2022 | 354 | 304 | 250000 | 240935 | 1 | 240935 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
248 | 7532725 | PRC_0126/2020_GAE - AR0569 - Contract for the Execution of the Remodeling Work for the Entry of the WWTP in Lamego and the EE of Adega dos Chãos (Lamego) | 45232423-3, 45252127-4 | Sewage pumping stations construction work, Wastewater treatment plant construction work | TRUE | 2020 | 2022 | Portugal | Lamego | Viseu | 20 | 33 | 25-02-2021 | 27-01-2022 | 336 | 210 | 270000 | 208744.69 | 1 | 244156.35 | -35411.66 | 85.4963 | Best value for money: No Criterion related to quality Name: Not applicable Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to add a period to comply with the additional contract - objective amendment of the contract, namely, supply and assembly of additional equipment of the "endless" type, a new need that was found to be necessary and inseparable from the object of the initial contract , detected during the course of the remaining works, necessary to automate the discharge of the grates into the final container (5 m3). | work resulting from tasks necessary to supply errors and omissions in the project, as well as the supply of an "endless" not foreseen in the project and which was due to a new need detected after the beginning of the project
249 | 7532416 | Construction of a viewpoint - Faia - Rio Côa. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2022 | Portugal | Pinhel | Guarda | 9 | 30 | 23-02-2021 | 20-06-2022 | 482 | 480 | 143450 | 124243.7 | 1 | 124243.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Lowest Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
250 | 7511269 | Contract for "Linha do Norte - Rehabilitation of Lines 4T, 5T, 6T, 7T and 8T of Triage do Entroncamento | 45234100-7 | Railway construction works | FALSE | 2020 | 2022 | Portugal | Entroncamento | Santarém | 16 | 21 | 03-03-2021 | 07-04-2022 | 400 | 120 | 310000 | 299138.16 | 2 | 313979.66 | -14841.5 | 95.2731 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A
251 | 7510599 | Contract for improvement works and replacement of roofs and window frames in 2nd/3rd cycle and High schools in the Municipality of Cascais | 45261900-3 | Roof repair and maintenance work | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 10 | 01-03-2021 | 15-02-2022 | 351 | 162 | 7218652.3 | 629117.21 | 2 | 629117.21 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | given the academic activities and national exams that last in the current academic year
252 | 7509479 | Canal Caveira and Cerrado das Aranhas paving | 45000000-7, 45233200-1 | Construction work, Various surface works | FALSE | 2020 | 2022 | Portugal | Grandola | Setúbal | 17 | 30 | 29-01-2021 | 25-01-2022 | 361 | 150 | 95310.53 | 95079.69 | 1 | 109530.35 | -14450.66 | 86.8067 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the economically most advantageous Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the performance of complementary works | complementary works
253 | 7503723 | Refurbishment and expansion of the playground, creation of a fenced enclosure for dog activities, equipping the park with elements for sports, elements for the physical maintenance of young people and adults | 45112711-2 | Landscaping work for parks | FALSE | 2020 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 24-02-2021 | 04-05-2022 | 434 | 150 | 270000 | 242794.43 | 1 | 249874.62 | -7080.19 | 97.1665 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allocation of 12 days for the execution of the complementary works, object of the 2nd additional contract of 09.15.2021 | approval of additional work, underwork and calculation of the ordinary/provisional and final price revision.
254 | 7503613 | Paving of the Caminho da Boavista in Pêra | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Silves | Faro | 8 | 30 | 04-02-2021 | 16-02-2022 | 377 | 90 | 143113 | 142689.3 | 1 | 152580.29 | -9890.99 | 93.5175 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to describe | revision of prices and work to be done
255 | 7503548 | Participatory Budget - Construction and Improvement of Gaming Fields and Sports Areas (Vale das Éguas Stadium / Albergaria dos Doze) - Proc. No. 52/2020 | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2020 | 2022 | Portugal | Pombal | Leiria | 10 | 18 | 29-09-2020 | 24-02-2022 | 513 | 90 | 68998.98 | 67984.57 | 1 | 71895.85 | -3911.28 | 94.5598 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this work had two deadline extensions duly authorized by the competent body (respectively 75+60 days), and these deadlines were extended until 5/6/2020. i should also mention that this work was suspended from 6/5/2020 to 8/3/2020, according to the suspension and resumption of work filed in the administrative process, with the project being completed in terms of execution of work on the on 3-8-2020, with the contractor verbally requesting the inspection for the purposes of provisional acceptance. considering the conclusion of the project on the project, the inspection was carried out as soon as possible by the parties, on the date closest to the completion of the project. the inspection was carried out on 08/28/2020, on which date the provisional acceptance document was drawn up and signed. | existence of complementary work and price revision
256 | 7503115 | Requalification of streetCoelho e Castro - Fiães | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 22-02-2021 | 13-06-2022 | 476 | 180 | 252429 | 227662.75 | 1 | 185516.96 | 42145.79 | 122.718 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | 17 days in the inspection appointment for provisional reception purposes | underwork
257 | 7502463 | Contract for improvement works and replacement of roofs and window frames in 2nd/3rd cycle and High schools in the Municipality of Cascais | 45261900-3 | Roof repair and maintenance work | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 10 | 25-02-2021 | 07-04-2022 | 406 | 180 | 7218652.3 | 566000 | 2 | 566000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension from academic activities and national exams
258 | 7502261 | Removal of asbestos-cement roofing at schools EB Nº2, EB Nº6 and EB Nº7 in Baixa da Banheira and EB Nº2 in Vale da Amoreira. | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Moita | Setúbal | 17 | 42 | 23-02-2021 | 17-01-2022 | 328 | 180 | 285000 | 51227.22 | 1 | 54547.23 | -3320.01 | 93.9135 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | pricing review.
259 | 7501145 | Rehabilitation of Avenida 25 de Abril | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 12-02-2021 | 07-04-2022 | 419 | 120 | 174305.15 | 160869.76 | 1 | 179139.1 | -18269.34 | 89.8016 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | did not meet the deadline. | underwork, price review.
260 | 7500642 | Construction of support walls in granite masonry and other infrastructure - September 2020 | 45262510-9 | Stonework | FALSE | 2020 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 10-02-2021 | 11-01-2022 | 335 | 150 | 162135 | 161973.5 | 1 | 156540.81 | 5432.69 | 103.4705 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork and price revision
261 | 7499187 | Contract for the execution of reinforced concrete elements in various locations in the Municipality of Cascais | 45262300-4 | Concrete work | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 23-02-2021 | 25-02-2022 | 367 | 365 | 258337.5 | 219857.75 | 1 | 219857.75 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
262 | 7498771 | Rehabilitation of Municipal Roads (Roads and streets ) - Infrastructure damaged by the 2017 fires - Municipal Emergency Fund | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Mação | Santarém | 16 | 14 | 05-02-2021 | 07-06-2022 | 487 | 90 | 498855 | 348420.94 | 2 | 370171.91 | -21750.97 | 94.1241 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price or Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension | ordinary price review
263 | 7498654 | Paving, in bituminous concrete, of streets - 9th Phase, in the parishes of Sanguedo and Fiães | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 22-02-2021 | 19-01-2022 | 331 | 120 | 310299 | 247282.15 | 1 | 247282.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 148 days delay in completion of work by contractor | contract price review
264 | 7498512 | Contract "South Line - Anticorrosive Protection of Metallic Bridges on the South Line, Phase 2" | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2020 | 2022 | Portugal | Alcácer do Sal | Beja | 2 | 30 | 23-02-2021 | 02-02-2022 | 344 | 210 | 820000 | 749951.39 | 2 | 783376.21 | -33424.82 | 95.7332 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation in the execution period of the project of 62 days
265 | 7491780 | Replacement of wooden window frames at the elementary School of Aguada de Baixo | 45421100-5 | Installation of doors and windows and related components | FALSE | 2020 | 2022 | Portugal | Águeda | Aveiro | 1 | 27 | 03-02-2021 | 05-04-2022 | 426 | 60 | 30000 | 28850 | 1 | 30290.02 | -1440.02 | 95.2459 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | although the projects were consigned in march/21 and the fps were approved in july/21, by superior decision, the projects only started at the end of the 20/21 school year. after completion of the project and respective inspection for the purpose of provisional acceptance, it was verified the need to repair detected defects. | there was no change to the award value.
266 | 7491662 | Removal and Replacement of the Fiber Cement Roofing at the Assequins elementary school | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Águeda | Aveiro | 1 | 21 | 03-02-2021 | 04-02-2022 | 366 | 90 | 41455.4 | 39862.41 | 1 | 43806.33 | -3943.92 | 90.9969 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the deadline for carrying out the project. | the only factor that caused an increase in the value of the project was the value due to price revision.
267 | 7490532 | P106/2020 - Requalification of the municipal road network - Several streets in the Union of Parishes of Rio de Couros and Casal dos Bernardos | 45233140-2 | Roadworks | TRUE | 2020 | 2022 | Portugal | Ourém | Santarém | 16 | 25 | 14-01-2021 | 06-06-2022 | 508 | 180 | 511696.6 | 492950.88 | 2 | 516786.47 | -23835.59 | 95.3877 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work suspension | underwork and price revision
268 | 7490432 | Contract for the construction of a parking lot in Albarraque | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 18-02-2021 | 17-01-2022 | 333 | 60 | 309881.27 | 174542.11 | 1 | 174542.11 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | 45 day extension
269 | 7478332 | Public Tender for the Requalification Work of the Piornos Viewpoint | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 02-02-2021 | 10-01-2022 | 342 | 120 | 56300 | 55787.95 | 1 | 55787.95 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes.
270 | 7477215 | Refurbishment of the access staircase at the entrance to the train station, refurbishment of the public lighting network, rainwater drainage, and renovation of all floors in the square | 45112711-2 | Landscaping work for parks | FALSE | 2020 | 2022 | Portugal | Valongo | Porto | 13 | 22 | 11-02-2021 | 01-04-2022 | 414 | 180 | 359000 | 297257.35 | 2 | 300836.17 | -3578.82 | 98.8104 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of 2 extensions of 30 days + 40 days, and allocation of 10 days to carry out the complementary work. | additional work - €32,154.99 underwork - €49,741.84 price revision calculation - €21,165.72
271 | 7473115 | Rehabilitation of the square of the Church of Rio de Galinhas | 45211360-0 | Urban development construction work | FALSE | 2020 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 03-02-2021 | 21-04-2022 | 442 | 120 | 132632.69 | 117045.65 | 1 | 137637.82 | -20592.17 | 85.0389 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project finished within the deadline. | positive definitive price revision, worth €12,801.35
272 | 7471107 | Public works contract designated for Rehabilitation of Cell II of the Alcanhões Reservoir | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2022 | Portugal | Santarém | Santarém | 16 | 60 | 08-02-2021 | 26-01-2022 | 352 | 240 | 750000 | 549860.56 | 2 | 579717.27 | -29856.71 | 94.8498 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | changes resulting from contractual work not carried out and the price review carried out.
273 | 7468272 | Asbestos Removal in School Buildings - Vila Franca de Xira Municipality | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 22 | 01-02-2021 | 04-01-2022 | 337 | 165 | 1327500 | 273792.76 | 2 | 282647.18 | -8854.42 | 96.8673 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | nothing to report | approval of works unless approval of final price revision
274 | 7468178 | Asbestos Removal in School Buildings - Vila Franca de Xira Municipality | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 22 | 01-02-2021 | 04-01-2022 | 337 | 165 | 1327500 | 313687.61 | 2 | 296761.35 | 16926.26 | 105.7037 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | nothing to report | approval of underwork and approval of definitive price review
275 | 7468132 | Asbestos Removal in School Buildings - Vila Franca de Xira Municipality | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 22 | 01-02-2021 | 04-01-2022 | 337 | 165 | 1327500 | 386977.5 | 2 | 345616.93 | 41360.57 | 111.9672 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | nothing to report | awarding of proposals for underwork and price revisions
276 | 7468111 | Cpn 75/2020/dicp - t-82/2020 removal of asbestos-containing asbestos cement in school buildings in the municipality of leiria | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 19 | 16-12-2020 | 11-08-2022 | 603 | 90 | 749402.5 | 259868.32 | 2 | 275456.64 | -15588.32 | 94.3409 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | complementary work (article 373) | complementary work (article 374)
277 | 7468058 | Cpn 75/2020/dicp - t-82/2020 removal of asbestos-containing asbestos cement in school buildings in the municipality of leiria | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 19 | 16-12-2020 | 11-08-2022 | 603 | 90 | 749402.5 | 353550.27 | 2 | 388764.23 | -35213.96 | 90.9421 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works (article 374). | complementary works (article 373).
278 | 7463821 | Cp 14/2020 - extensions of wastewater drainage networks - uf de tabuadelo and s. Faustino | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 27-10-2020 | 05-01-2022 | 435 | 120 | 150000 | 142242.45 | 1 | 132872.7 | 9369.75 | 107.0517 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
279 | 7426543 | Contract No. 64/2020 - Conservation and Improvement of Municipal Buildings/Municipal School Park - Miscellaneous Works | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 31 | 01-02-2021 | 31-03-2022 | 423 | 240 | 358996.55 | 323096.91 | 2 | 323096.91 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deviation was due to procedural delays in the invoicing and reception of the contract.
280 | 7422920 | Improvement of the bathing conditions of the Queimadela reservoir - Construction of Footbridges | 45246510-1 | Boardwalk construction work | FALSE | 2020 | 2022 | Portugal | Fafe | Braga | 3 | 15 | 01-02-2021 | 18-02-2022 | 382 | 60 | 156110 | 155044.5 | 1 | 155044.49 | 0.01 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value and guarantee of the Proposal Weighting: 40% Criterion related to cost Name: price (according to the adopted price formula) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was suspension of work and extension of deadline | there were complementary works
281 | 7422261 | Interior Rehabilitation Contract for the São João National Theater Building | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Porto | Porto | 13 | 30 | 29-01-2021 | 22-06-2022 | 509 | 165 | 953862.52 | 940000 | 2 | 1094556.54 | -154556.54 | 85.8795 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | execution of complementary works, according to amendment no. 1 to the construction contract. | execution of complementary works, according to amendment no. 1 to the construction contract.
282 | 7421461 | Contract nº 57/20 - EB D. Francisco Manuel de Melo - Execution of Work for Removal and Replacement of Asbestos | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 7 | 26-01-2021 | 13-01-2022 | 352 | 150 | 185000 | 184000 | 1 | 199841.6 | -15841.6 | 92.0729 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the slight deviation from the execution deadline is exclusively due to procedural factors of delay in the delivery of the waste management plan at work. | due to the 1st provisional price revision in the amount of €14,902.19 and the 2nd definitive price revision in the amount of €939.41.
283 | 7416949 | Paving streets in S. Pedro de Sólis | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Mértola | Beja | 2 | 3 | 25-01-2021 | 02-03-2022 | 401 | 180 | 721827.05 | 694430.1 | 2 | 679720.79 | 14709.31 | 102.164 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty in mobilizing labour due to the circumstances resulting from the pandemic | underwork
284 | 7416060 | Requalification of E.M.558 - Connection from Reguenga (Santo Tirso) to Seroa (Paços de Ferreira) | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Santo Tirso | Porto | 13 | 21 | 28-01-2021 | 29-03-2022 | 425 | 180 | 618787.86 | 543140.07 | 2 | 524335.53 | 18804.54 | 103.5864 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management systems, quality control and environmental management Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | non-execution of certain contractual works.
285 | 7415633 | Cp 11/2020 - Extension of water supply networks and wastewater sanitation networks in the parishes of Brito, Guardizela, Pinheiro, Silvares and UF de Conde and Gandarela - Guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 18-12-2020 | 21-07-2022 | 580 | 120 | 253000 | 231489.18 | 1 | 205331.75 | 26157.43 | 112.7391 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
286 | 7414390 | CP 38/2020_DEGA -Wastewater from Covelo, Angeja_Albergaria-a-Velha | 45232460-4 | Sanitary works | TRUE | 2020 | 2022 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 4 | 12-01-2021 | 04-01-2022 | 357 | 120 | 249900 | 235601.93 | 1 | 234921.98 | 679.95 | 100.2894 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
287 | 7414216 | Contract work for smiths in various locations in the Municipality of Cascais | 45262670-8 | Metalworking | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 27-01-2021 | 23-06-2022 | 512 | 730 | 316073.5 | 287427 | 2 | 287427 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Proximity Weighting: 20% Criterion related to cost name: price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed before the end of the contracted period
288 | 7412054 | Cp 26/2020 - execution of paving work to support the maintenance and conservation of water supply and wastewater sanitation systems, in the municipalities of guimarães and vizela | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Vizela | Braga | 3 | 14 | 09-12-2020 | 31-03-2022 | 477 | 365 | 190000 | 183531.5 | 1 | 155278.17 | 28253.33 | 118.1953 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
289 | 7412031 | 2020/144 - DGEP - Execution of the support wall on street7 de Junho in Barcarena | 45262310-7 | Reinforced-concrete work | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 20-01-2021 | 28-01-2022 | 373 | 60 | 38952.25 | 28453.5 | 1 | 29146.98 | -693.48 | 97.6207 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | constraints on the normal development of the project due to the whole situation involved in relation to the new coronavirus, the contingency plans and everything that involves the logistics of the project, namely everything with regard to subcontractors/suppliers, purchase of materials to be applied, etc. what delayed delayed the beginning of the contract by 11 days due to lack of team.
290 | 7411732 | Cp 12/2020 - extensions of water supply and wastewater drainage networks - uf de selho s. Lourenço and gominhães and uf de abação and twins | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 27-10-2020 | 11-02-2022 | 472 | 180 | 336000 | 323580 | 2 | 323520.15 | 59.85 | 100.0185 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
291 | 7411613 | CP 09/2020 - WAREHOUSE / WORKSHOPS at VIMÁGUA | 45213221-8 | Warehouse stores construction work | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 25 | 19-08-2020 | 05-05-2022 | 624 | 210 | 1147206.52 | 1147082.92 | 3 | 1080746.47 | 66336.45 | 106.138 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | complementary work
292 | 7411496 | Cp 05/2020 - extension of water supply networks and wastewater sanitation networks in seven parishes / union of parishes - municipality of guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 27-05-2020 | 12-07-2022 | 776 | 180 | 312700 | 295833.48 | 2 | 294125.91 | 1707.57 | 100.5806 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | extensions | underwork
293 | 7411395 | Cp 04/2020 - extension of wastewater drainage networks on streetde Santa Maria (northern section) and street1.º de Maio at u.f. Of atães and rendufe - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 26-05-2020 | 05-01-2022 | 589 | 120 | 152000 | 143420.11 | 1 | 143408.49 | 11.62 | 100.0081 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | works less
294 | 7411108 | Non-Technological Business Incubator in Portalegre | 45210000-2 | Building construction work | FALSE | 2020 | 2022 | Portugal | Portalegre | Portalegre | 12 | 10 | 25-01-2021 | 21-02-2022 | 392 | 365 | 748788.87 | 729690.85 | 2 | 781702.45 | -52011.6 | 93.3464 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A |  | the change in the value of the project refers to the price revision
295 | 7411081 | Cp 25/2020 - extension of wastewater drainage networks and replacement of water supply networks in the parishes of selho (são jorge) and gondar - municipality of guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 23-12-2020 | 21-07-2022 | 575 | 150 | 417300 | 410886.06 | 2 | 347074.78 | 63811.28 | 118.3855 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extensions | underwork
296 | 7409539 | Paving, in bituminous concrete, of streets - 9th Phase, in the parishes of Arrifana and Milheirós de Poiares | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 22-01-2021 | 02-02-2022 | 376 | 120 | 319753 | 220574.2 | 1 | 220574.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 165 days delay by the contractor in completing the project, 57 days in correcting defects between the 1st inspection and provisional acceptance
297 | 7407246 | Requalification of Largo 1º Maio in Sacavém | 45233140-2 | Roadworks | TRUE | 2020 | 2022 | Portugal | Loures | Lisboa | 11 | 30 | 05-11-2020 | 14-06-2022 | 586 | 180 | 349000 | 309988.37 | 2 | 330589.81 | -20601.44 | 93.7683 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Bid Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the supply of materials due to the pandemic crisis. difficulties in articulating work outside the contract. | price review
298 | 7407024 | Cp 21/2020 - rehabilitation of wastewater collectors using cipp technology, in the municipalities of guimarães and vizela | 45232411-6 | Foul-water piping construction work | FALSE | 2020 | 2022 | Portugal | Vizela | Braga | 3 | 14 | 02-11-2020 | 09-03-2022 | 492 | 365 | 173380 | 129720 | 1 | 129546.8 | 173.2 | 100.1337 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
299 | 7405145 | 2020/120 - DGEP - Execution and repair of pedestrian pavements in Oeiras and Paço-de-Arcos | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 60 | 19-01-2021 | 12-08-2022 | 570 | 365 | 163053.4 | 158420 | 1 | 158420 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
300 | 7404477 | Public tender for awarding the contract for "Fórum Cultural das Neves" | 45262700-8 | Building alteration work | TRUE | 2020 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 08-01-2021 | 04-05-2022 | 481 | 180 | 295700 | 286139.2 | 2 | 286139.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological instabilities and difficulty in the supply of materials and lack of available labor.
301 | 7401582 | Public tender for the award of the contract for "Recovery and Refurbishment of a Building for the International Observatory of Serra D'Arga | 45262700-8 | Building alteration work | TRUE | 2020 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 08-01-2021 | 17-02-2022 | 405 | 90 | 202664.95 | 195245.59 | 1 | 197433.19 | -2187.6 | 98.892 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | lack of conditions for waterproofing the first floor to start work. | underwork
302 | 7400056 | Territorial cohesion - Road transport - Rehabilitation of the Ega / Sebal road | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 15 | 20-10-2020 | 06-06-2022 | 594 | 120 | 220000 | 105300 | 1 | 119471.01 | -14171.01 | 88.1385 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | granted 30 days of graceful extension of the execution period of the contract | complementary works and price revision
303 | 7399680 | Requalification of streetBento Jesus Caraça and Roundabout - Montenegro | 45233252-0 | Surface work for streets | TRUE | 2020 | 2022 | Portugal | Faro | Faro | 8 | 15 | 15-01-2021 | 07-07-2022 | 538 | 180 | 565155.33 | 478281.9 | 2 | 556760.49 | -78478.59 | 85.9044 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
304 | 7399084 | Contract 141/Gebalis/2020 - Rehabilitation and conservation works in Bairro do Armador, lots 751A and 750A | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 14 | 14-01-2021 | 04-02-2022 | 386 | 240 | 449674.03 | 380094.85 | 2 | 365056.45 | 15038.4 | 104.1195 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | complexity in the execution of the project and adverse weather conditions during the course of the project
305 | 7395879 | Paving and streets - Requalification/Paving - streetDireita and streetCasa do Povo Pegarinhos and Paving and streets - Requalification/Paving - Access path to the WWTP in Pegarinho | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2020 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 16-12-2020 | 01-01-2022 | 381 | 180 | 202933 | 193612 | 1 | 193612 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the suspension of work relates to covid outbreaks in the company
306 | 7394767 | Requalification of Roads and Infrastructures at TAT - Armação de Pêra | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Silves | Faro | 8 | 30 | 04-12-2020 | 04-02-2022 | 427 | 120 | 246299 | 234391.22 | 1 | 227202.03 | 7189.19 | 103.1642 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the current situation of the pandemic due to covid 19 caused several delays in the supply of the necessary materials for the project; bad weather in february and march 2021 led to delays in earthworks for laying pipelines | nothing to say
307 | 7392148 | Widening and paving of berms, execution of sidewalks, construction of drains and support walls, creation of pedestrian crosswalks and placement of protection and road safety elements. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Coimbra | Coimbra | 6 | 33 | 04-12-2020 | 04-03-2022 | 455 | 150 | 456289 | 411959.96 | 2 | 431819.36 | -19859.4 | 95.401 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work without deadline extension | value related to price review
308 | 7389511 | Requalification of the Barrô Center Zone | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Águeda | Aveiro | 1 | 21 | 15-12-2020 | 04-04-2022 | 475 | 150 | 218954.07 | 210735.8 | 1 | 243325.46 | -32589.66 | 86.6066 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the causes for the alteration of the deadline for the execution of the project are related to the suspension of the projects and the complementary works that had to be carried out. | the value of the project changed following the approval and execution of complementary works, and also with some underwork that were not carried out.
309 | 7387328 | Community space madame faber/torrões - trafaria | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2020 | 2022 | Portugal | Almada | Setúbal | 17 | 12 | 22-12-2020 | 25-03-2022 | 458 | 150 | 207533.21 | 166026.58 | 1 | 202524.24 | -36497.66 | 81.9786 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Bid price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out the project. | price review
310 | 7382416 | Completion of the implementation of the measurement and control zones in the municipality of barreiro | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 15 | 15-12-2020 | 25-05-2022 | 526 | 180 | 190000 | 180565.54 | 1 | 216684.1 | -36118.56 | 83.3312 | Best value for money: Yes Criterion related to quality Name: Proposal Quality Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of complementary work of unforeseen circumstances | execution of complementary work
311 | 7378477 | Requalification of Primary Schools of the 1st Cycle and Kindergartens in the Municipality of Reguengos de Monsaraz - Requalification of Blocks A, B and C of the Manuel Augusto Papança Primary School | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 29-12-2020 | 14-02-2022 | 412 | 120 | 222193.25 | 221770.54 | 1 | 250269.31 | -28498.77 | 88.6128 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to suspend the project; execution of complementary works | complementary works underwork price review
312 | 7377567 | 13-Emp/20 - Contract to expand the Luz de Tavira Cemetery - Phase 1 | 45215400-1 | Cemetery works | FALSE | 2020 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 30-12-2020 | 01-07-2022 | 548 | 270 | 243203.45 | 226170.74 | 1 | 243432.86 | -17262.12 | 92.9089 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Bid price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension due to the covid 19 pandemic and delivery of the technical compilation of the contract. | underwork worth -950.00€ and definitive price revision worth €18,212.12 (positive).
313 | 7368630 | 12-Emp/20 - Contract to replace the pier at Cabanas beach | 45241100-9 | Quay construction work | FALSE | 2020 | 2022 | Portugal | Tavira | Faro | 8 | 30 | 22-12-2020 | 10-03-2022 | 443 | 200 | 545000 | 492972.22 | 2 | 577586.91 | -84614.69 | 85.3503 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | project completed ahead of schedule | complementary work and price revision
314 | 7359216 | Contracts for replacement of fiber cement coverings in schools, by lot | 45262660-5 | Asbestos-removal work | TRUE | 2020 | 2022 | Portugal | Alenquer | Lisboa | 11 | 21 | 23-12-2020 | 03-02-2022 | 407 | 60 | 633643.2 | 182212 | 1 | 180692.8 | 1519.2 | 100.8408 | Best value for money: Yes Criterion related to quality Name: Quality of Descriptive Memory Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the existence of more works and the market situation. | due to the existence of complementary work and underwork (errors and omissions (e&o) with regard to the quantities of roofs and gutters)
315 | 7359197 | Contracts for replacement of fiber cement coverings in schools, by lot | 45262660-5 | Asbestos-removal work | TRUE | 2020 | 2022 | Portugal | Alenquer | Lisboa | 11 | 21 | 23-12-2020 | 03-02-2022 | 407 | 60 | 633643.2 | 181680 | 1 | 180256.8 | 1423.2 | 100.7895 | Best value for money: Yes Criterion related to quality Name: Quality of Descriptive Memory Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | existence of complementary works and market instability regarding the acquisition of materials | existence of complementary work and less
316 | 7359182 | Contracts for replacement of fiber cement coverings in schools, by lot | 45262660-5 | Asbestos-removal work | TRUE | 2020 | 2022 | Portugal | Alenquer | Lisboa | 11 | 21 | 23-12-2020 | 04-05-2022 | 497 | 60 | 633643.2 | 234949 | 1 | 254218.55 | -19269.55 | 92.4201 | Best value for money: Yes Criterion related to quality Name: Quality of Descriptive Memory Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | extensions | complementary work and less
317 | 7356306 | The purpose of this contract is to improve the energy certification at EB 2+3 José Cardoso Pires. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 27 | 18-12-2020 | 02-03-2022 | 439 | 287 | 502941.92 | 485167.86 | 2 | 523465.81 | -38297.95 | 92.6838 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | good organization of the project, advance ordering of materials and timely delivery of materials. | due to the provisional price review in the amount of €38,297.95.
318 | 7355649 | Space adaptation for Animal Welfare Center - Kennel/Catry. | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2022 | Portugal | Pinhel | Guarda | 9 | 30 | 11-12-2020 | 14-02-2022 | 430 | 365 | 248000 | 226562.86 | 1 | 299826.65 | -73263.79 | 75.5646 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | complementary works | complementary work
319 | 7352695 | Rehabilitation of pavements on several roads in the municipality | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 28-10-2020 | 03-01-2022 | 432 | 180 | 559570 | 385708 | 2 | 385708 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
320 | 7352345 | Urban requalification contract for the West Zone of Vila de Arouca - 2nd phase | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Arouca | Aveiro | 1 | 30 | 22-12-2020 | 31-08-2022 | 617 | 365 | 138637.35 | 138628.15 | 1 | 140032.65 | -1404.5 | 98.997 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay attributable to the contractor. | existence of less and complementary work.
321 | 7350871 | Urban Requalification Contract for the West Zone of Vila de Arouca - Access to Romariz | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Arouca | Aveiro | 1 | 30 | 22-12-2020 | 31-03-2022 | 464 | 360 | 248940.36 | 222835.86 | 1 | 204216.43 | 18619.43 | 109.1175 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay attributable to the contractor. | existence of complementary works and others to be suppressed.
322 | 7346749 | Energy rehabilitation of roofs at Cova da Loba developments, D. António ferreira gomes, dr. Francisco Pinto Balsemão, Lot 73 Vila D'Este and Tabosa Lot 2. Review of roofs | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 16-12-2020 | 30-06-2022 | 561 | 360 | 847470 | 393500.5 | 2 | 417833.76 | -24333.26 | 94.1763 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the project took place within the contracted period, however the provisional acceptance notice was only prepared on the date indicated. | a price revision was determined with definitive indices worth €24,333.26.
323 | 7345400 | Its purpose is to improve energy certification at EB 2+3 Pedro D'Orey da Cunha. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 27 | 15-12-2020 | 28-03-2022 | 468 | 287 | 561614.43 | 533533 | 2 | 559671.85 | -26138.85 | 95.3296 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the deviation was due to the anticipation of tasks foreseen in the project plan due to the fact that the educational establishment was not operating during the period of confinement resulting from the pandemic. | due to the 1st provisional price review in the amount of €28,000.43; due to the 2nd definitive price revision in the amount of -1,861.58€; an addendum to the final account was made on 05/30/2022.
324 | 7344946 | Contract for the Rehabilitation of Various Pavements in the Municipality of Ponta Delgada | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 8 | 14-12-2020 | 04-02-2022 | 417 | 120 | 206000 | 204962.54 | 1 | 242215.21 | -37252.67 | 84.62 | If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | legal extensions | additional work and price revisions
325 | 7342210 | Contract for the Requalification of the Crossing of Portela de Moldes - Portas da Freita | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Arouca | Aveiro | 1 | 30 | 17-12-2020 | 08-02-2022 | 418 | 150 | 255896.63 | 253619.85 | 2 | 258865.97 | -5246.12 | 97.9734 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay attributable to the contractor. | existence of complementary and suppressed works.
326 | 7340929 | 2020/81 - DGEP - Repair of stone walls in Linda-a-Velha | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 45 | 11-12-2020 | 26-04-2022 | 501 | 120 | 142500 | 127850 | 1 | 134212.14 | -6362.14 | 95.2596 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
327 | 7339885 | CP 33/2020_DEGA - Rehabilitation of command house of Captação do Areeiro - Sever do Vouga | 45259000-7 | Repair and maintenance of plant | TRUE | 2020 | 2022 | Portugal | Sever do Vouga | Aveiro | 1 | 27 | 03-12-2020 | 18-03-2022 | 470 | 60 | 30000 | 26932.68 | 1 | 26932.68 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
328 | 7339814 | CP 31/2020_DEGA - Rehabilitation of the Carregal Reserve System - Ovar and Rehabilitation of the Grass Reserve System - Ovar | 45259000-7 | Repair and maintenance of plant | TRUE | 2020 | 2022 | Portugal | Ovar | Aveiro | 1 | 42 | 20-11-2020 | 02-05-2022 | 528 | 150 | 340000 | 185000 | 1 | 185000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | nothing to report | nothing to report
329 | 7339447 | Urban arrangements in Miranda do Douro, Vila Nova, Vale de Águia, Palancar, Pena Branca, Malhadas, Genisio and Especiosa | 45233251-3 | Resurfacing works | FALSE | 2020 | 2022 | Portugal | Miranda do Douro | Bragança | 4 | 15 | 20-11-2020 | 10-01-2022 | 416 | 270 | 350000 | 348994 | 2 | 295791.28 | 53202.72 | 117.9866 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable for the execution of the projects | works less in the amount of €53,202.72
330 | 7338579 | 2020/6 - DCAD - Various demolitions of real estate in the Municipality of Oeiras. | 45111300-1 | Dismantling works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 10-12-2020 | 14-04-2022 | 490 | 850 | 299700 | 232250 | 1 | 246849.29 | -14599.29 | 94.0857 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
331 | 7337881 | Public Tender for Execution of the Adaptation and Expansion Contract for an Existing Building the Funeral Chapel and Respective Accesses - Vila de Nordeste | 45215400-1 | Cemetery works | FALSE | 2020 | 2022 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 15 | 03-12-2020 | 21-02-2022 | 445 | 243 | 419125.26 | 374497.82 | 2 | 388750.85 | -14253.03 | 96.3336 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the causes of alterations to the execution period of the projects are filed in the procedure. | the amount of 19,962.84 was added to the effective total price, which corresponds to the provisional price revision.
332 | 7332234 | Acquisition of a public works contract | 45261210-9 | Roof-covering work | FALSE | 2020 | 2022 | Portugal | Évora | Évora | 7 | 15 | 02-11-2020 | 22-02-2022 | 477 | 90 | 180000 | 158781.25 | 1 | 207205.65 | -48424.4 | 76.6298 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was interrupted by determination of the municipality of évora, replacement of the roof, difficulty in the delivery of materials, namely iron. | payment of compensation to the contractor for the stoppage of the project, and alteration of the roof as well as other complementary works without which the project could not continue.
333 | 7331056 | Requalification of Avenida 14 de Janeiro - 2nd Phase | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Elvas | Portalegre | 12 | 15 | 09-12-2020 | 31-01-2022 | 418 | 150 | 180000 | 168818.84 | 1 | 168818.84 | 0 | 100 | Best value for money: No Criterion related to quality Name: Municipality of Elvas Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was necessary to make several corrections in the project in order to be able to carry out the provisional acceptance | there was a need to open ditches (80 ml) to support the video surveillance infrastructure to be placed in the moat parking lot
334 | 7327021 | This contract focuses on lot 2 and aims to improve the energy certification of elementary school Brandoa. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 03-12-2020 | 03-03-2022 | 455 | 245 | 371163.36 | 144022.53 | 1 | 152209.21 | -8186.68 | 94.6214 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the contingencies that implied the delay in the execution of the project were due to the logistics of receiving and packaging materials, as well as the availability of school spaces, related to the pandemic. | due to the definitive price revision in the amount of €8,186.68.
335 | 7324182 | Its object is the requalification of the main axes of the Municipality. | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 24-11-2020 | 01-04-2022 | 493 | 245 | 943250 | 799976.85 | 2 | 799976.85 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | with the completion of the project, the "plan for the prevention and management of construction and demolition waste" was requested from the contractor, which was delayed in delivery, the existence of underground infrastructure not foreseen in some interventions, causing delays in the completion of the interventions.
336 | 7323986 | Its object is to carry out defined works, as to their type, quantity and technical conditions of execution, in the project and in the specifications. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Sintra | Lisboa | 11 | 15 | 24-11-2020 | 25-01-2022 | 427 | 120 | 84949.99 | 72189.72 | 1 | 72189.72 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | unpredictable situations related to the pandemic
337 | 7319819 | 2020/124 - DGEP - Pedestrian access EVA-Carnaxide | 45233200-1, 45112720-8, 45316100-6, 45112000-5 | Various surface works, Landscaping work for sports grounds and recreational areas, Installation of outdoor illumination equipment, Excavating and earthmoving work | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 45 | 16-11-2020 | 22-04-2022 | 522 | 180 | 198432.43 | 144119.08 | 1 | 163533.93 | -19414.85 | 88.1279 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
338 | 7316751 | Public works contract Mrs. Do Desterro - Construction of flow measurement boxes | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Seia | Guarda | 9 | 62 | 07-10-2020 | 07-02-2022 | 488 | 180 | 150000 | 128103.84 | 1 | 142019.17 | -13915.33 | 90.2018 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | price revision calculated with final september 2021 indices
339 | 7310497 | Moimenta Community Center | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2020 | 2022 | Portugal | Cinfães | Viseu | 20 | 20 | 09-10-2020 | 18-02-2022 | 497 | 180 | 169734.6 | 168677.18 | 1 | 171753.39 | -3076.21 | 98.2089 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price evaluation/Lowest cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | price review, overwork and underwork.
340 | 7309473 | Construction of leisure coverage and accesses to buildings and replacement of fiber cement roofing at Ramada High school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2022 | Portugal | Odivelas | Lisboa | 11 | 15 | 18-11-2020 | 10-08-2022 | 630 | 60 | 580000 | 559707 | 2 | 559707 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality and Execution Time (total weighting) Weighting: 80% Criterion related to cost Name: Price Weighting: 20% | 1 | 20 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the project deadline | there were no changes
341 | 7297858 | Contract to repave streetde Santa Eulália and adjacent streets and contract to repave streetJosé Fontana. | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 20 | 18-11-2020 | 21-01-2022 | 429 | 90 | 605000 | 603701.62 | 2 | 623439.62 | -19738 | 96.834 | Best value for money: Yes Criterion related to quality Name: This criterion includes technical value and deadline Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | extension due to the extremely adverse weather conditions that occurred and constraints resulting from the pandemic and that affected suppliers | the effective value of the project reflects the total work carried out.
342 | 7295787 | Improvement and Conservation of the Farmers' Market / Local Market \ Short Chains - Proc. No. 45/2020 | 45259000-7 | Repair and maintenance of plant | FALSE | 2020 | 2022 | Portugal | Pombal | Leiria | 10 | 21 | 14-09-2020 | 13-01-2022 | 486 | 120 | 216325.16 | 216299.99 | 1 | 218399.78 | -2099.79 | 99.0386 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | there was an extension of the execution period | existence of underworks
343 | 7295265 | Primary school of Alpendorada - Removal of the fiber cement covering | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Porto | Porto | 13 | 15 | 04-11-2020 | 06-07-2022 | 609 | 120 | 204782.7 | 159476.01 | 1 | 168188.79 | -8712.78 | 94.8196 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended | positive definitive price review
344 | 7295133 | 4-Emp/20 - Contract for the conservation and improvement of the municipality's road network - Municipal Roads in the Parish of Tavira and in the Parish of Luz de Tavira and Santo Estêvão - Lot 2, 4 and 5 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 09-11-2020 | 06-07-2022 | 604 | 120 | 1722754.44 | 905935.45 | 2 | 1018485.1 | -112549.65 | 88.9493 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delivery of the technical compilation of the contract. | works less in the amount of -8,546.67€ and definitive price revision in the amount of €121,096.32 (positive).
345 | 7294695 | Pedestrian Trail- PR 8 Sirga Route | 45233260-9 | Pedestrian ways construction work | FALSE | 2020 | 2022 | Portugal | Gavião | Portalegre | 12 | 22 | 21-10-2020 | 15-02-2022 | 482 | 210 | 282928.2 | 194793.55 | 1 | 194793.55 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | there were no changes in the value of the project
346 | 7293384 | 4-Emp/20 - Contract for the conservation and improvement of the municipality's road network - Municipal Roads in the Parish of Tavira and in the Parish of Luz de Tavira and Santo Estêvão - Lot 1 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 12-11-2020 | 06-07-2022 | 601 | 120 | 1722754.44 | 353441.26 | 2 | 411798.87 | -58357.61 | 85.8286 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delivery of the technical compilation of the contract. | underwork worth -596.70€ and definitive price review worth €58,954.31 (positive).
347 | 7281964 | "CAO Requalification" based on application nº CENTRO-05-4842-FEDER-000213 of 30-04-2018 | 45215000-7 | Construction work for buildings relating to health and social services, for crematoriums and public conveniences | TRUE | 2020 | 2022 | Portugal | Viseu | Viseu | 20 | 15 | 06-11-2020 | 29-06-2022 | 600 | 180 | 376305.35 | 368469.74 | 2 | 368469.74 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 70% Criterion related to cost Name: Technical value of the proposal Weighting: 30% | 1 | 30 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reasons of public interest resulting from a new consideration of the existing circumstances, under the terms of the provisions of paragraph c) of article 312 of the "public procurement code".
348 | 7268680 | streets in Ervões | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Valpaços | Vila Real | 19 | 15 | 02-11-2020 | 23-03-2022 | 506 | 120 | 65769.91 | 63139.5 | 1 | 61414.5 | 1725 | 102.8088 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays caused by the covid-19 pandemic situation and delay in the delivery of materials necessary for the execution of the projects | there was no need to carry out all the project
349 | 7265224 | carry out the defined works, as to their type, quantity and technical conditions of execution in the project and in the specifications. | 45442180-2 | Repainting work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 15 | 05-11-2020 | 09-03-2022 | 489 | 210 | 475621.77 | 434604.43 | 2 | 434604.43 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 15% Criterion related to cost name: price Weighting: 85% | 1 | 85 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | consignment notice signed later than expected due to the unavailability of the intervening parties
350 | 7263976 | P063/2020 - Creation of the Agroal Walkway | 45233161-5 | Footpath construction work | TRUE | 2020 | 2022 | Portugal | Ourém | Santarém | 16 | 18 | 30-09-2020 | 04-04-2022 | 551 | 180 | 325986.9 | 176999.29 | 1 | 188187.91 | -11188.62 | 94.0545 | Best value for money: No Criterion related to quality Name: N\applicable Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension resulting from complementary work | complementary works and price revision
351 | 7263886 | Public tender for the execution of the Paving contract for Caminho da Baleeira - S. Rafael, street of Farol and Ponta da Baleeira | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 20 | 05-11-2020 | 04-03-2022 | 484 | 120 | 900000 | 676503.16 | 2 | 717104.65 | -40601.49 | 94.3381 | Best value for money: Yes Criterion related to quality Name: This criterion includes technical value and deadline Weighting: 50% Criterion related to cost name: price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | existence of asbestos-cement conduit in the alignment of the rock garden wall deployment, which represents an obstacle to the stable base of the wall.
352 | 7261035 | Cultural and recreational center of the historic core of portalegre | 45210000-2 | Building construction work | FALSE | 2020 | 2022 | Portugal | Portalegre | Portalegre | 12 | 30 | 05-11-2020 | 24-03-2022 | 504 | 365 | 218216.75 | 205474.74 | 1 | 215487.21 | -10012.47 | 95.3536 | Best value for money: No Quality criteriaDiary of the Republic, 2nd series No. 9414 August 21, 2020 Page 4 Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the pandemic, there was a delay in the delivery of materials and in personnel management | due to price revision
353 | 7259086 | CP 25/2020_DEGA - Wastewater from Bunheira - Oliveira do Bairro | 45232460-4 | Sanitary works | TRUE | 2020 | 2022 | Portugal | Oliveira do Bairro | Aveiro | 1 | 40 | 23-10-2020 | 21-01-2022 | 455 | 180 | 442000 | 362278.37 | 2 | 353240.7 | 9037.67 | 102.5585 | Best value for money: Yes Criterion related to quality Name: PRICE Weighting: 55% Criterion related to cost Name: VALIA TÉCNICA Weighting: 45% | 1 | 45 | 5 | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
354 | 7256147 | Rehabilitation of the Banda 14 de Janeiro headquarters building. | 45210000-2 | Building construction work | FALSE | 2020 | 2022 | Portugal | Elvas | Portalegre | 12 | 21 | 21-08-2020 | 22-04-2022 | 609 | 365 | 394000 | 376189.2 | 2 | 381511.27 | -5322.07 | 98.605 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the supply of materials used in the project, due to the pandemic. | in addition to suppressed work today a price review.
355 | 7253529 | The object of this contract concerns bituminous repaving, replacement of pavement bases and paintings | 45233223-8 | Carriageway resurfacing works | FALSE | 2020 | 2022 | Portugal | Cadaval | Lisboa | 11 | 15 | 03-11-2020 | 18-04-2022 | 531 | 300 | 738646.97 | 638408.13 | 2 | 702306.31 | -63898.18 | 90.9017 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the deadline | price review
356 | 7248149 | Requalification of streetFerreira de Lemos - Santo Tirso | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Santo Tirso | Porto | 13 | 21 | 30-10-2020 | 21-04-2022 | 538 | 365 | 1396238.25 | 1238095.22 | 3 | 1136953.46 | 101141.76 | 108.8959 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A |  | the non-execution of a certain type of contractual work during the course of the project.
357 | 7247867 | Energy rehabilitation of the Perosinho social housing development | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 19-10-2020 | 26-05-2022 | 584 | 270 | 661500 | 557146.38 | 2 | 587201.81 | -30055.43 | 94.8816 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the contracted period, however, the provisional acceptance notice was only drawn up on the date indicated, as it was necessary for the contractor to correct any anomalies in the project carried out. | a price review was carried out with definitive indices worth €30,055.43.
358 | 7245878 | Removal of roofs covered with asbestos-containing fiber cement sheets at schools in the municipality of loulé, in quarteira - drª laura ayres school | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Loulé | Faro | 8 | 18 | 22-10-2020 | 17-05-2022 | 572 | 120 | 221000 | 168883.19 | 1 | 168883.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the supply of material (sandwich panel and bituminous canvas) and repair of equipment affected by the contract works.
359 | 7245822 | Removal of roofs covered with asbestos-containing fiber cement sheets in schools in the municipality of loulé, schools in loulé, almancil and boliqueime | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2022 | Portugal | Loulé | Faro | 8 | 18 | 22-10-2020 | 13-05-2022 | 568 | 120 | 240000 | 189106.14 | 1 | 189106.14 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | atmospheric conditions in the month of february/2021, interference with class periods in the various school equipment, supplies of material (sandwich panel and waterproofing screen).
360 | 7242553 | House of Music Jorge Peixinho | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2020 | 2022 | Portugal | Montijo | Setúbal | 17 | 15 | 24-06-2020 | 26-04-2022 | 671 | 365 | 991000 | 925043.92 | 2 | 995767.14 | -70723.22 | 92.8976 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension of the execution period due to the pandemic situation, as well as the soil stereotomy found. | there was no change in the value of the contract.
361 | 7239911 | Stabilization contract for the cliff at Portinho de Areia Sul | 45220000-5 | Engineering works and construction works | FALSE | 2020 | 2022 | Portugal | Peniche | Leiria | 10 | 3 | 06-10-2020 | 29-03-2022 | 539 | 120 | 435000 | 349202.64 | 2 | 349202.64 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to deadlines | there were no contract price changes
362 | 7226897 | Revitalization of street5 de Outubro - Sertã | 45233160-8 | Paths and other metalled surfaces | FALSE | 2020 | 2022 | Portugal | Sertã | Castelo Branco | 5 | 21 | 14-08-2020 | 11-03-2022 | 574 | 120 | 212650 | 194844.44 | 1 | 184017.58 | 10826.86 | 105.8836 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | especially related to the covid 19 pandemic, with many workers and company managers affected by the disease and especially with many delays in the delivery of some materials for the project. | underwork mainly caused by the decrease in the area of ​​the fence wall and the decrease in the paving area on the sidewalk at the junction with largo do município
363 | 7226805 | Cpn 86/2020/dicp -t - 94/2020 ¦ conservation work at the municipal stadium of leiria | 45259900-6 | Plant upgrade work | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 15 | 16-10-2020 | 29-04-2022 | 560 | 120 | 249633.9 | 246951.64 | 1 | 246951.64 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
364 | 7217099 | Contract for remodeling the Laje Pumping Station (1st Phase Intervention) | 45240000-1 | Construction work for water projects | FALSE | 2020 | 2022 | Portugal | Serpa | Beja | 2 | 17 | 24-08-2020 | 15-02-2022 | 540 | 150 | 250000 | 177700 | 1 | 177700 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in reprogramming the pumping station automation and delay in supplying check valves. | no change
365 | 7216917 | PO 343/2020 - Padre Himalaya School - Alteration and Expansion of the Kindergarten | 45262800-9 | Building extension work | FALSE | 2020 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 30 | 22-10-2020 | 31-03-2022 | 525 | 120 | 160000 | 149923.89 | 1 | 173754.31 | -23830.42 | 86.285 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | changes made to the project, increased work and the covid 19 pandemic | changes made to the project, increased work and the covid 19 pandemic
366 | 7212830 | 2020/19 - DCAD - Various Civil Construction Works in Municipal Heritage | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 18 | 15-10-2020 | 21-04-2022 | 553 | 700 | 330575 | 320766.55 | 2 | 334457.1 | -13690.55 | 95.9066 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
367 | 7159762 | Contract for Requalification of streetCidade de Poligny - Proc. No. 21/dpo/sound/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2022 | Portugal | Arouca | Aveiro | 1 | 30 | 20-10-2020 | 02-02-2022 | 470 | 150 | 127740.25 | 100865.13 | 1 | 104122.79 | -3257.66 | 96.8713 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the only aspect of contract performance to be to celebrate. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay attributable to the contractor. | existence of complementary works.
368 | 7157710 | Ecovia between the Caminho da Cheira and the pedestrian bridge over the Ribeira de Ferreirim | 45422100-2 | Woodwork | FALSE | 2020 | 2022 | Portugal | Sernancelhe | Viseu | 20 | 30 | 24-08-2020 | 27-05-2022 | 641 | 240 | 589712.98 | 444698.33 | 2 | 500352.09 | -55653.76 | 88.8771 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost name: price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | cleaning. | complementary works.
369 | 7133970 | Cpn 26/2020/dicp - t - 55/2018 - repairs to the technical installations of the municipal stadium of leiria | 45310000-3 | Electrical installation work | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 96 | 01-10-2020 | 16-03-2022 | 531 | 180 | 834867.54 | 198977.94 | 1 | 214412.39 | -15434.45 | 92.8015 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A |  | complementary work under the terms of article 373 of the "public procurement code" and underwork under the terms of article 379 of the "public procurement code".
370 | 7133925 | Cpn 26/2020/dicp - t - 55/2018 - repairs to the technical installations of the municipal stadium of leiria | 45310000-3 | Electrical installation work | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 96 | 30-09-2020 | 16-03-2022 | 532 | 180 | 834867.54 | 414423.7 | 2 | 414423.7 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A
371 | 7129883 | CVTT - Technology Transfer and Valorization Center. | 45214610-9 | Laboratory building construction work | FALSE | 2020 | 2022 | Portugal | Elvas | Portalegre | 12 | 12 | 25-08-2020 | 02-05-2022 | 615 | 180 | 886000 | 843732.31 | 2 | 883703.74 | -39971.43 | 95.4768 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there were several deadline extensions and it was necessary to carry out several inspections in order to be able to carry out the provisional acceptance. | the difference in value verified in the price revisions
372 | 7128294 | Improvement of Urban Mobility and Road Safety in the Municipality of Alandroal - Parking Lot | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2022 | Portugal | Alandroal | Évora | 7 | 15 | 02-10-2020 | 21-03-2022 | 535 | 60 | 100007 | 99904.2 | 1 | 95845.26 | 4058.94 | 104.2349 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project. | suppressed works worth €4,650.53 and ordinary price review worth €591.59.
373 | 7125984 | Refurbishment of the Álvaro Guerra School - Vila Franca de Xira | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 21 | 14-05-2020 | 16-05-2022 | 732 | 270 | 1337125 | 1319000 | 3 | 1361892.48 | -42892.48 | 96.8505 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of materials and labor (covid-19) | underwork
374 | 7125781 | Citizens' Service Welcoming Center - Building Rehabilitation | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Ponte de Sor | Portalegre | 12 | 23 | 29-09-2020 | 15-12-2021 | 442 | 180 | 308365.45 | 288967.26 | 2 | 162904.33 | 126062.93 | 177.3846 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the modality of the most low price Weighting: 100% | 2 | 100 | 5 | FALSE | Non-fulfilment of the contract (Contract Termination) | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | termination of the contract on 12.15.2021, due to breach of contract by the contractor
375 | 7118580 | Complete Rehabilitation of the Former Headquarters of the Municipality of Lourinhã | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2022 | Portugal | Lourinhã | Lisboa | 11 | 15 | 07-10-2020 | 08-02-2022 | 489 | 365 | 297432.4 | 293950 | 2 | 391261.45 | -97311.45 | 75.1288 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award criterion is the evaluation of the price Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work due to the need to introduce changes to the project and acceptance by the d.o. of complementary works. | acceptance of complementary works, which included alterations to the initial project due to unpredictability. (inf. 1366/2021 02/02)
376 | 7112067 | Public tender for the execution of the contract for the survey and replacement/construction and repair of sidewalks in specific areas of the municipality of Albufeira. | 45233253-7 | Surface work for footpaths | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 01-10-2020 | 28-01-2022 | 484 | 450 | 345000 | 328645 | 2 | 328645 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
377 | 7102456 | Cyclable School Routes - Phases A and B | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Almada | Setúbal | 17 | 43 | 02-09-2020 | 16-05-2022 | 621 | 210 | 768428.28 | 765339.8 | 2 | 879852.22 | -114512.42 | 86.985 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | price review
378 | 7101969 | "Repaving and horizontal signaling of Av. D. João I - Abrantes" | 45233141-9 | Road-maintenance works | FALSE | 2020 | 2022 | Portugal | Abrantes | Santarém | 16 | 30 | 30-09-2020 | 08-03-2022 | 524 | 90 | 316438.01 | 293962.16 | 2 | 301782.6 | -7820.44 | 97.4086 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | correction of anomalies verified in the inspection of 26-02-2021 for the purpose of provisional acceptance. | ordinary price review.
379 | 7101396 | 2020/64 - DGEP - Execution of comfortable pedestrian pavements in the Municipality of Oeiras | 45233251-3 | Resurfacing works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 28-09-2020 | 19-05-2022 | 598 | 365 | 220457.5 | 206560 | 1 | 219049.78 | -12489.78 | 94.2982 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
380 | 7100683 | Enhancement and dynamization of the School Building - Visitation support space, in the parish of Vilarinho de São Romão | 45212410-3 | Construction work for lodging buildings | FALSE | 2020 | 2022 | Portugal | Sabrosa | Vila Real | 19 | 15 | 30-09-2020 | 20-01-2022 | 477 | 450 | 330000 | 328584.35 | 2 | 476779.13 | -148194.78 | 68.9175 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project started with the consignment date. | the need for over and underwork and price revisions
381 | 7100542 | Public Tender for the execution of the contract for the expansion of the general water supply network | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 28-09-2020 | 15-02-2022 | 505 | 395 | 202000 | 169823.61 | 1 | 169823.61 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
382 | 7097002 | Rehabilitation and recovery of buildings/fractions owned by the municipality - phase iii | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2020 | 2022 | Portugal | Portalegre | Portalegre | 12 | 14 | 28-08-2020 | 14-07-2022 | 685 | 180 | 332577.68 | 322490 | 2 | 326876.77 | -4386.77 | 98.658 | Best value for money: No Criterion related to quality Name: Quality Weighting: 100% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unavailability of materials and delays due to the pandemic | regarding price revision
383 | 7096913 | 2019/191 - DGEP - Requalification of public space on Consiglieri Pedroso road, in Queluz de Baixo | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 23-09-2020 | 28-01-2022 | 492 | 120 | 245779.66 | 237389.68 | 1 | 250652.29 | -13262.61 | 94.7088 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 6 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension, extra work | extra work
384 | 7062841 | 08-Emp/20 - Work contract for intervention at the existing BUS stops and shelters on the ER 125, in the municipality of Tavira | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 24-09-2020 | 26-04-2022 | 579 | 180 | 159652.89 | 159572.46 | 1 | 176205.66 | -16633.2 | 90.5603 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension | price review
385 | 7005650 | Construction contract for retaining walls at the Santa Casa da Misericórdia Complex in Aldeia Galega da Merceana | 45223000-6 | Structures construction work | FALSE | 2019 | 2022 | Portugal | Alenquer | Lisboa | 11 | 10 | 13-05-2020 | 14-02-2022 | 642 | 120 | 350000 | 347298.09 | 2 | 391560.94 | -44262.85 | 88.6958 | Best value for money: Yes Criterion related to quality Name: Guarantee of Good Execution (25%) + Technical Valuation of the Proposal (25%) Weighting: 50% Criterion related to cost Name: Global Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without changes | without changes
386 | 7002466 | Elevator Installation in the Old Barracks Building | 45313100-5 | Lift installation work | FALSE | 2020 | 2022 | Portugal | Penamacor | Castelo Branco | 5 | 9 | 02-09-2020 | 22-07-2022 | 688 | 90 | 41739.38 | 41054.77 | 1 | 47085.89 | -6031.12 | 87.1912 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work. | complementary work: not foreseen: €2,310.70; unpredictable: €3,473.10; underwork: €469.00; price review: €716.32.
387 | 7000887 | Improvement of the Light Vehicle Park and the Heavy Vehicle Park at the TMS-2 Terminal and New Entrance at the Ro-Ro Terminal - Coelho da Mota, at the Port of Setúbal | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2022 | Portugal | Setúbal | Setúbal | 17 | 8 | 04-07-2019 | 04-04-2022 | 1005 | 120 | 1450000 | 1210996 | 3 | 1237179.46 | -26183.46 | 97.8836 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | delays in the supply of some materials and covid 19 | complementary works
388 | 6998956 | Union of the Parishes of Guia, Ilha and Mata Mourisca / streets and Improvements on roads and paths in the Parish (street of Cemitério in Guia) - Proc. No. 38/2020 | 45233160-8 | Paths and other metalled surfaces | FALSE | 2020 | 2022 | Portugal | Pombal | Leiria | 10 | 6 | 31-08-2020 | 22-02-2022 | 540 | 90 | 86167.9 | 85781.75 | 1 | 86894.61 | -1112.86 | 98.7193 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the project was suspended from 12/18/2020 to 6/20/2021, according to suspension and restart records of work filed in the administrative process, i.e. the end date of the project was moved to 7/7/2021 as the project was completed in terms of execution of works on 7-7-2021, the contractor having verbally requested the inspection for the purpose of provisional acceptance, taking into account the conclusion of the projects of the project, the inspection was carried out as soon as possible to the parties on the earliest date after the completion of the project, with the provisional acceptance of the project being drawn up and signed on the inspection date on 7-30-2021. | price revision value.
389 | 6996369 | 2020/82 - DGEP - Requalification of Comendador Álvaro Vilela, Gôa, Damão, Timor and Mouzinho de Albuquerque streets in Tercena | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 21-09-2020 | 28-01-2022 | 494 | 45 | 55036.22 | 53064.52 | 1 | 51179.88 | 1884.64 | 103.6824 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
390 | 6996287 | 2020/67 - DGEP - Requalification of street of Constitution and street of Juventude in Tercena | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 21-09-2020 | 28-01-2022 | 494 | 60 | 71771.3 | 70936.42 | 1 | 71371.08 | -434.66 | 99.391 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
391 | 6983326 | Pesqueira and Lagoas do Tejo Route - 1st Phase | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2020 | 2022 | Portugal | Mação | Santarém | 16 | 14 | 31-08-2020 | 23-06-2022 | 661 | 180 | 329151.11 | 281863.52 | 2 | 292888.7 | -11025.18 | 96.2357 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - adverse weather conditions - work contract for the water tank/surrounding structure; - supply by the project owner of signage contents; - unfavorable season for planting due to weather conditions. | - complementary works; - review of prices.
392 | 6979322 | : Contract "Cascais Line - Improvement of track superstructure between PK7+400 and PK 16+000 VA and RV (Algés, Paço de Arcos and Santo Amaro)" eContracts No. 5010039444 | 45234100-7 | Railway construction works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 15-10-2020 | 10-03-2022 | 511 | 240 | 1995000 | 1735354.46 | 3 | 1799784.24 | -64429.78 | 96.4201 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
393 | 6977121 | 2020/68 - DGEP - Requalification of waste disposal points in the Municipality | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 21 | 15-09-2020 | 15-06-2022 | 638 | 365 | 108575 | 95515 | 1 | 95515 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
394 | 6975052 | 3/Eop/dcop/2020 - improvement and recovery works in schools of the 1st cycle of elementary education and kindergartens in the municipality of cascais 2020 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 30 | 16-09-2020 | 30-03-2022 | 560 | 60 | 2988143.02 | 553777.9 | 2 | 553777.9 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | TRUE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
395 | 6974971 | Café Barreiro - adaptation to the Police squadron - new procedure | 45216100-5 | Construction work for buildings relating to law and order or emergency services | FALSE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-09-2020 | 29-03-2022 | 559 | 274 | 1168700 | 1148758.18 | 3 | 1447029.08 | -298270.9 | 79.3874 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: cost 50 deadline 10 Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions | complementary work and less
396 | 6974716 | 2020/14 - DGEP - Conservation and repair of road pavements in Barcarena and Queijas | 45233142-6 | Road-repair works | FALSE | 2020 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 08-09-2020 | 02-03-2022 | 540 | 365 | 286052.1 | 219943.9 | 1 | 233499.54 | -13555.64 | 94.1946 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
397 | 6968609 | Contract work for the "Northern Line - Pk 202+000 - Slope and Hillside Stabilization" (Process No. 10003981) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2022 | Portugal | Montemor-o-Velho | Coimbra | 6 | 20 | 15-09-2020 | 21-02-2022 | 524 | 150 | 550000 | 544130.02 | 2 | 613689.95 | -69559.93 | 88.6653 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to mention | additional work had to be carried out
398 | 6924208 | Refurbishment of the sanitary facilities and accessibility of the Escola Básica do Outeiro - Rio Meão | 45210000-2 | Building construction work | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 09-09-2020 | 17-01-2022 | 495 | 180 | 163800 | 159700 | 1 | 170642 | -10942 | 93.5877 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | 15 days of legal extension (compl. work), 34 days of delay in completing the project, 30 days for scheduling inspections | complementary works
399 | 6920980 | Cpn 40/2020/dicp - t-57/2020 - rehabilitation and improvement of several streets in the municipality of leiria | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 33 | 02-09-2020 | 14-07-2022 | 680 | 300 | 2781498 | 873617.73 | 2 | 837640.63 | 35977.1 | 104.2951 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | graceful extension | underwork under the terms of article 379 of the "public procurement code".
400 | 6914892 | EB Amorosa recovery of installations | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Matosinhos | Porto | 13 | 9 | 31-08-2020 | 22-04-2022 | 599 | 120 | 42000 | 35457.35 | 1 | 35457.35 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
401 | 6908185 | Restoration of street of Rancho da Praça, street of Senra and Largo Guilherme Gomes Fernandes | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Vila do Conde | Porto | 13 | 21 | 31-07-2020 | 28-03-2022 | 605 | 243 | 320000 | 275666.94 | 2 | 273472.15 | 2194.79 | 100.8026 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
402 | 6904093 | "L.Sul - Rehabilitation of the Overpass at KP 0.576" (Case No. 10002941) | 45221119-9 | Bridge renewal construction work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 19 | 04-09-2020 | 31-01-2022 | 514 | 180 | 680000 | 490430.74 | 2 | 508660.9 | -18230.16 | 96.416 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | anticipation deadline for execution of the project of 34 days
403 | 6903968 | Paving, in bituminous concrete, of streets in the union of parishes of Canedo, Vale and Vila Maior - 8th Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 03-09-2020 | 19-01-2022 | 503 | 120 | 327450 | 225361.46 | 1 | 234565.96 | -9204.5 | 96.0759 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 90 days of extension, 97 days of delay in completing the project, 76 days in correcting deficiencies between the 1st inspection and provisional acceptance | complementary works, and price revision
404 | 6902078 | Construction of the cycling and pedestrian route in the city of Valpaços - filling | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Valpaços | Vila Real | 19 | 18 | 11-08-2020 | 24-02-2022 | 562 | 300 | 632075.47 | 602391.23 | 2 | 677617.69 | -75226.46 | 88.8984 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of raw material due to the pandemic situation caused by covid-19 | complementary works and ordinary revision of provisional prices
405 | 6891084 | Construction of the Transport Interface - Miranda do Douro Road Interface | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 21-08-2020 | 25-01-2022 | 522 | 240 | 317962 | 315095.96 | 2 | 315095.96 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions | price review
406 | 6888510 | Requalification of the pedestrian surroundings at CACE - União das Parishes of Sobrado and Neighborhoods | 45233120-6 | Road construction works | FALSE | 2020 | 2022 | Portugal | Castelo de Paiva | Aveiro | 1 | 15 | 31-07-2020 | 03-05-2022 | 641 | 150 | 109213.1 | 96641.84 | 1 | 104411.27 | -7769.43 | 92.5588 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions | complementary works and price revision
407 | 6881366 | Reduction of Water Losses in Supply Systems in the Municipality of Sabugal | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2022 | Portugal | Sabugal | Guarda | 9 | 25 | 25-08-2020 | 25-05-2022 | 638 | 365 | 493751.85 | 449031.41 | 2 | 510841.85 | -61810.44 | 87.9003 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions | complementary work, less and price revision
408 | 6874888 | Construction of the Tunes Sports Complex - 2nd Phase | 45212200-8 | Construction work for sports facilities | FALSE | 2020 | 2022 | Portugal | Silves | Faro | 8 | 30 | 23-06-2020 | 01-06-2022 | 708 | 210 | 611230.66 | 579185.01 | 2 | 625588.45 | -46403.44 | 92.5824 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | complementary works and price revision
409 | 6874145 | Contract for the 2nd Urban Rehabilitation Phase of the Seat of the Municipality of Velas | 45113000-2 | Siteworks | FALSE | 2020 | 2022 | Portugal | Velas | Região Autónoma dos Açores | 15 | 20 | 25-08-2020 | 21-04-2022 | 604 | 365 | 1449886.83 | 1369174.28 | 3 | 1478856.95 | -109682.67 | 92.5833 | Best value for money: Yes Criterion related to quality Name: deadline of execution of the contract Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 2 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions, difficulty with labor, late release of land and pandemic situation. | change in the value of the project due to the application of the price review mechanism as provided for in the contract.
410 | 6867997 | Road bridge over the Ovelha river | 45221111-3 | Road bridge construction work | FALSE | 2020 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 10 | 07-08-2020 | 22-07-2022 | 714 | 300 | 560420 | 504101.76 | 2 | 547522.46 | -43420.7 | 92.0696 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed on time | price review
411 | 6867793 | Rehabilitation of Sidewalks and Improvement of Accessibility on Crosswalks in the Municipality of Faro | 45233200-1 | Various surface works | TRUE | 2020 | 2022 | Portugal | Faro | Faro | 8 | 14 | 12-08-2020 | 30-06-2022 | 687 | 365 | 141509 | 121916.5 | 1 | 132084.59 | -10168.09 | 92.3018 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
412 | 6864621 | Faro Urban Bike Path -Avenida Calouste Gulbenkian | 45233162-2 | Cycle path construction work | TRUE | 2020 | 2022 | Portugal | Faro | Faro | 8 | 7 | 14-08-2020 | 07-07-2022 | 692 | 90 | 155365 | 150992.1 | 1 | 165551.59 | -14559.49 | 91.2055 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A
413 | 6861225 | Contract Intervention 1/2 life on SST Entroncamento (Ti and 12) and 63kV circuit breakers | 45234170-8 | Locomotive-substations construction works | FALSE | 2020 | 2022 | Portugal | Entroncamento | Santarém | 16 | 68 | 18-08-2020 | 28-04-2022 | 618 | 240 | 130000 | 129000 | 1 | 136837.48 | -7837.48 | 94.2724 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | in view of the contract's logistics, the entire intervention was carried out at the entroncamento substation, where the meteorological conditions cannot be controlled and it was necessary to open the equipment to be intervened, introducing unnecessary humidity. added to this is the fact that the month of april was wet. additionally, the 60kv crossings, had a delivery period of 153 days, having suffered a delay in their delivery of 86 calendar days | price review
414 | 6857640 | Requalification of Largo do Pé da Cruz and surrounding area | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2022 | Portugal | Faro | Faro | 8 | 20 | 12-08-2020 | 28-06-2022 | 685 | 120 | 362449.65 | 318848.88 | 2 | 340239.03 | -21390.15 | 93.7132 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
415 | 6850292 | Contract for execution of the bypass pipeline of the R4-Monte Novo Adduction (EDIA) to the ETA of Monte Novo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Évora | Évora | 7 | 23 | 28-07-2020 | 09-03-2022 | 589 | 240 | 2500000 | 1799324.95 | 3 | 2124908.15 | -325583.2 | 84.6778 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the deadline of 111 days. | underwork, work to supply errors and omissions, compensation paid to the contractor for financial rebalancing and price review carried out.
416 | 6846107 | Improvement of circulation and use of the main railway interfaces, allowing it to be carried out more safely and in order to promote smooth mobility | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 24-07-2020 | 16-07-2022 | 722 | 180 | 255000 | 228752.77 | 1 | 283248.53 | -54495.76 | 80.7604 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | assignment of 30 days as the deadline for carrying out the complementary work (1st additional contract of 11.03.2021). | approval of additional work, underwork and price revision calculations.
417 | 6843362 | EP-2020(5001)/10008 Replacement of Divisions in 1st and 2nd Cycle Classrooms - CED Maria Pia | 45259000-7 | Repair and maintenance of plant | TRUE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 14 | 12-08-2020 | 05-01-2022 | 511 | 120 | 237360.5 | 212855.77 | 1 | 210968.27 | 1887.5 | 100.8947 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution of works by the contractor | existence of complementary work and underwork that led to the existence of a contractual modification report
418 | 6838522 | Work to expand the Mosqueira reservoir, including interconnection pipelines to the existing system. | 45247270-3 | Reservoir construction works | FALSE | 2020 | 2022 | Portugal | Albufeira | Faro | 8 | 15 | 05-08-2020 | 09-02-2022 | 553 | 183 | 1500000 | 1363848.18 | 3 | 1341914.85 | 21933.33 | 101.6345 | Best value for money: No Criterion related to quality Name: this criterion includes technical value and deadline Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | serious errors in the steel frame on one of the foundation slabs of the roof of the new cells that forced to redo all the project and to lose a few days of work that could have been applied better. the executing entity placed only 80% of the reinforcement foreseen in the project, jeopardizing the structure of the reservoir, errors detected in time and orders to be corrected. labor shortage. | the tender quantity map did not consider the correct quantities of some works that resulted in increased costs for the developer; some works necessary for the proper execution of the project that result from unforeseeable circumstances impossible to foresee in the tendering phase
419 | 6829698 | Improved circulation and use of the main railway interfaces, in order to ensure and promote the principle of smooth mobility | 45233140-2 | Roadworks | FALSE | 2020 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 27-07-2020 | 12-07-2022 | 715 | 210 | 380000 | 320515.77 | 2 | 336579.87 | -16064.1 | 95.2273 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extensions (25 + 40 days) | additional work - €44,772.05 underwork - €33,981.53 price review - €5,273.58
420 | 6824238 | Execution of groundwater collection borehole at Quinta da Bomba | 45120000-4 | Test drilling and boring work | FALSE | 2019 | 2022 | Portugal | Almada | Setúbal | 17 | 30 | 18-05-2020 | 27-05-2022 | 739 | 120 | 299820 | 193171.8 | 1 | 244882.85 | -51711.05 | 78.8834 | Best value for money: No Criterion related to quality Name: Evaluation of price or cost as the sole aspect of the performance of the contract to be signed. Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the sole aspect of the performance of the contract to be signed. Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | during drilling, an area with a void was reached, with the loss of drilling fluids and making the hole unfeasible in this location. as a result, the location of the drilling was changed, leaving it a hundred meters away from the original location, which allowed the realization of the capture hole. | works lost due to change of drilling location implied the execution of complementary works. the price review also changed the value of the project.
421 | 6824169 | Public Tender No. 92/DGADR/2020 - Contract for the Construction of the Headquarters Building of the Association Beneficiaries of Cela | 45210000-2 | Building construction work | FALSE | 2020 | 2022 | Portugal | Alcobaça | Leiria | 10 | 15 | 07-07-2020 | 03-03-2022 | 604 | 270 | 365000 | 347762.36 | 2 | 347762.36 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Proposal value Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic | price review
422 | 6823019 | CP 66/2019_DOP "Repair of faults in the RDA and execution of other work in the NOC - 5th Phase" | 45232151-5 | Water-main refurbishment construction work | TRUE | 2020 | 2022 | Portugal | Estarreja | Aveiro | 1 | 40 | 20-07-2020 | 17-02-2022 | 577 | 730 | 700000 | 700000 | 2 | 700000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contract for contract value. value reached.
423 | 6821415 | Commissioning contract for the Vale de Estrela pipeline - Famalicão da Serra | 50514200-3 | Repair and maintenance services of reservoirs | FALSE | 2019 | 2022 | Portugal | Guarda | Guarda | 9 | 30 | 29-06-2020 | 13-07-2022 | 744 | 240 | 400000 | 353970.37 | 2 | 335109.71 | 18860.66 | 105.6282 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change to the execution period of the project due to a suspension of the contract of 61 days. | change in the value of the project due to contractual works not carried out and price revision.
424 | 6820925 | Pavement Rehabilitation Contract in the Municipality of Moura | 45233251-3 | Resurfacing works | FALSE | 2020 | 2022 | Portugal | Moura | Beja | 2 | 30 | 17-07-2020 | 09-02-2022 | 572 | 60 | 209256.7 | 158569.7 | 1 | 151835.3 | 6734.4 | 104.4353 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of 28 days to start work | underwork worth €6,734.40
425 | 6812815 | Paving, in bituminous concrete, of streets in the parish of Argoncilhe - 8th Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-07-2020 | 19-01-2022 | 540 | 120 | 288086 | 215674.51 | 1 | 219483.23 | -3808.72 | 98.2647 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 187 days late in completing the project | complementary works and price revision
426 | 6810796 | Contract "Linha do Leste - Pk 197,000/199,815 - Migration of wooden sleepers through concrete and transition from short bars to long welded bars" eContracts No. 5010043427 | 45234100-7 | Railway construction works | FALSE | 2019 | 2022 | Portugal | Crato | Portalegre | 12 | 32 | 22-07-2020 | 14-03-2022 | 600 | 120 | 800000 | 735390.76 | 2 | 721726.23 | 13664.53 | 101.8933 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 35% Criterion related to cost Name: Price Weighting: 65% | 1 | 65 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
427 | 6804276 | Paving, in bituminous concrete, of streets in the União de parishes of Lobão, Gião, Guisande and Louredo - 8th Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-07-2020 | 17-01-2022 | 538 | 120 | 329670 | 233350.86 | 1 | 233350.86 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 30 days of extension, 189 days of delay in completing the projects, 74 days in correcting deficiencies between the 1st inspection and provisional acceptance | price review
428 | 6801905 | Fair Street - West Side Fair and Exhibition Park | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Grandola | Setúbal | 17 | 30 | 09-06-2020 | 16-05-2022 | 706 | 90 | 110340.17 | 100000 | 1 | 107938.2 | -7938.2 | 92.6456 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay by the contractor in the presentation of the documents of compliance with the "plan for the prevention and management of construction and demolition waste" at the projectplace | the contract had complementary works and a price revision notice in favor of the municipality
429 | 6787386 | Municipal Accessibility Program for All of Valongo - Interventions of 2019 | 45233251-3 | Resurfacing works | FALSE | 2020 | 2022 | Portugal | Valongo | Porto | 13 | 22 | 16-07-2020 | 31-03-2022 | 623 | 180 | 479525 | 407500 | 2 | 339227.96 | 68272.04 | 120.1257 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the 60-day period; extension of the 15-day period. note: the project on the project was completed on 07.27.2021, however, the last measurement report (accounting for the project) is dated 09.22.2021, as the contractor was suggested to carry out some more sidewalk rehabilitation work, which did not come to fruition due to alleged unavailability of human resources. | approval of works at €71,775.74 less approval of the provisional price revision calculation - €3,503.70
430 | 6779623 | Rehabilitation of the Quinta dos Castelos development | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 15-07-2020 | 29-06-2022 | 714 | 180 | 556414.7 | 545848.6 | 2 | 567496.9 | -21648.3 | 96.1853 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | extensions to the deadline for carrying out the project were duly approved. | resulting from the completion of the project. - complementary work worth €54,317.70; - underwork worth €43,863.45 and - revision of prices with provisional indices in the amount of €11,194.05.
431 | 6779407 | 2019/171 - DGEP - Execution of white treadmills with red background - on preformed canvas - and hot thermoplastic painting of treadmills | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 14-07-2020 | 28-04-2022 | 653 | 365 | 298880 | 236040 | 1 | 241965.68 | -5925.68 | 97.551 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to unfavorable weather conditions in november, which forced several stops. due to covid 19, with a shortage of raw materials that made it difficult to carry out the project, the nature of the project being applied depending on needs and priorities.
432 | 6778050 | Project for the Rehabilitation of the Chapel sr. Do além | 45453100-8 | Refurbishment work | TRUE | 2019 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 27 | 16-07-2020 | 08-04-2022 | 631 | 365 | 350000 | 328912.71 | 2 | 364505.04 | -35592.33 | 90.2354 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed within the contracted period, however, the provisional acceptance notice was only prepared on the date indicated. | the completion of the project resulted in additional work due to unforeseen circumstances in the amount of €18,110.00 and a price review was determined with definitive indices in the amount of €17,482.33.
433 | 6758655 | Enlargement and requalification of the central separator of the northern section of Av. Fernão de Magalhães and the Casa do Sal junction, creation of a lane dedicated to emergency vehicles at the Casa do Sal junction | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Coimbra | Coimbra | 6 | 33 | 18-05-2020 | 10-03-2022 | 661 | 330 | 928717.2 | 639400 | 2 | 673296.6 | -33896.6 | 94.9656 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work without deadline extension | price revision amount
434 | 6758256 | Contract to replace existing toponymic plaques | 45233294-6 | Installation of road signals | FALSE | 2020 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 15 | 06-07-2020 | 09-02-2022 | 583 | 270 | 192000 | 70746.42 | 1 | 75271.25 | -4524.83 | 93.9886 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was concluded within the foreseen period, however, the inspection for provisional acceptance, was only carried out on the indicated date, due to the verification in all the parishes, of all the plates placed. | a price revision was determined with definitive indices worth €4,524.83.
435 | 6757311 | Conception-Build Contract for the Refurbishment of the WWTP in Vila Velha de Rodão, Nisa and Gavião | 45232460-4 | Sanitary works | FALSE | 2020 | 2022 | Portugal | Vila Velha de Ródão | Portalegre | 12 | 23 | 24-06-2020 | 09-02-2022 | 595 | 400 | 800000 | 798892.6 | 2 | 845685.42 | -46792.82 | 94.4669 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the 60-day period. a first inspection was carried out for the purposes of provisional acceptance, where some anomalies were detected, and it was necessary to correct them and deliver some missing documents. | price review carried out.
436 | 6757295 | Recovery of the Public Space Surrounding the Walls - Axis 6.5 PEDU | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Estremoz | Évora | 7 | 30 | 10-07-2020 | 15-06-2022 | 705 | 120 | 681214.34 | 679998.38 | 2 | 741151.28 | -61152.9 | 91.7489 | Best value for money: Yes Criterion related to quality Name: Technical Value and Deadline (40% and 10% respectively) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions, suspensions and delays | additional, suppression of work and design errors
437 | 6743174 | Its object is the requalification of the facilities of elementary school José Ruy. | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 15 | 22-06-2020 | 14-01-2022 | 571 | 441 | 443389.82 | 399050.89 | 2 | 411218.26 | -12167.37 | 97.0411 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | favorable conditions were created for the functioning of the school, in order to facilitate the execution of the project. | due to the 1st provisional price review - €11,766.86; 2nd final price revision - €400.51.
438 | 6742983 | Vila de Rei Wastewater Outfall | 45232440-8 | Construction work for sewage pipes | FALSE | 2020 | 2022 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 25-06-2020 | 05-01-2022 | 559 | 300 | 185000 | 178673.17 | 1 | 177687.9 | 985.27 | 100.5545 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in the delivery of equipment by suppliers. | existence of complementary work and underwork.
439 | 6739444 | Contract for "Renovation of the Catenary Installation at Cascais Station". (Contracts No. 5010043284) | 45234160-5 | Catenary's construction works | FALSE | 2020 | 2022 | Portugal | Cascais | Lisboa | 11 | 30 | 30-06-2020 | 14-01-2022 | 563 | 240 | 583000 | 501663.22 | 2 | 533444.43 | -31781.21 | 94.0423 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | - current pandemic moment (covid 19); - part of the equipment, to be installed on site, comes from regions seriously affected by the pandemic, including countries foreigners, who are banned from entering the country; - decrease in productivity of companies in the construction sector, due to the pandemic moment; - the delay in the supply and consequent assembly of equipment will not allow the renewal of the existing catenary on site; - unforeseen situations encountered on the ground, the resolution of which depends directly on third parties (águas de cascais, cascais city council, edp, etc.). | during the projects of the contract, at the time of the excavation carried out for the construction of the massif for the placement of pole 25-10, several cables were found. moving these cables would result in unscheduled work. foreseen, an extremely specialized task that only could be performed by an entity accredited for the purpose, rises to the command of edp and which would result in very high costs outside the scope of the object of the contract. it was presented by the executing entity, mota-engil railway, s.a., an alternative adaptation to the original solution for the elaboration of the aforementioned massif, allowing to take advantage of the post foreseen, its location and most of the contractual items foreseen for the elaboration of the mass recommended in the project and avoiding the displacement of the cables found.
440 | 6731573 | 100% Quality - Paving in granite cube sidewalk, State of São Mamede de Infesta and Senhora da Hora | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2022 | Portugal | Matosinhos | Porto | 13 | 9 | 29-06-2020 | 21-06-2022 | 722 | 90 | 494000 | 357275 | 2 | 357275 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
441 | 6725562 | Requalification of Alpalhão streets | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Nisa | Portalegre | 12 | 30 | 25-06-2020 | 18-01-2022 | 572 | 180 | 282701 | 231019.25 | 1 | 231419.14 | -399.89 | 99.8272 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of definitive price revision indices. | definitive price review worth €399.89.
442 | 6724612 | The object of the contract is to carry out the work defined in terms of its type and technical conditions of execution, in the project and in the terms of reference, namely the requalification of the streets | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 15-06-2020 | 11-02-2022 | 606 | 120 | 329783.05 | 269962.4 | 2 | 269962.4 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - multiplicity of interactions with the affected services; - delay by the contractor in delivering the "plan for the prevention and management of construction and demolition waste"; - several constraints related to the pandemic and the state of emergency; - delays in the supply of materials due to the pandemic.
443 | 6713737 | Rehabilitation and adaptation of the school building on the avenue for a library - bm1 | 45212330-8 | Library construction work | FALSE | 2019 | 2022 | Portugal | Baião | Porto | 13 | 31 | 31-01-2020 | 22-07-2022 | 903 | 540 | 875724.55 | 849984.08 | 2 | 849984.08 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of term granted with limit until 03/10/2022. | 849,984.08 eur - works on site; 39,005.21 eur - price review; total work = 888,989.29 eur.
444 | 6706497 | Contract 152/GEBALIS/2020 - Bairro Quinta do Cabrinha - Public tender for Installation, Modernization and repair of elevators in Bairro Quinta do Cabrinha lots 1 to 10 - Vale de Alcântara - Lisbon | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Lisboa | Lisboa | 11 | 15 | 08-06-2020 | 09-03-2022 | 639 | 180 | 280000 | 156358.7 | 1 | 165385.09 | -9026.39 | 94.5422 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
445 | 6704469 | Requalification of the north/east land area of ​​the fontaínhas dock, in the port of setúbal | 45113000-2 | Siteworks | TRUE | 2020 | 2022 | Portugal | Setúbal | Setúbal | 17 | 22 | 28-05-2020 | 17-03-2022 | 658 | 120 | 330000 | 327997.39 | 2 | 331781.5 | -3784.11 | 98.8595 | Best value for money: Yes Criterion related to quality Name: Work Methodology and Planning Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to delay in delivery by the supplier, delay due to covid 19 | complementary work
446 | 6703627 | Conservation of the Old House of Magistrates | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Grandola | Setúbal | 17 | 21 | 14-05-2020 | 19-04-2022 | 705 | 30 | 44417.83 | 42900 | 1 | 43435.78 | -535.78 | 98.7665 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to the pandemic | price review
447 | 6702503 | Subdivision infrastructure l 10 - lagoas / carvalhal | 45233252-0 | Surface work for streets | FALSE | 2020 | 2022 | Portugal | Grandola | Setúbal | 17 | 30 | 14-05-2020 | 02-03-2022 | 657 | 120 | 247017.95 | 226000 | 1 | 277746.36 | -51746.36 | 81.3692 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: THE AWARD WILL BE MADE ACCORDING TO THE CRITERIA OF THE ECONOMICALLY MOST ADVANTAGEOUS PROPOSAL Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to additional works (not foreseen and unpredictable) and the legal and graceful deadline extension | complementary works (not forecast and unpredictable) and negative price review
448 | 6697180 | Contract for the Execution of Technical Connections of the Sanitation Subsystems of Aguiar da Beira- Eirado Subsystem | 45232460-4 | Sanitary works | FALSE | 2019 | 2022 | Portugal | Aguiar da Beira | Guarda | 9 | 39 | 21-05-2020 | 08-06-2022 | 748 | 365 | 1500000 | 1082800 | 3 | 1026843.18 | 55956.82 | 105.4494 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the 51-day period. | resulting from suppressed work and work not carried out, as well as from the price review carried out.
449 | 6693496 | Conservation and restoration of the architectural complex of the monastery of santo andré de ancede - 3rd phase | 45454100-5 | Restoration work | FALSE | 2019 | 2022 | Portugal | Baião | Porto | 13 | 37 | 20-12-2019 | 21-07-2022 | 944 | 450 | 1835006.88 | 1666014.84 | 3 | 1666011.84 | 3 | 100.0002 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | 1st request for extension of term granted with limit 11/19/2021; 2nd request for extension of term granted with limit 12/31/2021; 3rd request for extension of term granted with limit 02/28/2022.; | 1,666,011.84 eur + vat - works on site; 97,570.37 eur - price review. total work = 1,763,582.21 eur + vat.
450 | 6678247 | Cpn 31/2020/dicp - t-47/2019 - rehabilitation of 13 de Maio street - lagoa - arrabal | 45232451-8 | Drainage and surface works | FALSE | 2020 | 2022 | Portugal | Leiria | Leiria | 10 | 21 | 08-06-2020 | 21-02-2022 | 623 | 180 | 662366.13 | 579975.75 | 2 | 579975.75 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work pursuant to article 365 b) "public procurement code" and graceful extension.
451 | 6670607 | Execution of an outdoor swimming pool for municipal public use in the parish of Tolosa | 45212212-5 | Construction work for swimming pool | FALSE | 2020 | 2022 | Portugal | Nisa | Portalegre | 12 | 30 | 05-06-2020 | 30-03-2022 | 663 | 365 | 863679.49 | 829305.88 | 2 | 852738.54 | -23432.66 | 97.2521 | Best value for money: No Criterion related to quality Name: lowest price Weighting: 100% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of definitive price revision indices. | price revision in the amount of €30,296.86
452 | 6667056 | Cp 06/2020 - extension and reinforcement of the water supply network in the parish of brito - municipality of guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 27-05-2020 | 18-01-2022 | 601 | 120 | 122000 | 109800 | 1 | 94587.37 | 15212.63 | 116.0832 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
453 | 6664890 | Network of Viewpoints - Construction and Requalification - Viewpoint of Casal de Loivos. | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2020 | 2022 | Portugal | Alijó | Vila Real | 19 | 15 | 01-06-2020 | 04-07-2022 | 763 | 365 | 376691.66 | 359269.29 | 2 | 419985.14 | -60715.85 | 85.5433 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | covid 19 and lack of material | project uncertainties
454 | 6662651 | EB Matosinhos - Contract repair of gym walls and infiltration in the multi-purpose park | 45450000-6 | Other building completion work | FALSE | 2020 | 2022 | Portugal | Matosinhos | Porto | 13 | 9 | 04-06-2020 | 22-02-2022 | 628 | 60 | 20800 | 15540.75 | 1 | 15150.38 | 390.37 | 102.5766 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
455 | 6651427 | Urban requalification of the housing area of ​​Colina do Sol and Avenida Nuno Simões in Pedras Salgadas | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 13-05-2020 | 15-06-2022 | 763 | 365 | 479362.36 | 453518.98 | 2 | 387750.91 | 65768.07 | 116.9614 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | project definitions. | job suppression and price revision.
456 | 6625176 | Empreitada Rotunda - intersection between Av. From the Marine Corps School, streetCapitães de Abril and streetHumberto Delgado. | 45233128-2 | Roundabout construction work | TRUE | 2020 | 2022 | Portugal | Barreiro | Setúbal | 17 | 20 | 03-04-2020 | 19-07-2022 | 837 | 150 | 300000 | 298445.71 | 2 | 320367.41 | -21921.7 | 93.1573 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
457 | 6622763 | Conservation, restoration and landscape architecture of the Real Fábrica do Gelo da Serra do Montejunto | 45454100-5 | Restoration work | FALSE | 2020 | 2022 | Portugal | Cadaval | Lisboa | 11 | 15 | 15-05-2020 | 21-02-2022 | 647 | 90 | 237500.25 | 234698.33 | 1 | 230369.88 | 4328.45 | 101.8789 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspensions | underwork
458 | 6618903 | Chaves and Segirei Hot Springs | 45112700-2 | Landscaping work | FALSE | 2020 | 2022 | Portugal | Chaves | Vila Real | 19 | 21 | 15-04-2020 | 31-03-2022 | 715 | 90 | 202063.81 | 189900 | 1 | 202865.87 | -12965.87 | 93.6086 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two extensions of 85 days, plus 60 days associated with complementary work and suspension of work for 341 days (due to adverse conditions, article 367 of the "public procurement code") | complementary works worth €14,460.38 and price revision -€1,494.51
459 | 6605686 | Requalification of streets in Paços de Brandão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 21-05-2020 | 06-01-2022 | 595 | 180 | 299861.88 | 267054.84 | 2 | 238273.32 | 28781.52 | 112.0792 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 37 days of legal extension (compl. work) 73 days of graceful extension 39 days when scheduling an inspection 75 days between the 1st inspection and the provisional reception for correcting deficiencies | complementary work and less
460 | 6588487 | Requalification of streetde Espiridião de Sousa - Oliveira do Douro | 45233140-2 | Roadworks | TRUE | 2019 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 18-05-2020 | 26-05-2022 | 738 | 120 | 320000 | 299217.07 | 2 | 313407.71 | -14190.64 | 95.4721 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two extensions of the deadline for carrying out the project were duly approved. | the completion of the project resulted in additional work worth €24,760.80, underwork worth €6,678.80 and a price review with final indices worth -€3,891.36.
461 | 6588304 | Network of pedestrian routes Sports Complex - Municipal Urban Park - 1st Phase | 45233140-2 | Roadworks | FALSE | 2019 | 2022 | Portugal | Lousada | Porto | 13 | 21 | 29-04-2020 | 12-08-2022 | 835 | 180 | 267805.05 | 264552.58 | 2 | 257262.84 | 7289.74 | 102.8336 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions: unavailability of land, installation of water supply pipe by another entity | additional work, underwork and price revisions
462 | 6588181 | Requalification/Improvement of Access to the Boassas Center | 45233142-6 | Road-repair works | FALSE | 2019 | 2022 | Portugal | Cinfães | Viseu | 20 | 18 | 18-02-2020 | 14-03-2022 | 755 | 365 | 415079.32 | 336745.66 | 2 | 361083.43 | -24337.77 | 93.2598 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price evaluation/Lowest cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of more works. | existence of extra work, underwork and price revisions.
463 | 6581669 | PRC_0239/2019_GAE-EB0428 - Extension of Wastewater Drainage Networks in the Parishes of São Gens, Estorãos and Vila Cova (Fafe) | 45232411-6 | Foul-water piping construction work | TRUE | 2020 | 2022 | Portugal | Fafe | Braga | 3 | 14 | 14-05-2020 | 31-05-2022 | 747 | 180 | 375000 | 358047.17 | 2 | 355144.02 | 2903.15 | 100.8175 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for extension due to the pandemic and suspension of work due to the need to study an alternative to the project | occasional errors in the project led to errors and omissions. underwork related to optimizing the solution for the flooring of the contract
464 | 6581062 | Contract for "Recovery, Enhancement and Refurbishment of Parque dos Marmelos and Riverside Bank of Ribeira de Cavalos" | 45212100-7 | Construction work of leisure facilities | FALSE | 2020 | 2022 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 19-05-2020 | 03-01-2022 | 594 | 270 | 820000 | 733640.35 | 2 | 716807.97 | 16832.38 | 102.3482 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension requests (covid 19 pandemic situation - constraints in forecasting the delivery of materials; adverse weather conditions - strong presence of water in the soil); request for partial suspension (groundwater flowing from the ground; covid 19 pandemic situation - constraints on the forecast delivery of materials); complementary works | underwork and additional work
465 | 6566722 | Construction of a belvedere with metal guardrails and pergola, execution of support walls in reinforced concrete and requalification of sidewalk berms, including drainage, public lighting and requalification | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Coimbra | Coimbra | 6 | 33 | 27-12-2019 | 26-01-2022 | 761 | 180 | 277365 | 246325.5 | 1 | 264279.2 | -17953.7 | 93.2065 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | legal extension of term associated with complementary work | value related to complementary work and price revision
466 | 6558738 | In particular, it consists of replacing damaged equipment, including disconnecting old equipment, supplying and installing new equipment in good condition | 45315100-9 | Electrical engineering installation works | FALSE | 2019 | 2022 | Portugal | Amadora | Lisboa | 11 | 31 | 05-05-2020 | 16-05-2022 | 741 | 560 | 181999.48 | 163799.54 | 1 | 174205.22 | -10405.68 | 94.0268 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | as a result of the covid19 pandemic, there were delays in the delivery of equipment, difficulties in transport and in the delivery of raw materials. there was also a lack of labour, difficulties in hiring workers, aggravated by the fact that many workers (work management included) were forced to isolate themselves, as they had contracted covid19. there were also constraints related to the opening hours of certain buildings, namely municipal schools, leading to certain works only being carried out at specific times. | due to the 1st provisional price review - €2,504.39; 2nd provisional price revision - €7,901.29
467 | 6545893 | Contract for "Enlargement of the Bensafrim Cemetery" | 45215400-1 | Cemetery works | FALSE | 2019 | 2022 | Portugal | Lagos | Faro | 8 | 34 | 27-04-2020 | 09-03-2022 | 681 | 240 | 250000 | 229960.52 | 1 | 246636.33 | -16675.81 | 93.2387 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Economically most advantageous proposal, as per article 74, paragraph 1 -b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for carrying out the project was extended, as a grace, for another 61 days, by order of mr. president of the chamber of 01/26/2021 | approval of complementary works in the global amount of €13,784.02, plus vat, in accordance with paragraphs 1 and 2 of article 370 of the public contracts code ("public procurement code"), approved by decree-law no. 18/2008, of january 29, as amended by decree-law no. 111-b/2017, of august 31. determined the final value of the price revision in the amount of €2,871.79, plus vat.
468 | 6541326 | CP 26/2019 - Reinforcement of the water supply network and extension of water supply networks and wastewater sanitation networks in the parishes of Infantas, Mesão Frio and UF de Serzedo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 23-03-2020 | 19-01-2022 | 667 | 150 | 264000 | 263890 | 2 | 248642.27 | 15247.73 | 106.1324 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
469 | 6536137 | Rehabilitation - Social Housing - Energy Efficiency - Bairro Per do Bom Retiro - Vila Franca de Xira | 45321000-3 | Thermal insulation work | FALSE | 2019 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 15 | 06-03-2020 | 18-01-2022 | 683 | 180 | 392000 | 373574.12 | 2 | 342206.66 | 31367.46 | 109.1662 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline deviation - covid19 | underwork and price revision.
470 | 6523578 | Rehabilitation of Avenida do Corgo - Arrifana | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-04-2020 | 06-01-2022 | 618 | 120 | 329325 | 329122.48 | 2 | 367071.98 | -37949.5 | 89.6616 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 149 days for deadline extensions, 33 days for contractor delay, 17 days for scheduling an inspection, 115 days for rectifying deficiencies between the 1st inspection and provisional acceptance | complementary and less approved works
471 | 6519361 | PO 322/2019 - Reconstruction and expansion of building for multifamily housing - street of Lira | 45211341-1 | Flats construction work | FALSE | 2020 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 16-04-2020 | 21-02-2022 | 676 | 365 | 298540 | 278160.42 | 2 | 313275.3 | -35114.88 | 88.791 | Best value for money: Yes Criterion related to quality Name: Valia Técnica (VT) Weighting: 50% Criterion related to cost Name: Price (P) Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the covid 19 pandemic, the projects did not have their normal pace in their development. | complementary works
472 | 6515427 | The object of the contract is namely the repair and requalification of the streets and respective surrounding areas located in the municipality of Amadora. | 45233200-1 | Various surface works | FALSE | 2020 | 2022 | Portugal | Amadora | Lisboa | 11 | 30 | 16-04-2020 | 26-01-2022 | 650 | 560 | 594330 | 534896.82 | 2 | 534896.82 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 3 the causes are due to: a) optimization/deployment of activities that led to the reduction of the term by 77 days; b) optimized scheduling of interactions with affected services; c) scheduling/priorities according to the pressing needs of the moment; complementarity / multidisciplinarity with other works.
473 | 6512458 | Conservation / Maintenance of Olhos da Fervença River Beach, by Contract: Casa do Guarda, Sanitary Installations, Pumping Well - CP-CCP-EMP n.º 06/2020 | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2020 | 2022 | Portugal | Cantanhede | Coimbra | 6 | 14 | 23-04-2020 | 04-02-2022 | 652 | 180 | 90000 | 88973.58 | 1 | 92004.13 | -3030.55 | 96.7061 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
474 | 6505771 | Contract for the execution of the infrastructures of the Allotment of S. Vicente Ferreira – 1st Phase, parish of S. Vicente Ferreira, municipality of Ponta Delgada | 45000000-7 | Construction work | FALSE | 2020 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 27 | 27-03-2020 | 07-04-2022 | 741 | 210 | 310000 | 306966.49 | 2 | 250946.64 | 56019.85 | 122.3234 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | supply of errors and omissions in the amount of €8,200.00 referring to the 1st amendment to the contract, underwork in the amount of €61,309.61, and negative price revision in the amount of €2,910.24
475 | 6500566 | Contract for the "Rehabilitation of Mercês Station". (EContracts No. 5010038626) | 45213320-2 | Construction work for buildings relating to railway transport | FALSE | 2019 | 2022 | Portugal | Sintra | Lisboa | 11 | 20 | 14-04-2020 | 26-04-2022 | 742 | 120 | 379000 | 378798 | 2 | 414599.16 | -35801.16 | 91.3649 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was necessary to carry out a set of work that forced to extend the deadline | it was necessary to execute an extra set of work that forced the price change
476 | 6499190 | Expansion of the Boa Fé Social Complex | 45215212-6 | Retirement home construction work | FALSE | 2019 | 2022 | Portugal | Elvas | Portalegre | 12 | 21 | 31-03-2020 | 28-06-2022 | 819 | 540 | 1100000 | 1048559.95 | 3 | 1151568.68 | -103008.73 | 91.0549 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous tender for the contracting authority. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | supply and installation of electric elevator. | complementary works
477 | 6496842 | Ciclovia - av. doctor Francisco Sá Carneiro - Santa Maria da Feira and S. João de Ver | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-04-2020 | 07-02-2022 | 661 | 180 | 312170 | 265220.28 | 2 | 264848.31 | 371.97 | 100.1404 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 21 days of legal extension 188 days of graceful extension, 76 days of delay in the conclusion of the projects by the contractor, 70 days in the correction of anomalies verified after the 1st inspection | additional work and underwork
478 | 6496273 | Landscaping of the Hospital Rotunda | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-04-2020 | 17-01-2022 | 641 | 60 | 89929 | 84941.66 | 1 | 76058.91 | 8882.75 | 111.6788 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 120 days extension, 102 days delay in completion of some landscaping related work | underwork
479 | 6489349 | Contract for "Infrastructures of the Municipal Allotment of Porto de Recreio" | 45432110-8 | Floor-laying work | FALSE | 2019 | 2022 | Portugal | Olhão | Faro | 8 | 30 | 29-11-2019 | 31-03-2022 | 853 | 300 | 720000 | 663954.8 | 2 | 640535.99 | 23418.81 | 103.6561 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extensions, resulting from delays for which the contractor is responsible. period suspensions due to the need for approval by the court of accounts; dpss approval; unavailability of land; unavailability of some materials on the market. | works suppressed by the client of the project, due to unaffected areas.
480 | 6486954 | Quality 100%- maintenance of the coastal walkways of Matosinhos 2019-2021 | 45240000-1 | Construction work for water projects | FALSE | 2019 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 14-04-2020 | 01-07-2022 | 808 | 720 | 179200 | 163420 | 1 | 163420 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
481 | 6483877 | Construction of the EB 2,3 Sports Pavilion Amadeo de Sousa-Cardozo | 45212225-9 | Sports hall construction work | FALSE | 2020 | 2022 | Portugal | Amarante | Porto | 13 | 9 | 30-03-2020 | 24-03-2022 | 724 | 360 | 932000 | 987853.5 | 2 | 1073198.97 | -85345.47 | 92.0476 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the project ended 3 days before the deadline | price review
482 | 6473244 | Valuing people: Education - Repairs to school buildings - Mosquito nets | 45421110-8 | Installation of door and window frames | FALSE | 2019 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 02-04-2020 | 21-06-2022 | 810 | 120 | 71000 | 66725.85 | 1 | 67919.58 | -1193.73 | 98.2424 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
483 | 6456727 | SPACE- Castelo de Vide Business Reception Space | 45453100-8 | Refurbishment work | FALSE | 2019 | 2022 | Portugal | Castelo de Vide | Portalegre | 12 | 21 | 13-03-2020 | 08-02-2022 | 697 | 400 | 1099159.12 | 1078180 | 3 | 1136957.45 | -58777.45 | 94.8303 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes | there were no changes
484 | 6456457 | Contract "Requalification and Refurbishment of the Yellow House for Research and Promotion Center of the Roman City of Bobadela - Conclusion" | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 26-03-2020 | 03-01-2022 | 648 | 270 | 349576 | 345240.29 | 2 | 338254.14 | 6986.15 | 102.0654 | Best value for money: No Criterion related to quality Name: N/A Weighting: 100% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | suspensions and extensions | complementary work and underwork
485 | 6453346 | Requalification of streetPrior João Gomes dos Santos and streetAntónio Dias Marques (Macinhata do Vouga) | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2022 | Portugal | Águeda | Aveiro | 1 | 21 | 10-02-2020 | 10-03-2022 | 759 | 90 | 128919.74 | 126920 | 1 | 139827.06 | -12907.06 | 90.7693 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the reasons for the changes in the deadline for carrying out the project were as follows: suspension of work due to adra carrying out the water supply networks; extension of work due to complementary work. | the execution of complementary works.
486 | 6424504 | Rehabilitation of the Public Space of the Riverside Historic Center of Arnelas - Olival | 45233140-2 | Roadworks | TRUE | 2019 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 11-03-2020 | 19-01-2022 | 679 | 270 | 611851.21 | 598108.17 | 2 | 666602.19 | -68494.02 | 89.7249 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | an extension of the deadline was duly authorized and after the completion of the project it was necessary for the contractor to correct anomalies in the project carried out, so the provisional acceptance notice was only drawn up on the date indicated. | the completion of the project resulted in additional work worth €59,139.30, underwork worth €207.50 and a provisional price review worth €9,562.22.
487 | 6422979 | Design and Execution of the Rehabilitation and Expansion of the Fairs and Exhibitions Park | 45453100-8 | Refurbishment work | FALSE | 2020 | 2022 | Portugal | Mogadouro | Bragança | 4 | 15 | 12-03-2020 | 30-08-2022 | 901 | 365 | 1250000 | 1144693.69 | 3 | 1286649.04 | -141955.35 | 88.967 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Economically Most Advantageous Proposal, Article 74.º, N.1, paragraph b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extensions and suspension based on information and decision-making about them, which are filed in the contract process. | execution of complementary work resulting from unforeseeable circumstances
488 | 6419222 | The object of this contract is the execution of all the preparatory work and accessories necessary for the execution of cleaning, conservation and improvement works | 45261900-3 | Roof repair and maintenance work | FALSE | 2019 | 2022 | Portugal | Amadora | Lisboa | 11 | 31 | 27-02-2020 | 29-03-2022 | 761 | 560 | 181971 | 163774 | 1 | 166567.22 | -2793.22 | 98.3231 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deviation was due to procedural delays in the invoicing and reception of the contract. | due to the provisional price revision in the amount of €2,793.22.
489 | 6411676 | Rehabilitation of the Sanctuary of Nossa Senhora do Cabo Espichel - Complementary works in the parking lot and Fenced in Horta | 45211360-0 | Urban development construction work | FALSE | 2019 | 2022 | Portugal | Sesimbra | Setúbal | 17 | 30 | 17-07-2019 | 24-03-2022 | 981 | 180 | 239160 | 238858.2 | 1 | 311245.48 | -72387.28 | 76.7427 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 180 days of initial execution period; 60 days of term extension, under the terms of art. a), paragraph 1, article 311 and al. b), of article 312 of the "public procurement code" and a 30-day extension of the deadline under the terms of article 374 of the "public procurement code". the communication of approval of the pss to the contractor occurred on 11/05/2019 and the end of the contract, considering the described deadline extensions, occurred on 08/01/2020. | more work, restoring financial balance, underwork and price revisions.
490 | 6409242 | Public tender for the rehabilitation works of social housing buildings at Quinta da Alâmpada - lot 24 to lot 28 - energy efficiency | 45453100-8 | Refurbishment work | FALSE | 2019 | 2022 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 24-02-2020 | 04-02-2022 | 711 | 100 | 219000 | 217479.34 | 1 | 229315.56 | -11836.22 | 94.8385 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal / execution period Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works.
491 | 6400909 | Cercal/cadaval pedestrian circuit: Chão de Sapo/Casual Cabreiro/Casais de Montejunto circuit | 45233161-5 | Footpath construction work | FALSE | 2020 | 2022 | Portugal | Cadaval | Lisboa | 11 | 14 | 06-03-2020 | 04-08-2022 | 881 | 90 | 338605.76 | 335319.02 | 2 | 297238.47 | 38080.55 | 112.8114 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place with some deviations from the deadline because the intervention area is included in the jurisdiction of infraestruturas de portugal and this entity did not issue the opinion in time. in addition to this factor, the covid-19 pandemic also contributed heavily to the delay, as many workers were affected; at the same time, the materials are also no longer available on the market due to the reduction in their production by some factories | complementary work, underwork (project measurement errors, adjustments with the implementation of the project in comparison with the existing and topographical conditions), price revision, contractual fine
492 | 6395550 | Requalification and expansion of the EB of Quintã | 45262800-9 | Building extension work | FALSE | 2019 | 2022 | Portugal | Vagos | Aveiro | 1 | 9 | 02-03-2020 | 24-06-2022 | 844 | 330 | 1100000 | 977392.39 | 2 | 968228.1 | 9164.29 | 100.9465 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | deadline originally planned: 07/06/2021. extensions (4) for a total of 209 days (covid-19 clearly affected and limited the project teams and consequently the normal course of work and also the lack of raw materials on the market and the consequent very long delivery period, of materials/equipment). effective deadline: 01/31/2022, with the partial provisional acceptance notice having been signed on 03/02/2022 (it should be noted that on this date the power of the electrical connection does not yet allow the connection of equipment installed for heating /cooling, chiller and hvac system, this part being subject to a subsequent inspection, as soon as possible, to verify the respective equipment). the partial provisional reception (final) is dated 11/04/2022. | complementary work resulting from unforeseen circumstances, underwork and final price revision.
493 | 6383345 | Contract for Public Works for Painting Pavements in the Municipality of Cascais (CP 028.DRU.DMEP.2019) | 45442100-8 | Painting work | FALSE | 2019 | 2022 | Portugal | Cascais | Lisboa | 11 | 15 | 18-02-2020 | 07-03-2022 | 748 | 730 | 200000 | 200000 | 1 | 199999.96 | 0.04 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect subject to competition Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the balance does not allow to carry out any work
494 | 6368488 | Wastewater from Jafafe (PAR 030) - Águeda | 45232460-4 | Sanitary works | TRUE | 2019 | 2022 | Portugal | Águeda | Aveiro | 1 | 48 | 24-02-2020 | 24-02-2022 | 731 | 365 | 1050000 | 820319.57 | 2 | 799309.07 | 21010.5 | 102.6286 | Best value for money: Yes Criterion related to quality Name: VALIA TÉCNICA Weighting: 45% Criterion related to cost Name: PRICE Weighting: 55% | 1 | 55 | 5 | TRUE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
495 | 6365374 | Design and execution of the Interpretive Center of the Mining Area of ​​Jales | 45210000-2 | Building construction work | FALSE | 2019 | 2022 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 23 | 26-02-2020 | 18-02-2022 | 723 | 270 | 598396.46 | 597931.39 | 2 | 597931.39 | 0 | 100 | Best value for money: No Criterion related to quality Name: .... Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid 19 pandemic.
496 | 6365069 | Vila Cã School Center - Proc. No. 64/2019 | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2022 | Portugal | Pombal | Leiria | 10 | 30 | 27-01-2020 | 26-04-2022 | 820 | 450 | 1398692.7 | 1370000 | 3 | 1458163.76 | -88163.76 | 93.9538 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the partial provisional acceptance notice was drawn up on september 10, 2021, with the result of this inspection that some works were not received, as they were not in a position to be received, as well as the failure to deliver the waste plan, as such they were 60 days are granted for rectification and completion of works not received. the final provisional acceptance notice was issued on november 23, 2021, the date on which all work not received in the partial provisional acceptance notice was completed and the correct execution of the prevention and management plan for construction and demolition waste was verified. | existence of complementary work, underwork and price revision value.
497 | 6363341 | Temporary incubator for new companies in the Economic Activities Zone of the municipality of Nisa - Structure to support the start-up of activities for economic agents. | 45213000-3 | Construction work for commercial buildings, warehouses and industrial buildings, buildings relating to transport | FALSE | 2019 | 2022 | Portugal | Nisa | Portalegre | 12 | 30 | 03-02-2020 | 06-01-2022 | 703 | 300 | 872442.36 | 849033.11 | 2 | 872885.07 | -23851.96 | 97.2675 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of definitive price revision indices. | definitive price revision in the amount of €23,851.96.
498 | 6358882 | The object of the contract is the requalification of streetCarvalho Araújo/streetHeróis de Dadrá/Avenida Padre Himalia and surroundings. | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Amadora | Lisboa | 11 | 31 | 18-02-2020 | 25-02-2022 | 738 | 150 | 424178 | 381760.21 | 2 | 381760.21 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - multiplicity of interactions with the affected services; - delay by the contractor in delivering the "plan for the prevention and management of construction and demolition waste"; - several constraints related to the pandemic and the state of emergency; - delays in the supply of materials due to the pandemic.
499 | 6310489 | Rehabilitation of public space in the urban park on the street of Vale de Cambra | 45112700-2 | Landscaping work | FALSE | 2019 | 2022 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 11-12-2019 | 28-01-2022 | 779 | 90 | 115000 | 104000 | 1 | 104000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climatic conditions for plantations.
500 | 6290370 | Contract for Requalification of the Sculpture Pavilion and Construction of the New Connection Building at FBAUP | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2022 | Portugal | Porto | Porto | 13 | 48 | 24-10-2019 | 06-05-2022 | 925 | 540 | 2142400 | 2033482.1 | 3 | 2116480.93 | -82998.83 | 96.0785 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Proposed global price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the date of 07/30/2021 was scheduled with the contractor for the provisional reception of the project. | resulting from increases and decreases, communicated
501 | 6288636 | Expansion and Reconversion of the Occupational Activities Center - CAO Solidário | 45215200-9 | Construction work for social services buildings | FALSE | 2019 | 2022 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 16-12-2019 | 27-01-2022 | 773 | 609 | 1200000 | 1149992.57 | 3 | 1488635.65 | -338643.08 | 77.2514 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A |  | complementary work
502 | 6276867 | PO 311/2019 - Expansion of the sanitation network to Tabaçô (Outeiro do Fojo/ Cova do Ouro), Guilhadeses (Cadorcas) and Prozelo (Gontilhe) | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 29-01-2020 | 17-02-2022 | 750 | 300 | 315000 | 274923.36 | 2 | 274923.36 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
503 | 6266259 | S.e.c. - Procº nº 130/A1/19 - Public Tender for the contract for the "Water Distribution Network in the Parishes of Deocriste, Deão, Portela Susã and Nogueira | 45232421-9 | Sewage treatment works | TRUE | 2019 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 5 | 28-01-2020 | 27-05-2022 | 850 | 180 | 1881954.49 | 233115.64 | 1 | 230606.8 | 2508.84 | 101.0879 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | epidemiological situation and difficulty in delivering materials. | underwork.
504 | 6265637 | Remodeling of the Meirinhos Water and Sanitation Network | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Mogadouro | Bragança | 4 | 30 | 10-01-2020 | 10-03-2022 | 790 | 300 | 808100.31 | 610455.46 | 2 | 610455.46 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the supply of raw materials
505 | 6264870 | Construction of a BMX sports track in Campos do Bolão, including, in addition to earthmoving and paving work, the placement of various infrastructure networks | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Coimbra | Coimbra | 6 | 33 | 10-10-2019 | 04-02-2022 | 848 | 180 | 286507 | 283149.37 | 2 | 288947.08 | -5797.71 | 97.9935 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions that were felt at the end of 2019 and beginning of 2020, which caused a high moisture content in the soil, preventing the execution of earthworks. | value of complementary works and price revision
506 | 6261562 | Public tender for awarding the contract for "Expansion of the South Bank Wastewater Network - Mujães, Vila de Punhe, Barroselas/ Mujães and Castelo de Neiva" | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 4 | 28-01-2020 | 18-02-2022 | 752 | 210 | 713719.31 | 215339.69 | 1 | 201330.54 | 14009.15 | 106.9583 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions and measures imposed by covid-19. | underwork
507 | 6261501 | Public tender for awarding the contract for "Expansion of the South Bank Wastewater Network - Mujães, Vila de Punhe, Barroselas/ Mujães and Castelo de Neiva" | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2022 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 4 | 28-01-2020 | 03-06-2022 | 857 | 300 | 713719.31 | 400363.42 | 2 | 344302.45 | 56060.97 | 116.2825 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | covid-19 measures and bad weather conditions | underwork.
508 | 6256130 | Requalification of Ruas Joaquim António de Aguiar, street of Sequeiro and streets aro Negrão, in Cantanhede, by Contract - CP-CCP-EMP n.º 10/2019 | 45113000-2 | Siteworks | FALSE | 2019 | 2022 | Portugal | Cantanhede | Coimbra | 6 | 31 | 27-01-2020 | 03-01-2022 | 707 | 330 | 504716.9 | 494500.02 | 2 | 547827.24 | -53327.22 | 90.2657 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works and underwork.
509 | 6247854 | Accessibility and Sustainable Urban Mobility Plan - Campo Meão Cycle Path | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Alijó | Vila Real | 19 | 14 | 10-01-2020 | 31-01-2022 | 752 | 366 | 462619 | 458489 | 2 | 482489 | -24000 | 95.0258 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a change in the deadlines due to the prior visa of the court of auditors and due to the covid 19 pandemic | with the development of the project, it was identified that due to the bad weather that was felt last winter, in rua de santa bárbara in favaios, two support walls to the road underwent changes. one of the walls has collapsed and the other is at risk of collapsing, thus making it impossible to build a cycle path in this section.
510 | 6246508 | Contract for the construction of six health units in Lisbon | 45000000-7 | Construction work | FALSE | 2019 | 2022 | Portugal | Lisboa | Lisboa | 11 | 45 | 31-10-2019 | 01-04-2022 | 883 | 450 | 13738476 | 1657827.03 | 3 | 1743947.21 | -86120.18 | 95.0618 | Best value for money: Yes Criterion related to quality Name: Experience Technical Team/Technical Value of Proposals Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | TRUE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | in view of the pandemic situation that the country has been through, and even with periods of confinement, the present work has always been carried out in such a way that this fact does not cause strong impacts on the development of the projects, thus contradicting the general state of the country. in the present contract, only the delay in the supply of the elevator, by the subcontractor, of more than 9 months from the date of delivery of the contract signed by the contractor, was due to logistical delays caused by the pandemic. | the change in the contractual value of the contract was due to the need to issue several complementary works in order to eliminate errors and omissions in the execution project. they were duly framed in accordance with the legislation in force and submitted to the court of auditors for appreciation.
511 | 6239192 | Rehabilitation of Drainage Networks | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2022 | Portugal | Almada | Setúbal | 17 | 20 | 11-10-2018 | 21-02-2022 | 1229 | 800 | 228000 | 225958.09 | 1 | 127574.45 | 98383.64 | 177.1186 | Best value for money: Yes Criterion related to quality Name: technical value Weighting: 60% Criterion related to cost name: price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | this contract was intended to carry out specific works in drainage networks, as they were requested, given the needs of the service. at the end of the execution period defined in the contract, the accumulated value of the requested works fell short of the contractual value, and the contract was terminated due to the end of the execution period.
512 | 6235005 | 100% Quality - Paving repair on R. Godinho Faria and R. Silva earring | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 20-01-2020 | 27-01-2022 | 738 | 120 | 230000 | 148072.55 | 1 | 162808.95 | -14736.4 | 90.9487 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
513 | 6212933 | Contract for "Requalification of Public Lighting on Avenida dos Pescadores - Vila da Luz" | 45231400-9 | Construction work for electricity power lines | FALSE | 2019 | 2022 | Portugal | Lagos | Faro | 8 | 30 | 13-01-2020 | 07-03-2022 | 784 | 90 | 160000 | 148313.5 | 1 | 150623.93 | -2310.43 | 98.4661 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1 - b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in compliance with the order of mr. president of 05/05/2020, the project was extended for another 60 days, as a grace | calculated as the final value of the price revision the amount of € 2,310.43, plus vat
514 | 6205192 | Pumping System, Domestic Wastewater Drainage Network and Complement of the Rainwater Drainage Network of street of Igreja Velha, crossstreet of Igreja Velha and street ofs Valhelhas | 45232400-6 | Sewer construction work | FALSE | 2019 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 27-12-2019 | 26-05-2022 | 881 | 300 | 405000 | 349049.02 | 2 | 349527.88 | -478.86 | 99.863 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract ended on the scheduled date, the provisional reception was only carried out on 11/10/2020. | price review
515 | 6197020 | The work includes the replacement of existing road pavements, reformulation/rehabilitation of electricity, telephone, rainwater and other infrastructure networks. | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2022 | Portugal | Valongo | Porto | 13 | 21 | 08-01-2020 | 03-06-2022 | 877 | 360 | 1260000 | 1071000 | 3 | 1068747.12 | 2252.88 | 100.2108 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension 50 days (deadline for carrying out additional work) 30 + 20 days - 2nd + 3rd additional contracts. extension of the execution period - 45 days. | additional work - €174,309.60 underwork - €235,245.68 price revision (provisional and definitive calculations) = €58,683.20
516 | 6163138 | 2019/27 - DEM - AC installation at Sylvia Philips school, Oeiras Animal Collection Centre, Marquês de Pombal Palace Press (Informatics) and Atrium Building | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 11-12-2019 | 05-04-2022 | 846 | 60 | 88247.13 | 76893.98 | 1 | 76893.98 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
517 | 6162587 | Renovation of the Green Structure of Largo da Fonte | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2022 | Portugal | Sabugal | Guarda | 9 | 30 | 26-12-2019 | 06-06-2022 | 893 | 240 | 942355.58 | 842412.77 | 2 | 904561.15 | -62148.38 | 93.1294 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions | complementary work and less
518 | 6162066 | 2019/174 - DGEP - Requalification of the walkways in Jardim da Outurela, Carnaxide | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 21 | 27-12-2019 | 09-02-2022 | 775 | 60 | 52920 | 49850 | 1 | 49850 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
519 | 6131434 | Construction of a roundabout at the intersection between Avenida 5 de Outubro and streetDr. Cândido Guerreiro and streetDr. José de Matos in Faro | 45233128-2 | Roundabout construction work | FALSE | 2019 | 2022 | Portugal | Faro | Faro | 8 | 20 | 16-12-2019 | 13-07-2022 | 940 | 90 | 161516.47 | 139368.09 | 1 | 148054.82 | -8686.73 | 94.1328 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
520 | 6117941 | 2019/44 - DGEP - Repaving of Adolfo Casais Monteiro and Américo Cortez Pinto streets , Carnaxide | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 45 | 12-12-2019 | 20-05-2022 | 890 | 45 | 130250 | 99242.88 | 1 | 101784.84 | -2541.96 | 97.5026 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
521 | 6117929 | 2019/167 - DGEP - Conservation and repair of pavements in Carnaxide and Caxias. | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 12-12-2019 | 16-05-2022 | 886 | 365 | 282350 | 250885.9 | 2 | 250885.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
522 | 6114831 | Sewerage network, pumping station and paving of the caleijas path, in nave de har" | 45232440-8 | Construction work for sewage pipes | FALSE | 2019 | 2022 | Portugal | Almeida | Guarda | 9 | 18 | 29-11-2019 | 09-05-2022 | 892 | 270 | 91469.7 | 68763.35 | 1 | 81768.22 | -13004.87 | 84.0954 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal in the modality provided for in paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work and legal extension | additional work and underwork
523 | 6099310 | Essentially, the task involves redesigning the plant material structure, globally unifying the entire space by creating routes and homogenizing the floors | 45112712-9 | Landscaping work for gardens | FALSE | 2019 | 2022 | Portugal | Benavente | Santarém | 16 | 30 | 09-09-2019 | 26-07-2022 | 1051 | 480 | 1250000 | 1185000.06 | 3 | 1221133.67 | -36133.61 | 97.041 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of the project and extension of the deadline for the execution of the complementary works. | the value of the complementary works and the value of the price revision must be added to the value of the award, the value of the underwork must be deducted.
524 | 6081468 | Rehabilitation of the Macedo de Cavaleiros National Guard barracks | 45216111-5 | Police station construction work | FALSE | 2019 | 2022 | Portugal | Macedo de Cavaleiros | Bragança | 4 | 12 | 28-11-2019 | 10-02-2022 | 805 | 360 | 660684.59 | 634010.91 | 2 | 670424.49 | -36413.58 | 94.5686 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the deadline for causes attributable to the contractor | complementary works.
525 | 6080321 | Contract for the rehabilitation of 4 social housing units in Bairro 1º de Maio in Tomar | 45453100-8 | Refurbishment work | TRUE | 2019 | 2022 | Portugal | Tomar | Santarém | 16 | 36 | 21-11-2019 | 28-01-2022 | 799 | 365 | 175038 | 171990.77 | 1 | 174975.73 | -2984.96 | 98.2941 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic, with interference in the normal functioning of companies and adverse weather conditions | price revision / decreases due to work not performed and measurement errors
526 | 6072859 | Quality 100% - Public tender for paving sidewalks 2019 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 27-11-2019 | 27-01-2022 | 792 | 45 | 399760 | 94125 | 1 | 94125 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
527 | 6069692 | Remonde Bridge Replacement | 45000000-7 | Construction work | FALSE | 2019 | 2022 | Portugal | Viseu | Viseu | 20 | 6 | 14-08-2019 | 14-03-2022 | 943 | 28 | 17650 | 17318 | 1 | 14069.5 | 3248.5 | 123.089 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reanalysis of the project considering that the accesses of the owners who were not protected | underwork
528 | 6064756 | Cp 28/2018 - extension of wastewater drainage networks in the parishes of caldelas and sande s. martinho - guimaraes | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 02-04-2019 | 07-03-2022 | 1070 | 90 | 126000 | 112938.36 | 1 | 80812.28 | 32126.08 | 139.754 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
529 | 6060145 | Improvement and rectification of streetNova - Pardelhas - Fafe | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2022 | Portugal | Fafe | Braga | 3 | 30 | 21-11-2019 | 14-07-2022 | 966 | 180 | 306863.6 | 294023.98 | 2 | 294022.41 | 1.57 | 100.0005 | Best value for money: Yes Criterion related to quality Name: Technical value and guarantee of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a partial suspension of work for 170 days | there were no changes to the value of the project
530 | 6058059 | Cp 16/2018 – extension of the water supply network in the sanctuary of penha – parish of costa e infantas - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2022 | Portugal | Guimarães | Braga | 3 | 14 | 23-10-2018 | 16-05-2022 | 1301 | 150 | 319250 | 302125.03 | 2 | 242266.56 | 59858.47 | 124.7077 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
531 | 6041747 | PRC_0246/2019_GAE-AA0441 - Water Supply to Celorico de Basto - 1st Phase | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2019 | 2022 | Portugal | Celorico de Basto | Braga | 3 | 47 | 18-11-2019 | 01-04-2022 | 865 | 720 | 4900000 | 2684319.83 | 3 | 2726094.68 | -41774.85 | 98.4676 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | TRUE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | contract term not reached | alteration of layout between profiles p813 and p0826 parish of s. clemente and between profiles p039 and p87 parish of veade, celorico de basto to which works correspond unless they revert in full to the client.
532 | 6041732 | PRC_0246/2019_GAE-AA0441 - Water Supply to Celorico de Basto - 1st Phase | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2019 | 2022 | Portugal | Celorico de Basto | Braga | 3 | 47 | 18-11-2019 | 24-01-2022 | 798 | 720 | 4900000 | 2188366.5 | 3 | 2342882.59 | -154516.09 | 93.4049 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | TRUE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | contractual term not reached | route change between profiles p195 and p218, on rua de sta. maria, parish of bucos (zona de casares), in the municipality of cabeceiras de bastos, with a cost of €64,580.76 per manifest public interest
533 | 6039895 | Refurbishment works on the building of the former José Gomes Ferreira School for the installation of Pole III of Teatro Municipal do Porto | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2022 | Portugal | Porto | Porto | 13 | 25 | 19-11-2019 | 21-02-2022 | 825 | 170 | 755000 | 685275.59 | 2 | 732662.15 | -47386.56 | 93.5323 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had three extensions of time, however, due to the fact that the new completion date was not met, the performing entity was subject to the application of a pecuniary contractual penalty. the contract was carried out with the required quality, in safe conditions and the necessary actions were implemented in order to minimize the environmental impact of the contract. | complementary work and unforeseen work.
534 | 6038862 | Carmen Miranda Museum - Marco de Canaveses | 45212313-3 | Museum construction work | FALSE | 2019 | 2022 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 12-11-2019 | 26-05-2022 | 926 | 540 | 1026891.35 | 1017462.2 | 3 | 1089189.34 | -71727.14 | 93.4146 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension and suspension. | complementary work, underwork, price revision.
535 | 6037550 | Construction of Service Areas for Motorhomes in the Municipality of Alandroal (Alandroal, Aldeia da Venda and Terena) | 45223700-3 | Service area construction work | FALSE | 2019 | 2022 | Portugal | Alandroal | Évora | 7 | 21 | 11-11-2019 | 27-05-2022 | 928 | 120 | 75563 | 74921.05 | 1 | 71291.67 | 3629.38 | 105.0909 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | stock changes and difficulty in acquiring materials and equipment - covid 19 | topographical checks that involved a larger area of ​​bituminous start-up and new paving (asa alandroal). ip pole (asa alandroal). trench for rainwater drainage (asa sale). pricing review.
536 | 6025398 | This intervention provides for the improvement of the energy efficiency of the Gavião Covered Swimming Pool, including the installation of a centralized collective solar thermal system and a photovoltaic solar system | 45262700-8 | Building alteration work | FALSE | 2019 | 2022 | Portugal | Gavião | Portalegre | 12 | 30 | 06-11-2019 | 17-03-2022 | 862 | 270 | 672344.92 | 648172.71 | 2 | 648172.71 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were extensions of the execution period which in total accounted for 247 days. | there were no changes to the value of the project
537 | 6022362 | Contract for "Rehabilitation of the Filter Feeding Channels and Filtered Water Channels of Line I of the Asseiceira ETA" | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2022 | Portugal | Tomar | Santarém | 16 | 60 | 10-10-2019 | 20-04-2022 | 923 | 270 | 770000 | 516452 | 2 | 555472.79 | -39020.79 | 92.9752 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended due to existing constraints on the operation of the supply system caused by an epidemiological outbreak (covid-19), as well as the expected increase in water consumption (between may and september), and it was only possible to resume work in november. | changes in the value of the project resulting from compensation paid to the contractor due to the dismantling and assembly of the shipyard during the period of suspension of the project, as well as the price review carried out.
538 | 6020415 | Rehabilitation of buildings in the S. Francisco de Assis | 45211000-9 | Construction work for multi-dwelling buildings and individual houses | FALSE | 2019 | 2022 | Portugal | Macedo de Cavaleiros | Bragança | 4 | 20 | 11-11-2019 | 08-04-2022 | 879 | 300 | 1421255.2 | 740079.28 | 2 | 745848.03 | -5768.75 | 99.2266 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | constraints due to the covid-19 pandemic and delays in the delivery of materials. | no work was carried out on a house that ceased to be owned by the municipality.
539 | 6006076 | Construction contract for the connection to the Morgavel water supply system of the Alqueva Multipurpose Project | 45232120-9 | Irrigation works | FALSE | 2018 | 2022 | Portugal | Santiago do Cacém | Beja | 2 | 40 | 24-10-2019 | 04-03-2022 | 862 | 395 | 11500000 | 9597947.44 | 3 | 9192859 | 405088.44 | 104.4066 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of works that conditioned the critical path of the project and the partial suspension of work on the main pipeline due to environmental constraints. intersection of the irrigation pipe in section 4 (pk3+000 to pk4+120) – figueiras area; crossing the river sado; presence of protected bird species (bee-eaters and red herons)”. | underwork and amounts of work less than quantities estimated in the project.
540 | 6001819 | Improvement and Conservation of Other Basic Education Buildings (CE de Carnide) - Proc. No. 47/2019 | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2022 | Portugal | Pombal | Leiria | 10 | 21 | 09-10-2019 | 05-01-2022 | 819 | 150 | 163254.8 | 159217.68 | 1 | 160089.58 | -871.9 | 99.4554 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | emergence of the covid-19 pandemic | underwork
541 | 5990049 | EMP-R/10/2019 - Supply and Installation of 7 lifts in Bairro da Nazaré III, street of EUA - blocks 153, 155, 160, 162, 164, 166 and 168 – Funchal | 45313100-5 | Lift installation work | FALSE | 2019 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 14 | 20-09-2019 | 07-01-2022 | 840 | 150 | 175000 | 159453.01 | 1 | 159453.01 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays due to the pandemic.
542 | 5990041 | EMP-R/9/2019 - Supply and Installation of 6 lifts in Bairro da Nazaré III, street of Venezuela - blocks 36, 38, 40, 42 and 46 and street of Brasil - block 76 - Funchal | 45313100-5 | Lift installation work | FALSE | 2019 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 14 | 28-08-2019 | 11-02-2022 | 898 | 150 | 150000 | 148325 | 1 | 148325 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays due to the pandemic.
543 | 5990037 | EMP-R/8/2019 - Supply and Installation of 6 lifts in Bairro da Nazaré I and V, street of Venezuela - blocks 2, 4, 6, 10 and 12 and street of Brasil - block 19 - Funchal | 45313100-5 | Lift installation work | FALSE | 2019 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 14 | 02-09-2019 | 14-02-2022 | 896 | 150 | 150000 | 148325 | 1 | 148325 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays due to the pandemic.
544 | 5988312 | Requalification of the Mário Duarte Stadium Zone | 45111100-9 | Demolition work | FALSE | 2019 | 2022 | Portugal | Aveiro | Aveiro | 1 | 21 | 25-10-2019 | 13-01-2022 | 811 | 120 | 631990 | 379145.31 | 2 | 391628.84 | -12483.53 | 96.8124 | Best value for money: Yes Criterion related to quality Name: Technical Value Weighting: 15% Criterion related to cost name: price Weighting: 85% | 1 | 85 | 5 | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspensions and additional work | complementary work
545 | 5977000 | Aljustrel Mining Park Reception Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2019 | 2022 | Portugal | Aljustrel | Beja | 2 | 21 | 24-10-2019 | 01-07-2022 | 981 | 540 | 1192000 | 1150000 | 3 | 1246722.56 | -96722.56 | 92.2419 | Best value for money: Yes Criterion related to quality Name: - Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the continuity of the pandemic situation, which created a lot of difficulties with the projectforce for the contract and delays in the supply of some materials to suppliers, an extension of the deadline for 60 days was requested and granted | calculation of the definitive price revision
546 | 5956372 | Contract for "Execution of the urban requalification of the Historic Center of Benavente - Peripheral car park" | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2022 | Portugal | Benavente | Santarém | 16 | 14 | 25-09-2019 | 24-01-2022 | 852 | 240 | 336000 | 330932.41 | 2 | 331704.7 | -772.29 | 99.7672 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | considering the state of emergency, the design and final specifications of the roundabout, difficulties in the strict definition regarding the electrical network, there was a need to extend the period of execution of the project. | the final value of the project was altered in relation to the initially awarded due to errors and omissions in the project arising in the execution phase
547 | 5909545 | Construction contract for the Hydraulic Circuit of Évora and the Irrigation Block | 45240000-1 | Construction work for water projects | FALSE | 2018 | 2022 | Portugal | Évora | Évora | 7 | 14 | 30-09-2019 | 14-02-2022 | 868 | 485 | 13350000 | 11995964.79 | 3 | 12233327.25 | -237362.46 | 98.0597 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 26 | N/A | N/A | N/A | N/A | N/A | N/A | execution of work to correct errors and omissions that conditioned the critical path of the project and caused loss of income, as well as some cases of force majeure related to bad weather | need to carry out work to correct errors and omissions related, essentially, to amounts of work greater than the amounts estimated in the project.
548 | 5907774 | E201804 - Expansion of the Industrial Zone of Campia | 45211360-0 | Urban development construction work | FALSE | 2019 | 2022 | Portugal | Vouzela | Viseu | 20 | 21 | 25-09-2019 | 11-02-2022 | 870 | 365 | 910000 | 899722.57 | 2 | 862160.22 | 37562.35 | 104.3568 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the change in the execution period resulted from a partial suspension of the period. | due to underwork.
549 | 5896852 | PO 296/2019 - Expansion of the water supply network - distribution network to the places of Gração and Vilarinho do Souto - Subsystem of S. Jorge - Lots 1 and 2 | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 12 | 02-10-2019 | 10-01-2022 | 831 | 365 | 644338 | 290078.31 | 2 | 285136.52 | 4941.79 | 101.7331 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A |  | works not performed
550 | 5895428 | Repaving of EM 520-2 | 45432110-8 | Floor-laying work | TRUE | 2019 | 2022 | Portugal | Faro | Faro | 8 | 14 | 01-10-2019 | 04-04-2022 | 916 | 90 | 377020 | 349385.8 | 2 | 349385.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work suspension
551 | 5892939 | PO 296/2019 - Expansion of the water supply network - distribution network to the places of Gração and Vilarinho do Souto - Subsystem of S. Jorge - Lots 1 and 2 | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 12 | 30-09-2019 | 10-01-2022 | 833 | 365 | 644338 | 218970.05 | 1 | 204879.99 | 14090.06 | 106.8772 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A |  | works not performed
552 | 5879842 | 100% Quality - Rehabilitation of the cube pavement of R. Do Senhor, Senhora da Hora - 1st Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 15 | 10-09-2019 | 22-03-2022 | 924 | 40 | 40900 | 26221 | 1 | 26221 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
553 | 5870049 | 1-Emp/19 - Contract for the conservation and improvement of the road network in the Municipality of Tavira - Municipal Roads in the Parish of Conceição and Cabanas de Tavira | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 20-09-2019 | 21-01-2022 | 854 | 120 | 1396232.57 | 54957.15 | 1 | 54415.96 | 541.19 | 100.9945 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extensions, deadline suspension and delivery of the technical compilation. | definitive price review
554 | 5869993 | 1-Emp/19 - Contract for the conservation and improvement of the road network in the Municipality of Tavira - Municipal Roads in the Parish of Conceição and Cabanas de Tavira | 45233220-7 | Surface work for roads | FALSE | 2019 | 2022 | Portugal | Tavira | Faro | 8 | 24 | 20-09-2019 | 24-01-2022 | 857 | 120 | 1396232.57 | 962100.52 | 2 | 943436.85 | 18663.67 | 101.9783 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 40% Criterion related to cost Name: Proposal Price (PV) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | term extensions, suspension and delivery of the technical compilation. | definitive pricing revision.
555 | 5867728 | CP 04/2019_DEGA - Wastewater from Ouca (PAR 011) - Vacant | 45232460-4 | Sanitary works | TRUE | 2019 | 2022 | Portugal | Vagos | Aveiro | 1 | 42 | 20-08-2019 | 31-01-2022 | 895 | 365 | 1400000 | 1096412.25 | 3 | 1083962.45 | 12449.8 | 101.1485 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A
556 | 5864760 | The present contract comprises the execution works of: - landscape architecture (floors, vegetation, signage and urban furniture); - irrigation network; - stability; | 45112700-2 | Landscaping work | FALSE | 2019 | 2022 | Portugal | Barreiro | Setúbal | 17 | 20 | 11-09-2019 | 04-05-2022 | 966 | 180 | 1250000 | 1087133.62 | 3 | 1143783.03 | -56649.41 | 95.0472 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work and covid | complementary work and less
557 | 5859454 | Requalification of the municipal stadium in the city park - Lavandeira | 45236119-7 | Repair work on sports fields | TRUE | 2019 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 14 | 09-09-2019 | 14-02-2022 | 889 | 45 | 318500 | 302704.18 | 2 | 262933.43 | 39770.75 | 115.1258 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 3 work suspension notices were duly authorised. | the completion of the project resulted in underwork to the value of €39,997.80 and a price review was determined with definitive indices worth €227.10.
558 | 5852445 | Improvement of the high Sobreiro road-cm1076 | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2022 | Portugal | Grandola | Setúbal | 17 | 15 | 12-07-2019 | 29-04-2022 | 1022 | 395 | 1886586.23 | 1255541.72 | 3 | 1278325.98 | -22784.26 | 98.2176 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | suspension due to covid | complementary work and work unless
559 | 5847945 | The contract essentially concerns the execution of road infrastructure (bike path), signaling, rainwater drainage, as well as the application of plant material and urban furniture | 45233162-2 | Cycle path construction work | FALSE | 2019 | 2022 | Portugal | Benavente | Santarém | 16 | 30 | 09-09-2019 | 09-05-2022 | 973 | 270 | 351000 | 349400.01 | 2 | 374938.34 | -25538.33 | 93.1887 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | arise from the extension of the execution period. | arises from complementary work and price review
560 | 5842660 | Phase 2 of the Business Center - Construction of Hangars A and B | 45213351-8 | Maintenance hangar construction work | FALSE | 2019 | 2022 | Portugal | Ponte de Sor | Portalegre | 12 | 30 | 13-09-2019 | 30-05-2022 | 990 | 365 | 2287659.31 | 2217218.51 | 3 | 2220504.29 | -3285.78 | 99.852 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | price review
561 | 5841727 | Rio ul urban park – landscaping alteration project | 45112700-2 | Landscaping work | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 15 | 02-07-2019 | 10-01-2022 | 923 | 90 | 100000 | 99700 | 1 | 99700 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | floods in river
562 | 5840998 | Contracts for maintenance dredging of the ports of Peniche and Lagos, comprising Lot 1 (Dredging maintenance of the Port of Peniche), whose base price is EUR 643 875.00 + VAT | 45252124-3 | Dredging and pumping works | FALSE | 2019 | 2022 | Portugal | Peniche | Leiria | 10 | 11 | 12-09-2019 | 07-03-2022 | 907 | 75 | 978950 | 465600 | 2 | 510575 | -44975 | 91.1913 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | additional contract.
563 | 5828838 | Requalification of the synthetic turf at the Penha Football Field | 45112720-8 | Landscaping work for sports grounds and recreational areas | TRUE | 2019 | 2022 | Portugal | Faro | Faro | 8 | 20 | 09-09-2019 | 15-07-2022 | 1040 | 90 | 149570 | 136393 | 1 | 144576.58 | -8183.58 | 94.3396 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
564 | 5821825 | Requalification of the Fire Station Building | 45262700-8 | Building alteration work | FALSE | 2019 | 2022 | Portugal | Mação | Santarém | 16 | 7 | 03-09-2019 | 21-02-2022 | 902 | 270 | 721972.08 | 721971.06 | 2 | 882424.74 | -160453.68 | 81.8167 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project and complementary works | underwork, additional work and price revisions
565 | 5815353 | Contract for Rehabilitation of Buildings and Implementation of Urban Vegetable Gardens in the Social Neighborhood João Rodrigues Lagos | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2022 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 03-09-2019 | 21-04-2022 | 961 | 450 | 320000 | 307322.22 | 2 | 359952.55 | -52630.33 | 85.3785 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of suspensions and extensions | existence of complementary work and underwork
566 | 5814257 | P021/2019 - Requalification of the former elementary school for a Health Center (UCS Olival) | 45215100-8 | Construction work for buildings relating to health | FALSE | 2019 | 2022 | Portugal | Ourém | Santarém | 16 | 3 | 05-07-2019 | 04-04-2022 | 1004 | 240 | 325057.44 | 309900 | 2 | 323202.08 | -13302.08 | 95.8843 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | extensions/suspensions | complementary works; underwork and price revision
567 | 5812392 | P020/2019 - Requalification of the Old JI for the Extension of the Health Center (UCS Alburitel) | 45215100-8 | Construction work for buildings relating to health | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 3 | 05-07-2019 | 04-04-2022 | 1004 | 180 | 228132.19 | 222500 | 1 | 219605.34 | 2894.66 | 101.3181 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions | underwork and price revision
568 | 5811008 | 2018/182 - DCAD - Miscellaneous conservation work and minor repairs to municipal real estate | 45442100-8 | Painting work | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 18 | 16-08-2019 | 30-03-2022 | 957 | 850 | 294490 | 292245 | 2 | 296067.74 | -3822.74 | 98.7088 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
569 | 5797534 | 2019/71-DGEP - Construction of a roundabout on Av. Miratejo with Av. Eng. Frankish Bonneville, Paço-de-Arcos | 45233128-2 | Roundabout construction work | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 12-08-2019 | 28-04-2022 | 990 | 90 | 237745.26 | 229432.37 | 1 | 219891.25 | 9541.12 | 104.339 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
570 | 5794332 | Meirinhas School Center - Proc. No. 23/2016 | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2022 | Portugal | Pombal | Leiria | 10 | 30 | 12-07-2016 | 22-04-2022 | 2110 | 450 | 1798479.49 | 1557000 | 3 | 1596033.86 | -39033.86 | 97.5543 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the extensions | price revision amount
571 | 5784297 | Rehabilitation/Remodeling of Buildings 1, 2, 3, 7, 8, 10, 16, 17, 19, 20, 31 and 32 in the Cerco do Porto neighborhood (EM.001.2019.027_28_29) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 30 | 06-08-2019 | 02-03-2022 | 939 | 540 | 6100000 | 1594960.48 | 3 | 1561716.68 | 33243.8 | 102.1287 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | this contract was characterized by some situations that implied the suspension of the projects as well as by several changes to the tender project, both introduced by the owner of work, and by needs resulting from errors and omissions in the project that resulted in the extensions of the term granted. | need for additional work due to changes to the project
572 | 5774400 | Creation of peripheral parking pockets (Cegonhas Parking Lot) - Proc. No. 14/2019 | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2022 | Portugal | Pombal | Leiria | 10 | 30 | 22-05-2019 | 03-02-2022 | 988 | 150 | 86343.35 | 75614.9 | 1 | 73771.2 | 1843.7 | 102.4992 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project carried out was expected to be completed on 01/02/2020, however, the project was suspended by the owner on 12/20/2019, with 137 days having elapsed from the scheduled deadline. the resumption of work took place on 06/16/2021 and was completed on 06/18/2021, on which date the inspection was carried out and the provisional acceptance was signed in accordance with paragraph 1 of article 394. | existence of underworks
573 | 5764587 | DPES-CPúblico 12/2018-Strengthening and remodeling of the water supply network in Póvoa do Pinheiro and street of Chorão | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2022 | Portugal | Coimbra | Coimbra | 6 | 24 | 25-02-2019 | 22-02-2022 | 1093 | 300 | 700000 | 651563.78 | 2 | 604874.09 | 46689.69 | 107.7189 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change due to being dependent on third parties | underwork has taken place
574 | 5761107 | Requalification of Av. General Humberto Delgado - Union of Parishes of Sobrado and Neighborhoods | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2022 | Portugal | Castelo de Paiva | Aveiro | 1 | 15 | 17-06-2019 | 28-04-2022 | 1046 | 210 | 306178.66 | 273530 | 2 | 268239.66 | 5290.34 | 101.9722 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work suspension - 02/01/2020 to 03/09/2020 | price review - €4,304.75
575 | 5747085 | UPAC'S for School Park - PHASE 1 | 45317000-2 | Other electrical installation work | FALSE | 2019 | 2022 | Portugal | Viseu | Viseu | 20 | 15 | 29-07-2019 | 26-06-2022 | 1063 | 112 | 122950 | 80284.94 | 1 | 80284.94 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
576 | 5738108 | Requalification of the outdoor pools of Miranda do Douro | 45212212-5 | Construction work for swimming pool | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 30 | 29-04-2019 | 16-02-2022 | 1024 | 450 | 970300 | 899452.23 | 2 | 878371.65 | 21080.58 | 102.4 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid pandemic | underworks and price review
577 | 5718475 | Maintenance dredging contract for the bar at the port of Povoa de Varzim | 45252124-3 | Dredging and pumping works | FALSE | 2019 | 2022 | Portugal | Póvoa de Varzim | Porto | 13 | 7 | 01-07-2019 | 04-03-2022 | 977 | 122 | 529000 | 400365.76 | 2 | 376150 | 24215.76 | 106.4378 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork.
578 | 5696734 | Requalification of the recreation area of ​​the JI of the EB Quinta de S. Gens | 45236290-9 | Repair work on recreational areas | FALSE | 2018 | 2022 | Portugal | Matosinhos | Porto | 13 | 15 | 05-07-2019 | 23-02-2022 | 964 | 15 | 60000 | 50556.94 | 1 | 49503.5 | 1053.44 | 102.128 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
579 | 5693517 | Construction of the Official Intermunicipal Collection Center - Union of the parishes of Raiva, Pedorido and Paraíso | 45000000-7 | Construction work | FALSE | 2019 | 2022 | Portugal | Castelo de Paiva | Aveiro | 1 | 15 | 01-07-2019 | 28-04-2022 | 1032 | 240 | 188628.86 | 183700 | 1 | 182075.5 | 1624.5 | 100.8922 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to covid and a lack of workers, the project was prolonged over time | additional work, underwork and price revisions
580 | 5691356 | PO 269/2018 - Distribution network to Ermelo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | N/A | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | N/A | 02-07-2019 | 10-01-2022 | 923 | 300 | N/A | 188271.74 | 1 | 186319.23 | 1952.51 | 101.0479 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A |  | works not performed
581 | 5687215 | 2019/8 - DGEP - Construction/maintenance of pedestrian pavements in Barcarena and Queijas | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 02-07-2019 | 21-01-2022 | 934 | 365 | 110992.5 | 103413.21 | 1 | 103413.21 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the state of emergency decreed in the country, due to the covid 19 pandemic, the contract was suspended for a total of 64 days
582 | 5671325 | Contract for the construction of the Building of the Territorial Detachment of the Republican National Guard (G.N.R.) in Alenquer | 45216111-5 | Police station construction work | TRUE | 2019 | 2022 | Portugal | Alenquer | Lisboa | 11 | 20 | 26-06-2019 | 17-06-2022 | 1087 | 550 | 1499603.43 | 1367700 | 3 | 1430601.34 | -62901.34 | 95.6032 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | complementary works, due to the covid19 pandemic, the project was suspended, alteration to the project of exterior arrangements and country situation and lack of "covid" stocks. | additional work and underwork
583 | 5667406 | Expansion of the Silves Municipal Swimming Pool Gym | 45212222-8 | Gymnasium construction work | FALSE | 2019 | 2022 | Portugal | Silves | Faro | 8 | 30 | 14-06-2019 | 26-01-2022 | 957 | 60 | 141260.73 | 138243.33 | 1 | 144697.21 | -6453.88 | 95.5397 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to say | nothing to say
584 | 5659290 | Repair and Construction of Various Pedestrian and Road Pavements - Charneca de Caparica and Sobreda | 45233251-3 | Resurfacing works | FALSE | 2019 | 2022 | Portugal | Almada | Setúbal | 17 | 21 | 30-05-2019 | 06-06-2022 | 1103 | 913 | 849056.6 | 679245.29 | 2 | 690224.92 | -10979.63 | 98.4093 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Bid Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work. | changes in the value of the project are due to an amount that remained on balance, of unfinished items.
585 | 5640918 | 2019/29 - DGEP - Construction of a retaining wall at elementary school Gil Vicente- Queijas | 45231221-0, 45262310-7, 45112700-2, 45315600-4 | Gas supply mains construction work, Reinforced-concrete work, Landscaping work, Low-voltage installation work | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 03-06-2019 | 01-02-2022 | 974 | 60 | 68661.37 | 68538.08 | 1 | 71599.52 | -3061.44 | 95.7242 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
586 | 5640703 | Requalification and energy efficiency works for the Municipal Auditorium | 45453100-8 | Refurbishment work | FALSE | 2019 | 2022 | Portugal | Lousada | Porto | 13 | 24 | 12-06-2019 | 19-05-2022 | 1072 | 300 | 628396.45 | 615499.8 | 2 | 635213.65 | -19713.85 | 96.8965 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions | complementary works; underwork and price revision
587 | 5630225 | 2019/15 - DGEP - Conservation and execution of pedestrian pavements in Carnaxide and Caxias | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 15 | 30-05-2019 | 09-02-2022 | 986 | 365 | 100850 | 96202.5 | 1 | 96202.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
588 | 5627277 | Rehabilitation of the building including all architectural works, stability, water network, domestic wastewater and rainwater network, equipment, electromechanical transport installations | 45262700-8 | Building alteration work | FALSE | 2018 | 2022 | Portugal | Nisa | Portalegre | 12 | 30 | 31-05-2019 | 06-01-2022 | 951 | 547 | 905285.43 | 774724.25 | 2 | 799691.53 | -24967.28 | 96.8779 | Best value for money: No Criterion related to quality Name: Price or cost Weighting: 100% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existence of definitive price revision indices. | lack of definitive price revision indices.
589 | 5617176 | CP 05/2019_DEGA - AA and AR Networks - Small Extensions 2019 | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2019 | 2022 | Portugal | Vagos | Aveiro | 1 | 40 | 24-05-2019 | 25-07-2022 | 1158 | 730 | 249000 | 217084.23 | 1 | 217084.23 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
590 | 5584241 | 2018/193 - DGEP - Road signs preferably in the parishes of Oeiras, Paço de Arcos and Caxias | 45233221-4, 45233290-8 | Road-surface painting work, Installation of road signs | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 14-05-2019 | 22-03-2022 | 1043 | 730 | 120360 | 99000 | 1 | 99000 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
591 | 5584108 | 2019/14 - DGEP - Construction of sidewalk on streetHelena Aragão in Tercena | 45233200-1 | Various surface works | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 20-05-2019 | 24-01-2022 | 980 | 60 | 42937.5 | 42456.78 | 1 | 37829.39 | 4627.39 | 112.2323 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
592 | 5552811 | Gardens of Garajau | 45112712-9 | Landscaping work for gardens | FALSE | 2019 | 2022 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 21 | 13-05-2019 | 18-01-2022 | 981 | 180 | 980000 | 878000 | 2 | 886572.38 | -8572.38 | 99.0331 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | ordinary revision of prices and work to be done
593 | 5551770 | Reconstruction of part of the block of Fábrica de Santo Thyrso - Alberto Carneiro Art Center | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2022 | Portugal | Santo Tirso | Porto | 13 | 20 | 29-04-2019 | 17-03-2022 | 1053 | 450 | 1357495.5 | 1179898.46 | 3 | 1210583.69 | -30685.23 | 97.4653 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award criterion set is that of the proposal economically more advantageous, under the deadlines of paragraph a) of paragraph 1 and paragraph 2 of article 74 of the Public Procurement Code, considering if the following factors and respective weightings: a) Price - 60% b) Technical value of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the alteration of works to what was initially proposed for the competition. | the execution of extra work - unforeseen work.
594 | 5535019 | 2018/192 - DGEP - Vertical signage in the Municipality of Oeiras | 45233290-8 | Installation of road signs | FALSE | 2019 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 29-04-2019 | 19-05-2022 | 1116 | 730 | 146802 | 133799.45 | 1 | 135729.96 | -1930.51 | 98.5777 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
595 | 5510031 | 2018/189 - DGEP - Conservation and repair of pavements in Carnaxide and Caxias | 45233200-1 | Various surface works | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 25-03-2019 | 13-05-2022 | 1145 | 365 | 298830 | 232849.8 | 1 | 232849.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
596 | 5504785 | Construction of the Props Warehouse at the Póvoa de Varzim fishing port | 45213221-8 | Warehouse stores construction work | FALSE | 2019 | 2022 | Portugal | N/A | N/A | N/A | 8 | 19-03-2019 | 27-04-2022 | 1135 | 365 | 7821760.42 | 7669349.21 | 3 | 8027284.76 | -357935.55 | 95.541 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | due to the covid-19 pandemic, the delivery of raw materials suffered successive delays and the number of labor reduced significantly. | unpredictable situations.
597 | 5501106 | 2018/179 - Fences and Railings in the Municipality of Oeiras | 45340000-2 | Fencing, railing and safety equipment installation work | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 18 | 02-04-2019 | 20-04-2022 | 1114 | 1095 | 270050 | 259370.65 | 2 | 269305.36 | -9934.71 | 96.311 | Best value for money: Yes Criterion related to quality Name: technical value of the proposal Weighting: 40% Criterion related to cost Name: bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
598 | 5433813 | Acquisition, Modernization, Maintenance and Conservation of Municipal Buildings - Energy Efficiency Program - Remodeling of General Warehouses - Phase B | 45213150-9 | Office block construction work | FALSE | 2018 | 2022 | Portugal | N/A | N/A | N/A | 15 | 28-03-2019 | 20-04-2022 | 1119 | 180 | 980000 | 938498.45 | 2 | 1072916.7 | -134418.25 | 87.4717 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
599 | 5431792 | Contract to build a bridge over the River Gilão connecting Largo da Caracolinha to street of Cais | 45221100-3 | Construction work for bridges | FALSE | 2018 | 2022 | Portugal | Tavira | Faro | 8 | 48 | 22-03-2019 | 21-01-2022 | 1036 | 500 | 1573400.58 | 1472334.1 | 3 | 1659028.88 | -186694.78 | 88.7467 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension due to the communication of the pss approval and due to the execution of complementary work | additional work, underwork and price revisions
600 | 5335902 | 2018/133 - DGEP - Connection of streetPaula da Gama with Alameda Calouste Gulbenkian, Caxias | 45316100-6, 45233120-6, 45315600-4 | Installation of outdoor illumination equipment, Road construction works, Low-voltage installation work | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 21 | 06-03-2019 | 22-04-2022 | 1143 | 120 | 180675.06 | 167800.24 | 1 | 158829.33 | 8970.91 | 105.6481 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
601 | 5335081 | Wastewater pumping station in the Liberdade neighborhood. | 45232431-2 | Wastewater pumping station | FALSE | 2018 | 2022 | Portugal | Barreiro | Setúbal | 17 | 10 | 21-02-2019 | 16-02-2022 | 1091 | 180 | 520000 | 489850.35 | 2 | 480415.93 | 9434.42 | 101.9638 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | excavation problems due to the groundwater level verified on site, equipment delivery deadlines and late supply of electricity to the building. | some works were not carried out as they were deemed unnecessary and others were replaced at no additional cost by other solutions found on site.
602 | 5327674 | Contract - "Urban and Landscape Requalification of the Space Surrounding the Sports and Multiservice Pavilions" | 45112700-2 | Landscaping work | TRUE | 2018 | 2022 | Portugal | Sobral de Monte Agraço | Lisboa | 11 | 15 | 19-12-2018 | 06-04-2022 | 1204 | 270 | 580000 | 579802.34 | 2 | 594537.36 | -14735.02 | 97.5216 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | requests for an extension of the deadline for the execution of the project, due to difficulties due to covid-19, difficulties in the acquisition of materials and skilled labor for the execution of the sidewalks. | pricing review.
603 | 5326851 | Construction of the WWTP from Vila Cova to Coelheira | 45232420-2 | Sewage work | FALSE | N/A | 2022 | Portugal | Vila Nova de Paiva | Viseu | 20 | N/A | 24-01-2019 | 07-02-2022 | 1110 | 365 | N/A | 596500 | 2 | 511323.66 | 85176.34 | 116.658 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable atmospheric conditions and delay in the supply of electricity | additional work and work to be done
604 | 5326770 | Construction of the WWTP in Touro | 45232420-2 | Sewage work | FALSE | 2018 | 2022 | Portugal | Vila Nova de Paiva | Viseu | 20 | 30 | 24-01-2019 | 05-04-2022 | 1167 | 365 | 647892.9 | 596500 | 2 | 568935.94 | 27564.06 | 104.8448 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | existence of a very high water table on the paiva river, delay in the supply of electricity and the availability of land adjacent to the touro ee | underwork
605 | 5299624 | Construction of classrooms for pre-schools in the elementary school of Bom João enclosure | 45214100-1 | Construction work for kindergarten buildings | TRUE | 2018 | 2022 | Portugal | Faro | Faro | 8 | 20 | 25-02-2019 | 14-07-2022 | 1235 | 270 | 298125.44 | 289364.76 | 2 | 311142.79 | -21778.03 | 93.0006 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
606 | 5271078 | Housing, urbanism and urbanization - paru - urban regeneration action plan - urban requalification - streetalexandre herculano | 45233222-1 | Paving and asphalting works | FALSE | 2018 | 2022 | Portugal | Soure | Coimbra | 6 | 20 | 03-10-2018 | 07-03-2022 | 1251 | 120 | 385332.4 | 336998.05 | 2 | 423805.43 | -86807.38 | 79.5172 | Best value for money: Yes Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change to deadline as a result of additional work identified. | work not foreseen in the initial project.
607 | 5242831 | A sustainable territory - Spatial Planning - Execution of the PARU - Contracts - Rehabilitation of Casa dos Arcos. | 45000000-7 | Construction work | FALSE | 2018 | 2022 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 12 | 27-12-2018 | 10-03-2022 | 1169 | 365 | 392785.03 | 350000 | 2 | 359215.62 | -9215.62 | 97.4345 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | granted 150 days of extension of the execution period | price review
608 | 5217686 | Work of urban regeneration and revitalization of the Municipal Park, including intervention in terms of different infrastructures, technical networks and equipment. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2022 | Portugal | Penacova | Coimbra | 6 | 31 | 23-11-2017 | 21-01-2022 | 1520 | 180 | 505289.76 | 505244.43 | 2 | 518290.13 | -13045.7 | 97.4829 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in work | existence of underwork and price revision
609 | 5204773 | Construction contract for the Pedestrian and Cycling Route in Vale de Arouca | 45233162-2 | Cycle path construction work | FALSE | 2017 | 2022 | Portugal | Arouca | Aveiro | 1 | 30 | 31-01-2019 | 01-06-2022 | 1217 | 545 | 1933087.54 | 1796769.33 | 3 | 1328635.99 | 468133.34 | 135.2341 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | checking works that have been suppressed.
610 | 5158049 | Catholic University - Viseu branch of the Authority to Combat Sports Violence | 45213150-9 | Office block construction work | FALSE | 2018 | 2022 | Portugal | Viseu | Viseu | 20 | 9 | 15-01-2019 | 20-01-2022 | 1101 | 42 | 40800 | 36804.85 | 1 | 45748.9 | -8944.05 | 80.4497 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need for additional work and work suspensions | need for additional work and underwork
611 | 5129669 | Rehabilitation of the Manor House - Casa dos Nouras - Rehabilitation Works (Casa dos Nouras - Houses for Exhibitions and Samples of Endogenous Products). | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2022 | Portugal | Alijó | Vila Real | 19 | 17 | 27-12-2018 | 13-01-2022 | 1113 | 548 | 539682.69 | 534920.97 | 2 | 564034.4 | -29113.43 | 94.8384 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | outbreaks/lockdowns due to covid 19 | due to complementary work and underwork
612 | 5090114 | Refurbishment of the campsite at Praia de Faro | 45112711-2 | Landscaping work for parks | TRUE | 2018 | 2022 | Portugal | Faro | Faro | 8 | 20 | 20-12-2018 | 16-05-2022 | 1243 | 180 | 423596.42 | 420680.02 | 2 | 420680.02 | 0 | 100 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Does not apply Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
613 | 5088953 | Work contract for interventions to mitigate the risk of flooding with INATEL | 45232411-6 | Foul-water piping construction work | TRUE | 2018 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 20-12-2018 | 07-03-2022 | 1173 | 120 | 312000 | 297053.22 | 2 | 297053.22 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the high season and due to the covid emergency | no change
614 | 5032395 | Work Contract for the Requalification of the Social Building in the Parque das Nações Precinct | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2022 | Portugal | Lisboa | Lisboa | 11 | 60 | 05-11-2018 | 13-04-2022 | 1255 | 240 | 600000 | 582143.04 | 2 | 570008.33 | 12134.71 | 102.1289 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | six inspections were carried out prior to the aforementioned one, but due to the existence of defects and/or work to be completed, they prevented provisional acceptance from taking place at an earlier date. | changes in the value of the project due to overwork, the supply of errors and omissions, the price review carried out and due to fines billed to the contractor.
615 | 4958965 | Elevator System of Curalha for Connection to the WWTP of Curalha | 45232410-9 | Sewerage work | FALSE | 2018 | 2022 | Portugal | Chaves | Vila Real | 19 | 30 | 14-11-2018 | 30-03-2022 | 1232 | 150 | 140000 | 129242.4 | 1 | 133723.26 | -4480.86 | 96.6492 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of works for 462 days plus 504 days, due to the need to readjust the project and authorization from infraestruturas de portugal to cross the en 103. | complementary works in the amount of €11,055.07, price revisions in the amount of €775.79 and underwork in the amount of €7,350.00.
616 | 4943052 | Construction/lowering of sidewalks in crosswalk areas, with application of tactile materials, removal of obstacles and repainting of pedestrian crossings, at street1.º de Maio - Campo | 45233251-3 | Resurfacing works | FALSE | 2018 | 2022 | Portugal | Valongo | Porto | 13 | 21 | 30-10-2018 | 20-04-2022 | 1268 | 120 | 112450 | 80000 | 1 | 94414.26 | -14414.26 | 84.733 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allocation of 20 days to carry out the complementary work - additional contract of 10.30.2019. note: the last measurement report dates from 11.15.2019, there was some delay in scheduling the inspection for the purposes of provisional acceptance. | additional work - €12,596.79 final calculation of the price revision - €1,817.47
617 | 4937149 | The object of the contract is the execution of the Contract for the Expansion and Rehabilitation of the Elementary School of São Pedro, Parish of São Pedro, Ponta Delgada | 45214210-5 | Primary school construction work | FALSE | 2017 | 2022 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 56 | 06-11-2018 | 05-01-2022 | 1156 | 548 | 4505000 | 3964054.66 | 3 | 4381146.1 | -417091.44 | 90.4799 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions | additional work, errors and omissions supply and price review
618 | 4931081 | 2018/117 - DGEP - Construction of the road viaduct at Quinta da Fonte, Paço de Arcos | 45316000-5, 45232451-8, 45221121-6 | Installation work of illumination and signalling systems, Drainage and surface works, Road viaduct construction work | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 05-11-2018 | 25-05-2022 | 1297 | 365 | 2086630.62 | 1979969.13 | 3 | 2689615.09 | -709645.96 | 73.6153 | Best value for money: Yes Criterion related to quality Name: Valia, technical feasibility and execution time Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
619 | 4911001 | 2017/249 - DGEP - Green and Blue Axis, Rio Jamor - 1st phase | 45233200-1, 45112720-8, 45112000-5, 45316100-6 | Various surface works, Landscaping work for sports grounds and recreational areas, Excavating and earthmoving work, Installation of outdoor illumination equipment | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 18-10-2018 | 27-04-2022 | 1287 | 270 | 1896186.68 | 1167300.07 | 3 | 1369024.96 | -201724.89 | 85.2651 | Best value for money: Yes Criterion related to quality Name: Valia, technical feasibility and execution time Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | apa impositions | project uncertainties
620 | 4909294 | Requalification of the Municipal Market and Riverfront, South - Construction of Kiosk/Bar to support leisure space | 45212423-7 | Cafeteria construction work | FALSE | 2018 | 2022 | Portugal | Ponte de Sor | Portalegre | 12 | 9 | 18-10-2018 | 05-01-2022 | 1175 | 120 | 159102.12 | 158203.57 | 1 | 158153.02 | 50.55 | 100.032 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | existence of underworks
621 | 4896025 | PRC_0140/2018_GAE - AA0390 - Design/construction contract for improving the quality of water produced at the Areias de Vilar ETA (Barcelos) | 45351000-2 | Mechanical engineering installation works | TRUE | 2018 | 2022 | Portugal | Barcelos | Braga | 3 | 15 | 12-10-2018 | 26-07-2022 | 1383 | 196 | 1000000 | 382278.38 | 2 | 382278.04 | 0.34 | 100.0001 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | having started the excavation work, it was found that the elements presented in the tender phase did not fully represent the existing conditions, namely the location of the said turning point of the dn1800 pipeline, as well as the existence of a medium voltage cables, or the existence of buried dn1200 piping, which conditions the area available for the installation of the reinforced concrete box that will house the equipment. resulted from the need for the base project prepared by the contractor to be the object of an objective modification, taking advantage of the opportunity to carry out a substantial improvement in terms of guaranteeing the functionality of the areias de vilar eta, fundamentally passing the installation line of the uv disinfection system to be developed laterally to the main conduit, thus allowing the existing conduit to function as a by-pass in case of anomaly, or maintenance of the new equipment, thus safeguarding the guarantee of water supply from the areias de vilar eta. this solution will also allow, whenever the quality of the produced water is sufficient, the deactivation of the treatment stage, with the respective cost savings, namely energy | having started the excavation work, it was found that the elements presented in the tender phase did not fully represent the existing conditions, namely the location of the said turning point of the dn1800 pipeline, as well as the existence of a medium voltage cables, or the existence of buried dn1200 piping, which conditions the area available for the installation of the reinforced concrete box that will house the equipment. resulted from the need for the base project prepared by the contractor to be the object of an objective modification, taking advantage of the opportunity to carry out a substantial improvement in terms of guaranteeing the functionality of the areias de vilar eta, fundamentally passing the installation line of the uv disinfection system to be developed laterally to the main conduit, thus allowing the existing conduit to function as a by-pass in case of anomaly, or maintenance of the new equipment, thus safeguarding the guarantee of water supply from the areias de vilar eta. this solution will also allow, whenever the quality of the produced water is sufficient, the deactivation of the treatment stage, with the respective cost savings, namely energy
622 | 4894084 | Arrangements and Walks at the Headquarters Parish Alb dozen (Revitalization of Praça da Igreja Velha and Largo Eng.º Guilherme Santos) - Proc. No. 02/2017 | 45233262-3 | Pedestrian zone construction work | FALSE | 2017 | 2022 | Portugal | Pombal | Leiria | 10 | 30 | 17-04-2017 | 04-03-2022 | 1782 | 270 | 827090.16 | 826873.1 | 2 | 817946.44 | 8926.66 | 101.0914 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the provisional acceptance due to the contractor's error was only verbally requested by the successful tenderer 5 days before the inspection for the purposes of provisional acceptance, despite the fact that the project had been fully carried out. the inspection for the purposes of provisional acceptance was carried out as soon as possible by the parties on the earliest date after the completion of the project, and the provisional acceptance document was drawn up and signed on the inspection date. | existence of underwork and price revision value.
623 | 4888716 | The contract involves the construction/lowering of sidewalks in the crosswalk areas, with the application of tactile materials, removal of obstacles and repainting of pedestrian crossings | 45233251-3 | Resurfacing works | FALSE | 2018 | 2022 | Portugal | Valongo | Porto | 13 | 15 | 04-10-2018 | 12-04-2022 | 1286 | 180 | 170500 | 150423.24 | 1 | 151216.15 | -792.91 | 99.4756 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions: 60 days - addendum to the initial contract on 5/30/2019 30 days - addendum to the initial contract on 7/2/2019 | approval of the definitive calculation of the price revision, on 04.04.2022 - €792.91
624 | 4886068 | PRC_0379/2017_GAE-AR0367 - Contract for the Improvement of the Preguiça Pumping Station - SAR Mirandela | 45232423-3 | Sewage pumping stations construction work | FALSE | 2018 | 2022 | Portugal | Mirandela | Bragança | 4 | 20 | 02-10-2018 | 15-03-2022 | 1260 | 365 | 950000 | 840000.69 | 2 | 867472.58 | -27471.89 | 96.8331 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 55% Technical value of the proposal: 45% | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of safety conditions for carrying out the project due to adverse weather conditions that caused flooding at the project site. delays by the contractor due to the current state of the covid-19 pandemic. suspensions of work are verified in accordance with subparagraph a) of point 3 of article 366 of the "public procurement code" due to natural phenomena and also suspensions in accordance with article 297 of the "public procurement code", depending on third parties for the certification of the electrical installation of the infrastructure, including pt and generator. | there was no need to carry out all the contractual work, namely with regard to exterior repair work, coatings, metalwork, ventilation system and application of 'strail' type rubber and connection of the floor whose amounts foreseen in lpu were higher than those needed on site.
625 | 4802630 | A4, B1 and B2 streets of the PP1 extension of Av. Antonio Jose de Almeida | 45233120-6 | Road construction works | FALSE | 2017 | 2022 | Portugal | Viseu | Viseu | 20 | 18 | 29-03-2018 | 03-01-2022 | 1376 | 154 | 1280000 | 1093898.47 | 3 | 1093898.47 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of works on b2 and b1 streets
626 | 4792218 | Construction contract for the pumping stations of Póvoa de Rio de Moinhos, Sobral do Campo and Pisco and rechlorination of the pumping station in Carvalhos | 45232152-2 | Pumping station construction work | FALSE | 2017 | 2022 | Portugal | Castelo Branco | Castelo Branco | 5 | 48 | 03-08-2018 | 19-01-2022 | 1265 | 240 | 1300000 | 859999.92 | 2 | 858091.47 | 1908.45 | 100.2224 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% and technical value - 30% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extended by 62 days. a first inspection was carried out on 10/30/2019, for the purpose of provisional acceptance, in which defects in the projectmanship were detected, which prevented the reception. subsequently, on 07/28/2020, a new inspection was carried out, and the conditional partial provisional receipt notice was signed. after the definitive power connection in the ee of povoa de rio de moinhos on 12/17/2020, the facility went into operation. on 03/08/2021, an inspection was carried out for the purposes of the provisional acceptance of the project. | underwork and definitive price revision.
627 | 4775069 | Contract for execution of pantries at EB 1, 2, 3 de Ferreiras | 45454000-4 | Restructuring work | FALSE | 2018 | 2022 | Portugal | Albufeira | Faro | 8 | 14 | 16-08-2018 | 13-01-2022 | 1246 | 70 | 213712.29 | 192211.36 | 1 | 200862.34 | -8650.98 | 95.6931 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project had complementary works | the project had complementary works
628 | 4763448 | Construction of the Sequeira/Cabreiros Health Unit | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2022 | Portugal | Braga | Braga | 3 | 30 | 27-07-2018 | 02-06-2022 | 1406 | 365 | 602000 | 576680.76 | 2 | 526442.69 | 50238.07 | 109.5429 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price - 70% B - Technical value of the proposal - 30% B1 - Descriptive memory - 10% B2 - Work, labor, equipment and payment plans - 10% B3 - Safety to be implemented in the work (technical note) - 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | economic and financial situation that made it difficult to hire reliable sub-contractors who honor their commitments; state of emergency related to covid 19 | the projects resulting from the measurement on site are lower than those foreseen in the terms of reference.
629 | 4695205 | 2018/4 - DGEPIM - Supply and placement of metallic guards (fixed and removable) and flexible bollards in the municipality of Oeiras | 45233280-5 | Erection of road-barriers | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 30 | 20-07-2018 | 09-08-2022 | 1481 | 1095 | 200075 | 158252.15 | 1 | 158252.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
630 | 4683312 | 2018/21 - DGEPIM - Conservation and repair of pavements in Carnaxide and Caxias | 45233200-1 | Various surface works | FALSE | 2018 | 2022 | Portugal | Oeiras | Lisboa | 11 | 24 | 22-06-2018 | 17-06-2022 | 1456 | 730 | 298725 | 228091.82 | 1 | 228091.82 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
631 | 4672154 | Installation of Sections of Wastewater Collecting Network in Several streets | 45232400-6 | Sewer construction work | FALSE | 2018 | 2022 | Portugal | Vila Nova de Gaia | Porto | 13 | 14 | 03-07-2018 | 16-03-2022 | 1352 | 365 | 100000 | 79965.1 | 1 | 101739.95 | -21774.85 | 78.5975 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Proposal for the lowest price under the deadlines of subparagraph b) no. 1 and no. 3, article 74 CCP Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension, as per board of directors resolution of 8/13/2019, provisional receipts with anomalies. | complementary works
632 | 4671617 | Creation of a new transport interface in the eastern riverside area, including landscaping and infrastructure. | 45233200-1 | Various surface works | FALSE | 2018 | 2022 | Portugal | Alcácer do Sal | Setúbal | 17 | 30 | 29-06-2018 | 22-04-2022 | 1393 | 365 | 1021000 | 878142.05 | 2 | 891906.9 | -13764.85 | 98.4567 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of paragraph 12 of the Procedure Program | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract had a 73-day extension due to the delay of some suppliers and weather conditions. the end of the physical execution of the project was on 01/31/2020, and it was only possible to schedule an inspection for provisional reception on 02/11/2020. the project provided for 1 year of maintenance of the exterior arrangements, (according to article 10-10.1 of the map quantities/works awarded). the inspection for the purposes of total provisional reception of the projects was only possible on 10.03.2021 (covid 19 conditions). | result of the definitive price revision of the project, in favor of the contractor, in the amount of €17,049.65. the project had records nºs 1 and 2 of underwork, in the total amount of €3,284.80
633 | 4565442 | Execution, in accordance with the terms of reference, of the contract called “Recovery of Levada do Norte - South Section - Pk9+500 to Pk34+500” | 45247110-4 | Canal construction | FALSE | 2017 | 2020 | Portugal | Ribeira Brava | Região Autónoma da Madeira | 14 | 48 | 20-06-2018 | 30-10-2020 | 863 | 640 | 3800000 | 3349588.01 | 3 | 1835585.75 | 1514002.26 | 182.4806 | lowest price | 2 | 100 | Yes (no values) | TRUE | Non-fulfilment of the contract (Revocation of the Contract) | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | yes | agreement revocation of the agreement of 10/30/2020
634 | 4541699 | Hospital dos Marmeleiros - Rehabilitation of Facades and Roofs | 45453100-8 | Refurbishment work | FALSE | 2017 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 40 | 29-05-2018 | 20-01-2022 | 1332 | 240 | 890000 | 712000.01 | 2 | 717943.16 | -5943.15 | 99.1722 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | ordinary review
635 | 4473787 | Adaptation/Expansion of the elementary school of the 1st Cycle of Souto | 45454000-4 | Restructuring work | FALSE | 2017 | 2022 | Portugal | Sabugal | Guarda | 9 | 25 | 11-05-2018 | 13-06-2022 | 1494 | 365 | 471702.36 | 396782.07 | 2 | 416574.95 | -19792.88 | 95.2487 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | overwork, underwork and price revisions
636 | 4473529 | Adaptation of the 2nd Cycle School of Sabugal into a elementary school of the 1st and 2nd Cycle of Sabugal | 45454000-4 | Restructuring work | FALSE | 2017 | 2022 | Portugal | Sabugal | Guarda | 9 | 25 | 11-05-2018 | 17-08-2022 | 1559 | 365 | 591156.76 | 494478.99 | 2 | 528392.64 | -33913.65 | 93.5817 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions | extra work and price revisions
637 | 4453864 | PRC_0050/2017-EGA-EB0324 - Contract for the Execution of Drainage Networks for Rabada SAR and Lordelo/Aves SAR (Santo Tirso) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2022 | Portugal | Santo Tirso | Porto | 13 | 12 | 11-10-2017 | 31-03-2022 | 1632 | 364 | 3400000 | 3062789.25 | 3 | 2885058.52 | 177730.73 | 106.1604 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the ones mentioned above. | there was no need to perform all contract work.
638 | 4450995 | Construction contract for the maritime shelter work in the fishing area of ​​Angeiras | 45241300-1 | Pier construction work | FALSE | 2017 | 2022 | Portugal | Matosinhos | Porto | 13 | 35 | 02-05-2018 | 15-03-2022 | 1413 | 540 | 3730000 | 3079311.93 | 3 | 3367836.08 | -288524.15 | 91.433 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award is carried out according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors and respective weighting coefficients: a) Price (40%) scored using the value function represented in annex 4 to the tender program; b) Technical value of the proposal (60%) evaluated using the evaluation model contained in annex 4 to the tender program. The subfactors and respective qualitative analysis descriptors and respective weightings and scores, to be considered for the evaluation of the factor "Technical value of the proposal" are the following: a) Descriptive memory and justification of the execution of the work - 40%; b) Work plan - 30%; c) Labor plan - 10%; d) Equipment plan - 20%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work due to adverse sea conditions. suspension of work during maritime winters (1st year-partial suspension and 2nd year-total suspension). | additional contracts (1 and 2).
639 | 4446338 | Municipal Road Vista Alegre/Serradêlo - Union of the Parishes of Raiva, Pedorido and Paraíso | 45000000-7 | Construction work | FALSE | 2017 | 2022 | Portugal | Castelo de Paiva | Aveiro | 1 | 30 | 02-05-2018 | 26-04-2022 | 1455 | 240 | 330861.93 | 286871.29 | 2 | 295709.77 | -8838.48 | 97.0111 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | having approved a 90-day extension of the deadline at a chamber meeting on 02/22/2019, the execution deadline was met | revision of prices and work to be done
640 | 4430663 | Contract for the Conception-Construction of the Expansion and Remodeling of the Sertã WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2022 | Portugal | Sertã | Castelo Branco | 5 | 60 | 06-04-2018 | 19-01-2022 | 1384 | 545 | 1300000 | 1115247.28 | 3 | 1130759.27 | -15511.99 | 98.6282 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: see program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extended by 60 days. | underwork and price revision carried out.
641 | 4390771 | Rehabilitation and Regularization of Ribeira de Santa Luzia - Urban Section between Km 0+386.38 and Km 1+860.05 - Paving of Adjacent streets | 45233223-8 | Carriageway resurfacing works | FALSE | 2017 | 2022 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 42 | 27-03-2018 | 25-01-2022 | 1400 | 90 | 945000 | 756000.01 | 2 | 789162.78 | -33162.77 | 95.7977 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of works | underworks and ordinary price review
642 | 4361360 | Construction of support walls such as gabions, reno mattresses or prefabricated concrete modules, for stabilizing slopes and/or reinforcing existing walls, in various locations in the municipality of Coimbra | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2022 | Portugal | Coimbra | Coimbra | 6 | 24 | 28-02-2018 | 25-01-2022 | 1427 | 180 | 195199 | 165998.82 | 1 | 173641.18 | -7642.36 | 95.5988 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension of term | value of additional works and price revision
643 | 4348579 | Requalification of E.M. 520, Between street of Camalhões and streetMarco da Poça - Argoncilhe/Olival - Santa Maria da Feira/Vila Nova de Gaia | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2022 | Portugal | Santa Maria da Feira | Porto | 13 | 36 | 14-03-2018 | 15-03-2022 | 1462 | 180 | 459660 | 348850.02 | 2 | 324584.15 | 24265.87 | 107.476 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 30 days of legal extension, 97 days of graceful extension, 83 days of procedural processing and contractor delays, 910 days for correction of physical and documental defects | underwork
644 | 4217475 | P082/2017 - Wastewater drainage network in the parishes of Cercal, Matas and Espite | 45232400-6 | Sewer construction work | FALSE | 2017 | 2022 | Portugal | Ourém | Santarém | 16 | 24 | 08-01-2018 | 21-03-2022 | 1533 | 300 | 1222547.64 | 976185.3 | 2 | 1066802.7 | -90617.4 | 91.5057 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (65% weighting) - Fprice b) Warranty period - Non-structural elements or Technical installations (5% weighting) - Warranty c) Proposed Price Justification Note (5% weighting) - Justification d) Work Plan (5% weighting) - Works e) Labor Plan (5% weighting) - Labor f) Equipment Plan (5% weighting) - Equipment g) Descriptive and Justification Memory (5% weighting) - Fmemoria h) Payment Plan (5% weighting) - Fpayments | 1 | 65 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspensions and extensions | more work and underwork and price revision
645 | 3982061 | Contract for the Construction of Power Reinforcement of the Álamos Pumping Station of the Alqueva Multipurpose Project | 45000000-7 | Construction work | FALSE | 2017 | 2022 | Portugal | Portel | Évora | 7 | 90 | 04-12-2017 | 22-06-2022 | 1661 | 670 | 13750000 | 9231421.59 | 3 | 9231421.9 | -0.31 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for the contract was largely exceeded for reasons related to difficulties in reconciling the pumping groups and the respective support structure to prevent vibrations, several internal difficulties at one of the companies in the awarded consortium, and the appearance of covid, which delayed delivery of equipment purchased abroad for several months. | the changes are essentially due to: - additional work at the substation, as required by edp; - adaptation of some equipment to the existing one; - repair not foreseen in existing equipment.
646 | 3828547 | 2013.517.11.C1 - Xabregas Building - Renovation of the 3rd floor, South Wing | 45213150-9 | Office block construction work | FALSE | 2014 | 2022 | Portugal | Lisboa | Lisboa | 11 | 21 | 09-05-2017 | 09-03-2022 | 1765 | 80 | 440000 | 314626.14 | 2 | 321284.62 | -6658.48 | 97.9275 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%, Proposed technical value: 30% and deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed on 08-06-2019 | final price review
647 | 3773337 | Expansion of the water supply network to the source system (Mezio) - Cabana Maior | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2022 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 13-10-2017 | 10-01-2022 | 1550 | 300 | 860000 | 801752.87 | 2 | 801752.87 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: 50% - Lowest global price 50% - Technical value of the proposal These criteria are decomposed into sub-criteria, in accordance with article 12 of the Procedure Program | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended by 155 days, due to a delay in the issuance of the ip license to open a trench on the en, and consequent replacement of the definitive pavement
648 | 3756855 | Construction of the Pipeline to the Carrier and Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2022 | Portugal | Aljustrel | Beja | 2 | 24 | 10-10-2017 | 14-04-2022 | 1647 | 365 | 536000 | 515000.03 | 2 | 533662.18 | -18662.15 | 96.503 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions; labor shortage. covid-19 pandemic | final calculation of the price revision
649 | 3640623 | Construction of a Wastewater Treatment Plant - Casas Novas and Redondelo | 45232410-9 | Sewerage work | FALSE | 2017 | 2022 | Portugal | Chaves | Vila Real | 19 | 30 | 30-08-2017 | 03-01-2022 | 1587 | 150 | 275000 | 252565 | 2 | 182296.34 | 70268.66 | 138.5464 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 3 term extensions 270 days (90 + 90 +90) 1 suspension of the execution period of the project for a period of 625 days due to the lack of guaranteed administrative possession of the land to be expropriated (article 297) 1 suspension of the execution period of the project for a period of 198 days due to awaiting a favorable opinion from the entity infraestruturas de portugal. (article 297) | underwork worth €70,946.75
650 | 3575946 | Completion of the Infrastructures of the Subdivision of the "Encosta do Sol-Torrão" Urbanization | 45233252-0 | Surface work for streets | FALSE | 2017 | 2022 | Portugal | Guarda | Guarda | 9 | 20 | 25-07-2017 | 11-02-2022 | 1662 | 150 | 175048.94 | 159000 | 1 | 147114.4 | 11885.6 | 108.0792 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of a suspension of works due to the impossibility of starting them | existence of underwork and price revision
651 | 3560349 | Museum nucleus of the church of s.pedro and reserves | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2016 | 2022 | Portugal | Grandola | Setúbal | 17 | 41 | 15-02-2017 | 29-04-2022 | 1899 | 365 | 669758.08 | 649062.82 | 2 | 789983.66 | -140920.84 | 82.1616 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | TRUE | FALSE | FALSE | N/A | it was necessary during the contract to extend the term of execution. | it was necessary to execute work that by their nature were classified under the law, as overwork, errors and omissions.
652 | 3545784 | Water Supply System for the Municipality of Penalva do Castelo (R1, R2, R3 and Mártir de Pindo Elevated) - Project Execution | 45231110-9 | Pipelaying construction work | FALSE | 2017 | 2022 | Portugal | Penalva do Castelo | Viseu | 20 | 22 | 26-07-2017 | 10-05-2022 | 1749 | 365 | 823099.6 | 811157.36 | 2 | 833075.09 | -21917.73 | 97.3691 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension and extension of term | underwork
653 | 3251645 | The contract is intended for the construction of a Multipurpose Complex of Tracks for the practice of Extreme Sports, including the construction of a building for the installation of the Control Tower | 45212210-1 | Single-purpose sports facilities construction work | FALSE | 2016 | 2022 | Portugal | Boticas | Vila Real | 19 | 21 | 19-04-2017 | 22-04-2022 | 1829 | 120 | 1085882.14 | 814411.62 | 2 | 736036.53 | 78375.09 | 110.6483 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 70% b) Technical Valuation of the Proposal - 30% To dedeadlineine the Technical Value of the Proposal, the following subfactors will be considered: - Descriptive Memory (MD) - 30% - Work Plan (PT) - 30% - Labor Plan (PMO) - 20% - Equipment Plan (PE) - 20% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension and extension of term for the reasons mentioned above. | underwork.
654 | 3109688 | Construction of the New WWTP in the Village (Gôje) | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2016 | 2022 | Portugal | Penalva do Castelo | Viseu | 20 | 22 | 25-01-2017 | 02-05-2022 | 1923 | 554 | 2301446.31 | 1817137.44 | 3 | 1805305.15 | 11832.29 | 100.6554 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension and term extensions | less and additional work
655 | 3109419 | Requalification of Green Spaces in the City of Guarda | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2022 | Portugal | Guarda | Guarda | 9 | 20 | 09-03-2017 | 21-02-2022 | 1810 | 90 | 349550.61 | 315733.4 | 2 | 319513.01 | -3779.61 | 98.8171 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existence of deadline extensions | existence of price revision
656 | 3064656 | Year 2017_Urbanization Works Contract for the Rio Seco Allotment, in Lisbon | 45000000-7, 45211360-0 | Construction work, Urban development construction work | FALSE | 2016 | 2022 | Portugal | Lisboa | Lisboa | 11 | 21 | 22-02-2017 | 18-01-2022 | 1791 | 180 | 1300000 | 886155.38 | 2 | 587131.8 | 299023.58 | 150.9295 | lowest price | 2 | 100 | Yes (no values) | FALSE | Non-fulfilment of the contract (Revocation of the Contract) | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 251 days of extension due to the appearance of prehistoric settlements, with the manual excavation of an area of ​​the project. | it became necessary to carry out work that was not initially foreseen, and work that could not be carried out was also withdrawn.
657 | 2922345 | Award contract for the Urban Rehabilitation of the Historic Center of Silves - 3rd phase | 45233252-0, 45231400-9, 45232300-5, 45232460-4 | Surface work for streets, Construction work for electricity power lines, Construction and ancillary works for telephone and communication lines, Sanitary works | FALSE | 2016 | 2022 | Portugal | Silves | Faro | 8 | 30 | 03-01-2017 | 10-03-2022 | 1892 | 540 | 1256654.05 | 889140.49 | 2 | 886830.97 | 2309.52 | 100.2604 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the execution period by another 3 months, and unresolved issue related to edp. | works less in the amount of 116,081.60; additional work worth 23,203.48 and price review worth 90,568.60
658 | 2547326 | 5010014413 - Construction work- “Northern Line- Modernization of subsection 2.3 Alfarelos – Pampilhosa. Comprehensive renovation of track between Alfarelos (PK 194,500) and Pampilhosa (PK 230,630) stations | 45234100-7 | Railway construction works | FALSE | 2014 | 2022 | Portugal | Aveiro | Aveiro | 1 | N/A | 29-10-2015 | 07-01-2022 | 2262 | 750 | 39996986.12 | 30542288.25 | 3 | 30067409.72 | 474878.53 | 101.5794 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A |  | the causes are essentially due to design errors and omissions
659 | 2429300 | Urban Requalification of the Plano and Algares Minas Gerais Neighborhoods | 45211360-0 | Urban development construction work | FALSE | 2016 | 2022 | Portugal | Aljustrel | Beja | 2 | 30 | 07-09-2016 | 21-03-2022 | 2021 | 365 | 525000 | 404678.09 | 2 | 396672.71 | 8005.38 | 102.0181 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project underwent changes to the execution period, in a total of 120 days. the first 75-day extension was due to specific changes to the project, rainfall that prevented excavations, organization of work to allow residents to circulate, need for paving with concrete. the second extension of 48 days was due to heavy rainfall that prevented the application of bituminous masses | changes to the value of the project are due to the value of price revisions in the amount of €18,372.91 and the project records for less in the total of €26,378.29
660 | 2400510 | Continuous Contract for Civil Construction - 2016 | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2022 | Portugal | Viseu | Viseu | 20 | 24 | 02-09-2016 | 05-07-2022 | 2132 | 371 | 300000 | 225163 | 1 | 47362.58 | 177800.42 | 475.4027 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A
661 | 2366542 | Contract work for the Iberian Museum of Archeology and Art of Abrantes - Phase 1 - Recovery, Remodeling and Expansion of the Convent of S. Domingos | 45454000-4 | Restructuring work | FALSE | 2015 | 2022 | Portugal | Abrantes | Santarém | 16 | 36 | 25-08-2016 | 05-04-2022 | 2049 | 910 | 4507970.23 | 3124398.26 | 3 | 3411925.86 | -287527.6 | 91.5729 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | four extensions of time were granted for a total of 570 days, justified in the technical information of the inspection that supported the cma deliberations of 06.25.2019, 03.03.2020, 07.21.2020 and 10.27.2020. | underwork, replacement of financial rebalancing and ordinary price review were considered.
662 | 2255709 | Construction of Carnide Outfall - Ilha - Louriçal - Proc. No. 25/2015 | 45232400-6 | Sewer construction work | FALSE | 2015 | 2022 | Portugal | Pombal | Leiria | 10 | 30 | 02-12-2015 | 26-01-2022 | 2247 | 600 | 3500000 | 2965301.55 | 3 | 2918174.13 | 47127.42 | 101.615 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delays verified in the execution of the contract in question had their origin in the fact that the collectors to be built were, for the most part, implanted in agricultural land, owned by individuals, whose authorizations for access to them were, many times, conditioned by the circumstance of the respective owners not being residents of the municipality, as well as the need to wait for the harvests to take place in july, august and september, which was not foreseeable when the project was initially designed). it should be noted that the contract in question is based on the execution of a work that comprises about 24 km of collectors, which, as already mentioned, crossed several dozens of rustic buildings, therefore, it is not possible to guarantee, in the project, at least with the desired rigor, which buildings would be cultivable, nor what would be cultivated in them. | existence of underworks.
663 | 2039847 | Improvement and Requalification of the Caminho do Saibro - Regadas | 45233142-6 | Road-repair works | FALSE | 2015 | 2022 | Portugal | Fafe | Braga | 3 | 31 | 26-02-2016 | 29-03-2022 | 2223 | 180 | 532324.6 | 370756.12 | 2 | 370755.64 | 0.48 | 100.0001 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 70% Technical Valuation and Proposal Guarantee: 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work was suspended due to lack of approval of materials by águas do norte and lack of authorization to intervene in some plots | there were no changes to the value of the project
664 | 1426230 | The objective of the intervention is the execution of a roundabout in the connection of the Salgueiro industrial subdivision street with the E.N. 16 | 45233128-2 | Roundabout construction work | FALSE | 2015 | 2022 | Portugal | Mangualde | Viseu | 20 | 12 | 06-04-2015 | 10-03-2022 | 2530 | 240 | 476000 | 428400.01 | 2 | 389718.99 | 38681.02 | 109.9254 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to unavailability of land for the implementation of the pt.
665 | 1415089 | Reservoir R2 - Quinta da Piedade - Póvoa de Santa Iria (C.79.8) | 45262310-7 | Reinforced-concrete work | FALSE | 2014 | 2022 | Portugal | Vila Franca de Xira | Lisboa | 11 | 21 | 14-01-2015 | 28-01-2022 | 2571 | 420 | 1403436.16 | 1052577.12 | 3 | 1052577.12 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | delay in delivery of the technical compilation by the contractor firm
666 | 1381930 | En118, km 43+400, ditch bridge - structural reinforcement of pillars and foundations | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2022 | Portugal | Santarém | Santarém | 16 | 31 | 11-02-2015 | 31-08-2022 | 2758 | 170 | 565000 | 414160.72 | 2 | 491955.41 | -77794.69 | 84.1866 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | it resulted from difficulties in carrying out complete drillings, my self-drilling piles. | it resulted from difficulties in carrying out complete drillings, my self-drilling piles.
667 | 1295967 | Parish of Abiúl / Asphalting of Roads and Paths in the Parish (E.M. 501 Abiúl - partnerships) - proc. No. 34/2014 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2022 | Portugal | Pombal | Leiria | 10 | 24 | 25-09-2014 | 07-02-2022 | 2692 | 90 | 220437.5 | 177000 | 1 | 166905.16 | 10094.84 | 106.0482 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | the delay in the contract is due to the calculation of all the projects carried out by the contractor, recorded in the measurement report after the end of the project term. according to the provisions of article 390.º of the "public procurement code", measurement errors, faults were detected in the previously drawn up measurement records, which were corrected and replaced in the subsequent measurement report, in collaboration with the contractor in relation to the object and the quantities to be corrected. this work was provisionally accepted on 09/15/2015, as it was only on that date that the contractor verbally requested inspection in accordance with article 394 of the "public procurement code", with the inspection being carried out between the parties and the report signed. | underwork value and negative price revision.
668 | 1295906 | CM 1028 (Moita do Boi - Antões - Guide EN 109) - Proc. No. 29/2014 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2022 | Portugal | Pombal | Leiria | 10 | 24 | 16-09-2014 | 07-02-2022 | 2701 | 90 | 180849.72 | 151000 | 1 | 118076.52 | 32923.48 | 127.8832 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the delay in the contract is due to the calculation of all the projects carried out by the contractor, recorded in the measurement report after the end of the project term. in accordance with the provisions of article 390 of the "public procurement code", measurement errors, faults were detected in the measurement records previously drawn up, which were corrected and replaced in the subsequent measurement report, in collaboration with the contractor in relation to the object and the quantities to be corrected. this work had the provisional reception on 07/04/2016 due to the fact that only on that date did the contractor verbally request the inspection in accordance with article 394 of the "public procurement code", when he delivered the duly completed rcd plan, and the inspection was carried out immediately and signed the auto. | existence of underwork and revision of orders
669 | 896677 | Improvement of the access road to Porinhos - Arões S.Romão | 45211360-0 | Urban development construction work | FALSE | 2013 | 2022 | Portugal | Fafe | Braga | 3 | 31 | 21-11-2013 | 31-03-2022 | 3052 | 150 | 238090.41 | 186680.35 | 1 | 182954.35 | 3726 | 102.0366 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was an extension of the contract period | not all the quantities foreseen for some items were executed.
670 | 207916 | Municipal Archive/Nucleus of Graphic Arts/Aljustrel Documentation Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2010 | 2022 | Portugal | Aljustrel | Beja | 2 | 91 | 28-06-2011 | 02-03-2022 | 3900 | 510 | 1080000 | 1037152.19 | 3 | 1087365.29 | -50213.1 | 95.3821 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the hiring of the necessary works to reinforce the structure and improve the drainage of rainwater took a while to start (only in 2019) so it was not possible to recover the delay and rather aggravated it. the project was subject to an extension of the execution period for another 210 days, and it is expected that it will be completed by the end of this period. another contract taking place in the same space which limited the execution of some works, lack of qualified labor in the area, delays in the delivery of materials, which led to an extension of the deadline for another 80 days. | price revisions caused changes in the value of the project.
671 | 9285499 | Execution of works related to the contract for "Conservation and improvement of the District Archive building of Viana do Castelo" | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 23-08-2019 | 15-12-2020 | 480 | 210 | 456966 | 445551.2 | 2 | 445551.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Mode of execution of the work (MEO) Weighting: 25% Criterion related to cost Name: Price (PR) Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay due to suspension due to pandemic
672 | 9126279 | Refurbishment of the HVAC installation's hot water production system | 45232141-2 | Heating works | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 27 | 03-06-2020 | 04-01-2021 | 215 | 150 | 160000 | 139805.13 | 1 | 142689.76 | -2884.63 | 97.9784 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution of the project due to facts attributable to the contractor | measurement errors in the execution project
673 | 8922584 | Rehabilitation of the engine room at the Azurara Naval Shipyards | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Vila do Conde | Porto | 13 | 15 | 26-05-2021 | 13-11-2021 | 171 | 60 | 33000 | 23696.25 | 1 | 26750.75 | -3054.5 | 88.5816 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to carry out additional work
674 | 8820310 | Public Tender "Alteration and Expansion of Home for the Elderly in Seixo de Mira" | 45000000-7 | Construction work | FALSE | 2017 | 2018 | Portugal | Mira | Coimbra | 6 | 30 | 19-06-2017 | 04-07-2018 | 380 | 300 | 181550 | 178391.54 | 1 | 178391.54 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | did not exist,
675 | 8536537 | Public Tender No. 12/DRL/DA/2021 - Air conditioning of classrooms and replacement of sanitary water heating systems in the barracks of the Portalegre Training Center | 45232141-2 | Heating works | FALSE | 2021 | 2021 | Portugal | Portalegre | Portalegre | 12 | 15 | 10-08-2021 | 29-12-2021 | 141 | 60 | 160000 | 128827.24 | 1 | 128827.24 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | failure in the supply of materials by suppliers. | nothing to say.
676 | 8426632 | Waterproofing of the Connection Area between Cells of the BRAVAL Sanitary Landfill | 45261420-4 | Waterproofing work | FALSE | 2021 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 13-09-2021 | 19-11-2021 | 67 | 20 | 65625 | 59125 | 1 | 55560 | 3565 | 106.4165 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Total price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work took place during the period strictly necessary, with the execution being influenced by adverse atmospheric conditions to the installation and application of the screens | verified deviation concerns material not delivered and material delivered but not applied
677 | 8382867 | Contract for the Rehabilitation of Exterior Spans in the Municipal District of Povos - Vila Franca de Xira | 45454100-5 | Restoration work | FALSE | 2019 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 11-09-2019 | 02-12-2020 | 448 | 120 | 123298 | 99257.87 | 1 | 99257.87 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | pricing review.
678 | 8349940 | Contract for the Rehabilitation of Houses in the Municipal Housing Park | 45454100-5 | Restoration work | FALSE | 2020 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 01-09-2020 | 22-11-2021 | 447 | 90 | 130294.5 | 45826 | 1 | 45826 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | pricing review.
679 | 8349558 | Contract for the Rehabilitation of Houses in the Municipal Housing Park | 45454100-5 | Restoration work | FALSE | 2020 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 02-09-2020 | 22-11-2021 | 446 | 90 | 130294.5 | 54784.75 | 1 | 54784.75 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | pricing review.
680 | 8348736 | Contract for the Rehabilitation of Houses in the Municipal Housing Park | 45454100-5 | Restoration work | FALSE | 2019 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 13-11-2019 | 21-09-2021 | 678 | 300 | 282990 | 100335 | 1 | 100335 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | pricing review.
681 | 8348272 | Contract for the Rehabilitation of Houses in the Municipal Housing Park | 45454100-5 | Restoration work | FALSE | 2019 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 13-11-2019 | 21-09-2021 | 678 | 300 | 282990 | 99100 | 1 | 99100 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | price review
682 | 8344312 | Contract for the rehabilitation of buildings in the municipal housing stock in arcena - alverca do ribatejo | 45454100-5 | Restoration work | FALSE | 2019 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 6 | 06-06-2019 | 02-12-2020 | 545 | 150 | 72810 | 55909 | 1 | 56060.29 | -151.29 | 99.7301 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | price review
683 | 8333839 | Cp 27/2018 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 29-01-2019 | 27-03-2020 | 423 | 365 | 297300 | 254767.51 | 2 | 254690.17 | 77.34 | 100.0304 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
684 | 8332398 | Cp 23/2018 - Extension of water supply and wastewater drainage networks in the parishes of Costa, Mesão Frio and Urzes - Guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 14-01-2019 | 01-09-2020 | 596 | 180 | 477750 | 428440.17 | 2 | 428268.63 | 171.54 | 100.0401 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
685 | 8142998 | Cp 08/2020 - Extension of wastewater drainage networks at streetJosé de Oliveira and street of Venda Nova in the parish of Ronfe | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 24-04-2020 | 05-01-2021 | 256 | 120 | 85526.66 | 83790 | 1 | 50367.13 | 33422.87 | 166.3585 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
686 | 8083009 | Requalification of streetReitor Teixeira Guedes and implantation of a roundabout at the intersection with Avenida Dr. Julio almeida tick | 45432110-8 | Floor-laying work | FALSE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 15 | 04-11-2019 | 17-05-2021 | 560 | 120 | 330187.61 | 323723.9 | 2 | 323723.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in the context of the covid-19 pandemic
687 | 8075980 | Extension of the water supply network on streetDr. José Eduardo Vieira in Arcena (Lot 1) and remodeling of the sanitation network on streetFrancisco dos Reis Sousa and streetBarreto Poeira in Vila Franca | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2021 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 19-07-2021 | 07-12-2021 | 141 | 60 | 78376 | 34730.15 | 1 | 34730.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: The award will be made on the basis of the lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in delivery of the technical compilation by the contractor firm
688 | 8072878 | Public tender no. 76/2021/dicp - t-99/2021 - requalification of the coverage of the caranguejeira health unit - leiria | 45261910-6 | Roof repair | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 21 | 17-09-2021 | 17-12-2021 | 91 | 120 | 90000 | 89000 | 1 | 89000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
689 | 7859963 | Contract for the Anticorrosive Protection of Metallic Bridges on the Belt Line, Concordance of Xabregas and Caxias Bridge, on the Cascais Line | 45221112-0 | Railway bridge construction work | FALSE | 2014 | 2021 | Portugal | N/A | N/A | N/A | N/A | 16-04-2015 | 21-08-2021 | 2319 | 152 | 680000 | 408000.01 | 2 | 375413.94 | 32586.07 | 108.68 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
690 | 7859492 | Requalification of the Brasileira road, paving the shoulders, 1st Phase. | 45233160-8 | Paths and other metalled surfaces | FALSE | 2021 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 6 | 30-08-2021 | 13-10-2021 | 44 | 90 | 26046.25 | 24985 | 1 | 24985 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
691 | 7857310 | Contract for carrying out various maintenance work at the INR Headquarters Building | 45400000-1 | Building completion work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 10-08-2021 | 31-12-2021 | 143 | 120 | 160000 | 154385.92 | 1 | 154385.92 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Lead time Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
692 | 7840371 | NPD-3021013645-AMN - Contract for Improvement of the Roof of the Captaincy of the Port of Peniche | 45261920-9 | Roof maintenance work | TRUE | 2021 | 2021 | Portugal | Peniche | Leiria | 10 | 15 | 08-09-2021 | 20-12-2021 | 103 | 30 | 65000 | 49495 | 1 | 49495 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: The constants of the Procedure Program Weighting: 0% Criterion related to cost Name: The constants of the Procedure Program Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | common agreement
693 | 7827872 | streets in Sonim | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 06-09-2021 | 27-12-2021 | 112 | 60 | 24386.95 | 24201.9 | 1 | 23536.56 | 665.34 | 102.8268 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | there was no need to proceed with the demolition of the wall object of the projects
694 | 7819706 | Public tender for the works to refurbish the pavement of municipal road 511 - the section between Sobral de São Miguel and Pedras Lavradas. | 45233251-3 | Resurfacing works | FALSE | 2021 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 27-08-2021 | 10-11-2021 | 75 | 90 | 409000 | 404964.39 | 2 | 404964.39 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value/execution time Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes | there were no changes
695 | 7818805 | CPN-50/2021 - T-47/2021 - Construction of sidewalks and various works on streetde São Miguel in the town of Ponte da Pedra - Regueira de Pontes | 45233161-5 | Footpath construction work | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 06-08-2021 | 30-11-2021 | 116 | 60 | 64511 | 54538.7 | 1 | 54538.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
696 | 7818372 | Contract for the Conservation of School Buildings EB/J1 do Livramento (Centennial Plan) and elementary school de Capelas | 45259000-7 | Repair and maintenance of plant | FALSE | 2021 | 2021 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 11 | 25-06-2021 | 25-11-2021 | 153 | 90 | 227000 | 201168.32 | 1 | 201168.32 | 0 | 100 | Lower price If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | legal suspension
697 | 7815952 | Urbanizations in the Municipality - Agunchos and Formoselos | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 6 | 20-08-2021 | 30-11-2021 | 102 | 30 | 142684.5 | 140901.37 | 1 | 135651.37 | 5250 | 103.8702 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Single factor - Lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of the execution period | underwork
698 | 7811633 | Execution of the wastewater drainage network in place of rande, parish of penafiel - 1st phase | 45232460-4 | Sanitary works | FALSE | 2020 | 2021 | Portugal | Penafiel | Porto | 13 | 21 | 15-01-2021 | 30-12-2021 | 349 | 240 | 140224.88 | 126727.98 | 1 | 139447.94 | -12719.96 | 90.8783 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | none. | pricing review.
699 | 7807951 | Rectification of rainwater networks in Lavra, R. Antão Gonçalves and R. Das pregudas | 45240000-1 | Construction work for water projects | FALSE | 2021 | 2021 | Portugal | Matosinhos | Porto | 13 | 15 | 18-08-2021 | 15-11-2021 | 89 | 30 | 30000 | 22410 | 1 | 22410 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
700 | 7799729 | Cpn 48/2021/dicp - t-72/2021 - expansion of windmill street - hives | 45233120-6 | Road construction works | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 20 | 10-08-2021 | 06-12-2021 | 118 | 90 | 114000 | 97868 | 1 | 97868 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
701 | 7791616 | Public tender for works on the Porsim path - paving work, horizontal and vertical traffic signs and security guards | 45233120-6 | Road construction works | FALSE | 2021 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 22-07-2021 | 18-11-2021 | 119 | 120 | 320000 | 298706.85 | 2 | 298706.85 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Proposed Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline for carrying out the project. there was approval of the specific safety plan 01 - contract deviation plan on august 25, 2021.
702 | 7790304 | Bituminous carpet paving on the Atalaia - EM 574 connection branch | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 09-08-2021 | 20-09-2021 | 42 | 122 | 161725 | 160650 | 1 | 160650 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation of work by the contractor
703 | 7790300 | Paving of rural paths in the parish of Alto do Palurdo - Vale de Madeira and Mangide | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 6 | 09-08-2021 | 09-12-2021 | 122 | 122 | 20657.1 | 20657.1 | 1 | 20657.1 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
704 | 7789873 | Eb 2/3 School of Santa Marinha do Zêzere - Requalification | 45454000-4 | Restructuring work | FALSE | 2021 | 2021 | Portugal | Baião | Porto | 13 | 18 | 22-07-2021 | 17-11-2021 | 118 | 90 | 390079.19 | 385389.77 | 2 | 385389.77 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% Diário da República, 2nd series No. 7268 June 1, 2021 Page 4 | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
705 | 7788660 | Public Tender No. 22/DRL/DA/2020 - Painting and Replacement of the Covering of the São João da Madeira Traffic Detachment | 45261200-6 | Roof-covering and roof-painting work | FALSE | 2020 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 14 | 21-12-2020 | 31-07-2021 | 222 | 70 | 105000 | 73000 | 1 | 73000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | due to the covid-19 pandemic.
706 | 7782434 | Contract for the execution of support walls in the parishes of Aldeia das Dez and São Gião | 45262300-4 | Concrete work | FALSE | 2021 | 2021 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 03-08-2021 | 21-12-2021 | 140 | 90 | 177000 | 130419.88 | 1 | 113757.69 | 16662.19 | 114.6471 | Best value for money: No Criterion related to quality Name: N/A Weighting: 100% Criterion related to cost Name: Criterion of the most economically advantageous proposal, in the modality of the lowest price low. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | existence of extension | existence of works
707 | 7781293 | CPN 57/2021/DICP - T-76/2021 - Execution of a rainwater collector to drain the watershed surrounding street of Restauração and street of Facho, in the town of Alcogulhe - UF de Parceiros e Azoia | 45232450-1 | Drainage construction works | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 15-07-2021 | 04-10-2021 | 81 | 30 | 46105.8 | 37907.28 | 1 | 37907.28 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
708 | 7775170 | Contracts for "repair of the sports venue at the elementary and High school Dr. Luis Maurílio da Silva Dantas, in Câmara de Lobos" and "repair of the sports center and coverage of the Primary School | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Santana | Região Autónoma da Madeira | 14 | 7 | 09-07-2021 | 05-11-2021 | 119 | 90 | 250000 | 98363.38 | 1 | 98363.38 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the term initially provided for in the contract
709 | 7775147 | Contracts for "repair of the sports venue at the elementary and High school Dr. Luis Maurílio da Silva Dantas, in Câmara de Lobos" and "repair of the sports center and coverage of the Primary School | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 7 | 09-07-2021 | 22-10-2021 | 105 | 90 | 250000 | 95957.5 | 1 | 95957.5 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the deadline.
710 | 7774861 | Construction of pontoons - Friões | 45262423-2 | Deck-fabrication work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 12-07-2021 | 25-11-2021 | 136 | 60 | 20078.58 | 18369.71 | 1 | 18790.91 | -421.2 | 97.7585 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
711 | 7773528 | CPN 54/2021/DICP - T - 12/2021 - Requalification of the road pavement at street of Ordem - Andrinos - Pousos, street of Romeiros - Cruz da Areia - Leiria, street ofutor Magalhães Manuel Pessoa, streetJoão de Deus | 45233141-9 | Road-maintenance works | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 13-07-2021 | 16-11-2021 | 126 | 60 | 119364.5 | 110994 | 1 | 110994 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
712 | 7773421 | Cpn 41/2021/dicp - t - 62/2021 - execution of the 2017/2018 participatory budget - contract for the execution of projects - proposal no. 7 eb1 a-dos-pretos/maceira - mobile protection of the covered playground | 45454000-4 | Restructuring work | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 13-07-2021 | 28-10-2021 | 107 | 60 | 18600 | 17700 | 1 | 17700 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
713 | 7772874 | Construction of horizontal signage in the Municipality - (Valpaços) | 45233221-4 | Road-surface painting work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 12-07-2021 | 25-11-2021 | 136 | 60 | 60165 | 37468.8 | 1 | 38082.08 | -613.28 | 98.3896 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
714 | 7771745 | 2021_CP_005 - ESA coverage improvement contract - POSEUR | 45260000-7 | Roof works and other special trade construction works | FALSE | 2021 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 15 | 09-07-2021 | 18-11-2021 | 132 | 120 | 184000 | 173491.8 | 1 | 173491.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
715 | 7770419 | Paving of streets at Pinhel Station. | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 16-07-2021 | 15-11-2021 | 122 | 122 | 24968 | 24480 | 1 | 24480 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
716 | 7770102 | Paving with bituminous carpet on the branch connecting Penhaforte - Pomares | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 16-07-2021 | 15-11-2021 | 122 | 122 | 134837.51 | 94071.16 | 1 | 94071.16 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
717 | 7768839 | Paving in bituminous carpet on the branch connecting Pomares - county boundary (Toito, Ribeira dos Carinhos). | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 16-07-2021 | 15-11-2021 | 122 | 122 | 17527.5 | 16177 | 1 | 16177 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
718 | 7760861 | Replacement of the synthetic turf on the Faial 11 football field | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2021 | 2021 | Portugal | Vila Verde | Braga | 3 | 9 | 07-07-2021 | 31-08-2021 | 55 | 45 | 100000 | 94817.25 | 1 | 94817.25 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
719 | 7760856 | Paving with bituminous carpet on the Carvalhal (Atalaia) - Manigoto branch line. | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 09-07-2021 | 08-11-2021 | 122 | 122 | 194431.25 | 189118.75 | 1 | 189118.75 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
720 | 7757982 | Roof replacement works, among other works - E. B. 1st cycle of Oliveira S. Mateus | 45261900-3 | Roof repair and maintenance work | FALSE | 2021 | 2021 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 02-06-2021 | 31-08-2021 | 90 | 75 | 125000 | 89293.4 | 1 | 89293.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed ahead of schedule.
721 | 7754332 | Water supply in Alfonge | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 12-07-2021 | 25-11-2021 | 136 | 90 | 19505.6 | 18000 | 1 | 18909.01 | -909.01 | 95.1927 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
722 | 7753120 | Contract for the work of "Transposition by fish of an existing obstacle in the watercourse, Rio Mouro, tributary of the Rio Minho_ Financed by POCTEP 2020_0016_MIGRA_MIÑO_MINHO_1_E_ ACTIVITY 1 | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2021 | Portugal | N/A | N/A | N/A | 14 | 26-03-2021 | 19-11-2021 | 238 | 45 | 82011 | 81892.86 | 1 | 81892.86 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | on that date, it was verified that the flow of the river mouro, where a substantial part of the actions related to the present contract take place, is greater than would be foreseeable at this time of the year, namely in comparison with past years and on which the costs were estimated. working days specified in the current contract, which implies increased delay in the intervention of the machines on the bed, as well as increased care in work carried out in the water. such reason constitutes an abnormal and unpredictable change in the circumstances initially contracted. in order to ensure compliance with the objectives described for the contract, based on correct execution without prejudice to the same or safety on site, this implies an increased deadline for its execution.
723 | 7752316 | Public tender for the contract for requalification works of various pavements on Municipal Road 513 (Parishes of Dominguizo and Union of Parishes of Peso and Vales do Rio) | 45233251-3 | Resurfacing works | FALSE | 2021 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 28-06-2021 | 17-11-2021 | 142 | 75 | 404500 | 387189.84 | 2 | 381189.84 | 6000 | 101.574 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Proposed Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project. there was an inspection on the 17th of november of the year 2021. | the amended version was approved and adapted to the start date of the projects, payment plan and financial schedule of the contract, on august 9, 2021.
724 | 7749529 | Supply and assembly of LED projectors, crowns, steel and electrical cables, at the ro-ro terminal in the port of Setubal | 45310000-3 | Electrical installation work | TRUE | 2020 | 2021 | Portugal | Setúbal | Setúbal | 17 | 45 | 01-09-2020 | 01-03-2021 | 181 | 150 | 215000 | 166000 | 1 | 166000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Factor B - Work Methodology and Planning Weighting: 30% Criterion related to cost Name: Factor A - Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | ended within 150 days
725 | 7749305 | Rehabilitation of the walkways inside the fontaínhas dock | 45241500-3 | Wharf construction work | TRUE | 2020 | 2021 | Portugal | Setúbal | Setúbal | 17 | 15 | 26-11-2020 | 14-07-2021 | 230 | 150 | 275000 | 274840 | 2 | 274840 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Factor B - Work Methodology and Planning Weighting: 30% Criterion related to cost Name: Factor A - Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completed before the 150-day deadline
726 | 7747208 | Construction of horizontal signage in the Municipality | 45233221-4 | Road-surface painting work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 24-06-2021 | 13-12-2021 | 172 | 60 | 91617.6 | 72719 | 1 | 73245.88 | -526.88 | 99.2807 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation caused by covid 19, delay in receiving materials for the execution of the project and weather conditions not favorable to the execution of the projects | non-execution of some planned works
727 | 7745523 | Cpn 25/2021/dicp - t-35/2021 - requalification of the en 356-1 road pavement, in the section between the firemen roundabout/campos roundabout - maceira | 45233220-7 | Surface work for roads | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 26-05-2021 | 06-12-2021 | 194 | 45 | 179100 | 160151.25 | 1 | 160151.25 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
728 | 7745161 | NPD-3021011198-AMN - Contract to Repair the Communications Tower of the Port Authority of Olhão | 45232332-8 | Ancillary works for telecommunications | FALSE | 2021 | 2021 | Portugal | Olhão | Faro | 8 | 9 | 02-07-2021 | 29-11-2021 | 150 | 30 | 25000 | 24950 | 1 | 24950 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the Procedure Program Weighting: 0% Criterion related to cost Name: The constants of the Procedure Program Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | common agreement
729 | 7744802 | Contract 377/gebalis/2020 - rehabilitation of municipal buildings - parish marvila - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 26 | 28-06-2021 | 12-11-2021 | 137 | 60 | 471000 | 61821.4 | 1 | 61821.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 30 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
730 | 7744792 | Contract 377/gebalis/2020 - rehabilitation of municipal buildings - parish marvila - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 26 | 28-06-2021 | 16-09-2021 | 80 | 90 | 471000 | 76236 | 1 | 76236 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 30 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | in accordance
731 | 7739944 | Contract 378/gebalis/2020 - rehabilitation of municipal buildings -parish areeiro / beato / penha frança / s. Vicente - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 22 | 29-06-2021 | 26-11-2021 | 150 | 60 | 366000 | 52480 | 1 | 52480 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 24 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
732 | 7739484 | Contract 379/gebalis/2020 - rehabilitation of municipal buildings - parish alcântara - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 28-06-2021 | 02-08-2021 | 35 | 60 | 150000 | 52296.58 | 1 | 52296.58 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 22 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
733 | 7739423 | Contract 396/gebalis/2020 - vale de alcântara neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 29-06-2021 | 05-07-2021 | 6 | 90 | 108800 | 35802.45 | 1 | 35802.45 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
734 | 7737763 | Repair of sidewalks in the village of Abrunheiro Grande | 45233160-8 | Paths and other metalled surfaces | FALSE | 2021 | 2021 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 31-05-2021 | 17-12-2021 | 200 | 120 | 80000 | 74768.75 | 1 | 74768.75 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no deadline changes. | there were no changes to the value of the project
735 | 7730819 | Improvement, Expansion, Repair and Improvements in the Schools of the Municipality-Schools of the Almancil Grouping | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 14 | 14-06-2019 | 09-03-2021 | 634 | 45 | 239500 | 211996.8 | 1 | 199997 | 11999.8 | 106 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the contract period, there was only a delay in the execution of the provisional acceptance | the amount was placed with vat due to an error
736 | 7726452 | NPD-3021006181-AMN - Contract for Installation of the ITED Network at GAT Azinheira - Seixal | 45232332-8 | Ancillary works for telecommunications | FALSE | 2021 | 2021 | Portugal | Seixal | Setúbal | 17 | 15 | 08-06-2021 | 02-12-2021 | 177 | 57 | 95755 | 95000 | 1 | 95000 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the Procedure Program Weighting: 0% Criterion related to cost Name: The constants of the Procedure Program Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | common agreement
737 | 7722349 | CPN-27/2021 - T-38/2021 - Refurbishment of the Pavement of street ofs Sismarias (connection of the town of Sismaria to the E.N. 109-9 Coimbrão), in the town of Sismaria - Union of Parishes of Monte Redondo | 45233220-7 | Surface work for roads | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 31-05-2021 | 30-07-2021 | 60 | 45 | 79927.5 | 79504 | 1 | 79504 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
738 | 7703706 | Repair of streets in the Municipality of Vila de Rei | 45233200-1 | Various surface works | FALSE | 2021 | 2021 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 27-05-2021 | 27-10-2021 | 153 | 60 | 235000 | 211151.95 | 1 | 207127.61 | 4024.34 | 101.9429 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline. | underwork.
739 | 7701631 | Bituminous carpet paving on the Safurdão connection branch - Pínzio junction, A25, Miragaia (EM 574). | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 31-05-2021 | 28-09-2021 | 120 | 120 | 167800 | 165490 | 1 | 165490 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
740 | 7701096 | Contract 379/gebalis/2020 - rehabilitation of municipal buildings - parish alcântara - lisbon | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 09-06-2021 | 13-10-2021 | 126 | 60 | 150000 | 54922.38 | 1 | 34993.62 | 19928.76 | 156.9497 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 22 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
741 | 7699739 | Reduction of energy consumption in public lighting in the municipality of mogadouro: led public lighting ii | 45211360-0 | Urban development construction work | FALSE | 2021 | 2021 | Portugal | Mogadouro | Bragança | 4 | 30 | 19-05-2021 | 12-11-2021 | 177 | 90 | 146000 | 110299.48 | 1 | 110299.48 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Energy Efficiency of Tech.LED Luminaires - 40% ; Warranty Period Tech light fixtures LED-10% Diário da República, 2nd series No. 2582 March 1, 2021 Page 4 Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the authorization of e-redes and the municipality for initiation of works.
742 | 7699332 | Contract 11/gebalis/2021 - Bela Flor neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Lisboa | Lisboa | 11 | 14 | 04-06-2021 | 13-08-2021 | 70 | 90 | 96350 | 58650 | 1 | 58650 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 22 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
743 | 7698325 | Contract for the Improvement of the Recreational Area of ​​the EB of S. Roque da Lameira | 45453000-7 | Overhaul and refurbishment work | FALSE | 2021 | 2021 | Portugal | Porto | Porto | 13 | 21 | 07-06-2021 | 02-12-2021 | 178 | 75 | 80000 | 68972.59 | 1 | 70885.38 | -1912.79 | 97.3016 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractual provisions. 30 days were granted to correct defects contained in the inspection report of 9/20/2021 | complementary work worth €1912.80
744 | 7697389 | NPD-3021007234-AMN - Contract for Energy Efficiency in the Captaincy of VRSA | 45320000-6 | Insulation work | FALSE | 2021 | 2021 | Portugal | Vila Real Sto Antonio | Faro | 8 | 15 | 26-05-2021 | 06-12-2021 | 194 | 60 | 45000 | 41923.84 | 1 | 41923.84 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constituents of the procedure parts Weighting: 0% Criterion related to cost Name: The constituents of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | common agreement
745 | 7696342 | 2019.063.01.C1 - SE de Viseu - Remodeling of the HVAC system, electrical installations and architecture | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2021 | 2021 | Portugal | Viseu | Viseu | 20 | 25 | 23-04-2021 | 21-12-2021 | 242 | 210 | 495000 | 435438.5 | 2 | 479625.16 | -44186.66 | 90.7873 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works. provisional and final price review
746 | 7691428 | Urbanization of Vilacetinho and surrounding roads | 45233251-3 | Resurfacing works | FALSE | 2021 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 31-05-2021 | 10-12-2021 | 193 | 90 | 253940 | 242831.31 | 1 | 229864.04 | 12967.27 | 105.6413 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time | underwork, price review.
747 | 7689649 | Fever Sports Park, by Contract: Rehabilitation works on the changing room and bench - CP-CCP-EMP n.º 07/2021 | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2021 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 31-05-2021 | 14-12-2021 | 197 | 60 | 86740.5 | 59147 | 1 | 63227 | -4080 | 93.5471 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works.
748 | 7682598 | Contract 104/GEBALIS/2020 - Public Tender for Rehabilitation of municipal housing - Bairro Armador | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 16 | 25-05-2021 | 10-12-2021 | 199 | 90 | 125000 | 89199.98 | 1 | 88274.98 | 925 | 101.0479 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 20 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
749 | 7675581 | Public Tender No. 165/2020 - Construction Works for the New Refrigerator Area of ​​the Microbiology Service | 45000000-7 | Construction work | TRUE | 2021 | 2021 | Portugal | Porto | Porto | 13 | 15 | 08-03-2021 | 06-12-2021 | 273 | 30 | 49000 | 48972.44 | 1 | 55120.91 | -6148.47 | 88.8455 | Best value for money: Yes Criterion related to quality Name: Analyze works+technical report site visit Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
750 | 7664282 | Paving contract for a section of streetJoaquim Maria Cabral, street ng.º Alberto Rodrigues, street ng.º Eugénio Ataíde da Câmara and street duardo Soares de Albergaria, Valados - Relva (Lot 1) | 45233220-7 | Surface work for roads | FALSE | 2021 | 2021 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 11 | 12-05-2021 | 19-11-2021 | 191 | 45 | 160000 | 157798.2 | 1 | 157798.2 | 0 | 100 | Lower price If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project.
751 | 7664037 | Arrangement of the tank and surrounding area in Crasto - Phase II | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 21 | 14-05-2021 | 21-12-2021 | 221 | 120 | 30911.89 | 29701 | 1 | 31285.41 | -1584.41 | 94.9356 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | employees or contractor infected by covid-19 and unavailability of essential materials for the normal development of the project | ordinary price review
752 | 7663985 | streets in Nozedo | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-05-2021 | 29-10-2021 | 172 | 90 | 31359.08 | 29650.5 | 1 | 30962.43 | -1311.93 | 95.7628 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
753 | 7663419 | Water supply to Corveira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-05-2021 | 19-10-2021 | 162 | 90 | 28556.33 | 26920 | 1 | 29945.24 | -3025.24 | 89.8974 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
754 | 7652450 | Removal of Fiber Cement from the elementary school of the 2nd and 3rd Cycles José Régio | 45261210-9 | Roof-covering work | FALSE | 2021 | 2021 | Portugal | Portalegre | Portalegre | 12 | 30 | 10-05-2021 | 29-06-2021 | 50 | 120 | 125226.25 | 106612 | 1 | 106612 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price assessment/ Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | advancement of the project plan
755 | 7652447 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school… | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 07-12-2021 | 235 | 90 | 1733000 | 196109.98 | 1 | 203245.98 | -7136 | 96.489 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
756 | 7652148 | Tender for Lots for the Contract for "Replacing Fiber Cement Roofs in Barreiro elementary Schools", by lots: Lot 1 - D. Luís mendonça Primary School furtado lot 2 - primary school | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 30 | 16-04-2021 | 20-12-2021 | 248 | 90 | 1733000 | 141461.49 | 1 | 151437.27 | -9975.78 | 93.4126 | Best value for money: Yes Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 12187 October 28, 2020 Page 4 Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
757 | 7631634 | Execution of abstractions in Rebordãos and Carragosa | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Bragança | Bragança | 4 | 20 | 26-04-2021 | 27-10-2021 | 184 | 120 | 69150 | 68984 | 1 | 68984 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work started on september 16, 2021 and completed on october 26, 2021.
758 | 7629785 | Urgent Public Tender for awarding the contract for the Reinforcement and Stabilization of an Excavation Slope on the Connecting Road between Maia and Lombinha da Maia - PK0+192,500 to PK0+227,500 | 45000000-7 | Construction work | TRUE | 2021 | 2021 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | N/A | 22-04-2021 | 23-10-2021 | 184 | 120 | 266411.86 | 266393.53 | 2 | 266393.53 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 1 | FALSE | N/A | N/A | N/A | N/A | FALSE
759 | 7627033 | Cpn 44/2020/dicp - t-32/2020 - slope stabilization on street of lapedo union of parishes of santa eufémia and boa vista | 45111230-9 | Ground-stabilisation work | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 03-08-2020 | 30-04-2021 | 270 | 90 | 35893.75 | 34446.99 | 1 | 34446.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
760 | 7619276 | Access to the National Guard and AAS in the Urban Park of Geão | 45262423-2 | Deck-fabrication work | FALSE | 2021 | 2021 | Portugal | Santo Tirso | Porto | 13 | 14 | 16-04-2021 | 16-12-2021 | 244 | 90 | 28054.65 | 27965.1 | 1 | 26865.1 | 1100 | 104.0945 | Best value for money: No Criterion related to quality Name: None Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the non-execution of some contractual works (underwork)
761 | 7615514 | "Plan for the eco-valorization of educational establishments" - (Installation of Photovoltaic Self-Consumption Units in elementary and JI Schools, 1st Phase) | 45310000-3 | Electrical installation work | FALSE | 2020 | 2021 | Portugal | Loulé | Faro | 8 | 30 | 23-11-2020 | 24-11-2021 | 366 | 150 | 343500 | 188308.4 | 1 | 180354.11 | 7954.29 | 104.4104 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork.
762 | 7614431 | Execution of c.m.593 a paradela - improvement and rectification of e.m. 593 Between Remondes and the e.n.216. | 45233200-1 | Various surface works | FALSE | 2021 | 2021 | Portugal | Mogadouro | Bragança | 4 | 21 | 09-04-2021 | 28-09-2021 | 172 | 365 | 292367.95 | 291000 | 2 | 333317.14 | -42317.14 | 87.3042 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price or Cost Assessment-line b) of paragraph 1 of Article 74 of the CCP-(Code of Public Contracts) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | accomplishment of complementary works
763 | 7613858 | 2019/72 - DGEP - Praia da Torre-Praia de Carcavelos connection (2nd phase), Oeiras " | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 15 | 19-07-2019 | 12-07-2021 | 724 | 75 | 100284.24 | 96400 | 1 | 94758.94 | 1641.06 | 101.7318 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
764 | 7612148 | 2020_CP_010 - Contract for the Thermal Power Station of ESTG - POSEUR | 45232141-2 | Heating works | TRUE | 2020 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 17-03-2021 | 19-07-2021 | 124 | 60 | 123993.71 | 93915.19 | 1 | 93915.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
765 | 7611082 | Contract for requalification of spaces for the Project Management Office on the Gualtar campus of the University of Minho, in Braga. (Cp/eop usgci-19/2020) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 14 | 30-03-2021 | 29-11-2021 | 244 | 60 | 65500 | 57496.38 | 1 | 55696.35 | 1800.03 | 103.2319 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the time of completion of the contractual work, they were not in a position to be received. | underwork in accordance with article 4.1.1.3 of the unit price list.
766 | 7610713 | Public Tender for the execution of the contract for requalification of the Vale Rabelho road, in Guia | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 31-03-2021 | 19-10-2021 | 202 | 60 | 180000 | 154459.53 | 1 | 154459.53 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
767 | 7603873 | Construction of Social Housing in Mosteiros - Construction of 1 - T3 and 4 - T2 | 45211300-2 | Houses construction work | FALSE | 2019 | 2021 | Portugal | Arronches | Portalegre | 12 | 18 | 28-02-2020 | 25-08-2021 | 544 | 365 | 305712.8 | 305397.46 | 2 | 312347.46 | -6950 | 97.7749 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works and project doubts | complementary works
768 | 7600840 | Contract for "Layouts in various places in the Municipality (Corveira) - Connection of the EM 314 to Corveira" | 45233200-1 | Various surface works | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 18 | 22-03-2021 | 08-10-2021 | 200 | 150 | 136653.36 | 124794.86 | 1 | 121490.51 | 3304.35 | 102.7198 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | consignment signed on april twelfth. | underwork worth €3,304.35
769 | 7599710 | Eb1 and kindergarten - improvement of thermal conditions | 45321000-3 | Thermal insulation work | FALSE | 2021 | 2021 | Portugal | Mogadouro | Bragança | 4 | 21 | 24-03-2021 | 22-11-2021 | 243 | 120 | 208271.87 | 199593.44 | 1 | 199593.44 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most Economically Advantageous Proposal-Art. 74.º, nº 1, line b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the decision to change led`s interior lighting models and delay in the supply of this material.
770 | 7598571 | Small Works Contract 2021 P.PORTO - Common Services - Presidential Building and Exterior Arrangements | 45453100-8 | Refurbishment work | FALSE | 2021 | 2021 | Portugal | Porto | Porto | 13 | 21 | 31-03-2021 | 21-12-2021 | 265 | 120 | 289381 | 62102.13 | 1 | 47523 | 14579.13 | 130.6781 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Diário da República, 2nd series No. 893 January 25, 2021 Page 4 Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | covid-19 pandemic | works that it was not necessary to carry out due to an error in measuring the spaces.
771 | 7598370 | Contract for "Renovation of Fiber Cement Roofing in Barreiro elementary Schools" | 45262660-5, 45261213-0 | Asbestos-removal work, Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 21 | 26-01-2021 | 27-12-2021 | 335 | 60 | 120000 | 96259.93 | 1 | 96259.93 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
772 | 7596867 | Contract for "Roads in Pardelinha - Section of EM 544" | 45233220-7 | Surface work for roads | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 18 | 22-03-2021 | 17-05-2021 | 56 | 60 | 61337.75 | 51059 | 1 | 51059 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | works were performed before the end date.
773 | 7596861 | Contract for "Construction of a wall in Veiga de Lila" | 45262310-7 | Reinforced-concrete work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 18 | 25-03-2021 | 23-06-2021 | 90 | 90 | 40070.52 | 39410 | 1 | 39410 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | works were performed before the end date.
774 | 7596852 | Contract for "Layouts in Valpaços - streetFernão de Magalhães" | 45432110-8 | Floor-laying work | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 18 | 25-03-2021 | 23-07-2021 | 120 | 90 | 27613.49 | 26617 | 1 | 26617 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the current pandemic situation of covid-19, conditioned the delivery of the necessary material for the execution of the project in the foreseen time.
775 | 7595438 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 31-03-2021 | 18-11-2021 | 232 | 120 | 1830000 | 184731.24 | 1 | 204072.18 | -19340.94 | 90.5225 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | final price revision values
776 | 7595433 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 31-03-2021 | 18-11-2021 | 232 | 120 | 1830000 | 130129.73 | 1 | 143756.65 | -13626.92 | 90.5208 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | final price revision values.
777 | 7595426 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 31-03-2021 | 18-11-2021 | 232 | 120 | 1830000 | 185094 | 1 | 205590.79 | -20496.79 | 90.0303 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | final pricing review.
778 | 7595418 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 31-03-2021 | 18-11-2021 | 232 | 120 | 1830000 | 216360.12 | 1 | 240571.72 | -24211.6 | 89.9358 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | values ​​from the final price revision.
779 | 7595246 | Cp 31/2020 - extension of water supply networks and wastewater sanitation networks in the parish of nespereira and u. F. From conde and gandarela - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 26-02-2021 | 22-10-2021 | 238 | 120 | 272000 | 271924.98 | 2 | 249655.29 | 22269.69 | 108.9202 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | extension | underwork
780 | 7589104 | Contract 372/gebalis/2020 - Bairro Alta Lisboa - Rehabilitation of municipal buildings - Red Cross rehousing process | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 14 | 26-03-2021 | 24-09-2021 | 182 | 60 | 71850 | 46845 | 1 | 46845 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
781 | 7588260 | Contract - Remodeling of Minor Surgery in the Outpatient Clinic of the Torres Vedras Hospital Unit of Centro Hospitalar do Oeste | 45215100-8 | Construction work for buildings relating to health | FALSE | 2019 | 2020 | Portugal | Caldas da Rainha | Leiria | 10 | 14 | 09-10-2019 | 07-01-2020 | 90 | 60 | 98047 | 82747.35 | 1 | 82747.35 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
782 | 7584175 | Cp 22/2018 – rehabilitation of wastewater collectors using cipp technology, in the municipalities of guimarães and vizela | 45232460-4 | Sanitary works | FALSE | 2018 | 2021 | Portugal | Vizela | Braga | 3 | 14 | 25-01-2019 | 10-02-2021 | 747 | 365 | 165140 | 124394 | 1 | 116518.98 | 7875.02 | 106.7586 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
783 | 7584120 | Refurbishment of outdoor playground ji/ primary school wall 4 | 45112700-2 | Landscaping work | FALSE | 2021 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 24-03-2021 | 12-11-2021 | 233 | 30 | 184098.26 | 175248.31 | 1 | 175248.31 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
784 | 7582635 | Cp 24/2020 - Milling and replacement of pavements in interventions at Vimágua, in the municipalities of Guimarães and Vizela | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 25-11-2020 | 23-12-2021 | 393 | 365 | 74535 | 73530 | 1 | 73529.93 | 0.07 | 100.0001 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
785 | 7581847 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 22-03-2021 | 18-11-2021 | 241 | 120 | 1830000 | 231673 | 1 | 252777.35 | -21104.35 | 91.651 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | values ​​from the final price revision.
786 | 7581765 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 22-03-2021 | 18-11-2021 | 241 | 120 | 1830000 | 252534.5 | 2 | 278794 | -26259.5 | 90.581 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | final price revision values.
787 | 7581618 | Replacement of asbestos-containing fiber cement roofs in six elementary schools (2nd and 3rd cycles) and one High school in the Municipality of Moita - By Lots | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 21 | 22-03-2021 | 18-11-2021 | 241 | 120 | 1830000 | 187853 | 1 | 207042.89 | -19189.89 | 90.7314 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | final price revision values
788 | 7580666 | 2020.517.07.C1 - SC do IEFP - Renovation of the bar, cafeteria and kitchen | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 10 | 09-02-2021 | 12-07-2021 | 153 | 90 | 90000 | 69303.91 | 1 | 69303.91 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
789 | 7571873 | PRC_0399/2020 - EB0612 - Extensions of wastewater drainage networks in the parishes of Santa Eulália and Urrô (2nd Phase) (Arouca) | 45232411-6 | Foul-water piping construction work | TRUE | 2020 | 2021 | Portugal | Arouca | Aveiro | 1 | 14 | 15-03-2021 | 02-11-2021 | 232 | 90 | 194000 | 184680.28 | 1 | 173316.92 | 11363.36 | 106.5564 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful 60-day extension | underwork done
790 | 7571231 | Removal of asbestos-containing roofs and placement of new roofs on EB 2.3 in Algoz and EB 2.3 Dr. António da Costa Contreiras from Armação de Pêra. | 45262660-5, 45261213-0 | Asbestos-removal work, Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Silves | Faro | 8 | 31 | 01-03-2021 | 27-12-2021 | 301 | 60 | 352136.28 | 260603.7 | 2 | 227191.11 | 33412.59 | 114.7068 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to say | nothing to say
791 | 7570989 | Arrangements and Walks at the Parish Meirinhas Headquarters (Requalification of Bela Vista, Cabine and Vale streets ) - Proc. No. 63/2019 | 45233253-7 | Surface work for footpaths | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 21 | 21-01-2020 | 12-11-2021 | 661 | 120 | 162627.94 | 113795.53 | 1 | 108303.66 | 5491.87 | 105.0708 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic | existence of underwork and value of price revision.
792 | 7568255 | streets in Valpaços - Paving of streets in Alto do Gaspar | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 10-03-2021 | 03-11-2021 | 238 | 90 | 21401.9 | 20847.5 | 1 | 21180.85 | -333.35 | 98.4262 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conditioning caused by the covid-19 pandemic in the execution of works and supply of materials to be used | the total planned walkway area has not been implemented / ordinary price review
793 | 7567108 | Contract for the rehabilitation of the stairs and fenders of the fish unloading pier at the fishing port of Vila Real Santo António | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Vila Real Sto Antonio | Faro | 8 | 10 | 24-11-2020 | 26-03-2021 | 122 | 60 | 33000 | 28596.13 | 1 | 29890.38 | -1294.25 | 95.67 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal in the price assessment mode. Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of materials (fenders) due to contingencies imposed by the covid19 pandemic and waiting for the necessary tide states to carry out the project to fix the stairs at the lower points. | complementary works necessary for the correct fixation of the stairs.
794 | 7566149 | streets in Valpaços - street of Crasta | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 15-03-2021 | 05-08-2021 | 143 | 60 | 9055.3 | 8847 | 1 | 8847 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
795 | 7563848 | Renovation of the Professor Ribeirinha Machado School Pavilion (Asbestos Removal) | 45454000-4 | Restructuring work | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 30 | 11-03-2021 | 14-06-2021 | 95 | 180 | 210816.04 | 188917.46 | 1 | 201665.84 | -12748.38 | 93.6785 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
796 | 7541526 | Replacement and Assembly of Three Solar Systems and Boilers for Apartments nº 1 to 41, in the Building Next to the Meeting Room and Spa Located in the middle of the CFCC Campsite | 45400000-1 | Building completion work | FALSE | 2020 | 2021 | Portugal | Almada | Setúbal | 17 | 21 | 08-02-2021 | 28-07-2021 | 170 | 120 | 175000 | 141199.5 | 1 | 141199.5 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to add
797 | 7540419 | Contract to Improve Energy Efficiency at the Center for Judicial Studies | 45331220-4 | Air-conditioning installation work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 24 | 05-02-2021 | 06-10-2021 | 243 | 180 | 354630 | 297553.63 | 2 | 291533.88 | 6019.75 | 102.0649 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay due to unavailability of material. | reduction in value, due to the failure to carry out planned work that was not necessary.
798 | 7540123 | Acquisition of Six Bungalows (T-1) for the Costa de Caparica Holiday Camp, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2020 | 2021 | Portugal | Almada | Setúbal | 17 | 21 | 05-03-2021 | 14-10-2021 | 223 | 180 | 200000 | 193900 | 1 | 193900 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
799 | 7540062 | Water supply to Deimões | 45247270-3 | Reservoir construction works | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 09-03-2021 | 28-12-2021 | 294 | 90 | 27321.54 | 26300 | 1 | 26986.62 | -686.62 | 97.4557 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation caused by covid-19 and delay in the supply of materials for carrying out the project and hiring the respective qualified workforce. | ordinary price review
800 | 7539968 | Water supply to Paranhos | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 04-03-2021 | 14-09-2021 | 194 | 120 | 73365.53 | 66910.25 | 1 | 74562.55 | -7652.3 | 89.7371 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
801 | 7539917 | streets in Zebras | 45233252-0 | Surface work for streets | FALSE | 2021 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 09-03-2021 | 10-08-2021 | 154 | 90 | 12274.85 | 11665 | 1 | 11665 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
802 | 7538037 | Complete Refurbishment of the Exterior, Water Column, Electricity and New Roofing in the Building, in street of Açores, Barreiro, Property of the Social services of the National Guard | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 21 | 29-01-2021 | 14-10-2021 | 258 | 90 | 90000 | 75547.5 | 1 | 75547.5 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
803 | 7537611 | 2019/21 - DCAD - Various paintings in civil construction elements of municipal buildings | 45442100-8 | Painting work | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 18 | 19-07-2019 | 01-09-2021 | 775 | 900 | 121500 | 91950 | 1 | 91950 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
804 | 7534104 | 1400007/2020 Adaptation contract for Covid Zones and Refurbishment of the Emergency Service at Hospital do Barreiro | 45454000-4 | Restructuring work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 15 | 09-10-2020 | 03-08-2021 | 298 | 150 | 250000 | 216200.2 | 1 | 216200.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the pandemic delayed the projects
805 | 7534076 | Construction of the Headquarters Building of the Parish Council of Moita | 45210000-2 | Building construction work | FALSE | 2017 | 2020 | Portugal | Moita | Setúbal | 17 | 30 | 20-08-2018 | 28-12-2020 | 861 | 480 | 433000 | 395917.5 | 2 | 453856.69 | -57939.19 | 87.234 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Price (P) - 75% (Fp); b) Technical Quality of the Proposal (Q) - 25% (Fq) (Refer to clause 14 of the Program of Procedure) | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | technical conditions work / covid 19 pandemic | unforeseen and essential works for the good execution of the project
806 | 7533093 | Contract for improvement works and replacement of roofs and window frames in 2nd/3rd cycle and High schools in the Municipality of Cascais | 45261900-3 | Roof repair and maintenance work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 10 | 03-03-2021 | 13-10-2021 | 224 | 30 | 7218652.3 | 423130.88 | 2 | 423130.88 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A
807 | 7532974 | Requalification of the Fair Space and Economic Activities and Market in Arronches | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Arronches | Portalegre | 12 | 18 | 09-09-2020 | 31-05-2021 | 264 | 90 | 163525.17 | 155000 | 1 | 155000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | heavy rains that did not let the machines work and project doubts
808 | 7511273 | Public works contract for the introduction of traffic lights for pedestrians on Av. of the Armed Forces | 45113000-2 | Siteworks | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 18 | 22-02-2021 | 16-09-2021 | 206 | 49 | 35000 | 29425.05 | 1 | 29425.05 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the fact that the energy supplier took time to complete the energy branch, it was only possible to complete the project within this period.
809 | 7502228 | Removal of asbestos-cement roofing at schools EB Nº2, EB Nº6 and EB Nº7 in Baixa da Banheira and EB Nº2 in Vale da Amoreira. | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 42 | 23-02-2021 | 27-12-2021 | 307 | 180 | 285000 | 50339.51 | 1 | 53663.95 | -3324.44 | 93.8051 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | price revision values.
810 | 7502186 | Removal of asbestos-cement roofing at schools EB Nº2, EB Nº6 and EB Nº7 in Baixa da Banheira and EB Nº2 in Vale da Amoreira. | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Moita | Setúbal | 17 | 42 | 23-02-2021 | 08-11-2021 | 258 | 180 | 285000 | 90563.2 | 1 | 100654.5 | -10091.3 | 89.9743 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | pricing review.
811 | 7501425 | Cold repaving of microagglomerate floors | 45233223-8 | Carriageway resurfacing works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 14 | 08-02-2021 | 22-10-2021 | 256 | 120 | 584447 | 241885.87 | 1 | 234229.29 | 7656.58 | 103.2688 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was completed on time | underwork
812 | 7501381 | Cold repaving of microagglomerate floors | 45233223-8 | Carriageway resurfacing works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 14 | 08-02-2021 | 22-10-2021 | 256 | 120 | 584447 | 265101.7 | 2 | 260871.69 | 4230.01 | 101.6215 | Best value for money: No Criterion related to quality name: factor Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project finished within the deadline. | underwork
813 | 7500701 | Requalification of the schoolelementary school No. 2 of Setúbal of Santa Maria da Graça | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Setúbal | Setúbal | 17 | 30 | 13-01-2021 | 12-08-2021 | 211 | 90 | 319118.24 | 307635.96 | 2 | 307635.96 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conditions not met for carrying out interior painting work and replacement of floors; classrooms occupied with school furniture, walls with classroom boards and various decorations.
814 | 7500679 | Refurbishment of street of Calvário - Várzea do Douro | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 05-02-2021 | 16-06-2021 | 131 | 60 | 38148 | 35949.93 | 1 | 35949.93 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was finished before the deadline
815 | 7498373 | Contract for improvement works and replacement of roofs and window frames in 2nd/3rd cycle and High schools in the Municipality of Cascais | 45261900-3 | Roof repair and maintenance work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 10 | 22-02-2021 | 18-10-2021 | 238 | 60 | 7218652.3 | 515214.24 | 2 | 515214.24 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A
816 | 7498210 | Contract 262/gebalis/2019 - neighborhood dr. Alfredo Bensaúde, lots A1 to C13 - Various works to restore safety and habitability | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 23-02-2021 | 07-10-2021 | 226 | 240 | 149229.66 | 145987.83 | 1 | 122493.33 | 23494.5 | 119.1802 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complexity in the execution of the project and adverse weather conditions during the course of the project
817 | 7495438 | Cpe.26.20.dmosm - fiber cement removal in school buildings | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 30 | 22-02-2021 | 10-09-2021 | 200 | 90 | 953043.61 | 197479.66 | 1 | 197479.66 | 0 | 100 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the pandemic situation, there was difficulty in starting some activities foreseen in the contractual work plan, as well as a shortage of material and labor to carry out the project within the foreseen deadlines. | ordinary price review
818 | 7495435 | Cpe.26.20.dmosm - fiber cement removal in school buildings | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 30 | 22-02-2021 | 10-09-2021 | 200 | 60 | 953043.61 | 147388.54 | 1 | 147388.54 | 0 | 100 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the pandemic situation, there was difficulty in starting some activities foreseen in the contractual work plan, as well as a shortage of material and labor to carry out the project within the foreseen deadlines. | ordinary price review
819 | 7495356 | Intervention in the Social Response Facilities APPACDM Occupational Activities Center in Gualtar – Braga | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 39 | 30-10-2020 | 30-11-2021 | 396 | 120 | 333988.92 | 333988.7 | 2 | 332378.74 | 1609.96 | 100.4844 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | the contract initially foreseen with a contractual term of 120 days, presents a new delay in its execution, which is essentially due to the lack of material/equipment on the market and the extension of supply deadlines, resulting from the covid19 pandemic situation | not all awarded works were carried out, with a global value of works of less than €1,609.96.
820 | 7495335 | CPN-101/2020 - T-100/2020 - Repair of the Roof of the South Tower of the José Lúcio da Silva Theater - Leiria | 45261900-3 | Roof repair and maintenance work | FALSE | 2021 | 2021 | Portugal | Leiria | Leiria | 10 | 76 | 17-02-2021 | 21-07-2021 | 154 | 60 | 170875 | 138885.53 | 1 | 124395.79 | 14489.74 | 111.6481 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to say | underwork
821 | 7493815 | Cpe.26.20.dmosm - fiber cement removal in school buildings | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 30 | 18-02-2021 | 29-10-2021 | 253 | 60 | 953043.61 | 46211.4 | 1 | 44258.14 | 1953.26 | 104.4133 | Best value for money: No Criterion related to quality Name: factor Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | term extension following the objective modification to the contract (additional), as well as, due to the difficulty in supplying certain materials, essentially the "sandwich" panel for the roof. | objective modification of the contract following the need to supply errors and omissions
822 | 7473103 | Construction of a kitchen and dining hall at Feira Nova elementary school - Bem Viver Parish | 45214210-5 | Primary school construction work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 03-02-2021 | 04-11-2021 | 274 | 180 | 133384.4 | 121872.79 | 1 | 150651.2 | -28778.41 | 80.8973 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had a 15 extension | complementary work worth: €29,814.81 underwork worth €5,600.00
823 | 7471320 | Construction/Acquisition of Passenger Shelters | 45213315-4 | Bus-stop shelter construction work | FALSE | 2020 | 2021 | Portugal | Mogadouro | Bragança | 4 | 21 | 09-02-2021 | 14-12-2021 | 308 | 180 | 74214.58 | 71744.09 | 1 | 71744.09 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Economically Most Advantageous Proposal-Article 74.º, N.1, Paragraph b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | mandatory confinement derived from the state of emergency as a result of the pandemic (covid19) and consequently delay in the supply of materials and equipment. | no change
824 | 7466862 | Demolition of 3 buildings in the former Armada Marinha school for future installations of the judicial court - Vila Franca de Xira | 45111100-9 | Demolition work | FALSE | 2019 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 18 | 16-03-2020 | 28-09-2020 | 196 | 120 | 235000 | 179000 | 1 | 179000 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
825 | 7453714 | Requalification of the streets of Padim and Várzeas in the Parish of Fontarcada | 45233140-2 | Roadworks | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 05-01-2021 | 24-08-2021 | 231 | 45 | 277819.82 | 235605 | 1 | 254184 | -18579 | 92.6907 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | more work and suspension of work. | additional work
826 | 7452756 | Rehabilitation of the Sports Center in the Social Neighborhood dos Assentos | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2020 | 2021 | Portugal | Portalegre | Portalegre | 12 | 17 | 09-02-2021 | 20-07-2021 | 161 | 150 | 271067.53 | 219995.6 | 1 | 219995.6 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline has been met
827 | 7450064 | Bus Terminal - Conservation and improvement interventions | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 25-08-2020 | 13-09-2021 | 384 | 120 | 152000 | 150839.55 | 1 | 163502.91 | -12663.36 | 92.255 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of materials due to the constraints caused by the pandemic | unforeseen and unpredictable complementary work under the terms of article 370 of the "public procurement code".
828 | 7449223 | Placement of Buried Containers in street of Picoto - Santo Tirso | 45213270-6 | Construction works for recycling station | FALSE | 2020 | 2021 | Portugal | Santo Tirso | Porto | 13 | 14 | 29-01-2021 | 05-07-2021 | 157 | 30 | 48992.5 | 46746.9 | 1 | 48246.9 | -1500 | 96.891 | Best value for money: Yes Criterion related to quality Name: Valia Técnica, quality control systems, safety management and environmental management Weighting: 10% Criterion related to cost Name: Price Weighting: 10% | 1 |  | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the definition and execution of complementary work. | the execution of complementary works.
829 | 7448831 | Replacement of Frames and Improvement of Exterior Coatings at elementary school-JI - Vila Nova do Campo | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Santo Tirso | Porto | 13 | 14 | 04-02-2021 | 23-11-2021 | 292 | 120 | 122723.63 | 105422.96 | 1 | 104823.17 | 599.79 | 100.5722 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management systems, quality control and environmental management Weighting: 10% Criterion related to cost Name: Price Weighting: 10% | 1 | 10 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the need to perform more work. | the existence of over and underwork in the course of the project.
830 | 7426168 | Public Tender for the contract for "Urban Arrangement of the Civic Center - Phase 2 - Vila Nova de Anha | 45113000-2 | Siteworks | TRUE | 2020 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 03-02-2021 | 02-09-2021 | 211 | 120 | 247030.87 | 245016.83 | 1 | 224262.15 | 20754.68 | 109.2547 | Best value for money: Yes Criterion related to quality Name: Valia Tecnica of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions and difficulty in delivering materials due to the pandemic | underwork was required than those previously defined.
831 | 7423212 | Paving streets in Paradela | 45211360-0 | Urban development construction work | FALSE | 2020 | 2021 | Portugal | Mogadouro | Bragança | 4 | 21 | 26-01-2021 | 28-09-2021 | 245 | 180 | 153302.39 | 151787.87 | 1 | 176112.87 | -24325 | 86.1878 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | accomplishment of complementary works | accomplishment of complementary works
832 | 7422946 | Execution of coverage for the gold market in Largo da Feira | 45223210-1 | Structural steelworks | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 25-01-2021 | 24-03-2021 | 58 | 42 | 117365.95 | 57784.52 | 1 | 57784.52 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
833 | 7421453 | Complete Refurbishment of the Exterior of Two Buildings and Replacement of Roofs in Alto Pina, Property of the Social services of the National Guard | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 15-01-2021 | 28-07-2021 | 194 | 90 | 150000 | 99200 | 1 | 99200 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to add
834 | 7418730 | CPN-102/2020/DICP - T - 25/2020 - Improvement of existing deck floor next to the Hot Spring | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 17 | 05-01-2021 | 15-07-2021 | 191 | 60 | 146700 | 107679.28 | 1 | 107679.28 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the delivery of material, namely the deck due to the "covid 19" pandemic
835 | 7416944 | Refurbishment and Expansion of the Tamengos School Center | 45214210-5 | Primary school construction work | FALSE | 2016 | 2020 | Portugal | Anadia | Aveiro | 1 | 20 | 08-03-2017 | 27-02-2020 | 1086 | 270 | 413841.22 | 347601.96 | 2 | 342742.38 | 4859.58 | 101.4179 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
836 | 7416254 | Contract 376/gebalis/2020 - public tender for the repair of elevators in the neighborhoods of vale de alcântara (ceuta north), plum and myrtle in lisbon at the addresses: - av. North Ceuta, lots 5, 10 11 | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 4 | 28-01-2021 | 07-05-2021 | 99 | 90 | 136000 | 110723.16 | 1 | 110723.16 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
837 | 7415902 | «Cp 29/2020 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela» - adjudication by lots | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 05-01-2021 | 10-09-2021 | 248 | 270 | 435000 | 135104.55 | 1 | 135076.33 | 28.22 | 100.0209 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | underwork | underwork
838 | 7415586 | «Cp 29/2020 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela» - adjudication by lots | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 09-12-2020 | 18-11-2021 | 344 | 365 | 435000 | 249998.65 | 1 | 249945.02 | 53.63 | 100.0215 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | underwork | underwork
839 | 7414644 | Requalification from streetde São Cosme to the boundary of the municipality with Arosa | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 21-12-2020 | 26-05-2021 | 156 | 60 | 228860.53 | 160043.15 | 1 | 157668.28 | 2374.87 | 101.5062 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | underwork.
840 | 7412605 | Construction / Improvement / Repair of School Buildings, by Contract: Removal of Fiber Cement in elementary and High school Equipment - CP-CCP-EMP n.º 20/2020 | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 27-01-2021 | 19-11-2021 | 296 | 180 | 178674.3 | 141824 | 1 | 168364 | -26540 | 84.2365 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
841 | 7412548 | Horizontal and Vertical Signage in the Municipality, by Contract: Execution of signaling on several roads in the Municipality - CP-CCP-EMP n.º 24/2020 | 45233294-6 | Installation of road signals | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 27-01-2021 | 13-12-2021 | 320 | 60 | 79000 | 44919.47 | 1 | 45180.09 | -260.62 | 99.4232 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of additional work and underwork.
842 | 7411275 | Cp 10/2020 - Extensions of water supply and wastewater drainage networks in the parish of Gondar - streetPrainha de Cima and street and crossstreet of Soeiro - Guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 02-07-2020 | 16-07-2021 | 379 | 120 | 93000 | 86146.94 | 1 | 84452.62 | 1694.32 | 102.0062 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
843 | 7408882 | Contract for excavation and peripheral containment - 1st phase | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2021 | Portugal | N/A | Região Autónoma dos Açores | 15 | 30 | 21-11-2019 | 29-06-2021 | 586 | 75 | 540000 | 530000 | 2 | 530000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality and lead time Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | TRUE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | bad weather conditions.
844 | 7407319 | Contract for requalification of the thermal power plant of the School of Medicine of the University of Minho, on the Gualtar campus, in Braga. (Cp/eop dcm-25/2019) | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2020 | 2021 | Portugal | Braga | Braga | 3 | 14 | 23-12-2020 | 17-05-2021 | 145 | 90 | 250000 | 162600 | 1 | 162600 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the time of completion of the contractual work, the Client was not in a position to be receive the project
845 | 7407277 | Contract for the Repair of Sidewalks Damaged by Tree Roots | 45233200-1 | Various surface works | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 30 | 29-10-2020 | 08-10-2021 | 344 | 150 | 200000 | 158918.77 | 1 | 158918.77 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Description of the Contract (40%) / Mode of Execution of the Works (30%) / Work Program (30%) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contractual modification communicated
846 | 7407200 | Cp 15/2020 - Replacement of water supply networks and wastewater sanitation networks in the parishes of Fermentões, Ponte e Silvares - Guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 23-10-2020 | 23-11-2021 | 396 | 150 | 308650 | 302770.52 | 2 | 263628.18 | 39142.34 | 114.8476 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
847 | 7402672 | Cp 19/2019 - Repair of defects in the work within the scope of the contract for water and sanitation networks in the southern area of ​​the municipality of Guimarães - inag - Água em abação, calvos, gémeos, infantas and tabuadelo | 45233142-6 | Road-repair works | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 02-03-2020 | 19-05-2021 | 443 | 30 | 89990 | 79901 | 1 | 65040.43 | 14860.57 | 122.8482 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
848 | 7402094 | Cp 18/2019 - repair of work defects within the scope of the contract for the design and construction of water supply and sanitation networks on the southeast front of guimarães | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 02-03-2020 | 16-11-2020 | 259 | 60 | 209820.75 | 176803.5 | 1 | 173187.85 | 3615.65 | 102.0877 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
849 | 7399770 | Cp 03/2019 - execution of paving work to support the maintenance and conservation of water supply and wastewater sanitation systems, in the municipalities of guimarães and vizela | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 22-05-2019 | 16-12-2020 | 574 | 365 | 147840 | 146352.2 | 1 | 67340.04 | 79012.16 | 217.3331 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | works less
850 | 7392528 | Children's and Picnic Park in Painho - participatory budget | 45212140-9 | Recreation installation | FALSE | 2020 | 2021 | Portugal | Cadaval | Lisboa | 11 | 16 | 14-01-2021 | 02-11-2021 | 292 | 60 | 56602.3 | 53227.66 | 1 | 54467.86 | -1240.2 | 97.7231 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work | complementary work
851 | 7389075 | Cpn 94/2020/dicp - t-111/2020 - requalification of the sections between the Outeiro das Barrocas and the IC2 - Boa Vista | 45233141-9 | Road-maintenance works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 19 | 29-12-2020 | 01-06-2021 | 154 | 120 | 317264.25 | 279900 | 2 | 335459.81 | -55559.81 | 83.4377 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A |  | complementary works pursuant to the provisions of art. 370.º, nº 4 "public procurement code"
852 | 7382050 | elementary school Cabo - Maureles - replacing the fiber cement roof | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 16-12-2020 | 20-07-2021 | 216 | 60 | 33212.84 | 25311.09 | 1 | 25311.09 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time
853 | 7378012 | Contract 327/gebalis/2020 - padre cruz neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 17 | 07-01-2021 | 22-06-2021 | 166 | 90 | 94000 | 66535 | 1 | 66535 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 21 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
854 | 7377593 | Improvement of the Municipal Road Network - Various Paving in the Parish of Olhão | 45432110-8 | Floor-laying work | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 23-10-2020 | 15-06-2021 | 235 | 60 | 95000 | 87542.75 | 1 | 87542.75 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the extension of the execution period of the contract
855 | 7377421 | streets in Vassal | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 08-01-2021 | 27-09-2021 | 262 | 180 | 86411.03 | 83895.5 | 1 | 89786.72 | -5891.22 | 93.4387 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | ordinary price review
856 | 7377416 | Exterior maintenance works on blocks 6 to 11 of the public housing buildings in Bairro do Carriçal | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 15 | 07-01-2021 | 02-09-2021 | 238 | 180 | 425000 | 375000 | 2 | 368553.13 | 6446.87 | 101.7492 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the projects of the contract took place normally from the consignment until the end of the contract, despite the decree of the state of emergency. all legal and contractual obligations of the contractor arising from the identified works contract are fully and perfectly fulfilled. | complementary and unforeseen work
857 | 7374125 | Requalification of the Surrounding Area of ​​the Granja Church. | 45112700-2 | Landscaping work | FALSE | 2020 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 18 | 21-12-2020 | 15-10-2021 | 298 | 120 | 58600.49 | 57441.27 | 1 | 57441.27 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | shortage of personnel caused by the pandemic | price review
858 | 7372795 | Public works contract for the construction of a bicycle lane section on Avenida Marechal Gomes da Costa | 45113000-2 | Siteworks | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 36 | 29-12-2020 | 13-05-2021 | 135 | 44 | 400000 | 305000 | 2 | 320132.35 | -15132.35 | 95.2731 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the rain made painting impossible. | it verified the need to elaborate an objective modification to the contract. (moc)
859 | 7372468 | CP 36/2020_DEGA - AA and AR Network - Small Extensions 2021 | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2020 | 2021 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 42 | 23-12-2020 | 08-07-2021 | 197 | 730 | 245000 | 223636.96 | 1 | 223636.96 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
860 | 7372399 | Refurbishment of the Municipal Garden - treatment of humid arcades | 45223110-0 | Installation of metal structures | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 09-12-2020 | 23-03-2021 | 104 | 30 | 27288.98 | 18660.65 | 1 | 18660.65 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the deadline on 02/10/2021.
861 | 7368000 | Repair and painting of the walls surrounding the elementary school in Ferreira do Alentejo, repair of the EB in Santa Margarida do Sado and improvement of the Covered Swimming Pool in Ferreira do Alentejo | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 06-11-2020 | 22-11-2021 | 381 | 60 | 75000 | 63494.18 | 1 | 62711.69 | 782.49 | 101.2478 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was delayed immensely due to the covid 19 pandemic, which caused delays in the supply of materials | additional work and underwork due to design measurement errors
862 | 7367100 | Refurbishment of Grupo Desportivo Street in Porto d'Ave and street of Agro in Taíde | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 04-12-2020 | 27-07-2021 | 235 | 60 | 150458.37 | 119781 | 1 | 125213 | -5432 | 95.6618 | Best value for money: Yes Criterion related to quality Name: Technical quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work and additional works. | additional work
863 | 7361840 | Modernization of the Municipal Market of Alcochete | 45213141-3 | Covered market construction work | FALSE | 2020 | 2021 | Portugal | Alcochete | Setúbal | 17 | 21 | 11-12-2020 | 25-10-2021 | 318 | 244 | 250000 | 221837.57 | 1 | 221837.57 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Tecnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to say | nothing to say
864 | 7358651 | The purpose of this contract is to improve energy certification at EB 2+3 Cardoso Lopes. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 24 | 23-12-2020 | 26-08-2021 | 246 | 245 | 234191.53 | 210772.39 | 1 | 226615.67 | -15843.28 | 93.0087 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | in the case of an intervention in a school, the execution period of the project was shorter than expected, since the phases in which there was confinement due to the pandemic were taken advantage of, which allowed to considerably reduce the constraints that would occur if classes took place normally. | due to the definitive price review in the amount of €15,843.28. having made the final account of the contract on 08/26/2021, where the price revision was not yet included. an addendum to the account was made on 01/12/2022.
865 | 7355979 | The object of this contract is the execution of works on the aforementioned streets in the municipality of Amadora. | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 17-12-2020 | 19-07-2021 | 214 | 120 | 188675 | 182716.5 | 1 | 182716.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | with the completion of the project, the "plan for the prevention and management of construction and demolition waste" was requested from the successful tenderer, which was delayed in delivery.
866 | 7353413 | Replacement of Coverings Containing Asbestos in the Buildings of Escola Dr. john lucio | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 15 | 22-12-2020 | 13-09-2021 | 265 | 180 | 216926.74 | 199500 | 1 | 179069.1 | 20430.9 | 111.4095 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | to adjust the execution of the projects with the holiday period foreseen in the school calendar, also accommodating the safety requirements of the dgs in relation to the covid 191 pandemic | more quantified work
867 | 7352873 | Contract 319/gebalis/2020 - paço lumiar neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 16 | 23-12-2020 | 19-03-2021 | 86 | 90 | 40000 | 26349 | 1 | 27264 | -915 | 96.6439 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others) | complementary works
868 | 7351334 | Contract 332/gebalis/2020 - boavista neighborhood / good pastor - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 18-12-2020 | 24-03-2021 | 96 | 60 | 76000 | 49340.05 | 1 | 50010.05 | -670 | 98.6603 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others) | additional works
869 | 7350065 | Renovation of the rainwater network at R. Padre Gonçalo de Sousa, in Perafita | 45240000-1 | Construction work for water projects | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 22-12-2020 | 28-06-2021 | 188 | 10 | 116000 | 85785 | 1 | 85785 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
870 | 7348353 | Replacement of Coverings Containing Asbestos in the Buildings of Escola Dr. Alberto would | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 15 | 16-12-2020 | 03-05-2021 | 138 | 150 | 118538.67 | 104480 | 1 | 104480 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work finished ahead of schedule
871 | 7348296 | Contract 252/gebalis/2020 - county district - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 8 | 18-12-2020 | 13-09-2021 | 269 | 120 | 286255.91 | 214236.14 | 1 | 214236.14 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
872 | 7348078 | Replacement of Roofs Containing Asbestos in the João da Rosa School Buildings | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 15 | 16-12-2020 | 03-05-2021 | 138 | 150 | 96808.99 | 86320 | 1 | 86320 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work finished ahead of schedule
873 | 7347131 | Public tender n.º adene-cp-2020-001 public works contract for the adaptation/renovation of the 1st, 5th and 6th floors of the santa maria building | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 22 | 19-11-2020 | 10-11-2021 | 356 | 119 | 467000 | 170316.47 | 1 | 170316.47 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | the project at a certain point progressed very slowly due to lack of raw materials, namely the ceiling on the 5th floor and light fixtures on the same floor. the deadlines for delivering materials were constantly postponed due to the difficulties that were felt due to the pandemic.
874 | 7345839 | 2020.040.02.C1 - North Regional Delegation - Replacement of fiber cement roofing | 45261213-0 | Metal roof-covering work | TRUE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 13-11-2020 | 25-10-2021 | 346 | 90 | 117000 | 95940 | 1 | 103152.5 | -7212.5 | 93.0079 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | additional work and underwork
875 | 7345614 | Its object is the execution of works on the aforementioned streets in the Municipality of Amadora. | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 17-12-2020 | 24-08-2021 | 250 | 120 | 319884.5 | 270800 | 2 | 270800 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the advance of the deadline was due to the reinforcement of equipment and personnel assigned to the project.
876 | 7345320 | Contract "Environmental and Urban Rehabilitation of the Riverfront along streetMiguel Pais - Phase 2" | 45112700-2 | Landscaping work | TRUE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 20 | 11-11-2020 | 26-04-2021 | 166 | 120 | 320000 | 256500 | 2 | 256500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
877 | 7345273 | Roundabout rehabilitation at street of Ribeirinha - Santa Maria de Lamas | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-12-2020 | 16-07-2021 | 211 | 45 | 18130 | 14990 | 1 | 15741.32 | -751.32 | 95.2271 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 11 days to schedule the inspection for provisional acceptance | additional work resulting from unforeseen circumstances
878 | 7344860 | Its purpose is to improve energy certification at EB 2+3 Almeida Garrett. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 24 | 15-12-2020 | 10-09-2021 | 269 | 287 | 495152.19 | 445636.99 | 2 | 471935.12 | -26298.13 | 94.4276 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | organization of the project in advance, ease of response to orders for materials, workspace free of normal use by students and teachers. | due to the definitive price revision in the amount of €26,298.13. an addendum to the account was made on 01/13/2022.
879 | 7344602 | CPN 98/2020/DICP -T - 96/2020 - Requalification and Improvement of street of Restauração in Alcogulhe - União das Parishes of Parceiros e Azoia | 45233141-9 | Road-maintenance works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 02-12-2020 | 11-10-2021 | 313 | 30 | 43157 | 40990 | 1 | 40990 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension pursuant to the provisions of article 365, paragraph b) of the pcc.
880 | 7344524 | Contract 156/GEBALIS/2020 - Bairro Paço Lumiar - Rehabilitation of municipal buildings | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 16 | 17-12-2020 | 23-06-2021 | 188 | 120 | 115000 | 87207.4 | 1 | 82957.4 | 4250 | 105.1231 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 20 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others) | underwork
881 | 7344305 | Contract for the construction of an auditorium on Avª Nuno Alvares | 45212321-2 | Auditorium construction work | TRUE | 2020 | 2021 | Portugal | Setúbal | Setúbal | 17 | 15 | 02-12-2020 | 29-04-2021 | 148 | 90 | 280000 | 253224.91 | 2 | 253224.91 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: lead time Weighting: 30% Criterion related to cost name: price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place in 90 days. however, there was a need to suspend work for 58 days due to the prophylactic isolation of workers (covid-19) and the closure of borders within the scope of the state of emergency decreed in portugal and europe, making it difficult to import materials. | there were no changes to the value of the project
882 | 7343736 | Exterior arrangements for access to the new Primary school Pavilion in Marco de Canaveses | 45262310-7 | Reinforced-concrete work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 16-12-2020 | 12-10-2021 | 300 | 60 | 33213.88 | 31673.08 | 1 | 31673.08 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended.
883 | 7343683 | Expansion of the basic sanitation network in various locations in the Municipality | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 09-12-2020 | 08-10-2021 | 303 | 90 | 63288 | 53395.69 | 1 | 53395.69 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100 % Diário da República, 2nd series No. 10428 September 21, 2020 Page 4 | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended
884 | 7343106 | Rehabilitation of the Toutosa reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 25-11-2020 | 12-02-2021 | 79 | 45 | 27827.3 | 26003.9 | 1 | 26003.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project finished within the deadline.
885 | 7342960 | Construction of game and recreation parks in the urbanizations Quinta das Flores and Maria Teresa Jesus Lopes Viegas | 45112723-9 | Landscaping work for playgrounds | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 27-10-2020 | 28-09-2021 | 336 | 120 | 146873 | 136457.3 | 1 | 136457.3 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension / indefinite
886 | 7342278 | Construction of roofs located in the square of the bocage | 45260000-7 | Roof works and other special trade construction works | FALSE | 2020 | 2021 | Portugal | Setúbal | Setúbal | 17 | 30 | 28-10-2020 | 06-09-2021 | 313 | 180 | 339521.59 | 239715.46 | 1 | 239715.46 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 15 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | partial suspension of the projects so that the procedures necessary for the execution of the infrastructure network (wiring) that will be applied under the zinc roof to be carried out and the placement of spotlights on the pillars and pavement are carried out
887 | 7340537 | Works for the replacement of the covering of the roof of Block A of Bairro Agra do Amial | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 30 | 16-12-2020 | 27-04-2021 | 132 | 30 | 50000 | 48006.42 | 1 | 47466.42 | 540 | 101.1376 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was delayed by 40 days due to the weather conditions that occurred during the execution of the project. | unforeseen work
888 | 7339735 | Its object is the requalification and expansion of the kennel, in accordance with the work to be carried out defined, regarding its type, quantity and technical conditions of execution, in the project | 45223600-2 | Dog kennels construction work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 21 | 10-12-2020 | 30-08-2021 | 263 | 120 | 358451.58 | 322606.44 | 2 | 334789.45 | -12183.01 | 96.361 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deviation in the execution time is not directly attributable to the consigned work whose development and materialization took place in the foreseen time, but rather to the non-existence of a local sewage network, which implied the monitoring and supervision of simas, the opening operation of new ditches filled in by tubes and compaction of the set for its creation, complemented by the implementation of a decantation and filtering pit, and connection of the entire system to an existing network at the boundary of the lot, proposed by the aforementioned entity. | due to the 1st provisional price revision in the amount of €10,847.41 and the 2nd definitive price revision in the amount of €1,335.60. two addendums were made to the final contract account with the respective dates of 11/23/2021 and 01/12/2022.
889 | 7339662 | Setúbal District Center_Rehabilitation Works on the Existing Terraces in the Almada Local Service Building | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Almada | Setúbal | 17 | 12 | 06-08-2020 | 21-01-2021 | 168 | 60 | 25317.66 | 23440 | 1 | 23440 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no changes
890 | 7337282 | Cpn 71/2020/dicp - full replacement of the covering roofs of the Visconde de Barrier manor - union of parishes of Leiria, Poems, Barrier and Cortes | 45260000-7 | Roof works and other special trade construction works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 21 | 21-10-2020 | 27-09-2021 | 341 | 60 | 135089.74 | 134882.02 | 1 | 102241.12 | 32640.9 | 131.9254 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork (art.º 379.º n.º 2)
891 | 7336248 | elementary school Outeiro - Constance - replacement of the fiber cement roof | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 03-12-2020 | 26-05-2021 | 174 | 60 | 38575.96 | 30100 | 1 | 30100 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was finished ahead of schedule
892 | 7336156 | Eb1 couple - s. Lourenço do Douro - Removal of the fiber cement covering | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 03-12-2020 | 16-06-2021 | 195 | 92 | 61655.9 | 49540 | 1 | 49540 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was finished ahead of schedule
893 | 7336056 | elementary school Freita - Marco - Removal of the fiber cement covering | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 20-11-2020 | 30-04-2021 | 161 | 60 | 19168.18 | 15780.34 | 1 | 15780.34 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time
894 | 7335955 | Replacement of fiber cement coverings in school buildings in the municipality - EB de Silvares S. Martinho, EB de Montelongo, EB Padre Joaquim Flores and EB Prof. carlos teixeira. | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Fafe | Braga | 3 | 15 | 09-12-2020 | 02-12-2021 | 358 | 150 | 369415 | 307249.5 | 2 | 301841.5 | 5408 | 101.7917 | Best value for money: Yes Criterion related to quality Name: TECHNICAL ADVANTAGE AND PROPOSAL GUARANTEE Weighting: 40% Criterion related to cost Name: PRICE Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a suspension of work, since the replacement of the roof of the prof. carlos teixeira, would only be executed after the end of the school year | all the project in article 2.1.4 has not been carried out.
895 | 7335183 | Pa/2020/214 - cp/4/2020 | 45321000-3 | Thermal insulation work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 5 | 16-11-2020 | 26-02-2021 | 102 | 60 | 64562.07 | 57956.43 | 1 | 57956.43 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | weather reasons
896 | 7333827 | Public tender 84/20 - t-36/20 replacement of gutters and paintwork in the sports pavilion at Landings Leiria | 45261900-3 | Roof repair and maintenance work | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 1 | 05-11-2020 | 14-07-2021 | 251 | 180 | 57020 | 52077 | 1 | 52077 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to say
897 | 7330958 | Contract for the Repaving of the EM 508 Road (Ribeira da Foupana Bridge - Alcaria Queimada branch), Year 2020 | 45432110-8 | Floor-laying work | FALSE | 2020 | 2021 | Portugal | Alcoutim | Faro | 8 | 20 | 26-10-2020 | 12-03-2021 | 137 | 30 | 165766.2 | 147640.76 | 1 | 147640.76 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to provisional reception.
898 | 7330725 | Energy efficiency in primary school from the fair | 45310000-3 | Electrical installation work | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 27-11-2020 | 15-06-2021 | 200 | 60 | 35312 | 34202.58 | 1 | 36403.9 | -2201.32 | 93.9531 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 5 days regarding availability in the provisional reception inspection appointment | the change in the value of the project is essentially due to unforeseen additional work, due to the need for more air conditioning equipment than initially planned, and the project carried out the electrical pre-installation of this equipment and the safeguarding of power
899 | 7328885 | E.CP_31/2020 - Parque do Arnal - Improvement | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Figueira da Foz | Coimbra | 6 | 7 | 09-11-2020 | 28-09-2021 | 323 | 60 | 51327.8 | 49428.3 | 1 | 54355.11 | -4926.81 | 90.9359 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | due to weather conditions and covid 19 pandemic | there was a need to carry out additional work that was not foreseen
900 | 7328238 | Contract for New Operational Facilities for CM Barreiro. | 45213252-4 | Workshops construction work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 20 | 19-11-2020 | 23-09-2021 | 308 | 126 | 749176.82 | 728259.41 | 2 | 793352.03 | -65092.62 | 91.7952 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Criterion relating to the period of execution of the work with a weighting of 10% Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
901 | 7327920 | Execution contract for the Transformation Station of the Urban Allotment KM 8 - Estrada da Ribeira Grande | 45000000-7 | Construction work | TRUE | 2020 | 2021 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 04-12-2020 | 11-06-2021 | 189 | 60 | 57500 | 43255.13 | 1 | 43255.13 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Work execution quality factor. Weighting: 40% Criterion related to cost Name: Price Factor Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
902 | 7327004 | This contract focuses on lot 1 and aims to improve the energy certification of EB/JI Alice Vieira. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 26-11-2020 | 22-11-2021 | 361 | 245 | 371163.36 | 198328.3 | 1 | 209491.09 | -11162.79 | 94.6715 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the contingencies that implied the deviation in the execution time of the project were due to the pandemic. | due to the provisional price revision in the amount of €11,162.79. having made the final account of the contract on 11/11/2021, which still did not contain the price review. an addendum to the account was made on 12/22/2021.
903 | 7325829 | Its purpose is to adapt the existing space to the effective needs of the Municipal Police, so it will be necessary to reorganize the existing space and create new spaces and requalification | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 21 | 02-12-2020 | 21-07-2021 | 231 | 120 | 353704.94 | 318334.46 | 2 | 332438.56 | -14104.1 | 95.7574 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period of the project, it took place in 120 days. | due to provisional price revisions in the amount of €12,083.42 and definitive in the amount of €2,020.68. having made the final account of the contract on 07/21/2021, where price revisions were not yet included. two amendments were made to the account on 11/11/2021 and on 12/22/2021.
904 | 7324069 | Exterior Maintenance Works for Public Housing Building No. 2 in the Contumil District | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 02-12-2020 | 14-06-2021 | 194 | 150 | 230000 | 188035.63 | 1 | 186114.82 | 1920.81 | 101.0321 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the contractually foreseen | withdrawal of works worth €1,920.81
905 | 7323984 | Requalification of the José Carlos da Maia Primary School (E.B. 1 / Ji n.º7) | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 27-10-2020 | 23-04-2021 | 178 | 90 | 279658.92 | 205425.12 | 1 | 205425.12 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the extension of the execution period of the project, for 45 days, was authorized, as a grace, due to delay in the delivery of materials by suppliers, due to the pandemic situation.
906 | 7323111 | Installation of water supply and wastewater drainage infrastructure | 45232411-6 | Foul-water piping construction work | FALSE | 2020 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 02-12-2020 | 08-11-2021 | 341 | 90 | 89950 | 78980 | 1 | 78980 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | covid-19 pandemic
907 | 7322285 | Contract 295/gebalis/2020 - sergento abilio neighborhood / good shepherd - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 18 | 27-11-2020 | 23-12-2020 | 26 | 60 | 50000 | 33968.6 | 1 | 33968.6 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 18 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work went smoothly/on schedule
908 | 7322215 | Requalification of streetDr. Abilio Torres at U.F. From Caldas de Vizela (S. Miguel and S. João) | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Vizela | Braga | 3 | 21 | 27-11-2020 | 19-10-2021 | 326 | 180 | 424528.3 | 366592.19 | 2 | 433556.91 | -66964.72 | 84.5546 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary works
909 | 7319875 | Repaving of Caminho da Grazina and refurbishment of streetde São Lourenço | 45432110-8 | Floor-laying work | FALSE | 2020 | 2021 | Portugal | Loulé | Faro | 8 | 15 | 14-10-2020 | 28-06-2021 | 257 | 90 | 210790.77 | 169116.63 | 1 | 168166.63 | 950 | 100.5649 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the necessary conditions in terms of humidity and temperature were not met for the correct execution of the project | underwork
910 | 7307800 | 2018.150.01.C1-SE Évora - Replacement of Lighting, SADI and SADIR | 45310000-3 | Electrical installation work | TRUE | 2020 | 2021 | Portugal | Évora | Évora | 7 | 21 | 10-09-2020 | 17-05-2021 | 249 | 120 | 80000 | 62547.01 | 1 | 62547.01 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
911 | 7307621 | Repair of sanitation manholes | 45232411-6 | Foul-water piping construction work | FALSE | 2020 | 2021 | Portugal | Lousada | Porto | 13 | 20 | 17-11-2020 | 13-09-2021 | 300 | 90 | 41400 | 33453 | 1 | 33453 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | no change
912 | 7307384 | Requalification of the Road Network in the Union of the Parishes of Portunhos and Outil and in the Parish of Ançã and Rueing of the Industrial Zone of Cantanhede, by Contract - CP-CCP-EMP n.º 14/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 16 | 23-11-2020 | 23-12-2021 | 395 | 180 | 240237 | 111621.3 | 1 | 86249.1 | 25372.2 | 129.4174 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
913 | 7306492 | Cp 18/2020 - rehabilitation of the buildings of the prazins santa eufémia water treatment plant | 45442100-8 | Painting work | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 10-09-2020 | 12-07-2021 | 305 | 60 | 38400 | 34960.81 | 1 | 34960.81 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
914 | 7306241 | Contract for "Delimitation Wall Construction Works between the Palácio dos Correios building and adjacent buildings" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 15 | 19-11-2020 | 05-04-2021 | 137 | 100 | 210000 | 192379.98 | 1 | 181808.29 | 10571.69 | 105.8147 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractual provisions. | work not carried out worth €10,571.69
915 | 7305587 | C. Public No. 37/ Social services of the National Guard/2020 | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Figueira da Foz | Coimbra | 6 | 21 | 22-06-2020 | 31-12-2020 | 192 | 30 | 24000 | 20813.55 | 1 | 20813.55 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
916 | 7302870 | Rehabilitation contract for the Municipal Swimming Pool of Moura | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Moura | Beja | 2 | 30 | 08-04-2019 | 15-11-2021 | 952 | 120 | 282031.14 | 229231.13 | 1 | 214632.52 | 14598.61 | 106.8017 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of the term for 93 days and request for 2 extensions of the term (1st 75 days) and (23rd 84 days) | due to underwork
917 | 7301610 | Cp 13/2020 - Replacement and extension of water supply networks and wastewater sanitation networks in the parishes of Azurém, Costas and U.F. Of Oliveira, s. Paio and S. Sebastian | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 23-10-2020 | 30-11-2021 | 403 | 120 | 201000 | 198229.66 | 1 | 188101.95 | 10127.71 | 105.3842 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
918 | 7301536 | Construction of a car park in Pinhel | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Pinhel | Guarda | 9 | 15 | 16-11-2020 | 23-04-2021 | 158 | 120 | 145000 | 114369.2 | 1 | 114369.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | suspension by the contractor, due to the covid 19 pandemic
919 | 7299663 | 2020/SFPRH/UPC/172 - Contract to carry out early demolition work, peripheral containment and excavations for the requalification of the future Center for Valorization and Technology Transfer | 45100000-8 | Site preparation work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 11-11-2020 | 30-09-2021 | 323 | 183 | 1074518.66 | 1009000 | 3 | 1046896.45 | -37896.45 | 96.3801 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the causes for changes in the value of the project were due to the following cases: - works that it was not possible to identify in the design phase; - work that was found not to be necessary due to changes in the project.
920 | 7298911 | Improvement of streets (Povoções de Cimo do Vale, Amêndoa, Cabo and Monte Fundeiro) and Municipal Roads E.N. 244 (section cross. E.n. 241-1 / Amêndoa) and EM597 (section S. José das Matas / cross. EN359) | 45233141-9 | Road-maintenance works | FALSE | 2020 | 2021 | Portugal | Mação | Santarém | 16 | 14 | 06-11-2020 | 06-05-2021 | 181 | 60 | 288190 | 272997.47 | 2 | 272997.47 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension.
921 | 7296571 | Paving connecting paths between cm1279, vnc3 and vnc4 - pear frame | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Silves | Faro | 8 | 30 | 12-11-2020 | 23-12-2021 | 406 | 60 | 81195 | 76995.5 | 1 | 83624.87 | -6629.37 | 92.0725 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | price review
922 | 7293393 | Public tender for the +access work contract - promotion of inclusive accessibility - Praça do Município and surrounding area - Covilhã | 45233260-9 | Pedestrian ways construction work | FALSE | 2019 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 09-11-2020 | 16-07-2021 | 249 | 70 | 133100 | 132224 | 1 | 137894.94 | -5670.94 | 95.8875 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal / execution period Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was additional work in relation to the contract. carrying out inspection.
923 | 7292585 | 2019.166.01.C1 - SE MONTEMOR-O-NOVO - Exterior Paintings and Window Frames | 45259000-7 | Repair and maintenance of plant | TRUE | 2020 | 2021 | Portugal | Montemor-o-Novo | Évora | 7 | 21 | 29-07-2020 | 05-03-2021 | 219 | 75 | 98740 | 81329.66 | 1 | 81329.66 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Valuation of the Proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension
924 | 7283210 | Requalification of the Road Network in the Parish of Tocha, by Contract - 1st Phase - CP-CCP-EMP n.º 17/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 16 | 13-11-2020 | 25-11-2021 | 377 | 180 | 276688.5 | 151999.73 | 1 | 163449.73 | -11450 | 92.9948 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works.
925 | 7283183 | Requalification of the Road Network in the Union of the Parishes of Sepins and Bolho, by Contract - 1st Phase - CP-CCP-EMP n.º 15/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 16 | 13-11-2020 | 25-11-2021 | 377 | 180 | 335078.5 | 138037.44 | 1 | 136389.44 | 1648 | 101.2083 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underworks.
926 | 7281713 | Irrigation System for Compost Piles at the Organic Valorization Center | 45332200-5 | Water plumbing work | FALSE | 2020 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 7 | 02-04-2020 | 12-11-2020 | 224 | 25 | 28500 | 24965 | 1 | 24965 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | without changes
927 | 7281499 | Coimbra District Center - Replacement of a heat pump and fan coils in the HVAC system of the headquarters building | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2020 | 2021 | Portugal | Coimbra | Coimbra | 6 | 30 | 03-09-2020 | 22-01-2021 | 141 | 90 | 81138 | 76900 | 1 | 76900 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
928 | 7279972 | Contract nº 39/20 - Urban Requalification of the City - Carrying out the Work in the Municipal Market of Mina | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 11-11-2020 | 30-09-2021 | 323 | 154 | 458130.05 | 412317.06 | 2 | 421964.96 | -9647.9 | 97.7136 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the slight deviation from the execution time is exclusively due to procedural factors of delay in the delivery of the waste management plan at work and the price revision. | provisional price revisions worth €9,647.90.
929 | 7279657 | Urban rehabilitation of street of Mourão - Rio Meão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 09-11-2020 | 02-12-2021 | 388 | 90 | 117000 | 89096.81 | 1 | 74594.45 | 14502.36 | 119.4416 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 14 days from inspection appointment for provisional acceptance | underwork
930 | 7279219 | 2nd Phase of Requalification of C.M.1359, streetde Cancelos, S.João de Rei | 45233200-1 | Various surface works | FALSE | 2020 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 12-11-2020 | 15-12-2020 | 33 | 35 | 103758.84 | 76578.63 | 1 | 70269.92 | 6308.71 | 108.9778 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent | underwork.
931 | 7272818 | Reinforcement of an earth retaining wall in Póvoa de Lanhoso | 45262212-0 | Trench sheeting work | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | N/A | 10-11-2020 | 30-03-2021 | 140 | 60 | 69971.55 | 61545.25 | 1 | 72022.42 | -10477.17 | 85.4529 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 4 | FALSE | N/A | N/A | N/A | N/A | FALSE | suspension by the developer. | more work and underwork.
932 | 7272519 | "Removal of the Fiber Cement Roofing at the elementary school of Miranda do Douro" | 45262660-5 | Asbestos-removal work | FALSE | 2020 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 15 | 16-10-2020 | 05-05-2021 | 201 | 180 | 125138.5 | 97998 | 1 | 97998 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate causes
933 | 7270292 | Contract 292/gebalis/2020 - Boavista neighborhood - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 4 | 10-11-2020 | 04-02-2021 | 86 | 60 | 71000 | 52530 | 1 | 52530 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
934 | 7268639 | Sanitation in Sá | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 02-11-2020 | 22-12-2021 | 415 | 180 | 88000.04 | 82972 | 1 | 83399.33 | -427.33 | 99.4876 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation caused by covid-19 and delay in the delivery of materials to carry out the project | there was no need to build ditches or place half-rounds, as well as not placing all the panels
935 | 7261167 | Quality 100% - Rehabilitation of the granite cube pavement on R. Dr. José Domingues dos Santos - Phase 2 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 06-11-2020 | 09-09-2021 | 307 | 90 | 176000 | 129626 | 1 | 129626 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
936 | 7259730 | Contract for the Rehabilitation of street of Bairro 25 de Abril in Moura | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Moura | Beja | 2 | 30 | 26-10-2020 | 03-11-2021 | 373 | 90 | 170749.75 | 144885.76 | 1 | 151784.54 | -6898.78 | 95.4549 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for 2 deadline extensions (1st 30 days) and (2nd 39 days) | no change
937 | 7257330 | Contract for the replacement of water supply columns, which are made of galvanized iron, due to ruptures, at 2 Praça de Londres Building - Lisbon. | 45332200-5 | Water plumbing work | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 04-09-2020 | 11-02-2021 | 160 | 89 | 120000 | 119849.24 | 1 | 119849.24 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Lead time Weighting: 40% Criterion related to cost Name: Price Weighting: 60% Diário da República, 2nd series No. 7484 July 13, 2020 Page 4 | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
938 | 7254926 | Cpn 83/2020/dicp - t-61/2020 - reformulation of the e. M. 349-1 With streetCentral - Casal dos Claros - Parish of amor | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 02-11-2020 | 20-07-2021 | 260 | 90 | 137008 | 135580.17 | 1 | 127340.17 | 8240 | 106.4709 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of underground infrastructure work for lighting, low voltage and telecommunications networks | underwork
939 | 7254641 | Cpn-u n.º 95/2020/dicp - t - 112/2020 work to replace the lawn at the municipal stadium of leiria | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2020 | 2020 | Portugal | Leiria | Leiria | 10 | N/A | 03-11-2020 | 26-11-2020 | 23 | 15 | 130000 | 99756.5 | 1 | 99756.5 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 0 | FALSE | N/A | N/A | N/A | N/A | FALSE
940 | 7254630 | OPJ - Refurbishment of the playground at the Ave Primary School - Vila das Aves | 45236119-7 | Repair work on sports fields | FALSE | 2020 | 2021 | Portugal | Santo Tirso | Porto | 13 | 14 | 28-10-2020 | 24-09-2021 | 331 | 90 | 89900 | 88959.48 | 1 | 97532.47 | -8572.99 | 91.2101 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of the deadline by 60 days. the existence of complementary works | the existence of complementary works
941 | 7252995 | Horizontal Signaling and Repaving - City of Portalegre | 45233200-1 | Various surface works | FALSE | 2020 | 2021 | Portugal | Portalegre | Portalegre | 12 | 30 | 03-11-2020 | 04-03-2021 | 121 | 90 | 254988.31 | 216598.19 | 1 | 216598.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change in the execution period of the project, due to the difficulty of the contractor's representative's schedule
942 | 7251430 | Installation of LED Projectors in the Lighting Towers of Roundabouts in the Municipality of Matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Matosinhos | Porto | 13 | 30 | 28-10-2020 | 01-07-2021 | 246 | 90 | 72601 | 71126.68 | 1 | 71126.68 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
943 | 7249937 | Global Requalification of Escola dos Assentos - Portalegre | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Portalegre | Portalegre | 12 | 30 | 03-11-2020 | 26-02-2021 | 115 | 180 | 420767.14 | 394392.92 | 2 | 394392.92 | 0 | 100 | Best value for money: No Criterion related to quality Name: QualityDiary of the Republic, 2nd series No. 9611 August 28, 2020 Page 4 Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project plan was executed faster than expected
944 | 7248363 | Contract 256/gebalis/2020 - Alto da Faia, Horta Nova and Quinta dos Barros neighborhoods - rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 16 | 02-11-2020 | 16-11-2021 | 379 | 90 | 63000 | 55233.52 | 1 | 53933.52 | 1300 | 102.4104 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
945 | 7248354 | Contract 253/gebalis/2020 - Casal dos Machados neighborhood / Quinta das Laranjeiras - Rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 8 | 02-11-2020 | 19-05-2021 | 198 | 120 | 208185.07 | 142167.63 | 1 | 142167.63 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
946 | 7245855 | Contract 233/GEBALIS/2020 - Bairro 2 Maio / Liberdade / Quinta do Jacinto - Rehabilitation of municipal housing | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 29-10-2020 | 05-05-2021 | 188 | 90 | 95000 | 69256.22 | 1 | 68356.22 | 900 | 101.3166 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others) | works less
947 | 7240010 | Water supply in Santa Vala | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 29-10-2020 | 18-05-2021 | 201 | 120 | 51414.92 | 49138.8 | 1 | 43971.53 | 5167.27 | 111.7514 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | it was not necessary to open the bituminous pavement, as planned/ ordinary price review
948 | 7239531 | Construction Contract for "Exterior maintenance works for public housing buildings in the neighborhood of Francos" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 28-10-2020 | 26-08-2021 | 302 | 180 | 1535000 | 430902.48 | 2 | 447773.74 | -16871.26 | 96.2322 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the projects of the contract took place normally from the consignment until the end of the contract, despite the decree of the state of emergency. | complementary and unforeseen work
949 | 7239386 | Construction Contract for "Exterior maintenance works for public housing buildings in the neighborhood of Francos" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 28-10-2020 | 26-08-2021 | 302 | 180 | 1535000 | 450530.96 | 2 | 467464.82 | -16933.86 | 96.3775 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the projects of the contract took place normally from the consignment until the end of the contract, despite the decree of the state of emergency. | complementary and unforeseen work
950 | 7239323 | Construction Contract for "Exterior maintenance works for public housing buildings in the neighborhood of Francos" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 28-10-2020 | 26-08-2021 | 302 | 180 | 1535000 | 447809.51 | 2 | 481464.01 | -33654.5 | 93.01 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the projects of the contract took place normally from the consignment until the end of the contract, despite the decree of the state of emergency. | complementary and unforeseen work
951 | 7237423 | Requalification pain multisports Dr. Mayan witch - mozelos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 26-10-2020 | 18-06-2021 | 235 | 120 | 92794 | 88590 | 1 | 88399 | 191 | 100.2161 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | 12 days in advance of the project execution deadline | additional work and underwork
952 | 7235785 | Work to rehabilitate streetPereira da Costa, as part of the application called Intervenção Integrada do Castelo - 1st phase | 45453100-8 | Refurbishment work | TRUE | 2020 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 15 | 26-10-2020 | 21-12-2021 | 421 | 150 | 299913.71 | 264000 | 2 | 243540.29 | 20459.71 | 108.401 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | a work suspension notice was duly approved. | the conclusion of the project resulted in underwork to the value of €32,258.26 and a definitive price review was determined in the amount of €11,798.55.
953 | 7235540 | Execution of the public works contract for the construction of a section of bicycle path on Avenida Brasília, next to the Bom Sucesso Dock | 45113000-2 | Siteworks | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 21 | 05-08-2020 | 02-03-2021 | 209 | 60 | 200000 | 156012.6 | 1 | 137643.01 | 18369.59 | 113.3458 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the difference to the contractual period results from the date on which the provisional reception by emel was scheduled, complying with the maximum period of 30 days as stipulated in the "public procurement code". | works not performed.
954 | 7234214 | 100% Quality - Maintenance and resurfacing on sidewalks 2020 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 28-10-2020 | 23-03-2021 | 146 | 60 | 60000 | 47760 | 1 | 47760 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
955 | 7233779 | 2020.502.02.C1 - SFP Bragança - rehabilitation of ceramic tile roofs | 45261910-6 | Roof repair | TRUE | 2020 | 2021 | Portugal | Bragança | Bragança | 4 | 30 | 28-07-2020 | 22-07-2021 | 359 | 90 | 73000 | 69337.33 | 1 | 74985.51 | -5648.18 | 92.4676 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | supplementary work and suspension of the contract under the terms of article 366, paragraph 3, point a) of the "public procurement code" | supplementary work
956 | 7231824 | streets in the Parish of Bouçoães | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 21-10-2020 | 09-09-2021 | 323 | 90 | 31295.09 | 30983.5 | 1 | 31515.33 | -531.83 | 98.3125 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unavailability of markets for the supply of granite cubes and prophylactic isolation of several company employees; | ordinary price review
957 | 7231208 | Requalification of the Road Network in the Union of the Parishes of Covões and Camarneira, by Contract - 1st Phase - CP-CCP-EMP n.º 11/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 16 | 27-10-2020 | 15-06-2021 | 231 | 180 | 301398 | 170099.21 | 1 | 187099.21 | -17000 | 90.9139 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works.
958 | 7229967 | Repair and painting works on the facades and boundary walls of the Municipal Police building | 45430000-0 | Floor and wall covering work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 20 | 27-10-2020 | 17-03-2021 | 141 | 120 | 135000 | 69325.63 | 1 | 69325.63 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 26 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractual provisions.
959 | 7228554 | Refurbishment and Improvement of dwellings in the Social Housing Districts of Mãe d'Água and Coxa. | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Bragança | Bragança | 4 | 14 | 23-10-2020 | 23-06-2021 | 243 | 120 | 55000 | 46750.01 | 1 | 46750.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay due to difficulties experienced in the supply of materials and labor.
960 | 7226874 | 1st - Phase of the Energy Efficiency Requalification Project of 6 Social Neighborhoods: Bairro Social de Atalaia | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2021 | Portugal | Lourinhã | Lisboa | 11 | 15 | 21-10-2020 | 16-06-2021 | 238 | 90 | 116178.22 | 112500 | 1 | 121863.31 | -9363.31 | 92.3165 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award criterion is the evaluation of the price. Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | miscellaneous constraint: due to the confinement decreed at national level in january 2021; prophylactic isolation of construction company workers, prophylactic isolation of residents in the atalia neighborhood and bad weather/heavy rain in the first months of the year, which prevented the project to replace the asbestos roof and carry out the exterior coating on the roof. | complementary works to supply errors and omissions - proc no. 1
961 | 7225038 | Control and reduction of losses in water distribution and supply systems in the municipality of penafiel - renovation of the water distribution network in the parish of rio de moinhos | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Penafiel | Porto | 13 | 20 | 27-07-2020 | 10-11-2021 | 471 | 300 | 452410 | 427988.85 | 2 | 427988.83 | 0.02 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension. | residual hit.
962 | 7221066 | Exterior maintenance works of public housing buildings in Bairro do Carriçal | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 21 | 23-10-2020 | 08-09-2021 | 320 | 270 | 1225000 | 752100 | 2 | 750480.29 | 1619.71 | 100.2158 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the projects of the contract took place normally from the consignment until the end of the contract, despite the decree of the state of emergency~. all legal and contractual obligations of the contractor arising from the identified works contract are fully and perfectly fulfilled | complementary and unforeseen work
963 | 7220875 | CM 1103 Requalification Contract | 45233220-7 | Surface work for roads | FALSE | 2020 | 2020 | Portugal | Arronches | Portalegre | 12 | 15 | 25-08-2020 | 06-12-2020 | 103 | 60 | 160000 | 117711 | 1 | 117711 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed before the deadline defined in the tender.
964 | 7218391 | Contract "Northern Line: Renovation of Track Superstructure between Kms 230.711/230.950 (VA)" (Process No. 10003514) | 45234100-7 | Railway construction works | FALSE | 2020 | 2021 | Portugal | Mealhada | Aveiro | 1 | 7 | 22-10-2020 | 07-07-2021 | 258 | 60 | 230000 | 227898.96 | 1 | 217627.41 | 10271.55 | 104.7198 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
965 | 7216462 | Requalification of Pescadores street | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Almada | Setúbal | 17 | 18 | 24-09-2020 | 06-09-2021 | 347 | 150 | 650259.41 | 644332.67 | 2 | 651075.24 | -6742.57 | 98.9644 | Best value for money: Yes Criterion related to quality Name: Bid Price Weighting: 40% Criterion related to cost Name: Technical Value of the Proposal Weighting: 60% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of 25 days. | due to underwork and price revision.
966 | 7216372 | Requalification of the Road Network in the Parish of Murtede and on Estrada de Sepins up to the County Limit, by Contract - CP-CCP-EMP n.º 12/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 22-10-2020 | 23-12-2021 | 427 | 180 | 330023 | 151250 | 1 | 149687.25 | 1562.75 | 101.044 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
967 | 7215251 | Contract for the improvement of buildings and equipment: - Contract for the installation of roofs in the car park at the Páteo premises and in the parking lot for buses at the premises | 45223110-0 | Installation of metal structures | FALSE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 01-10-2020 | 28-05-2021 | 239 | 90 | 250000 | 197997.06 | 1 | 197997.06 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
968 | 7215165 | streets in Zebras | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 21-10-2020 | 13-05-2021 | 204 | 120 | 32030.98 | 27976 | 1 | 27976 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
969 | 7213125 | Contract for "Recovery of the Old School of Fornos do Pinhal" | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-10-2020 | 22-06-2021 | 245 | 60 | 72966.95 | 72345.3 | 1 | 72345.3 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the deadline until may 10, 2021, although the provisional acceptance notice has only been drawn up now.
970 | 7212711 | streets in the parish of S. João de Corveira - Sobrado | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 19-10-2020 | 07-07-2021 | 261 | 60 | 25395.65 | 23600 | 1 | 23600 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to unfavorable weather conditions for carrying out the project
971 | 7202123 | Coastal protection measures - PP50 (Cabo do Mundo beach) | 45240000-1 | Construction work for water projects | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 20-10-2020 | 16-05-2021 | 208 | 90 | 108924 | 79490.76 | 1 | 79490.76 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
972 | 7170472 | Requalification and modernization of the elementary school at Peso-Santo Isidoro | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 20-10-2020 | 19-03-2021 | 150 | 120 | 160785.54 | 137435.05 | 1 | 137435.05 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time on: 03/01/2021
973 | 7159752 | CP No. 52/2020 - Contract for Supply and Installation of Covering and Air Conditioning/Ventilation System in the Clinical Hematology Pavilion | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 17 | 02-10-2020 | 26-02-2021 | 147 | 30 | 260000 | 62111.97 | 1 | 62111.97 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value per lot Weighting: 50% Criterion related to cost Name: Overall Value per lot Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | meteorological causes
974 | 7159696 | Carmelitas Church, Aveiro- Rehabilitation of the Church and Annex Building | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Aveiro | Aveiro | 1 | 21 | 16-10-2020 | 29-04-2021 | 195 | 120 | 114900 | 97040.06 | 1 | 96690.06 | 350 | 100.362 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on 06/04/2021 - the delivery and validation of the report proving compliance with the "plan for the prevention and management of construction and demolition waste" was awaited | job suppression
975 | 7158311 | Pedestrian route network - Construction of sidewalks | 45233161-5 | Footpath construction work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 07-10-2020 | 29-11-2021 | 418 | 120 | 615575.15 | 253179.75 | 2 | 278146.28 | -24966.53 | 91.024 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project finished within the deadline. | the project had complementary works worth €14,808.60 - underwork worth €340.79 - positive price revision worth €10,498.72.
976 | 7158247 | Improvement of the Rural Paths of Serra and Escáparos | 45233225-2 | Single carriageway construction work | FALSE | 2020 | 2021 | Portugal | Meda | Guarda | 9 | 14 | 08-10-2020 | 08-06-2021 | 243 | 180 | 188213.12 | 170714.63 | 1 | 169943 | 771.63 | 100.4541 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Item b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the stipulated period, the end of the project took place on april 18, 2021. | it results from correcting small amounts of work.
977 | 7157499 | Refurbishment of the southern façade of the Alpendurda Municipal Stadium | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 15-10-2020 | 05-08-2021 | 294 | 240 | 598000 | 567300 | 2 | 584907.21 | -17607.21 | 96.9897 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project ended within the deadline 06/24/2021 | the project had additional works worth: €13,099.27 and underwork worth: €1,097.04
978 | 7151033 | Refurbishment of the Vergada - Ordonhe - Argoncilhe sports center | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-10-2020 | 11-10-2021 | 360 | 90 | 86940 | 83705.56 | 1 | 88010.06 | -4304.5 | 95.1091 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 25 days extension additional work 6 days on inspection appointment | additional work and underwork
979 | 7150809 | Paving of the playground at Coelho e Castro School - Fiães | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 18 | 16-10-2020 | 10-02-2021 | 117 | 45 | 106807 | 98501.55 | 1 | 88364.75 | 10136.8 | 111.4715 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 25 days of graceful extension + 2 days for scheduling and carrying out the inspection for provisional rectification | underwork arising from discrepancies between the actual dimensions provided for in the paving project and the actual measurements on site
980 | 7150087 | Public Tender No. 38/ Social services of the National Guard/2020 | 45300000-0 | Building installation work | FALSE | 2020 | 2020 | Portugal | Almada | Setúbal | 17 | 21 | 14-07-2020 | 31-12-2020 | 170 | 180 | 180000 | 144378.33 | 1 | 144378.33 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
981 | 7150083 | Public Tender No. 39/ Social services of the National Guard/2020 | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Coimbra | Coimbra | 6 | 21 | 28-09-2020 | 29-12-2020 | 92 | 90 | 65000 | 32859.89 | 1 | 32859.89 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report
982 | 7134106 | Cpn 46/2020/dicp - t-50/2018 - execution of the road connection between Quinta dos Maristas and Casal dos Matos - Poões - Leiria | 45233120-6 | Road construction works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 30-07-2020 | 31-05-2021 | 305 | 90 | 74373 | 70462.7 | 1 | 69312.7 | 1150 | 101.6591 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (by the developer) due to lack of safety conditions (art. 365, paragraph a) | underwork (art.º 379.º n.º 2)
983 | 7133872 | 2017.016.01.C1 - Employment Service of Vila Nova de Gaia - Renovation of Facilities | 45259900-6 | Plant upgrade work | TRUE | 2020 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 12 | 23-07-2020 | 06-10-2021 | 440 | 180 | 620000 | 609850.84 | 2 | 627539.87 | -17689.03 | 97.1812 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension | additional work and underwork
984 | 7133665 | Rehabilitation of living space | 45212100-7 | Construction work of leisure facilities | FALSE | 2020 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 09-07-2020 | 31-05-2021 | 326 | 90 | 42000 | 38825.94 | 1 | 38825.94 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid
985 | 7131189 | Intervention contract at vitorino nemésio High school | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 33 | 30-09-2020 | 02-07-2021 | 275 | 153 | 330000 | 296999.07 | 2 | 325067.08 | -28068.01 | 91.3655 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works
986 | 7130375 | Contract work for the "Douro Line - Reinforcement of the Support Wall to Pk 119,080 (left side)" (Process No. 10000305) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Sabrosa | Vila Real | 19 | 35 | 08-10-2020 | 15-10-2021 | 372 | 150 | 275000 | 274814 | 2 | 288380.76 | -13566.76 | 95.2955 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 4 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | more work had to be done
987 | 7129356 | Supply and placement of road protection rails | 45233280-5 | Erection of road-barriers | FALSE | 2020 | 2021 | Portugal | Lousada | Porto | 13 | 12 | 02-10-2020 | 09-02-2021 | 130 | 15 | 22765 | 13272 | 1 | 13272 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: The most economically advantageous proposals Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | weather conditions
988 | 7127684 | Work to refurbish the Mosqueira road | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 11 | 13-10-2020 | 19-10-2021 | 371 | 150 | 1400000 | 1377433.3 | 3 | 1377433.3 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the execution period of the project is due to delays on the part of the contractor.
989 | 7125759 | Riverside area of ​​Ponte de Sor - North - Requalification of the Children's Park | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2020 | 2021 | Portugal | Ponte de Sor | Portalegre | 12 | 15 | 30-09-2020 | 18-08-2021 | 322 | 45 | 250453.75 | 212427.3 | 1 | 212427.3 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
990 | 7124764 | Requalification and Rehabilitation of Largo dos Combatentes | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Elvas | Portalegre | 12 | 21 | 20-08-2020 | 17-12-2021 | 484 | 120 | 130000 | 113893.27 | 1 | 113893.27 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to make several corrections in the project for the purpose of provisional acceptance.
991 | 7124542 | Cpn 49/2020/dicp - t-47/2020 rehabilitation and adaptation of the buildings and annexes of the municipal agromuseum dona julinha - union of the parishes of souto da carpalhosa and ortigosa | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 14-08-2020 | 29-11-2021 | 472 | 120 | 181373.36 | 171000 | 1 | 165070.68 | 5929.32 | 103.592 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | partial suspension under paragraph a) of art. 297 of the "public procurement code". | additional work pursuant to the provisions of 373-º and underwork pursuant to the provisions of art. 379º, nº2.
992 | 7122522 | Cpn 47/2020/dicp - t-45/2019 - roof replacement work and various repairs at the municipal sports pavilion in maceira | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 29 | 08-09-2020 | 10-05-2021 | 244 | 180 | 248675.5 | 234675.7 | 1 | 234675.7 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
993 | 7121879 | streets in the parish of Padrela and Tazém | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 01-10-2020 | 27-12-2021 | 452 | 90 | 20290.84 | 19720 | 1 | 19759.01 | -39.01 | 99.8026 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation caused by covid-19 and unavailability of materials to complete the project | ordinary price review
994 | 7118783 | Pavement rehabilitation - August 2020 | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 30-09-2020 | 18-11-2021 | 414 | 90 | 329535.75 | 327091.61 | 2 | 327091.61 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project finished within the deadline.
995 | 7116669 | CP No. 12/DRL/DA/2020 - Contract to expand facilities for the situation room in the Territorial Command of Guarda | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Guarda | Guarda | 9 | 14 | 31-08-2020 | 05-08-2021 | 339 | 120 | 100000 | 97523.82 | 1 | 97523.82 | 0 | 100 | Best value for money: No Criterion related to quality Name: See procedure parts Weighting: 0% Criterion related to cost Name: See procedure parts Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the covid19 pandemic
996 | 7116629 | CP No. 28/DRL/DA/2020 - Contract to replace the roof and various repairs at the Territorial Post of Vila do Bispo. | 45453100-8 | Refurbishment work | FALSE | 2020 | 2020 | Portugal | Vila do Bispo | Faro | 8 | 17 | 17-08-2020 | 18-12-2020 | 123 | 70 | 142500 | 98900 | 1 | 98900 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to covid19. | nothing to say.
997 | 7116610 | Restoration of streetde Nasce | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 18-09-2020 | 15-02-2021 | 150 | 90 | 44457.4 | 35552.13 | 1 | 38586.63 | -3034.5 | 92.1359 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work | additional work
998 | 7114577 | Urban Rehabilitation of the Municipality - Rehabilitation of the Bandstand | 45211310-5 | Bathrooms construction work | FALSE | 2020 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 9 | 02-10-2020 | 30-08-2021 | 332 | 60 | 56531.97 | 53243.5 | 1 | 58503.5 | -5260 | 91.0091 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | free extension of the execution period | complementary works
999 | 7112722 | Cp 27/2019 - rehabilitation of wastewater collectors using cipp technology on Avenida d. João iv in the parish of urgezes and uf de oliveira, s. Paio and S. Sebastião - municipality of guimarães | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 02-06-2020 | 03-09-2020 | 93 | 90 | 113000 | 73011 | 1 | 71308.69 | 1702.31 | 102.3872 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work planning | underwork
1000 | 7111359 | Expansion / Remodeling of Water Networks in Bairro Alegre, Casais da Areia and Picanceira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Mafra | Lisboa | 11 | 20 | 01-06-2020 | 01-02-2021 | 245 | 60 | 201900 | 52237.2 | 1 | 52237.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the pandemic, there were delays in the execution of the projects
1001 | 7110688 | Rehabilitation of property at street of Mouraria, n.º32 and n.º34, 2 dwellings, T1 and T2, in Portalegre, P.E.D.U. - P.a.i.c.d. 07 | 45210000-2 | Building construction work | FALSE | 2020 | 2021 | Portugal | Portalegre | Portalegre | 12 | 14 | 27-08-2020 | 18-11-2021 | 448 | 180 | 180438.75 | 179993.15 | 1 | 184221.37 | -4228.22 | 97.7048 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | location of the building, and state of degradation and weather conditions | price review
1002 | 7108654 | Pedestrian route network - Construction of sidewalks | 45233161-5 | Footpath construction work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 30-09-2020 | 15-04-2021 | 197 | 120 | 615575.15 | 140505.05 | 1 | 140125.05 | 380 | 100.2712 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project finished within the deadline. | the project had underwork
1003 | 7108077 | Implementation of ZMC to control losses in the water supply system of the Municipality of Lousada | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 21-09-2020 | 18-10-2021 | 392 | 270 | 657500 | 593304.83 | 2 | 593304.83 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | no change.
1004 | 7105527 | Expansion / Remodeling of Water Networks in Bairro Alegre, Casais da Areia and Picanceira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2020 | Portugal | Mafra | Lisboa | 11 | 20 | 08-06-2020 | 29-10-2020 | 143 | 60 | 201900 | 25382.82 | 1 | 25382.82 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the pandemic, there were delays in the execution of the projects
1005 | 7105391 | EP-2020(5001)/10015 Improvement of CA Areia Branca and Surrounding Exterior - CED SCT | 45113000-2 | Siteworks | TRUE | 2020 | 2021 | Portugal | Lourinhã | Lisboa | 11 | 14 | 01-10-2020 | 18-02-2021 | 140 | 90 | 125000 | 114941.33 | 1 | 112412.62 | 2528.71 | 102.2495 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out the project | penalty for delays in completing the contract
1006 | 7105381 | Expansion / Remodeling of Water Networks in Bairro Alegre, Casais da Areia and Picanceira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2020 | Portugal | Mafra | Lisboa | 11 | 20 | 25-05-2020 | 10-12-2020 | 199 | 90 | 201900 | 94376.75 | 1 | 94376.75 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to the pandemic, there were delays in the execution of the projects
1007 | 7104562 | Energy Efficiency in Public Lighting in Póvoa de Lanhoso | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 30-09-2020 | 14-01-2021 | 106 | 90 | 395330 | 339878.42 | 2 | 339878.42 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1008 | 7102390 | Quarteira entrance project - atlântico avenue | 45112700-2 | Landscaping work | FALSE | 2020 | 2021 | Portugal | Loulé | Faro | 8 | 18 | 01-09-2020 | 26-05-2021 | 267 | 150 | 233699.56 | 228552.24 | 1 | 226852.25 | 1699.99 | 100.7494 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it took place conditioned by covid 19 | there were works that were not performed
1009 | 7101904 | Municipal Pavilion - Intervention to Improve Energy Efficiency. | 45212200-8 | Construction work for sports facilities | FALSE | 2020 | 2021 | Portugal | Fafe | Braga | 3 | 15 | 09-09-2020 | 01-09-2021 | 357 | 150 | 619712.31 | 580863.91 | 2 | 630259.47 | -49395.56 | 92.1627 | Best value for money: Yes Criterion related to quality Name: Technical value and guarantee of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were two graceful deadline extensions | there were complementary works
1010 | 7101668 | Carpet Paving Contract in Various Locations in the Municipality for 2020 -Proc.nº23/DPO/SOM/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Arouca | Aveiro | 1 | 15 | 30-09-2020 | 18-10-2021 | 383 | 60 | 451155 | 288896.9 | 2 | 306700.33 | -17803.43 | 94.1952 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment as the only aspect of contract performance to be to celebrate Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work | additional work, underwork and price revisions
1011 | 7100909 | Contract for Requalification of the São Francisco Xavier Car Park, São José | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 17 | 28-09-2020 | 22-04-2021 | 206 | 120 | 349000 | 345052.82 | 2 | 345052.82 | 0 | 100 | PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 146 THURSDAY, JULY 30, 2020 If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | there were no changes to the value of the project
1012 | 7098014 | 1400006/2020 - Contract to create the Day Hospital of Psychiatry at Hospital do Montijo, at CHBM,E.P.E | 45215140-0 | Hospital facilities construction work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 15 | 28-08-2020 | 04-06-2021 | 280 | 150 | 190650 | 181694.72 | 1 | 163539.56 | 18155.16 | 111.1014 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost modality Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
1013 | 7060080 | Road Transport, Municipal Roads and Street Paving - Municipal Road Safres - Amieiro - Franzilhal. | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2020 | 2021 | Portugal | Alijó | Vila Real | 19 | 14 | 27-08-2020 | 14-01-2021 | 140 | 90 | 382187.5 | 320092.1 | 2 | 320092.1 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | elapsed within the term of the contract
1014 | 7006111 | 2017.114.01.C1 - SE Abrantes-Remodeling of Lighting, ITED and HVAC Installation | 45310000-3 | Electrical installation work | TRUE | 2019 | 2021 | Portugal | Abrantes | Santarém | 16 | 30 | 19-09-2019 | 15-12-2021 | 818 | 180 | 450000 | 394400 | 2 | 409919.76 | -15519.76 | 96.214 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension. covid-19 | additional work, underwork and price revisions
1015 | 7005793 | 2014.092.03.C1 - Loures Employment Service - refurbishment of facilities | 45210000-2 | Building construction work | TRUE | 2020 | 2021 | Portugal | Loures | Lisboa | 11 | 21 | 23-04-2020 | 17-12-2021 | 603 | 180 | 392000 | 379973 | 2 | 385567 | -5594 | 98.5491 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works. covid-19 | additional work and underwork
1016 | 7002197 | Application of sandwish panel plate to replace tile and flat roofing, also including replacement of glazed skylights and painting of exterior walls. | 45214220-8 | Secondary school construction work | FALSE | 2020 | 2021 | Portugal | Sertã | Castelo Branco | 5 | 21 | 06-08-2020 | 24-09-2021 | 414 | 90 | 166742 | 139474.8 | 1 | 141289.33 | -1814.53 | 98.7157 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delay in completing the project, translated into two graceful extensions of 30 and 60 days, was caused by heavy rains and delays in supplies related to the covid-19 pandemic. | occurrence of complementary work.
1017 | 7001502 | Recovery of deactivated school buildings (Improvement of the School of Ribeira de St.º Amaro) - Proc. No. 46/2020 | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 22-09-2020 | 22-11-2021 | 426 | 60 | 49537.3 | 46745.73 | 1 | 46745.73 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | closing of accounts for the project and delay in delivering the waste plan. | works not performed and price review.
1018 | 6999183 | Refurbishment of Alameda da Saudade | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 16-09-2020 | 08-11-2021 | 418 | 304 | 533987.7 | 455475.41 | 2 | 480289.06 | -24813.65 | 94.8336 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work was completed on time | complementary work, underwork, revision of prices.
1019 | 6999131 | streets in Possacos | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 14-09-2020 | 04-06-2021 | 263 | 120 | 39781.48 | 30666 | 1 | 30666 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | current pandemic situation associated with covid 19, having tested positive most employees of the contracting authority
1020 | 6999118 | Cp/02/dom/2020 - sjm efficient eco lighting | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2020 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 11 | 22-06-2020 | 02-02-2021 | 225 | 180 | 303852.27 | 299991.15 | 2 | 299991.15 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | greater allocation of means
1021 | 6995115 | 2018.061.01.C1 - Marinha Grande Employment Service - refurbishment of facilities | 45210000-2 | Building construction work | TRUE | 2020 | 2021 | Portugal | Marinha Grande | Leiria | 10 | 21 | 27-04-2020 | 21-10-2021 | 542 | 240 | 459224 | 438834 | 2 | 467776.47 | -28942.47 | 93.8128 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data | complementary work and underwork and definitive price revision
1022 | 6984158 | Repaving of the EM 509 Municipal Road. | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Mértola | Beja | 2 | 30 | 24-08-2020 | 27-09-2021 | 399 | 180 | 1217000 | 964971.59 | 2 | 964971.59 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by price assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | they didn't exist.
1023 | 6979130 | Construction of Tennis Courts in the City Park. | 45212200-8 | Construction work for sports facilities | FALSE | 2020 | 2021 | Portugal | Fafe | Braga | 3 | 15 | 12-08-2020 | 30-11-2021 | 475 | 61 | 141416.71 | 134999.95 | 1 | 134990.31 | 9.64 | 100.0071 | Best value for money: Yes Criterion related to quality Name: Technical value and guarantee of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | there was a deadline extension and a suspension of work | not all quantities have been executed in an article.
1024 | 6976487 | Contract for "Installation of New Ecological Islands - Includes Equipment and Landscape Treatment" | 45262640-9 | Environmental improvement works | FALSE | 2020 | 2021 | Portugal | Lagos | Faro | 8 | 30 | 11-09-2020 | 20-12-2021 | 465 | 120 | 431000 | 417309.58 | 2 | 418650.76 | -1341.18 | 99.6796 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in subparagraph b) of paragraph 1 of article 74. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended for another 80 days | the value of the project has changed, due to the determination of the provisional value of the price review
1025 | 6975275 | The purpose of this procedure is to carry out a contract for the reformulation of the building, namely the construction of 4 rooms, alteration of the metallic guards and the rehabilitation of the building | 45262700-8, 45443000-4 | Building alteration work, Facade work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 30 | 04-06-2020 | 31-08-2021 | 453 | 123 | 272500 | 236284.47 | 1 | 240685.91 | -4401.44 | 98.1713 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to unforeseen changes in the course of the project
1026 | 6973906 | Cpn 50/2020 - t-65/2020 - rehabilitation and improvement of the road pavement of several streets in the urban area of ​​leiria | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 26-08-2020 | 05-02-2021 | 163 | 90 | 345443 | 322983.09 | 2 | 322983.09 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1027 | 6972492 | Public works contract for Installation of HVAC, Lighting, application of external thermal insulation and Installation of photovoltaic panels, HEADQUARTERS building | 45261215-4 | Solar panel roof-covering work | TRUE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 4 | 12-06-2020 | 07-09-2020 | 87 | 60 | 206000 | 43940 | 1 | 43940 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | completion of the project in less time than contracted.
1028 | 6970564 | Work contract for the repair and replacement of equipment at the water plants in Ericeira, Encarnação and Torres Vedras | 45232460-4 | Sanitary works | FALSE | 2019 | 2021 | Portugal | Torres Vedras | Lisboa | 11 | 28 | 23-04-2020 | 25-05-2021 | 397 | 300 | 480000 | 467960.82 | 2 | 467960.82 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the expected time frame.
1029 | 6965625 | Cpn 55/2020/dicp- process t-53/2020 - replacement of window frames in housing and various works in the social neighborhood of cova das faias - union of parishes of santa eufémia and boa vista | 45421110-8 | Installation of door and window frames | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 04-08-2020 | 24-11-2021 | 477 | 90 | 91538 | 85271.65 | 1 | 82420.35 | 2851.3 | 103.4595 | Best value for money: No Criterion related to quality Name: Not applicable Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork under the terms of article 379, paragraph 2 of the "public procurement code".
1030 | 6965605 | Energy Requalification of Public Lighting in the Municipality of Sabrosa Lot 1; Energy Requalification of Public Lighting in the Municipality of Sabrosa Lot 2. | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2020 | 2021 | Portugal | Sabrosa | Vila Real | 19 | 15 | 07-05-2020 | 22-03-2021 | 319 | 150 | 562340 | 369312.91 | 2 | 390596.76 | -21283.85 | 94.5509 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | carrying out additional work | execution of complementary work
1031 | 6933981 | Bituminous repaving in several parishes - June 2020 | 45233251-3 | Resurfacing works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 04-09-2020 | 12-08-2021 | 342 | 60 | 195000 | 188505.05 | 1 | 188505.05 | 0 | 100 | Best value for money: No Diário da República, 2nd series No. 7651 July 15, 2020 Page 4 Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work
1032 | 6933630 | Contract for the Refurbishment of Laboratories at the Escola Superior de Saúde, Campus 2 of the Polytechnic of Leiria | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2020 | Portugal | Leiria | Leiria | 10 | 22 | 11-08-2020 | 20-11-2020 | 101 | 90 | 277000 | 260000 | 2 | 260000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it took place in accordance with the terms set out in the terms of reference
1033 | 6931330 | Measurement and Control Areas (ZMC) of the Water Supply Networks of the Municipality of Reguengos de Monsaraz (MACPerdas) | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 02-09-2020 | 16-08-2021 | 348 | 120 | 164735.65 | 164500 | 1 | 164500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of the execution period for 21 days, pursuant to article 297(a)
1034 | 6922956 | Execution contract for the Pipeline between the Outeiro Grande and Rendufas Reservoirs | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Torres Novas | Santarém | 16 | 21 | 27-08-2020 | 16-08-2021 | 354 | 180 | 500000 | 389221.2 | 2 | 380366.26 | 8854.94 | 102.328 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work pursuant to an opinion issued by the directorate-general for cultural heritage (dgpc). | underwork.
1035 | 6922921 | Rehabilitation contract for the Foros de Almada and Rebocho Reservoirs | 45247270-3 | Reservoir construction works | FALSE | 2020 | 2021 | Portugal | Coruche | Santarém | 16 | 21 | 27-08-2020 | 20-08-2021 | 358 | 240 | 500000 | 466489.7 | 2 | 464281.89 | 2207.81 | 100.4755 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the foreseen period and the provisional acceptance derives from the correction of defects detected in the inspection. | the objective of the project was fully achieved, not requiring the invoicing of all items. the effective total value also includes the price revision value.
1036 | 6921896 | 2018.517.04.C1 - SC Xabregas - electrical intervention at Teatro Ibérico | 45310000-3 | Electrical installation work | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 30 | 28-05-2020 | 22-01-2021 | 239 | 120 | 69000 | 56000 | 1 | 60817 | -4817 | 92.0795 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
1037 | 6921226 | Requalification of street of Tranhedos in Rendufinho | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 09-09-2020 | 07-01-2021 | 120 | 90 | 47424.23 | 35900 | 1 | 45930.12 | -10030.12 | 78.1622 | Best value for money: Yes Criterion related to quality Name: Technical quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline extension is for the good execution of the additional work. | additional work
1038 | 6920556 | Improvement of the connection of the M314 to Aveleda | 45233220-7 | Surface work for roads | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 07-09-2020 | 28-12-2020 | 112 | 90 | 86163.33 | 76181.91 | 1 | 71557.6 | 4624.31 | 106.4624 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | underwork €4,624.31
1039 | 6912171 | Contract for the Construction of the Social/Children's Park in Pechão | 45112723-9 | Landscaping work for playgrounds | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 04-08-2020 | 09-11-2021 | 462 | 270 | 320000 | 315000.02 | 2 | 315000.02 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of 66 days to study changes to the project. graceful extension of 40 days due to delays attributable to the contractor.
1040 | 6911651 | Contract for "Urban Arrangement in the Place of Santa Rita - Sanfins" | 45112723-9 | Landscaping work for playgrounds | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 08-09-2020 | 22-12-2021 | 470 | 120 | 70605.09 | 69580 | 1 | 69580 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions
1041 | 6910804 | Requalification of the Municipal Road between the EN2 and Seada | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 20-08-2020 | 25-06-2021 | 309 | 240 | 349500 | 289600 | 2 | 289600 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty in entering the project by the company that will execute the signage of the project, due to successive unfavorable weather conditions and the existence of commitments previously assumed by that subcontractor. | non-existence
1042 | 6910169 | 19CC11CP015-Contract work to repair the retaining and drainage wall of the Social Work of Pousal da Santa Casa da Misericórdia de Lisboa | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | N/A | N/A | N/A | 9 | 25-08-2020 | 08-06-2021 | 287 | 90 | 65000 | 61450.44 | 1 | 66046.1 | -4595.66 | 93.0417 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to carry out unforeseen complementary work, resulting from errors and omissions in the project. | complementary works were carried out which implied an increase in the value of the project of € 4,595.66.
1043 | 6907508 | Paving, in bituminous concrete, of streets in the union of the parishes of Santa Maria da Feira, Travanca, Sanfins and Espargo - 8th Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 04-09-2020 | 17-11-2021 | 439 | 120 | 331751 | 263475.63 | 2 | 261112.09 | 2363.54 | 100.9052 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 153 days of delay by the contractor in completing the projects, 100 days between the 1st inspection and the provisional acceptance of the project in the correction of deficiencies | underwork
1044 | 6907133 | Contract for carrying out basic sanitation and paving of streetArantes Oliveira | 45000000-7 | Construction work | TRUE | 2020 | 2021 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 26-08-2020 | 11-05-2021 | 258 | 210 | 189000 | 178658.9 | 1 | 178658.9 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Factor Weighting: 60% Criterion related to cost Name: Work execution quality factor. Weighting: 40% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1045 | 6906987 | Landscape requalification of the Largo de Santa Apolónia - Malta | 45112710-5 | Landscaping work for green areas | FALSE | 2020 | 2021 | Portugal | Vila do Conde | Porto | 13 | 21 | 03-08-2020 | 25-10-2021 | 448 | 213 | 650000 | 620236.51 | 2 | 629717.92 | -9481.41 | 98.4943 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1046 | 6906583 | Requalification of Avenida 14 de Janeiro - 3rd Phase. | 45432110-8 | Floor-laying work | FALSE | 2020 | 2021 | Portugal | Elvas | Portalegre | 12 | 21 | 20-08-2020 | 27-04-2021 | 250 | 180 | 288000 | 269688.29 | 2 | 269688.29 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to make some corrections in the project in order to be able to carry out the provisional acceptance
1047 | 6905907 | EP-2020(5001)/10009 Replacement of Existing Spans in Wood at CED JRP | 45259900-6 | Plant upgrade work | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 31 | 04-09-2020 | 06-01-2021 | 124 | 90 | 190000 | 139858.06 | 1 | 139858.06 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
1048 | 6904688 | Improvement of the Sports Center of Canaveses | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 18 | 04-09-2020 | 23-09-2020 | 19 | 60 | 7750 | 7750 | 1 | 7750 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1049 | 6902255 | Works Contract "Rehabilitation Works of Roofs of the New Building of School Equipment EB/JI of S. Miguel de Nevogilde" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 15 | 02-09-2020 | 30-09-2021 | 393 | 90 | 550000 | 478840.76 | 2 | 455849.4 | 22991.36 | 105.0436 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was delayed by 91 days, having been completed only on july 2, 2021. 3 pecuniary contractual sanctions were applied | complementary and unforeseen work
1050 | 6899655 | Refurbishment / conservation of the municipal sports pavilion of the waterfalls | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2020 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 12 | 07-08-2020 | 03-03-2021 | 208 | 150 | 215100 | 150388.4 | 1 | 150388.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
1051 | 6898954 | Street layouts in various places in the municipality - (São Pedro de Veiga de Lila) | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 14-08-2020 | 26-11-2020 | 104 | 60 | 11284.77 | 10983 | 1 | 10983 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1052 | 6898887 | Construction of a water tank in S. Pedro de Veiga de Lila | 45247270-3 | Reservoir construction works | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 01-09-2020 | 11-02-2021 | 163 | 90 | 25110.51 | 24598.5 | 1 | 24598.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1053 | 6898718 | Sanitation in Vale de Espinho | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 18 | 19-08-2020 | 07-10-2021 | 414 | 300 | 199470.11 | 186000 | 1 | 188673.85 | -2673.85 | 98.5828 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension motivated by the covid-19 pandemic, which conditioned the production of materials to be used | ordinary price review
1054 | 6898617 | Street layouts in the parish of São João de Corveira - (Rio Bom) | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 12-08-2020 | 15-01-2021 | 156 | 90 | 26701.43 | 25510 | 1 | 25510 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1055 | 6898542 | Water supply in Crasto | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 12-08-2020 | 04-06-2021 | 296 | 120 | 66019.22 | 61825.6 | 1 | 56110.6 | 5715 | 110.1852 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects | non-execution of planned works near the edge and consequent failure of the bituminous pavement
1056 | 6896994 | Rehabilitation of Roofs and Rainwater Drainage Network at Casa do Infante | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Porto | Porto | 13 | 30 | 01-09-2020 | 15-10-2021 | 409 | 180 | 350000 | 316198.39 | 2 | 339766.03 | -23567.64 | 93.0636 | Best value for money: Yes Criterion related to quality Name: Technical Valuation of the Proposal (Methodology / Work Program / Safety) Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to extend the deadline by 37 days | complementary works
1057 | 6892045 | Street paving - Bairro da Liberdade and Bairro das Amoreiras | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Grandola | Setúbal | 17 | 30 | 17-08-2020 | 01-04-2021 | 227 | 90 | 150662.58 | 118638.22 | 1 | 125762.89 | -7124.67 | 94.3348 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | some difficulty in scheduling the signing of the contract, due to the retirement of the contract manager and the appointment of a new manager.
1058 | 6890102 | Reorganization contract for the Treasury of the Headquarters Building - OA013220 | 45432000-4 | Floor-laying and covering, wall-covering and wall-papering work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 28 | 09-07-2020 | 19-02-2021 | 225 | 123 | 25000 | 19221.33 | 1 | 20827.28 | -1605.95 | 92.2892 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | objective modification of contract | objective modification of contract
1059 | 6888700 | Contract for "Ecovia do Litoral Algarve between the Municipal Shipyard and the Limit of the Municipality of Faro" | 45432110-8 | Floor-laying work | FALSE | 2020 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 03-08-2020 | 29-10-2021 | 452 | 180 | 350000 | 293944.08 | 2 | 291639.85 | 2304.23 | 100.7901 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the suspension of work had to do with weather issues that flooded part of the area where the intervention was carried out and w/ problems related to the pandemic | work that was not carried out and others carried out but not foreseen (complementary work)
1060 | 6887903 | Paving of Village streets - VII Phase | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Grandola | Setúbal | 17 | 21 | 17-08-2020 | 22-03-2021 | 217 | 90 | 142168.73 | 99957.98 | 1 | 103731.96 | -3773.98 | 96.3618 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid 19 pandemic nationwide.
1061 | 6884384 | Construction contract for the Car Park on streetde Santana, São Sebastião | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 17 | 24-08-2020 | 29-07-2021 | 339 | 120 | 174000 | 173250 | 1 | 166193.4 | 7056.6 | 104.246 | If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | legal suspension of term | underwork
1062 | 6881810 | Cpn 57/2020/dicp - t-06/2020 - execution of the earth support wall in gabions in the area surrounding the urbanization of belo Horizonte - union of the parishes of marrazes and barosa | 45341000-9 | Erection of railings | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 28-07-2020 | 10-02-2021 | 197 | 90 | 95377.5 | 95230 | 1 | 89280 | 5950 | 106.6644 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork under the terms of article 379, paragraph 2 of the "public procurement code".
1063 | 6877102 | 100% Quality - Bituminous paving at the UF of Perafita, Lavra and Santa Cruz do Bispo | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 21-08-2020 | 15-02-2021 | 178 | 90 | 370000 | 275555.72 | 2 | 295184.92 | -19629.2 | 93.3502 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1064 | 6876596 | Remodeling of the EB 2/3 José dos Anjos School Pavilion - Carrazedo de Montenegro | 45454000-4 | Restructuring work | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 30 | 06-08-2020 | 01-04-2021 | 238 | 120 | 88099.5 | 87480.65 | 1 | 87480.65 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of materials to the site by transport companies and manufacturers; shortage of workers due to prophylactic isolation caused by the covid-19 pandemic
1065 | 6873742 | Contract - Execution of works in the External Consultation Office of the Ophthalmology Service of the Torres Vedras unit of the Centro Hospitalar do Oeste | 45215000-7 | Construction work for buildings relating to health and social services, for crematoriums and public conveniences | FALSE | 2019 | 2019 | Portugal | Caldas da Rainha | Leiria | 10 | 14 | 20-11-2019 | 31-12-2019 | 41 | 30 | 12000 | 5581.5 | 1 | 5581.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1066 | 6871715 | Parque do Leça, Ermesinde - Restoration of the riparian gallery, promotion of the continuity of the corridor and stabilization of the banks using natural engineering techniques | 45246200-5 | Riverbank protection works | FALSE | 2020 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 18-08-2020 | 12-10-2021 | 420 | 210 | 214000 | 149323.13 | 1 | 151064.65 | -1741.52 | 98.8472 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution deadline, however the project was completed ahead of schedule and the provisional reception took place about 1 month ahead of schedule. | approval of the calculation of the provisional price revision in the amount of 1,741.52
1067 | 6870708 | Construction of water supply and wastewater networks on street of Tapada Velha in the parish of Romariz | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-05-2020 | 14-01-2021 | 246 | 120 | 84707.52 | 74675.69 | 1 | 74526.02 | 149.67 | 100.2008 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | 78 days for delay in delivery of final screens that caused delay in provisional reception | underwork
1068 | 6865100 | Contract for the Improvement of the Road from Forno Telheiro to the Church - Urrô. | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Arouca | Aveiro | 1 | 30 | 20-08-2020 | 25-06-2021 | 309 | 210 | 304519.68 | 248531.53 | 1 | 270032.2 | -21500.67 | 92.0377 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project took place in a pandemic period that affected the deadlines for delivery of materials and the frequency of workers. | it was verified that there was no need for the amounts foreseen in the project for the completion of the project.
1069 | 6864361 | streets in the parish of Lebução | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-08-2020 | 24-05-2021 | 277 | 90 | 49307.38 | 49300.5 | 1 | 49300.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | impediment of the contractor's staff due to covid-19 infection; lack of material, namely granite cubes and unfavorable weather conditions for carrying out the project.
1070 | 6861787 | General Improvement of the Elementary School Building Maria Máxima Vaz - Odivelas | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Odivelas | Lisboa | 11 | 20 | 26-07-2019 | 28-07-2020 | 368 | 60 | 155000 | 143661.88 | 1 | 158033.69 | -14371.81 | 90.9059 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without changes | execution of unforeseen works
1071 | 6861607 | Requalification of the Nossa Senhora de Fátima neighborhood in Travassos | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 18-08-2020 | 15-01-2021 | 150 | 90 | 52986.61 | 39838.14 | 1 | 49650.76 | -9812.62 | 80.2367 | Best value for money: Yes Criterion related to quality Name: Technical quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works. | complementary works.
1072 | 6854437 | Sanitation infrastructure street ofs Alminhas - Parish of Avessadas and Rosém | 45232460-4 | Sanitary works | FALSE | 2020 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 27-07-2020 | 12-11-2020 | 108 | 60 | 27890 | 26505 | 1 | 26195 | 310 | 101.1834 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project was finished ahead of schedule | underwork
1073 | 6851467 | Requalification of streets in Arez, Nisa and Alpalhão | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Nisa | Portalegre | 12 | 18 | 30-07-2020 | 27-09-2021 | 424 | 180 | 165891.35 | 151890.51 | 1 | 153814.79 | -1924.28 | 98.749 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of definitive price revision indices. | price revision in the amount of €1,924.28.
1074 | 6844996 | EP-2020(5001)/10012 Miscellaneous repairs in the kitchen and dining room | 45113000-2 | Siteworks | TRUE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 12-08-2020 | 22-12-2020 | 132 | 60 | 141000 | 127738.25 | 1 | 127738.25 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1075 | 6844375 | Furnace Interceptor (2nd Phase) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2021 | Portugal | Castelo de Paiva | Aveiro | 1 | 21 | 22-05-2020 | 02-06-2021 | 376 | 180 | 500000 | 180849.72 | 1 | 176505.89 | 4343.83 | 102.461 | Best value for money: Yes Criterion related to quality Name: - Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | this contract had 3 deadline extensions for a total of 100 days: due to a request to change the project requested by the municipality of castelo de paiva; due to adverse weather conditions; due to the effect that the covid19 pandemic had on the performance of the contract works. | the diameter of the elevator piping has been changed and a reduction cone has been removed
1076 | 6842496 | Rehabilitation of the Lota da Fuseta building | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 07-10-2019 | 12-02-2021 | 494 | 100 | 320000 | 299200 | 2 | 346512 | -47312 | 86.3462 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
1077 | 6842396 | Requalification / Enhancement of the Mêda Cemetery | 45215400-1 | Cemetery works | FALSE | 2020 | 2021 | Portugal | Meda | Guarda | 9 | 14 | 10-08-2020 | 08-06-2021 | 302 | 180 | 99991 | 95652.94 | 1 | 92109.05 | 3543.89 | 103.8475 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conditional execution due to the pandemic situation. | it is the result of correcting the amount of work.
1078 | 6841133 | Expansion and Improvement of the Wastewater Collection Network in Barreira, Coriscada and Meda | 45232460-4 | Sanitary works | FALSE | 2020 | 2021 | Portugal | Meda | Guarda | 9 | 14 | 10-08-2020 | 20-12-2021 | 497 | 180 | 67162.5 | 65987.5 | 1 | 74486.25 | -8498.75 | 88.5902 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price - paragraph b) of no. 1 of art. 74 of the CCP Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had a normal execution during the first two months, after this period there were several mishaps, namely people infected with covid 19, which delayed the normal progress of the projects. | execution of complementary works.
1079 | 6840179 | Public Works Contract for Geometric Reformulations and Improvement of Pedestrian Accessibility in the Municipality of Cascais | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 15 | 11-08-2020 | 20-07-2021 | 343 | 60 | 276086.22 | 45566.18 | 1 | 45566.18 | 0 | 100 | Best value for money: No Criterion related to quality Name: Criterion related to quality Weighting: 0% Criterion related to cost Name: Price is the only aspect submitted to competition Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1080 | 6840172 | Public Works Contract for Geometric Reformulations and Improvement of Pedestrian Accessibility in the Municipality of Cascais | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 15 | 11-08-2020 | 20-07-2021 | 343 | 60 | 276086.22 | 70252.26 | 1 | 70252.26 | 0 | 100 | Best value for money: No Criterion related to quality Name: Criterion related to quality Weighting: 0% Criterion related to cost Name: Price is the only aspect submitted to competition Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1081 | 6840170 | Public Works Contract for Geometric Reformulations and Improvement of Pedestrian Accessibility in the Municipality of Cascais | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 15 | 11-08-2020 | 04-08-2021 | 358 | 60 | 276086.22 | 89611.41 | 1 | 89611.41 | 0 | 100 | Best value for money: No Criterion related to quality Name: Criterion related to quality Weighting: 0% Criterion related to cost Name: Price is the only aspect submitted to competition Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | minor fixes
1082 | 6837994 | Construction of the waste water drainage network at street of Parque Desportivo - Vila Maior | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 10-08-2020 | 14-01-2021 | 157 | 60 | 14629.95 | 12875.24 | 1 | 12504.95 | 370.29 | 102.9611 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 44 days of delay in the inspection for provisional acceptance was due to the delay in the delivery of the final screens of the contract | underwork
1083 | 6837970 | Public C. No. 35/ Social services of the National Guard/2020 | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 21 | 25-06-2020 | 31-12-2020 | 189 | 30 | 43000 | 25499 | 1 | 25499 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price/Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1084 | 6835519 | Current conservation of the pavement of roads in the municipality of Guimarães 2020 | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 20 | 06-08-2020 | 13-10-2021 | 433 | 365 | 348541.54 | 347791.54 | 2 | 347791.54 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the approval of the safety and health plan for the project was communicated on 09/29/2020
1085 | 6835051 | EP-2020(5001)/10010 Rehabilitation of the apartment on Av. Madeira Island, 24 - 1st Left/Frt | 45113000-2 | Siteworks | TRUE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 14 | 07-08-2020 | 21-01-2021 | 167 | 120 | 100000 | 66894 | 1 | 66894 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1086 | 6834318 | CP 15/2018 – Execution of paving work to support the maintenance and conservation of water supply and wastewater sanitation systems, in the municipalities of Guimarães and Vizela | 45432110-8 | Floor-laying work | FALSE | 2018 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 23-10-2018 | 30-07-2020 | 646 | 365 | 88000 | 87093 | 1 | 87093 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
1087 | 6833916 | 2017.087.01.C1 - Employment Service of Salvaterra de Magos - remodeling of facilities | 45259900-6 | Plant upgrade work | TRUE | 2020 | 2020 | Portugal | Salvaterra de Magos | Santarém | 16 | 21 | 14-05-2020 | 16-12-2020 | 216 | 150 | 245969.85 | 244743.49 | 1 | 244743.49 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1088 | 6833897 | Public Contest No. 08/2020 | 45453100-8 | Refurbishment work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 15 | 31-07-2020 | 23-12-2020 | 145 | 115 | 400000 | 349691.62 | 2 | 363731.62 | -14040 | 96.14 | Best value for money: Yes Criterion related to quality Name: Period of execution of the work Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulties in delivering some materials due to covid-19. | there was a need to carry out complementary works that were not foreseen in the project, but without which the project would not have been completed.
1089 | 6832648 | CP 13/2020_DEGA - Renovation RDA and RDAR of Bairro da Bela Vista - Aveiro | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2020 | 2021 | Portugal | Aveiro | Aveiro | 1 | 30 | 04-08-2020 | 26-05-2021 | 295 | 120 | 240000 | 215171.41 | 1 | 210825.9 | 4345.51 | 102.0612 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1090 | 6832599 | Contract for the execution of water supply lines | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 31-07-2020 | 28-04-2021 | 271 | 153 | 70700 | 51300 | 1 | 51300 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1091 | 6832339 | Requalification of street of Longainho in Geraz do Minho | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 05-05-2020 | 02-11-2020 | 181 | 90 | 69043.58 | 59940 | 1 | 59940 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for extension of term, for a period of 90 days at the request of the company due to the covid 19 pandemic. | non-existent.
1092 | 6829179 | CP 14/2020_DEGA - AA and AR Network - Small Extensions 2020 | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2020 | 2021 | Portugal | Ovar | Aveiro | 1 | 30 | 04-08-2020 | 17-06-2021 | 317 | 730 | 245000 | 225663.69 | 1 | 225663.69 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1093 | 6825866 | Requalification and modernization of elementary school in Paredes de Viadores | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 30-07-2020 | 18-12-2020 | 141 | 60 | 65135.13 | 57447.35 | 1 | 57447.36 | -0.01 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the contract was performed in full.
1094 | 6825307 | Requalification of the Bernardino Coutinho pavilion - Marco de Canaveses | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 24-07-2020 | 26-02-2021 | 217 | 150 | 318955.5 | 286386.72 | 2 | 286386.72 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time
1095 | 6821557 | Maintenance Works on the Pedestrian Access Towers to the CP Station | 45442100-8 | Painting work | FALSE | 2020 | 2020 | Portugal | Santo Tirso | Porto | 13 | 14 | 16-07-2020 | 23-10-2020 | 99 | 60 | 15620 | 14972.5 | 1 | 19072.5 | -4100 | 78.5031 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the existence of complementary works. | execution of additional work to the initial contract.
1096 | 6821220 | Contract for refurbishment of the pavement and exterior facades - 2nd phase - of the building of the School of Architecture of the University of Minho, in Guimarães. (Cp/03/2019) | 45450000-6 | Other building completion work | FALSE | 2020 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 13-07-2020 | 10-12-2020 | 150 | 90 | 150000 | 133391.16 | 1 | 133391.16 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the time of completion of the contractual work, it was not in a position to be received
1097 | 6821213 | Water Conduct between S. Pedro-granja | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 15 | 20-07-2020 | 12-07-2021 | 357 | 120 | 49990 | 48490 | 1 | 41411.9 | 7078.1 | 117.0919 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate causes | works less in the amount of €7,078.10
1098 | 6821109 | Requalification of the Infantado Road Axis and cycle route - Loures | 45233222-1 | Paving and asphalting works | TRUE | 2020 | 2021 | Portugal | Loures | Lisboa | 11 | 26 | 08-05-2020 | 07-05-2021 | 364 | 305 | 715000 | 643500.01 | 2 | 643500.01 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A
1099 | 6820401 | Total Interior Refurbishment of Six Properties Located in Bragança, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Bragança | Bragança | 4 | 21 | 08-04-2020 | 31-12-2020 | 267 | 210 | 299000 | 210066.97 | 1 | 210066.97 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1100 | 6819558 | Public Tender No. 11/DRL/DA/2020 - Refurbishment of Lodgings in the General Command - Carmo Barracks | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 24 | 27-05-2020 | 03-11-2020 | 160 | 90 | 130000 | 112720.9 | 1 | 119463.17 | -6742.27 | 94.3562 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | technical justification presented was based, firstly, due to covid-19 and the lack of definition of some elements of the project. | complementary works were carried out, which caused the final value of the project to change.
1101 | 6818907 | Cpn 30/2020/dicp - t-19/2019 - requalification of the sidewalks on street ofs Fontaínhas - amor | 45232451-8 | Drainage and surface works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 21 | 09-07-2020 | 09-02-2021 | 215 | 180 | 365318.85 | 278962.78 | 2 | 278962.78 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1102 | 6818610 | Construction of roofs in the schools of Figueiras and Lustosa | 45223100-7 | Assembly of metal structures | FALSE | 2020 | 2020 | Portugal | Lousada | Porto | 13 | 18 | 21-07-2020 | 16-11-2020 | 118 | 120 | 157432.5 | 149951.73 | 1 | 149951.73 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | without changes
1103 | 6818077 | Contract for the execution of the urban arrangement of Largo da Grota - Roundabout | 45000000-7 | Construction work | TRUE | 2020 | 2021 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 27-07-2020 | 22-06-2021 | 330 | 270 | 243232.93 | 242325.52 | 1 | 242325.52 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Factor Weighting: 60% Criterion related to cost Name: Work execution quality factor Weighting: 40% | 1 | 40 | 2 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1104 | 6817598 | Repair of granite cube pavements in the various parishes of the county | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 17-07-2020 | 31-05-2021 | 318 | 90 | 35300 | 31600 | 1 | 31600 | 0 | 100 | Best value for money: No Criterion related to quality name: without Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | work suspension for 90 days.
1105 | 6815562 | streets in Argeriz | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-07-2020 | 10-12-2020 | 143 | 60 | 23108.65 | 20910 | 1 | 20910 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1106 | 6815555 | streets in Água Revé | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-07-2020 | 10-12-2020 | 143 | 60 | 17735.95 | 15988 | 1 | 15988 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1107 | 6815010 | Refurbishment of the School Pavilion EB 2,3 Júlio do Carvalhal | 45454000-4 | Restructuring work | FALSE | 2020 | 2021 | Portugal | Valpaços | Vila Real | 19 | 13 | 31-07-2020 | 23-07-2021 | 357 | 240 | 287106.57 | 276456.4 | 2 | 280170.97 | -3714.57 | 98.6742 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | safety and health safeguard conditions caused by the covid 19 pandemic and unfavorable weather conditions for carrying out the project | reuse of existing materials on site and regular price review
1108 | 6814813 | CP 81/2020 - Construction contract for the construction of a prefabricated physiotherapy pavilion at the Lagos Health Center | 45223800-4 | Assembly and erection of prefabricated structures | FALSE | 2020 | 2021 | Portugal | Lagos | Faro | 8 | 8 | 28-07-2020 | 18-06-2021 | 325 | 156 | 120000 | 104463.04 | 1 | 104463.04 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | extended execution period, following constraints arising due to the covid-19 pandemic, such as difficulties in mobilizing and accommodating employees, given the distance between the company's headquarters and the project site, or the impossibility of mobilizing larger teams size, in order to maintain distances between workers and avoid sharing tools, or even delays in the supply of materials and equipment.
1109 | 6812527 | Paving of Avenida de Ferreiros, 2nd Phase. | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 21-07-2020 | 21-09-2020 | 62 | 60 | 133615.11 | 88767.72 | 1 | 88767.72 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1110 | 6808753 | Exterior restoration of housing blocks 1, 2 and 3 - Bairro do Barreiro | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2019 | 2020 | Portugal | Carregal do Sal | Viseu | 20 | 15 | 05-06-2019 | 03-01-2020 | 212 | 60 | 56500 | 55659.08 | 1 | 55055.24 | 603.84 | 101.0968 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Quality Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the manufacturer of the sheets for the roof was closed during the month of may, only returning to work at the beginning of september. | underwork
1111 | 6807796 | Public tender for the award of the contract for "Enlargement of the Cemetery of Darque" | 45113000-2 | Siteworks | TRUE | 2020 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 17-07-2020 | 19-02-2021 | 217 | 180 | 334670.61 | 280799.5 | 2 | 274479.5 | 6320 | 102.3025 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to weather conditions and covid-19 measures. | underwork
1112 | 6804288 | The contract for “Paving streetAlbertino Veloso – Carregal do Sal” includes; Preparatory Works, Sidewalk Paving, Road Paving and Signaling all this, in accordance with the notebook | 45233252-0 | Surface work for streets | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 18-03-2019 | 01-07-2020 | 471 | 120 | 70000 | 59559.26 | 1 | 55421.89 | 4137.37 | 107.4652 | Best value for money: No Criterion related to quality Name: QUALITY Weighting: 0% Criterion related to cost Name: PRICE Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for carrying out the project has not changed | changes in the value of the project are due to the fact that some quantities estimated in the project were not fully executed, which led to a value of underwork, and with the value of the price revision, as shown in the final bill.
1113 | 6804148 | Expansion of the sewage network of Torre Cimeira and Torre Fundeira | 45232460-4 | Sanitary works | FALSE | 2020 | 2021 | Portugal | Gavião | Portalegre | 12 | 30 | 20-07-2020 | 26-02-2021 | 221 | 270 | 216430 | 189489.99 | 1 | 189489.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed faster than anticipated. | there were no changes to the value of the project
1114 | 6796528 | Installation of a rainwater network on R. Da Cruz, in Lavra | 45240000-1 | Construction work for water projects | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 14-07-2020 | 15-02-2021 | 216 | 60 | 115000 | 81637.5 | 1 | 81637.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1115 | 6796263 | EP-2020(5001)/10006 Requalification of the Preschool Canteen - CED NSC | 45262700-8 | Building alteration work | TRUE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 24-07-2020 | 30-12-2020 | 159 | 90 | 65000 | 53175.33 | 1 | 53175.33 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | impossibility of carrying out the project on weekdays with the existence of children in the spaces to be intervened due to covid-19 | no change
1116 | 6796011 | Construction of the water supply network at street ofs Ribeiras and the wastewater drainage networks at street of Ribeiras and streetde S. Pedro in Lobão" | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 22-07-2020 | 14-01-2021 | 176 | 120 | 64517.17 | 43181.52 | 1 | 42823.01 | 358.51 | 100.8372 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | small lead time | underwork
1117 | 6794543 | Contract for "Beira Baixa Line - Contract for Anticorrosive Protection of Metallic Bridges Phase 2" DESCO n.º 10002590 | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2020 | 2021 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 15 | 24-07-2020 | 09-09-2021 | 412 | 180 | 850000 | 844963.4 | 2 | 844963.4 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1118 | 6794161 | Execution of sidewalk, fence wall and tank - street of Cerejeira, n.º 106 - Fiães | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 22-07-2020 | 14-06-2021 | 327 | 60 | 42810 | 42706.65 | 1 | 42706.65 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 137 days due to the need to combine and adapt the project to the residents of the house
1119 | 6793222 | Monster Collection Park (Abiúl, Albergaria dos dois, Redinha, Santiago de Litém and Vermoil) - Proc. No. 61/2019 | 45222110-3 | Waste disposal site construction work | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 45 | 02-03-2020 | 29-10-2021 | 606 | 90 | 137250.2 | 131426 | 1 | 138584.02 | -7158.02 | 94.8349 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | existence of complementary work | existence of complementary work
1120 | 6792917 | Rehabilitation works on the roof and facades of the Casa do Roseiral building | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 20 | 20-07-2020 | 17-12-2020 | 150 | 90 | 92500 | 73766.35 | 1 | 73766.35 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 21 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractually stipulated
1121 | 6792463 | Tomar branch - Replacement of wooden sleepers with biblock concrete sleepers and transition from BC to BLS - Pk 0.000/1.933 - Phase 3 | 45234100-7 | Railway construction works | FALSE | 2020 | 2021 | Portugal | Tomar | Santarém | 16 | 30 | 08-07-2020 | 25-05-2021 | 321 | 90 | 860000 | 763187.94 | 2 | 730638.27 | 32549.67 | 104.455 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A
1122 | 6790385 | streets in Valpaços - crossstreet ofPinheiro Manso | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 17-07-2020 | 28-10-2020 | 103 | 30 | 9433.56 | 9290.85 | 1 | 9290.85 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1123 | 6788582 | Rehabilitation contract for the public space surrounding the castle of Alenquer and Porta da Conceição | 45112700-2 | Landscaping work | FALSE | 2020 | 2021 | Portugal | Alenquer | Lisboa | 11 | 21 | 21-07-2020 | 31-08-2021 | 406 | 90 | 186357.96 | 184959.45 | 1 | 190709.5 | -5750.05 | 96.9849 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions due to complementary work/financial rebalancing/climate changes/material supply/changes to the excavation method. suspension due to covid-19 | unforeseen/unpredicted complementary work
1124 | 6783189 | Execution of rainwater and wastewater drainage infrastructure in Tabuado and Marco. | 45232411-6 | Foul-water piping construction work | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 20-07-2020 | 27-04-2021 | 281 | 150 | 367940.74 | 348361.5 | 2 | 312839.44 | 35522.06 | 111.3547 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of term | underwork and final price revision
1125 | 6781980 | CP 23-2020 - Renovation of heating, ventilation and air conditioning (HVAC) systems in Services buildings, D.G.H., D.S.A. E LEMES, exterior Led retrofit, of the headquarters of the National Institute of Health | 45454000-4 | Restructuring work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 14 | 10-07-2020 | 14-03-2021 | 247 | 120 | 616129.39 | 614826.43 | 2 | 645083.26 | -30256.83 | 95.3096 | Best value for money: Yes Criterion related to quality Name: Warranty, Energy Efficiency and Lead Time Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | during the execution of the projects, a high state of degradation was found in the closed water distribution network for air conditioning in the dsa building, especially high levels of corrosion in the ferrous piping. the replacement of the deteriorated distribution network is essential for the correct operation of the entire network, under penalty of inconsiderate damage to the new equipment that is intended to be connected to the network.
1126 | 6781516 | Improvement and Conservation of Other elementary Education Buildings - CE dos Vieirinhos - Proc. No. 29/2020 | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 18 | 15-07-2020 | 28-10-2021 | 470 | 60 | 96567.5 | 91587.4 | 1 | 83543.12 | 8044.28 | 109.6289 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivering the waste management plan. | existence of underworks.
1127 | 6781376 | Improvement and Conservation of other elementary Education Buildings (EC of Albergaria dos Doze) - Proc. No. 26/2020 | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 18 | 15-07-2020 | 28-10-2021 | 470 | 60 | 96123 | 88479.5 | 1 | 78805.5 | 9674 | 112.2758 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivering the waste plan. | existence of underworks.
1128 | 6781158 | Contract for Public Works for the Maintenance and Occasional Repairs of Sidewalks and Paves in the Municipality of Cascais | 45233253-7 | Surface work for footpaths | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 15 | 17-07-2020 | 14-04-2021 | 271 | 730 | 340000 | 248038.41 | 1 | 248038.41 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Performance (20%) and Responsiveness (20%) Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the work finished ahead of schedule
1129 | 6779873 | Refurbishment of the Occupational Activity Centers in Oliveira de Frades. | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Oliveira de Frades | Viseu | 20 | 10 | 03-07-2020 | 13-05-2021 | 314 | 180 | 180000 | 171106.95 | 1 | 171106.95 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | due to the current pandemic situation in the country (covid-19)
1130 | 6776877 | Requalification of the road network in the parishes of Angústias and Conceição | 45233220-7 | Surface work for roads | FALSE | 2020 | 2020 | Portugal | Horta | Região Autónoma dos Açores | 15 | 15 | 29-05-2020 | 22-12-2020 | 207 | 120 | 300217.87 | 289927.13 | 2 | 289927.13 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project
1131 | 6774937 | C. Public No. 34/ Social services of the National Guard/2020 | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Coimbra | Coimbra | 6 | 21 | 29-06-2020 | 31-12-2020 | 185 | 60 | 73000 | 40972.43 | 1 | 40972.43 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price/Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1132 | 6774907 | C. Public No. 36/ Social services of the National Guard/2020 | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Olhão | Faro | 8 | 21 | 22-06-2020 | 31-12-2020 | 192 | 50 | 46000 | 38993 | 1 | 38993 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price/Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1133 | 6774832 | Kitchen refurbishment at the Costa de Caparica Summer Camp, owned by the Social services of the National Guard | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2020 | Portugal | Almada | Setúbal | 17 | 15 | 10-07-2020 | 31-12-2020 | 174 | 150 | 230000 | 209270 | 1 | 209270 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1134 | 6774168 | Coverage Change for Sendim Kindergarten | 45261213-0 | Metal roof-covering work | FALSE | 2020 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 15 | 26-05-2020 | 12-08-2021 | 443 | 90 | 32298.75 | 30417 | 1 | 28969.4 | 1447.6 | 104.997 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate reasons | there was underwork to the value of €1,447.60
1135 | 6769148 | Maintenance of the Ribeira da Venda sports center - Argoncilhe | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-07-2020 | 30-09-2020 | 79 | 30 | 23063 | 17735 | 1 | 17710 | 25 | 100.1412 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed ahead of schedule | underwork
1136 | 6768855 | Contract 95/GEBALIS/2020 - Public Tender for Repair of Elevators in the Neighborhoods Vale de Alcântara (Ceuta Norte) and Casalinho da Ajuda - South Zone of Lisbon at the addresses: - Av. North Ceuta, lots 6 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 09-07-2020 | 29-10-2020 | 112 | 60 | 87000 | 73358.84 | 1 | 73358.84 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
1137 | 6766390 | Construction of the connection between street ng.º Adelino Amaro da Costa and streetD. Pedro v - mafamude | 45233140-2 | Roadworks | TRUE | 2020 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 45 | 06-07-2020 | 07-06-2021 | 336 | 150 | 230000 | 214680.25 | 1 | 214680.25 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed in less time than originally planned.
1138 | 6765423 | Its object is the execution of demolitions of existing illegal constructions in the Municipality of Amadora. | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 14 | 03-07-2020 | 09-07-2021 | 371 | 365 | 235609.56 | 213028.9 | 1 | 213028.9 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the contract ended ahead of schedule due to the fact that the contractor, on his own initiative, increased the projectforce, which resulted in the completion of the contract
1139 | 6764642 | Public tender for the execution of the contract for the remodeling of the metallic guard of the pontoon at Praia dos Pescadores. | 45220000-5 | Engineering works and construction works | FALSE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 07-07-2020 | 10-03-2021 | 246 | 30 | 18223 | 15999.6 | 1 | 15999.6 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1140 | 6763054 | EP-2020(5001)/10003 Improvement of the João Inácio Ferreira Lapa Shelter House | 45113000-2 | Siteworks | TRUE | 2020 | 2020 | Portugal | Sintra | Lisboa | 11 | 5 | 08-07-2020 | 30-12-2020 | 175 | 90 | 165000 | 144297.33 | 1 | 144297.33 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | no change | there was no change
1141 | 6762028 | EP-2020(5001)/10007 Improvement of the ballroom and creation of a new sanitary installation | 45262700-8 | Building alteration work | TRUE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 01-07-2020 | 30-12-2020 | 182 | 90 | 120000 | 106305.2 | 1 | 106305.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1142 | 6761671 | 2017.507.01.C1 - Lousã Employment Service - requalification of the service area and remodeling of electrical installations and ITED | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2020 | Portugal | Lousã | Coimbra | 6 | 15 | 07-05-2020 | 18-12-2020 | 225 | 60 | 100000 | 96100 | 1 | 99881.37 | -3781.37 | 96.2141 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | additional contract
1143 | 6760002 | Contract nº 62/19 - Playgrounds - Execution of Construction / Recovery Works | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 47 | 25-06-2020 | 24-06-2021 | 364 | 180 | 428025 | 372239.9 | 2 | 372239.9 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | with the completion of the project, the "plan for the prevention and management of construction and demolition waste" was requested from the successful tenderer, which was delayed in delivery.
1144 | 6757884 | 100% Quality - Paving in granite cube sidewalk, in Perafita | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 29-06-2020 | 15-02-2021 | 231 | 90 | 495000 | 338800 | 2 | 338800 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1145 | 6747407 | Contract for requalification works on the Caminho do Porsim - earthworks, drainage and execution of the base of the pavement. | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 30-06-2020 | 05-05-2021 | 309 | 120 | 200000 | 120194.6 | 1 | 127256.95 | -7062.35 | 94.4503 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal / Period of execution Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a suspension order on july 20, 2020.
1146 | 6741518 | Improvement of the Energy Efficiency of the Museum of Contemporary Art of Elvas (MACE). | 45421112-2 | Installation of window frames | FALSE | 2020 | 2021 | Portugal | Elvas | Portalegre | 12 | 21 | 03-07-2020 | 04-01-2021 | 185 | 90 | 100000 | 99385 | 1 | 99385 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a delay on the part of suppliers in relation to the pandemic situation in which the country finds itself.
1147 | 6741467 | Contract for Public Works to Execution of Paintings in Various Locations in the Municipality of Cascais | 45442180-2 | Repainting work | FALSE | 2020 | 2021 | Portugal | Cascais | Lisboa | 11 | 15 | 01-07-2020 | 06-01-2021 | 189 | 184 | 80000 | 60015.22 | 1 | 60015.22 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect subject to competition Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1148 | 6736313 | Public works contract for Installation of HVAC, Lighting, application of external thermal insulation and Installation of photovoltaic panels, HEADQUARTERS building | 45311200-2 | Electrical fitting work | TRUE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 4 | 16-06-2020 | 13-08-2020 | 58 | 35 | 206000 | 16443.39 | 1 | 17016.86 | -573.47 | 96.63 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | completion of the project before the time stipulated in the contract. | caused by overwork and underwork
1149 | 6736281 | Public works contract for Installation of HVAC, Lighting, application of external thermal insulation and Installation of photovoltaic panels, HEADQUARTERS building | 45331000-6 | Heating, ventilation and air-conditioning installation work | TRUE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 4 | 12-06-2020 | 07-09-2020 | 87 | 75 | 206000 | 57663.58 | 1 | 61822.22 | -4158.64 | 93.2732 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | completion of the project prior to the execution period. | extra work
1150 | 6734704 | Quality 100% - Bituminous paving at the UF of São Mamede de Infesta and Senhora da Hora | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 3 | 01-07-2020 | 14-12-2021 | 531 | 90 | 497000 | 359419.55 | 2 | 395361.01 | -35941.46 | 90.9092 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | extra work
1151 | 6732917 | Control and reduction of losses in water distribution and supply systems in the municipality of penafiel - renovation of the water distribution network in the parish of rio mau | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Penafiel | Porto | 13 | 20 | 05-06-2020 | 22-09-2021 | 474 | 360 | 218037.08 | 197077.27 | 1 | 197077.27 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension.
1152 | 6732656 | Public Tender No. 15-2019 UALG - Execution contract for the Clinical Simulation Center on the Gambelas Campus | 45300000-0 | Building installation work | FALSE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 43 | 03-03-2020 | 29-04-2021 | 422 | 180 | 641522.61 | 574087.16 | 2 | 611087.97 | -37000.81 | 93.9451 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | errors and omissions supplies | errors and omissions supplies
1153 | 6730808 | Quality 100% - conservation of road markings in the municipality of matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 15 | 23-06-2020 | 29-12-2021 | 554 | 365 | 230000 | 104601.77 | 1 | 104601.77 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1154 | 6730715 | Quality 100% - conservation of road markings in the municipality of matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 15 | 29-06-2020 | 29-12-2021 | 548 | 365 | 230000 | 93645.03 | 1 | 93645.03 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1155 | 6725513 | Its purpose is the global requalification of the facilities of elementary school Ricardo Alberty | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Amadora | Lisboa | 11 | 13 | 17-06-2020 | 27-05-2021 | 344 | 441 | 538497.93 | 484648.19 | 2 | 484648.19 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out in a shorter period than expected, due to the anomalous situation in which it was developed (covid pandemic), which allowed, due to a lack of students in some periods, that some of the projects took place in the normal school period and not in vacation periods as initially scheduled.
1156 | 6725222 | Cp/03/dom/2020 - "replacement of fiber cement roofing - 3rd phase" | 45210000-2 | Building construction work | FALSE | 2020 | 2020 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 24-04-2020 | 01-09-2020 | 130 | 60 | 130000 | 108604.6 | 1 | 108604.6 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | for project analysis
1157 | 6724795 | Extension of the Home for the Elderly | 45262800-9 | Building extension work | FALSE | 2020 | 2021 | Portugal | Baião | Porto | 13 | 14 | 15-06-2020 | 22-04-2021 | 311 | 180 | 168385.86 | 168378.03 | 1 | 168378.03 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A
1158 | 6721134 | Contract 182/GEBALIS/2020 - Contract for the Maintenance and Conservation of buildingss and common areas of municipal housing heritage in Neighborhoods of the North East Zone | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 26-06-2020 | 02-12-2021 | 524 | 730 | 600000 | 456657.88 | 2 | 456657.88 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
1159 | 6719959 | Its object is the rehabilitation of the facilities, namely the execution of all the works mentioned in the drawings, in the written documents of the projects and in the specifications. | 45453100-8 | Refurbishment work | FALSE | 2020 | 2020 | Portugal | Amadora | Lisboa | 11 | 21 | 16-06-2020 | 04-11-2020 | 141 | 77 | 254713.13 | 229241.83 | 1 | 229241.83 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1160 | 6719817 | Requalification of the Road Network in the Parish of Sanguinheira and streetJoão de Ruão in Cantanhede, by Contract - CP-CCP-EMP n.º 09/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 26-06-2020 | 22-12-2021 | 544 | 240 | 246381.2 | 139581.22 | 1 | 118337.31 | 21243.91 | 117.952 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underworks.
1161 | 6718449 | Cpn 21/2020/dicp - t-02/2020 - placement of metal road protection guards in various locations in the municipality of leiria | 45233292-2 | Installation of safety equipment | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 01-06-2020 | 12-01-2021 | 225 | 180 | 168800 | 118997 | 1 | 118997 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1162 | 6715712 | 2015.170.01.C1 - SFP Faro - exterior rehabilitation of facilities and HVAC - 2nd phase - Blocks 1, 3, 4, 8, 9, 10, 11 and warehouse | 45331200-8 | Ventilation and air-conditioning installation work | FALSE | 2015 | 2021 | Portugal | Faro | Faro | 8 | 22 | 24-11-2015 | 30-04-2021 | 1984 | 150 | 1028596 | 898390.34 | 2 | 1020027.83 | -121637.49 | 88.0751 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | Additional works | Additional works and price review
1163 | 6713948 | Pipeline between the one-armed catchment and the boulder reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Mogadouro | Bragança | 4 | 30 | 05-06-2020 | 15-04-2021 | 314 | 90 | 87051.69 | 84041.25 | 1 | 84041.25 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | risk of fire and delays in the supply of materials | no change
1164 | 6713838 | Contract "Repaving of the Road Network of Quinta dos Fidalguinhos - South" | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2020 | Portugal | Barreiro | Setúbal | 17 | 20 | 03-06-2020 | 19-10-2020 | 138 | 45 | 295000 | 244040 | 1 | 227564.61 | 16475.39 | 107.2399 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary work and underwork
1165 | 6713674 | 2017.054.04.C1 - SFP Coimbra - Installation of the gas and plumbing and electricity and ITED sections | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2019 | 2021 | Portugal | Coimbra | Coimbra | 6 | 7 | 30-09-2019 | 12-03-2021 | 529 | 245 | 600000 | 584797.24 | 2 | 585112.9 | -315.66 | 99.9461 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | no data | underwork and price revision
1166 | 6709031 | Energy efficiency in public lighting in the municipality of baião - 2nd phase | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2019 | 2021 | Portugal | Baião | Porto | 13 | 30 | 27-01-2020 | 14-10-2021 | 626 | 190 | 1211121 | 1144463.14 | 3 | 1144463.14 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there are no changes to the time for completion of the project. | there were no changes to the value of the project
1167 | 6704268 | Requalification of the Road Network in the Parish of Tocha and Sanguinheira, by Contract - 1st Phase: Connection Tocha / Sanguinheira - CP-CCP-EMP n.º 08/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 22-06-2020 | 25-11-2021 | 521 | 240 | 349215.25 | 195690 | 1 | 194557.2 | 1132.8 | 100.5822 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underworks.
1168 | 6703988 | Requalification of the Road Network in the Union of the Parishes of Vilamar and Corticeiro de Cima, by Contract - 1st Phase - CP-CCP-EMP n.º 07/2020 | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 22-06-2020 | 26-02-2021 | 249 | 120 | 250093.5 | 213037.61 | 1 | 143137.29 | 69900.32 | 148.8345 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
1169 | 6701912 | Requalification of public space, essentially with regard to pedestrian mobility and modernization of water distribution and domestic and rainwater drainage infrastructure | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Coimbra | Coimbra | 6 | 33 | 13-02-2020 | 10-12-2021 | 666 | 180 | 528365 | 526300 | 2 | 675300.64 | -149000.64 | 77.9357 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension associated with complementary work | value related to price review
1170 | 6701729 | Contract to Improve Accessibility (recovery of accessibility on the Caminho do Linhõ-Vreia de Bornes | 45233222-1 | Paving and asphalting works | FALSE | 2020 | 2020 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 05-06-2020 | 30-12-2020 | 208 | 210 | 188679 | 180960.26 | 1 | 180960.26 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | with more staff working.
1171 | 6698981 | Requalification of the road network in the parishes of Ribeirinha, Cedros, Capelo and Feteira | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Horta | Região Autónoma dos Açores | 15 | 15 | 20-05-2020 | 07-12-2020 | 201 | 150 | 338645.49 | 331000.16 | 2 | 331000.16 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project
1172 | 6698000 | Contract for "Earthworks in Campo Queimado-Outeiro Seco" | 45112000-5 | Excavating and earthmoving work | FALSE | 2020 | 2021 | Portugal | Chaves | Vila Real | 19 | 24 | 08-06-2020 | 15-11-2021 | 525 | 180 | 391373.72 | 335302.68 | 2 | 335302.68 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the provisional acceptance notice has only now been drawn up.
1173 | 6697746 | Adaptation of Diffusers and Renewal of Cathodic Protection in the Espinho and S. Jacinto Submarine Outfalls. | 45232440-8 | Construction work for sewage pipes | FALSE | 2018 | 2021 | Portugal | Aveiro | Aveiro | 1 | 41 | 09-06-2020 | 22-11-2021 | 531 | 180 | 1500000 | 1039998.1 | 3 | 1372280.5 | -332282.4 | 75.7861 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: A - Price - 60% B - Technical Value - 40% | 1 | 60 | N/A | TRUE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | more work and coincidence of part of the project carried out with the winter months, during which it is only sporadically possible to work at sea | worsening of corrosion of the metal parts to be protected, between the date of the underwater inspection on which the execution project was based (april and june 2016) and the date of the start of the contract
1174 | 6694281 | Contract for "Minho Line - Rehabilitation of the Barroselas Station Line II Track Platform" (Process No. 10002931) | 45234100-7 | Railway construction works | FALSE | 2020 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 14 | 18-06-2020 | 19-08-2021 | 427 | 60 | 385000 | 338571.37 | 2 | 349981.54 | -11410.17 | 96.7398 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | need to carry out additional work
1175 | 6693069 | Cp 03/2020 - repair of defects in the work within the scope of the contract for water and sanitation networks - guimarães - southeast front - 2nd phase | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 26-05-2020 | 29-01-2021 | 248 | 60 | 188705 | 178776 | 1 | 178776 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension
1176 | 6693002 | CP 08/2020_DEGA - Water supply to Cadaveira . 1st phase - Águeda | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2020 | Portugal | Águeda | Aveiro | 1 | N/A | 27-04-2020 | 24-08-2020 | 119 | 90 | 130000 | 103701.97 | 1 | 73093.37 | 30608.6 | 141.876 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 3 | FALSE | N/A | N/A | N/A | N/A | FALSE | nothing to report | nothing to report
1177 | 6692385 | Requalification of Barroco, Alegria and Maia streets in the Union of Parishes of Verim, Friande and Ajuda | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 17-06-2020 | 15-10-2020 | 120 | 120 | 179884.76 | 174990.58 | 1 | 174990.58 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1178 | 6688255 | Requalification of the Municipal Garden | 45212100-7 | Construction work of leisure facilities | FALSE | 2020 | 2021 | Portugal | Boticas | Vila Real | 19 | 18 | 25-05-2020 | 16-06-2021 | 387 | 150 | 149579.97 | 136300 | 1 | 136300 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1179 | 6687851 | Requalification of the 1st Section of Avenida da Liberdade | 45000000-7, 45233251-3 | Construction work, Resurfacing works | FALSE | 2019 | 2021 | Portugal | São Brás de Alportel | Faro | 8 | 15 | 07-01-2020 | 29-03-2021 | 447 | 120 | 280000 | 257603.94 | 2 | 284912.58 | -27308.64 | 90.4151 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1180 | 6684863 | Supply and Installation of Photovoltaic Generator System | 45261215-4 | Solar panel roof-covering work | FALSE | 2019 | 2020 | Portugal | Aveiro | Aveiro | 1 | 27 | 07-02-2020 | 21-12-2020 | 318 | 120 | 245000 | 143498.31 | 1 | 143543.31 | -45 | 99.9687 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Total Proposal Value Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract registered some constraints/constraints due to the pandemic/covid. | the contractual value differs from the value of contractual works insofar as the contractual value has an error in the sum of all items in the quantities map.
1181 | 6682473 | elementary Education Establishments - Conservation and Repair of Favaios School | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Alijó | Vila Real | 19 | 30 | 15-06-2020 | 01-03-2021 | 259 | 248 | 144568.8 | 136053.19 | 1 | 136053.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1182 | 6680523 | 100% Quality - Pavement repair on R. Aldeia de Baixo, Santa Cruz do Bispo | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 15-06-2020 | 16-11-2021 | 519 | 45 | 32500 | 22210.75 | 1 | 22210.75 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Valia Técnica Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1183 | 6675272 | Road/pedestrian upgrading of Euroceramic street | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2021 | Portugal | Setúbal | Setúbal | 17 | 30 | 08-06-2020 | 02-02-2021 | 239 | 90 | 66827.68 | 58476.76 | 1 | 58476.76 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: evaluation of the price or cost as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1184 | 6674475 | Requalification of Public Lighting in the municipality of Alijó - replacement of existing luminaires with LED's. | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2020 | 2021 | Portugal | Alijó | Vila Real | 19 | 15 | 08-06-2020 | 19-03-2021 | 284 | 245 | 692010 | 489600 | 2 | 489600 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | due to prior approval by the court of auditors
1185 | 6672652 | Construction of Pier No. 4 at the Fishing Port of Sesimbra | 45241100-9 | Quay construction work | FALSE | 2019 | 2021 | Portugal | Sesimbra | Setúbal | 17 | 16 | 05-03-2020 | 17-06-2021 | 469 | 239 | 3000000 | 2788330 | 3 | 2891680.46 | -103350.46 | 96.4259 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | constraints in the delivery and operationality of floating formwork, in the selection of suppliers of ready-fixed concrete due to the specificity of “submersible” concrete and in the supply and assembly of fenders and mooring headers | placement of a superior quantity of riffilling
1186 | 6670254 | Urbanizations in the Municipality - Balteiro | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 15 | 20-05-2020 | 04-05-2021 | 349 | 210 | 245047.8 | 220095.03 | 1 | 167127.02 | 52968.01 | 131.6933 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful deadline extension - 30 days. suspension (by the developer) under the provisions of article 369 of the "public procurement code"- 90 days. legal extension of the period under the provisions of article 471(2)(d) of the "public procurement code" - 2 days. | underwork.
1187 | 6667696 | Cpn 15/2020/dicp - t-72/2019 - improvement of existing equipment in the surroundings of the lake of ervedeira - parish of coimbrão | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 29-04-2020 | 18-01-2021 | 264 | 60 | 60553 | 47070.02 | 1 | 48656.75 | -1586.73 | 96.7389 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works pursuant to the provisions of art. 374th "public procurement code" | complementary works pursuant to the provisions of art. 370.º of the "public procurement code" and underwork under the terms of the provisions of art. 379.º, nº 2 of the "public procurement code"
1188 | 6666274 | Construction of Wastewater Collector Sections for Physical Access to the Public Sanitation Network | 45232460-4 | Sanitary works | FALSE | 2020 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 14 | 25-05-2020 | 13-12-2021 | 567 | 365 | 200000 | 200000 | 1 | 211232.44 | -11232.44 | 94.6824 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 0% Criterion related to cost Name: The award criterion is the most economically advantageous tender (see point 21 Programa Proc) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract ended on the scheduled date, however due to the unavailability of the intervening parties, the inspection can only be carried out on the mentioned date. | there was underwork worth €3,413.19 and additional work worth €14,645.63.
1189 | 6664433 | Adduction System Between the "Paço-Gasparões" Hole and the Gasparões Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2020 | Portugal | Ferreira do Alentejo | Beja | 2 | N/A | 07-05-2020 | 02-11-2020 | 179 | 60 | 95000 | 86563.57 | 1 | 74393.57 | 12170 | 116.3589 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 6 | FALSE | N/A | N/A | N/A | N/A | FALSE | the project was carried out within the normal time frame. due to the collection rules due to covid-19, there was some delay in the date of provisional reception. | underwork worth €12,170.00
1190 | 6664351 | E.CP_144_Reformulation of sidewalks and green areas | 45112700-2 | Landscaping work | FALSE | 2020 | 2021 | Portugal | Figueira da Foz | Coimbra | 6 | 14 | 03-06-2020 | 24-02-2021 | 266 | 90 | 83659.88 | 80099.99 | 1 | 76378.13 | 3721.86 | 104.8729 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the covid19 pandemic | due to underwork
1191 | 6661076 | Minho Line - Rehabilitation of Track Superstructure between km 5,050 and 7,750 DV | 50225000-8 | Railway-track maintenance services | FALSE | 2020 | 2021 | Portugal | Maia | Porto | 13 | 8 | 03-06-2020 | 15-10-2021 | 499 | 150 | 950000 | 892760.32 | 2 | 892760.32 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
1192 | 6661010 | Cpn 22/2020/dicp - t-15/2020 - rehabilitation of streetvale são joão in the locality of canals, parish of caranguejeira - leiria | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 12-05-2020 | 11-05-2021 | 364 | 120 | 281753.5 | 234999 | 1 | 234999 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1193 | 6660886 | Requalification of the public space adjacent to Avenida Dr. Lúcio Vidal - 2nd phase | 45112700-2 | Landscaping work | FALSE | 2020 | 2021 | Portugal | Vagos | Aveiro | 1 | 15 | 05-06-2020 | 02-03-2021 | 270 | 90 | 165000 | 159746.9 | 1 | 159431.24 | 315.66 | 100.198 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2 extensions (60 days and 30 days). end of the project period after extensions: 01/02/2021, with the contract effectively ending on 12/30/2020. provisional receipt signed only on 02/02/2021 | underwork worth 315.66 euros
1194 | 6659549 | Cpn 20/2020/dicp - t-13/2020 - requalification and improvement of the east car park of maceira market - maceira | 45232451-8 | Drainage and surface works | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 04-05-2020 | 04-01-2021 | 245 | 90 | 189318.9 | 149998 | 1 | 149998 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1195 | 6656613 | Execution of a contract for the structuring and reformulation of Datacenter data cabling, in order to comply with TIER2 certification standards or higher | 45259000-7 | Repair and maintenance of plant | TRUE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 1 | 28-11-2019 | 12-10-2020 | 319 | 150 | 350000 | 175000 | 1 | 175000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | there was a suspension in the contract pursuant to article 298 of the "public procurement code", and the project was assigned on 02/11/2020
1196 | 6653816 | Work to improve the odemira gymnastics pavilion | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2019 | 2021 | Portugal | Odemira | Beja | 2 | 24 | 28-04-2020 | 02-07-2021 | 430 | 90 | 225158.92 | 195043.03 | 1 | 195043.03 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the start of the projects only started after the date of communication to the contractor of the approval of the health and safety plan, which was on 7/20/2020 (as per acknowledgment of receipt).
1197 | 6651157 | L. Norte - Santarém Valley - Improvement of the Neutral Zone Catenary Post | 45234160-5 | Catenary's construction works | FALSE | 2020 | 2021 | Portugal | Santarém | Santarém | 16 | 2 | 02-06-2020 | 20-10-2021 | 505 | 180 | 406000 | 344536.08 | 2 | 353280.06 | -8743.98 | 97.5249 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the justification is due to the delay in the supply of core materials for the execution of the contract (coelme switches) from italy, a region seriously affected by the 1st wave of covid, this in the 3rd and 4th quarter of 2020, therefore an extension was necessary. | ordinary price review
1198 | 6650562 | Maintenance and conservation works of the Urban Ecological Park of Viana do Castelo | 45453100-8 | Refurbishment work | FALSE | 2020 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 01-06-2020 | 18-12-2020 | 200 | 60 | 274126 | 243442.5 | 1 | 243442.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | rupture of raw material due to covid-19 measures and unforeseen pathologies in the wooden structures of the bridges.
1199 | 6650314 | Requalification of the access road to the Industrial Park of the União de Freguesias de Campo e Louredo | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 26-05-2020 | 28-01-2021 | 247 | 90 | 107171.79 | 95994.77 | 1 | 123755.57 | -27760.8 | 77.568 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension and extra work. | additional work
1200 | 6647271 | "streets in loulé - maintenance of pavements in largo manuel arriaga" | 45233142-6 | Road-repair works | FALSE | 2020 | 2021 | Portugal | Loulé | Faro | 8 | 14 | 28-05-2020 | 08-03-2021 | 284 | 120 | 95000 | 68368 | 1 | 68368 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1201 | 6635363 | Block 2 Roof Replacement Contract | 45261210-9 | Roof-covering work | FALSE | 2020 | 2020 | Portugal | Aveiro | Aveiro | 1 | 21 | 08-04-2020 | 17-12-2020 | 253 | 60 | 79000 | 78890 | 1 | 78890 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Total Proposal Value Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract registered some constraints / constraints due to the pandemic / covid
1202 | 6635092 | Repaving of Salgado Zenha Avenue - Stº António dos Cavaleiros | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2020 | Portugal | Loures | Lisboa | 11 | 21 | 20-03-2020 | 29-07-2020 | 131 | 30 | 200000 | 130707 | 1 | 130707 | 0 | 100 | Best value for money: No Criterion related to quality Name: Unweighted Weighting: 0% Criterion related to cost Name: Point 18 of the Contest Program Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change in the execution period
1203 | 6633945 | Public tender for the execution of a contract to replace public lighting columns on Av. Of the Discoveries, Albufeira | 45316000-5 | Installation work of illumination and signalling systems | TRUE | 2020 | 2021 | Portugal | Albufeira | Faro | 8 | 15 | 22-05-2020 | 23-04-2021 | 336 | 90 | 232000 | 196277.53 | 1 | 196277.53 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Drawing Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | as it coincides with the increase in traffic on the road due to the start of the bathing season and the impossibility of carrying out the projects, due to the decorative lighting of the christmas festive season.
1204 | 6632545 | Improvement and Requalification of Municipal Housing Buildings in S. Martinho do Campo | 45259000-7 | Repair and maintenance of plant | FALSE | 2020 | 2021 | Portugal | Santo Tirso | Porto | 13 | 22 | 19-05-2020 | 10-03-2021 | 295 | 210 | 454335.4 | 395087.38 | 2 | 414624.34 | -19536.96 | 95.288 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the existence of complementary works. | the existence of complementary works necessary for the good finishing of the project.
1205 | 6631100 | Cpn 27/dicp/2020 - rehabilitation of sanitary facilities in pedrógão - parish of coimbrão | 45215000-7 | Construction work for buildings relating to health and social services, for crematoriums and public conveniences | FALSE | 2020 | 2021 | Portugal | Leiria | Leiria | 10 | 15 | 14-05-2020 | 25-05-2021 | 376 | 60 | 60368.95 | 59733.07 | 1 | 58827.57 | 905.5 | 101.5392 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork (art.º 379.º n.º 2)
1206 | 6627490 | 2019.534.02.C1 - SFP Lisbon - Electrical and telecommunications infrastructure | 45310000-3 | Electrical installation work | TRUE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 31-03-2020 | 03-09-2020 | 156 | 90 | 70000 | 53800 | 1 | 53578 | 222 | 100.4143 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional work | job suppression
1207 | 6621015 | Cpn 17/2020/dicp - t-08/2020 - requalification of berms and ditches on cm 1218 in the parish of caranguejeira and union of the parishes of colmeias and Memória, municipality of leiria | 45232451-8 | Drainage and surface works | FALSE | 2020 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 30-04-2020 | 26-10-2020 | 179 | 120 | 291494 | 246681.25 | 1 | 246681.25 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1208 | 6617860 | Parish of Louriçal / Street layout and Improvements on roads and paths in the Parish (Passeios on E.N. 237 - Matas do Louriçal) - Proc. No. 13/2020 | 45233253-7 | Surface work for footpaths | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 21-05-2020 | 12-11-2021 | 540 | 150 | 155126 | 149390.51 | 1 | 149390.51 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed before the deadline.
1209 | 6616843 | PO 328/2020 - Rehabilitation of Urban Spaces - streetPadre Manuel Himalaya | 45233252-0 | Surface work for streets | FALSE | 2020 | 2021 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 15 | 19-05-2020 | 15-12-2021 | 575 | 210 | 310000 | 295371.1 | 2 | 283172.68 | 12198.42 | 104.3078 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1210 | 6605460 | Contract for Requalification of the Sea Front - Fajã das Almas | 45233161-5 | Footpath construction work | FALSE | 2020 | 2021 | Portugal | Velas | Região Autónoma dos Açores | 15 | 14 | 22-05-2020 | 23-07-2021 | 427 | 180 | 206940.11 | 203792.44 | 1 | 221152.44 | -17360 | 92.1502 | Best value for money: Yes Criterion related to quality Name: deadline of execution of the contract Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the changes in the execution time of the project are due to the lack of materials due to the covid 19 pandemic situation and lack of labour.
1211 | 6605380 | Construction work for the Third Opening Phase of the Caminho da Fajã de João Dias | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2020 | 2021 | Portugal | Velas | Região Autónoma dos Açores | 15 | 14 | 22-05-2020 | 26-08-2021 | 461 | 180 | 271934.27 | 270875.65 | 2 | 270875.65 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Contract Execution Deadline Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 2 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the causes of the changes in deadlines were due to adverse weather conditions.
1212 | 6605234 | 100% Quality - Paving on street5 de Outubro, São Mamede de Infesta | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 20-05-2020 | 09-03-2021 | 293 | 90 | 385000 | 247176.5 | 1 | 326051.27 | -78874.77 | 75.8091 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work | complementary works
1213 | 6605130 | Execution of the contract "Kitchen and Laundry Construction" | 45210000-2 | Building construction work | FALSE | 2020 | 2021 | Portugal | Ílhavo | Aveiro | 1 | 21 | 11-03-2020 | 21-07-2021 | 497 | 365 | 500000 | 478686.88 | 2 | 490520 | -11833.12 | 97.5876 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Criterion related to quality Name: Technical value of the proposal Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change in the execution period of the project | unforeseen work
1214 | 6603055 | Remodeling of the Water Supply Network in Lugar de Ancas - 1st Phase | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Anadia | Aveiro | 1 | 15 | 26-02-2020 | 03-05-2021 | 432 | 150 | 207516.26 | 197971.77 | 1 | 197971.77 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1215 | 6590922 | Paving of streetde Santiago in the parish of Vilela | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 06-05-2020 | 02-06-2020 | 27 | 30 | 37714.51 | 26156.39 | 1 | 26156.39 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1216 | 6590725 | Repaving of street of Misericórdia in Póvoa de Lanhoso (Execution of repaving works in bituminous mixture, to improve the existing one). | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 06-05-2020 | 31-08-2020 | 117 | 60 | 65881.05 | 48899.67 | 1 | 48899.67 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the municipality was carrying out water supply infrastructure works and the company could not carry out the projects in question simultaneously.
1217 | 6590381 | Requalification of E.M. 1359, In ​​the parishes of S.João de Rei and Rendufinho, execution of work to repave the street in bituminous. | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 06-05-2020 | 22-07-2020 | 77 | 90 | 70000 | 52168.82 | 1 | 52168.82 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1218 | 6589652 | Contract work for "street of Portela and crossstreet of Chanca", in Carrazedo Montenegro | 45233252-0 | Surface work for streets | FALSE | 2020 | 2020 | Portugal | Valpaços | Vila Real | 19 | 18 | 05-05-2020 | 30-09-2020 | 148 | 120 | 169811.32 | 162391.26 | 1 | 149771.94 | 12619.32 | 108.4257 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the consignment was signed on june 3, 2020 | underwork worth €12,619.31
1219 | 6589619 | Rehabilitation of the Collecting Network and Other Components of the Sanitation System in Baixa | 45232400-6 | Sewer construction work | FALSE | 2020 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 24 | 15-05-2020 | 13-12-2021 | 577 | 365 | 200000 | 200000 | 1 | 199170.78 | 829.22 | 100.4163 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | this contract had a 90-day extension and a 40-day suspension of work | the estimated quantities were higher than the quantities actually needed during the contract.
1220 | 6588587 | Paving, in bituminous concrete, of streets in the parish of Paços de Brandão e Mozelos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 18-05-2020 | 07-10-2021 | 507 | 180 | 323568 | 241073.24 | 1 | 143096.9 | 97976.34 | 168.4685 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 115 days delay in completion of works by contractor 37 days in scheduling inspection for provisional acceptance | in one of the streets, work was carried out to rehabilitate sidewalks and parking bays, which it was not possible to make compatible with the project foreseen in the contract, and for this reason they were withdrawn from the contract.
1221 | 6587147 | Contract for "Improvement of the Municipal Road Network - streetCalouste Gulbenkian and Av. Do Parque Natural da Ria Formosa" | 45432110-8 | Floor-laying work | FALSE | 2020 | 2020 | Portugal | Olhão | Faro | 8 | 30 | 19-05-2020 | 23-11-2020 | 188 | 120 | 280000 | 272364.48 | 2 | 272364.48 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1222 | 6582092 | Improvement of Mobility in the Urban Core - Pedestrian Cycling Mobility and Urban Transport - Tours in the Bairro da Estação | 45233253-7 | Surface work for footpaths | FALSE | 2020 | 2021 | Portugal | Bragança | Bragança | 4 | 10 | 15-05-2020 | 22-06-2021 | 403 | 180 | 165000 | 154056.75 | 1 | 146721.93 | 7334.82 | 104.9991 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay verified due to the decrease in productivity due to constraints caused by covid 19. | there was underwork
1223 | 6575765 | hub paving | 45233220-7 | Surface work for roads | FALSE | 2020 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 12-05-2020 | 11-12-2020 | 213 | 180 | 268551 | 127386.1 | 1 | 118806.6 | 8579.5 | 107.2214 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was finished ahead of schedule | underwork
1224 | 6575700 | hub paving | 45233220-7 | Surface work for roads | FALSE | 2020 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 12-05-2020 | 21-12-2020 | 223 | 180 | 268551 | 138512.55 | 1 | 134117.05 | 4395.5 | 103.2774 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was finished ahead of schedule | underwork
1225 | 6575216 | Expansion of the water supply and wastewater drainage network and execution of the rainwater network on street ntre Campos - Lobão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-05-2020 | 30-04-2021 | 352 | 180 | 101994.38 | 94545.45 | 1 | 92423.31 | 2122.14 | 102.2961 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 63 days of delay in the delivery of the final screens that caused a delay in the provisional reception | a small decrease in the length of the executed network resulted in less excavation and less landfills.
1226 | 6574406 | Quality 100% - Repaving of the area surrounding the shopping area of ​​Leça da Palmeira and Perafita | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Matosinhos | Porto | 13 | 9 | 07-05-2020 | 15-02-2021 | 284 | 90 | 710000 | 479455.55 | 2 | 479455.55 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1227 | 6573513 | Cold microagglomerate repaving - February 2020 | 45233222-1 | Paving and asphalting works | FALSE | 2020 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 12-05-2020 | 29-04-2021 | 352 | 120 | 246200 | 228428.7 | 1 | 217105.7 | 11323 | 105.2154 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the project had underwork
1228 | 6572528 | Improvement of the Municipal Road Network - EM 514 (Between the A22 Underpass) and the County Limit | 45432110-8 | Floor-laying work | FALSE | 2019 | 2020 | Portugal | Olhão | Faro | 8 | 30 | 06-01-2020 | 18-06-2020 | 164 | 120 | 260000 | 216366.1 | 1 | 216366.1 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1229 | 6567818 | AR026 E1 - Decommissioning and landscaping WWTP Paredes/Penafiel | 45110000-1 | Building demolition and wrecking work and earthmoving work | TRUE | 2020 | 2021 | Portugal | Paredes | Porto | 13 | 32 | 29-04-2020 | 03-02-2021 | 280 | 180 | 486500 | 462094.65 | 2 | 431093.62 | 31001.03 | 107.1913 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | delays verified had as the main cause the current pandemic situation | replacement of variable section flow meters by flow measurement with parshal channels
1230 | 6566652 | Construction of retaining walls / Ground retaining wall at street of Vale do Fojo (next to the sports area) - Vermoil - Proc. No. 10/2020 | 45262600-7 | Miscellaneous special-trade construction work | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 18 | 08-04-2020 | 21-12-2021 | 622 | 90 | 102307.2 | 89703 | 1 | 72407.05 | 17295.95 | 123.8871 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the inspection for the purpose of provisional acceptance was carried out as soon as the project was completed, and after the contractor's verbal request, that is, the inspection took place within 18 days after the completion of the project, with the provisional acceptance document having been drawn up, and signed by the stakeholders. | existence of underworks.
1231 | 6565724 | Cp 24/2019 - Extension of wastewater drainage networks in street of Trancosa - UF de Tagilde and Vizela (S. Paio) and alteration of the water supply system in the parish of Infias | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 14 | 17-01-2020 | 17-09-2020 | 244 | 90 | 40000 | 37451.08 | 1 | 347476.73 | -310025.65 | 10.778 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1232 | 6565472 | Cp 21/2019 - Extensions of the wastewater drainage network in the parish of Longos - street of Devesa | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 02-03-2020 | 13-08-2021 | 529 | 120 | 123000 | 104025.88 | 1 | 98247.87 | 5778.01 | 105.8811 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1233 | 6565376 | Cp 10/2019 - Replacement of water supply networks on streetJosé Francisco Ribeiro and street of Lugarinho - Parish of Costa - Guimarães | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 24-10-2019 | 01-07-2021 | 616 | 120 | 99270 | 98999.18 | 1 | 84965.48 | 14033.7 | 116.5169 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1234 | 6565164 | Improvement of Praia do Osso da Baleia / Other Interventions (Requalification of the Picnic Park) - Proc. No. 05/2020 | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2020 | 2021 | Portugal | Pombal | Leiria | 10 | 21 | 18-03-2020 | 30-11-2021 | 622 | 90 | 110136.4 | 102716.49 | 1 | 91777.39 | 10939.1 | 111.9192 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this work was already started during the time of the covid-19 pandemic, with the constraints and delays at a global level of all known. | existence of underworks
1235 | 6565110 | Cp 02/2020 - extension and alteration of the water supply system in the parish of gondar - municipality of guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 23-04-2020 | 05-01-2021 | 257 | 90 | 75000 | 73246.61 | 1 | 66652.48 | 6594.13 | 109.8933 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1236 | 6564905 | Execution of Water Supply Columns in Twelve Buildings Located at streetVale Formoso de Cima, Lots A1 to A6 and B1 to B6, Chelas, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 21 | 28-04-2020 | 31-12-2020 | 247 | 180 | 180000 | 129510.69 | 1 | 129510.69 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1237 | 6555391 | CP 009/2020 - Structural remodeling contract for the supported warehouse at Boavista | 45259000-7 | Repair and maintenance of plant | FALSE | 2020 | 2021 | Portugal | Portimão | Faro | 8 | 30 | 07-05-2020 | 06-09-2021 | 487 | 90 | 157000 | 98365.65 | 1 | 99127.24 | -761.59 | 99.2317 | Best value for money: Yes Criterion related to quality Name: Technical Valuation (clause 19 of the Procedure Program) Weighting: 40% Criterion related to cost Name: Price (clause 19 of the Procedure Program) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the initial deadline for the contract was met. | the underwork is due to the fact that while the tender process was running and the project was starting, emarp had already replaced the ladder for safety reasons for its employees.
1238 | 6551794 | Rehabilitation of Vimieiro River Beach / Landscaping Intervention at Vimieiro River Beach - Phase 2 | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Penacova | Coimbra | 6 | 18 | 29-02-2020 | 05-02-2021 | 342 | 150 | 331833.33 | 329806.22 | 2 | 329496.01 | 310.21 | 100.0941 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in the delivery of materials and human resources in prophylactic isolation due to covid | over and underwork
1239 | 6551020 | CP 002/2020 - Execution of the Distribution Conduct of the Great Reserve Deposit | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2020 | 2021 | Portugal | Portimão | Faro | 8 | 30 | 07-05-2020 | 13-10-2021 | 524 | 90 | 128000 | 127345.6 | 1 | 129567.35 | -2221.75 | 98.2853 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the initial deadline for the contract was 90 days, stipulated in the ec, it was not met, because there was a work suspension notice due to the summer period, and connections to the existing network could not be made, because it jeopardized the public supply to the population in high summer season. then there was an extension of the deadline for the contract until 03/27/201, due to the covid19 problem, and the factories did not deliver the accessories and joints made to order for this work due to its specificity and size, and also due to the need that emarp had to carry out another work for the sectioning and deactivation of existing unregistered ducts, so that the definitive connections of the dn900, 800 and 600mm ducts could be carried out. | price review
1240 | 6550539 | Febres Sports Park, by Contract: Construction of WC on the 1st floor, entrance wall and other works - CP-CCP-EMP n.º 05/2020 | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 14 | 08-05-2020 | 19-02-2021 | 287 | 60 | 35000 | 34935.45 | 1 | 33868.83 | 1066.62 | 103.1493 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works and underwork.
1241 | 6550147 | Expansion contract for the compound warehouse and material reception bays | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 33 | 10-03-2020 | 21-08-2020 | 164 | 120 | 200000 | 193749.63 | 1 | 193749.63 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic
1242 | 6545902 | Contract for "Requalification of the Levante Market, in Lagos" | 45453100-8 | Refurbishment work | FALSE | 2020 | 2021 | Portugal | Lagos | Faro | 8 | 10 | 27-04-2020 | 29-03-2021 | 336 | 150 | 321000 | 299996.07 | 2 | 374367.24 | -74371.17 | 80.1342 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for carrying out the project was extended for another 30 days by order of mr. president of 11/02/2020, due to the execution of complementary work | approved complementary works in the amount of €77,414.64, plus vat and accepted underwork in the amount of €3,043.47, plus vat, by order of mr. president of 11/02/2020
1243 | 6541708 | Cp 23/2019 - Extension of wastewater drainage networks on streetde Cedofeita and street of Molos - U. F. From tagilde and vizela s. Paio (s. Paio) - municipality of vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2021 | Portugal | Vizela | Braga | 3 | 14 | 16-01-2020 | 14-01-2021 | 364 | 90 | 64000 | 58770.17 | 1 | 58559.8 | 210.37 | 100.3592 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension | underwork
1244 | 6541207 | Cp 25/2019 - extension of wastewater drainage networks in the union of parishes of briteiros s. Salvador and briteiros sta leocádia and union of parishes of souto sta maria, souto s. | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 30-03-2020 | 13-07-2021 | 470 | 90 | 74500 | 74327.87 | 1 | 66507.6 | 7820.27 | 111.7585 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | works less
1245 | 6541003 | Cp 01/2020 - replacement of water supply networks and wastewater sanitation networks in the parishes of azurém, costa, creixomil and uf de oliveira, s. Paio and S. Sebastian | 45232151-5 | Water-main refurbishment construction work | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 21-04-2020 | 24-03-2021 | 337 | 90 | 78000 | 76600 | 1 | 68256.87 | 8343.13 | 112.2231 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1246 | 6540834 | CP 28/2019 - Extension and Alteration of Wastewater Drainage Networks in the Parish of Nespereira, U.F. Candoso Santiago and Mascotelos and U.F. From Caldas de Vizela (S. Miguel and S. João) | 45232411-6 | Foul-water piping construction work | FALSE | 2020 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 30-03-2020 | 23-07-2021 | 480 | 120 | 135900 | 124805.95 | 1 | 121823.15 | 2982.8 | 102.4485 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1247 | 6540015 | Luís Sttau Monteiro Primary School - Reformulation of the Rainwater Drainage Network - Work | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2020 | Portugal | Loures | Lisboa | 11 | 20 | 22-11-2019 | 22-09-2020 | 305 | 90 | 272724.92 | 265491.82 | 2 | 290371.79 | -24879.97 | 91.4317 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | on november 22, 2019, a contract was signed between the municipality of loures and manuel gomes de almeida & filhos – construcción civil e obra publicas, lda (mgaf), with the purpose of carrying out the project at “escola básica luís sttau monteiro – reformulation of the rainwater drainage network” in loures. the assignment of the contract was carried out on march 26, 2020, and the health and safety plan was approved on march 30, 2020, with the deadline starting on march 30. with mgaf as one of its main objectives the fulfillment of its contractual obligations and satisfaction of the owner of work, it has always made every effort to compliance with the contract deadlines. as everyone knows, this project began in the midst of a state of emergency, decreed by his excellency the president of the republic, and which, following the renovations, ended only on may 2, 2020, with the entry of the state of calamity. we have never stopped or suspended work on the sites, always with the objective that the conclusion of the projects would not compromise the objectives of the owner of work. the resolution of the mgaf management to maintain the project, but with strict compliance with the indications of the general directorate of health (dgs) national health service (sns), in terms of safety at work and maintenance of the health of workers, namely the maintenance distance between workers, reduction in the capacity of personnel transport vehicles, limitation of travel, among others, led to a significant drop in normal income from work. we also suffered consequences in terms of the arrival of materials, as a result of some suppliers having temporarily or partially closed their services due to vehicle circulation limitations and which did not allow some materials, mainly those coming from abroad, to be supplied in due time. according to the project deadlines. for all of the above and mainly as a result of the health catastrophe of the pandemic that the country and the world are going through and of which the consequences persist, we have taken the initiative to submit to your excellencies a request for a graceful extension of the deadline, which includes a new deadline of the undertaking. in summary, we ask for the graceful approval of a request for a 3-week extension, with the resulting final date, 21 july 2020. | moc 1.-legal framework and responsibility regime. having analyzed the circumstances that determine the need to carry out these works not foreseen in the contract (tm1 - landfill of ditches and pavements), the inspection considers that the projects that constitute this objective modification of the contract must be classified as complementary works that result from circumstances not foreseen, as provided for in article 370 of the "public procurement code". therefore, in the case of complementary work resulting from unforeseen circumstances, it is necessary to verify the liability regime applicable to the allocation of the respective costs between the contractor and the client of the project, as provided for in article 378 of the "public procurement code". moc 2. - legal framework and responsibility regime. having analyzed the circumstances that determine the need to carry out these works not foreseen in the contract (tm2 - paving the playing field), the inspection considers that the projects that constitute this objective modification of the contract must be classified as complementary works that result from circumstances that result from unforeseeable circumstances as provided for in article 370 of the "public procurement code".
1248 | 6539898 | Contract for the Refurbishment of the Transformation Station of the Vila Fria Pumping Station (Oeiras) | 45000000-7 | Construction work | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 60 | 18-03-2020 | 21-07-2021 | 490 | 168 | 260000 | 216828.06 | 1 | 218499.43 | -1671.37 | 99.2351 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of the execution period by 62 days due to existing constraints in the context of the covid-19 pandemic and the conditions adverse weather conditions that impacted the normal development of civil works. | change in the value of the project due to the contractual works not carried out and the price revision carried out.
1249 | 6539689 | EP-2020(5001)/10001 Improvement of the Januário Barreto Pavilion - CED PM | 45113000-2 | Siteworks | FALSE | 2020 | 2021 | Portugal | Lisboa | Lisboa | 11 | 14 | 04-05-2020 | 25-10-2021 | 539 | 180 | 430000 | 359599.87 | 2 | 362966.65 | -3366.78 | 99.0724 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in the execution of works | existence of complementary work and underwork
1250 | 6537486 | Environmental Requalification of the River Front of the Douro River between Ponte do Freixo and Quinta dos Cubos - Oliveira do Douro | 45233140-2 | Roadworks | TRUE | 2019 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 20-04-2020 | 16-11-2021 | 575 | 180 | 586101.52 | 549388.99 | 2 | 577434.19 | -28045.2 | 95.1431 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed on time, however the provisional acceptance notice was only drawn up on the date indicated. | with the completion of the project, additional work resulted in the amount of €66,728.92 and a negative provisional price revision was determined in the amount of €10,027.41.
1251 | 6536751 | Action Plan to improve accessibility and smooth mobility in Vizela (Execution of Cycle Path - PAMUS) | 45233162-2 | Cycle path construction work | FALSE | 2020 | 2021 | Portugal | Vizela | Braga | 3 | 31 | 04-05-2020 | 04-05-2021 | 365 | 180 | 497006.6 | 447480.46 | 2 | 490295.97 | -42815.51 | 91.2674 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
1252 | 6530262 | 52/Eop/dcop/2019 - "reformulation of the en249-4 road layout, between the cemetery roundabout in são Domingos de rana and trajouce, at the end of the county - 2nd phase | 45232410-9, 45233200-1, 45111000-8, 45112700-2, 45100000-8, 45262310-7, 45232130-2, 45232151-5, 45232332-8, 45233294-6 | Sewerage work, Various surface works, Demolition, site preparation and clearance work, Landscaping work, Site preparation work, Reinforced-concrete work, Storm-water piping construction work, Water-main refurbishment construction work, Ancillary works for telecommunications, Installation of road signals | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 28-04-2020 | 01-10-2021 | 521 | 270 | 2628123.22 | 2312400 | 3 | 2312400 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1253 | 6529545 | Work to improve the sorting station | 45213270-6 | Construction works for recycling station | FALSE | 2019 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 25 | 21-02-2020 | 30-09-2021 | 587 | 240 | 2500000 | 2489000 | 3 | 2667549.55 | -178549.55 | 93.3066 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works; graceful extension. | complementary works; underwork.
1254 | 6529356 | New street layout, rainwater infrastructure, 1st Phase in the parish of Galegos | 45232130-2 | Storm-water piping construction work | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 29-04-2020 | 29-05-2020 | 30 | 60 | 20216.8 | 15429.35 | 1 | 15429.35 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1255 | 6529074 | Requalification of the Civic Center in the parish of Lanhoso | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 29-04-2020 | 23-07-2020 | 85 | 90 | 84033.58 | 63192.6 | 1 | 63192.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1256 | 6525528 | Construction of a metallic pedestrian pier over the Aljezur stream | 45221220-0 | Culverts | FALSE | 2019 | 2020 | Portugal | Aljezur | Faro | 8 | 30 | 16-04-2020 | 30-12-2020 | 258 | 120 | 200461 | 196330 | 1 | 200098.38 | -3768.38 | 98.1167 | Best value for money: Yes Criterion related to quality Name: Methodology for planning, controlling and managing deadlines and costs Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension by 30 days. | complementary work and underwork
1257 | 6525020 | Requalification of the Road Network in the Municipality, by Contract: Roundabout Padre Américo, street of Fonte Nova and Elevated Crosswalk at streetAntero de Quental, in the City of Cantanhede - CP-CCP-EMP n.º 15/2019 | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 29-04-2020 | 23-12-2020 | 238 | 180 | 177000 | 174766.17 | 1 | 174473.95 | 292.22 | 100.1675 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
1258 | 6524741 | Requalification of streetde Goim - Romariz | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 8 | 29-04-2020 | 14-12-2021 | 594 | 180 | 318931 | 277680 | 2 | 281880.11 | -4200.11 | 98.51 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | 15 days of extension due to additional work, 60 days of delay by the contractor, 43 days between the 1st inspection and the provisional acceptance in the repair of deficiencies | complementary works and less resulting from the need to change the layout of the storm drainage network
1259 | 6523985 | Qualification of the industrial zones of Gil Vaz and Fontainhas | 45233100-0 | Construction work for highways, roads | FALSE | 2020 | 2020 | Portugal | Elvas | Portalegre | 12 | 21 | 03-04-2020 | 09-12-2020 | 250 | 120 | 936700 | 148072.19 | 1 | 148072.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there was a need to make several corrections in the project before the provisional acceptance was carried out.
1260 | 6521946 | Cpe.3.20.dmosm - Gerizes playground | 45212130-6 | Amusement park construction work | FALSE | 2020 | 2020 | Portugal | Braga | Braga | 3 | 30 | 24-04-2020 | 24-07-2020 | 91 | 45 | 89316.77 | 72122.16 | 1 | 71952.16 | 170 | 100.2363 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1261 | 6517778 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Souto, Mosteirô and Fornos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 23-04-2020 | 03-12-2021 | 589 | 180 | 312494 | 262809.78 | 2 | 286090.81 | -23281.03 | 91.8624 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2 days when scheduling an inspection for the purposes of provisional acceptance, 267 days between the 1st inspection and the provisional acceptance of the project for the correction of deficiencies | complementary work and less
1262 | 6517639 | Sangalhos Parish Council Building Rehabilitation | 45210000-2 | Building construction work | FALSE | 2020 | 2021 | Portugal | Anadia | Aveiro | 1 | 15 | 20-04-2020 | 11-01-2021 | 266 | 120 | 126158.76 | 108008.03 | 1 | 108008.03 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1263 | 6516144 | Complete Refurbishment of the Exterior of Four Buildings and Replacement of Roofs, Located at street ofmingos Reis Quita, Alto Pina, belonging to the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 11 | 09-04-2020 | 31-12-2020 | 266 | 120 | 240000 | 213528 | 1 | 213528 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to point out
1264 | 6516093 | Total Exterior Rehabilitation of the Former Aid Post Building, Located at streetAzinhaga Fonte do Louro, Alto Pina, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2020 | 2020 | Portugal | Lisboa | Lisboa | 11 | 21 | 09-04-2020 | 31-12-2020 | 266 | 150 | 199000 | 123231.7 | 1 | 123231.7 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1265 | 6511041 | Improvement of Municipal Road 597 - Section Cruz. E.N.3 - Avessada - Vale da Gama - S. José das Matas | 45233251-3 | Resurfacing works | FALSE | 2020 | 2020 | Portugal | Mação | Santarém | 16 | 14 | 31-03-2020 | 08-07-2020 | 99 | 30 | 161706 | 152490.7 | 1 | 152490.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price or Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension
1266 | 6510571 | Contract 298/Gebalis/2019 - Rehabilitation and conservation works in Bairro dos Alfinetes, Lots B1 to B7 | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 23 | 12-03-2020 | 29-07-2021 | 504 | 330 | 525136.08 | 505049.12 | 2 | 531375.81 | -26326.69 | 95.0456 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
1267 | 6510180 | Wastewater from Óis da Ribeira (PAR 019) - Águeda / phase 2 | 45233222-1 | Paving and asphalting works | TRUE | 2019 | 2020 | Portugal | Águeda | Aveiro | 1 | 15 | 07-04-2020 | 06-07-2020 | 90 | 30 | 115000 | 90000 | 1 | 88000 | 2000 | 102.2727 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1268 | 6509916 | CONTRACT FOR VARIOUS REPAIRS AT elementary school 1, 2, 3/S CARDEAL COSTA NUNES – MADALENA, carrying out various repair works | 45214200-2 | Construction work for school buildings | FALSE | 2020 | 2020 | Portugal | Madalena | Região Autónoma dos Açores | 15 | 31 | 22-04-2020 | 30-11-2020 | 222 | 153 | 215000 | 214810 | 1 | 214810 | 0 | 100 | most economically advantageous proposal, modality with the best quality-price ratio If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 22 FRIDAY, JANUARY 31, 2020 Factor 1 – Price – 40%; Factor 2 – Technical Quality of the proposal – 60%; - Subfactor 2.1: Plan of works (70%); Subfactor 2.2; Descriptive memory and justification of the execution of the work (30%). | 1 | 40 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather
1269 | 6508612 | East Line Contract - Pk 194.450/197.00- Migration of wooden sleepers by concrete and passage from BC to BLS | 45234100-7 | Railway construction works | FALSE | 2019 | 2021 | Portugal | Crato | Portalegre | 12 | 18 | 20-04-2020 | 10-11-2021 | 569 | 120 | 619620 | 606245.9 | 2 | 591626.5 | 14619.4 | 102.4711 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A
1270 | 6507795 | Wastewater from street ofs Candeeiras - Trofa - Águeda | 45232460-4 | Sanitary works | TRUE | 2019 | 2020 | Portugal | Águeda | Aveiro | 1 | 25 | 07-04-2020 | 16-10-2020 | 192 | 90 | 85000 | 74139.04 | 1 | 58936.4 | 15202.64 | 125.795 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1271 | 6504859 | Refurbishment of the sanitary facilities at the elementary school of Pigeiros | 45210000-2 | Building construction work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-04-2020 | 27-10-2020 | 193 | 60 | 44350 | 39883.59 | 1 | 44434.06 | -4550.47 | 89.759 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 30-day extension of the deadline and 9 days for scheduling an inspection for provisional acceptance | complementary works
1272 | 6504400 | Its object is the execution of various carpentry and painting works in municipal buildings and the municipal school park. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 21 | 02-04-2020 | 08-04-2021 | 371 | 560 | 150800 | 135720.01 | 1 | 135720.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contingencies that implied the deviation in the execution time of the project were: the projects related to the continuation of the contract were anticipated due to the pandemic, since the intervened equipment was closed, namely schools and ji's, facilitating the execution of the projects.
1273 | 6500063 | Requalification of the surroundings of the chapel of the lady. Da tocha - parish of vizela (santo adrião) - ppi:12/2017, requalification and repair to the surroundings of the streetde s. Gonçalo | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 15 | 25-03-2019 | 29-07-2020 | 492 | 35 | 995545.29 | 39880.7 | 1 | 39880.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1274 | 6500014 | Requalification of the surroundings of the chapel of the lady. Da tocha - parish of vizela (santo adrião) - ppi:12/2017, requalification and repair to the surroundings of the streetde s. Gonçalo | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 15 | 25-03-2019 | 25-03-2020 | 366 | 210 | 995545.29 | 227680.38 | 1 | 222365.82 | 5314.56 | 102.39 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | works not performed
1275 | 6499900 | Requalification of the surroundings of the chapel of the lady. Da tocha - parish of vizela (santo adrião) - ppi:12/2017, requalification and repair to the surroundings of the streetde s. Gonçalo | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 15 | 25-03-2019 | 16-03-2020 | 357 | 35 | 995545.29 | 48341.09 | 1 | 53175.09 | -4834 | 90.9093 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | complementary works
1276 | 6499045 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Arrifana and Milheirós de Poiares | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-04-2020 | 08-11-2021 | 570 | 180 | 291838 | 211791.93 | 1 | 210539.49 | 1252.44 | 100.5949 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 181 days delay in completion of work by the contractor, 93 days in correction of physical and documental defects | underwork related to the supply of sections of some streets
1277 | 6496037 | Public Tender No. 07 - SC/IPS/2019 - Contracts for Various Works for the Polytechnic Institute of Setúbal - Lot 5 | 45300000-0 | Building installation work | FALSE | 2019 | 2020 | Portugal | Setúbal | Setúbal | 17 | 14 | 28-02-2020 | 03-07-2020 | 126 | 45 | 65022.53 | 17274.5 | 1 | 17274.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | not verified
1278 | 6494235 | Paving street prof. Domingos Henrique Ferreira, street of Barreiro and crossstreet of Estrada Nova - Sanguedo | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-04-2020 | 09-04-2021 | 358 | 120 | 146000 | 123826.29 | 1 | 133969.89 | -10143.6 | 92.4284 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 15 days grace period extension, 25 days when scheduling an inspection for the purposes of provisional acceptance, 97 days between the 1st inspection and provisional acceptance for rectification of deficiencies | complementary work and less
1279 | 6491571 | Public Tender No. 34/2020 - Antechamber Construction Work at CICA | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2020 | 2020 | Portugal | Porto | Porto | 13 | 15 | 15-04-2020 | 15-06-2020 | 61 | 30 | 10000 | 9758.21 | 1 | 9758.21 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Report Weighting: 50% Criterion related to cost Name: Global Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | structural reasons
1280 | 6491220 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Sanguedo, Fiães and Romariz | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2020 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 12 | 15-04-2020 | 08-11-2021 | 572 | 180 | 320807 | 231187.82 | 1 | 221718.26 | 9469.56 | 104.271 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | 159 days delay in completion of work by the contractor, 163 days in correction of physical and documental defects | underwork related to the supply of some sections of streets
1281 | 6490922 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of S. Paio de Oleiros and Nogueira da Regedoura | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 14-04-2020 | 28-06-2021 | 440 | 180 | 316994 | 251655.14 | 2 | 236398.11 | 15257.03 | 106.454 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 54 days of delay in completion of works by the contractor, 168 days between the 1st inspection and the provisional acceptance in the correction of deficiencies | underwork
1282 | 6490099 | Construction of Service Station - Caravan Park - Service Area and Overnight Camping | 45223300-9 | Parking lot construction work | FALSE | 2020 | 2021 | Portugal | Ponte de Sor | Portalegre | 12 | 15 | 30-03-2020 | 29-01-2021 | 305 | 60 | 71879.31 | 64646 | 1 | 64306 | 340 | 100.5287 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | existence of underworks
1283 | 6489236 | Contract for Leisure Park and Parking Next to School E.B 2/3 Dr. António Eusebio, in Moncarapacho | 45432110-8 | Floor-laying work | FALSE | 2019 | 2021 | Portugal | Olhão | Faro | 8 | 30 | 08-01-2020 | 23-06-2021 | 532 | 180 | 470000 | 448710.79 | 2 | 448710.79 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | initial suspension for purposes of court approval and dpss approval. graceful extensions due to bad weather, supplier delays and pandemic situation.
1284 | 6488495 | Requalification of street of Carvoeiro in Serzedelo | 45233160-8 | Paths and other metalled surfaces | FALSE | 2020 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 09-04-2020 | 07-07-2020 | 89 | 120 | 68032.96 | 58752.08 | 1 | 58752.08 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1285 | 6486162 | Cercal Pedestrian Circuit - Cadaval, South Entrance to the Village | 45233161-5 | Footpath construction work | FALSE | 2020 | 2021 | Portugal | Cadaval | Lisboa | 11 | 14 | 31-03-2020 | 29-10-2021 | 577 | 60 | 155611.46 | 133910.33 | 1 | 142766.33 | -8856 | 93.7969 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1st partial suspension for 58 days, for study alterations for the creation of a land support wall and 2nd partial suspension of 74 days due to difficulties in the delivery of materials due to the covid 19 pandemic | execution of complementary work
1286 | 6485671 | Public Tender for the Execution of Sidewalks on streets anta Marinha in Astromil | 45233200-1 | Various surface works | FALSE | 2020 | 2020 | Portugal | Paredes | Porto | 13 | 15 | 03-04-2020 | 28-12-2020 | 269 | 60 | 55758 | 45000 | 1 | 43600 | 1400 | 103.211 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | indefinitions in the project | underwork
1287 | 6483692 | General painting work on facades in the Azeda neighborhood - Setúbal | 45442110-1 | Painting work of buildings | FALSE | 2019 | 2020 | Portugal | Setúbal | Setúbal | 17 | 30 | 23-03-2020 | 09-07-2020 | 108 | 80 | 101821 | 88785 | 1 | 88785 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1288 | 6481099 | Quinta do Castelo electricity supply infrastructure | 45310000-3 | Electrical installation work | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 08-04-2020 | 22-06-2021 | 440 | 60 | 33504 | 33300 | 1 | 37041.9 | -3741.9 | 89.8982 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 82 days of graceful extension and 3 days for scheduling inspections and 37 days for correcting deficiencies between the 1st inspection and provisional acceptance | additional work and underwork
1289 | 6477302 | Exterior repairs in various locations in the municipality - requalification of green spaces on Avenida Francisco Sá Carneiro in Quarteira | 45112710-5 | Landscaping work for green areas | FALSE | 2020 | 2020 | Portugal | Loulé | Faro | 8 | 21 | 30-03-2020 | 09-10-2020 | 193 | 120 | 145000 | 124533.65 | 1 | 122082.88 | 2450.77 | 102.0075 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | work unless performed
1290 | 6475933 | Rehabilitation of the water supply network at streetCândido Manuel Pereira and Praça Cinco de Outubro - Lavradio | 45232151-5 | Water-main refurbishment construction work | FALSE | 2020 | 2021 | Portugal | Barreiro | Setúbal | 17 | 25 | 13-03-2020 | 18-06-2021 | 462 | 180 | 224400 | 194243.69 | 1 | 194243.7 | -0.01 | 100 | Best value for money: Yes Criterion related to quality Name: Quality of the proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | drop in income due to constraints caused by existing infrastructure and difficulty in supplying materials due to the pandemic. | no change
1291 | 6472705 | Paving South Zone of the Municipality | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 20-03-2020 | 17-11-2021 | 607 | 240 | 1155000 | 693000.03 | 2 | 691950.03 | 1050 | 100.1517 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 121 days of delay by the contractor in completing the projects, 100 days between the 1st inspection and the provisional reception of the project in the correction of defects | underwork
1292 | 6472337 | Its object is the requalification of streetAlfredo Silva, as well as the carrying out of all consequential or necessary works for their perfect execution and that are considered indispensable | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 31 | 18-03-2020 | 30-08-2021 | 530 | 90 | 244789.04 | 213494.6 | 1 | 213494.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - multiplicity of interactions with the affected services; - interventions by simas and gdl during the same period of the project; - delay by the contractor in delivering the "plan for the prevention and management of construction and demolition waste"; - several constraints related to the pandemic and the state of emergency; - delays in the supply of materials due to the pandemic.
1293 | 6471851 | Cp 22/2019 - repair of the bituminous pavement on street of Covelo - Parish of Nespereira - Guimarães | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 16-01-2020 | 13-03-2020 | 57 | 15 | 23530 | 22989 | 1 | 22433.47 | 555.53 | 102.4763 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | urgency | underwork
1294 | 6471241 | Public Tender No. 138/2019 - Renovation of the Sanitary Facilities of the Nephrology Service | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 15 | 09-03-2020 | 09-07-2020 | 122 | 30 | 18000 | 17255.68 | 1 | 17255.68 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Global Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unpredictable reasons | unpredictable reasons
1295 | 6466304 | 2015.129.01.C1 - SE Montijo - infrastructure refurbishment energy optimization | 45214800-8 | Training facilities building | TRUE | 2019 | 2020 | Portugal | Montijo | Setúbal | 17 | 21 | 14-05-2019 | 07-10-2020 | 512 | 150 | 493000 | 423403.31 | 2 | 434730.92 | -11327.61 | 97.3943 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension | complementary works
1296 | 6464954 | Exterior Arrangements of the Area Surrounding the Building of the Parish Council of Espinhel | 45211360-0 | Urban development construction work | TRUE | 2019 | 2021 | Portugal | Águeda | Aveiro | 1 | 25 | 26-03-2020 | 30-11-2021 | 614 | 120 | 149420.23 | 135820.34 | 1 | 134944.52 | 875.82 | 100.649 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the execution period for the contract was extended due to the need to carry out additional work, namely the elimination of the septic tank in the parish council building, reformulation of the network, execution of an extension box and connection to the public sanitation network. | changes in the value of the project result from the execution of complementary works and from the quantities of works not carried out.
1297 | 6462746 | Contract "High school of Oliveira do Hospital - conclusion" | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 30-03-2020 | 14-12-2021 | 624 | 365 | 1263952 | 1168502.13 | 3 | 1146206.73 | 22295.4 | 101.9451 | Best value for money: No Criterion related to quality Name: N/A Weighting: 100% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | constraints in terms of supplies and difficulties in guaranteeing concrete forecasts for the delivery of materials, by suppliers, causing disturbances in planning and in the normal development of the contract work, motivated by the covid 19 pandemic | project design errors and/or omissions
1298 | 6459256 | Paving on National Road 13 | 45233220-7 | Surface work for roads | TRUE | 2019 | 2021 | Portugal | Esposende | Braga | 3 | 20 | 23-12-2019 | 01-06-2021 | 526 | 60 | 118786.69 | 88449.6 | 1 | 77559.17 | 10890.43 | 114.0414 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 60% Criterion related to cost Name: Bid price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work was suspended. | underwork worth € 10,890.43.
1299 | 6456958 | Requalification of the CM - (street of Ponte de Passos, streetJosé Carvalho V. Castro, streetMira Fafe and streetPinheiro | 45233142-6 | Road-repair works | FALSE | 2016 | 2019 | Portugal | Fafe | Braga | 3 | 30 | 29-09-2016 | 03-10-2019 | 1099 | 435 | 849000 | 639992.33 | 2 | 609468.9 | 30523.43 | 105.0082 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a1) - Price Factor: 60% a2) Technical Valuation Factor and proposal guarantee: 40% a2.1) subfactor - Descriptive and Justification: 50% a2.2) subfactor - Work Program: 50% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a 35 day deadline extension | there were underworks worth €30,523.46
1300 | 6453079 | S.e.c. - Procº nº 224/A1/19 - Public Tender for the award of the contract for Requalification and Modernization of the facilities of the elementary and High school of Monte da Ola | 45262700-8 | Building alteration work | TRUE | 2020 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 6 | 26-03-2020 | 30-04-2021 | 400 | 450 | 1955322.52 | 1798036.87 | 3 | 1803930.27 | -5893.4 | 99.6733 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | covid-19 measures. | underwork.
1301 | 6450310 | The work to be carried out involves all the work necessary for the exterior and interior rehabilitation of the building. | 45216111-5 | Police station construction work | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 20 | 20-03-2020 | 11-11-2021 | 601 | 300 | 800000 | 718222.6 | 2 | 810762.41 | -92539.81 | 88.5861 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | granted: 13 days - deadline for execution of additional work - additional contract on 11.16.2020 09 days - deadline for execution of complementary works - additional contract - 03.25.2021 22 days - deadline for execution of complementary works - additional contract - 07.12.2021 extensions (105 days): 75 days – graceful – addendum to the initial contract on 03.25.2021 30 days – graceful – addendum to the initial contract on 7/12/2021 | additional work – €87,040.28 underwork – €14,897.61 price revision (provisional + final calculation) - €20,397.14
1302 | 6450274 | 2017.158.03.C1 - SFP Évora - kitchen remodeling | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 03-10-2019 | 23-10-2020 | 386 | 180 | 234000 | 225800 | 1 | 243130.28 | -17330.28 | 92.872 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | objective modification of the contract | underwork and additional work
1303 | 6448457 | Vouga Line - Contract for Structural Rehabilitation and anti-corrosion protection of metal bridges | 45221119-9 | Bridge renewal construction work | FALSE | 2019 | 2021 | Portugal | Oliveira de Azemeis | Aveiro | 1 | 33 | 24-03-2020 | 05-11-2021 | 591 | 270 | 700000 | 630618.66 | 2 | 631043.23 | -424.57 | 99.9327 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A
1304 | 6444668 | Contract for the Requalification of Public Spaces in the Calouste Gulbenkian Neighborhood, in Paredes. | 45233160-8 | Paths and other metalled surfaces | TRUE | 2020 | 2021 | Portugal | Alenquer | Lisboa | 11 | 14 | 20-03-2020 | 11-03-2021 | 356 | 180 | 335241.38 | 323449.38 | 2 | 287549.45 | 35899.93 | 112.4848 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the project before starting was suspended due to covid-19 | there were additional works due to project measurement errors and there was underwork since the route of the sidewalk was changed (pedestrian access) following the demolition of the boundary wall of the damião de goes secondary school, an option taken by the client.
1305 | 6442636 | Construction of a car park in the Cássima area in Loulé | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 21 | 30-12-2019 | 05-03-2021 | 431 | 240 | 460000 | 434611.93 | 2 | 434611.93 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | failure by the supplier to deliver the material on time.
1306 | 6442105 | 2019-CPUB-EMP-404 contract for the 2nd phase of promoting accessibility and pedestrian safety at crossings, in the parish of Arroios | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 30 | 02-03-2020 | 17-12-2020 | 290 | 120 | 146922 | 134089.3 | 1 | 147428.12 | -13338.82 | 90.9523 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary works art 370 of the "public procurement code"
1307 | 6440303 | Requalification of the streets of Amieira do Tejo | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Nisa | Portalegre | 12 | 18 | 18-03-2020 | 29-09-2021 | 560 | 180 | 251404.25 | 245998.05 | 1 | 245998.05 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of price revision indices.
1308 | 6434084 | Public tender for the rehabilitation works of social housing buildings at Quinta da Alâmpada - lot 1 to lot 7 - energy efficiency | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 02-03-2020 | 29-06-2021 | 484 | 150 | 345000 | 341108.64 | 2 | 341108.64 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal / execution period Weighting: 50% Criterion related to cost Name: Proposed price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contract work.
1309 | 6429042 | Contract 08/dhru/2019 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Sintra | Lisboa | 11 | 14 | 10-03-2020 | 18-03-2021 | 373 | 300 | 188675.44 | 162500 | 1 | 162500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | receipt of the project in advance by one day
1310 | 6428724 | Improvement and Rectification of Access to Vilela, Moreira de Rei - Fafe | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2021 | Portugal | Fafe | Braga | 3 | 30 | 09-03-2020 | 08-07-2021 | 486 | 150 | 107257.04 | 105883.46 | 1 | 117618.87 | -11735.41 | 90.0225 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 60% Criterion related to cost Name: Valia Técnica and guarantee of the proposal Weighting: 40% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a suspension of work | there was complementary work and underwork
1311 | 6428655 | Construction of Pedestrian Areas at the West Entrance of Alter do Chão | 45112700-2 | Landscaping work | TRUE | 2019 | 2021 | Portugal | Alter do Chão | Portalegre | 12 | 24 | 27-02-2020 | 31-03-2021 | 398 | 120 | 147023.15 | 112825 | 1 | 112825 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Proposal cost Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate conditions. | price review pursuant to article 382 of the "public procurement code".
1312 | 6427157 | Execution contract for several sections of cycle paths of the Structuring Network of the Municipality of Cascais | 45233162-2 | Cycle path construction work | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 21 | 14-02-2020 | 01-06-2021 | 473 | 105 | 2355122.67 | 483798.23 | 2 | 531327.67 | -47529.44 | 91.0546 | Best value for money: Yes Criterion related to quality Name: Deadline (40%) and Quality of the Technical Team (10%) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | extension in order to cause minor inconvenience to citizens.
1313 | 6423766 | Conservation / Maintenance of Olhos da Fervença River Beach, by Contract: Rehabilitation of walkways, walls and palisades - CP-CCP-EMP n.º 02/2020 | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2020 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 9 | 16-03-2020 | 25-09-2020 | 193 | 75 | 75000 | 73388 | 1 | 73388 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
1314 | 6423715 | Contract for the "Southern Line - Repair of Reinforced Concrete in the Pragal Tunnel". (EContracts No. 5010042045) | 45221248-2 | Tunnel linings construction work | FALSE | 2019 | 2021 | Portugal | Almada | Setúbal | 17 | 8 | 16-03-2020 | 20-08-2021 | 522 | 180 | 300000 | 249449.72 | 1 | 249449.72 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A
1315 | 6423670 | Construction of Bike Paths in the Municipality, by Contract: Execution of walls on the Pocariça road - CP-CCP-EMP n.º 01/2020 | 45113000-2 | Siteworks | FALSE | 2020 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 12 | 16-03-2020 | 20-10-2020 | 218 | 60 | 72515 | 68432.8 | 1 | 65542 | 2890.8 | 104.4106 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underwork.
1316 | 6422659 | Refurbishment of the gravity conduit Ericeira - Foz do Lizandro, on the ER247 | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2020 | Portugal | Mafra | Lisboa | 11 | 15 | 18-02-2020 | 11-12-2020 | 297 | 180 | 191000 | 175204.1 | 1 | 175204.1 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 30% Criterion related to cost Name: Global proposal price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | greater efficiency in carrying out work than expected
1317 | 6421211 | Cp nº 84/2019 - supply and installation of emergency stairs | 45220000-5 | Engineering works and construction works | TRUE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 22 | 14-02-2020 | 07-05-2020 | 83 | 70 | 50000 | 49850 | 1 | 49850 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: VALIA TECNICA Weighting: 50% Criterion related to cost Name: GLOBAL PROPOSAL PRICE Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unforeseen reasons | unforeseen reasons
1318 | 6420359 | Execution of inclusive accessibility - requalification of Avenida Infante Dom Pedro - Alverca do Ribatejo - Phase 1 | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 22 | 22-01-2020 | 26-02-2021 | 401 | 120 | 718900 | 618259.96 | 2 | 624741.75 | -6481.79 | 98.9625 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change of completion date of the project | short work approval and price review
1319 | 6419434 | Execution of Walks on Ladeira da Granja, in Ançã, by Contract - CP-CCP-EMP n.º 04/2020 | 45113000-2 | Siteworks | FALSE | 2020 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 12 | 13-03-2020 | 20-09-2021 | 556 | 180 | 105000 | 99950.02 | 1 | 109889.94 | -9939.92 | 90.9547 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works.
1320 | 6419316 | Contract for the execution of water supply lines. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 11-03-2020 | 04-06-2020 | 85 | 90 | 38165 | 31450 | 1 | 31450 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | no change | no change
1321 | 6419203 | AR021 E1 - Lordelo Interceptor - Cosme Portelinha. | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2020 | Portugal | Paredes | Porto | 13 | 22 | 03-02-2020 | 22-12-2020 | 323 | 180 | 400000 | 332995.2 | 2 | 332546.34 | 448.86 | 100.135 | Best value for money: Yes Criterion related to quality Name: - Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulties in carrying out the project due to the existence of a large volume of hard rock, difficult to disassemble and delay in the supply of certain materials due to the current situation of the covid-19 pandemic | there was no need to carry out all contractual work
1322 | 6418981 | The purpose of the contract is to carry out various works in terms of basic sanitation networks, as well as water distribution networks in municipal buildings and the municipal school park. | 45232452-5 | Drainage works | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 27-02-2020 | 24-08-2021 | 544 | 560 | 181746.95 | 163572.27 | 1 | 163572.27 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early organization of the project and ease of response to orders for materials.
1323 | 6418790 | The purpose of the contract is to carry out various stabilization works for earth support structures in various locations in the Municipality. | 45262310-7 | Reinforced-concrete work | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 27-02-2020 | 29-09-2021 | 580 | 560 | 188521.04 | 169668.95 | 1 | 169668.95 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | good organization and management of work. fast acting teams. timely delivery of materials.
1324 | 6416508 | Land modeling, execution of small walls for the vegetable gardens, execution of a fence in the entrance area, installation of a water supply network, rainwater network, public lighting network | 45112711-2 | Landscaping work for parks | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 02-03-2020 | 31-05-2021 | 455 | 180 | 218000 | 189890 | 1 | 197242.4 | -7352.4 | 96.2724 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | assigned 30 days as deadline for execution of complementary works. note: there was a delay in scheduling the inspection (provisional reception), as the last measurement report was dated 11.27.2020. | - additional contract signed on 10/14/2020: additional work = €32,605.32 and underwork €19,640.53; - addendum dated 08.01.2021 - underwork = €5,612.39.
1325 | 6416215 | Construction of the Municipal Warehouse Wall | 45262310-7 | Reinforced-concrete work | FALSE | 2019 | 2021 | Portugal | Penamacor | Castelo Branco | 5 | 6 | 24-02-2020 | 19-11-2021 | 634 | 45 | 66644.93 | 64599.2 | 1 | 79383.93 | -14784.73 | 81.3757 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension approved by deliberation of 04/28/2020. and extension relating to complementary work. | additional work resulting from unforeseen circumstances: €6,453.84; additional work due to unforeseen circumstances: €9,560.68; underwork: €1,989.44; price review: €759.66.
1326 | 6414924 | Contract for the rehabilitation of the lighting systems of the University of Lisbon buildings, for the following batch: - LOT 2 - Contract for the rehabilitation of the lighting systems of the Faculty | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 11-03-2020 | 22-02-2021 | 348 | 204 | 303200 | 69873 | 1 | 69873 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Overall efficiency or luminous yield of LED lamps+Warranty period of equipment Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | addendum to contract no. 20in10060013: due to the emergence of the covid-19 pandemic, the consequent declaration of a state of emergency in the country, in the period between march 19, 2020 and may 2, 2020, and the set of measures adopted by the faculty of letters of the university of lisbon within the scope of the contingency plan (namely with the decision to temporarily close some buildings, placing employees in telework, and keeping some buildings open with serious restrictions in terms of the number of users), no it was possible, under the terms foreseen in the contract in conjunction with articles 356.º and 359.º of the pcc, for the faculty of letters of the university of lisbon to provide lux concept – sigmaworld with access to the buildings where the projects would be carried out, as well as to carry out to the signing of the consignment notice, within the defined period, which may never exceed 30 days after the date of conclusion of the contract.
1327 | 6407746 | Contract for the rehabilitation of lighting systems for the buildings of the Faculty of Law of the University of Lisbon (2nd phase) | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 27-02-2020 | 23-07-2020 | 147 | 90 | 60000 | 56365.56 | 1 | 60951.25 | -4585.69 | 92.4765 | Best value for money: Yes Criterion related to quality Name: Warranty Factor (Fg) Weighting: 30% Criterion related to cost Name: Price Factor (Fp) Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work was suspended due to the covid-19 pandemic | additional work worth €4585.69
1328 | 6405604 | Contract for civil works to reduce water losses in the Municipality of Póvoa de Lanhoso - Lots 1, 2 and 3. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Póvoa de Lanhoso | Braga | 3 | 24 | 21-02-2020 | 31-03-2021 | 404 | 300 | 284237.02 | 124917.32 | 1 | 120457.43 | 4459.89 | 103.7025 | Best value for money: No Criterion related to quality Name: Technical quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | although work was suspended for 52 days, there were no changes to the project execution deadline. | underwork.
1329 | 6405211 | Contract for civil works to reduce water losses in the Municipality of Póvoa de Lanhoso - Lots 1, 2 and 3. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 24 | 21-02-2020 | 01-10-2020 | 223 | 300 | 284237.02 | 47414.41 | 1 | 39116.24 | 8298.17 | 121.2141 | Best value for money: No Criterion related to quality Name: Technical quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | underwork.
1330 | 6402191 | Urban Regeneration - Requalification of the Area Surrounding Plátano | 45453000-7 | Overhaul and refurbishment work | FALSE | 2020 | 2021 | Portugal | Alijó | Vila Real | 19 | 14 | 03-03-2020 | 16-04-2021 | 409 | 365 | 430583.4 | 425671.8 | 2 | 425671.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the change in the deadline for the project was based on the prior assessment of the court of auditors
1331 | 6401780 | 2019.038.02.C1 - sfp bragança - fifth costume - accessibility | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2020 | Portugal | Bragança | Bragança | 4 | 10 | 16-12-2019 | 29-04-2020 | 135 | 45 | 31500 | 30750 | 1 | 30750 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19
1332 | 6400083 | PO 308/2019 - Reconversion of the street layout on the left bank of the River Vez - Lamela | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 18 | 03-03-2020 | 06-12-2021 | 643 | 180 | 295060 | 283519.81 | 2 | 281356.83 | 2162.98 | 100.7688 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | some project uncertainties, execution of the contract in phases and complementary works did not allow the normal development of the projects of the contract. | some project uncertainties, execution of the contract in phases and complementary works did not allow the normal development of the projects of the contract.
1333 | 6395878 | Social Housing Rehabilitation PER da Outrela | 45321000-3 | Thermal insulation work | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 24 | 21-02-2020 | 11-10-2021 | 598 | 210 | 596332 | 579503.77 | 2 | 595074.5 | -15570.73 | 97.3834 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the execution period of the project was extended by 30 days due to prophylactic isolation (covid-19). | provisional calculation of the price revision in the amount of €15,570.73
1334 | 6395120 | Cascais Line - Anticorrosive Protection of the Jamor Bridge to Pk 9,671 | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 40 | 05-03-2020 | 19-08-2021 | 532 | 180 | 450000 | 371931.32 | 2 | 371931.32 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1335 | 6394838 | PRC_0222/2019 - EB0444 - Extension of the wastewater drainage network in the parish of Mansores (Arouca) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2020 | Portugal | Arouca | Aveiro | 1 | 14 | 06-03-2020 | 11-09-2020 | 189 | 45 | 56000 | 50721.17 | 1 | 50721.17 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the volume of hard rock, higher than estimated in the project; the large amount of unregistered infrastructure. final paving was also slightly delayed due to the intention of the parish council to pave rua de n. sr.ª do rosário to its full width. last-minute steps were taken with the municipality of arouca, an entity that did not accept the request.
1336 | 6394658 | PRC_0221/2019_GAE-EB0443 - Extensions of the Wastewater Drainage Networks in the Parishes of Santa Eulália, Rossas, Burgo and Urrô (Arouca) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2021 | Portugal | Arouca | Aveiro | 1 | 14 | 06-03-2020 | 11-06-2021 | 462 | 180 | 285000 | 278593.14 | 2 | 290320.74 | -11727.6 | 95.9605 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic | objective modification to the contract
1337 | 6389263 | Requalification of Pedestrian Routes in São Pedro do Corval - 2nd Phase | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 26-02-2020 | 08-06-2021 | 468 | 300 | 525000 | 446897.74 | 2 | 446897.74 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the stipulated time frame. | there was no change in the value of the project
1338 | 6387156 | Requalification of accesses to the New Nisa Health Center | 45112700-2 | Landscaping work | FALSE | 2019 | 2020 | Portugal | Nisa | Portalegre | 12 | 30 | 02-09-2019 | 24-09-2020 | 388 | 90 | 149905.96 | 124799.62 | 1 | 124799.62 | 0 | 100 | Best value for money: No Criterion related to quality Name: Not Applicable Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work price review.
1339 | 6386733 | PROCº nº 17/A1/17 - Public Tender for the award of the contract for "Execution E.R. 308 - Km 1+100 - Transformation of junction into roundabout intersection" | 45233128-2 | Roundabout construction work | FALSE | 2017 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 02-03-2020 | 01-03-2021 | 364 | 90 | 280000 | 232364.29 | 1 | 218490.01 | 13874.28 | 106.3501 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the Proposal - 60%; Price - 40%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work had to be suspended due to the pandemic situation, which caused a lack of labour and the fact that adverse weather conditions prevented the carrying out of paving work and the execution of horizontal paintings without interruptions. | fewer services were performed than previously anticipated.
1340 | 6384707 | Official Collection Center for Companion Animals_CRO - Intermunicipal | 45223600-2 | Dog kennels construction work | FALSE | 2019 | 2021 | Portugal | Penedono | Viseu | 20 | 10 | 24-02-2020 | 24-06-2021 | 486 | 180 | 309704.42 | 293702.44 | 2 | 315820.01 | -22117.57 | 92.9968 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | climatic
1341 | 6384457 | Requalification of Children's Parks - EB de Silvares, Paços, Medelo, Montelongo, Moreira de Rei, EB and JI de Quinchães, Centro Escolar de Revelhe and JI de Golães, S. Gens and Travassós - FAFE. | 45212130-6 | Amusement park construction work | FALSE | 2019 | 2020 | Portugal | Fafe | Braga | 3 | 30 | 26-02-2020 | 22-06-2020 | 117 | 30 | 94329 | 82800 | 1 | 82683 | 117 | 100.1415 | Best value for money: Yes Criterion related to quality name: price Weighting: 60% Criterion related to cost Name: technical value and guarantee of the proposal Weighting: 40% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | not all quantities in point 1.2 have been executed.
1342 | 6382623 | Contract for the execution of the infrastructures of the Urban Subdivision of Milagres, parish of Arrifes, municipality of Ponta Delgada (2nd phase) which consists, namely, of work on the road network | 45000000-7 | Construction work | FALSE | 2019 | 2021 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 29 | 26-02-2020 | 28-09-2021 | 580 | 180 | 185813 | 157941.06 | 1 | 151192.12 | 6748.94 | 104.4638 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork worth €151,192.12
1343 | 6382475 | Alteration and expansion of the Torreguia nursery | 45262800-9 | Building extension work | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 24-02-2020 | 12-08-2021 | 535 | 189 | 800000 | 779896.57 | 2 | 779896.57 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | partial suspension - in accordance with paragraph b of article 365 of the "public procurement code".
1344 | 6381819 | Acquisition and Assembly of Containers - Temporary Auction in Costa da Caparica | 45223810-7 | Prefabricated constructions | FALSE | 2019 | 2020 | Portugal | Almada | Setúbal | 17 | 12 | 29-03-2019 | 28-04-2020 | 396 | 25 | 60000 | 51960 | 1 | 59995 | -8035 | 86.6072 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works (additional to the contract)
1345 | 6379496 | Urban Regeneration of the Maria de Fátima District - Sabrosa | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Sabrosa | Vila Real | 19 | 15 | 10-02-2020 | 28-10-2021 | 626 | 365 | 311940.87 | 308526.63 | 2 | 338627.57 | -30100.94 | 91.1109 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work started with the consignment date. | the sum of overworks, underworks and price revisions.
1346 | 6378466 | Cp 12/2017 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Guimarães | Braga | 3 | 20 | 20-12-2017 | 27-02-2020 | 799 | 540 | 265000 | 199331.37 | 1 | 198280.77 | 1050.6 | 100.5299 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension | underwork
1347 | 6378382 | Improvement of the surroundings along the sé | 45112700-2 | Landscaping work | FALSE | 2019 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 28-02-2020 | 20-08-2021 | 539 | 365 | 327736.3 | 319660.28 | 2 | 314259.83 | 5400.45 | 101.7185 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate causes | works less in the amount of €5,400.45
1348 | 6378056 | Contract for "Improvement in FRP Pipes" | 45453000-7 | Overhaul and refurbishment work | TRUE | 2019 | 2020 | Portugal | Sines | Setúbal | 17 | 20 | 21-02-2020 | 28-10-2020 | 250 | 120 | 240000 | 234354.87 | 1 | 235938.41 | -1583.54 | 99.3288 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Valia Técnica Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension | price review
1349 | 6377966 | Cp 06/2017 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Vizela | Braga | 3 | 20 | 26-05-2017 | 30-12-2019 | 948 | 540 | 265000 | 199926.37 | 1 | 199909.28 | 17.09 | 100.0085 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension | works less
1350 | 6376521 | Improvement and requalification of municipal housing buildings - Rebordões | 45321000-3 | Thermal insulation work | FALSE | 2019 | 2021 | Portugal | Santo Tirso | Porto | 13 | 22 | 28-02-2020 | 14-07-2021 | 502 | 210 | 355130 | 309630 | 2 | 328680 | -19050 | 94.2041 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the existence of complementary work and suspension of work for the purpose of redefining the project. | the existence of complementary work and underwork.
1351 | 6376399 | Cp 05/2018 – execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Vizela | Braga | 3 | 14 | 16-07-2018 | 27-02-2020 | 591 | 365 | 276500 | 199982.45 | 1 | 199781.65 | 200.8 | 100.1005 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | extension | works less
1352 | 6375967 | AA014-E1 Construction of the new Ramalde-Pedrouços pipeline. Rehabilitation-phase1. | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2019 | 2021 | Portugal | Gondomar | Porto | 13 | 21 | 11-11-2019 | 04-05-2021 | 540 | 180 | 1000000 | 965025.85 | 2 | 873370.66 | 91655.19 | 110.4944 | Best value for money: No Criterion related to quality Name: - Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | alterations/definitions in the execution project / objective modification of the contract / delays in deliveries from the performing entity's suppliers / execution of complementary work/covid 19/ incompatibilities between the execution project and the registration of existing infrastructures. | execution of complementary works / removal of works / alteration of the layout referring to volume 2 by pass, and volume 3 discharge collector.
1353 | 6373765 | Contract "replacement of the fiber cement covering of the elementary school eb1 nº2 of the lavradio" | 45261213-0 | Metal roof-covering work | FALSE | 2019 | 2020 | Portugal | Barreiro | Setúbal | 17 | 20 | 10-05-2019 | 28-02-2020 | 294 | 75 | 235000 | 219961.73 | 1 | 240221.98 | -20260.25 | 91.566 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions and partial receptions | additional work and underwork
1354 | 6371044 | Refurbishment of the water network next to Praça Nª Sª dos Navegantes in Costa de Caparica | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2021 | Portugal | Almada | Setúbal | 17 | 20 | 16-10-2018 | 26-01-2021 | 833 | 180 | 217000 | 168903.04 | 1 | 173423.35 | -4520.31 | 97.3935 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the period of execution, under the terms of article 362, nº 1, begins with the act that takes place later between the consignment of the projects and the approval of the dpss, as expressed in the article: "the period of execution of the project begins to count - the date of completion of the total assignment or the first partial assignment or the date on which the owner of the project communicates to the contractor the approval of the safety and health plan, under the terms provided for by law, if the latter date is later". | complementary work was carried out that changed the value of the project, which also had a price review
1355 | 6369695 | Conduct of water distribution in the village of the future | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Grandola | Setúbal | 17 | 30 | 16-01-2020 | 23-03-2021 | 432 | 90 | 75737.51 | 69900 | 1 | 76798.8 | -6898.8 | 91.017 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: THE AWARD WILL BE MADE ACCORDING TO THE CRITERIA OF THE MOST ECONOMICALLY ADVANTAGEOUS PROPOSAL Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to complementary works and limitations caused by the covid-19 pandemic | during the project, it was verified to replace the existing pad with a new one
1356 | 6369433 | Reinforcement of the Earth Support Wall at the Vila das Aves Cemetery. | 45223200-8 | Structural works | FALSE | 2019 | 2020 | Portugal | Santo Tirso | Porto | 13 | 21 | 18-02-2020 | 19-10-2020 | 244 | 120 | 133136.5 | 118697 | 1 | 154997.31 | -36300.31 | 76.58 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost name: price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the granting of a graceful extension of 47 days and the existence of complementary work with an extension of 72 days. | the need to carry out additional work during the course of the project.
1357 | 6368694 | Improvement and requalification of municipal housing buildings - S. Tomé de Negrelos | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2021 | Portugal | Santo Tirso | Porto | 13 | 14 | 09-12-2019 | 28-07-2021 | 597 | 240 | 326614 | 289149.5 | 2 | 288229.5 | 920 | 100.3192 | Best value for money: Yes Criterion related to quality Name: Technical value, safety, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the existence of complementary works. | the existence of extra work and underwork.
1358 | 6363067 | Expansion and requalification of the Escola Básica da Lage - Vilarinho | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2019 | 2021 | Portugal | Santo Tirso | Porto | 13 | 21 | 19-02-2020 | 11-05-2021 | 447 | 120 | 300000 | 292514.45 | 2 | 300860.99 | -8346.54 | 97.2258 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | during the course of the project, a graceful extension of 150 days was granted for the execution of the projects. | the existence of additional work as well as underwork.
1359 | 6362962 | Improvement of the Football Field of Refojos | 45236119-7 | Repair work on sports fields | FALSE | 2019 | 2020 | Portugal | Santo Tirso | Porto | 13 | 22 | 10-02-2020 | 31-08-2020 | 203 | 120 | 275500 | 263383.65 | 2 | 263606.85 | -223.2 | 99.9153 | Best value for money: Yes Criterion related to quality Name: Technical value, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the existence of more works
1360 | 6359312 | Refurbishment of the Esperança 1st cycle of elementary education school - Parish of Várzea, Aliviada and Folhada | 45453000-7 | Overhaul and refurbishment work | TRUE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 17-02-2020 | 20-10-2020 | 246 | 120 | 185793.04 | 179685.18 | 1 | 179685.18 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended
1361 | 6358738 | Execution of event power supply branch at Parque João Paulo II | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Vila do Conde | Porto | 13 | 15 | 17-01-2020 | 17-06-2020 | 152 | 60 | 35000 | 32700 | 1 | 31985.78 | 714.22 | 102.2329 | Best value for money: No Criterion related to quality Name: _ Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1362 | 6353276 | The object of the contract is the execution of horizontal road signs, especially parking markings, covering the geographical area of ​​the municipality of Amadora | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 17-02-2020 | 21-06-2021 | 490 | 560 | 188625 | 188000 | 1 | 188764.05 | -764.05 | 99.5952 | Best value for money: Yes Criterion related to quality Name: Quantity of work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion was anticipated due to weather conditions being very favorable for the application of paints with specific chemical components. the profitability of the teams was higher than estimated because they were not conditioned to weather conditions, namely rain. rain, humidity and heat influence the carrying out of the parking demarcation work. | due to the final price revision in the amount of €764.05, an addendum was made to the project bill on 01/19/2022.
1363 | 6352764 | 100% Quality - Repaving of Avenida Dr. Fernando Aroso in Leça da Palmeira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 2 | 18-02-2020 | 02-09-2020 | 197 | 180 | 425000 | 318487.16 | 2 | 348638.1 | -30150.94 | 91.3518 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
1364 | 6352066 | 14-Emp/19 - Contract for requalification of the Cachopo Iron Fountain | 45112710-5 | Landscaping work for green areas | FALSE | 2019 | 2021 | Portugal | Tavira | Faro | 8 | 10 | 13-02-2020 | 03-09-2021 | 568 | 180 | 159190.44 | 158713.85 | 1 | 158713.85 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | delivery of the technical compilation
1365 | 6348758 | bonfim Ciprestes emissary | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Setúbal | Setúbal | 17 | 30 | 10-11-2017 | 26-09-2019 | 685 | 240 | 668924.63 | 609481.1 | 2 | 609481.08 | 0.02 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension: 39 days for the random dispersal of buried and unregistered infrastructure and 60 days for the simultaneous execution of another contract (central separator on avenida 22 de novembro) | final account rounding
1366 | 6343150 | Project and Improvement of the Covered Municipal Swimming Pool | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2019 | 2021 | Portugal | Mogadouro | Bragança | 4 | 30 | 14-02-2020 | 19-11-2021 | 644 | 180 | 263320.47 | 239948.5 | 1 | 333537.87 | -93589.37 | 71.9404 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Economically Most Advantageous Proposal Criterion-Article 74.º, n.1, subparagraph b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | state of emergency, allegedly non-timely delivery of materials by the supplier and completion of complementary works | performance of complementary work resulting from unforeseen circumstances
1367 | 6337107 | Rehabilitation of streets anta Casa da Misericórdia - PARU do Marco de Canaveses | 45220000-5 | Engineering works and construction works | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 27-01-2020 | 11-11-2020 | 289 | 150 | 250702.35 | 211505.81 | 1 | 208036.42 | 3469.39 | 101.6677 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of term | underwork
1368 | 6336406 | Contract for the Comporta Interceptor System | 45232431-2 | Wastewater pumping station | FALSE | 2019 | 2021 | Portugal | Alcácer do Sal | Setúbal | 17 | 45 | 15-10-2019 | 30-11-2021 | 777 | 275 | 1050000 | 839854.47 | 2 | 839618 | 236.47 | 100.0282 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work execution fixes | two causes were identified for the variation in forecast quantities compared to those actually executed, namely:  elimination of constraints arising during the execution of the contract  optimization of the solutions recommended in the project once the construction of the waste water pumping station was completed, where the solution is installed that allows pre-treatment of the local effluents, and with the comporta wwtp still under construction, it was possible to implement a solution for this infrastructure to come into operation, in order to immediately alleviate existing environmental problems resulting from the lack of wastewater treatment. this solution led to unforeseen complementary work that resulted in an addition to the contract signed on 12/17/2020. as for the project not carried out/underwork, these are specific situations of work that were verified during the contract and were not necessary, such as the lack of archaeological finds, excessive amounts of plaster on walls and ceilings, etc.
1369 | 6332653 | hub paving - October 2019 | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 27-01-2020 | 23-09-2020 | 240 | 180 | 209140.22 | 203842.29 | 1 | 185236.95 | 18605.34 | 110.0441 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time | underwork
1370 | 6332549 | Construction of sanitary facilities in the Tâmega river park | 45332400-7 | Sanitary fixture installation work | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 28-01-2020 | 12-08-2020 | 197 | 90 | 30835.49 | 29305.93 | 1 | 29305.93 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1371 | 6331816 | Light rehabilitation of the Pavilhão Gimnodesportivo de Resende, namely roofing, cladding facades, refurbishment of changing rooms and exterior arrangements. | 45453000-7 | Overhaul and refurbishment work | TRUE | 2019 | 2020 | Portugal | Resende | Viseu | 20 | 14 | 15-04-2019 | 13-02-2020 | 304 | 180 | 349950 | 334245.55 | 2 | 382645.55 | -48400 | 87.3512 | Best value for money: No Criterion related to quality Name: Evaluation of the price or cost as the only aspect of the execution of the contract to be concluded. Weighting: 100% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed before the end of the contractually established period. | there were complementary works
1372 | 6329507 | Paving of streets in Alcaria Ruiva | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Mértola | Beja | 2 | 30 | 15-01-2020 | 07-05-2021 | 478 | 240 | 304469.26 | 274305.6 | 2 | 272955.61 | 1349.99 | 100.4946 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | underwork.
1373 | 6326849 | L..Cintura - Contract to rehabilitate the pavement of passenger platforms and accesses to Roma-Areeiro station | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 20 | 06-02-2020 | 20-07-2021 | 530 | 210 | 345000 | 344166 | 2 | 390716.07 | -46550.07 | 88.086 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 60% Criterion related to cost Name: Technical Valia Weighting: 40% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1374 | 6326632 | Public Tender for the requalification contract for the road connecting the E.N.270 to Fonte de Paderne, in Cerca Velha. | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 10-02-2020 | 27-07-2020 | 168 | 30 | 98700 | 97673.3 | 1 | 90698.72 | 6974.58 | 107.6898 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
1375 | 6325196 | Construction of the Community Music School of Bitarães | 45262700-8 | Building alteration work | FALSE | 2017 | 2021 | Portugal | Paredes | Porto | 13 | 20 | 05-12-2019 | 03-05-2021 | 515 | 365 | 334000 | 299876.9 | 2 | 288180.26 | 11696.64 | 104.0588 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work stoppage to carry out another electrical infrastructure procedure
1376 | 6321867 | Cp 25/2018 – rehabilitation and reinforcement of the frades reservoir – cell 1 and 2, union of parishes of s. Miguel and S. João – municipality of vizela | 45220000-5 | Engineering works and construction works | FALSE | N/A | 2019 | Portugal | Vizela | Braga | 3 | N/A | 14-01-2019 | 03-05-2019 | 109 | 90 | N/A | 69988.26 | 1 | 69988.26 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension
1377 | 6321323 | Requalification and Enhancement of the Old Baths of Castelo de Vide for the Garcia de Orta Interpretation Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2019 | 2020 | Portugal | Castelo de Vide | Portalegre | 12 | 30 | 16-01-2020 | 04-11-2020 | 293 | 240 | 348981.94 | 346745.78 | 2 | 346745.78 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Proposal Quality Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period of the contract | there was no change in the value of the contract
1378 | 6320793 | Cpn 61/2019/dicp - t-37/2018 - requalification and improvement of equipment and infrastructure in the marachão area - leiria | 45233251-3 | Resurfacing works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 16-10-2019 | 02-03-2020 | 138 | 30 | 28000 | 24608.22 | 1 | 24608.22 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work for security reasons
1379 | 6318622 | Rehabilitation of reborn spaces in the former. Salazar Foundation and streetMilheirós de Poiares | 45212100-7 | Construction work of leisure facilities | FALSE | 2019 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 11-12-2019 | 05-03-2021 | 450 | 90 | 84000 | 83262.78 | 1 | 83262.78 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | verification of the need to study changes to the project, in addition to the pandemic factor
1380 | 6314313 | PRC_0252/2019_GAE-EB0437 - Construction of the Tapada and Gove Wastewater Drainage Network (Baião) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2021 | Portugal | Baião | Porto | 13 | 14 | 07-02-2020 | 25-01-2021 | 353 | 120 | 215000 | 214992.84 | 1 | 203842.07 | 11150.77 | 105.4703 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the aforementioned | errors and omissions supply works worth 5,033.20 euros. in this sense there was no need to carry out all contractual work.
1381 | 6314050 | Cp 08/2018 – application of reflective films on glass surfaces of the head office building of vimágua eim, sa – municipality of guimarães | 45261400-8 | Sheeting work | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 28-09-2018 | 14-05-2019 | 228 | 30 | 16000 | 9600 | 1 | 9600 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension
1382 | 6312715 | Requalification of the Residential Structure for the Elderly, IPSS - Alcanena Social Welfare Center | 45000000-7 | Construction work | FALSE | 2019 | 2021 | Portugal | Alcanena | Santarém | 16 | 31 | 04-02-2020 | 29-11-2021 | 664 | 480 | 642734.61 | 639312.57 | 2 | 660920.33 | -21607.76 | 96.7307 | Best value for money: No Criterion related to quality Name: We don't have Weighting: 0% Criterion related to cost Name: lowest price Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the expected time frame. | the project increased its total contracted price due to the price review. materials are rising in price reaching record highs. it was the only budget slippage in the project.
1383 | 6312535 | Alteration of an existing building, called the Multipurpose Hall, for the installation of a common kitchen and construction of a support building for storage | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2021 | Portugal | Penafiel | Porto | 13 | 14 | 24-01-2020 | 23-06-2021 | 516 | 365 | 500140.33 | 447800 | 2 | 447800 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid19 pandemic
1384 | 6312488 | Cp 05/2015 - extensions of water supply and wastewater drainage networks in zone 1 - 2nd phase - fermentations and pumping system in the neighborhood of s. José - parish of Ponte | 45232411-6 | Foul-water piping construction work | FALSE | 2015 | 2019 | Portugal | Guimarães | Braga | 3 | 20 | 07-09-2015 | 28-02-2019 | 1270 | 120 | 197440.5 | 180648.8 | 1 | 150914.13 | 29734.67 | 119.703 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension | underwork
1385 | 6309820 | The object of this contract is the execution of various waterproofing and painting works in municipal buildings and the municipal school park. | 45261420-4 | Waterproofing work | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 21 | 29-01-2020 | 21-12-2020 | 327 | 560 | 150800 | 135720.01 | 1 | 135720.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the anticipation of the conclusion of the contract by 298 days was due, on the one hand, to an increase in needs in relation to what was initially foreseen and, on the other hand, to the fact that schools and kindergartens were closed for a long period of time as a result of the pandemic. , which made it possible to anticipate planned interventions for school interruptions.
1386 | 6308001 | Requalification of Accesses and Public Space Adjacent to Neighborhood PER - Vale da Amoreira | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Moita | Setúbal | 17 | 36 | 23-01-2020 | 02-10-2020 | 253 | 120 | 220000 | 219641.5 | 1 | 219641.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1387 | 6306452 | Bairro 1.º de Maio - Urban Requalification | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Valpaços | Vila Real | 19 | 15 | 05-02-2020 | 15-03-2021 | 404 | 180 | 467983.92 | 467289 | 2 | 491379 | -24090 | 95.0975 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works
1388 | 6297518 | Renovation of the water supply network at streetTorcato José Clavine and streetGalileu Saúde Correia - Pragal | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2020 | Portugal | Almada | Setúbal | 17 | 31 | 02-05-2019 | 30-01-2020 | 273 | 120 | 85000 | 74435.93 | 1 | 74435.93 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1389 | 6297216 | Contract for the Repair of Electrical Infrastructures in the Port of Figueira da Foz | 45241600-4 | Installation of port lighting equipment | TRUE | 2019 | 2020 | Portugal | Figueira da Foz | Coimbra | 6 | 27 | 08-01-2020 | 16-10-2020 | 282 | 90 | 240000 | 141739.16 | 1 | 141739.16 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project ended in the actual period of 146 days. the days after the end of the period were due to the suspension of the period and for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective provisional acceptance certificate.
1390 | 6296819 | Multipurpose space construction - Eiró - Soalhães | 45212100-7 | Construction work of leisure facilities | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 29-01-2020 | 11-11-2020 | 287 | 120 | 282449.45 | 282446.44 | 2 | 280882.16 | 1564.28 | 100.5569 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended and suspended. | underwork worth € 1,564.28
1391 | 6295705 | Business reception area of ​​gafanha de aquém | 45211360-0 | Urban development construction work | FALSE | 2019 | 2021 | Portugal | Ílhavo | Aveiro | 1 | 30 | 24-10-2019 | 14-07-2021 | 629 | 304 | 582526.05 | 457194.61 | 2 | 455520.93 | 1673.68 | 100.3674 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | approval of specialty projects and execution of connections to existing infrastructures and respective tests. | underwork and price revision.
1392 | 6295546 | Requalification of Social Housing - Bairro Dr. Pedro guimaraes | 45262700-8 | Building alteration work | FALSE | 2019 | 2021 | Portugal | Vagos | Aveiro | 1 | 18 | 28-01-2020 | 22-03-2021 | 419 | 240 | 490000 | 457770.02 | 2 | 464105.06 | -6335.04 | 98.635 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary work resulting from unforeseen circumstances - under the responsibility of the client
1393 | 6291850 | 2019.517.02.C1 - IEFP SC in Xabregas - preparation of the ICT room for the Call Center | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 10 | 03-12-2019 | 18-03-2020 | 106 | 30 | 30000 | 28850 | 1 | 28850 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1394 | 6290999 | Requalification works of the public space in the neighborhood of Alvoraçães | 45112700-2 | Landscaping work | FALSE | 2019 | 2021 | Portugal | Lamego | Viseu | 20 | 16 | 31-01-2020 | 03-11-2021 | 642 | 330 | 548380.19 | 541052.95 | 2 | 511114.39 | 29938.56 | 105.8575 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension and complementary work | over and underwork
1395 | 6290467 | Contract " Structural Repair of the Albergaria Tunnel on the North Line " eContracts No. 5010041279) | 45221248-2 | Tunnel linings construction work | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 30 | 10-01-2020 | 06-09-2021 | 605 | 270 | 500000 | 491025 | 2 | 502806.65 | -11781.65 | 97.6568 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation of the execution period of the project of 9 days
1396 | 6289677 | Quality 100% - Alteration of the cycle route on the Tv.Areal/R section. Of the mills - agudela | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 30-01-2020 | 22-04-2020 | 83 | 30 | 20600 | 14664 | 1 | 14664 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1397 | 6288348 | Rehabilitation of the Municipal Market of Cantanhede, by Contract: Execution of coverage, improvement of the facade, accessibilities and sanitary facilities - CP-CCP-EMP n.º 14/2019 | 45213141-3 | Covered market construction work | FALSE | 2019 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 20 | 04-02-2020 | 19-02-2021 | 381 | 120 | 189983.3 | 187972.38 | 1 | 206597.88 | -18625.5 | 90.9847 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of complementary works.
1398 | 6288115 | CP No. 106/2019 - Miscellaneous Arrangements per Contract - Requalification of the Entrance Zone of the Urban Gardens of Várzea - ​​Tavarede | 45112710-5 | Landscaping work for green areas | FALSE | 2019 | 2020 | Portugal | Figueira da Foz | Coimbra | 6 | 14 | 16-01-2020 | 18-08-2020 | 215 | 60 | 15175.63 | 15175.63 | 1 | 15490.63 | -315 | 97.9665 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | due to the covid 19 pandemic | due to additional work not foreseen in the project
1399 | 6286907 | Procº 80/eop/dcop/2019 - rainwater drainage of São Pedro Avenue, Monte Estoril, union of the parishes of Cascais and Estoril | 45111000-8, 45233200-1, 45100000-8, 45232130-2 | Demolition, site preparation and clearance work, Various surface works, Site preparation work, Storm-water piping construction work | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | N/A | 30-01-2020 | 05-01-2021 | 341 | 150 | 299000 | 286945.97 | 2 | 286945.97 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 1 | FALSE | N/A | N/A | N/A | N/A | N/A | pandemic
1400 | 6285551 | Improvement of the Porcas Bridge dam on the Côja River | 45247220-8 | Weir construction work | FALSE | 2019 | 2021 | Portugal | Penalva do Castelo | Viseu | 20 | 15 | 30-01-2020 | 15-02-2021 | 382 | 365 | 80031.5 | 63863.14 | 1 | 70248.48 | -6385.34 | 90.9104 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | complementary works
1401 | 6284479 | Refurbishment work on the Archives of the Directorate of the Housing Park of Domus Social located in the Municipal Offices of Monte dos Burgos | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Porto | Porto | 13 | 21 | 27-01-2020 | 26-03-2021 | 424 | 100 | 180000 | 159390.85 | 1 | 158561.27 | 829.58 | 100.5232 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out in accordance with the contractual provisions, although with a delay of 58 days in relation to the foreseen period, resulting in pecuniary contractual sanctions. | complementary and unforeseen work
1402 | 6283359 | Oe-cp nº 8/2019 "paving the road from porto novo to cancelo" | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2021 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 24-01-2020 | 30-03-2021 | 431 | 60 | 319728.5 | 254811.65 | 2 | 254811.65 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A
1403 | 6282136 | Building rehabilitation for the installation of the popular university of Ferreira do Alentejo | 45454000-4 | Restructuring work | FALSE | 2019 | 2021 | Portugal | Ferreira do Alentejo | Beja | 2 | 7 | 12-12-2019 | 22-11-2021 | 711 | 150 | 200000 | 167702.07 | 1 | 168929.85 | -1227.78 | 99.2732 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | 1 - covid 19 pandemic 2 - complementary works | additional work due to design errors and omissions and underwork due to design measurement errors.
1404 | 6281918 | Cp 12/2018 - Milling and replacement of pavements in interventions at Vimágua, in the municipalities of Guimarães and Vizela | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 23-10-2018 | 04-07-2019 | 254 | 365 | 74535 | 73350 | 1 | 73350 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | urgency
1405 | 6277502 | Construction / Improvement Machinery and Vehicle Park Building / Shipyards - 2nd Phase, by Contract: Repair of damage caused by Leslie - CP-CCP-EMP n.º 12/2019 | 45261213-0 | Metal roof-covering work | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 19 | 31-01-2020 | 25-06-2020 | 146 | 30 | 23736 | 23650 | 1 | 21650 | 2000 | 109.2379 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of underworks.
1406 | 6276720 | Cp 24/2018 – Enhancement of the Leather River and Selho River – Elimination of undue connections between wastewater and rainwater drainage networks in various locations in the urban area of ​​Guimarães | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 05-12-2018 | 07-08-2019 | 245 | 180 | 184000 | 163901.77 | 1 | 148949.77 | 14952 | 110.0383 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | urgency | underwork
1407 | 6276681 | Contract 312/GEBALIS/2019 - Public Tender for Maintenance and Repair of fires and common areas in Neighborhoods in the North West Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 5 | 30-01-2020 | 29-12-2021 | 699 | 730 | 600000 | 508000 | 2 | 508000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | in accordance.
1408 | 6276458 | Contract for the Expansion/Remodeling of the Arouca Sports Complex - Engine Room -Proc. No. 30/2019 | 45331200-8 | Ventilation and air-conditioning installation work | FALSE | 2019 | 2020 | Portugal | Arouca | Aveiro | 1 | 30 | 31-01-2020 | 29-12-2020 | 333 | 150 | 310021.15 | 264997.58 | 2 | 278424.27 | -13426.69 | 95.1776 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the final self held in october | underwork and additional work
1409 | 6275528 | Repaving of EM 600 from Variz to São Martinho do Peso | 45233220-7 | Surface work for roads | FALSE | 2020 | 2021 | Portugal | Mogadouro | Bragança | 4 | 30 | 24-01-2020 | 02-02-2021 | 375 | 365 | 989840.75 | 879407.77 | 2 | 879407.77 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
1410 | 6269513 | Contract to improve safety conditions in AdVT Infrastructures (GRP Elements) - Alentejo Hub | 45340000-2 | Fencing, railing and safety equipment installation work | FALSE | 2019 | 2021 | Portugal | Crato | Évora | 7 | 48 | 14-01-2020 | 24-03-2021 | 435 | 180 | 200000 | 182913.83 | 1 | 170409.74 | 12504.09 | 107.3377 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the partial provisional acceptance of the project was carried out first for the portalegre area on 10/06/2020 and, subsequently, for the évora area on 12/15/2020. however, as on these dates the contractor did not deliver all the necessary documents, namely the pgrcd, the total provisional reception was only carried out after the delivery of the said document, which happened on 02/11/2021. | underwork worth €12,504.25.
1411 | 6269285 | Rehabilitation of the 25 de Abril Children's Park and the Cruz de Pau Children's Park - Union of the Parishes of Matosinhos and Leça da Palmeira | 45236290-9 | Repair work on recreational areas | FALSE | 2019 | 2021 | Portugal | Matosinhos | Porto | 13 | 21 | 27-01-2020 | 15-02-2021 | 385 | 60 | 77500 | 59474 | 1 | 59474 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1412 | 6268342 | CP No. 98/2019 - Avifauna Observation Center of Lagoas da Vela and Braças - Infrastructure and Surrounding Area | 45422100-2 | Woodwork | FALSE | 2019 | 2021 | Portugal | Figueira da Foz | Coimbra | 6 | 6 | 06-09-2019 | 19-01-2021 | 501 | 365 | 163620 | 136594.28 | 1 | 128788.59 | 7805.69 | 106.0609 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the municipality was in negotiations with the icnf regarding issues of prior cleaning of the intervention area of ​​this contract, not being, for the time being, in the said land with conditions that attest to the safety of people and goods | there was a need to review/adjust some work. in this sense, it was decided to suppress some works worth €6,950.00
1413 | 6267341 | Contract work for "Igreja de São Pedro de Lourosa - arrangements of the surrounding areas - CONCLUSION | 45112700-2 | Landscaping work | FALSE | 2019 | 2021 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 29-01-2020 | 19-11-2021 | 660 | 150 | 90000 | 86164.7 | 1 | 81382.95 | 4781.75 | 105.8756 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | existence of suspensions and extensions | existence of complementary work and underwork
1414 | 6266703 | Contract for the survey and replacement/construction and repair of sidewalks in specific areas of the municipality of Albufeira 2019-2020-2021 | 45233253-7 | Surface work for footpaths | FALSE | 2019 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 29-01-2020 | 15-04-2021 | 442 | 450 | 345000 | 288870 | 2 | 288870 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
1415 | 6266601 | Contract for the Requalification of Avenida 21 de Junho in Lagares da Beira | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 29-01-2020 | 31-08-2020 | 215 | 150 | 227600 | 175993.25 | 1 | 201588.96 | -25595.71 | 87.303 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | sanitation and paving works in the extension of a street, meanwhile integrated in the public domain; extension of a water supply network; replacement of a section of water supply pipe; small works considered essential for the proper execution and exploitation of the project.
1416 | 6241624 | Qualification of the Industrial Zone of Castelo de Vide | 45211360-0 | Urban development construction work | FALSE | 2019 | 2021 | Portugal | Castelo de Vide | Portalegre | 12 | 30 | 21-01-2020 | 31-08-2021 | 588 | 420 | 1111157.04 | 1085704.8 | 3 | 1119128.47 | -33423.67 | 97.0134 | Best value for money: Yes Criterion related to quality Name: Quality of the proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | amount of the provisional price review payable to the contractor
1417 | 6240785 | Improvement of the Town Hall Building - Energy Performance Improvement Works | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2019 | 2021 | Portugal | Penalva do Castelo | Viseu | 20 | 15 | 22-01-2020 | 09-03-2021 | 412 | 180 | 229819.98 | 192474.84 | 1 | 204602.34 | -12127.5 | 94.0726 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension and extension of term | complementary works
1418 | 6238614 | Construction of Floating Piers | 45241100-9 | Quay construction work | FALSE | 2019 | 2020 | Portugal | Tavira | Faro | 8 | 25 | 25-11-2019 | 08-10-2020 | 318 | 178 | 604564 | 569685 | 2 | 569685 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | tidal range
1419 | 6237954 | Arrangements and Tours at the Ilha Parish Headquarters (Requalification of streetPadre Joaquim Moderno) - Proc. No. 59/2019 | 45432110-8 | Floor-laying work | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 21 | 14-11-2019 | 25-10-2021 | 711 | 90 | 85114.5 | 79122.56 | 1 | 71759.05 | 7363.51 | 110.2614 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid 19 pandemic | existence of underworks.
1420 | 6235178 | 1400003/2019 POSEUR Contract for the Supply of Interior Lighting to Hospital do Barreiro | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Barreiro | Setúbal | 17 | 26 | 07-06-2019 | 31-08-2020 | 451 | 120 | 395965 | 395965 | 2 | 354104.29 | 41860.71 | 111.8216 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | interruption due to covid 19 | works less
1421 | 6230639 | Implementation of ZMC's in the water supply network in the Municipality of Vila Verde | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Vila Verde | Braga | 3 | 24 | 16-01-2020 | 19-05-2021 | 489 | 365 | 341000 | 329434.75 | 2 | 329434.75 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1422 | 6223492 | PRC_0492/2019_GAE-AR0510 - Construction contract for the execution of the Laúndos Interceptor - Part A - Bike path (Póvoa de Varzim) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2020 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 16-01-2020 | 30-12-2020 | 349 | 210 | 860000 | 617978.06 | 2 | 660680.43 | -42702.37 | 93.5366 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | appearance of various underground infrastructures that collided with the interceptor route, namely unforeseen and therefore unidentified aqueducts. this situation implied the need to reprofile some sections of the interceptor, including a length of approximately 1500 meters. pipe resulting in greater volumes of excavations and embankments. there were also delays for which the contractor was responsible, mainly due to the pandemic due to covid19, which affects and is transversal to the entire community. | due to an optimization of the route, not all contractual works were carried out, namely manholes and respective covers concerning the connecting sections. however, it was necessary to reshape part of the interceptor, installing it at a depth greater than expected, which led to additional work complementary.
1423 | 6223064 | PRC_0284/2019_GAE-EB0436 - Construction of the Water Supply Network to Lugar de Várzea, Teixeira (Baião) | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2019 | 2021 | Portugal | Baião | Porto | 13 | 14 | 17-01-2020 | 07-05-2021 | 476 | 120 | 150000 | 138500 | 1 | 141613.22 | -3113.22 | 97.8016 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to proceed with the execution of complementary works, to correct project errors and omissions, inseparable from the functioning of the infrastructure. there was a need to wait for the approval of the associated works | there was a need to proceed with the execution of complementary works, to supply project errors and omissions, inseparable from the functioning of the infrastructure
1424 | 6222722 | Expansion Contract for the Poço do Canto Cemetery | 45215400-1 | Cemetery works | FALSE | 2019 | 2021 | Portugal | Meda | Guarda | 9 | 14 | 08-01-2020 | 07-07-2021 | 546 | 180 | 147188.93 | 143121.48 | 1 | 131066.5 | 12054.98 | 109.1976 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the pandemic, covid 19, the project was subject to suspension and deadline extension. | it is due to the adjustment of small adjustments in the quantities of the projects of the project.
1425 | 6222029 | Contract to replace the roof in the Francisco Neves pavilion. | 45261213-0 | Metal roof-covering work | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 03-05-2019 | 12-08-2020 | 467 | 90 | 163994 | 145000 | 1 | 145000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reasons not attributable to the contractor
1426 | 6220771 | Energy efficiency - social housing | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 16-12-2019 | 13-12-2021 | 728 | 360 | 1147421.13 | 559864.2 | 2 | 559864.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal for each lot Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension | price review
1427 | 6220034 | Pedestrian Circuit "Relógio do Sol" access to the Urban Center | 45112700-2 | Landscaping work | FALSE | 2019 | 2021 | Portugal | Lamego | Viseu | 20 | 11 | 09-12-2019 | 30-08-2021 | 630 | 180 | 476300 | 454785.69 | 2 | 444333.24 | 10452.45 | 102.3524 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two graceful extensions | underwork and price revision
1428 | 6216119 | Dimensioning and construction of tensioned structure, lighting system and multimedia projection panel for the Municipal Garden amphitheater | 45223000-6 | Structures construction work | FALSE | 2019 | 2020 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 25-11-2019 | 23-06-2020 | 211 | 70 | 180000 | 169500 | 1 | 169500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: PI - Intervention Proposal Weighting: 30% Criterion related to cost Name: VEP - Economic Value of the Proposal Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the constraints caused by the covid 19 pandemic (state of emergency in the country) | there were no value changes
1429 | 6215413 | Extension of the wastewater network in the oliveiras district - lousal | 45232400-6 | Sewer construction work | FALSE | 2019 | 2021 | Portugal | Grandola | Setúbal | 17 | 21 | 05-12-2019 | 31-05-2021 | 543 | 90 | 28278.14 | 24870.8 | 1 | 24870.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: THE AWARD WILL BE MADE ACCORDING TO THE CRITERIA OF THE MOST ECONOMICALLY ADVANTAGEOUS PROPOSAL Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1430 | 6214649 | Urban Regeneration of Praça da Liberdade | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 13-01-2020 | 08-06-2021 | 512 | 270 | 857433.66 | 834900 | 2 | 872052.23 | -37152.23 | 95.7397 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | accomplishment of complementary works | underwork and price revision amount
1431 | 6212668 | Requalification of streetConselheiro Carvalho and street ofs Parreiras, by Contract - CP-CCP-EMP n.º 09/2019 | 45113000-2 | Siteworks | FALSE | 2019 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 20 | 15-01-2020 | 11-11-2021 | 666 | 300 | 291699.91 | 255270.02 | 2 | 275462.48 | -20192.46 | 92.6696 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
1432 | 6212047 | Pedestrian Corridor to the Health Center | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2020 | Portugal | Castelo de Vide | Portalegre | 12 | 20 | 17-12-2019 | 30-10-2020 | 318 | 180 | 149458.35 | 148701.14 | 1 | 148701.14 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposal Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension for another 60 days due to the pandemic situation in the country, due to the need to implement the contingency plan in the company | there were no changes to the contract value
1433 | 6210788 | Rehabilitation of distribution ducts and home extensions - Portunhos, Pena, Lemede, Cadima and Sanguinheira ZMC | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 30 | 12-05-2016 | 12-09-2019 | 1218 | 540 | 900000 | 566535.18 | 2 | 580311.46 | -13776.28 | 97.6261 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension - weather conditions | works and more and less
1434 | 6208539 | Drainage of Rainwater in the Municipality, by Contract: street of Cancioneiro in Cantanhede - CP-CCP-EMP n.º 11/2019 | 45232452-5 | Drainage works | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 14-01-2020 | 29-06-2020 | 167 | 60 | 39147.32 | 37850 | 1 | 37850 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of underworks.
1435 | 6208525 | Construction / Improvement / Repair of School Buildings (JI / elementary school / CE), by Contract: Requalification of the former Pocariça Primary School in Kindergarten - CP-CCP-EMP n.º 06/2019 | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 32 | 14-01-2020 | 24-11-2020 | 315 | 180 | 62339.83 | 61527.87 | 1 | 64601.67 | -3073.8 | 95.2419 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of more work and underwork.
1436 | 6208514 | Conservation and Improvement of the Praia da Tocha Campsite, by Contract: Execution of the Fire Network - CP-CCP-EMP No. 04/2019 | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 32 | 14-01-2020 | 22-09-2020 | 252 | 60 | 37389.54 | 37058.98 | 1 | 37058.98 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underworks.
1437 | 6208263 | 2019/130 - DGEP - Requalification of streets alette Tavares, Oeiras | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 60 | 06-01-2020 | 12-07-2021 | 553 | 150 | 330172.21 | 325869.08 | 2 | 335472.05 | -9602.97 | 97.1375 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1438 | 6208142 | Contract for the supply and installation of railway telecommunications systems on the Covilhã-Guarda section of the Beira Baixa line | 45234100-7 | Railway construction works | FALSE | 2019 | 2021 | Portugal | Guarda | Castelo Branco | 5 | 22 | 23-12-2019 | 10-11-2021 | 688 | 269 | 715000 | 697255.12 | 2 | 686795.32 | 10459.8 | 101.523 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
1439 | 6207821 | The work includes the replacement of existing road pavements, reformulation/rehabilitation of electricity, telephone, rainwater and other infrastructure networks. | 45233251-3 | Resurfacing works | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 15 | 04-12-2019 | 04-02-2021 | 428 | 150 | 324972.75 | 289560.5 | 2 | 319353.84 | -29793.34 | 90.6707 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allotted 20 days for the execution of the additional contract - additional work. | signing of an additional contract on 9/18/2020: additional work = €44,736.54 and underwork = €12,934.68 celebration of addendum (underwork) in the amount of 10,993.19 approval of the provisional calculation of the price revision in the amount of €7,714.98 approval of the final calculation of the price revision in the amount of €1,269.67
1440 | 6207635 | Contract for the Environmental Recovery of the Old Mining Area of ​​Quinta do Bispo - Phase 1 | 45232420-2 | Sewage work | TRUE | 2019 | 2021 | Portugal | Mangualde | Viseu | 20 | 17 | 06-01-2020 | 07-06-2021 | 518 | 365 | 2700000 | 2499985 | 3 | 2624359.38 | -124374.38 | 95.2608 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A |  | additional 1 - resulting from the acceptance of errors and omissions as well as related to the suppression of works; additional 2 - regarding the approval of works provided for in the initial contract, additional work not provided for in the contract, works of a different kind as others provided but to carried out under different conditions, as well as regarding the deletion of works; additional 3 - relating to work of a different kind or of the same kind as others provided for in the contract but to be carried out under different conditions, namely the improvement and adaptation of the circulation to enhance the functioning of the systems for monitoring the gamma radiation spectrum of water; suppression of contractual work not performed by intervention threshold adjustments
1441 | 6206533 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Caldas de S. Jorge, Escapães and Pigeiros | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 20-12-2019 | 09-10-2020 | 294 | 180 | 279835 | 194061.43 | 1 | 210902.35 | -16840.92 | 92.0148 | Best value for money: No Criterion related to quality Name: Applicable hand Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 14 extension due to complementary work and 6 days for scheduling and carrying out inspections | complementary work
1442 | 6205476 | Construction of a Transfer Station at the Landfill of Vila Fria | 45222100-0 | Waste-treatment plant construction work | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 35 | 09-10-2019 | 14-08-2020 | 310 | 180 | 725000 | 637795.3 | 2 | 650404.69 | -12609.39 | 98.0613 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic | contract modification - complementary work
1443 | 6200723 | Rehabilitation of the Parque Infantil do Jardim do Tabolado | 45236290-9 | Repair work on recreational areas | FALSE | 2019 | 2021 | Portugal | Chaves | Vila Real | 19 | 21 | 07-01-2020 | 07-09-2021 | 609 | 120 | 499437.72 | 449743.67 | 2 | 450319.01 | -575.34 | 99.8722 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work | price revision worth €575.34
1444 | 6195716 | The procedure aims at signing a public works contract whose main purpose is the execution of technical connections to the wastewater subsystems of Celorico da Beira | 45232460-4 | Sanitary works | FALSE | 2019 | 2021 | Portugal | Celorico da Beira | Guarda | 9 | 19 | 20-12-2019 | 06-12-2021 | 717 | 300 | 1200000 | 992742.04 | 2 | 614895.53 | 377846.51 | 161.4489 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of the 30-day period due to the covid-19 pandemic and extension of 21 days based on the availability of new land. | change in the value of the project resulting from suppressed contractual works, contractual works not carried out and price revisions.
1445 | 6193104 | Cp 17/2018 - expansion of the s. bento - vizela | 45247270-3 | Reservoir construction works | FALSE | 2018 | 2019 | Portugal | Vizela | Braga | 3 | 14 | 23-10-2018 | 26-06-2019 | 246 | 120 | 119723 | 114595.69 | 1 | 113641.37 | 954.32 | 100.8398 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | extension | works less
1446 | 6192756 | Live leaves urban park: recreational, support and surrounding areas | 45212100-7 | Construction work of leisure facilities | FALSE | 2019 | 2020 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 20-11-2019 | 30-07-2020 | 253 | 180 | 150000 | 149950 | 1 | 158861.65 | -8911.65 | 94.3903 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work | complementary works
1447 | 6192255 | CP027.DRU.DMEP.2019 (Contract for Public Works for the Pedestrian Overpass on Avenida de Alcabideche) | 45233261-6 | Pedestrian overpass construction work | FALSE | 2019 | 2020 | Portugal | Cascais | Lisboa | 11 | N/A | 31-12-2019 | 18-12-2020 | 353 | 60 | 222828.67 | 222594.47 | 1 | 222594.47 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 4 | FALSE | N/A | N/A | N/A | N/A | FALSE | works completed before the estimated time.
1448 | 6191851 | Public tender for the contract for the rehabilitation of social housing buildings in the Heritage District - Energy Efficiency | 45261215-4 | Solar panel roof-covering work | FALSE | 2019 | 2020 | Portugal | Covilhã | Castelo Branco | 5 | 20 | 06-01-2020 | 15-10-2020 | 283 | 90 | 128000 | 127000 | 1 | 135214.41 | -8214.41 | 93.9249 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal (30%) - execution period (5%) Weighting: 35% Criterion related to cost Name: Proposed price Weighting: 65% | 1 | 65 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unforeseen works.
1449 | 6190711 | Remodeling and improvement of the municipal road network - Repaving of E.M. 540, From the intersection of Paradinha Nova to Calvelhe. | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Bragança | Bragança | 4 | 20 | 08-01-2020 | 24-08-2020 | 229 | 180 | 230000 | 223928 | 1 | 223928 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the covid 19 pandemic.
1450 | 6188770 | Rehabilitation of public space in the Mourisca neighborhood | 45112700-2 | Landscaping work | FALSE | 2019 | 2020 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 13-09-2019 | 29-05-2020 | 259 | 60 | 50000 | 48927.38 | 1 | 48927.38 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1451 | 6187772 | Rehabilitation of seven buildings in the orreiro neighborhood | 45320000-6 | Insulation work | FALSE | 2019 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 15-07-2019 | 01-06-2021 | 687 | 540 | 1820000 | 1478637.18 | 3 | 1511834.24 | -33197.06 | 97.8042 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | 33 days before the contractual deadline | price revision in the amount of €33,197.06
1452 | 6180605 | Repaving of streets and parking lots in various locations in the municipality | 45233142-6 | Road-repair works | TRUE | 2019 | 2020 | Portugal | Almada | Setúbal | 17 | 15 | 16-12-2019 | 22-07-2020 | 219 | 90 | 188000 | 187236.6 | 1 | 187236.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Bid Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1453 | 6178992 | Contract for Requalification/Expansion of the Municipal Cemetery | 45262522-6 | Masonry work | FALSE | 2019 | 2021 | Portugal | Arouca | Aveiro | 1 | 30 | 06-01-2020 | 20-09-2021 | 623 | 150 | 87554.33 | 84034.08 | 1 | 95744.08 | -11710 | 87.7695 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weak development of work due to the constraints caused by the pandemic. | additional work and underwork
1454 | 6169636 | Cp 29/2018 - Extension of water supply networks and wastewater sanitation networks in the parishes of Guardizela, Moreira de Cônegos, S. Torcato | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 19-02-2019 | 30-09-2020 | 589 | 120 | 211000 | 210273.78 | 1 | 205409.2 | 4864.58 | 102.3682 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1455 | 6169453 | Contract for "Improvement of the Municipal Road Network - Caminho da Boavista" | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Olhão | Faro | 8 | 30 | 19-07-2019 | 21-04-2020 | 277 | 120 | 280000 | 252290.31 | 2 | 251590.32 | 699.99 | 100.2782 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for graceful extension | works that have not been performed
1456 | 6169101 | Cp 09/2019 - Milling and replacement of pavements in interventions by Vigua, in the municipalities of Guimarães and Vizela | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Vizela | Braga | 3 | 14 | 06-12-2019 | 03-09-2021 | 637 | 365 | 74535 | 74500 | 1 | 74498.91 | 1.09 | 100.0015 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1457 | 6168796 | Contract for the Rehabilitation of Common Parts and Fractions at streetCasal Monte Leite 25 / EN8 - Malveira | 45453000-7 | Overhaul and refurbishment work | FALSE | N/A | 2020 | Portugal | Mafra | Lisboa | 11 | N/A | 01-02-2019 | 03-11-2020 | 641 | 118 | N/A | 239642.69 | 1 | 271446.89 | -31804.2 | 88.2835 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | execution of additional work resulting from the needs identified during the course of the project. | execution of additional work resulting from the needs identified during the course of the project.
1458 | 6168552 | Contract for installation of air conditioning, replacement of lighting with LED lamps, replacement of window frames and remodeling of cells at the Palace of Justice in Barcelos | 45300000-0 | Building installation work | FALSE | 2019 | 2020 | Portugal | Barcelos | Braga | 3 | 10 | 20-12-2019 | 14-10-2020 | 299 | 150 | 345000 | 328275.96 | 2 | 328275.96 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | delay due to covid 19
1459 | 6167919 | Paving contract for street of Bobeiro 1st phase, parish Taíde | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 30-12-2019 | 20-03-2020 | 81 | 120 | 272912.25 | 207862.4 | 1 | 204736.78 | 3125.62 | 101.5267 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | price review
1460 | 6167835 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Santa Maria de Lamas and Rio Meão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 20-12-2019 | 31-05-2021 | 528 | 180 | 329747 | 245090.68 | 1 | 205379.5 | 39711.18 | 119.3355 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 90 days of legal extension, 172 days of delay in the completion of the project by the contractor | less approved works
1461 | 6167772 | CP 42/2019 - Public Tender for a contract for the rehabilitation and conservation of the road network | 45233222-1 | Paving and asphalting works | TRUE | 2019 | 2021 | Portugal | Vendas Novas | Évora | 7 | 21 | 03-01-2020 | 03-12-2021 | 700 | 120 | 383000 | 340201.18 | 2 | 332486.91 | 7714.27 | 102.3202 | Best value for money: Yes Criterion related to quality Name: Deadline, guarantee of signaling and execution of the contract Weighting: 5% Criterion related to cost Name: lowest price Weighting: 95% | 1 | 95 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | supply of works and complementary works
1462 | 6167691 | Cp 05/2019 – Replacement of the wastewater drainage network at street of Souto and street of Souto de Baixo – Parish of Selho S. Jorge - guimaraes | 45232460-4 | Sanitary works | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 16-07-2019 | 02-09-2020 | 414 | 60 | 76300 | 67821.85 | 1 | 65792.22 | 2029.63 | 103.0849 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1463 | 6167272 | CP 32/DRL/DA/2019 - Construction of infrastructure for the implementation of observation posts at Pico da Cruz and Ponta de São Lourenço | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 15 | 17-10-2019 | 29-01-2020 | 104 | 60 | 130000 | 102600 | 1 | 102600 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: See procedure parts Weighting: 0% Criterion related to cost Name: See procedure parts Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | nothing to say.
1464 | 6163403 | Contract for "Repair of the Roof of the Main Building and of the Automata Room of the Aeration System of the WWTP of Ribeira dos Moinhos" | 45261420-4 | Waterproofing work | TRUE | 2019 | 2020 | Portugal | Sines | Setúbal | 17 | 20 | 31-10-2019 | 10-03-2020 | 131 | 30 | 40000 | 37915 | 1 | 38725 | -810 | 97.9083 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | when the victory was requested for the purposes of provisional acceptance, the owner of the project carried out the respective inspection 30 days from the date of receipt of the said request. | from underwork
1465 | 6162666 | Construction of the Municipal Stadium - Serralharias da Bencada - 3rd Phase | 45223100-7 | Assembly of metal structures | FALSE | 2019 | 2021 | Portugal | Lousada | Porto | 13 | 9 | 19-12-2019 | 12-02-2021 | 421 | 90 | 57235 | 56150.74 | 1 | 56247.82 | -97.08 | 99.8274 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | price review
1466 | 6157710 | Requalification of the elementary school of Lousada Centro - 2nd Phase | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Lousada | Porto | 13 | 9 | 19-12-2019 | 18-12-2020 | 365 | 120 | 97803.26 | 89836.46 | 1 | 72511.26 | 17325.2 | 123.8931 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | covid-19 pandemic situation | underwork
1467 | 6157463 | Construction of the New Bus Terminal | 45213310-9 | Construction work for buildings relating to road transport | FALSE | 2019 | 2021 | Portugal | São Brás de Alportel | Faro | 8 | 30 | 26-09-2019 | 15-04-2021 | 567 | 365 | 500000 | 466191.93 | 2 | 466191.93 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1468 | 6153486 | Improvement of street of Restauração in Boim | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 09-12-2019 | 18-01-2021 | 406 | 150 | 198994.2 | 198822 | 1 | 198822 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | delays in releasing land
1469 | 6153201 | Refurbishment of the Nossa Senhora da Saúde sports complex - S. Paio de Oleiros | 45210000-2 | Building construction work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 23-12-2019 | 01-07-2020 | 191 | 90 | 29532 | 29255.08 | 1 | 26845.33 | 2409.75 | 108.9764 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contractor completes the project before the deadline | additional work and underwork
1470 | 6138874 | Sanitary facilities at Largo da Feira, Santa Eufémia-Freineda (2nd phase) | 45215500-2 | Public conveniences | FALSE | 2019 | 2021 | Portugal | Almeida | Guarda | 9 | 18 | 05-12-2019 | 22-09-2021 | 657 | 240 | 76699.99 | 67467.01 | 1 | 67422.65 | 44.36 | 100.0658 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal in the modality provided for in paragraph b) of paragraph 1 of article 74 of the CC Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work according to the order of the president of the chamber, dated 03/27/2020 | underwork and price revision
1471 | 6134619 | Requalification of c.m. 1208 - Maxial - Abrantes | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2021 | Portugal | Abrantes | Santarém | 16 | 30 | 13-12-2019 | 06-04-2021 | 480 | 90 | 326343.09 | 266811.07 | 2 | 270211.2 | -3400.13 | 98.7417 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register. | addition of the ordinary revision of prices.
1472 | 6134538 | Cpn 53/2019/dicp - t-20/2019 - Improvement of games and playground spaces in pre-school and 1st cycle education establishments in the municipality of Leiria | 45212130-6 | Amusement park construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 28 | 16-10-2019 | 15-05-2020 | 212 | 120 | 260560 | 205240 | 1 | 205240 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A
1473 | 6132686 | Refurbishment of changing rooms and teachers' room - Fiães Municipal Swimming Pools | 45210000-2 | Building construction work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 18-12-2019 | 21-12-2020 | 369 | 60 | 177185.2 | 158763.09 | 1 | 158763.09 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 23 days of extension, 40 days of delay under the responsibility of the contractor and 112 days between the 1st inspection and the provisional acceptance in the correction of defects
1474 | 6132180 | Reconstruction of the outer wall at the Alvito Local Service | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Alvito | Beja | 2 | 14 | 14-10-2019 | 29-01-2020 | 107 | 45 | 20000 | 19456.81 | 1 | 19456.81 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1475 | 6128320 | 2018.116.04.C1 - SFP Setúbal - replacement of PT | 45310000-3 | Electrical installation work | TRUE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 15 | 09-07-2019 | 19-01-2021 | 560 | 120 | 115000 | 96364.7 | 1 | 96364.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (by the owner) by binding determination or relevant recommendation - 304 days
1476 | 6127723 | CP 063/2019 - Execution of the water supply pipeline to Penina | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Portimão | Faro | 8 | 21 | 18-12-2019 | 22-03-2021 | 460 | 45 | 145000 | 134670 | 1 | 135227.57 | -557.57 | 99.5877 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to covid 19/firm layoff. | pricing revision ordinary.
1477 | 6123907 | Cold Waste Water (PAR 011) - Albergaria-a-Velha | 45232460-4 | Sanitary works | TRUE | 2019 | 2021 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 40 | 12-12-2019 | 07-09-2021 | 635 | 180 | 500000 | 405500 | 2 | 405500 | 0 | 100 | Best value for money: No Criterion related to quality Name: Nothing to register Weighting: 0% Criterion related to cost Name: Price, as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1478 | 6122836 | Replacement of the lawn at the Estádio Capitão Josino da Costa | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2019 | 2020 | Portugal | Lagoa | Faro | 8 | 14 | 14-10-2019 | 05-03-2020 | 143 | 40 | 347500 | 344690.4 | 2 | 344690.4 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline for execution of the contract and Technical Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | date on which the provisional acceptance notice was prepared, concluding the project.
1479 | 6110476 | Energy Efficiency of Municipal Swimming Pools | 45300000-0 | Building installation work | FALSE | 2019 | 2020 | Portugal | Elvas | Portalegre | 12 | 21 | 09-12-2019 | 26-10-2020 | 322 | 120 | 184000 | 172920.26 | 1 | 172920.26 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covi 19 pandemic
1480 | 6108035 | SFP Faro - Parking Change | 45214800-8 | Training facilities building | TRUE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 20 | 24-04-2019 | 23-12-2019 | 243 | 90 | 72000 | 71999.99 | 1 | 71999.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: Proposed technical value Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1481 | 6106527 | AR004 E2 - Washer Lifting Station Reformulation | 45232431-2 | Wastewater pumping station | TRUE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 11 | 28-10-2019 | 09-06-2020 | 225 | 150 | 200000 | 172709.66 | 1 | 172709.66 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A
1482 | 6101138 | Refurbishment of the Engenho Velho sports center - S. Paio de Oleiros | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 31-10-2019 | 10-03-2020 | 131 | 90 | 29423 | 22978.02 | 1 | 22978 | 0.02 | 100.0001 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed ahead of schedule | there were no changes to the value of the project
1483 | 6101083 | Requalification of the Boticas Campsite | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2021 | Portugal | Boticas | Vila Real | 19 | 18 | 11-11-2019 | 28-07-2021 | 625 | 120 | 259200 | 252284 | 2 | 252284 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1484 | 6098064 | Replacement of a heat pump and fan coil units in the HVAC system in the District Center of Viana do Castelo. | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 21 | 19-08-2019 | 27-01-2020 | 161 | 90 | 72900 | 58934.69 | 1 | 58934.69 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1485 | 6093939 | Contract for the refurbishment of the pavilion d | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Évora | Évora | 7 | 14 | 13-11-2019 | 09-03-2020 | 117 | 75 | 110000 | 99473.94 | 1 | 101186.56 | -1712.62 | 98.3075 | Best value for money: No Criterion related to quality Name: X Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | maintenance of sanitary installations, contrary to what is mentioned in the terms of reference, as required by the customer/contracted operator. floor finishes. | maintenance of sanitary installations, contrary to what is mentioned in the terms of reference, as required by the customer/contracted operator. floor finishes.
1486 | 6093531 | Repair of Malfunctions in the RDA and Execution of Other Works - 2019 | 45232151-5 | Water-main refurbishment construction work | TRUE | 2019 | 2021 | Portugal | Oliveira do Bairro | Aveiro | 1 | 40 | 28-11-2019 | 27-11-2021 | 730 | 730 | 1400000 | 619200 | 2 | 619200 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1487 | 6085456 | Renovation of the Dr. Jaime dias simão - bungalows and surrounding area - vila franca de xira | 45112711-2 | Landscaping work for parks | FALSE | 2019 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 18 | 27-09-2019 | 26-02-2021 | 518 | 150 | 216300 | 213779.96 | 1 | 215689.25 | -1909.29 | 99.1148 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1488 | 6085110 | Construction of the Dinosaur Route in Lourinhã | 45220000-5 | Engineering works and construction works | TRUE | 2019 | 2020 | Portugal | Lourinhã | Lisboa | 11 | 16 | 05-12-2019 | 04-08-2020 | 243 | 50 | 172094.1 | 165000 | 1 | 179518.46 | -14518.46 | 91.9126 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | errors and omissions detected during the execution of the project/contract, accepted by the owner of work that jeopardized the normal development of the approved work plan. | errors and omissions detected during the execution of the /contract, accepted by the client, not foreseen in the initial contract.
1489 | 6082131 | AA and AR Networks - Small Extensions 2019 - 2nd PHASE | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2019 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 40 | 04-11-2019 | 25-11-2020 | 387 | 730 | 249000 | 228284.31 | 1 | 228281.59 | 2.72 | 100.0012 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1490 | 6081813 | Water Supply to Couto de Esteves (Couto de Cima, Couto de Baixo and Lourizela - PAA 015) - Phase 2 | 45232100-3 | Ancillary works for water pipelines | TRUE | 2019 | 2020 | Portugal | Sever do Vouga | Aveiro | 1 | 50 | 14-11-2019 | 30-10-2020 | 351 | 90 | 240000 | 215749.34 | 1 | 214500.11 | 1249.23 | 100.5824 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1491 | 6081671 | Paving, in bituminous concrete, of streets - 8th Phase, in the parishes of Lourosa and S. João de Ver | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-11-2019 | 11-08-2020 | 272 | 150 | 331941 | 224018.99 | 1 | 224018.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 10 days of legal extension + 10 days for free, 28 days related to the period for scheduling inspections
1492 | 6079061 | Contract for Remodeling the Electrical Installations of the SPMS EPE Building, located at street of Breiner 121, Porto | 45259000-7 | Repair and maintenance of plant | TRUE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 13 | 18-06-2019 | 13-10-2020 | 483 | 180 | 455000 | 399000 | 2 | 365687.07 | 33312.93 | 109.1097 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | change of validity for carrying out complementary work pursuant to paragraph 2 of article 370 of the "public procurement code" | the change in value results from underwork under the terms of article 379 of the "public procurement code" and the execution of complementary work under the terms of paragraph 2 of article 370 of the "public procurement code"
1493 | 6078448 | 2014.617.04.C1 - SFP Lisboa (Escola Fonseca Benevides)- Pedagogical kitchen and Table/bar | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 21 | 26-03-2019 | 28-12-2020 | 643 | 150 | 450000 | 448888.84 | 2 | 459966.59 | -11077.75 | 97.5916 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | health reasons | underwork. price review
1494 | 6076558 | Public Tender - CP 03-2019 - Peneireiro Tourist Complex - Pools and Leisure Area | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Vila Flor | Bragança | 4 | 30 | 26-08-2019 | 30-04-2020 | 248 | 210 | 557415.05 | 556844.74 | 2 | 556844.74 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | complementary work
1495 | 6075883 | Implementation of a roundabout at the intersection of Avenida Calouste Gulbenkian and streetde Alportel. | 45233128-2 | Roundabout construction work | TRUE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 15 | 25-11-2019 | 11-05-2021 | 533 | 90 | 203760 | 186270.26 | 1 | 176724.26 | 9546 | 105.4016 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in the context of the covid-19 pandemic
1496 | 6075514 | Improvement, expansion, repair and improvements in schools in the parish of Padre João Coelho Cabanita | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 9 | 20-08-2019 | 30-01-2021 | 529 | 180 | 162450 | 153116.69 | 1 | 153116.69 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline for the execution of the contract, there was only a delay in the execution of the provisional acceptance.
1497 | 6075454 | Enlargement of the changing rooms at the Duarte Pacheco School | 45210000-2 | Building construction work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 20 | 22-05-2019 | 09-03-2021 | 657 | 180 | 343500 | 326988.2 | 2 | 326988.2 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in work on reinforced concrete structures (namely formwork carpenters and ironworks)
1498 | 6075370 | Improvement, Expansion, Repair and Improvements in the Schools of the Municipality-Schools of the Laura Ayres and elementary school D. Francisca Aragão Group in Quarteira | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 9 | 16-07-2019 | 08-03-2021 | 601 | 180 | 349722 | 298404.5 | 2 | 298404.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Does not apply Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline for the execution of the contract, there was only a delay in the execution of the provisional acceptance
1499 | 6075107 | Pedestrian route network - streetde Camões / soccer field | 45454000-4 | Restructuring work | FALSE | 2019 | 2020 | Portugal | Baião | Porto | 13 | 30 | 12-11-2019 | 12-08-2020 | 274 | 240 | 286130 | 283649.4 | 2 | 283649.4 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | date of suspension of works - 04/02/2020 work restart date - 05/04/2020 | there were no changes to the value of the project
1500 | 6072832 | Quality 100% - Public tender for paving sidewalks 2019 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 27-11-2019 | 21-04-2020 | 146 | 45 | 399760 | 78195 | 1 | 78195 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1501 | 6072756 | Quality 100% - Public tender for paving sidewalks 2019 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 13-11-2019 | 21-04-2020 | 160 | 45 | 399760 | 149910 | 1 | 149910 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1502 | 6072313 | Public Tender No. 15/DRL/DA/2019 - Repair of the façade of the USHE Command building - Ajuda Barracks - Lisbon | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 09-07-2019 | 26-08-2020 | 414 | 120 | 125000 | 112185.55 | 1 | 112185.55 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | covid19 and lack of material.
1503 | 6071094 | Scales in the industrial zone of Vilar Formoso | 45221117-5 | Weighbridge construction work | FALSE | 2019 | 2021 | Portugal | Almeida | Guarda | 9 | 18 | 19-11-2019 | 16-07-2021 | 605 | 120 | 54650 | 54603.02 | 1 | 54273.64 | 329.38 | 100.6069 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal in the modality provided for in paragraph b) of paragraph 1 of article 74 of the CC Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in providing electricity, as well as difficulties in carrying out bituminous paving work. | underwork
1504 | 6071090 | Paving contract for Caminho da Aldeia and section of Caminho da Escola (Vale de Santa Maria) | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 20-05-2019 | 26-06-2020 | 403 | 90 | 410000 | 345974 | 2 | 361724.37 | -15750.37 | 95.6458 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
1505 | 6068855 | Public Path Paving Contract | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2019 | 2021 | Portugal | Velas | Região Autónoma dos Açores | 15 | 36 | 28-11-2019 | 25-11-2021 | 728 | 212 | 494013.39 | 484000 | 2 | 552640.35 | -68640.35 | 87.5796 | Best value for money: Yes Criterion related to quality Name: deadline of execution of the contract Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 2 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the changes to the execution time of the project were adverse weather conditions, constraints in terms of materials and labor caused by the covid-19 pandemic. | need to perform unforeseen work necessary for the execution of the project.
1506 | 6066594 | Paving of street of Serra in Rendufinho | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 27-11-2019 | 06-03-2020 | 100 | 60 | 19330.55 | 13253.9 | 1 | 13253.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the company alleged adverse weather conditions that prevented the execution of all the projects within the foreseen period.
1507 | 6064152 | Works contract for the rehabilitation of the roof of the Health Center of Buarcos, ACES Baixo Mondego | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Figueira da Foz | Coimbra | 6 | 15 | 30-08-2018 | 08-02-2019 | 162 | 90 | 107000 | 90222.49 | 1 | 90222.49 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1508 | 6061597 | Infrastructure damaged by the fires of October 2017 (Parish of Sobral) - FSUE - RV2 and RV3 | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Mortágua | Viseu | 20 | 2 | 22-11-2019 | 16-12-2020 | 390 | 90 | 329996.09 | 264974.51 | 2 | 264974.51 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | epidemiological reasons
1509 | 6061204 | Construction of the Transport Coordinating Center (PAMUS 4) | 45213310-9 | Construction work for buildings relating to road transport | FALSE | 2019 | 2021 | Portugal | Chaves | Vila Real | 19 | 30 | 19-11-2019 | 12-11-2021 | 724 | 300 | 935883.37 | 832800 | 2 | 825308.06 | 7491.94 | 100.9078 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension 70 days (60 + 10) | complementary work worth €16,502.90, underwork worth €27,003.08, price revision worth €3,008.24 (11,641.66 - 8,633.42)
1510 | 6060734 | CP No. 37/DRL/DA/2019 - Refurbishment of the warehouse in Poço do Bispo for the installation of the UCC Naval Maintenance Platoon | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 11 | 19-11-2019 | 30-04-2020 | 163 | 45 | 80000 | 74899.9 | 1 | 74899.9 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: See procedure parts Weighting: 0% Criterion related to cost Name: See procedure parts Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1511 | 6059022 | Cp 06/2019 - execution of the rehabilitation / waterproofing of the drinking water reservoir - r3e, in guardizela - municipality of guimarães | 45261420-4 | Waterproofing work | FALSE | 2019 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 16-07-2019 | 30-10-2019 | 106 | 45 | 35260 | 27451.72 | 1 | 25963.48 | 1488.24 | 105.7321 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1512 | 6058736 | Cp 07/2019 - Replacement of the water supply network and installation of a collector to eliminate improper connection of rainwater in the sanitation network. Parish of Costa and UF of Oliveira, S | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 02-09-2019 | 03-09-2020 | 367 | 150 | 160400 | 149360.71 | 1 | 141068.86 | 8291.85 | 105.8779 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1513 | 6058310 | Center for the promotion and development of water sports (surfing and canoeing) | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2019 | 2021 | Portugal | Vagos | Aveiro | 1 | 18 | 15-11-2019 | 17-09-2021 | 672 | 150 | 120000 | 119730.48 | 1 | 122586.69 | -2856.21 | 97.67 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid 19 pandemic | complementary works resulting from unforeseen circumstances (project errors and omissions), price revisions and underwork, resulting from the measurements of the quantities of works actually carried out during the course of the project (93.27%)
1514 | 6058010 | Cp 12/2019 - extensions of water supply and wastewater drainage networks in the parish of serzedelo - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 14-10-2019 | 30-08-2021 | 686 | 120 | 129000 | 127863.23 | 1 | 118827.91 | 9035.32 | 107.6037 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1515 | 6057496 | Cp 13/2019 - extensions of water supply and wastewater drainage networks in the parishes of selho s. Jorge and Selho S. Christopher | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 14-10-2019 | 19-01-2021 | 463 | 150 | 137000 | 128421.89 | 1 | 88741.72 | 39680.17 | 144.7142 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1516 | 6057267 | Building Rehabilitation in the Aguda Fishing Nucleus - Building next to the Aguda Volunteer Fire Department | 45262690-4 | Refurbishment of run-down buildings | TRUE | 2019 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 45 | 25-11-2019 | 13-01-2021 | 415 | 365 | 580000 | 516977.46 | 2 | 608418.78 | -91441.32 | 84.9707 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed in less time than originally planned. | the completion of the project resulted in additional work worth €98,204.68, underwork worth €19,054.14 and a final price review worth €12,290.78.
1517 | 6057257 | Improvement and Requalification of Municipal Housing Buildings - Palmeira. | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2020 | Portugal | Santo Tirso | Porto | 13 | 5 | 06-11-2019 | 21-10-2020 | 350 | 180 | 166825 | 166628.76 | 1 | 180034.87 | -13406.11 | 92.5536 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the existence of complementary works. | the need to carry out some complementary work essential to the good finish of the project.
1518 | 6057243 | Cp 14/2019 - replacement of water supply networks in the union of the parishes of caldas de vizela (s. Miguel and s. João) - municipality of vizela | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Vizela | Braga | 3 | 14 | 10-10-2019 | 29-01-2021 | 477 | 90 | 116500 | 87325.37 | 1 | 79146.04 | 8179.33 | 110.3345 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | works less
1519 | 6056966 | Cp 09/2018 – extension of wastewater drainage networks in the parish of silvares, between the a11 and the en206 / en101 connection - guimarães | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 23-08-2018 | 30-10-2019 | 433 | 150 | 248300 | 198966.31 | 1 | 198966.29 | 0.02 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1520 | 6056799 | Cp 11/2018 – extension of wastewater drainage networks in zone 7 – parish of guardizela and union of parishes of conde and gandarela – 3rd phase | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 23-08-2018 | 30-10-2019 | 433 | 150 | 263000 | 215364.36 | 1 | 215364.36 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
1521 | 6055310 | Cp 04/2019 – Replacement of water supply networks on streetde Damão and streetde Gôa - Parish of Azurém | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 14 | 16-07-2019 | 02-06-2020 | 322 | 60 | 57000 | 48228.61 | 1 | 43832.48 | 4396.13 | 110.0294 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | works less
1522 | 6054899 | Cp 15/2019 - Replacement of water supply networks on streetde São Gualter - parish of Urzes - Guimarães | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 14-10-2019 | 05-01-2021 | 449 | 120 | 121000 | 107264.25 | 1 | 107218.25 | 46 | 100.0429 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1523 | 6054521 | Cp 08/2019 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela - project_12/2019 | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 22-08-2019 | 18-11-2021 | 819 | 365 | 297300 | 267225.53 | 2 | 267223.16 | 2.37 | 100.0009 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1524 | 6053873 | Public works contract to repair EMEL car parks - Belém, Avenida dos Combatentes and Estrada da Luz | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 21 | 04-11-2019 | 31-07-2020 | 270 | 140 | 120000 | 119980 | 1 | 119212.93 | 767.07 | 100.6434 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was due to work not performed. | results from work not performed.
1525 | 6051500 | Work to improve the basement archives of the Ministry of Labour, Solidarity and Social Security Building, with a fire protection system. | 45300000-0 | Building installation work | FALSE | 2019 | 2019 | Portugal | Lisboa | Lisboa | 11 | 15 | 11-10-2019 | 05-12-2019 | 55 | 50 | 105000 | 92026.88 | 1 | 92026.88 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1526 | 6051296 | Contract for the reorganization and qualification of the maritime front of the nucleus of amorous | 45233200-1 | Various surface works | FALSE | 2013 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 48 | 20-10-2014 | 02-05-2018 | 1290 | 240 | 1825000 | 1679557.86 | 3 | 1673845.15 | 5712.71 | 100.3413 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | the phasing of works to minimize interference in that nucleus during the bathing season; alterations, albeit occasional, to the project and details; poorly detailed registers at the level of existing infrastructures; pressure arising from the bathing season; and execution of a small contiguous work, under the responsibility of the municipality of viana do castelo; weather conditions in the last months of work | works not performed
1527 | 6051238 | Requalification of streetde Santo António | 45112710-5 | Landscaping work for green areas | FALSE | 2019 | 2020 | Portugal | Lousada | Porto | 13 | 18 | 22-11-2019 | 02-09-2020 | 285 | 60 | 103092.75 | 101690.4 | 1 | 101690.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1528 | 6049905 | The objective of the work is to repair and refurbish the aforementioned streets and respective surrounding areas, such as parking lots and sidewalks, in need of modernization or improvement | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 11-11-2019 | 21-07-2021 | 618 | 140 | 216067.5 | 215345 | 1 | 215345 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | multiplicity of interactions with the affected services; several constraints related to the pandemic and the state of emergency; delays in the supply of materials due to the pandemic
1529 | 6049192 | The contract in question is intended for the execution of horizontal road signs, covering the entire north and south zone of the geographical area of ​​the municipality of Amadora | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 15-11-2019 | 29-04-2021 | 531 | 630 | 475000 | 380002 | 2 | 379623.78 | 378.22 | 100.0996 | Best value for money: Yes Criterion related to quality Name: Quality of work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the deadline for execution of the project was brought forward due to the completion of several municipal paving works. to ensure road safety, it was necessary to carry out the horizontal signaling of the same. | due to the final price review in the amount of -378.22€, due to the price review an addendum was made to the project bill on 02/24/2022.
1530 | 6048917 | Rehabilitation Works for Block 33 of Bairro do Cerco in Porto | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Porto | Porto | 13 | 30 | 12-11-2019 | 30-03-2021 | 504 | 300 | 950000 | 943113.7 | 2 | 1002167.9 | -59054.2 | 94.1074 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | N/A | TRUE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract works were concluded, as well as the corrections inherent to the first inspection for the purposes of provisional acceptance. | complementary works worth €80,877.73 and unfinished work worth €34,732.30
1531 | 6045951 | Execution of foundations for building H at Escola Coelho e Castro - Fiães | 45210000-2 | Building construction work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-11-2019 | 28-05-2020 | 197 | 60 | 111257 | 92750.41 | 1 | 101655.38 | -8904.97 | 91.24 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 17 days of graceful extension, 10 days of legal extension resulting from complementary work, 16 days related to scheduling the inspection for provisional acceptance purposes | complementary work resulting from unforeseeable circumstances
1532 | 6045793 | Contract for replacement of glazed gaps | 45421132-8 | Installation of windows | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 10 | 19-11-2019 | 30-01-2021 | 438 | 180 | 320000 | 311991.25 | 2 | 333345.54 | -21354.29 | 93.5939 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the deadline were related to the covid-19 pandemic and the consequent difficulty in supplying materials. | complementary work, underwork and price revision.
1533 | 6044592 | Improvement of the subdivision of the request, 1st phase - Povoa de Lanhoso | 45211360-0 | Urban development construction work | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 15-10-2019 | 30-04-2020 | 198 | 180 | 270701.85 | 191459.85 | 1 | 206217.76 | -14757.91 | 92.8435 | Best value for money: Yes Criterion related to quality Name: Technical quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extra work | additional work
1534 | 6044366 | Paving contract for streetde Vila, parish of Covelas | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 06-11-2019 | 27-03-2020 | 142 | 90 | 146156.25 | 122982.73 | 1 | 122982.73 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions. | non-existent.
1535 | 6042699 | C.p. Nº 01/2018 - remodeling and expansion of the st.ª eufémia de prazins collection and treatment system - guimarães - improvement of the road entrance and the aspiration | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2021 | Portugal | Guimarães | Braga | 3 | 20 | 21-05-2018 | 17-06-2021 | 1123 | 120 | 234800 | 188997.97 | 1 | 188997.42 | 0.55 | 100.0003 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | underwork
1536 | 6042181 | Refurbishment of Floor 0-Bar, Staff Cup and Reprography - Polo A | 45454000-4 | Restructuring work | TRUE | 2019 | 2020 | Portugal | Coimbra | Coimbra | 6 | 14 | 09-10-2019 | 24-07-2020 | 289 | 75 | 200000 | 194923.57 | 1 | 194923.57 | 0 | 100 | Best value for money: No Criterion related to quality Name: --- Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the acquisition of hotel equipment by the contractor, weather conditions and change in the design of the exterior metallic structure. | considering that: water infiltration was detected in 2 deactivated cores, it was necessary to correct it, such as the plasterboard wall due to a change in the hvac device, availability of flooring for application in future faults outside, placement of water for irrigation, placement of an anti-grass blanket under the esplanade, error in measurements at various points, reduction in the number of projectors and application of signage, exclusion of hotel equipment.
1537 | 6041800 | Lots 9 and 13 - Requalification of Avenida Tenente Valadim (PAMUS 1.6) and Avenida de Santo Amaro (PAMUS 1.7) | 45233220-7 | Surface work for roads | FALSE | 2019 | 2021 | Portugal | Chaves | Vila Real | 19 | 21 | 19-11-2019 | 30-06-2021 | 589 | 210 | 499639.75 | 465610 | 2 | 458002.49 | 7607.51 | 101.661 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work suspension and deadline extension | underwork worth €8,001.68 and definitive price review worth €394.17
1538 | 6039043 | Construction of the landscaping of the Escola Básica de Fornos | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 12-11-2019 | 01-04-2020 | 141 | 30 | 51730.99 | 49119.37 | 1 | 49119.37 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 20% Criterion related to cost Name: Price (P) Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-significant change
1539 | 6035136 | Contract for the expansion of the water supply network and domestic wastewater network - Caminho das Arrobeiras | 45232460-4 | Sanitary works | FALSE | 2019 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 09-05-2019 | 17-12-2019 | 222 | 45 | 90516.96 | 61466.98 | 1 | 67613.26 | -6146.28 | 90.9097 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1540 | 6034512 | CE Gondomar - roof waterproofing | 45000000-7 | Construction work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 8 | 03-10-2019 | 01-07-2020 | 272 | 60 | 273000 | 226800 | 1 | 234208.68 | -7408.68 | 96.8367 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | additional work, deadline extension
1541 | 6034075 | Works on the building of the municipal swimming pool of Alhos Vedros in terms of conservation of the building and the surrounding area in the translucent component and in the systems, namely heating, ventilation, air conditioning | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2019 | 2020 | Portugal | Moita | Setúbal | 17 | 30 | 15-10-2019 | 07-10-2020 | 358 | 180 | 365500 | 365168.21 | 2 | 386428.8 | -21260.59 | 94.4982 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary work and regular price review
1542 | 6033246 | Remodeling of the water supply networks in street of Feira and Estrada Militar in Valejas and street of Lameiro in Queijas, municipality of Oeiras | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 9 | 14-10-2019 | 05-05-2021 | 569 | 120 | 149397 | 128472.5 | 1 | 128472.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline was met in full.
1543 | 6030734 | C.p. Nº 14/2017 - replacement of water supply networks and extension of wastewater sanitation networks in the parishes of fermentões,pencelo u.f. From selho s. Lourenço and Gominhães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Guimarães | Braga | 3 | 20 | 09-04-2018 | 11-10-2019 | 550 | 120 | 316500 | 240824.12 | 1 | 240824 | 0.12 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Nf - Final Grade Nf = 0.60 x Pr + 0.40 x VTP a) Price (60% weighting) Pr = (100 - 25 x VPC / 316,500.00) / 5 b) Technical value (40% weighting) ii) Technical value of the proposal with a weight of 40% with the following weighting of sub-criteria: a) Note 1 - Descriptive Memory - 35% b) Grade 2 - Work Plan - 30% c) Grade 3 - Management and Quality Control System - 15% d) Note 4 - Security Management System - 10% e) Note 5 - Environmental Monitoring System - 10% VTP = (0.35 x Note1 + 0.30 x Note2 + 0.15 x Note3 + 0.10 x Note4+ 0.10 x Note5) | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | no change
1544 | 6030482 | Refurbishment contract for street5 de Outubro - Phase 2 | 45232130-2 | Storm-water piping construction work | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 30-10-2019 | 10-12-2020 | 407 | 350 | 243281.35 | 235620.27 | 1 | 222636.6 | 12983.67 | 105.8318 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
1545 | 6026905 | 2018.151.02.C1 - Alentejo Regional Delegation - Refurbishment of HVAC, electrical and window openings | 45331000-6 | Heating, ventilation and air-conditioning installation work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 14-05-2019 | 06-03-2020 | 297 | 150 | 280000 | 259690.95 | 2 | 259690.95 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1546 | 6026025 | Public works contract with a view to carrying out the necessary works to improve mobility on Avenida dos Combatentes - Lisbon | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 30 | 07-10-2019 | 31-08-2020 | 329 | 44 | 200000 | 184000 | 1 | 175565.1 | 8434.9 | 104.8044 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | a partial provisional reception was carried out on 01/30/2020 and on 07/03/2020 the provisional reception of the missing works was carried out. for reasons of force majeure, through no fault of the supplier, this was done. work on the viaduct was suspended for safety reasons. | there were works that were not performed.
1547 | 6025360 | Requalification of the Gymnodesportivo de Alter do Chão | 45212290-5 | Repair and maintenance work in connection with sports facilities | TRUE | 2019 | 2021 | Portugal | Alter do Chão | Portalegre | 12 | 18 | 11-10-2019 | 29-03-2021 | 535 | 150 | 321000 | 304523.52 | 2 | 304523.52 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Proposal cost Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions
1548 | 6024886 | Refurbishment of the water supply network and branches of the ZMC in Cordinhã and the ZMC in Pena | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 21 | 19-01-2018 | 16-09-2020 | 971 | 360 | 500000 | 479204.18 | 2 | 471344.68 | 7859.5 | 101.6675 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
1549 | 6024674 | Construction of a Business Nest - 2nd Phase | 45213250-0 | Construction work for industrial buildings | FALSE | 2019 | 2021 | Portugal | Arronches | Portalegre | 12 | 30 | 08-11-2019 | 29-06-2021 | 599 | 365 | 574741.49 | 569689.02 | 2 | 564465.65 | 5223.37 | 100.9254 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | heavy rains and pandemic | measurement errors
1550 | 6024500 | Rehabilitation/replacement of sections of the alviela monsanto pipeline | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Alcanena | Santarém | 16 | 30 | 07-11-2019 | 10-09-2021 | 673 | 270 | 403979.7 | 392503.15 | 2 | 392503.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | last self measurement of 11/26/2020
1551 | 6022437 | Contract to Improve Security Conditions in AdVT Infrastructures: Phase 1: Beiras Hub. FRP elements | 45341000-9 | Erection of railings | FALSE | 2019 | 2021 | Portugal | Penamacor | Guarda | 9 | 60 | 23-09-2019 | 03-02-2021 | 499 | 180 | 200000 | 189226.43 | 1 | 185524.36 | 3702.07 | 101.9955 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract execution period was suspended for 30 days due to the pandemic situation caused by the covid-19 outbreak. on 02/06/2020, an inspection was carried out, in which it was found that there were pending works, and the contractor was granted a deadline for their suppression. subsequently, on 08/21/2020, a new inspection was carried out, in which the partial provisional reception of the project was approved, where it was found that there were no conditions for the operations department to authorize access to certain locations for completion of the projects, which would be carried out, predictably, until october/november. once the aforementioned works were completed, a new inspection was carried out, where the inspection report was signed for the purpose of full provisional acceptance on 12/30/2020. | change in the contractual value resulting from contractual work not carried out, as well as from the price review carried out.
1552 | 6020954 | Parish of Pombal / Street layout and Improvements on roads and paths in the parish (Requalification of Public Spaces - streetJosé Aguiar) - Proc. No. 42/2019 | 45432110-8 | Floor-laying work | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 21 | 27-09-2019 | 25-10-2021 | 759 | 120 | 146987.5 | 126370.49 | 1 | 122658.81 | 3711.68 | 103.026 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this work has the provisional reception on 7/9/2020 due to the fact that it was only on that date that the contractor verbally requested it by the contractor for inspection in accordance with article 394 of the "public procurement code", when he delivered the duly completed rcd plan, and the inspection was carried out immediately and the inspection report was signed that day, as well as the final measurement report also carried out on that day. | existence of underwork and revision of prices.
1553 | 6020604 | Quality 100% - replacement of walkways on beaches at u.f. Of perafita, lavra and s.c. of the bishop | 45240000-1 | Construction work for water projects | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 12-11-2019 | 02-09-2020 | 295 | 90 | 131750 | 104082.5 | 1 | 104082.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1554 | 6019793 | Expansion of the Spilled Water Community Center | 45262800-9 | Building extension work | FALSE | 2019 | 2021 | Portugal | Grandola | Setúbal | 17 | 21 | 30-10-2019 | 20-01-2021 | 448 | 120 | 39622.19 | 39501.17 | 1 | 40875.26 | -1374.09 | 96.6383 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty in signing the contractual modification contract and the respective invoicing, due to the state in which our country was due to covid 19
1555 | 6019778 | EN 321 - Construction of the sidewalk at km 19+000 and km 20+300 (Ancede and Ribadouro - Baião) - EN 321 - Construction of the sidewalk at km 8+900 and km 9+500 (Campelo and Ovil - Baião) | 45454000-4 | Restructuring work | FALSE | 2019 | 2021 | Portugal | Baião | Porto | 13 | 30 | 16-10-2019 | 04-01-2021 | 446 | 120 | 303182.19 | 273918.12 | 2 | 273918.12 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there are no changes to the time for completion of the project. | there were no changes to the value of the project
1556 | 6017902 | Paving of street ofs Lages in Sobadelo da Goma | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2019 | Portugal | Póvoa de Lanhoso | Braga | 3 | 14 | 23-09-2019 | 13-12-2019 | 81 | 120 | 85364.55 | 78979.06 | 1 | 78979.06 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-existent. | non-existent.
1557 | 6017577 | Cp 26/2018 – replacement of water supply networks and extension of wastewater drainage networks in the parishes of s. Torcato, brito and uf de atães and rendufe - guimarães | 45231300-8 | Construction work for water and sewage pipelines | FALSE | N/A | 2020 | Portugal | Guimarães | Braga | 3 | N/A | 14-01-2019 | 30-09-2020 | 625 | 180 | N/A | 455571.21 | 2 | 434205.14 | 21366.07 | 104.9207 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | underwork
1558 | 6017322 | Cp 20/2018 – Replacement of water supply networks in the parishes of Creixomil, Fermentos and Ponte - Guimarães | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 06-11-2018 | 26-09-2019 | 324 | 120 | 99950 | 85908.02 | 1 | 84131.64 | 1776.38 | 102.1114 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1559 | 6017275 | Cp 02/2019 – Replacement of a section of the water supply network in crossstreet ofMouril – Parish of Silvares - Guimarães | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 17-04-2019 | 19-01-2021 | 643 | 45 | 44000 | 34214.97 | 1 | 28830.04 | 5384.93 | 118.6782 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | works less
1560 | 6017221 | Cp 01/2018 – Replacement of the water supply network at street of Covelo – Parish of Nespereira – Guimarães | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 11-04-2019 | 03-10-2019 | 175 | 60 | 38100 | 35294.72 | 1 | 18991.23 | 16303.49 | 185.8475 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
1561 | 6017152 | CP 10/2018 – Replacement of water supply networks on street Reitor Joaquim Augusto Maciel Ribeiro Torres, street Emílio Castelar Guimarães, Largo Comendador Manuel Gonçalves and street of Gandra – F | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2021 | Portugal | Guimarães | Braga | 3 | 14 | 23-08-2018 | 29-01-2021 | 890 | 120 | 228215 | 201783.26 | 1 | 200630.25 | 1153.01 | 100.5747 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1562 | 6012622 | Conservation and Improvement of the Municipal Cemetery, by contract: Application of colored carpet (dark red) in pedestrian streets - CP-CCP-EMP n.º 07/2019 | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 6 | 08-11-2019 | 29-04-2020 | 173 | 9 | 53560.2 | 50295.2 | 1 | 50295.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works that were delayed due to adverse weather conditions
1563 | 6011335 | EP-2019(5001)/10015 Miscellaneous Repairs to the Areia Branca Support Building | 45211310-5 | Bathrooms construction work | TRUE | 2019 | 2020 | Portugal | Lourinhã | Lisboa | 11 | 14 | 05-11-2019 | 04-03-2020 | 120 | 45 | 75000 | 64631.47 | 1 | 64631.47 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work for security reasons | no change
1564 | 6010302 | Installation of Playgrounds in Schools - Valongo | 45212130-6 | Amusement park construction work | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 12 | 31-10-2019 | 29-11-2021 | 760 | 90 | 143300 | 123452.74 | 1 | 128299 | -4846.26 | 96.2227 | Best value for money: No Criterion related to quality name: no Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of 2 (two) term extensions of 35 days + 20 days allocation of 5 days to carry out additional work (additional contract) note: the project was completed on 23.06.2020 (last measurement report), there was a delay in scheduling the provisional reception | approval of: - additional work - €5,402.50 - (order of 21.04.2020) - underwork – €1,050.00 - (order of 21.04.2020) - calculation of the final price revision - €493.76 (order of 22.11.2021)
1565 | 6010243 | Installation of Playgrounds in Schools - Ermesinde | 45212130-6 | Amusement park construction work | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 12 | 31-10-2019 | 29-11-2021 | 760 | 90 | 167000 | 144992.23 | 1 | 146652.04 | -1659.81 | 98.8682 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of 2 (two) term extensions of 35 days + 20 days allocation of 10 days to carry out additional work (additional contract) note: there was a delay in scheduling the provisional reception. | additional contract: additional work = €7,680.75 + underwork = €7,130.00 final price revision calculation = €1,109.06
1566 | 6010019 | PATA – Animal Welcoming and Treatment Platform - Building Construction | 45210000-2 | Building construction work | TRUE | 2019 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 25 | 24-10-2019 | 03-12-2021 | 771 | 365 | 1400000 | 1298537.77 | 3 | 1338728.27 | -40190.5 | 96.9979 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed on time, however, it was necessary for the contractor to correct anomalies in the project carried out, so the provisional acceptance notice was only prepared on the date indicated. | the completion of the project resulted in additional work worth €9,696.25 and a provisional price review of €30,494.25 was determined.
1567 | 6009698 | Cpn 60/2019/dicp - t-48/2019 - stabilization of the banks of Ribeira do Amparo and sedimentation control - union of parishes of marrazes and barosa | 45111230-9 | Ground-stabilisation work | FALSE | 2019 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 14-10-2019 | 25-05-2021 | 589 | 90 | 70653.05 | 63000 | 1 | 59022.1 | 3977.9 | 106.7397 | Best value for money: No Criterion related to quality Name: N.A. Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (by the contractor) due to lack of safety conditions (art. 366.º, n.º 3, subparagraph a) | underwork (art.º 379.º n.º 2)
1568 | 6009039 | Requalification of Praça da República and Jardim Manuel Faria - U.F. From Caldas de Vizela (S. Miguel and S. João) | 45220000-5 | Engineering works and construction works | FALSE | 2019 | 2021 | Portugal | Vizela | Braga | 3 | 42 | 07-11-2019 | 01-07-2021 | 602 | 365 | 2300000 | 1738759.97 | 3 | 2304789.88 | -566029.91 | 75.4411 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
1569 | 6008539 | Urban requalification contract in the Municipality of Cascais | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 17 | 22-10-2019 | 15-12-2021 | 785 | 135 | 1271440.54 | 297719.69 | 2 | 297719.68 | 0.01 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | indefinitions in the project
1570 | 6008519 | Urban requalification contract in the Municipality of Cascais | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 17 | 22-10-2019 | 02-07-2021 | 619 | 135 | 1271440.54 | 326183.13 | 2 | 326183.13 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | pandemic and uncertainties in the project
1571 | 6008483 | Urban requalification contract in the Municipality of Cascais | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 17 | 22-10-2019 | 19-01-2021 | 455 | 135 | 1271440.54 | 207938.35 | 1 | 207938.35 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | pandemic and project changes
1572 | 6008448 | Urban requalification contract in the Municipality of Cascais | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Cascais | Lisboa | 11 | 17 | 22-10-2019 | 19-01-2021 | 455 | 135 | 1271440.54 | 339898.08 | 2 | 339898.08 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | covid-19, and project changes
1573 | 6007837 | Construction of a Parking lot next to the Arronches School Centre. | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2021 | Portugal | Arronches | Portalegre | 12 | 15 | 08-10-2019 | 16-04-2021 | 556 | 90 | 143493.82 | 128452.44 | 1 | 114975.87 | 13476.57 | 111.7212 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | doubts about the project and approval of the application, since it could not be physically completed. | measurements on site
1574 | 6007805 | Infrastructure damaged by the fires of October 2017 - RV1 (Access to the Industrial Pole / Pellets Power and Thermoelectric Central); RV4 (in Chão de Vento/Albufeira da Barragem da Aguieira) | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Mortágua | Viseu | 20 | 8 | 29-10-2019 | 22-01-2021 | 451 | 90 | 343437.74 | 284155.33 | 2 | 288173.31 | -4017.98 | 98.6057 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological reasons. | complementary work and price revision
1575 | 6007267 | Reconstruction and Recovery of the Municipal Road Network - Praceta Salvador Caeiro Braz, streetComendador João Pereira Magalhães Roundabout and Lions Clube de Vizela Roundabout | 45212314-0 | Historical monument or memorial construction work | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 15 | 06-11-2019 | 22-05-2020 | 198 | 90 | 40000 | 39953.77 | 1 | 43896.25 | -3942.48 | 91.0186 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension | complementary works
1576 | 6006546 | Its object is the execution of recovery works in the Central Garden of Buraca and surrounding streets . | 45236290-9 | Repair work on recreational areas | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 30-10-2019 | 18-08-2020 | 293 | 210 | 235687.9 | 198634.68 | 1 | 198634.68 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contractor was slow to deliver the "plan for the prevention and management of construction and demolition waste".
1577 | 6005601 | Requalification of Av. from s. Vicente with connection to the Urban Variant | 45233120-6 | Road construction works | FALSE | 2019 | 2020 | Portugal | Lousada | Porto | 13 | 18 | 11-10-2019 | 17-12-2020 | 433 | 240 | 399070.5 | 334936.05 | 2 | 363880.54 | -28944.49 | 92.0456 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out paving work. | complementary works; underwork.
1578 | 6005136 | Contract for "Repair of the access road to the Morgavel ETA" | 45233140-2 | Roadworks | TRUE | 2019 | 2020 | Portugal | Sines | Setúbal | 17 | 14 | 31-10-2019 | 10-03-2020 | 131 | 45 | 100000 | 65000 | 1 | 65000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | when the victory was requested for the purposes of provisional acceptance, the developer carried out the respective inspection 30 days from the date of receipt of said solicitation.
1579 | 6004373 | Town Hall Building - Frames and Painting - Loures | 45421110-8 | Installation of door and window frames | FALSE | 2019 | 2020 | Portugal | Loures | Lisboa | 11 | 10 | 31-07-2019 | 23-04-2020 | 267 | 90 | 178176.81 | 168297.31 | 1 | 173150.53 | -4853.22 | 97.1971 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | time-consuming process of almost manual production of the opening in the main hall (graceful extension) and due to complementary work on the supply and installation of blackout blinds in the south quadrant of the building (legal extension) | the execution of complementary work in unforeseen circumstances
1580 | 6003273 | Contract for the installation of an air conditioning system in the Palace of Justice of Évora - Tribunal + | 45331220-4 | Air-conditioning installation work | FALSE | 2019 | 2020 | Portugal | Évora | Évora | 7 | 30 | 22-10-2019 | 26-02-2020 | 127 | 30 | 30000 | 21778.24 | 1 | 21778.24 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1581 | 5999713 | Requalification of street1.º de Maio and Avenida da Liberdade - 1st Phase | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Lousada | Porto | 13 | 21 | 25-10-2019 | 19-07-2021 | 633 | 180 | 344821.5 | 321072.6 | 2 | 289680.71 | 31391.89 | 110.8367 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork
1582 | 5999660 | Contract for "Repaving of the Municipal Cemetery of Olhão" | 45215400-1 | Cemetery works | FALSE | 2019 | 2021 | Portugal | Olhão | Faro | 8 | 9 | 15-10-2019 | 21-06-2021 | 615 | 30 | 29925 | 25000 | 1 | 25000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended for 232 days, primarily due to atmospheric conditions that did not allow the continuity of the project, a situation to which the covid-19 pandemic was added.
1583 | 5999544 | Recovery of deactivated school buildings (Improvement and Restoration of the Primary School of Pousadas Vedras) - Proc. No. 50/2019 | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 03-10-2019 | 03-12-2021 | 792 | 120 | 78157.15 | 73659.1 | 1 | 71543.01 | 2116.09 | 102.9578 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid 19 pandemic | existence of underworks.
1584 | 5999184 | Partial repaving of CM 1308 Estrada da Relva | 45432110-8 | Floor-laying work | TRUE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 12 | 29-10-2019 | 17-05-2021 | 566 | 90 | 220874 | 185830.5 | 1 | 185830.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1585 | 5998770 | Supply and replacement of the hot or cold water production group in the Faro District Center Headquarters Building | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Faro | Faro | 8 | 21 | 18-09-2019 | 14-01-2020 | 118 | 90 | 100000 | 73597.85 | 1 | 73597.85 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was possible to carry out the project in less time
1586 | 5998509 | Requalification of the spans of the Elvas Town Hall Building | 45421130-4 | Installation of doors and windows | FALSE | 2019 | 2020 | Portugal | Elvas | Portalegre | 12 | 21 | 06-09-2019 | 15-01-2020 | 131 | 90 | 180000 | 172631 | 1 | 172631 | 0 | 100 | Best value for money: No Criterion related to quality Name: Municipality of Elvas Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1587 | 5995794 | Repaving of CM 1320 in Faro. | 45432110-8 | Floor-laying work | FALSE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 20 | 25-10-2019 | 11-05-2021 | 564 | 90 | 245365 | 197587.66 | 1 | 194538.48 | 3049.18 | 101.5674 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | in the context of the covid-19 pandemic
1588 | 5995775 | Contract for the Rehabilitation of Water Supply Infrastructures in crossstreet ofLago, in Quinta do Lago | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2020 | Portugal | Loulé | Faro | 8 | 18 | 10-10-2019 | 21-09-2020 | 347 | 100 | 240000 | 190211.65 | 1 | 190211.65 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | interruptions by agreement between the parties at christmas/new year, and due to constraints due to simultaneous work carried out by third parties and due to covid19. graceful extension of the deadline due to external constraints.
1589 | 5995494 | Pavement rehabilitation in the urban center of Fundões | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2021 | Portugal | Mangualde | Viseu | 20 | 24 | 18-10-2019 | 02-07-2021 | 623 | 120 | 169358.5 | 159532.21 | 1 | 157857.83 | 1674.38 | 101.0607 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: nonexistent Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | underwork.
1590 | 5992145 | Intervention on roofs and conservation of fires Quinta dos Vidais neighborhood | 45262660-5 | Asbestos-removal work | FALSE | 2017 | 2020 | Portugal | Setúbal | Setúbal | 17 | 30 | 23-10-2019 | 20-03-2020 | 149 | 120 | 186514.89 | 180299.79 | 1 | 180299.79 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
1591 | 5990996 | Remodeling of the Proverba Water Supply and Sanitation Network (part) - Alverca do Ribatejo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 19-09-2019 | 11-08-2020 | 327 | 120 | 195027 | 159994.12 | 1 | 159994.12 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the delivery of the technical compilation / final screens
1592 | 5989187 | Contract for the Requalification of the Public Space of the Municipal Museum of Moura and Rehabilitation of the Hydraulic Passage called Pontão do Matadouro. | 45112700-2 | Landscaping work | FALSE | 2019 | 2020 | Portugal | Moura | Beja | 2 | 21 | 29-10-2019 | 15-07-2020 | 260 | 120 | 248120.16 | 220863.13 | 1 | 234268.37 | -13405.24 | 94.2778 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary work and underwork
1593 | 5989122 | Repair and requalification of streets and respective surroundings such as parking lots and sidewalks, in need of modernization or improvement of conditions of use | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 30 | 24-10-2019 | 11-01-2021 | 445 | 574 | 1036490 | 881016.51 | 2 | 881016.51 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline was advanced due to the poor condition of the pavement on the main roads.
1594 | 5988648 | EMP-C/1/2017 - Construction of 30 Homes, Infrastructures and Exterior Arrangements in São Gonçalo - Funchal | 45211340-4 | Multi-dwelling buildings construction work | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 20 | 18-07-2018 | 28-10-2019 | 467 | 450 | 2380000 | 1975400 | 3 | 1975400 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | labor shortage.
1595 | 5985578 | Its purpose is to carry out work on the roofs of the buildings located in the aforementioned street, in the parish of Falagueira-Venda Nova, namely the replacement of the current roofing system. | 45261214-7 | Bituminous roof-covering work | FALSE | 2019 | 2021 | Portugal | Amadora | Lisboa | 11 | 14 | 18-10-2019 | 09-09-2021 | 692 | 75 | 84113.08 | 72493.13 | 1 | 72493.13 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change in the execution period of the project, unpredictable situations, related to the covid19 pandemic, meteorology and execution of complementary works | complementary work
1596 | 5982965 | Rehabilitation contract for Levada de Fareja | 45247000-0 | Construction work for dams, canals, irrigation channels and aqueducts | FALSE | 2019 | 2021 | Portugal | Fafe | Braga | 3 | 15 | 22-10-2019 | 14-05-2021 | 570 | 180 | 206891.23 | 196873.46 | 1 | 191270.64 | 5602.82 | 102.9293 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - weather conditions that made it impossible to advance in the execution of the projection. - the water needs of the crops supplied by the canal forced the project to stop. | - execution of underwork (contracted, but not executed) - articles that the client of the project considered unnecessary for its execution. - execution of underwork (contracted, but not executed) - articles that contemplated the complete demolition of the section to be rehabilitated, but that with the beginning of the project it was possible to verify its structural integrity, and that for this reason the alteration was carried out of the type of work to be carried out, resulting in underwork, and an increase in the quantities of work of another nature but with a lower unit price. - the alteration of the constructive solution in some sections (hydraulic passages), resulted in a decrease of the unit price per linear meter of rehabilitated channel.
1597 | 5981552 | Refurbishment of the water supply and sanitation network on Avenida "Gaibéus" (Vila Franca de Xira), street layout parallel to streetCalouste Gulbenkian in Quintas (Castanheira do Ribatejo) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 9 | 22-08-2019 | 09-03-2021 | 565 | 60 | 149834.5 | 49816.1 | 1 | 49816.1 | 0 | 100 | Best value for money: No Criterion related to quality Name: lowest price Weighting: 100% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay in delivery of the technical compilation by the contractor
1598 | 5979257 | Rehabilitation and Improvement of Municipal Public Housing Buildings in Fernão de Magalhães, Blocks 12 to 17 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 40 | 24-10-2019 | 07-12-2020 | 410 | 210 | 1880000 | 939953.51 | 2 | 986898.08 | -46944.57 | 95.2432 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the contract works were concluded, and the contractor appealed to a request for a deadline extension. | complementary work not foreseen and unpredictable and work not performed.
1599 | 5979080 | Rehabilitation and Improvement of Municipal Public Housing Buildings in Fernão de Magalhães, Blocks 12 to 17 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Porto | Porto | 13 | 40 | 24-10-2019 | 04-01-2021 | 438 | 210 | 1880000 | 939406.12 | 2 | 982864.21 | -43458.09 | 95.5784 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project on the contract was completed, with the contractor resorting to two requests for extension of the deadline. | unforeseen and unpredictable complementary work.
1600 | 5977162 | Requalification of streetRaul Brandão, Praceta Prof. Laurentino Monteiro and streetJoão Crisóstomo (from the Cemetery to the Mother Church) - Fafe | 45233251-3 | Resurfacing works | FALSE | 2019 | 2020 | Portugal | Fafe | Braga | 3 | 17 | 23-10-2019 | 22-12-2020 | 426 | 300 | 682630.8 | 633860.46 | 2 | 633860.46 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | there were no changes to the value of the project
1601 | 5975967 | Restoration of the Cine Building – Teatro da Mina de S. Domingos | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Mértola | Beja | 2 | 30 | 18-10-2019 | 09-08-2021 | 661 | 365 | 251600 | 249818.96 | 1 | 249818.96 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by price assessment. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unavailability/difficulty in mobilizing human resources and guaranteeing the supply of materials on site aggravated by the covid pandemic situation, namely for carpentry work, microconcrete coatings and exterior painting. | there were no changes to the value of the project
1602 | 5975834 | Pedestrian and Cycling Networks/EM 569 - Zambujal/Corredoura | 45233161-5 | Footpath construction work | FALSE | 2018 | 2021 | Portugal | Sesimbra | Setúbal | 17 | 31 | 22-05-2019 | 24-03-2021 | 672 | 180 | 162567.75 | 156735.29 | 1 | 192769.05 | -36033.76 | 81.3073 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract was extended for a period of 72 days under paragraph a) of paragraph 1 of article 311 and paragraph b) of article 312 of the "public procurement code" | complementary work under the terms of paragraphs a) and b) of paragraph 4 of article 370 "public procurement code"
1603 | 5975467 | Reconfiguration of the Preliminary Treatment of the Côja EEAR | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Arganil | Coimbra | 6 | 35 | 30-08-2019 | 09-11-2020 | 437 | 150 | 175000 | 155666.03 | 1 | 171546.24 | -15880.21 | 90.7429 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for reasons of force majeure, not imputed to the contractor. | more work defined as unforeseen and unpredictable on site.
1604 | 5972748 | Cpn 27/2019/dicp - t - 23/2019 - execution of underground infrastructure for the IP and BT network and rainwater drainage on streetde Santa Catarina | 45231110-9 | Pipelaying construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 06-06-2019 | 26-06-2020 | 386 | 90 | 149670 | 114177.29 | 1 | 114177.29 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1605 | 5972393 | Construction contract for the Confluência Dam of the Vale do Lis hydro-agricultural development | 45247220-8 | Weir construction work | FALSE | 2019 | 2021 | Portugal | Leiria | Leiria | 10 | 30 | 17-04-2020 | 29-06-2021 | 438 | 270 | 450000 | 448464.35 | 2 | 448464.35 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: F2 - Technical value of the proposal Weighting: 40% Criterion related to cost Name: F1 - Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic
1606 | 5970596 | Repaving of EM 518-1 (Sea and War - Faro) | 45432110-8 | Floor-laying work | TRUE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 14 | 17-10-2019 | 17-05-2021 | 578 | 90 | 283951.2 | 258211.3 | 2 | 252771.3 | 5440 | 102.1521 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1607 | 5969170 | Construction of a bridge in reinforced and pre-stressed concrete, with a total length of 14m between extreme support axes | 45221000-2 | Construction work for bridges and tunnels, shafts and subways | FALSE | 2019 | 2021 | Portugal | Montemor-o-Velho | Coimbra | 6 | 33 | 17-07-2019 | 14-12-2021 | 881 | 330 | 384213 | 375450.89 | 2 | 402316.74 | -26865.85 | 93.3222 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension due to adverse weather conditions, namely heavy rainfall which caused the waters of the stream to rise a lot. | complementary work
1608 | 5962539 | CP 06/2019_DEGA - Rehabilitation of the Furadouro Reserve System - Ovar | 45259000-7 | Repair and maintenance of plant | TRUE | 2019 | 2021 | Portugal | Ovar | Aveiro | 1 | 40 | 04-10-2019 | 23-11-2021 | 781 | 180 | 300000 | 260000 | 2 | 260000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: PRICE Weighting: 55% Criterion related to cost Name: VALIA TÉCNICA Weighting: 45% | 1 | 55 | 5 | TRUE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1609 | 5962044 | 2018.099.02.C1 - SFP Santarém - replacement of roofs - Building C | 45259000-7 | Repair and maintenance of plant | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 24-06-2019 | 17-03-2020 | 267 | 120 | 169632.51 | 162688.26 | 1 | 162688.26 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension
1610 | 5961019 | CP 39/2019 - Contract for the Requalification of Public Space and Creation of Green Space next to Largo Dr. Luís ricardo | 45112711-2 | Landscaping work for parks | FALSE | 2019 | 2020 | Portugal | Vendas Novas | Évora | 7 | 21 | 14-10-2019 | 19-06-2020 | 249 | 120 | 116000 | 113832.7 | 1 | 117930.2 | -4097.5 | 96.5255 | Best value for money: Yes Criterion related to quality Name: Warranty period and maintenance of green spaces Weighting: 15% Criterion related to cost Name: Price Weighting: 85% | 1 | 85 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | interruption of the contract | complementary works
1611 | 5957546 | Official Collection Center for Companion Animals | 45000000-7 | Construction work | FALSE | 2019 | 2021 | Portugal | Anadia | Aveiro | 1 | 15 | 18-09-2019 | 12-10-2021 | 755 | 240 | 246440.41 | 225999.77 | 1 | 200103.12 | 25896.65 | 112.9417 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1612 | 5957374 | Paving streets with bituminous carpet - 2019 | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 05-07-2019 | 18-03-2020 | 257 | 60 | 120000 | 114885.96 | 1 | 114656.5 | 229.46 | 100.2001 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions | work reduction
1613 | 5955971 | Requalification of streetCustódio Freire - Proc. No. 25/2019 | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 10 | 24-07-2019 | 12-10-2021 | 811 | 210 | 366000 | 347768.5 | 2 | 341799.93 | 5968.57 | 101.7462 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the project had its contractual term on 20-5-2020, the last record was measured during the month of june 2020 and prepared with the date of 30-6-2020, within the legal deadlines of the "public procurement code", the contractor verbally requested the inspection the inspection of the project on that date and it was scheduled for 7/14/2020 by verbal agreement between the parties, the report was drawn up with that date, the inspection clarifies that the project was physically completed within the deadline. | work not done (work less)
1614 | 5952976 | Improvement and repair of the Animal Collection Center - Proc. No. 10/2019 | 45223600-2 | Dog kennels construction work | FALSE | N/A | 2021 | Portugal | Pombal | Leiria | 10 | N/A | 16-05-2019 | 28-10-2021 | 896 | 150 | N/A | 210796.61 | 1 | 211737.42 | -940.81 | 99.5557 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | it was not carried out in the scheduled time due to weather conditions. | price revision amount.
1615 | 5952963 | Recovery of deactivated school buildings (Improvement and restoration of Casal Fernão João School) - Proc. No. 12/2019 | 45214200-2 | Construction work for school buildings | FALSE | N/A | 2019 | Portugal | Pombal | Leiria | 10 | N/A | 08-05-2019 | 30-12-2019 | 236 | 120 | N/A | 71999.34 | 1 | 71603.32 | 396.02 | 100.5531 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the projects were completed within the project deadline, that is, on 10/09/2019, and the contractor verbally requested on that day to schedule the inspection for provisional acceptance. this was carried out and signed on 11/05/2019 (27 days after completion, still within the 30-day period of the contractor's request pursuant to paragraph 5 of article 394 of the "public procurement code"). | existence of underworks
1616 | 5950718 | 2018/194 - DGEP - Road signs preferably in the parishes of Porto Salvo, Barcarena and UF de Carnaxide e Queijas | 45233290-8, 45233221-4 | Installation of road signs, Road-surface painting work | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 30 | 04-10-2019 | 13-08-2021 | 679 | 360 | 119520 | 95861.2 | 1 | 95861.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1617 | 5947714 | Repair of Anomalies in the Neighborhood of Aldoar, Blocks 1, 2, 3, 5, 7, 9, 11, 13, 15 and 16 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Porto | Porto | 13 | 30 | 17-10-2019 | 12-07-2021 | 634 | 210 | 1030000 | 494169.55 | 2 | 478105.15 | 16064.4 | 103.36 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project had a deadline extension, however, due to the fact that the new completion date was not met, the performing entity was subject to the application of a pecuniary contractual penalty. the contract was carried out with the required quality, in safe conditions and the necessary actions were implemented in order to minimize the environmental impact of the contract. | complementary work and underwork
1618 | 5945126 | Leiria District Center - Rehabilitation works on the Local Service building in Alcobaça | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Alcobaça | Leiria | 10 | 15 | 08-10-2019 | 16-01-2020 | 100 | 70 | 79000 | 77853.14 | 1 | 77853.14 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1619 | 5944007 | Construction and Improvement of Leisure and Recreation Areas (Albergaria dos Doze Adventure and Leisure Park) - Proc. No. 36/2018 | 45212100-7 | Construction work of leisure facilities | FALSE | 2018 | 2020 | Portugal | Pombal | Leiria | 10 | 30 | 20-02-2019 | 27-08-2020 | 554 | 240 | 186525.58 | 178972.74 | 1 | 182998.13 | -4025.39 | 97.8003 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the provisional acceptance, due to the contractor's mistake, was only verbally requested by the contractor 5 days before the inspection for the purpose of provisional acceptance. the project was carried out within the deadline, as attested by the measurement records (last report drawn up on 12/17/2019, which corresponds to 20 days after the completion of the project), and the inspection for the purposes of provisional acceptance was carried out on the nearest date after the contractor's request, having been scheduled for 01/31/2020 where the inspection was carried out and the provisional acceptance certificate was signed. | existence of rounding in the measurement records and existence of price revision value.
1620 | 5943089 | Contract for the Expansion/Remodeling of the Arouca Sports Complex - Multipurpose Room | 45212100-7 | Construction work of leisure facilities | FALSE | 2019 | 2020 | Portugal | Arouca | Aveiro | 1 | 30 | 16-10-2019 | 03-11-2020 | 384 | 150 | 142156.63 | 141170.72 | 1 | 160119.35 | -18948.63 | 88.1659 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | deadline extension | additional work and underwork
1621 | 5942698 | Requalification of Public Lighting in the Fishing Port of Peniche | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Peniche | Leiria | 10 | 21 | 11-10-2019 | 15-12-2020 | 431 | 90 | 210000 | 179600 | 1 | 182909.09 | -3309.09 | 98.1909 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 5% Criterion related to cost Name: Price Weighting: 95% | 1 | 95 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay delivery of materials/covid | complementary works
1622 | 5942546 | 2019.116.04.C1 - SF Setúbal - replacement of lighting in 4 workshops | 45310000-3 | Electrical installation work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 7 | 07-08-2019 | 04-02-2020 | 181 | 100 | 97000 | 76493.01 | 1 | 76493.01 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | no data
1623 | 5941360 | Conservation and Rehabilitation of the Praia da Vitória Wall | 45262620-3 | Supporting walls | FALSE | 2019 | 2021 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 14-10-2019 | 30-04-2021 | 564 | 270 | 237767.6 | 202102.46 | 1 | 202102.46 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the pandemic situation, invite 19, with the required distance, the number of workers had to be reduced
1624 | 5938855 | Fund conservation dredging at the Aveiro Fishing Port | 45252124-3 | Dredging and pumping works | FALSE | 2019 | 2021 | Portugal | Ílhavo | Aveiro | 1 | 14 | 08-10-2019 | 21-01-2021 | 471 | 46 | 305000 | 244746.45 | 1 | 295782.95 | -51036.5 | 82.7453 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension report and respective lifting report, demobilization and remobilization of the dredger. deadline extension. additional to the contract | more works. additional to the contract
1625 | 5937380 | Residential Building Rehabilitation at street of Comércio do Porto, n.ºs 135 to 139 | 45262700-8 | Building alteration work | FALSE | 2019 | 2021 | Portugal | Porto | Porto | 13 | 21 | 30-09-2019 | 01-03-2021 | 518 | 360 | 500000 | 499194.15 | 2 | 495038.93 | 4155.22 | 100.8394 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two deadline extensions were granted, one for 37 days and a second for 18 days, both following the impact on the planning and development of the project caused by the covid-19 pandemic and subsequent states of emergency and calamity decreed by the portuguese government. | additional work worth €8,756.75 and unforeseen work worth €12,911.97
1626 | 5932448 | Reinforced and metallic concrete structure for the construction of the roof; Reformulation of rainwater and electrical sanitation infrastructure; outdoor lighting; | 45261213-0 | Metal roof-covering work | TRUE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 10-10-2019 | 16-11-2020 | 403 | 90 | 190000 | 178000 | 1 | 191109.33 | -13109.33 | 93.1404 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on schedule, however, it was necessary for the contractor to correct some anomalies. | the completion of the project resulted in additional works worth €11,995.30 and a price review was determined with definitive indices worth €1,114.03.
1627 | 5926161 | Contract No. 36/19 - Amadora Sports Recreations - Work Execution | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 15 | 10-10-2019 | 25-06-2020 | 259 | 150 | 582853.2 | 524567.89 | 2 | 524567.89 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the stipulated time. the observed deviation is due to the late delivery by the contractor of the waste management plan and the calculation of the price revision.
1628 | 5925961 | Rehabilitation of the Basílio Teles Children's Park | 45236290-9 | Repair work on recreational areas | FALSE | 2019 | 2021 | Portugal | Matosinhos | Porto | 13 | 20 | 10-10-2019 | 16-02-2021 | 495 | 60 | 36000 | 28524.8 | 1 | 28524.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1629 | 5925104 | Alfândega da Fé elementary and High school - Remodeling and Requalification - 1st Phase | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2018 | 2021 | Portugal | Alfandega da Fé | Bragança | 4 | 30 | 08-03-2019 | 02-09-2021 | 909 | 365 | 770000 | 734680.99 | 2 | 734680.99 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the need to extend the project has been verified due to the various conditions existing in the entire chain ​​of execution of the construction resulting from the pandemic experienced throughout the period of the project.
1630 | 5924734 | S.e.c. - PROC No. 81/A1/19 - Public Tender for the award of the contract for "Interventions in Infrastructures of Public Lighting Systems" | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 24 | 07-10-2019 | 01-10-2020 | 360 | 180 | 1922717.47 | 533864.91 | 2 | 533864.91 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions.
1631 | 5924691 | S.e.c. - PROC No. 81/A1/19 - Public Tender for the award of the contract for "Interventions in Infrastructures of Public Lighting Systems" | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 24 | 07-10-2019 | 20-10-2020 | 379 | 180 | 1922717.47 | 1272898.91 | 3 | 1272898.91 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions
1632 | 5923627 | NPD-3019022666-AMN - Contract to change a building in Quarteira | 45262522-6 | Masonry work | FALSE | 2019 | 2019 | Portugal | Loulé | Faro | 8 | 9 | 11-10-2019 | 14-12-2019 | 64 | 60 | 113000 | 111000 | 1 | 111000 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties
1633 | 5921325 | Rehabilitation of Bouças irrigation | 45232120-9 | Irrigation works | FALSE | 2019 | 2020 | Portugal | Celorico de Basto | Braga | 3 | 14 | 26-09-2019 | 13-07-2020 | 291 | 90 | 35377.36 | 32834.84 | 1 | 32834.84 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1634 | 5921277 | Rehabilitation of Britelo irrigation | 45232120-9 | Irrigation works | FALSE | 2019 | 2020 | Portugal | Celorico de Basto | Braga | 3 | 14 | 24-09-2019 | 14-07-2020 | 294 | 90 | 108490 | 101757.02 | 1 | 101757.02 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1635 | 5921223 | Rehabilitation of the Carrazedo irrigation system | 45232120-9 | Irrigation works | FALSE | 2019 | 2020 | Portugal | Celorico de Basto | Braga | 3 | 14 | 26-09-2019 | 13-07-2020 | 291 | 90 | 47169.81 | 46915.2 | 1 | 46915.2 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1636 | 5917242 | Refurbishment of the floor of the clinical consumption warehouse | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 15 | 11-07-2019 | 16-12-2019 | 158 | 30 | 25000 | 18982.5 | 1 | 18982.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical visit report Weighting: 40% Criterion related to cost Name: overall value of the proposal Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climate reasons
1637 | 5916594 | Cpn 11/2019/dicp - t-74/2018 - construction of road shelters in various locations in the municipality of leiria | 45213315-4 | Bus-stop shelter construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 18-06-2019 | 29-06-2020 | 377 | 120 | 141000 | 129229.79 | 1 | 129229.79 | 0 | 100 | Best value for money: No Criterion related to quality Name: N.A. Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1638 | 5916095 | Construction contract for the irrigation infrastructure of the Cuba-Odivelas Block, of the Alqueva Multipurpose Project | 45232120-9 | Irrigation works | FALSE | 2018 | 2021 | Portugal | Cuba | Beja | 2 | 40 | 30-09-2019 | 30-11-2021 | 792 | 365 | 9200000 | 8441900 | 3 | 8519998 | -78098 | 99.0834 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | execution of work to correct errors and omissions that conditioned the critical path of the project and the partial suspension of work on the main pipeline due to environmental constraints. | need to carry out work to correct errors and omissions related, essentially, to amounts of work greater than the amounts estimated in the project.
1639 | 5914957 | Requalification of Pinhel High school | 45454000-4 | Restructuring work | FALSE | 2017 | 2021 | Portugal | Pinhel | Guarda | 9 | N/A | 22-01-2018 | 07-01-2021 | 1081 | 390 | 2299982.06 | 1995000 | 3 | 2223790.39 | -228790.39 | 89.7117 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | because of the owner of the project, because of the contractor. | complementary work, price revision, underwork
1640 | 5913443 | Refurbishment contract for the headquarters building of the Regional Directorate of Sport, Terceira Island, Azores | 45000000-7 | Construction work | FALSE | 2019 | 2020 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 31 | 29-08-2019 | 29-05-2020 | 274 | 120 | 210519.69 | 178949.19 | 1 | 183468.04 | -4518.85 | 97.537 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension due to the authorization of complementary works, and two graceful extensions. | authorization of complementary works. the contractor, in the measurement records and corresponding invoices resulting from the projects contract, did not invoice the amount of €7.44.
1641 | 5911982 | The present contract aims to fully replace the coverings on the roof, reinforce the seals in the waterproofing systems and treat the interior coverings damaged by infiltrations. | 45261900-3 | Roof repair and maintenance work | FALSE | 2019 | 2020 | Portugal | Valongo | Porto | 13 | 15 | 30-09-2019 | 30-12-2020 | 457 | 90 | 95000 | 89788.5 | 1 | 100600.64 | -10812.14 | 89.2524 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of 47 days; assignment of a period of 45 days to carry out the complementary work. | approval by order of 26.06.2020 of additional work resulting from unforeseeable and unforeseen circumstances, in the global amount of €10,795.40 - object of an additional contract on 06.07.2020 approval by order of 11.08.2021 of the definitive calculation of the price revision, in the amount of €16.74.
1642 | 5908462 | Interventions on tours in various locations in the Municipality - year 2019 | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2021 | Portugal | Odivelas | Lisboa | 11 | 15 | 04-10-2019 | 25-01-2021 | 479 | 365 | 83000 | 83000 | 1 | 83000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes in the execution period of the project. | there were no changes to the value of the project
1643 | 5907766 | Synthetic Turf at Cernache do Bonjardim Training Ground | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2019 | 2021 | Portugal | Sertã | Castelo Branco | 5 | 15 | 23-09-2019 | 03-12-2021 | 802 | 30 | 122400 | 91721.9 | 1 | 89056.27 | 2665.63 | 102.9932 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change in the execution period of the project | underwork and price revision
1644 | 5906944 | Urban Requalification – West Section of street of Bombeiros Voluntários | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 31-07-2019 | 26-08-2020 | 392 | 30 | 40753.62 | 37598.99 | 1 | 41481.19 | -3882.2 | 90.6411 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of complementary works. | existence of complementary works.
1645 | 5904916 | Contract for public works to remodel the secretariat of the ESEP HEADQUARTERS. | 45113000-2 | Siteworks | TRUE | 2019 | 2019 | Portugal | Porto | Porto | 13 | 10 | 07-05-2019 | 18-07-2019 | 72 | 60 | 57500 | 49662.15 | 1 | 51821.55 | -2159.4 | 95.833 | Best value for money: Yes Criterion related to quality Name: Price or cost Weighting: 100% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Non-fulfilment of the contract (Contract Termination) | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extra work | more work and underwork.
1646 | 5899079 | Public works contract to repair EMEL car parks - Avenida Lusíada - University - Casal Vistoso | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 58 | 26-07-2019 | 05-05-2020 | 284 | 89 | 280000 | 251210.7 | 2 | 180187.03 | 71023.67 | 139.4166 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A |  | works have been deleted.
1647 | 5898387 | Lagos Municipal Cemetery (New) - Conservation and Improvement Works | 45215400-1 | Cemetery works | FALSE | 2019 | 2021 | Portugal | Lagos | Faro | 8 | 32 | 30-09-2019 | 13-01-2021 | 471 | 240 | 287000 | 261499.99 | 2 | 283262.81 | -21762.82 | 92.3171 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1 -b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for carrying out the project has not changed | complementary work contracts concluded in the global amount of €24,387.82, plus vat, underwork accepted in the amount of €2,625.00, plus vat
1648 | 5898163 | Contract for the Requalification of P.PORTO Building Spaces | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 30 | 29-09-2019 | 30-01-2020 | 123 | 60 | 165026.23 | 146640.96 | 1 | 92342.7 | 54298.26 | 158.8008 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | teaching activities that prevented some lots from starting on the scheduled date.
1649 | 5897562 | CP No. 90/2019 - Vila Verde Berth | 45241100-9 | Quay construction work | FALSE | 2019 | 2020 | Portugal | Figueira da Foz | Coimbra | 6 | 6 | 12-09-2019 | 12-08-2020 | 335 | 60 | 79145 | 69985 | 1 | 73350 | -3365 | 95.4124 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | adjustments to the project | complementary works
1650 | 5897169 | PO 295/2019 - Expansion of the basic sanitation network - Arcos de Valdevez (S. Paio) - Section 2 and 3 | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2021 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 02-10-2019 | 04-05-2021 | 580 | 150 | 139113.25 | 118812 | 1 | 118812 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 40% Criterion related to cost Name: Valia Técnica Weighting: 60% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1651 | 5896948 | Contract for "Rehabilitation of the Alvoco das Várzeas Irrigation System - Main Levada" | 45247111-1 | Irrigation channel construction work | FALSE | 2019 | 2020 | Portugal | Oliveira do Hospital | Coimbra | 6 | 15 | 17-09-2019 | 10-11-2020 | 420 | 180 | 185130.86 | 184259.57 | 1 | 174102.31 | 10157.26 | 105.8341 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, according to the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | work suspension | existence of underworks
1652 | 5896840 | Requalification of Public Lighting in the Fishing Port of Nazaré | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Nazaré | Leiria | 10 | 21 | 27-09-2019 | 30-03-2020 | 185 | 60 | 103300 | 94700 | 1 | 94700 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 5% Criterion related to cost Name: Price Weighting: 95% | 1 | 95 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay delivery of materials
1653 | 5896086 | Requalification of Municipal Leisure Equipment Affected by Forest Fires - 2017 | 45422100-2 | Woodwork | FALSE | 2019 | 2019 | Portugal | Oleiros | Castelo Branco | 5 | 14 | 26-08-2019 | 29-11-2019 | 95 | 100 | 349100 | 317213.15 | 2 | 317213.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work was carried out ahead of schedule
1654 | 5895594 | Requalification and Expansion of elementary school and Caneiro Kindergarten | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2021 | Portugal | Chaves | Vila Real | 19 | 15 | 19-09-2019 | 25-08-2021 | 706 | 180 | 802466.6 | 787000 | 2 | 877513.08 | -90513.08 | 89.6853 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2 term extensions for a period of 120 days (90 + 30) and 35 days associated with complementary works | complementary works in the amount of €78,234.04 underwork in the amount of €6,848.83 and price revision in the amount of €19,127.87
1655 | 5894926 | Requalification of streetManuel Carneiro Geraldes - Bem Viver | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 20-09-2019 | 22-04-2020 | 215 | 180 | 214646.36 | 191984.32 | 1 | 191984.32 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on time
1656 | 5894914 | Repaving of the EM 522 in Faro | 45432110-8 | Floor-laying work | TRUE | 2019 | 2021 | Portugal | Faro | Faro | 8 | 14 | 01-10-2019 | 10-05-2021 | 587 | 120 | 320624.5 | 285821.26 | 2 | 280189.76 | 5631.5 | 102.0099 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1657 | 5894000 | Requalification of Pedestrian Crossings in the village of Ferreira do Alentejo | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 20 | 12-09-2019 | 29-06-2021 | 656 | 90 | 130000 | 128284.42 | 1 | 120076.88 | 8207.54 | 106.8352 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions and difficulty in supplying materials | underwork resulting from changes to the initial design
1658 | 5892686 | 18/Eop/dcop/2019 - contract for the requalification of Largo 31 de Março and garden at Penedo | 45112700-2 | Landscaping work | FALSE | 2019 | 2020 | Portugal | Cascais | Lisboa | 11 | 14 | 25-09-2019 | 12-11-2020 | 414 | 120 | 532840.85 | 412500.02 | 2 | 412287.28 | 212.74 | 100.0516 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
1659 | 5889609 | Requalification and Refurbishment of streetPadre Manuel Torrão Mesquita, in Valpaços | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 30-09-2019 | 16-07-2020 | 290 | 120 | 103700.51 | 103611.29 | 1 | 108321.29 | -4710 | 95.6518 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects | complementary works
1660 | 5889563 | Construction of a car park next to Hospital de Valpaços | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 30-09-2019 | 16-07-2020 | 290 | 120 | 121482.39 | 117220.38 | 1 | 117216.38 | 4 | 100.0034 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects | underwork and additional work
1661 | 5887493 | Construction of Crosswalks With Traffic Calming Characteristics | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2020 | Portugal | Mogadouro | Bragança | 4 | 21 | 17-09-2019 | 26-06-2020 | 283 | 365 | 236319.14 | 198808.5 | 1 | 198808.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Economically Most Advantageous Proposal Criterion-Article 74, paragraph 1, line b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the typology of the project allowed it to be carried out before the end of the period foreseen for its conclusion. | there were no changes
1662 | 5885830 | HMC sports - Santa Maria da Feira municipal swimming pools - Refurbishment of therapeutic rooms | 45210000-2 | Building construction work | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 18 | 25-09-2019 | 16-03-2021 | 538 | 30 | 78292.53 | 78217 | 1 | 77717 | 500 | 100.6434 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 47 days of deadline extension and 155 days of responsibility of the contractor, 80 days in inspections until provisional acceptance | underwork
1663 | 5884492 | "streets in the parish of Lebução" | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 13-09-2019 | 04-06-2020 | 265 | 120 | 79432.34 | 71185.88 | 1 | 71185.88 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unfavorable weather conditions
1664 | 5881993 | Contract Improvement of recommended pedestrian routes, footpaths and paths of tourist interest in Rabaçal | 45233260-9 | Pedestrian ways construction work | FALSE | 2019 | 2021 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 10 | 19-09-2019 | 31-05-2021 | 620 | 270 | 1041906 | 673867.83 | 2 | 673867.83 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | extension due to successive states of emergency due to the covid 19 pandemic
1665 | 5878344 | Requalification of the square located next to the waterfront and in front of the former fire department building (currently GNR) in Quarteira | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 30 | 21-06-2019 | 17-11-2021 | 880 | 270 | 650000 | 600002.44 | 2 | 601300.53 | -1298.09 | 99.7841 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulties in executing the replacement of nos in the water network and delay in carrying out scheduled water cuts. | the value indicated is that of the award of the project plus the price revision.
1666 | 5878140 | Sernancelhe business zone - phase 3 and access roundabout | 45211360-0 | Urban development construction work | FALSE | 2019 | 2020 | Portugal | Sernancelhe | Viseu | 20 | 30 | 26-09-2019 | 16-11-2020 | 417 | 180 | 948918.97 | 818832.79 | 2 | 805044.51 | 13788.28 | 101.7127 | Best value for money: Yes Criterion related to quality Name: Technical Validity of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unforeseen complementary works: inf/dtou/0046/2020 - alteration of public lighting columns and luminaires; execution of wall in reinforced concrete; and underwork due to the non-placement of the luminaires foreseen in the project. | unforeseen complementary works: inf/dtou/0046/2020 - alteration of public lighting columns and luminaires; execution of wall in reinforced concrete; and underwork due to the non-placement of the luminaires foreseen in the project.
1667 | 5877962 | PO 305/2019 - Requalification of Urban Spaces - Requalification of streetFélix Alves Pereira | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 15 | 25-09-2019 | 26-07-2021 | 670 | 80 | 158000 | 156065.2 | 1 | 170990.2 | -14925 | 91.2714 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of work to supply errors and omissions and difficulties in the supply and delivery of materials due to the covid-19 pandemic. | errors and omissions procurement work not included in the initial contract
1668 | 5874644 | Public works contract for the exterior rehabilitation of the facades and roofs of several buildings allocated to R&D on the FCUL campus | 45453100-8 | Refurbishment work | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 25 | 16-09-2019 | 16-04-2020 | 213 | 90 | 155000 | 123636.58 | 1 | 125234.41 | -1597.83 | 98.7241 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | an extension of the execution period was granted due to adverse weather conditions in november and december, which prevented the project from being carried out over multiple days, with a special impact on the execution phase of the paintings. | change in the value of the project due to the need to carry out additional work.
1669 | 5873640 | Contract for "Various Interventions in Street Layouts in the Municipality - 2019" | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2020 | Portugal | Odivelas | Lisboa | 11 | 14 | 04-09-2019 | 31-03-2020 | 209 | 304 | 322376 | 322376 | 2 | 322726 | -350 | 99.8915 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes in the execution period of the project | there were no changes to the value of the project
1670 | 5872569 | Rehabilitation contract for the former kitchen, bar and related annexes of the Faculty of Economics of the University of Porto | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 30 | 05-09-2019 | 03-07-2020 | 302 | 120 | 425000 | 410881.18 | 2 | 445133.63 | -34252.45 | 92.3051 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Global price proposed for the Contract Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extensions duly substantiated, approved by the owner of the project. | work not performed, as well as complementary work.
1671 | 5872509 | 2019.116.11.C1 - SFP SETÚBAL AND CACE - Refurbishment of sanitary facilities and changing rooms | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 01-08-2019 | 12-02-2020 | 195 | 120 | 348780 | 348298.58 | 2 | 348298.58 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1672 | 5871484 | EP-2019(5001)/10012 Rehabilitation of the Sheltering House Pre-Autonomy Project João José Aguiar | 45113000-2 | Siteworks | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 19-09-2019 | 03-06-2020 | 258 | 90 | 220000 | 217298.78 | 1 | 217298.78 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work for security reasons | no change
1673 | 5869369 | CP 25/2019_DEGA - S. Marcos Wastewater (par 012) – albergaria-a-velha | 45232000-2 | Ancillary works for pipelines and cables | TRUE | 2019 | 2021 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 40 | 04-09-2019 | 14-07-2021 | 679 | 150 | 460000 | 389429.18 | 2 | 378424.23 | 11004.95 | 102.9081 | Best value for money: No Criterion related to quality Name: Not applicable Weighting: 0% Criterion related to cost Name: Price, as the sole aspect of contract performance Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
1674 | 5869227 | Requalification of the E.M. 505-2, streetNossa Senhora das Candeias, in Chavão. | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Barcelos | Braga | 3 | 13 | 02-08-2019 | 25-02-2021 | 573 | 60 | 112913.99 | 112833.21 | 1 | 112538.21 | 295 | 100.2621 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension due to operational reasons related to the adverse weather conditions that occurred during the months of october and november 2019, which made it impossible to apply the bituminous layers foreseen in the project, which generated some delay in relation to the approved work plan. | underwork in the amount of 250.00 resulting from underwork carried out in relation to the project due to the lack of execution, namely road markings.
1675 | 5864997 | Intervention at the Cultural Center of Arronches - Replacement of the HVAC and recovery of the roof of the building | 45331220-4 | Air-conditioning installation work | FALSE | 2019 | 2020 | Portugal | Arronches | Portalegre | 12 | 24 | 17-07-2019 | 28-04-2020 | 286 | 90 | 116413.45 | 113702.91 | 1 | 113702.91 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | it was detected on site that two machines were in need of replacement and were working well when the project was carried out.
1676 | 5864628 | Cpn 28/2019/dicp - t- 53/2018 - Improvement of streetJoão Ferreira and access to the soccer field - Milagres | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 22 | 03-07-2019 | 30-04-2020 | 302 | 120 | 436669.98 | 384998.93 | 2 | 384998.93 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A
1677 | 5863814 | EP-2019(5001)/10013 Waterproofing and Interior Improvements at Centro Cultural Casapiano | 45113000-2 | Siteworks | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 18-09-2019 | 14-01-2020 | 118 | 80 | 120000 | 109220 | 1 | 109220 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1678 | 5863126 | "streets in Valongo" | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 13-09-2019 | 20-02-2020 | 160 | 90 | 18867.92 | 15911 | 1 | 15911 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1679 | 5862857 | Public Tender for the Contract to Replace Manhole Covers in the Terminals of the Port of Aveiro | 45310000-3 | Electrical installation work | FALSE | 2019 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 33 | 26-06-2019 | 18-03-2020 | 266 | 30 | 30000 | 22700 | 1 | 21828.81 | 871.19 | 103.991 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the contractual period of 30 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective provisional acceptance certificate. | underwork
1680 | 5862826 | Contract refers to the execution of an urban arrangement in Bairro 1º de Maio, in Santo Estevão, comprising works within the scope of Preparatory Works; Support wall; Earth movement; | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Benavente | Santarém | 16 | 30 | 29-08-2019 | 25-11-2021 | 819 | 60 | 67000 | 58142 | 1 | 47950.08 | 10191.92 | 121.2553 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | following the various suspensions, the execution period was extended for a period equal to the period initially set. | the change in the value of the project was due to complementary works and underwork and also to the revision of prices
1681 | 5860009 | Contract for the Installation of a Video Surveillance System in the City of Olhão | 45314000-1 | Installation of telecommunications equipment | FALSE | 2019 | 2020 | Portugal | Olhão | Faro | 8 | 18 | 20-08-2019 | 27-03-2020 | 220 | 45 | 60570 | 59938.28 | 1 | 59938.28 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in supplying equipment.
1682 | 5859849 | streetPara Todos / Alta - Repaving and Refurbishment of Infrastructures in street of Coutinhos, street of Colégio Novo, street of Fonte Nova and streetJoaquim António de Aguiar. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | Coimbra | Coimbra | 6 | 30 | 04-03-2019 | 17-11-2021 | 989 | 211 | 707130 | 637811.92 | 2 | 628476.17 | 9335.75 | 101.4855 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | legal extension of term | value of additional work, underwork and price revision
1683 | 5859614 | Tocha-Praia da Tocha Adductor - 1st. Phase and remodeling of the water supply network and branches of the ZMC da Tocha - 2nd. Phase | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 20 | 26-06-2019 | 19-05-2021 | 693 | 120 | 210000 | 174415.65 | 1 | 169240.38 | 5175.27 | 103.0579 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension due to weather conditions | underwork
1684 | 5858479 | Surface capture of salt water - Peniche Fishing Port | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Peniche | Leiria | 10 | 14 | 01-08-2019 | 18-10-2021 | 809 | 90 | 200000 | 198430.43 | 1 | 205605.48 | -7175.05 | 96.5103 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work | additional work and underwork
1685 | 5858360 | 100% Quality - Pavement renovation in Basílio Teles Park, Matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 10-09-2019 | 20-08-2020 | 345 | 60 | 98000 | 78400 | 1 | 78400 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Technical Valia Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1686 | 5857928 | EP-2019(5001)/10010 I.S. E ports - ced aacf | 45261420-4 | Waterproofing work | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 09-09-2019 | 03-12-2020 | 451 | 70 | 75000 | 69600.17 | 1 | 57211.34 | 12388.83 | 121.6545 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out the project by the contractor | sanction applied to the contractor for delay in carrying out the project
1687 | 5857240 | "Sadoncelho streets " | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 13-09-2019 | 13-02-2020 | 153 | 90 | 23584.91 | 20794.5 | 1 | 20794.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1688 | 5857238 | Contract for the requalification of the EM 526-1 between the EN 125 and the boundary of the municipality in Guia. | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 16-09-2019 | 23-12-2020 | 464 | 90 | 410000 | 305202.58 | 2 | 291304.01 | 13898.57 | 104.7712 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
1689 | 5855629 | Oe-cp nº 5/2019 Pedestrian and cycle path to the apple tree core | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 19-07-2019 | 15-12-2020 | 515 | 180 | 490508.79 | 364439.35 | 2 | 484378.35 | -119939 | 75.2386 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1690 | 5854023 | Cycleway From Coimbra - Coimbra B / Vale Das Flores / Portela – Lot 1 consisting of all the works to be carried out on the sections of Coimbra B, Avenida de Conimbriga and Lot 2 | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2021 | Portugal | Coimbra | Coimbra | 6 | 33 | 10-05-2019 | 06-08-2021 | 819 | 150 | 2265823 | 759100 | 2 | 692005.94 | 67094.06 | 109.6956 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | graceful extension of term | additional work, underwork and price revision value.
1691 | 5853633 | CP/02/DOM/2019 - Energy Rehabilitation of Public Lighting in São João da Madeira | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2019 | 2019 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 05-06-2019 | 26-11-2019 | 174 | 60 | 502941.09 | 470789 | 2 | 470789 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1692 | 5852053 | NPD-3019016344-AMN - ITED network installation in an AMN building in Quarteira | 45232332-8 | Ancillary works for telecommunications | FALSE | 2019 | 2019 | Portugal | Loulé | Faro | 8 | 15 | 18-09-2019 | 14-12-2019 | 87 | 30 | 36800 | 36075.91 | 1 | 36075.91 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the Procedure Program Weighting: 0% Criterion related to cost Name: The constants of the Procedure Program Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties
1693 | 5851205 | Drainage of rainwater at street of Canteiros/street ofs Corgas - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-09-2019 | 23-04-2021 | 588 | 150 | 152687 | 147720.29 | 1 | 131386.58 | 16333.71 | 112.4318 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 30 days of graceful extension and 10 days for scheduling and carrying out inspections | additional work and underwork
1694 | 5850522 | Execution of the shading of the Melides Beach Car Park | 45422100-2 | Woodwork | FALSE | 2018 | 2020 | Portugal | Grandola | Setúbal | 17 | 20 | 11-02-2019 | 20-02-2020 | 374 | 45 | 76255.92 | 68481.9 | 1 | 71245.3 | -2763.4 | 96.1213 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this suspension due to the delay in the approval of the 1st contractual amendment | contract modification
1695 | 5849803 | Public Works Contract No. 27/DRA/2019 for the execution of the "CONSTRUCTION CONTRACT FOR HYDRAULIC CORRECTION OF RIBEIRA DA CALHETA, SÃO MATEUS, PICO ISLAND" | 45246000-3 | River regulation and flood control works | FALSE | 2019 | 2020 | Portugal | Madalena | Região Autónoma dos Açores | 15 | 4 | 07-08-2019 | 26-03-2020 | 232 | 180 | 300000 | 279800 | 2 | 279800 | 0 | 100 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out in the expected time
1696 | 5849501 | Construction of support walls in granite masonry in the parishes of Cristelos and Vilar do Torno and Alentém | 45262512-3 | Dressed stonework | FALSE | 2019 | 2020 | Portugal | Lousada | Porto | 13 | 12 | 12-09-2019 | 09-06-2020 | 271 | 90 | 40564.5 | 40525 | 1 | 40525 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1697 | 5849258 | Execution of a public works contract for the construction of raised walkways - Encarnação | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 18 | 16-08-2019 | 26-04-2020 | 254 | 29 | 125000 | 109000 | 1 | 92673.15 | 16326.85 | 117.6177 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this was due to the difficulty in obtaining policing to monitor the project, and the occurrence of rains that made it impossible to carry out the project temporarily. | there were changes to the project.
1698 | 5849177 | Replacement of the synthetic turf at the Field Hockey Stadium | 45236119-7 | Repair work on sports fields | FALSE | 2018 | 2020 | Portugal | Lousada | Porto | 13 | 9 | 10-09-2019 | 17-02-2020 | 160 | 45 | 199768.03 | 183868.8 | 1 | 207328.59 | -23459.79 | 88.6847 | Best value for money: Yes Criterion related to quality Name: Synthetic grass guarantee Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | complementary works and price revision
1699 | 5848532 | Contract for Energy Efficiency in Public Lighting in the Municipality of Arouca - 1st Phase. | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2019 | 2020 | Portugal | Arouca | Aveiro | 1 | 30 | 17-09-2019 | 23-10-2020 | 402 | 240 | 361166.46 | 316980 | 2 | 320330 | -3350 | 98.9542 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | final report approved on 09.16.2020 | additional work and underwork
1700 | 5847810 | Requalification of Jardim das Laranjeiras - Proc. No. 28/2019 | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 10-07-2019 | 12-10-2021 | 825 | 180 | 350000 | 344538.86 | 2 | 344575.04 | -36.18 | 99.9895 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the inspection for the purpose of provisional acceptance was carried out as soon as the project was completed, and after the verbal request by the contractor, that is, the completion of the project took place within a period of 11 days after the final measurement, reason which is considered within the legal deadlines. | value of underwork and price revision.
1701 | 5843040 | Pavement Recovery on Av. Garcia de Orta and Adjacent Roundabouts | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Montijo | Setúbal | 17 | 15 | 20-08-2019 | 03-02-2020 | 167 | 60 | 165000 | 145642.5 | 1 | 142901.94 | 2740.56 | 101.9178 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, in deadlines of price as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was only delay in scheduling the inspection | underwork report in the amount of €2,740.56
1702 | 5843009 | Extension of the route PR1 - Jans Trail | 45233250-6 | Surfacing work except for roads | FALSE | 2019 | 2021 | Portugal | Nisa | Portalegre | 12 | 30 | 02-09-2019 | 27-09-2021 | 756 | 365 | 400075.73 | 319498.92 | 2 | 320262 | -763.08 | 99.7617 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Cost or price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of price revision indices. | price revision in the amount of €763.08.
1703 | 5842486 | 2019.116.09.C1 - SFP SETÚBAL - Repair of exterior facades | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 14 | 05-06-2019 | 20-12-2019 | 198 | 150 | 233000 | 219836.92 | 1 | 219836.92 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
1704 | 5842416 | Sanitation in Vassal | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 11-09-2019 | 22-04-2020 | 224 | 180 | 207547.17 | 179500 | 1 | 179500 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes
1705 | 5842352 | The object is the execution of works on the aforementioned streets . | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 09-09-2019 | 19-06-2020 | 284 | 266 | 423327.5 | 419827 | 2 | 419827 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reinforcement of equipment and planned labour.
1706 | 5841884 | streets in the Parish of Friões | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 13-09-2019 | 04-05-2020 | 234 | 120 | 123734.82 | 123617.86 | 1 | 121687.86 | 1930 | 101.586 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to weather conditions and non-delivery of material | underwork worth € 1,930.00
1707 | 5841609 | Rehabilitation of the street art work of the volunteer firefighters on the street of the vouga valley | 45221119-9 | Bridge renewal construction work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 24-07-2019 | 28-02-2020 | 219 | 180 | 140000 | 137112.91 | 1 | 137112.91 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation of the project deadline by 10 days
1708 | 5841509 | Correction of constructive pathologies – association house, transport coordination center and intermodal center | 45213000-3 | Construction work for commercial buildings, warehouses and industrial buildings, buildings relating to transport | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 01-08-2019 | 30-04-2020 | 273 | 90 | 100000 | 94400 | 1 | 94400 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1709 | 5841129 | Cpn 33/2019/dicp - t-03/2019 - rehabilitation of the ervideira lagoon - parish of coimbrão | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 25-07-2019 | 06-01-2020 | 165 | 150 | 279230 | 216945.12 | 1 | 220205.99 | -3260.87 | 98.5192 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary works - earthworks and walkway elevation
1710 | 5839826 | Cpn 21/2019/dicp - t-15/2019 - rehabilitation and improvement of several streets in the municipality of leiria | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 21 | 13-06-2019 | 06-03-2020 | 267 | 120 | 3194870 | 323733.5 | 2 | 323733.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | relevant recommendations from the smas entity, in the execution of projects for the execution of buried infrastructure for the networks that they have at the site of the contract
1711 | 5834352 | 2019/78-DGEP - Reorganization of the intersection of streetOeiras do Piauí and Av. doctor Francisco Sá Carneiro and Av. Do ultramar, oeiras | 45233128-2 | Roundabout construction work | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 24 | 22-08-2019 | 21-09-2021 | 761 | 120 | 410417.43 | 396846.4 | 2 | 430062.78 | -33216.38 | 92.2764 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1712 | 5833597 | Repair of granite cube floors in different locations | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Lousada | Porto | 13 | 9 | 04-09-2019 | 04-09-2020 | 366 | 60 | 37000 | 36120 | 1 | 36120 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | adverse weather conditions
1713 | 5832915 | Construction of the ecovia between Sarzeda, Sernancelhe, Vila da Ponte and Ferreirim, including tours - phase 1.1 | 45233161-5 | Footpath construction work | TRUE | 2019 | 2020 | Portugal | Sernancelhe | Viseu | 20 | 26 | 02-09-2019 | 24-08-2020 | 357 | 150 | 330794.93 | 252297.25 | 2 | 279640.71 | -27343.46 | 90.2219 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | additional work | additional work and underwork
1714 | 5831094 | 2019/58-DGEP - Maintenance and execution of pedestrian and road pavements in Oeiras and Paço-de-Arcos | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 15 | 03-09-2019 | 20-05-2021 | 625 | 180 | 200213.4 | 171300 | 1 | 171300 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1715 | 5829646 | Contract 117/gebalis/2019 - neighborhood dr. Alfredo Bensaúde, lots A1 to C13 - Building rehabilitation works | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 10 | 12-08-2019 | 13-08-2021 | 732 | 300 | 842470.47 | 769611.46 | 2 | 731076.38 | 38535.08 | 105.271 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complexity of work
1716 | 5828512 | Paving paths in various locations in the municipality | 45233222-1 | Paving and asphalting works | FALSE | N/A | 2018 | Portugal | São Brás de Alportel | Faro | 8 | N/A | 28-08-2018 | 06-11-2018 | 70 | 60 | N/A | 103133.4 | 1 | 103133.4 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
1717 | 5827686 | Construction of showers to support the Murteira football field, in Samora Correia | 45212230-7 | Installation of changing rooms | FALSE | 2018 | 2021 | Portugal | Benavente | Santarém | 16 | 23 | 21-05-2019 | 03-11-2021 | 897 | 300 | 365000 | 364559.49 | 2 | 368956 | -4396.51 | 98.8084 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the changes to the execution period of the project were due to the extension of the deadline by 140 days, due to (covid-19), which limits the number of workers in the project and the delay in the delivery of materials. | change in the value of the project was due to over and underwork and price revision
1718 | 5826099 | Improvement works in schools of the 1st cycle of elementary education and kindergartens in the municipality of cascais | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Cascais | Lisboa | 11 | 5 | 02-09-2019 | 26-11-2020 | 451 | 57 | 1872960.97 | 370655.85 | 2 | 369523.79 | 1132.06 | 100.3064 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A |  | work not done
1719 | 5825796 | 100% Quality - Flooring in the Municipality in 2019 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 04-09-2019 | 21-04-2020 | 230 | 90 | 581050 | 142550 | 1 | 142550 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1720 | 5825770 | 100% Quality - Flooring in the Municipality in 2019 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Matosinhos | Porto | 13 | 15 | 04-09-2019 | 21-04-2020 | 230 | 90 | 581050 | 246444.6 | 1 | 246444.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
1721 | 5825646 | Construction of a WWTP in Canaveses | 45232421-9 | Sewage treatment works | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 30-08-2019 | 23-03-2020 | 206 | 120 | 41360.67 | 39955.64 | 1 | 39955.64 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1722 | 5825338 | Requalification of the Public Space of Av.ª 25 de Abril, Pontinha | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Odivelas | Lisboa | 11 | 14 | 04-09-2019 | 15-01-2021 | 499 | 90 | 360280 | 349669.84 | 2 | 349669.84 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was consigned on 10-07-2019, having been suspended on 11-13-2019 and restarted on 01-06-2020. the project was suspended for reasons of public interest relating to the maintenance of normal road traffic during the christmas season. | there were no changes to the value of the project
1723 | 5825103 | Construction of a Kennel in the Parish of Infias - Vizela | 45223600-2 | Dog kennels construction work | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 21 | 09-09-2019 | 18-12-2020 | 466 | 120 | 271699.2 | 259850 | 2 | 276049.97 | -16199.97 | 94.1315 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | additional work and underwork
1724 | 5824696 | 2016.095.01.C1 - FOR-MAR ​​Peniche - exterior rehabilitation of the building | 45259000-7 | Repair and maintenance of plant | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 24-06-2019 | 02-04-2020 | 283 | 120 | 298000 | 246766.58 | 1 | 246766.58 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions
1725 | 5824505 | Improvement works in schools of the 1st cycle of elementary education and kindergartens in the municipality of cascais | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Cascais | Lisboa | 11 | 5 | 30-08-2019 | 23-03-2020 | 206 | 50 | 1872960.97 | 390493.97 | 2 | 390493.97 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
1726 | 5824459 | Improvement works in schools of the 1st cycle of elementary education and kindergartens in the municipality of cascais | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Cascais | Lisboa | 11 | 5 | 30-08-2019 | 17-02-2020 | 171 | 58 | 1872960.97 | 332655.96 | 2 | 332655.96 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
1727 | 5823260 | Paving by E.M. 304 - Meruf | 45233220-7 | Surface work for roads | FALSE | 2019 | 2019 | Portugal | Monção | Viana do Castelo | 18 | 14 | 10-05-2019 | 02-09-2019 | 115 | 60 | 346123.8 | 262901.1 | 2 | 262901.1 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1728 | 5823128 | Energy efficiency in municipal buildings in Vila Pouca de Aguiar | 45321000-3 | Thermal insulation work | FALSE | 2019 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 04-09-2019 | 22-09-2021 | 749 | 270 | 1230302.28 | 256575.79 | 2 | 209083.65 | 47492.14 | 122.7144 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | pandemic (covid 19). | job suppression and price revision.
1729 | 5822941 | Energy efficiency in municipal buildings in Vila Pouca de Aguiar | 45321000-3 | Thermal insulation work | FALSE | 2019 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 04-09-2019 | 24-09-2021 | 751 | 270 | 1230302.28 | 102264.22 | 1 | 66253.25 | 36010.97 | 154.3535 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | pandemic (covid 19). | job suppression and price revision.
1730 | 5821430 | Requalification of the River Beach of Ronqueira | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2018 | 2021 | Portugal | Tábua | Coimbra | 6 | 24 | 23-04-2019 | 23-09-2021 | 884 | 365 | 345978 | 336032.9 | 2 | 335865.47 | 167.43 | 100.0499 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change in the execution period of the project | underwork
1731 | 5820921 | streets in Veiga de Lila | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 30-08-2019 | 13-02-2020 | 167 | 90 | 28301.89 | 28200 | 1 | 27765 | 435 | 101.5667 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion | underwork worth €435.00
1732 | 5819308 | Construction of a hydraulic passage for crossing a railway, Póvoa de Baixo, Paços de Brandão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 24 | 30-08-2019 | 04-11-2020 | 432 | 70 | 30000 | 28662.98 | 1 | 37467.48 | -8804.5 | 76.501 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 257 days grace period extension | complementary works
1733 | 5819271 | Requalification of roundabouts in Romariz - Rotunda do Chapa, Roundabout street of Serra and Roundabout street ofs Lameiras | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 30-08-2019 | 20-03-2020 | 203 | 60 | 22856 | 21223.13 | 1 | 22848.08 | -1624.95 | 92.888 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contractor completed the project ahead of schedule. | complementary works
1734 | 5819021 | Repaving of streets in São Martinho do Peso | 45432112-2 | Laying of paving | FALSE | 2019 | 2020 | Portugal | Mogadouro | Bragança | 4 | 21 | 14-08-2019 | 12-11-2020 | 456 | 365 | 283499.72 | 248837.05 | 1 | 248837.05 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Good Performance Guarantee Weighting: 60% Criterion related to cost Name: Criterion of the Economically Most Advantageous Proposal-Article 74.º, nº1, subparagraph b) Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | "the covid 19 outbreak that caused delays in the delivery of raw materials and equipment repairs"; "torrional rains that were felt in early september" | no change
1735 | 5816105 | Rehabilitation of the elementary and High school dr. José Casimiro Matias, in Almeida | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Almeida | Guarda | 9 | 18 | 21-06-2018 | 20-08-2019 | 425 | 75 | 198860 | 174227.55 | 1 | 196719.41 | -22491.86 | 88.5665 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension and legal extension | existence of over and underwork
1736 | 5815975 | EP-2019(5001)/10011 Improvement/Rehabilitation of CA António do Couto | 45212410-3 | Construction work for lodging buildings | TRUE | 2019 | 2020 | Portugal | Sintra | Lisboa | 11 | 14 | 28-08-2019 | 22-06-2020 | 299 | 90 | 190000 | 188488.88 | 1 | 188488.88 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of security and the covid 19 pandemic | no change
1737 | 5815742 | Repair of the playground at the Almeida Kindergarten | 45236290-9 | Repair work on recreational areas | FALSE | 2019 | 2021 | Portugal | Almeida | Guarda | 9 | 18 | 08-08-2019 | 07-01-2021 | 518 | 75 | 49635.2 | 43993.29 | 1 | 48662.01 | -4668.72 | 90.4058 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal in the modality provided for in paragraph b) of paragraph 1 of article 74 of the CC Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to carry out additional work | complementary works and price revision
1738 | 5815465 | Cpn 13/2019/dicp - t-08/2019 - requalification of the road surface of en 356-1, in the section between ic2-azoia and the fire department roundabout, maceira - municipality of leiria | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 15 | 13-05-2019 | 20-02-2020 | 283 | 60 | 725270.7 | 557697.02 | 2 | 557697.02 | 0 | 100 | Best value for money: No Criterion related to quality Name: N.A. Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1739 | 5814581 | Proc. Nº 20/EOP/DCOP/2018 - Improvement of rainwater drainage and water lines in the parishes of Cascais/Estoril and Carcavelos/Parede | 45232130-2 | Storm-water piping construction work | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 30 | 15-07-2019 | 04-11-2021 | 843 | 567 | 3959999.4 | 3167933.53 | 3 | 3167933.53 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | covid-19 pandemic
1740 | 5814501 | Improvement, expansion, repair and improvements in schools in the municipality-schools in the eng. duarte pacheco | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Loulé | Faro | 8 | 9 | 19-07-2019 | 08-03-2021 | 598 | 45 | 318000 | 288467.16 | 2 | 288467.16 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | there were no works left
1741 | 5813485 | streets in Alpande | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 29-08-2019 | 11-02-2020 | 166 | 90 | 18867.92 | 18550 | 1 | 18550 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | early completion
1742 | 5813110 | They include: - water network works, drainage network, rainwater drainage network, electrical infrastructure, infrastructure and telecommunications, gas distribution network, infrastructure | 45211360-0 | Urban development construction work | FALSE | 2019 | 2021 | Portugal | Barreiro | Setúbal | 17 | 20 | 26-08-2019 | 16-07-2021 | 690 | 180 | 1550000 | 1489919.07 | 3 | 1185977.33 | 303941.74 | 125.628 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | article 370 | complementary works
1743 | 5812668 | Renovation of the Water Supply Network in the Locality of Mata da Curia | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2020 | Portugal | Anadia | Aveiro | 1 | 15 | 09-05-2019 | 12-05-2020 | 369 | 180 | 167393.74 | 154118.81 | 1 | 154118.81 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1744 | 5809569 | Requalification of the Industrial Zone of Alto da Cruz - Santo Tirso | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Santo Tirso | Porto | 13 | 8 | 12-08-2019 | 16-02-2021 | 554 | 210 | 971870.7 | 874490.27 | 2 | 929871 | -55380.73 | 94.0443 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the project did not change the execution period. | the execution of complementary work, as well as the non-performance of some contractual work (underwork)
1745 | 5809154 | Requalification of the school of the 1st cycle of elementary education in Sobretâmega - parish of Sobretâmega | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 22-08-2019 | 10-01-2020 | 141 | 90 | 145825.21 | 131900 | 1 | 131900 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work in point a) article 365 of the "public procurement code".
1746 | 5808098 | Realization of the contract for the requalification/remodeling of the old wing of ERPI - Residential Structure for Elderly People. | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 30 | 16-08-2019 | 16-09-2020 | 397 | 240 | 216956.69 | 215999.94 | 1 | 215517.06 | 482.88 | 100.2241 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal (VTP) Weighting: 50% Criterion related to cost Name: Price (P) Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension due to work on the electricity grid and vinyl supply (delays caused by covid-19). | the reduction in value (€482.88) is due to a replacement of the material applied to the roof.
1747 | 5807594 | Oe - cp nº 3/2019 "pedestrian and cycle path structuring the north / south connections" | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 25-06-2019 | 23-02-2021 | 609 | 365 | 917613.34 | 723151.95 | 2 | 667268.26 | 55883.69 | 108.375 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1748 | 5807530 | Stabilization of Excavation Slopes between km 56+550 and 56+960 (LE+LD) of the Douro Line | 45234100-7 | Railway construction works | FALSE | 2019 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 24 | 27-08-2019 | 18-02-2021 | 541 | 150 | 365000 | 365000 | 2 | 359421 | 5579 | 101.5522 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register | nothing to register
1749 | 5807483 | En16, km65+900, replacement of the embankment support wall | 45233142-6 | Road-repair works | FALSE | 2019 | 2021 | Portugal | Vouzela | Viseu | 20 | 14 | 22-08-2019 | 21-06-2021 | 669 | 90 | 185000 | 175647.9 | 1 | 156553.7 | 19094.2 | 112.1966 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions | underwork
1750 | 5807428 | Contract for the Alteration and Conservation of the Municipal Pavilion of Castro Verde | 45212290-5 | Repair and maintenance work in connection with sports facilities | TRUE | 2019 | 2020 | Portugal | Castro Verde | Beja | 2 | 15 | 14-08-2019 | 16-10-2020 | 429 | 180 | 348000 | 331753.73 | 2 | 331753.73 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the term of this contract elapsed within the established period
1751 | 5807165 | 2019/121 - DCAD - New DCAD facilities in Vila Fria: Reconversion of the changing rooms on the 3rd Floor | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 15 | 20-08-2019 | 19-07-2021 | 699 | 90 | 94000 | 93710.58 | 1 | 96195.2 | -2484.62 | 97.4171 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1752 | 5806847 | Bituminous resurfacing - July 2019 | 45233251-3 | Resurfacing works | FALSE | 2019 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 26-08-2019 | 22-06-2021 | 666 | 120 | 255090 | 252787.86 | 2 | 246738.86 | 6049 | 102.4516 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had suspensions | the project had underwork
1753 | 5805398 | Contract process nº 09/2019 - Rehabilitation of municipal roads (roads and streets ) and road safety - Infrastructure damaged by the 2017 fires - Municipal Emergency Fund | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Mação | Santarém | 16 | 10 | 20-08-2019 | 25-11-2020 | 463 | 180 | 1811971.91 | 1288245.78 | 3 | 1288245.78 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to say | nothing to say
1754 | 5805238 | Urban rehabilitation of streetCapitão Lebre | 45232451-8 | Drainage and surface works | FALSE | N/A | 2021 | Portugal | Aveiro | Aveiro | 1 | N/A | 21-12-2018 | 10-08-2021 | 963 | 60 | N/A | 75000 | 1 | 88288.87 | -13288.87 | 84.9484 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | due to the need to replace the water supply pipe by the adra entity and the formalization of the contract for complementary works | due to the verification of the technical specifications of the different works to be carried out and their adequacy to the local execution conditions
1755 | 5800892 | Flooring Silveirinha Industrial Area - São João de Ver | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 27-08-2019 | 01-09-2020 | 371 | 180 | 259606 | 209808.84 | 1 | 188961.23 | 20847.61 | 111.0327 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 20 days of extension granted by the owner of work, 19 days until the contractor requests the inspection, 13 days regarding the scheduling of the same for the purposes of provisional reception | underwork
1756 | 5800685 | streets in Lamas | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 27-08-2019 | 30-01-2020 | 156 | 90 | 23584.91 | 23307 | 1 | 23307 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1757 | 5797856 | Proc. No. 22/EOP/DCOP/2018 Maintenance of pavements in the municipality of Cascais 2018-2020 | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 30-07-2019 | 05-01-2021 | 525 | 567 | 3961865 | 910959.19 | 2 | 910959.19 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | covid-19 pandemic decreed by who
1758 | 5797802 | Rehabilitation of the Noble Staircase and replacement of rainwater pipes - courtyard 4 | 45453100-8 | Refurbishment work | TRUE | 2019 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 04-06-2019 | 19-11-2019 | 168 | 90 | 130000 | 120102.62 | 1 | 120102.62 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price or Cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1759 | 5797794 | Proc. No. 22/EOP/DCOP/2018 Maintenance of pavements in the municipality of Cascais 2018-2020 | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 30-07-2019 | 05-01-2021 | 525 | 567 | 3961865 | 540077.83 | 2 | 540077.83 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | covid-19 pandemic decreed by who
1760 | 5795938 | Contract for the Rehabilitation of Public Spaces in the Social Neighborhood of Pade | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2020 | Portugal | Arouca | Aveiro | 1 | 30 | 26-08-2019 | 22-05-2020 | 270 | 90 | 71794.3 | 64816.15 | 1 | 63505.17 | 1310.98 | 102.0644 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the Price or cost as the only skewer of the Execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | additional work and underwork
1761 | 5794895 | Cpn 26/2019/dicp - t-22/2019 - execution of buried infrastructure for the ip and bt network and rainwater drainage on av. | 45231110-9 | Pipelaying construction work | FALSE | 2019 | 2021 | Portugal | Leiria | Leiria | 10 | 14 | 13-06-2019 | 03-02-2021 | 601 | 90 | 199717.65 | 153123.88 | 1 | 153123.88 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1762 | 5794849 | Cpn 29/2019/dicp - t-04/2019 - urban arrangement in Largo do Paço - Caranguejeira | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 18 | 12-06-2019 | 14-04-2020 | 307 | 120 | 174832.5 | 130615 | 1 | 130615 | 0 | 100 | Best value for money: No Criterion related to quality Name: N.A. Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change
1763 | 5794497 | "streets in the parish of S. João de Corveira" | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 13-08-2019 | 27-01-2020 | 167 | 120 | 84905.66 | 76833 | 1 | 76833 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1764 | 5794366 | 2018.116.05.C1 - SFP Setúbal - Telecommunications Infrastructures | 45310000-3 | Electrical installation work | TRUE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 15 | 19-07-2019 | 19-03-2021 | 609 | 150 | 352000 | 274000 | 2 | 275967 | -1967 | 99.2872 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary work and suppression of work
1765 | 5794080 | Requalification of the school of the 1st cycle of elementary education - Barroca - Rio de Galinhas - parish of Marco | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 16-07-2019 | 17-01-2020 | 185 | 75 | 215443.36 | 189400 | 1 | 189400 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of works
1766 | 5793403 | Refurbishment of the garden Adriano José Carvalho e Melo (Municipal Garden) Marco - Marco de Canaveses | 45112712-9 | Landscaping work for gardens | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 29-07-2019 | 12-08-2020 | 380 | 180 | 309176.65 | 276440.46 | 2 | 275465.45 | 975.01 | 100.354 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension term | underwork
1767 | 5792210 | Contract for execution of the Porto Formoso pipeline | 45000000-7 | Construction work | TRUE | 2019 | 2020 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 16-08-2019 | 17-09-2020 | 398 | 270 | 350000 | 324473.58 | 2 | 324473.58 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality of Work Execution Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline | price review
1768 | 5791163 | Proc. No. 22/EOP/DCOP/2018 Maintenance of pavements in the municipality of Cascais 2018-2020 | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 22-07-2019 | 05-01-2021 | 533 | 567 | 3961865 | 996744.2 | 2 | 996744.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1769 | 5791133 | Proc. No. 22/EOP/DCOP/2018 Maintenance of pavements in the municipality of Cascais 2018-2020 | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 14 | 22-07-2019 | 05-01-2021 | 533 | 567 | 3961865 | 721644.77 | 2 | 721644.77 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | critical situation that the country is going through in relation to the covid-19 pandemic decreed by the who.
1770 | 5789191 | streets in Possacos | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-08-2019 | 10-02-2020 | 174 | 90 | 86613.4 | 72688.5 | 1 | 72688.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1771 | 5789147 | streets in the Parish of Padrela and Tazém | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 20-08-2019 | 10-02-2020 | 174 | 90 | 41215.45 | 39619 | 1 | 31119 | 8500 | 127.3145 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork worth €8,500.00
1772 | 5789064 | streets in Argeriz | 45233252-0 | Surface work for streets | FALSE | 2019 | 2019 | Portugal | Valpaços | Vila Real | 19 | 15 | 19-08-2019 | 26-12-2019 | 129 | 90 | 32733.68 | 31750 | 1 | 31750 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1773 | 5788981 | Improvement and requalification of streetD.ª Amélia Castelo, up to Av.ª da Liberdade, in Vilarandelo | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 19-08-2019 | 03-06-2020 | 289 | 120 | 144406.17 | 137900 | 1 | 137900 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | due to unfavorable weather conditions
1774 | 5788838 | "Construction or improvement of fence walls for opening streets , roads or municipal paths" - (Veiga de Lila) | 45262512-3 | Dressed stonework | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 21-08-2019 | 09-03-2020 | 201 | 90 | 38928.5 | 31486.36 | 1 | 21943.7 | 9542.66 | 143.487 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension for 30 days | underwork worth € 9,542.66
1775 | 5788586 | Contract for "Coercive Execution of Works in Bairro dos Pedernais, in the town of Ramada" | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Odivelas | Lisboa | 11 | 14 | 02-08-2019 | 27-08-2020 | 391 | 120 | 290335.5 | 203240.62 | 1 | 203240.62 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to say. | nothing to say.
1776 | 5788371 | Contract for "Other Interventions in streets in the Municipality for 2019" | 45233222-1 | Paving and asphalting works | FALSE | 2019 | 2020 | Portugal | Odivelas | Lisboa | 11 | N/A | 31-07-2019 | 31-03-2020 | 244 | 153 | 173900 | 173900 | 1 | 173900 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes in the execution period of the project. | there were no changes to the value of the project
1777 | 5787681 | New Pontinha Market | 45213141-3 | Covered market construction work | FALSE | 2019 | 2021 | Portugal | Odivelas | Lisboa | 11 | 20 | 30-07-2019 | 25-01-2021 | 545 | 180 | 610879.5 | 604700 | 2 | 604700 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without changes | without changes
1778 | 5786938 | Total Refurbishment Works for Seven Apartments in Coimbra, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2019 | 2020 | Portugal | Coimbra | Coimbra | 6 | 21 | 26-06-2019 | 10-01-2020 | 198 | 150 | 298000 | 284845.55 | 2 | 284845.55 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1779 | 5785561 | Execution of Alternative Public Transport Routes and Temporary Parking Areas - Sacavém | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Loures | Lisboa | 11 | N/A | 25-07-2019 | 06-02-2020 | 196 | 75 | 206000 | 181582.49 | 1 | 181582.49 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 4 | FALSE | N/A | N/A | N/A | N/A | FALSE
1780 | 5785302 | Rehabilitation of streets in the area surrounding the town hall building - PARU of Marco de Canaveses | 45233160-8 | Paths and other metalled surfaces | FALSE | 2019 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 31-07-2019 | 15-02-2021 | 565 | 240 | 428181.2 | 372345.65 | 2 | 324609.6 | 47736.05 | 114.7057 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project had 2 extensions (45 days + 70 days = 115 days) | the project had underwork in the amount of € 47,736.05
1781 | 5783981 | Reprofiling of Travessa Nossa Senhora da Saúde - São Bernardo | 45211360-0 | Urban development construction work | FALSE | 2019 | 2019 | Portugal | Aveiro | Aveiro | 1 | 21 | 02-08-2019 | 23-12-2019 | 143 | 60 | 56284.25 | 51000 | 1 | 55192 | -4192 | 92.4047 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
1782 | 5782464 | streets in the Parish of Sonim and Barreiros | 45233252-0 | Surface work for streets | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 08-08-2019 | 18-08-2020 | 376 | 120 | 98082.04 | 91964 | 1 | 91964 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | occurrence of unfavorable weather conditions
1783 | 5781861 | New access to CHMA - Centro Hospitalar do Médio Ave - Santo Tirso | 45233120-6 | Road construction works | FALSE | 2019 | 2020 | Portugal | Santo Tirso | Porto | 13 | 21 | 12-08-2019 | 01-07-2020 | 324 | 150 | 188049.46 | 179454.74 | 1 | 191521.25 | -12066.51 | 93.6996 | Best value for money: Yes Criterion related to quality Name: Valia Técnica, safety management, quality control and environmental management systems Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the existence of complementary works. | the existence of complementary works
1784 | 5781608 | Rehabilitation works for block 34 of Bairro Cerco do Porto (EM.001.2019.073) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 30 | 06-08-2019 | 14-05-2021 | 647 | 210 | 575000 | 563358.73 | 2 | 549350.24 | 14008.49 | 102.55 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract works were carried out according to the project. | additional work worth €39,895.80 and unforeseen work worth €53,904.29
1785 | 5781599 | Execution of Works in Various streets . | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 06-08-2019 | 11-02-2020 | 189 | 120 | 187409.5 | 186830.7 | 1 | 186830.7 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | with the completion of the project, the "plan for the prevention and management of construction and demolition waste" was requested from the successful tenderer, which was delayed in delivery.
1786 | 5781572 | Supply and assembly of a warehouse at the Régua Maritime Delegation | 45113000-2 | Siteworks | FALSE | 2019 | 2019 | Portugal | Peso da Régua | Vila Real | 19 | 15 | 19-08-2019 | 13-12-2019 | 116 | 60 | 85000 | 80500 | 1 | 80500 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties
1787 | 5780653 | Carrying out work necessary for the exterior and interior rehabilitation of buildings as well as building demolition | 45400000-1 | Building completion work | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 15 | 09-08-2019 | 08-03-2021 | 577 | 210 | 280000 | 273292.21 | 2 | 314666.58 | -41374.37 | 86.8514 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allotted 75 days to the execution of the projects corresponding to the 3 additional contracts, respectively, 15, 30 and 30 days | celebration of 3 additional contracts: approval of complementary works in the global amount of €68,654.17 and suppression of works (underwork) in the global amount of €29,414.00. approval by order of 01.09.2021 of the definitive calculation of the price revision in the amount of €2,134.21.
1788 | 5780580 | Contract for the execution of basic sanitation and paving of streetHermano Mota | 45000000-7 | Construction work | FALSE | 2019 | 2020 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 16-08-2019 | 26-05-2020 | 284 | 240 | 398500 | 316000 | 2 | 316000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality of Work Execution Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline | price review
1789 | 5779918 | EP-2019(5001)/10009 Waterproofing and Miscellaneous Repairs at the S. Marçal Support Home | 45261420-4 | Waterproofing work | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 12-08-2019 | 03-01-2020 | 144 | 70 | 75000 | 73435.56 | 1 | 73435.56 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | no change | no change
1790 | 5776282 | 5010023002 - Contract called "Algarve Line - Section Tunes to Vila Real de Santo António - Stabilization of excavation slopes between km 371,700 and km 371,900" | 45111230-9 | Ground-stabilisation work | FALSE | 2018 | 2021 | Portugal | Tavira | Faro | 8 | 33 | 07-08-2019 | 30-09-2021 | 785 | 154 | 400000 | 385692.55 | 2 | 414312.96 | -28620.41 | 93.0921 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 65% Technical Valuation 15% Safety Management System 10% Quality Control System 5% Environmental Management System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
1791 | 5776123 | Replacement of the outer spans in the Captaincy of the Port of Caminha | 45262522-6 | Masonry work | FALSE | 2019 | 2019 | Portugal | Caminha | Viana do Castelo | 18 | 15 | 13-08-2019 | 22-11-2019 | 101 | 30 | 40000 | 35816.66 | 1 | 35816.66 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties
1792 | 5774200 | Contract for the alteration and adaptation of a building in Quarteira | 45262522-6 | Masonry work | FALSE | 2019 | 2019 | Portugal | Loulé | Faro | 8 | 15 | 13-08-2019 | 14-12-2019 | 123 | 135 | 80600 | 27787.72 | 1 | 27787.72 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | agreement between the parties
1793 | 5774006 | Contract for the Requalification of streetNova do Visconde, São Pedro | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 15 | 05-08-2019 | 21-04-2020 | 260 | 120 | 349500 | 345637.12 | 2 | 345637.12 | 0 | 100 | If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project.
1794 | 5773450 | Construction of the chestnut interpretive center | 45212312-6 | Exhibition centre construction work | TRUE | 2019 | 2020 | Portugal | Viseu | Viseu | 20 | 30 | 12-08-2019 | 11-12-2020 | 487 | 180 | 245800 | 237000 | 1 | 286678.71 | -49678.71 | 82.6709 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | climate change, under and over work | complementary work, underwork and price revision.
1795 | 5772562 | Contract for the repair of ruptures in pipes and branches of the water supply network in the municipality of Albufeira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 08-08-2019 | 13-07-2020 | 340 | 480 | 250000 | 247558.8 | 1 | 246406.9 | 1151.9 | 100.4675 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | €1151.90 remained to be invoiced
1796 | 5771975 | Recovery Works for Coverings, Facades and Exterior Works in Three Buildings in Bragança, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 21 | 01-08-2019 | 01-12-2019 | 122 | 120 | 220000 | 132000.01 | 1 | 132000.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price/cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1797 | 5771615 | Construction or improvement and municipal roads and paths - (EM551 and CM1119) - exit to Crasto, Vales and Zebras | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 07-08-2019 | 25-05-2020 | 292 | 120 | 85893.65 | 83992.92 | 1 | 82692.74 | 1300.18 | 101.5723 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects | works not performed
1798 | 5771604 | streets in Vilartão | 45233252-0 | Surface work for streets | FALSE | 2019 | 2019 | Portugal | Valpaços | Vila Real | 19 | 15 | 07-08-2019 | 10-12-2019 | 125 | 60 | 23584.91 | 22760.91 | 1 | 22760.91 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1799 | 5769418 | Contract for the Requalification of the Main Entrance of the ISCSP | 45261100-5 | Roof-framing work | FALSE | 2018 | 2018 | Portugal | N/A | N/A | N/A | 14 | 06-06-2018 | 03-10-2018 | 119 | 90 | 179000 | 30032.64 | 1 | 30032.64 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | agreement between the parties
1800 | 5769062 | Execution of a contract for the requalification of the ISCSP bar | 45400000-1 | Building completion work | FALSE | 2019 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 29-07-2019 | 22-11-2019 | 116 | 45 | 119000 | 76800 | 1 | 76800 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Bid Price Weighting: 50% Criterion related to cost Name: Delivery Period and Warranty Period Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | intercurrences in the execution of the project
1801 | 5768920 | DPES-CPúblico 5/2019-Increased sectorization and measurement in the water supply system - Installation of 27 flowmeters | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2021 | Portugal | Coimbra | Coimbra | 6 | 21 | 04-06-2019 | 19-08-2021 | 807 | 150 | 230000 | 222525.03 | 1 | 205700.39 | 16824.64 | 108.1792 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | awaiting elements for the contractor | there was underwork
1802 | 5768883 | Contract for the Requalification of the water line of Praia da Galé | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 08-08-2019 | 05-03-2020 | 210 | 60 | 26805.99 | 24820.2 | 1 | 24820.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1803 | 5768867 | Refurbishment and expansion works of Casa de Ponto do Viveiro Municipal | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 20 | 06-08-2019 | 04-02-2020 | 182 | 150 | 120000 | 115589.07 | 1 | 115589.07 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1804 | 5768682 | Expansion contract for the water supply network and domestic wastewater network on Caminho do Páteo - Guia | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 06-08-2019 | 22-06-2020 | 321 | 90 | 98416.84 | 85016.5 | 1 | 85016.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
1805 | 5768478 | Lot 1 - Redevelopment of the surroundings of the Chapel of Senhora da Tocha - Parish of Vizela (Santo Adrião) and Lot 2 - Redevelopment of the area adjacent to the church of Santa Eulália | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 16 | 09-08-2019 | 30-06-2020 | 326 | 150 | 259274.16 | 207953.24 | 1 | 227901.82 | -19948.58 | 91.2469 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | term extension | complementary works
1806 | 5767879 | Contract for the Requalification of the Main Entrance of the ISCSP | 45261100-5 | Roof-framing work | FALSE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 24-05-2018 | 18-12-2018 | 208 | 91 | 179000 | 107833.23 | 1 | 119247.68 | -11414.45 | 90.4279 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | extra work | extra work
1807 | 5767819 | Drainage grating replacement contract | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 26-07-2019 | 21-04-2020 | 270 | 90 | 77151.79 | 72635.53 | 1 | 72635.53 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1808 | 5767720 | CP 23/2019_DEGA - Wastewater on Avenida Doutor Vasco Branco - Aveiro | 45232440-8 | Construction work for sewage pipes | TRUE | 2019 | 2020 | Portugal | Aveiro | Aveiro | 1 | 25 | 08-07-2019 | 09-01-2020 | 185 | 30 | 52500 | 52000 | 1 | 52000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Not Applicable Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays under the responsibility of the contracting company | nothing to report
1809 | 5767604 | Contract for the Extension of the Interior Breakwater at the Port of Peniche | 45243200-4 | Breakwater construction work | FALSE | 2019 | 2020 | Portugal | Peniche | Leiria | 10 | 17 | 07-06-2019 | 31-03-2020 | 298 | 150 | 1825000 | 1120848.35 | 3 | 1148346.24 | -27497.89 | 97.6054 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no deadline extension | complementary works
1810 | 5766368 | Requalification of Building for Lota da Trafaria | 45262700-8 | Building alteration work | FALSE | 2019 | 2020 | Portugal | Almada | Setúbal | 17 | 25 | 19-07-2019 | 19-09-2020 | 428 | 120 | 90000 | 89360 | 1 | 89360 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension derived from the installation of refrigeration equipment
1811 | 5765726 | Construction of the Beça River Leisure Park. | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2019 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 21 | 12-07-2019 | 19-02-2021 | 588 | 365 | 313269.7 | 306852.82 | 2 | 316773.82 | -9921 | 96.8681 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 | complementary work and underwork
1812 | 5765166 | Functional Adaptation Contract for Dentistry/Oral Health Offices at ARS Algarve, I.P. | 45454000-4 | Restructuring work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 08-08-2019 | 02-01-2020 | 147 | 60 | 135000 | 127994.03 | 1 | 127994.03 | 0 | 100 | Best value for money: No Criterion related to quality Name: Compliance with the mandatory minimum requirements of the Tender Specifications Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1813 | 5764079 | Contract for the Requalification of the Church Branch, Candelária | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 31 | 05-08-2019 | 14-04-2020 | 253 | 150 | 349000 | 348980 | 2 | 348980 | 0 | 100 | If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project.
1814 | 5762919 | Pe_19056_cne - contract to replace the flooring of the uncovered parking lot at the Lisbon School of Hospitality and Tourism | 45430000-0 | Floor and wall covering work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 06-08-2019 | 07-12-2020 | 489 | 61 | 32000 | 27298 | 1 | 26269 | 1029 | 103.9172 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Review - Lowest Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it was possible to complete the execution of the projects in a shorter period than foreseen in the contract | during the execution of the projects, it was verified that it was not necessary to carry out all the contracted works
1815 | 5762409 | Sanitation in Redondelo | 45232421-9 | Sewage treatment works | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 15 | 05-08-2019 | 26-03-2020 | 234 | 150 | 149056.6 | 146904.93 | 1 | 146904.93 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1816 | 5761477 | Rehabilitation of the Trincheira Municipal Park - 1st phase | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Pinhel | Guarda | 9 | N/A | 25-08-2018 | 21-08-2020 | 727 | 365 | 600000 | 579000 | 2 | 576815.95 | 2184.05 | 100.3786 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | because of the contractor | underwork and price revision
1817 | 5760994 | 2015.079.03.C1 - SFP Aveiro - Installation of the Welding Section | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2018 | 2020 | Portugal | Aveiro | Aveiro | 1 | 20 | 26-02-2019 | 13-05-2020 | 442 | 150 | 260000 | 257777.77 | 2 | 245358.8 | 12418.97 | 105.0616 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | additional work, underwork and price revisions
1818 | 5756600 | Improvement of Municipal streets 2018, in the municipality of Estarreja | 45233142-6 | Road-repair works | FALSE | 2018 | 2021 | Portugal | Estarreja | Aveiro | 1 | 45 | 25-07-2019 | 07-10-2021 | 805 | 90 | 430066 | 142528.58 | 1 | 145122.82 | -2594.24 | 98.2124 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | suspension of work | price review
1819 | 5755008 | Contract 25/GEBALIS/2019 - Contract for the Maintenance and Repair of housing and Common Areas in Neighborhoods in the South Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 05-08-2019 | 12-08-2021 | 738 | 730 | 599856.33 | 496991.42 | 2 | 496991.42 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work went smoothly/on schedule
1820 | 5754737 | The work consists of repairing and waterproofing the section Monte dos Alhos - Canal Condutor Geral de Campilhas. After washing and identifying the most degraded areas of the channel, rehabilitation is carried out | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2019 | Portugal | Santiago do Cacém | Setúbal | 17 | N/A | 03-01-2018 | 01-07-2019 | 544 | 130 | 402000 | 317052.19 | 2 | 317052.19 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Factors: F1 - Technical value of the proposal: 60% F2 - Price: 40% b) F1 subfactors - Technical value of the proposal: F1.1 - Descriptive memory: 30% F1.2 - Work plans, equipment and labor: 25% F1.3 - Descriptive memory of the shipyard: 5% | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
1821 | 5753979 | The work consists of replacing Irrigator 28 (R28) at the Campilhas Hydro-Agricultural Development, with a total length of 2.32 km. The channel-type watering can with rectangular section is replaced | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2019 | Portugal | Santiago do Cacém | Setúbal | 17 | N/A | 25-01-2018 | 20-03-2019 | 419 | 120 | 250000 | 208899 | 1 | 208899 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Factors: F1 - Technical value of the proposal: 60% F2 - Price: 40% b) F1 subfactors - Technical value of the proposal: F1.1 - Descriptive memory: 30% F1.2 - Work plans, equipment and labor: 25% F1.3 - Descriptive memory of the shipyard: 5% | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension
1822 | 5753823 | Contract for "Construction of Ossuaries at the June 16 Cemetery - Year 2019" | 45215400-1 | Cemetery works | FALSE | 2019 | 2019 | Portugal | Olhão | Faro | 8 | 9 | 23-07-2019 | 22-11-2019 | 122 | 90 | 75000 | 66150 | 1 | 66150 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1823 | 5753555 | Rehabilitation of Irrigation Machine 15 (R15) of the Campilhas Hydro-Agricultural Development. The intention is to derive the Canal Condutor Geral de Campilhas, including the supply, installation and calibration of modules. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2019 | Portugal | Odemira | Beja | 2 | N/A | 15-10-2018 | 10-07-2019 | 268 | 120 | 1064000 | 946867.56 | 2 | 946867.56 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Factors: F1 - Technical value of the proposal: 60% F2 - Price: 40% b) F1 subfactors - Technical value of the proposal: F1.1 - Descriptive memory: 30% F1.2 - Work plans, equipment and labor: 25% F1.3 - Descriptive memory of the shipyard: 5% | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension.
1824 | 5753388 | 2018.040.04.C1 - DR Norte - I.S. and fix | 45259900-6 | Plant upgrade work | TRUE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 15 | 11-06-2019 | 13-12-2019 | 185 | 90 | 61000 | 51240 | 1 | 55105.88 | -3865.88 | 92.9846 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | additional
1825 | 5753224 | Paving, water supply network, rainwater network, irrigation network, plantations, electrical infrastructure, telecommunications, signaling and urban equipment. | 45112700-2 | Landscaping work | FALSE | 2019 | 2021 | Portugal | Nisa | Portalegre | 12 | 30 | 19-07-2019 | 15-02-2021 | 577 | 240 | 251114.25 | 199751.48 | 1 | 199751.48 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1826 | 5753125 | 2013.079.01.C1 - SFP Aveiro - Air conditioning system replacement | 45300000-0 | Building installation work | FALSE | 2015 | 2021 | Portugal | Aveiro | Aveiro | 1 | 22 | 21-09-2015 | 14-12-2021 | 2276 | 120 | 531000 | 363746.63 | 2 | 372553.34 | -8806.71 | 97.6361 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 29 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no data | underwork and price review
1827 | 5751175 | Improvement of the Marquês de Niza Palace - CED MP | 45113000-2 | Siteworks | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 02-08-2019 | 16-01-2020 | 167 | 60 | 150000 | 139944.2 | 1 | 129308.44 | 10635.76 | 108.2251 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the development of works by the contractor | in view of the delay registered in the completion of the project, a penalty of €10,635.76 was applied
1828 | 5750644 | Infraquinta Office Expansion Contract | 45213150-9 | Office block construction work | FALSE | 2019 | 2020 | Portugal | Loulé | Faro | 8 | 18 | 26-07-2019 | 15-12-2020 | 508 | 180 | 238000 | 217343.59 | 1 | 215302.61 | 2040.98 | 100.948 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (between | underwork
1829 | 5750296 | PRC_0130/2019_GAE-EB0435 - Construction of the Wastewater Drainage Network in Lugar do Peso, Parish of Santa Marinha do Zêzere (Baião) | 45232411-6 | Foul-water piping construction work | TRUE | 2019 | 2021 | Portugal | Baião | Porto | 13 | 14 | 01-08-2019 | 02-02-2021 | 551 | 60 | 70000 | 63624.64 | 1 | 60809.86 | 2814.78 | 104.6288 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need for an objective modification of the contract at the request of the c.m. baião to adnorte, leading to a reformulation of the initial project and later approval of the complementary works introduced within the scope of the contract. | complementary work and underwork resulting from the objective modification of the contract.
1830 | 5749679 | EP-2019(5001)/10008 Rehabilitation of the Morbey Rodrigues Building - CED NAP | 45113000-2 | Siteworks | TRUE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 01-08-2019 | 16-01-2020 | 168 | 90 | 203500 | 202889.96 | 1 | 205027.89 | -2137.93 | 98.9572 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | existence of complementary works worth €1,431.00
1831 | 5749081 | Execution of the House of Culture at the U.F. From Caldas de Vizela (S. Miguel and S. João) | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2019 | 2020 | Portugal | Vizela | Braga | 3 | 20 | 31-07-2019 | 03-04-2020 | 247 | 150 | 212260 | 199990 | 1 | 223550.9 | -23560.9 | 89.4606 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary works
1832 | 5748635 | 1400009/2019 Work to Improve the Physical Space of the Endoscopic Techniques Unit | 45454000-4 | Restructuring work | FALSE | 2019 | 2020 | Portugal | Barreiro | Setúbal | 17 | 15 | 09-07-2019 | 08-05-2020 | 304 | 90 | 300000 | 282109.13 | 2 | 279790.36 | 2318.77 | 100.8288 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | extracontractual works | extracontractual works
1833 | 5748167 | 2018.192.01.C1 - CRPG Gaia - Replacement of fiber cement roofing | 45261213-0 | Metal roof-covering work | TRUE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 15 | 10-05-2019 | 22-05-2020 | 378 | 210 | 220000 | 179264.07 | 1 | 183307.59 | -4043.52 | 97.7941 | Best value for money: No Criterion related to quality Name: Valia Técnica Proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | gracious deadline extension, suspension of work due to covid 19 | complementary works
1834 | 5746393 | Work to Repair Damage Resulting from the Fires of 2017 and Other Interventions in Infrastructures of AVT - Beira Alta | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Sabugal | Coimbra | 6 | 31 | 29-03-2019 | 30-09-2020 | 551 | 300 | 440000 | 397532.4 | 2 | 394014.03 | 3518.37 | 100.893 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change in the deadline resulting from the suspension of the execution period of the contract due to the pandemic situation caused by the covid-19 outbreak. | change in the value of the project resulting from contractual work not carried out and the price review carried out.
1835 | 5744121 | Proc. Nº 19/EOP/DCOP/2018 - Improvement of rainwater drainage and water lines in the parishes of Alcabideche and S.Domingos de Rana | 45232130-2 | Storm-water piping construction work | FALSE | 2018 | 2021 | Portugal | Cascais | Lisboa | 11 | 30 | 15-07-2019 | 04-11-2021 | 843 | 567 | 3959999.4 | 3167933.53 | 3 | 3167933.53 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | covid-19 pandemic
1836 | 5743659 | Construction of a car park, including all infrastructure and paving. | 45223300-9 | Parking lot construction work | FALSE | 2019 | 2019 | Portugal | Vizela | Braga | 3 | 21 | 31-07-2019 | 22-11-2019 | 114 | 90 | 94278 | 88546.74 | 1 | 88546.74 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1837 | 5741300 | “Intervention for Emergency Stabilization in Water Lines” | 45246000-3 | River regulation and flood control works | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 14 | 22-07-2019 | 21-12-2021 | 883 | 120 | 646809.93 | 141598.97 | 1 | 129102.17 | 12496.8 | 109.6798 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extensions and suspension, caused by bad weather. | complementary works and price revision
1838 | 5741100 | “Intervention for Emergency Stabilization in Water Lines” | 45246000-3 | River regulation and flood control works | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 14 | 22-07-2019 | 10-02-2021 | 569 | 120 | 646809.93 | 115637.28 | 1 | 58765.93 | 56871.35 | 196.7761 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension granted | existence of underwork and price revision
1839 | 5741088 | “Intervention for Emergency Stabilization in Water Lines” | 45246000-3 | River regulation and flood control works | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 22-07-2019 | 23-11-2020 | 490 | 120 | 646809.93 | 174447.44 | 1 | 178122.44 | -3675 | 97.9368 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension due to adverse weather conditions | due to price revision
1840 | 5741072 | “Intervention for Emergency Stabilization in Water Lines” | 45246000-3 | River regulation and flood control works | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 22-07-2019 | 23-11-2020 | 490 | 120 | 646809.93 | 63081.19 | 1 | 64396.83 | -1315.64 | 97.957 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | price revision granted | due to price revision
1841 | 5738873 | Rehabilitation contract for Largo das Freiras | 45000000-7 | Construction work | TRUE | 2019 | 2020 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 30 | 19-07-2019 | 08-09-2020 | 417 | 270 | 345000 | 310770.52 | 2 | 310770.52 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Municipality of Ribeira Grande Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 2 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline | price review
1842 | 5738790 | Repair and Installation of Monoblocks in Various Locations in the Municipality | 45454000-4 | Restructuring work | FALSE | 2019 | 2020 | Portugal | Loures | Lisboa | 11 | 20 | 08-07-2019 | 06-10-2020 | 456 | 104 | 252754.88 | 246517.65 | 1 | 246517.65 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Work Plan and Deadline Weighting: 50% Criterion related to cost Name: Bid Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the project deadline
1843 | 5727485 | Improvement of Energy Performance and Comfort at CA Martins Correia | 45212410-3 | Construction work for lodging buildings | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 23-07-2019 | 09-01-2020 | 170 | 80 | 110000 | 108979.28 | 1 | 115319.65 | -6340.37 | 94.5019 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | existence of complementary work
1844 | 5725792 | Execution of works necessary for the rehabilitation of road pavements and pedestrian accesses, on Avenida dos Combatentes da Grande Guerra in Vila Franca de Xira | 45000000-7 | Construction work | FALSE | 2019 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 15 | 08-07-2019 | 21-02-2020 | 228 | 120 | 288500 | 257688.5 | 2 | 257688.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report
1845 | 5725168 | "Requalification of the Panoramic Access Route to the Alto Douro Vinhateiro - World Heritage - Municipal Road 323 | 45233142-6 | Road-repair works | FALSE | 2019 | 2021 | Portugal | Sabrosa | Vila Real | 19 | 15 | 15-07-2019 | 25-02-2021 | 591 | 270 | 1162650.87 | 1162427.11 | 3 | 1154162.48 | 8264.63 | 100.7161 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | authorized deadline extensions | the sum of over and under works.
1846 | 5722546 | CP/04/Sun/2019 - Replacement of fiber cement roofing - 2nd phase | 45210000-2 | Building construction work | FALSE | 2019 | 2019 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 23-05-2019 | 13-09-2019 | 113 | 60 | 100000 | 89739.85 | 1 | 89739.85 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions
1847 | 5720522 | Restoration of the children's workshop building | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Alcácer do Sal | Setúbal | 17 | 30 | 17-07-2019 | 03-12-2021 | 870 | 300 | 472900 | 447800 | 2 | 498159.19 | -50359.19 | 89.8909 | Best value for money: Yes Criterion related to quality Name: Value and feasibility of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the term expired on a non-working day | over and underwork and price revision (final).
1848 | 5717660 | Bread House of Paraduça | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2019 | 2021 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 10-07-2019 | 11-02-2021 | 582 | 180 | 193543.97 | 192850 | 1 | 192849.54 | 0.46 | 100.0002 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | did not have. | did not have.
1849 | 5717613 | Rehabilitation of Playgrounds | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2021 | Portugal | Murtosa | Aveiro | 1 | 21 | 18-07-2019 | 25-10-2021 | 830 | 122 | 334100.02 | 323227.19 | 2 | 319986.15 | 3241.04 | 101.0129 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project proceeded as normal. | there was underwork and complementary work.
1850 | 5717574 | Repaving contract on the sidewalk of street of Miragaia, street of Pereira and street of Palácio | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2020 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 21 | 27-06-2019 | 04-09-2020 | 435 | 120 | 199802.66 | 189900 | 1 | 189900 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | not applicable
1851 | 5717172 | Requalification of the social space/dressing room | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2020 | Portugal | Porto | Porto | 13 | 15 | 11-07-2019 | 29-05-2020 | 323 | 30 | 12000 | 10224.5 | 1 | 10224.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: technical visit report; deadline Weighting: 40% Criterion related to cost Name: proposal value Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological causes
1852 | 5716246 | Requalification of streets in the Parish of Assunção - Industrial Zones and other streets in Arronches -2019 | 45233252-0 | Surface work for streets | FALSE | 2019 | 2019 | Portugal | Arronches | Portalegre | 12 | 15 | 30-05-2019 | 10-09-2019 | 103 | 60 | 189261.45 | 117492.4 | 1 | 117492.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the projects took place at a good pace and the end of the project was anticipated.
1853 | 5713959 | Energy Dissipating Structure | 45243500-7 | Sea defences construction work | TRUE | 2019 | 2020 | Portugal | Setúbal | Setúbal | 17 | 28 | 26-06-2019 | 29-09-2020 | 461 | 120 | 230000 | 216031.64 | 1 | 216031.64 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Factor B - Work Methodology and Planning Weighting: 40% Criterion related to cost Name: Factor A - Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delivery delay
1854 | 5713264 | CCCA - CMA Car Park | 45211360-0 | Urban development construction work | FALSE | 2019 | 2020 | Portugal | Aveiro | Aveiro | 1 | 21 | 05-07-2019 | 02-11-2020 | 486 | 90 | 131133.45 | 126842.75 | 1 | 125503.25 | 1339.5 | 101.0673 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions and application of contractual sanction for delay in the execution of the contract | underwork
1855 | 5710603 | Replacement of the water distribution networks in the western sector of Funchal - asbestos-cement network on the Caminho de São Martinho and surrounding areas | 45232151-5 | Water-main refurbishment construction work | FALSE | 2019 | 2020 | Portugal | N/A | Região Autónoma da Madeira | 14 | 30 | 11-06-2019 | 13-04-2020 | 307 | 210 | 391495 | 325384.12 | 2 | 324412.39 | 971.73 | 100.2995 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays due to momentary suspension situations due to adverse weather conditions | underwork related to the fact that it was not necessary to carry out all the planned home connections
1856 | 5709910 | It consists of the execution of works for the public works contract, “Contract for the Rehabilitation of the Sandomil Water Pipeline – Phase 2 – CPC”. This contract will be carried out in the municipality of Seia | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Seia | Guarda | 9 | 24 | 01-03-2019 | 27-01-2020 | 332 | 120 | 80000 | 67018.01 | 1 | 67018.01 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1857 | 5709554 | Rehabilitation/Remodeling of Buildings 1, 2, 3, 7, 8, 10, 16, 17, 19, 20, 31 and 32 in the Cerco do Porto neighborhood (EM.001.2019.027_28_29) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 30 | 12-07-2019 | 26-04-2021 | 654 | 330 | 6100000 | 689491.47 | 2 | 658099.44 | 31392.03 | 104.7701 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension due to additional work and confinement (covid) | complementary work and unforeseen work
1858 | 5709036 | Requalification of streetCentral de Lever between streetde Abrecovo and street of Leira - Lever | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 25-06-2019 | 11-11-2020 | 505 | 150 | 220000 | 197666.2 | 1 | 198754.91 | -1088.71 | 99.4522 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed on schedule, however, the provisional acceptance notice was only prepared on the date indicated. | a price revision with provisional indices amounting to €1,088.71 was determined.
1859 | 5705384 | Montijo Cyclable and Reconversion of the Railway Line | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2020 | Portugal | Montijo | Setúbal | 17 | 30 | 05-04-2019 | 23-09-2020 | 537 | 225 | 830471.7 | 726289.89 | 2 | 716073.86 | 10216.03 | 101.4267 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal, in deadlines of price as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were two extensions to the deadline, essentially due to bad weather during the winter and a delay in carrying out the projects by the contractor. | there was a reduction in the final value of the contract in relation to the contract value, motivated by some differences between the projects foreseen in the project and those carried out.
1860 | 5705271 | Floor repair 2019 | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 15 | 05-07-2019 | 20-04-2020 | 290 | 180 | 342000 | 285300 | 2 | 155913.93 | 129386.07 | 182.9856 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | effective deadline: 02/14/2020, with the provisional acceptance of the contract being signed on 02/17/2020 | underwork and compensation for reduction of the total amount. during the contract it was verified that there were streets that did not need leveling, others that did not need opening the box and respective filling with tout-venant, others did not need the execution of their tillering and regularization with dense bituminous mixture and others in which two layers were foreseen but which were not executed due to works by adra - águas da região de aveiro, s.a. soon, opting to execute the second layer after this intervention. thus, there were several works that were not carried out, being the one corresponding to article 3.1.1 - tillering and regularization of the existing pavement with dense bituminous mixture (binder type), which had the greatest weight.
1861 | 5703783 | Roof building for the EB 2,3 Sports Pavilion in Miragaia | 45260000-7 | Roof works and other special trade construction works | FALSE | 2019 | 2020 | Portugal | Lourinhã | Lisboa | 11 | 15 | 09-07-2019 | 07-07-2020 | 364 | 150 | 149365.36 | 140222.58 | 1 | 148755.22 | -8532.64 | 94.264 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of complementary works | approval of complementary works
1862 | 5702062 | Contract to improve the façade and reception of the headquarters building of the National Institute for Rehabilitation, IP, located at Avenida Conde de Valbom n.º 63, in Lisbon. | 45259000-7 | Repair and maintenance of plant | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 16 | 12-12-2018 | 12-07-2019 | 212 | 30 | 56000 | 36398.57 | 1 | 36398.57 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Period of execution of the work Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension between 01/14/2019 and 03/25/2019 - reason for city council authorizations for assembly of the shipyard; constant rain and showers that prevented work on the façade; closure of the construction site due to various holidays during the execution period; delays in the delivery of the flooring that was imported from italy, due to public holidays also existing in that country, according to the contractor's statement in the file.
1863 | 5698704 | Environmental Remediation Contract for the Old Mortório Mining Area | 45112500-0 | Earthmoving work | TRUE | 2018 | 2021 | Portugal | Meda | Guarda | 9 | 70 | 05-07-2019 | 29-12-2021 | 908 | 365 | 4000000 | 2799626.58 | 3 | 3026738.92 | -227112.34 | 92.4965 | Best value for money: Yes Criterion related to quality Name: VT - Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: FP - Price Factor Weighting: 60% | 1 | 60 | 5 | TRUE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unpredictable vicissitudes in obtaining the discharge/cleaning license on the water line. | unpredictable circumstances that could not be defined during the design phase, namely due to the high amount of suspended sludge at the bottom of the pit, which was only possible to measure after draining the pit
1864 | 5698666 | PRC_0312/2018_AAD - Contract for the Rehabilitation of the Arroio, Camba and Palameiro Dams | 45247212-9 | Dam-reinforcement works | FALSE | 2019 | 2021 | Portugal | Torre de Moncorvo | Bragança | 4 | 7 | 05-07-2019 | 10-02-2021 | 586 | 270 | 560000 | 508998.81 | 2 | 530048.52 | -21049.71 | 96.0287 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | epidemic caused by a new coronavirus (2019-ncov) caused constraints in terms of food and accommodation logistics, delay in the supply of materials/equipment, decrease in the performance of teams due to restrictions on security compliance | complementary work in replacing the diameter of the pipes and accessories inside the camba dam water intake tower
1865 | 5698604 | Public Tender for the execution of the contract for the expansion of the water supply network - Monte Velho path. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 04-07-2019 | 23-10-2019 | 111 | 30 | 15113.72 | 13000 | 1 | 13000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays by the contractor
1866 | 5696851 | Contract for Substitution of the Feeding Pipeline to the Camarate Pumping Station | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2019 | Portugal | Loures | Lisboa | 11 | 24 | 04-04-2019 | 02-12-2019 | 242 | 120 | 140000 | 138284 | 1 | 138284 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A
1867 | 5696774 | The public works contract “Rehabilitation of the Olivais Pumping Station – 1st Phase”, is mainly aimed at carrying out the following works: Rehabilitation of the Pumping Station building | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2021 | Portugal | Lisboa | Lisboa | 11 | 45 | 05-04-2019 | 28-04-2021 | 754 | 270 | 660000 | 621546.33 | 2 | 553537.51 | 68008.82 | 112.2862 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the inspection for the purpose of provisional acceptance of the project was carried out on 04/03/2020, but it was found that there were defects in the project that prevented the reception of the project, in which a period of 30 days was granted to correct them. on 03/16/2020, work was suspended until 04/05/2020 due to the covid-19 pandemic situation. on 06/22/2020, a new inspection was carried out, where it was found that the defects had not been fully corrected, having been assigned a period of 20 days to correct them. on 07/15/2020, a new inspection was carried out, where it was verified that the previously identified defects were corrected, but not enough to allow the reception to be carried out, being necessary to correct them within a period of 30 days. finally, on 08/20/2020, a new inspection was carried out where it was verified that the previously identified defects were corrected and, as such, the 4th and last inspection notice was signed for the purposes of provisional acceptance. | the changes in the value of the project resulted from the execution of more work, underwork (for which additional contract no. 1648-a was signed) and the price review carried out.
1868 | 5695184 | C.p. No. 06/2019 | 45000000-7 | Construction work | FALSE | 2019 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 17-06-2019 | 13-11-2019 | 149 | 90 | 190000 | 181181 | 1 | 200089.12 | -18908.12 | 90.5502 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to extend the deadline due to the extra work and the difficulty in delivering the materials. | due to more work
1869 | 5694537 | Public Tender for the Contract for the Supply and Installation of Floating Equipment in the Port of Shelter for Small Fishing in the Port of Aveiro | 45244100-0 | Marine installations | FALSE | 2019 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 21 | 25-06-2019 | 04-03-2020 | 253 | 101 | 284000 | 245425 | 1 | 245425 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the deadline, 101 days, but the rest were for administrative procedures.
1870 | 5693345 | Porous concrete paving of school playgrounds - Various Parishes | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 08-07-2019 | 14-07-2020 | 372 | 75 | 55000 | 49292.36 | 1 | 27105.5 | 22186.86 | 181.8537 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the stipulated time | termination of work and consequent compensation for reduction of contract price
1871 | 5693262 | Works in Municipal Buildings - Paintings | 45442110-1 | Painting work of buildings | FALSE | 2019 | 2021 | Portugal | Almada | Setúbal | 17 | 4 | 21-05-2019 | 15-01-2021 | 605 | 913 | 437992.45 | 350393.97 | 2 | 350393.97 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed ahead of the initial scheduled deadline.
1872 | 5691679 | Beira Alta Line Contract - Complete renovation of track, in the track specialty, between Pk 58+300 (Luso Bifurcation) and Pk 65+050 (Mortágua side exit of the Trezói tunnel | 45234100-7 | Railway construction works | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 42 | 28-04-2016 | 21-12-2020 | 1698 | 180 | 4200000 | 3745401 | 3 | 3630121.65 | 115279.35 | 103.1756 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price 60% | 1 | 60 | N/A | TRUE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to difficulties on the part of the contractor, it was necessary to grant a graceful extension | checking for errors and omissions
1873 | 5687563 | Landscape Requalification of the roundabout at Olho D'Água, the roundabout on the EN109 and the roundabout giving access to Ersuc | 45112700-2 | Landscaping work | FALSE | 2019 | 2020 | Portugal | Aveiro | Aveiro | 1 | 25 | 03-06-2019 | 18-05-2020 | 350 | 90 | 54103.11 | 52630.7 | 1 | 52630.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | difficulty with plantations and delivery of some species
1874 | 5686931 | Contract nº 05/dmmc/ds/2018 - "contract for the execution of priority and urgent works for the conservation and maintenance of the drainage network of the municipality of lisbon" | 45232451-8 | Drainage and surface works | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 21 | 01-07-2019 | 10-03-2021 | 618 | 730 | 748000 | 249000 | 1 | 250355.68 | -1355.68 | 99.4585 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1875 | 5686683 | Contract for “Execution of Collective Protection in Several Installations of Águas de Santo André” | 45223820-0 | Prefabricated units and components | TRUE | 2019 | 2020 | Portugal | Santiago do Cacém | Setúbal | 17 | 37 | 01-07-2019 | 24-01-2020 | 207 | 120 | 75000 | 71117.17 | 1 | 69753.82 | 1363.35 | 101.9545 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | when the victory was requested for the purposes of provisional acceptance, the owner of the project carried out the respective inspection 30 days from the date of receipt of the said request. | due to the existence of underwork
1876 | 5685485 | Contract for the expansion of the cherry garden reservoir | 45247270-3 | Reservoir construction works | FALSE | 2018 | 2021 | Portugal | Torres Novas | Santarém | 16 | 30 | 11-10-2018 | 25-03-2021 | 896 | 300 | 1300000 | 970392.55 | 2 | 964945.21 | 5447.34 | 100.5645 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | TRUE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | correction of execution defects and delivery of elements necessary for provisional acceptance. | underwork.
1877 | 5684158 | Cpn 12/2019/dicp - t - 51/2018 - rehabilitation of the caranguejeira variant (1st section) and creation of a pedestrian corridor, caranguejeira | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 15 | 03-06-2019 | 26-06-2020 | 389 | 120 | 340534 | 295717.5 | 2 | 291647.5 | 4070 | 101.3955 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
1878 | 5680294 | Construction of the bmx track in Quarteira | 45212210-1 | Single-purpose sports facilities construction work | FALSE | 2018 | 2021 | Portugal | Loulé | Faro | 8 | 20 | 01-04-2019 | 01-06-2021 | 792 | 540 | 600000 | 599999.57 | 2 | 595801.39 | 4198.18 | 100.7046 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 pandemic
1879 | 5680206 | Construction of a cycling and pedestrian path in the city of Valpaços | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 18 | 03-05-2019 | 24-06-2020 | 418 | 180 | 456150 | 403258.69 | 2 | 390385 | 12873.69 | 103.2977 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions not favorable to the execution of the projects | underwork
1880 | 5676977 | Improvement of energy efficiency at elementary school nº1 | 45261213-0 | Metal roof-covering work | FALSE | 2019 | 2019 | Portugal | São Brás de Alportel | Faro | 8 | 21 | 15-04-2019 | 02-09-2019 | 140 | 180 | 75000 | 72203.22 | 1 | 72203.22 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
1881 | 5676739 | Granite cube flooring - February 2019 | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 14-06-2019 | 26-02-2020 | 257 | 180 | 199885 | 198865.84 | 1 | 180770.72 | 18095.12 | 110.01 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project finished within the deadline. | underwork worth €18,095.12
1882 | 5673837 | Building of the former primary school in Pereira - Construction - Adaptation of the building for the extension of the Health Center | 45000000-7 | Construction work | TRUE | 2019 | 2020 | Portugal | Montemor-o-Velho | Coimbra | 6 | 30 | 02-05-2019 | 23-09-2020 | 510 | 180 | 81769.76 | 79337.44 | 1 | 86758.82 | -7421.38 | 91.446 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no additional period granted for execution of complementary works | execution of complementary works
1883 | 5672799 | Urban mobility (PEDU): Urban ring road of the city - Cycle path | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2020 | Portugal | Póvoa de Varzim | Porto | 13 | 30 | 08-08-2018 | 21-03-2020 | 591 | 150 | 398000 | 301682.78 | 2 | 276732.32 | 24950.46 | 109.0161 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Total bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | adjustments in the course of the project
1884 | 5672691 | POSEUR - Penalonga Wastewater Drainage Network | 45232460-4 | Sanitary works | FALSE | 2018 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 21 | 23-11-2018 | 15-04-2021 | 874 | 360 | 390735.83 | 327743.8 | 2 | 297163.73 | 30580.07 | 110.2906 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful lead time extensions. | underwork.
1885 | 5670067 | Revitalization of Avenida Dr. Ângelo Henriques Vidigal and Surroundings to the Municipal Market | 45233160-8 | Paths and other metalled surfaces | FALSE | 2018 | 2020 | Portugal | Sertã | Castelo Branco | 5 | 21 | 29-11-2018 | 01-07-2020 | 580 | 120 | 336700 | 307270.29 | 2 | 333442.9 | -26172.61 | 92.1508 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two extensions were granted, requested by the contractor and approved by mr. president of the city council, the first being graceful, due to reasons related to periods of very intense rain and heat, difficulties in reconciling some work with circulation and car parking and also the weekly fair that takes place on fridays at the mercado municipal. in the case of the 2nd extension granted, also approved by mr. president of the city council, this was in part graceful, due to some unexpected situations in the existing infrastructures - water supply networks and domestic waste water drainage networks - which made it difficult to carry out some works and in part legal due to the occurrence of works complementary. | occurrence of complementary work and occurrence of underwork.
1886 | 5668253 | Contract for Replacement of Pavements in Supply and Sanitation Networks | 45233220-7 | Surface work for roads | FALSE | 2018 | 2021 | Portugal | Benavente | Santarém | 16 | 14 | 08-03-2019 | 20-04-2021 | 774 | 730 | 271875 | 93125 | 1 | 67539.55 | 25585.45 | 137.8822 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there were no changes to the project deadline. the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
1887 | 5668152 | "Requalification and Rehabilitation of the Children's Center - Creche de Odivelas" | 45454000-4 | Restructuring work | FALSE | 2019 | 2021 | Portugal | Odivelas | Lisboa | 11 | 30 | 26-06-2019 | 25-01-2021 | 579 | 120 | 170859 | 150105.53 | 1 | 150105.53 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions for the execution of exterior repair work, exterior metallic structures and roofs, as well as disturbances due to the covid pandemic, significant reduction of raw materials, materials and labor | without changes
1888 | 5667927 | Execution contract for the Malhada Alta WWTP | 45232420-2 | Sewage work | FALSE | 2018 | 2020 | Portugal | Coruche | Santarém | 16 | 21 | 26-07-2018 | 08-01-2020 | 531 | 150 | 300000 | 231101.29 | 1 | 225430.21 | 5671.08 | 102.5157 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements | the objective of the project was fully achieved, not requiring the invoicing of all items
1889 | 5667805 | Refurbishment contract for the almeirim ETA | 45252120-5 | Water-treatment plant construction work | FALSE | 2018 | 2021 | Portugal | Almeirim | Santarém | 16 | 21 | 27-08-2018 | 15-04-2021 | 962 | 365 | 450000 | 429118.47 | 2 | 433057.49 | -3939.02 | 99.0904 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the foreseen period and the provisional acceptance derives from the suspension of the project and delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the objective of the project was fully achieved, not requiring the invoicing of all items. the effective total value also includes the price revision value.
1890 | 5667241 | Execution contract for the Sanitation Subsystem of Foros de Salvaterra - Elevator System of Aldeia do Peixe | 45232423-3 | Sewage pumping stations construction work | FALSE | 2018 | 2021 | Portugal | Benavente | Santarém | 16 | 21 | 27-08-2018 | 24-06-2021 | 1032 | 240 | 700000 | 566355.17 | 2 | 567389.6 | -1034.43 | 99.8177 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the objective of the project was fully achieved, not requiring the invoicing of all items
1891 | 5666274 | Refurbishment contract for the Alpiarça stage | 45252120-5 | Water-treatment plant construction work | FALSE | 2018 | 2021 | Portugal | Alpiarça | Santarém | 16 | 21 | 26-07-2018 | 15-04-2021 | 994 | 545 | 410000 | 398899.84 | 2 | 398625.04 | 274.8 | 100.0689 | Best value for money: No Criterion related to quality Name: not applicable Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the foreseen period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the objective of the project was fully achieved, not requiring the invoicing of all items. the effective total value also includes the price revision value.
1892 | 5665963 | Cpn - 32/2019/dicp - t - 01/2019 - execution of electrical infrastructure works, replacement of window frames in several dwellings and construction of land support wall | 45210000-2 | Building construction work | FALSE | 2019 | 2019 | Portugal | Leiria | Leiria | 10 | 6 | 28-05-2019 | 29-08-2019 | 93 | 30 | 98725 | 98494.38 | 1 | 98494.38 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes
1893 | 5665874 | Contract for the Refurbishment and Expansion of the Alcoutim Nautical Center Building | 45262800-9 | Building extension work | FALSE | 2019 | 2020 | Portugal | Alcoutim | Faro | 8 | 20 | 11-06-2019 | 06-10-2020 | 483 | 180 | 162579.2 | 161010.05 | 1 | 161010.04 | 0.01 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to provisional reception. | vat compromise settlement -0.01 €.
1894 | 5665534 | CP 02/2019_DEGA - Water supply to Agadão (PAA 023) - 2nd phase | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2019 | 2021 | Portugal | Águeda | Aveiro | 1 | 34 | 25-06-2019 | 06-08-2021 | 773 | 365 | 875000 | 829243.81 | 2 | 700433.68 | 128810.13 | 118.3901 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A
1895 | 5662797 | Rectification of the EM 507 Montalegre/Chaves - Connection to the A24 - Section 2 from Km 0+302.987 to Km 1+511.113 | 45233200-1 | Various surface works | FALSE | 2019 | 2020 | Portugal | Chaves | Vila Real | 19 | 24 | 03-06-2019 | 06-07-2020 | 399 | 120 | 339622.64 | 333109.62 | 2 | 348878.85 | -15769.23 | 95.48 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for extension of deadline until march 2020; there was suspension of work and resumption of the same work. | additional work worth €17,908.50.
1896 | 5661709 | ETAR of Lobelhe do Mato | 45232421-9 | Sewage treatment works | FALSE | 2019 | 2021 | Portugal | Mangualde | Viseu | 20 | 20 | 25-06-2019 | 18-09-2021 | 816 | 365 | 272000 | 231200.01 | 1 | 219597.34 | 11602.67 | 105.2836 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: non-existent Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | blockage of terain that needed to be crossed. | underwork
1897 | 5661193 | CPN 31/2019/DICP -T-21/2019- Improvement of the wooden access walkways to the sandy beach of Pedrógão - Leiria | 45422100-2 | Woodwork | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 14 | 30-05-2019 | 18-11-2020 | 538 | 30 | 68465.76 | 54787.9 | 1 | 54787.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension (by the developer) by binding determination or relevant recommendation (art. 365.º, paragraph c)
1898 | 5660289 | Contract for the Refurbishment of Fractions 2nd Dto. And 3rd left E Dto., of the building located at streetDuque de Palmela, 2-4, in Lisbon, for reinstallation of the Health Unit W-Mais | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 9 | 19-06-2019 | 03-08-2021 | 776 | 120 | 320000 | 308057.3 | 2 | 350348.31 | -42291.01 | 87.9289 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to carry out unforeseen additional work and additional work that resulted from unforeseeable circumstances, as well as to extend the deadline for execution of the project. | compensation was necessary for work conditions different from those foreseen. €16,259.45 were paid for additional work, €29,764.64 for errors and omissions and €14,760.00 for compensation paid to the contractor. there was a decrease of € 18,493.09 due to underworks.
1899 | 5660236 | Current conservation of the pavement of roads in the municipality of Guimarães 2019 | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 20 | 11-06-2019 | 24-08-2020 | 440 | 365 | 348105.83 | 347891.04 | 2 | 344141.04 | 3750 | 101.0897 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the approval of the health and safety plan was communicated on 08/23/2019. | existence of underwork corresponding to the non-exhaustion of the quantities of work foreseen in the bill of quantities.
1900 | 5659832 | Requalification of Largo do Grémio and Surrounding Area | 45232460-4, 45233251-3, 45316100-6 | Sanitary works, Resurfacing works, Installation of outdoor illumination equipment | FALSE | N/A | 2020 | Portugal | Olhão | Faro | 8 | N/A | 29-01-2019 | 09-06-2020 | 497 | 270 | N/A | 333117.99 | 2 | 333117.99 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | contractor requests for extension of time
1901 | 5659666 | Execution of the Public Spas of Melides | 45262522-6 | Masonry work | FALSE | 2019 | 2019 | Portugal | Grandola | Setúbal | 17 | 20 | 30-04-2019 | 10-10-2019 | 163 | 120 | 49982.46 | 49597.87 | 1 | 49597.87 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
1902 | 5659376 | Paving Center Area of ​​the Municipality | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 21-06-2019 | 28-06-2021 | 738 | 240 | 754489 | 488308.96 | 2 | 463114.03 | 25194.93 | 105.4403 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 37 days for delay by the contractor in completing the project, 168 days between the 1st inspection and the provisional acceptance in the correction of deficiencies | underwork
1903 | 5658376 | Contract for the execution of works in the spaces related to the animal and terminal experimentation rooms (SEAT) in the Biotério of the School of Medicine of the University of Minho, in Braga. (Cp/eop-on-01/2018) | 45454000-4 | Restructuring work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 11-06-2019 | 10-03-2020 | 273 | 120 | 340000 | 305162.53 | 2 | 305162.53 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | facts associated with market activity resulting from periods of suspension of production in the national market due to periods of working holidays compromising delivery times and lack of market stocks.
1904 | 5657869 | POSEUR - Favais and Sludge Wastewater Drainage Network | 45232460-4 | Sanitary works | FALSE | 2018 | 2021 | Portugal | Ribeira de Pena | Vila Real | 19 | 21 | 09-11-2018 | 15-04-2021 | 888 | 360 | 400841.49 | 399840.2 | 2 | 395166.9 | 4673.3 | 101.1826 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful lead time extensions- | underwork.
1905 | 5654917 | hub paving - proximity works - 2019 | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 04-06-2019 | 21-02-2020 | 262 | 180 | 349785.44 | 133666.34 | 1 | 133666.34 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1906 | 5654873 | hub paving - proximity works - 2019 | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 04-06-2019 | 07-01-2020 | 217 | 180 | 349785.44 | 106375.83 | 1 | 106375.83 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
1907 | 5654792 | hub paving - proximity works - 2019 | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 04-06-2019 | 11-02-2020 | 252 | 180 | 349785.44 | 101810.44 | 1 | 99582.98 | 2227.46 | 102.2368 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was completed on time | underwork € 2,227.45
1908 | 5653749 | Replacement of the Roof of the Moda Design Building | 45000000-7 | Construction work | TRUE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 14 | 19-06-2019 | 16-01-2020 | 211 | 90 | 105000 | 102817.62 | 1 | 94078.12 | 8739.5 | 109.2896 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the development of work under the responsibility of the contractor | in view of the delay in completing the projects, a penalty of €8,739.50 was applied to the contractor
1909 | 5652738 | Requalification of the surroundings of the chapel of Senhora da Tocha - parish of vizela (santo adrião) - ppi:12/2017; refurbishment and repair of the surroundings of the church of santo adrião - parish of vizela | 45233140-2 | Roadworks | FALSE | N/A | 2020 | Portugal | Vizela | Braga | 3 | N/A | 24-06-2019 | 06-08-2020 | 409 | 120 | N/A | 138682.94 | 1 | 151824.72 | -13141.78 | 91.3441 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | complementary works
1910 | 5652723 | Requalification of the surroundings of the chapel of Senhora da Tocha - parish of vizela (santo adrião) - ppi:12/2017; refurbishment and repair of the surroundings of the church of santo adrião - parish of vizela | 45233140-2 | Roadworks | FALSE | N/A | 2019 | Portugal | Vizela | Braga | 3 | N/A | 24-06-2019 | 03-12-2019 | 162 | 35 | N/A | 36853.36 | 1 | 36853.36 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions
1911 | 5652716 | Requalification of the surroundings of the chapel of Senhora da Tocha - parish of vizela (santo adrião) - ppi:12/2017; refurbishment and repair of the surroundings of the church of santo adrião - parish of vizela | 45233140-2 | Roadworks | FALSE | N/A | 2020 | Portugal | Vizela | Braga | 3 | N/A | 24-06-2019 | 02-04-2020 | 283 | 120 | N/A | 70910.21 | 1 | 70910.21 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
1912 | 5652694 | Requalification of the surroundings of the chapel of Senhora da Tocha - parish of vizela (santo adrião) - ppi:12/2017; refurbishment and repair of the surroundings of the church of santo adrião - parish of vizela | 45233140-2 | Roadworks | FALSE | N/A | 2020 | Portugal | Vizela | Braga | 3 | N/A | 24-06-2019 | 03-01-2020 | 193 | 35 | N/A | 35097.77 | 1 | 35097.77 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
1913 | 5652094 | Contract for Replacement of Pavements in Supply and Sanitation Networks | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Torres Novas | Santarém | 16 | 14 | 26-04-2019 | 02-10-2020 | 525 | 730 | 232375 | 89375 | 1 | 89012.5 | 362.5 | 100.4072 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the contract has a duration of 24 months or until the contractual price runs out, whichever comes first. | the objective of the project was fully achieved, not requiring the invoicing of all items.
1914 | 5651919 | Coercive Execution of Works in the Urbanization of Colinas do Cruzeiro, in Odivelas - Permit 1/2001 (Zones 1, 6 and 7) | 45233251-3 | Resurfacing works | FALSE | 2019 | 2020 | Portugal | Odivelas | Lisboa | 11 | 15 | 19-06-2019 | 21-05-2020 | 337 | 120 | 572659.9 | 343595.95 | 2 | 343595.95 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes in the execution period of the project | there were no changes to the value of the project
1915 | 5651820 | Execution of basic sanitation infrastructure in street of Cabrita - Constance | 45232400-6 | Sewer construction work | FALSE | 2019 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 07-06-2019 | 05-11-2019 | 151 | 90 | 102586.75 | 92722.55 | 1 | 83964.51 | 8758.04 | 110.4306 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork worth 8758.04
1916 | 5651666 | Installation contract for a cogeneration system | 45251220-9 | Cogeneration plant construction work | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 24 | 09-04-2019 | 13-08-2019 | 126 | 90 | 65620 | 63889.65 | 1 | 63889.65 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
1917 | 5649789 | Its object is to carry out work on window frames, blind boxes, kitchen furniture, kitchen and bathroom taps, interior and exterior doors, wardrobes, floors, interior paint | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 14 | 06-06-2019 | 24-06-2020 | 384 | 240 | 249999.71 | 203805.5 | 1 | 203805.5 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty in the finding labour
1918 | 5646514 | Requalification of the surroundings of the chapel of Senhora da Tocha - parish of vizela (santo adrião) - ppi:12/2017; refurbishment and repair of the surroundings of the church of santo adrião - parish of vizela | 45233140-2 | Roadworks | FALSE | N/A | 2020 | Portugal | Vizela | Braga | 3 | N/A | 18-06-2019 | 20-04-2020 | 307 | 120 | N/A | 114020.03 | 1 | 114020.03 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
1919 | 5643635 | Contract for remodeling the water supply network and rainwater wastewater network - crossstreet ofMar | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 31-05-2019 | 23-09-2020 | 481 | 60 | 71499.7 | 58971.88 | 1 | 70733.61 | -11761.73 | 83.3718 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to high season | need for adjustments
1920 | 5643246 | Construction of the official collection center for companion animals in Alandroal | 45223600-2 | Dog kennels construction work | FALSE | 2019 | 2020 | Portugal | Alandroal | Évora | 7 | 15 | 06-06-2019 | 28-02-2020 | 267 | 180 | 138685 | 137124 | 1 | 145993.29 | -8869.29 | 93.9249 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | legal extension for 10 days, due to the occurrence of complementary works included in the contract by indication of the dgav during the contract. | due to the inclusion of complementary works in the contract, in the amount of €9,704.80 and the suppression of works in the amount of €835.51.
1921 | 5642546 | Contract for the Maintenance of Sanitation Networks | 45259000-7 | Repair and maintenance of plant | FALSE | 2019 | 2020 | Portugal | Coruche | Santarém | 16 | 14 | 06-06-2019 | 15-06-2020 | 375 | 730 | 121000 | 121000 | 1 | 120734 | 266 | 100.2203 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the contract term. | it was not necessary to exhaust all quantities of all lpu items.
1922 | 5641646 | 2019/20 - DGEP - Conservation and repair of road pavements in Oeiras and Paço de Arcos. | 45233140-2 | Roadworks | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 12 | 11-06-2019 | 12-07-2021 | 762 | 365 | 298145.3 | 276271 | 2 | 276271 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1923 | 5641375 | Cpn 15/2019/dicp - t - 61/2018 - requalification of Largo Afonso Lopes Vieira and construction of metallic pedestrian walkway over the River Lis - Cortes | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 15 | 10-05-2019 | 20-11-2020 | 560 | 120 | 199184 | 190000 | 1 | 190000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1924 | 5640551 | 2019/18 - DGEP - Conservation and repair of road pavements in Barcarena and Queijas | 45233142-6 | Road-repair works | FALSE | 2019 | 2021 | Portugal | Oeiras | Lisboa | 11 | 24 | 11-06-2019 | 01-06-2021 | 721 | 730 | 236849.5 | 208885.4 | 1 | 208885.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1925 | 5639935 | Enlargement and Improvement of the access road to CIRES, in the parish of Beduído e Veiros, in the Municipality of Estarreja | 45233142-6 | Road-repair works | FALSE | 2018 | 2020 | Portugal | Estarreja | Aveiro | 1 | 21 | 14-06-2019 | 10-09-2020 | 454 | 180 | 162368 | 142356.44 | 1 | 172318.43 | -29961.99 | 82.6124 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary works and price revision
1926 | 5639831 | Contract 52/GEBALIS/2019 - Contract for the Maintenance and Repair of housing and Common Areas in Neighborhoods in the West Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 14-06-2019 | 30-06-2021 | 747 | 730 | 600000 | 555000 | 2 | 555000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in accordance
1927 | 5639404 | Repair and maintenance contract for the premises of the antero de Quental High school | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2020 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 30 | 13-06-2019 | 15-01-2020 | 216 | 122 | 269470 | 258500 | 2 | 258500 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climate conditions
1928 | 5636321 | Emp- r/5/2019 - contract for the rehabilitation of blocks 2, 3, 6, 10, 12, 13, 14, 15, 18, 21, 22, 23, 25, 27, 29 and 31 of street of Venezuela and 153 and 155 of the United States of America Street in the Nazaré neighborhood | 45453100-8, 45442110-1 | Refurbishment work, Painting work of buildings | FALSE | 2019 | 2020 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 03-06-2019 | 20-05-2020 | 352 | 210 | 500000 | 361208.29 | 2 | 361208.29 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | executed on time.
1929 | 5635565 | Emp–r/7/2019 - contract for the rehabilitation of 16 houses in Porto Moniz | 45453100-8, 45442110-1 | Refurbishment work, Painting work of buildings | FALSE | 2019 | 2020 | Portugal | Porto Moniz | Região Autónoma da Madeira | 14 | 13 | 30-05-2019 | 25-08-2020 | 453 | 150 | 228000 | 169997.5 | 1 | 169997.5 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the deadline for the execution of the project until the 20th of march 2020 due to adverse weather conditions, which coincided with the suspension of the construction sector after the decreed state of emergency for exceptional reasons of the covid-19 pandemic and led again to the extension until the 15th of june 2020.
1930 | 5631047 | Placement of Fenders on Bridge-Pier 3, in the Port of Sesimbra | 45243500-7 | Sea defences construction work | TRUE | 2018 | 2020 | Portugal | Sesimbra | Setúbal | 17 | 30 | 18-04-2019 | 23-09-2020 | 524 | 180 | 250000 | 214850 | 1 | 214850 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Factor B - Work Methodology and Planning Weighting: 40% Criterion related to cost Name: Factor A - Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in delivery of fenders
1931 | 5628421 | Improvement of the CED SCT Building and Playground | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 28-05-2019 | 16-01-2020 | 233 | 90 | 90000 | 77441.49 | 1 | 71478.5 | 5962.99 | 108.3424 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the development of work under the responsibility of the contractor | in view of the delay in completing the contract, a penalty of €5,962.99 was applied to the contractor
1932 | 5627170 | Contract for Removal and Replacement of Fiber Cement Coverings at Aveiro Unit (Infant D. Pedro Hospital) at Centro Hospitalar do Baixo Vouga, EPE | 45261210-9 | Roof-covering work | FALSE | 2018 | 2020 | Portugal | Aveiro | Aveiro | 1 | 20 | 01-10-2018 | 28-08-2020 | 697 | 120 | 414900 | 392031.9 | 2 | 418162.31 | -26130.41 | 93.7511 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0 Criterion related to cost Name: Evaluation of price or cost as a single aspect Weighting: 100 | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | a deadline extension was approved, related to the implementation of forensic medicine coverage. | a deadline extension was approved, related to the implementation of forensic medicine coverage.
1933 | 5624414 | Construction of support walls in reinforced concrete, concrete blocks, in stone and gabion, reconstruction/repair of existing walls and stairs in various places in the Municipality of Coimbra | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2021 | Portugal | Coimbra | Coimbra | 6 | 30 | 26-12-2018 | 11-02-2021 | 778 | 180 | 284541 | 252999.99 | 2 | 253851.09 | -851.1 | 99.6647 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work without deadline extension | price revision amount
1934 | 5623683 | CPN 18/2019/DICP - T-18/2019 - Implementation of a domestic wastewater drainage system in public toilets in the Levante market - Leiria | 45232460-4 | Sanitary works | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 6 | 02-05-2019 | 09-11-2020 | 557 | 30 | 12633.4 | 12500 | 1 | 12500 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1935 | 5623491 | Cpn 24/2019/dicp - t 71/2018 - execution of works for the installation of automatic traffic signaling systems on the road to sailors | 45233294-6 | Installation of road signals | FALSE | 2019 | 2019 | Portugal | Leiria | Leiria | 10 | 15 | 29-05-2019 | 20-09-2019 | 114 | 90 | 26579 | 18753.33 | 1 | 18753.33 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1936 | 5623375 | The object of this contract is to carry out work on window frames, blind boxes, kitchen furniture, kitchen and bathroom faucets, interior and exterior doors | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 05-06-2019 | 22-12-2020 | 566 | 210 | 57414.5 | 45931.6 | 1 | 45931.6 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work met deadline
1937 | 5622941 | Shipyard assembly and disassembly; Demolition of sidewalk pavements; Milling of layers of existing pavements, in bituminous mixtures; Paving the carriageway with bituminous mixtures | 45233140-2 | Roadworks | FALSE | 2019 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 31-05-2019 | 20-04-2020 | 325 | 90 | 200000 | 163127.8 | 1 | 167446.6 | -4318.8 | 97.4208 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | a work suspension notice was duly authorised. | a price revision with provisional indices in the amount of €4,318.80 was calculated
1938 | 5617767 | Contract for the improvement of streets , roads and paths in specific areas of the municipality of Albufeira | 45233252-0 | Surface work for streets | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 15 | 21-05-2019 | 29-07-2020 | 435 | 400 | 470000 | 419850 | 2 | 419850 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
1939 | 5617759 | Correction of defects in indoor municipal swimming pools - 1st phase | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Lamego | Viseu | 20 | 14 | 05-04-2019 | 30-03-2020 | 360 | 180 | 250000 | 200000.01 | 1 | 233812.61 | -33812.6 | 85.5386 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of complementary work | execution of complementary work
1940 | 5617333 | Requalification contract for path 1281 (from the Vale de Parra roundabout to Guia). | 45233220-7 | Surface work for roads | FALSE | 2019 | 2021 | Portugal | Albufeira | Faro | 8 | 14 | 20-05-2019 | 09-03-2021 | 659 | 120 | 460000 | 380500 | 2 | 233312.24 | 147187.76 | 163.0862 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the execution period of the project is due to delays on the part of the contractor.
1941 | 5617319 | Contract for the requalification of the EM 526 from the Balaia roundabout to the boundary of the municipality of Loulé | 45233220-7 | Surface work for roads | FALSE | 2019 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 21-05-2019 | 16-06-2020 | 392 | 120 | 987000 | 876370.72 | 2 | 860941.1 | 15429.62 | 101.7922 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
1942 | 5617245 | Replacement of Exterior Frames in the Social services of the National Guard Delegation Building and in the Women's Home of Porto, owned by the Social services of the National Guard | 45100000-8 | Site preparation work | FALSE | 2019 | 2019 | Portugal | Porto | Porto | 13 | 21 | 28-05-2019 | 01-12-2019 | 187 | 30 | 40000 | 34000 | 1 | 34000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1943 | 5616984 | Expansion contract for the general water supply network and domestic wastewater network - Montes Juntos | 45232460-4 | Sanitary works | FALSE | 2019 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 20-05-2019 | 23-10-2019 | 156 | 60 | 99352.61 | 84500 | 1 | 84500 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | delays by the contractor
1944 | 5616719 | Contract for the Refurbishment and Revitalization of the Building of the Old Conde Ferreira School / Hipólito Cabaço Museum | 45212313-3 | Museum construction work | TRUE | 2019 | 2021 | Portugal | Alenquer | Lisboa | 11 | 15 | 03-06-2019 | 07-10-2021 | 857 | 180 | 374999.99 | 374613.72 | 2 | 374917.72 | -304 | 99.9189 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work / covid-19 / archaeological finds / project changes | complementary work and less
1945 | 5615091 | Lighting installation at Leça do Balio Monastery and Avenida General Norton de Matos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 15 | 03-06-2019 | 27-07-2020 | 420 | 30 | 70000 | 68418.95 | 1 | 75109.15 | -6690.2 | 91.0927 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1946 | 5611425 | Contract for the "Mitigating action of incidents due to the lack of the RCT+TP system". (EContracts No. 5010030937) | 45234115-5 | Railway signalling works | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | 21 | 30-05-2019 | 22-03-2021 | 662 | 180 | 590000 | 385089.89 | 2 | 366725.3 | 18364.59 | 105.0077 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A
1947 | 5609386 | The object of this contract is the requalification of the Santos Mattos Elementary School. | 45453100-8 | Refurbishment work | FALSE | 2019 | 2019 | Portugal | Amadora | Lisboa | 11 | 21 | 28-05-2019 | 14-11-2019 | 170 | 90 | 235844.85 | 212260.38 | 1 | 212260.38 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out on schedule. the deviation verified in the project period is due to the late delivery by the contractor of the waste management plan.
1948 | 5608906 | Urbanization Works for the Allotment on the Land located at the confluence of Avenida das Tílias and street of Calçada in Sernancelhe | 45211360-0 | Urban development construction work | TRUE | 2019 | 2020 | Portugal | Sernancelhe | Viseu | 20 | 30 | 24-05-2019 | 09-10-2020 | 504 | 180 | 212972.44 | 206904.05 | 1 | 206649.42 | 254.63 | 100.1232 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the deadline by 45 days | additional work, price revision, underwork
1949 | 5608691 | The object of this contract is the requalification of the Terra dos Arcos Elementary School. | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Amadora | Lisboa | 11 | 21 | 28-05-2019 | 15-10-2020 | 506 | 90 | 188658.97 | 169793.08 | 1 | 169454.68 | 338.4 | 100.1997 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | constraints resulting from the acquisition of some materials, such as aluminum, and especially from covid19. | no work was carried out on article 4.2 - "supply and application of swivel and respective pipes...", in the amount of €338.40
1950 | 5607101 | Construction of water supply and wastewater drainage networks in several streets in the city of Fiães | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 31-05-2019 | 06-07-2020 | 402 | 180 | 119788.68 | 104700.89 | 1 | 102056.3 | 2644.59 | 102.5913 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45-day extension due to bad weather, 84-day delay in delivery of final canvases | underwork due to shorter length in the supply network performed
1951 | 5606646 | Emp-r/4/2019 - contract for the rehabilitation of blocks 9a, 10, 11, 11a, 12, 13, 18 and 19 of the hospital district - funchal | 45442110-1 | Painting work of buildings | FALSE | 2019 | 2021 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 10-05-2019 | 20-05-2021 | 741 | 150 | 250000 | 194994.43 | 1 | 194994.43 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | considering decree of the president of the republic no. 14-a/2020, of march 18, which declares a state of emergency, based on the verification of a situation of public calamity.
1952 | 5605475 | Contract for the rehabilitation of the Ecopista do Dão, after the fires of 15 and 16 October | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Tondela | Viseu | 20 | 21 | 01-02-2019 | 08-09-2020 | 585 | 240 | 848213.45 | 693046.86 | 2 | 676564.09 | 16482.77 | 102.4362 | Best value for money: No Criterion related to quality name: none Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period of the project | given the degradation of the state of the infrastructure, due to the time that elapsed in the elaboration of the project and the execution of the project, there was an increase of works to be carried out.
1953 | 5602314 | Contract for Replacement of Pavements in Supply and Sanitation Networks | 45233220-7 | Surface work for roads | FALSE | 2019 | 2021 | Portugal | Salvaterra de Magos | Santarém | 16 | 14 | 27-05-2019 | 24-05-2021 | 728 | 730 | 171000 | 171000 | 1 | 170810.9 | 189.1 | 100.1107 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline. | it was not necessary to run all the quantities of some articles.
1954 | 5601228 | Contract nº 1/19 - elementary school Orlando Gonçalves - Work Execution | 45453100-8 | Refurbishment work | FALSE | 2019 | 2019 | Portugal | Amadora | Lisboa | 11 | 21 | 27-05-2019 | 13-11-2019 | 170 | 90 | 259367.68 | 233430.92 | 1 | 233430.92 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out on schedule. the deviation verified in the project period is due to the late delivery by the contractor of the waste management plan.
1955 | 5600806 | Construction of the Road connecting the Fortnightly Fair to street of Bombeiros Voluntários, by Contract - CP-CCP-EMP n.º 02/2019 | 45233100-0 | Construction work for highways, roads | FALSE | 2019 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 30 | 30-05-2019 | 10-12-2020 | 560 | 240 | 454680.66 | 393393.64 | 2 | 395710.55 | -2316.91 | 99.4145 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
1956 | 5596289 | Road markings with hot spray plastic and thermoplastic paint on municipal roads in the municipality of Leiria | 45233221-4 | Road-surface painting work | FALSE | 2019 | 2019 | Portugal | Leiria | Leiria | 10 | 14 | 28-05-2019 | 05-12-2019 | 191 | 240 | 119360 | 77137.29 | 1 | 77137.29 | 0 | 100 | Best value for money: No Criterion related to quality Name: N.A. Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no deadline changes
1957 | 5596186 | Acquisition, Construction and Maintenance of Buildings - School Buildings - Requalification of Playgrounds at the Primary School of Ponte de Sor | 45236290-9 | Repair work on recreational areas | FALSE | 2018 | 2021 | Portugal | Ponte de Sor | Portalegre | 12 | 6 | 25-09-2018 | 26-03-2021 | 913 | 30 | 47744.24 | 46748.39 | 1 | 46748.39 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1958 | 5596106 | Public tender for the rehabilitation works of the City Museum building | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Covilhã | Castelo Branco | 5 | 30 | 27-05-2019 | 28-05-2020 | 367 | 180 | 223550 | 222944.9 | 1 | 244800.08 | -21855.18 | 91.0722 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Proposed price / lead time Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a notice of suspension of work on june 11, 2019.
1959 | 5594835 | Construction of an urban park | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 48 | 22-05-2019 | 27-04-2021 | 706 | 730 | 970344.79 | 909745.98 | 2 | 939896.44 | -30150.46 | 96.7922 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50.00%; Technical Quality of the Proposal - 50.00%; face-to-face draw | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed in less time than originally planned. | a price review was determined with definitive indices worth €30,150.46.
1960 | 5591248 | Refurbishment of the headquarters of the Sociedade Filarmónica Veirense | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Estremoz | Évora | 7 | 21 | 27-05-2019 | 03-12-2020 | 556 | 365 | 649413.61 | 638100 | 2 | 721684 | -83584 | 88.4182 | Best value for money: Yes Criterion related to quality Name: Technical Value and Deadline (40% and 10% respectively) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works approved | complementary works approved
1961 | 5589997 | Preventive maintenance work on the roofs of the buildings in the Ilhéu Group (Blocks 1, 2, 3 and 6) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2019 | Portugal | N/A | N/A | N/A | 21 | 23-05-2019 | 17-09-2019 | 117 | 150 | 220000 | 197122.38 | 1 | 197122.38 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the foreseen contractualize
1962 | 5587685 | Construction of retaining walls and fences on streetde Goim - Romariz | 45210000-2 | Building construction work | FALSE | 2018 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 24-05-2019 | 19-12-2019 | 209 | 30 | 136828 | 119575.86 | 1 | 115318.78 | 4257.08 | 103.6916 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 28 days graceful extension 26 days delay due to the contractor | underwork
1963 | 5579431 | Rehabilitation of the buildings at street ofs Carvalheiras n.º 153, 157, 161 and 163 consisting of the construction of the building and reprofiling of the road and stabilization of the west wall | 45210000-2 | Building construction work | FALSE | 2018 | 2021 | Portugal | N/A | N/A | N/A | 30 | 15-05-2019 | 22-02-2021 | 649 | 360 | 660000 | 611276 | 2 | 660213.44 | -48937.44 | 92.5876 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | unforeseen work and additional work
1964 | 5578451 | 100% Quality - track repairs and cap corrections | 45233220-7 | Surface work for roads | FALSE | 2014 | 2019 | Portugal | Matosinhos | Porto | 13 | 36 | 16-07-2015 | 23-04-2019 | 1377 | 1080 | 345000 | 187500 | 1 | 187500 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
1965 | 5577874 | 100% QUALITY - Changes in access to Av. Duarte Pacheco à R. Roberto ivens | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 21-05-2019 | 28-08-2019 | 99 | 45 | 44105 | 28368.15 | 1 | 28368.15 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1966 | 5575378 | Domestic drainage of streetGago Coutinho | 45232460-4 | Sanitary works | FALSE | 2018 | 2020 | Portugal | Barreiro | Setúbal | 17 | 20 | 03-04-2019 | 16-03-2020 | 348 | 150 | 210000 | 197570.53 | 1 | 197856.35 | -285.82 | 99.8555 | Best value for money: Yes Criterion related to quality Name: Quality of the proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | staff and supplier holidays/ delay in connecting the ee to the general electricity grid | there were works unless they were works that were considered unnecessary on site
1967 | 5574548 | 2018.040.02.C1 - DR Norte - remodeling of the transformation station and additional facilities | 45310000-3 | Electrical installation work | TRUE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 21 | 03-12-2018 | 15-12-2020 | 743 | 150 | 263000 | 195942.74 | 1 | 206692.09 | -10749.35 | 94.7993 | Best value for money: No Criterion related to quality Name: Technical value of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension, deadline suspension and complementary work | complementary works
1968 | 5573582 | Rehabilitation contract for the “R1” water reservoir at Quinta do Lago | 45453100-8 | Refurbishment work | FALSE | 2018 | 2020 | Portugal | Loulé | Faro | 8 | 18 | 20-02-2019 | 14-10-2020 | 602 | 90 | 222000 | 181025.48 | 1 | 181025.48 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to pandemic/covid19. graceful extension of the deadline due to delays and planning changes caused by the suspension.
1969 | 5572993 | Paving East Area of ​​the Municipality | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-05-2019 | 10-11-2020 | 543 | 240 | 1093000 | 691222.1 | 2 | 654625.58 | 36596.52 | 105.5905 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 29 days for non-compliance by the contractor and 150 days for correcting physical and documental defects between the 1st inspection and provisional acceptance | underwork
1970 | 5570141 | Paving North Zone of the Municipality | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 17-05-2019 | 14-09-2020 | 486 | 240 | 882308 | 574029.26 | 2 | 571394.42 | 2634.84 | 100.4611 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 6 days for scheduling the inspection, 147 for correcting physical and documental defects | underwork
1971 | 5568829 | Maintenance of Rural Paths | 45233141-9 | Road-maintenance works | FALSE | 2019 | 2020 | Portugal | Guarda | Guarda | 9 | 14 | 15-05-2019 | 20-01-2020 | 250 | 90 | 250000 | 184390 | 1 | 187652.59 | -3262.59 | 98.2614 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | an inspection was carried out for the purposes of provisional acceptance on 10/01/2019. anomalies were verified and a period of 60 days was granted to correct them. | price review
1972 | 5568811 | Rehabilitation of the Typical Orchestra, Songbook and Conservatory buildings and the surrounding outdoor space | 45200000-9, 45110000-1, 45112000-5 | Works for complete or part construction and civil engineering work, Building demolition and wrecking work and earthmoving work, Excavating and earthmoving work | FALSE | 2018 | 2021 | Portugal | Águeda | Aveiro | 1 | 5 | 21-03-2019 | 18-06-2021 | 820 | 120 | 1100731.45 | 1019983.46 | 3 | 1061377.88 | -41394.42 | 96.0999 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for execution of the project was changed due to work suspensions and deadline extensions. it should be noted that the project execution period was 365 days and not 120 days as initially communicated (when submitting the contract formation report). | the value of the project was changed due to the approval of the complementary work maps.
1973 | 5566420 | DPES-CPublica - 11/2018-Rainwater drainage network on the street Zona Industrial da Pedrulha | 45232440-8 | Construction work for sewage pipes | FALSE | 2018 | 2021 | Portugal | Coimbra | Coimbra | 6 | 23 | 30-01-2019 | 27-08-2021 | 940 | 150 | 230000 | 217831.81 | 1 | 190941.45 | 26890.36 | 114.083 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | charged to the owner | there was underwork
1974 | 5566373 | PRC_0434/2018_GAE-AA0407 - Execution contract for PE Cabeço - SAA Arcossó (Valpaços) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2019 | 2020 | Portugal | Valpaços | Vila Real | 19 | 14 | 17-05-2019 | 04-11-2020 | 537 | 60 | 66000 | 54650.28 | 1 | 54650.28 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
1975 | 5566162 | PRC_0403/2018_GAE-EB0414 - Construction contract for the Wastewater Drainage Network on EM 614 and crossstreet of Casares, in the parish of Revelhe (Fafe) | 45232411-6 | Foul-water piping construction work | FALSE | 2019 | 2019 | Portugal | Fafe | Braga | 3 | 14 | 16-05-2019 | 26-10-2019 | 163 | 60 | 120000 | 105456.23 | 1 | 104033.81 | 1422.42 | 101.3673 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline and budget met | exact measurements of the project, resulting in underwork worth €1422.42
1976 | 5563241 | Urban rehabilitation of the central area of ​​Fiães - Phase 4 | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 30-04-2019 | 24-06-2021 | 786 | 180 | 335929 | 334530.93 | 2 | 361799.95 | -27269.02 | 92.463 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 52 days of legal extension of the deadline and 98 days of grace, 63 days of delay of the contractor in the conclusion of the projects. 163 days between the 1st inspection and the provisional acceptance resulting from issues related to edp | complementary work and less
1977 | 5560831 | Construction contract for the water supply pipeline to the farm’s hill from the spring of Anieiras water pipeline | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2021 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 15 | 06-05-2019 | 29-06-2021 | 785 | 240 | 1120000 | 868812.34 | 2 | 861483.96 | 7328.38 | 100.8507 | Best value for money: Yes Criterion related to quality Name: Period of execution of the Work and Technical Valuation of the Work Plan Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic situation and adverse weather conditions | underwork
1978 | 5558403 | 100% QUALITY – Alteration of the pavement on R. Cândido dos Reis in Custóias | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 15 | 15-05-2019 | 17-02-2020 | 278 | 45 | 146500 | 104417.5 | 1 | 104417.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
1979 | 5556702 | Requalification of the Surrounding Area of ​​the Town Hall Buildings. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2019 | 2019 | Portugal | Alijó | Vila Real | 19 | 14 | 09-05-2019 | 29-11-2019 | 204 | 180 | 160150 | 145227 | 1 | 145227 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1980 | 5556527 | Contract for "Beira Baixa Line - Complete Rehabilitation of Track. Migration from TM to TBB- Phase 2: PK 28,030/53,420 and Mouriscas - Line II" | 45234100-7 | Railway construction works | FALSE | 2019 | 2021 | Portugal | Vila Velha de Ródão | Santarém | 16 | 24 | 13-05-2019 | 01-03-2021 | 658 | 120 | 1623144.46 | 1445223.9 | 3 | 1482677.88 | -37453.98 | 97.4739 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 35% Criterion related to cost Name: Price Weighting: 65% | 1 | 65 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1981 | 5556333 | Requalification and Modernization of the facilities of the Fernão de Magalhães School, Chaves | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2021 | Portugal | Chaves | Vila Real | 19 | 24 | 06-05-2019 | 09-08-2021 | 826 | 365 | 530691.3 | 470637.1 | 2 | 463908.66 | 6728.44 | 101.4504 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork worth €10,021.26 and price review worth €3,292.82
1982 | 5554484 | C. Public No. 34/ Social services of the National Guard/2019 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 02-05-2019 | 01-12-2019 | 213 | 120 | 90000 | 83115 | 1 | 83115 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price/Cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1983 | 5554383 | C. Public No. 31/2019 | 45000000-7 | Construction work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 21 | 12-04-2019 | 06-01-2020 | 269 | 120 | 235000 | 193295 | 1 | 193295 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1984 | 5554303 | Total Refurbishment of the Exterior of Four Buildings and Replacement of Roofs in Alto Pina, Property of the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 11-04-2019 | 06-01-2020 | 270 | 120 | 240000 | 213236.5 | 1 | 213236.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
1985 | 5554200 | Total Refurbishment of the Interior of Four Apartments in Chelas, Property of the Social services of the National Guard | 45450000-6 | Other building completion work | FALSE | 2019 | 2020 | Portugal | Lisboa | Lisboa | 11 | 21 | 16-04-2019 | 01-01-2020 | 260 | 150 | 180000 | 176761.8 | 1 | 176761.8 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price/cost Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
1986 | 5553896 | Requalification and expansion of the Fafião school - Briteiros Sto. Stephen | 45214210-5 | Primary school construction work | TRUE | 2019 | 2020 | Portugal | Guimarães | Braga | 3 | 20 | 08-05-2019 | 29-07-2020 | 448 | 300 | 676173.77 | 601425.44 | 2 | 596882.33 | 4543.11 | 100.7611 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the approval of the safety and health plan for the project was communicated on 07/15/2019. following the inspection report for provisional acceptance (11/05/2020), the successful tenderer was granted a period of 20 days to correct anomalies. | existence of underwork due to the foreseen quantities not being used up.
1987 | 5552719 | Contract for "Rehabilitation of the Building Set for an Exhibition Nucleus, in Póvoa e Meadas" | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2019 | 2020 | Portugal | Castelo de Vide | Portalegre | 12 | 20 | 25-04-2019 | 14-08-2020 | 477 | 180 | 166735.98 | 165990 | 1 | 165990 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price as the only aspect of the execution of the contract to be concluded - lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period of the project | there were no changes to the value of the project
1988 | 5550844 | Construction of a retaining wall at street of Fonte - Travanca | 45210000-2 | Building construction work | FALSE | 2019 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-05-2019 | 15-07-2020 | 429 | 90 | 118292 | 108577.42 | 1 | 99803.12 | 8774.3 | 108.7916 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 184 days for free extensions for reasons beyond the control of the project owner | underwork in earthmoving
1989 | 5550727 | Urban rehabilitation of street layout - Largo Inácio Monteiro - Souto | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2019 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 13-05-2019 | 09-12-2019 | 210 | 75 | 34412.89 | 25006.46 | 1 | 22794.15 | 2212.31 | 109.7056 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 23 days corresponding to the period for scheduling the inspection for provisional acceptance | underwork
1990 | 5550598 | Construction of the Emigrant Square | 45000000-7 | Construction work | FALSE | 2019 | 2020 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | N/A | 08-05-2019 | 30-06-2020 | 419 | 210 | 290000 | 281400 | 2 | 281400 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price: 60%; 2. Work Execution Quality: 40%; The. Descriptive memory and justification of the execution of the work: 30%; B. Work plan: 25%; ç. Labor Plan: 25% d. Equipment Plan: 20% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline | price review
1991 | 5549781 | Public works contract - Construction of cycle routes in the Planalto Central area of ​​Lisbon - street dison and Avenida de Paris | 45113000-2 | Siteworks | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-02-2019 | 11-07-2019 | 141 | 49 | 100000 | 93000 | 1 | 75494.03 | 17505.97 | 123.1885 | Best value for money: Yes Criterion related to quality Name: Lead time Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | objective modification to the contract | objective modification to the contract
1992 | 5548147 | 5010038054 - Work contract for the Anticorrosive Protection of Metallic Bridges on the North Line, phase 4 | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2018 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 39 | 08-05-2019 | 15-03-2021 | 677 | 210 | 660000 | 409268.74 | 2 | 340835.12 | 68433.62 | 120.0782 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | 21-day advance deadline for the contract
1993 | 5545879 | Public Tender for the Construction Contract for the Multipurpose Building on the Commercial Pier of the Port of Figueira da Foz | 45213350-1 | Construction work for buildings relating to various means of transport | TRUE | 2018 | 2020 | Portugal | Figueira da Foz | Coimbra | 6 | 28 | 04-04-2019 | 22-05-2020 | 414 | 210 | 990000 | 987329.85 | 2 | 1013471.58 | -26141.73 | 97.4206 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | additional contract | additional contract
1994 | 5544083 | 2017.036.01.C1 - Penafiel Employment Services - facilities refurbishment | 45210000-2 | Building construction work | TRUE | 2018 | 2019 | Portugal | Penafiel | Porto | 13 | 21 | 18-02-2019 | 19-12-2019 | 304 | 210 | 349870 | 328336.94 | 2 | 342063.67 | -13726.73 | 95.9871 | Best value for money: No Criterion related to quality Name: Valia Tecnica of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary work and price review
1995 | 5541618 | Construction of retaining walls in granite masonry - February 2019 | 45262510-9 | Stonework | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 9 | 06-05-2019 | 28-10-2020 | 541 | 180 | 149072 | 133752.5 | 1 | 128481.48 | 5271.02 | 104.1026 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended. | underwork worth 5,271.02
1996 | 5541418 | Contract 19/GEBALIS/2018 - Contract for the Maintenance and Repair of housing and Common Areas in Neighborhoods in the East Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2019 | 2021 | Portugal | Lisboa | Lisboa | 11 | 15 | 09-05-2019 | 11-08-2021 | 825 | 730 | 600000 | 588852.8 | 2 | 588852.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | maintenance contract
1997 | 5540938 | Execution of the contract for “Requalification of the Training Field of the Municipal Sports Complex – Municipal Stadium”, | 45212200-8 | Construction work for sports facilities | FALSE | 2017 | 2019 | Portugal | Lagos | Faro | 8 | N/A | 07-03-2018 | 28-03-2019 | 386 | 120 | 450000 | 449620.63 | 2 | 449620.63 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay caused by rupture of the mains with direct interference in the execution of the projects, unpredictable interruption of supply and application of synthetic grass, delay of the supplier of the covering of the changing rooms.
1998 | 5538016 | Contract for "Improvement and Requalification of EM 544-1-Section from Valpaços to Vale de Casas | 45233220-7 | Surface work for roads | FALSE | 2019 | 2019 | Portugal | Valpaços | Vila Real | 19 | 18 | 15-04-2019 | 08-11-2019 | 207 | 180 | 330188.68 | 280696.71 | 2 | 280696.71 | 0 | 100 | Best value for money: No Criterion related to quality Name: nothing Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | consignment note signed later.
1999 | 5537563 | Public tender for the award of the contract for "Requalification of streetCidade de Recife Largo João da Rocha and streetZinguinchor" | 45233200-1 | Various surface works | TRUE | 2019 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 09-05-2019 | 23-02-2021 | 656 | 210 | 1146755.85 | 1135426.51 | 3 | 1088166.21 | 47260.3 | 104.3431 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | covid-19 measures. | underwork.
2000 | 5535436 | 2-Emp/19 - Contract for the execution of the pedestrian and cycle bridge over the Almargem stream. | 45422100-2 | Woodwork | FALSE | 2019 | 2021 | Portugal | N/A | N/A | N/A | N/A | 29-04-2019 | 30-11-2021 | 946 | 120 | 180179.03 | 158354.63 | 1 | 156958.53 | 1396.1 | 100.8895 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 6 | FALSE | N/A | N/A | N/A | N/A | FALSE | extensions of deadline and delivery of the technical compilation. | definitive price revision in the amount of -1,396.10€ (negative).
2001 | 5535249 | Rehabilitation contract for the listed building "Ex-Grémio da Lavoura" - Centro Documental da Oliveira. | 45453100-8 | Refurbishment work | FALSE | 2018 | 2021 | Portugal | Moura | Beja | 2 | 30 | 18-04-2019 | 29-12-2021 | 986 | 180 | 506819.12 | 499412.92 | 2 | 556436.06 | -57023.14 | 89.7521 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | request for 4 deadline extensions | unpredictable complementary work worth €45,361.50
2002 | 5531773 | Requalification of the area surrounding the Paços do Concelho Building. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | São João da Pesqueira | Viseu | 20 | 12 | 29-01-2019 | 20-08-2020 | 569 | 270 | 346821.7 | 335770 | 2 | 335770 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a delay of 159 days attributable to the contracting party, however, pursuant to law n.º 1.a/2020, of march 19 and law n.º 4.a/2020, of april 6, the deadline was suspended for 29 days due to the epidemiological infection sars-cov-2. obtaining a total of 130 days of effective delay in the contract. | it was necessary to carry out complementary works that were not initially foreseen in the initial project, detected only during the course of the project, which translated into a technical and economic added value for the client, since they allow the technical correction of the project, as well as a better adequacy of the project to the existing reality.
2003 | 5529391 | Construction of the EB 2.3 School in Santa Luzia | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2021 | Portugal | Elvas | Portalegre | 12 | 28 | 12-04-2019 | 30-11-2021 | 963 | 670 | 6090729 | 5922247 | 3 | 5989231.18 | -66984.18 | 98.8816 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a need to make several corrections in the project in order to be able to carry out the provisional acceptance | there was a need to carry out complementary works to the contract, such as the suppression of other works.
2004 | 5526938 | Public Tender for the award of the contract for "Requalification of the Public Space surrounding the Social Neighborhood of Meadela (IRHU)" | 45113000-2 | Siteworks | FALSE | 2019 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 3 | 06-05-2019 | 19-08-2020 | 471 | 120 | 582783.55 | 582030.26 | 2 | 499652.51 | 82377.75 | 116.487 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
2005 | 5526062 | Requalification of the municipal library afonso lopes vieira - replacement of spans, leiria | 45421110-8 | Installation of door and window frames | FALSE | 2018 | 2020 | Portugal | Leiria | Leiria | 10 | 21 | 06-03-2019 | 29-06-2020 | 481 | 90 | 141721.21 | 99540 | 1 | 99540 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2006 | 5525187 | Cpn 06/2019/dicp - t-66/2018 - construction of promenade on en 356 (campos-cerca), parish of maceira, leiria | 45233161-5 | Footpath construction work | FALSE | 2019 | 2019 | Portugal | Leiria | Leiria | 10 | 14 | 27-03-2019 | 28-08-2019 | 154 | 120 | 160025.15 | 136787.3 | 1 | 136787.3 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2007 | 5524800 | Trafaria prison - rehabilitation of building 3 | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Almada | Setúbal | 17 | 18 | 02-04-2019 | 27-02-2020 | 331 | 180 | 315579.87 | 315408.62 | 2 | 310042.48 | 5366.14 | 101.7308 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Bid Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work | underwork
2008 | 5524439 | 5010033886 - Contract "Sintra Line - Rossio Tunnel - Reformulation of Special Installations (Emergency Lighting)" | 50000000-5 | Repair and maintenance services | FALSE | 2018 | 2020 | Portugal | Lisboa | Lisboa | 11 | 7 | 22-04-2019 | 16-11-2020 | 574 | 150 | 300000 | 255437.27 | 2 | 249775.65 | 5661.62 | 102.2667 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | anticipation of the execution period of the project of 10 days | revision of prices and additional work less
2009 | 5523454 | Soft Mobility Infrastructure Improvement Program - Correction of Discontinuities in the Quinta da Lousa Area - Valongo | 45233252-0 | Surface work for streets | FALSE | 2019 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 29-04-2019 | 16-11-2021 | 932 | 150 | 137000 | 117042.86 | 1 | 126617.07 | -9574.21 | 92.4385 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allotment of 35 days for the execution of additional work (additional contract signed on 12.04.2019) note: the last measurement report dates from 23.12.2020, there was only a delay in scheduling the inspection for provisional reception purposes. | additional work: €7,832.75 underwork: - €326.32 final calculation of the price revision: €2,067.78
2010 | 5521105 | Contract for requalification of the exterior pavement and finishing of the exterior facades of the building of the School of Architecture of the University of Minho | 45450000-6 | Other building completion work | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 14 | 03-04-2019 | 04-11-2019 | 215 | 60 | 75000 | 69440 | 1 | 49979.25 | 19460.75 | 138.9377 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the removal of existing mechanical equipment in the areas involved in the project. | reformulation of intervention areas and alteration of construction solutions / finishes, with special focus on floors.
2011 | 5521070 | Replacement of fiber-cement roofs with Sandwich panels, renovation work on the interior of the building, adapting it to children with special needs, located at street of Ougueiros – | 45214200-2 | Construction work for school buildings | FALSE | 2019 | 2019 | Portugal | Valongo | Porto | 13 | 15 | 15-04-2019 | 13-11-2019 | 212 | 150 | 162500 | 139285.65 | 1 | 161879.55 | -22593.9 | 86.0428 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of complementary works in the amount of €10,750.30 and €11,843.60, which were assigned, respectively, 20 days and 15 days as execution deadline. allocation of more human resources in the execution of the project, reduced the execution period. | approval of complementary works in the total amount of €22,593.90
2012 | 5519595 | Requalification of the Boticas Sports Complex - Lot 1 | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2019 | 2021 | Portugal | Boticas | Vila Real | 19 | 16 | 30-04-2019 | 26-07-2021 | 818 | 120 | 283018.87 | 135496.72 | 1 | 135496.72 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
2013 | 5518782 | Cleaning, milling and video inspection of plots P4, P5 and P6 at Herdade da Aroeira | 45232460-4 | Sanitary works | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 15 | 14-11-2018 | 10-04-2019 | 147 | 90 | 40800 | 40225 | 1 | 40225 | 0 | 100 | Best value for money: No Criterion related to quality Name: Not Applicable Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the sole aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2014 | 5518686 | Reconstruction/sealing of the lake in João Paulo II Park - Vila do Conde | 45453100-8 | Refurbishment work | FALSE | 2019 | 2020 | Portugal | Vila do Conde | Porto | 13 | 21 | 28-03-2019 | 10-07-2020 | 470 | 180 | 170000 | 145033 | 1 | 137283 | 7750 | 105.6453 | Best value for money: No Criterion related to quality Name: __ Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2015 | 5517942 | Requalification of the Boticas Sports Complex | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2019 | 2021 | Portugal | Boticas | Vila Real | 19 | 16 | 24-04-2019 | 26-07-2021 | 824 | 120 | 283018.87 | 143781.49 | 1 | 143781.49 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | during the period of school holidays, there were daily activities promoted by the municipality, carried out in the multipurpose building, removing some speed from the normal course of work; the period of energy crisis, aided by the closure of some companies during the month of august, delayed the supply of materials, also causing some deadlock in the execution of the projects.
2016 | 5517736 | Barroso Nature Observation Center | 45212120-3 | Theme park construction work | FALSE | 2019 | 2021 | Portugal | Boticas | Vila Real | 19 | 18 | 24-04-2019 | 14-01-2021 | 631 | 210 | 278200 | 264334.73 | 2 | 261334.73 | 3000 | 101.148 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the atmospheric conditions that were felt, especially in the high rainfall, aided by the existing type of terrain, of a vegetable nature, prevented the movement of mechanical equipment and consequently the execution of the projects. | underpinning this claim is the fact that for the dissemination of activities related to the nature observation center of barroso, the placement of five billboards with metallic structure and printing on canvas, with dimensions 8*5m, is foreseen. however, the planned placement points are distributed along the n312, n103 and r311 roads, which under the terms of law no. to the prior opinion of infraestruturas de portugal, and the rules laid down in the internal document of this body, regarding visible advertising on the roads, must be complied with. these impose in their points 8 and 9 criteria for the placement and location of the panels. however, given the size of the panels and the mandatory minimum spacing, starting from the outer limit of the carriageway, it appears that the legally possible location is incompatible with the disclosure criteria intended by this municipality, since their placement in the places permissible, would have little visual impact on motorists and passers-by.
2017 | 5514874 | Improvement of streets in Ortiga | 45233140-2 | Roadworks | FALSE | 2010 | 2019 | Portugal | Mação | Santarém | 16 | 31 | 22-02-2011 | 07-03-2019 | 2935 | 45 | 151950.55 | 151928.68 | 1 | 151928.68 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension
2018 | 5514803 | Installation of LEDs in Public Lighting | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2018 | 2019 | Portugal | Miranda do Douro | Bragança | 4 | 24 | 12-04-2019 | 11-10-2019 | 182 | 150 | 508267 | 452173.48 | 2 | 452173.48 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Energy Efficiency of Luminaires - 45%; Warranty Period Luminaires - 5%; Execution time - 5% Weighting: 55% Criterion related to cost Name: Price Weighting: 45% | 1 | 45 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | favorable climate conditions for the performance of the projects
2019 | 5514714 | Replacement of Roofs on EB nº 1 in Baixa da Banheira | 45261213-0 | Metal roof-covering work | FALSE | 2018 | 2019 | Portugal | Moita | Setúbal | 17 | 30 | 22-04-2019 | 20-11-2019 | 212 | 120 | 180000 | 165280.65 | 1 | 165280.65 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2020 | 5514345 | T-65/2018- repairs to the east building of the municipal market for the installation of the transitory market - leiria | 45213141-3 | Covered market construction work | FALSE | 2019 | 2020 | Portugal | Leiria | Leiria | 10 | 17 | 11-03-2019 | 29-06-2020 | 476 | 20 | 127534.6 | 114947 | 1 | 139664.54 | -24717.54 | 82.3022 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A |  | unforeseen work resulting from errors and omissions
2021 | 5514252 | Exterior maintenance work on the Regado Municipal Public Housing buildings blocks 1 to 5 - Lot 1 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 17-04-2019 | 09-03-2020 | 327 | 270 | 1820000 | 422746.84 | 2 | 419559.74 | 3187.1 | 100.7596 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | work took place within the foreseen contractual terms | underwork
2022 | 5513497 | Rehabilitation of social housing developments - Paços de Brandão | 45210000-2 | Building construction work | FALSE | 2018 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 24-04-2019 | 06-08-2021 | 835 | 180 | 369124.5 | 368000.06 | 2 | 367064.88 | 935.18 | 100.2548 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 63 days of work suspension, 179 days of graceful extension, 34 days for scheduling inspections, 268 days between the 1st inspection and provisional acceptance to correct deficiencies | underwork
2023 | 5513165 | Public Tender No. 2/DRCALEN/2018 - Contract:"Citizenship House - Salgueiro Maia". | 50000000-5 | Repair and maintenance services | FALSE | 2018 | 2021 | Portugal | Castelo de Vide | Portalegre | 12 | 30 | 02-04-2019 | 07-12-2021 | 980 | 400 | 925000 | 836200 | 2 | 836200 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Proposal Quality Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project presented an irregular development due to the great constraints of covid 19, which affected various elements of the different companies of the subcontractors and caused prophylactic isolation of the majority of the teams in different periods of development of the projects. | nothing to register.
2024 | 5513147 | Execution of the Qualification of the City's Interfaces | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2021 | Portugal | Viseu | Viseu | 20 | 20 | 29-04-2019 | 14-12-2021 | 960 | 120 | 208000 | 198123.62 | 1 | 209342.8 | -11219.18 | 94.6408 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: non-existent Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | at the request of the contractor due to bad weather and the context of the covid 19 pandemic, which led to a lack of labour. | works of the same kind as others foreseen and not foreseen in the contract and alteration to the texture of the pavements, according to information in the process.
2025 | 5511753 | Rehabilitation of Av.ª Adelino Amaro da Costa and Av.ª Gago Coutinho - PARU do Marco de Canaveses | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 05-04-2019 | 01-10-2020 | 545 | 240 | 698905.92 | 643881.25 | 2 | 640820.29 | 3060.96 | 100.4777 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was suspended | the project had underwork and complementary work.
2026 | 5508496 | 2018/159 - DGEP - Construction of a roundabout in Leceia, Oeiras | 45232460-4, 45233140-2, 45112710-5, 45262310-7, 45316000-5 | Sanitary works, Roadworks, Landscaping work for green areas, Reinforced-concrete work, Installation work of illumination and signalling systems | FALSE | 2018 | 2021 | Portugal | Oeiras | Lisboa | 11 | 21 | 12-04-2019 | 18-10-2021 | 920 | 120 | 327691.03 | 297000 | 2 | 297755.12 | -755.12 | 99.7464 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2027 | 5508372 | Access and connection of the building to the existing road; execution of walls and exterior fencing, allowing on the one hand the limit of the lot, and in a controlled way that the animals can temporarily leave the enclosures | 45211360-0 | Urban development construction work | FALSE | 2018 | 2020 | Portugal | Sesimbra | Setúbal | 17 | 30 | 21-01-2019 | 02-11-2020 | 651 | 300 | 450000 | 444157.04 | 2 | 583024.66 | -138867.62 | 76.1815 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 300 days of initial execution period and 211 days of extension of the execution period under the terms of article 374 of the "public procurement code". | errors and omissions, overwork, underwork and compensation to the contractor.
2028 | 5508150 | General improvement of the MT floating dock in Foz de Odeleite | 45241100-9 | Quay construction work | FALSE | 2018 | 2019 | Portugal | Castro Marim | Faro | 8 | 14 | 19-03-2019 | 18-09-2019 | 183 | 84 | 75000 | 66290 | 1 | 66290 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2029 | 5505569 | 2018/171 - DGEP - Execution of a temporary car park next to the finances of Paço de Arcos | 45223300-9 | Parking lot construction work | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 26-03-2019 | 18-06-2020 | 450 | 75 | 46780 | 43278.22 | 1 | 46738.72 | -3460.5 | 92.5961 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | extra work
2030 | 5505521 | Quality 100% - conservation of road markings in the municipality of matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | Matosinhos | Porto | 13 | 15 | 09-04-2019 | 10-09-2021 | 885 | 365 | 230000 | 227794.4 | 1 | 222772.92 | 5021.48 | 102.2541 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | the entire contract has not been performed
2031 | 5504182 | Requalification of the Transport Coordinating Center (Truck Center) | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2018 | 2020 | Portugal | Fafe | Braga | 3 | 30 | 12-02-2019 | 05-11-2020 | 632 | 180 | 349296.96 | 349252.55 | 2 | 348244.55 | 1008 | 100.2895 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 60% Criterion related to cost Name: Technical Value of the Proposal Weighting: 40% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a deadline extension due to minor adjustments to the project | the quantities foreseen in some articles were not executed
2032 | 5503294 | Requalification of streets in Louriceira and other places in the Municipality of Alcanena | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Alcanena | Santarém | 16 | 30 | 17-04-2019 | 13-05-2020 | 392 | 120 | 315659.65 | 263900 | 2 | 263900 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | last self measurement 09/24/2019
2033 | 5502858 | Contract for the conservation and improvement of the municipality's road network - Municipal roads and paths in the parish of Luz de Tavira and Santo Estêvão | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Tavira | Faro | 8 | 30 | 15-04-2019 | 17-07-2020 | 459 | 120 | 279579.2 | 199193.9 | 1 | 202381.58 | -3187.68 | 98.4249 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the projects were completed and accepted before the deadline for the project | price review
2034 | 5502115 | EMP-R/12/2018 - Contract for the Rehabilitation of the Blocks of the Housing Complex on Estrada Comandante Camacho de Freitas - Funchal | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 27-03-2019 | 18-10-2019 | 205 | 120 | 298000 | 219771.31 | 1 | 219771.31 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project were carried out within the deadline
2035 | 5501118 | Rehabilitation of the Municipal Housing Park - Vale da Amoreira | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Moita | Setúbal | 17 | 30 | 21-03-2019 | 27-12-2019 | 281 | 180 | 285500 | 262009.48 | 2 | 258161.47 | 3848.01 | 101.4905 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
2036 | 5501033 | Requalification of the Riverfront between Moita and Gaio | 45246200-5 | Riverbank protection works | FALSE | 2018 | 2019 | Portugal | Moita | Setúbal | 17 | 30 | 11-03-2019 | 28-11-2019 | 262 | 180 | 257300 | 239057.61 | 1 | 248383.12 | -9325.51 | 96.2455 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
2037 | 5499712 | Paving Urbanização das Penas - Paços de Brandão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-04-2019 | 24-06-2020 | 435 | 180 | 188425 | 157930.97 | 1 | 164347.85 | -6416.88 | 96.0955 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 19 days of extension due to complementary work, 53 days of extension for free, and 30 days for scheduling and carrying out the provisional acceptance inspection | complementary and less approved works
2038 | 5498760 | 2018/187 - DGEP - Containment in gabions on the left bank of Ribeira da Laje, adjacent to the Municipal Garden of Oeiras | 45316100-6, 45246200-5 | Installation of outdoor illumination equipment, Riverbank protection works | FALSE | 2018 | 2021 | Portugal | Oeiras | Lisboa | 11 | 21 | 03-04-2019 | 16-03-2021 | 713 | 60 | 87217.33 | 79000.02 | 1 | 82667.49 | -3667.47 | 95.5636 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2039 | 5495398 | Circular of Vale Figueira | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Grandola | Setúbal | 17 | 30 | 21-03-2019 | 16-09-2020 | 545 | 120 | 140664.83 | 127700 | 1 | 148630.21 | -20930.21 | 85.9179 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions of the project term | additional works (1st moc) and price review
2040 | 5493199 | Repair and painting of the Municipal Cemetery of Olhão | 45215400-1 | Cemetery works | FALSE | 2018 | 2019 | Portugal | Olhão | Faro | 8 | 15 | 01-04-2019 | 30-07-2019 | 120 | 90 | 160000 | 143267.14 | 1 | 143267.14 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2041 | 5491909 | Requalification of the public space surrounding the Social Neighborhood in Darque (IHRU) | 45233200-1 | Various surface works | FALSE | N/A | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | N/A | 11-04-2019 | 15-05-2020 | 400 | 90 | N/A | 263229.8 | 2 | 260529.8 | 2700 | 101.0363 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork.
2042 | 5487032 | Expansion of the former primary school in Vila da Ponte to become a nautical sports center on the Távora River | 45262700-8 | Building alteration work | FALSE | 2019 | 2020 | Portugal | Viseu | Viseu | 20 | 30 | 08-04-2019 | 14-01-2020 | 281 | 240 | 238734.41 | 238642.83 | 1 | 230390.73 | 8252.1 | 103.5818 | Best value for money: Yes Criterion related to quality Name: Technical Valuation of the Proposal (VT) Weighting: 40% Criterion related to cost Name: Price (P) Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the project period by 30 days | underwork worth €8,252.10
2043 | 5486823 | Creation of a pedestrian route through the construction/lowering of sidewalks in the crosswalk areas and ordering parking with the reformulation of parking bays | 45233251-3 | Resurfacing works | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 20-03-2019 | 16-11-2021 | 972 | 150 | 107000 | 82815.3 | 1 | 84525.68 | -1710.38 | 97.9765 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period. (the 3rd measurement report is dated 07.30.2019 - "completion of the project", the 4th and last measurement report of 01.10.2020, concerns only the dismantling of the shipyard, since, by mistake, it was not included the provisional reception took place on 28.04.2020, with some delay, as the project was awaited by ip - infraestruturas de portugal, which only took place on 27.04.2020. | approval of the final calculation of the price revision, in the amount of €1,710.38 + vat
2044 | 5485856 | Assumadas road refurbishment contract (Ferreiras, up to the limit of the municipality of Silves) | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 15 | 29-03-2019 | 06-03-2020 | 343 | 30 | 330000 | 263969.5 | 2 | 263969.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
2045 | 5485617 | Cpn 24/2018/dicp - t-29/2018 - rehabilitation and improvement of several streets in the municipality of leiria | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Leiria | Leiria | 10 | 28 | 14-11-2018 | 09-11-2020 | 726 | 180 | 3628028.26 | 889928.63 | 2 | 889928.63 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
2046 | 5485560 | Cpn 24/2018/dicp - t-29/2018 - rehabilitation and improvement of several streets in the municipality of leiria | 45233220-7 | Surface work for roads | FALSE | 2018 | 2021 | Portugal | Leiria | Leiria | 10 | 28 | 27-11-2018 | 24-09-2021 | 1032 | 180 | 3628028.26 | 610261.38 | 2 | 592309.51 | 17951.87 | 103.0308 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension pursuant to art. 365, b) of the "public procurement code" | underwork under the terms of art. 379º, nº 2
2047 | 5485321 | Cpn 24/2018/dicp - t-29/2018 - rehabilitation and improvement of several streets in the municipality of leiria | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Leiria | Leiria | 10 | 28 | 23-11-2018 | 09-11-2020 | 717 | 180 | 3628028.26 | 603970.35 | 2 | 603970.35 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
2048 | 5485078 | Cpn 24/2018/dicp - t-29/2018 - rehabilitation and improvement of several streets in the municipality of leiria | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Leiria | Leiria | 10 | 28 | 28-11-2018 | 16-03-2020 | 474 | 180 | 3628028.26 | 604999 | 2 | 636704.14 | -31705.14 | 95.0204 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | changes in chains of complementary work | additional work
2049 | 5484672 | Refurbishment contract for the Amorosa Health Unit | 45454000-4 | Restructuring work | FALSE | 2018 | 2021 | Portugal | Braga | Braga | 3 | 24 | 11-02-2019 | 18-10-2021 | 980 | 270 | 790000 | 780000 | 2 | 857801.17 | -77801.17 | 90.9302 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension until april 30, 2021 | complementary works
2050 | 5482762 | 5010031559 - Contract on the Tomar Branch - Replacement of Wooden Sleepers with Biblock Concrete Sleepers and Passag for BLS - KP 2.156 to KP 6.274 - Phases 1 and 2 | 45234100-7 | Railway construction works | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 34 | 28-03-2019 | 23-09-2020 | 545 | 180 | 2032000 | 1649962.65 | 3 | 1645963.21 | 3999.44 | 100.243 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 65% Technical Valuation: 15% Security Management System: 10% Quality Management System: 5% Environmental Management System: 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2051 | 5481644 | Work to repave the path of Aldeia Grande | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 15 | 29-03-2019 | 28-06-2019 | 91 | 30 | 94000 | 84150.6 | 1 | 83325.6 | 825 | 100.9901 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
2052 | 5480284 | Contract for the supply of water to the SKY CITY allotment, parish of Venteira, municipality of Amadora. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 11 | 06-03-2019 | 09-10-2020 | 583 | 150 | 218000 | 160422.57 | 1 | 160422.37 | 0.2 | 100.0001 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | vat settlements
2053 | 5476267 | Installation of synthetic turf and improvement of facilities in the Fornelo games park | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 15 | 05-04-2019 | 13-08-2020 | 496 | 75 | 271115 | 259427.33 | 2 | 259060.27 | 367.06 | 100.1417 | Best value for money: Yes Criterion related to quality Name: TECHNICAL QUALITY OF THE PROPOSAL Weighting: 50% Criterion related to cost Name: PRICE Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | there was underwork
2054 | 5474549 | Stabilization contract for the Earth Support Wall at the Clinical Center - Lisbon | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | N/A | 2019 | Portugal | N/A | N/A | N/A | N/A | 27-11-2018 | 15-07-2019 | 230 | 120 | N/A | 81500 | 1 | 81500 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions
2055 | 5470667 | Creation of Zone 30 on street1º Maio - Baixa da Banheira | 45233251-3 | Resurfacing works | FALSE | 2018 | 2019 | Portugal | Moita | Setúbal | 17 | 30 | 03-12-2018 | 02-12-2019 | 364 | 240 | 282500 | 264905.38 | 2 | 269374.45 | -4469.07 | 98.3409 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | includes price revision values.
2056 | 5469595 | Construction contract for two buildings with ossuaries and columbariums in the cemetery of Alenquer – Carregado | 45215400-1 | Cemetery works | TRUE | 2019 | 2020 | Portugal | Alenquer | Lisboa | 11 | 14 | 04-04-2019 | 06-05-2020 | 398 | 30 | 24268.18 | 23994.19 | 1 | 23994.19 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2057 | 5468691 | 2018.017.01.C1 - CEFPI Gaia - Replacement of fiber cement roofing | 45261213-0 | Metal roof-covering work | TRUE | N/A | 2019 | Portugal | N/A | N/A | N/A | N/A | 14-01-2019 | 11-09-2019 | 240 | 100 | N/A | 75415.34 | 1 | 80008.04 | -4592.7 | 94.2597 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works | complementary work and suppression of work
2058 | 5467034 | “Avenida João da Cruz/ Praça Cavaleiro Ferreira and Avenida Sá Carneiro/Stairs” | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Bragança | Bragança | 4 | 30 | 07-03-2019 | 07-12-2021 | 1006 | 480 | 3063207.55 | 1215000 | 3 | 1215000 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | delay due to the state of the covid 19 pandemic that has occurred since march 2020 | 2.16% of the project was not carried out
2059 | 5464083 | Contract for the Restoration of the Channel System for Collecting Surface Runoff Water from the Former Mining Area of ​​São Domingos: Phase 2 - Left bank | 45240000-1 | Construction work for water projects | TRUE | 2018 | 2021 | Portugal | Mértola | Beja | 2 | 21 | 27-03-2019 | 10-05-2021 | 775 | 425 | 2300000 | 2243380 | 3 | 2297431.86 | -54051.86 | 97.6473 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the project took place in compliance with the contractual stipulations, not having deviated significantly from the partial deadlines and having complied with the deadline for completion of the project of 10/24/2020, with the exception of soil decontamination work (technosols), relatively to whom an extension of 85 days was granted. | no change
2060 | 5459090 | CP No. 19/2018 - Hiring Services for Performing Magnetic Resonances Abroad | 85000000-9 | Health and social work services | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 14 | 18-07-2018 | 31-12-2019 | 531 | 150 | 208281 | 84726 | 1 | 84726 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: technical value and response times Weighting: 40% Criterion related to cost Name: Global Value per Lot Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
2061 | 5458910 | Work creation service unit internal medicine | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 18 | 31-10-2018 | 26-11-2019 | 391 | 90 | 130000 | 95166.37 | 1 | 95166.37 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: technical value Weighting: 50% Criterion related to cost Name: overall value Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2062 | 5458740 | Refurbishment of the pavement at the entrance to the cons. Management | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2018 | Portugal | Porto | Porto | 13 | 14 | 28-08-2018 | 26-10-2018 | 59 | 20 | 45000 | 44798.63 | 1 | 44798.63 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal and Execution Deadline Weighting: 40% Criterion related to cost Name: Global price of the proposal Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2063 | 5458692 | Refurbishment of the roof of the former rectory building in the former cicap | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 15 | 26-09-2018 | 05-08-2020 | 679 | 120 | 248000 | 218989.8 | 1 | 218989.8 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Execution Deadline and Technical Valuation Weighting: 40% Criterion related to cost Name: Global Proposal Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climatic reasons
2064 | 5457658 | Contract execution new layout of the pathological anatomy | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 19 | 09-01-2019 | 18-06-2019 | 160 | 90 | 48500 | 46714.98 | 1 | 46714.98 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: technical value Weighting: 50% Criterion related to cost Name: Global price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2065 | 5435753 | Children's Park and Garden on street of Cerâmica | 45112711-2 | Landscaping work for parks | FALSE | 2018 | 2020 | Portugal | Bragança | Bragança | 4 | 14 | 09-10-2018 | 10-02-2020 | 489 | 120 | 81800 | 78341.28 | 1 | 76528.76 | 1812.52 | 102.3684 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | scarcity of skilled labor to carry out specific tasks, namely installing irrigation and carrying out plantations. | underwork
2066 | 5434890 | Ocf complex parking – exterior arrangements | 45113000-2 | Siteworks | FALSE | N/A | 2020 | Portugal | N/A | N/A | N/A | N/A | 25-02-2019 | 27-10-2020 | 610 | 120 | N/A | 119395.65 | 1 | 130654.93 | -11259.28 | 91.3824 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | project analysis | complementary works
2067 | 5434728 | Partial repaving of the auction building | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Olhão | Faro | 8 | 18 | 11-03-2019 | 06-09-2019 | 179 | 100 | 220000 | 198851.16 | 1 | 211260.02 | -12408.86 | 94.1263 | Best value for money: Yes Criterion related to quality Name: Proposed Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
2068 | 5432798 | Soft Mobility Infrastructure Increment Program - Correction of discontinuities on street of Outrela - Valongo | 45233262-3 | Pedestrian zone construction work | FALSE | 2019 | 2020 | Portugal | Valongo | Porto | 13 | 15 | 28-03-2019 | 13-10-2020 | 565 | 150 | 133000 | 112825.6 | 1 | 110073.36 | 2752.24 | 102.5004 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period since the last measurement report dates from 12.23.2019. there was a delay in scheduling the inspection for the provisional reception of the project. | approval of underwork worth €4,350.73 (addendum to the contract dated 24.01.2020) approval of the provisional price revision in the amount of €1,586.47 (order of 18.06.2020) approval of the definitive price revision in the amount of €12.02 (order of 04.09.2020)
2069 | 5432456 | Contract for "Requalification of the Public Spaces of Associação 18 de Maio" | 45112700-2 | Landscaping work | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 11 | 15-03-2019 | 25-05-2020 | 437 | 120 | 98000 | 78480.1 | 1 | 78480.1 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
2070 | 5432170 | Rehabilitation and Expansion of the elementary school in Lama - Figueiró | 45214200-2 | Construction work for school buildings | FALSE | 2018 | 2021 | Portugal | Amarante | Porto | 13 | 10 | 01-04-2019 | 14-07-2021 | 835 | 365 | 847208.14 | 846500 | 2 | 863429.49 | -16929.49 | 98.0393 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the inspection for provisional acceptance purposes | positive price review
2071 | 5423469 | 5010033941 - Contract called "Linha do Norte - Replacement of Cracked Monobloc Sleepers between km 232+500 and 291+000" | 45234100-7 | Railway construction works | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 20 | 27-03-2019 | 14-10-2020 | 567 | 180 | 1200000 | 1188325 | 3 | 1174160.8 | 14164.2 | 101.2063 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (80% weighting) - FPRECIO b) Technical value (20% weighting) - FVT | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | underwork
2072 | 5416760 | Construction contract for the Pinheiro Agricultural Path | 45233123-7 | Secondary road construction work | FALSE | 2018 | 2019 | Portugal | Ribeira Brava | Região Autónoma da Madeira | 14 | 35 | 26-03-2019 | 02-09-2019 | 160 | 333 | 1469029.89 | 1050000 | 3 | 1045349.19 | 4650.81 | 100.4449 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | amendment of the contractual term of the contract from 303 days to 120 days, without inconsistencies, from a technical point of view, to the completion of the contract within this period. | the change in the term of the project did not entail extra costs.
2073 | 5416204 | Improvement and refurbishment of Residential Buildings - Municipal Housing in Água Longa | 45000000-7 | Construction work | FALSE | 2018 | 2021 | Portugal | Santo Tirso | Porto | 13 | 20 | 20-03-2019 | 26-03-2021 | 737 | 240 | 699386.6 | 228857.62 | 1 | 245145.75 | -16288.13 | 93.3557 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | during the course of the project, the need arose to carry out additional work, suspend work to study and change the project and also grant graceful extensions. | the existence of complementary work and underwork.
2074 | 5416153 | Improvement and requalification of Housing Buildings - Municipal Housing of Reguenga | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Santo Tirso | Porto | 13 | 20 | 11-03-2019 | 29-06-2020 | 476 | 240 | 699386.6 | 261980.4 | 2 | 253003.2 | 8977.2 | 103.5483 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the adverse weather conditions that were felt during the course of the project implying the development of thermal plastering work to be carried out outside. | the existence of extra work and underwork.
2075 | 5416117 | Requalification of Carlos Marnoto Street | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 22 | 26-11-2018 | 30-01-2020 | 430 | 152 | 168320.31 | 165000 | 1 | 161662.21 | 3337.79 | 102.0647 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions and unregistered networks
2076 | 5416027 | Improvement and requalification of Housing Buildings - Municipal Housing of Agrela | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Santo Tirso | Porto | 13 | 20 | 11-03-2019 | 29-06-2020 | 476 | 150 | 699386.6 | 129007.9 | 1 | 129007.9 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the adverse weather conditions that were felt between the months of october/2019 and january/2020, delaying the execution of the thermal plastering work on the exterior of the building.
2077 | 5414887 | Requalification of pedestrian accesses and surroundings in the center of Santa Marinha do Zêzere | 45454000-4 | Restructuring work | FALSE | 2018 | 2020 | Portugal | Baião | Porto | 13 | 31 | 04-01-2019 | 23-09-2020 | 628 | 210 | 442790.94 | 372400 | 2 | 361938.51 | 10461.49 | 102.8904 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work on the project from 07/01/2019 to 08/11/2019, due to parish festivities and changes to the public lighting network under the responsibility of edp; suspension of works on the projects from 15/11/2019 to 14/07/2020, due to an intervention at the site of the projects by the entity águas do norte. | underwork worth eur 10,461.49.
2078 | 5414261 | Inclusive city extensive interventions and reprofiling of streetJoão de Deus | 45233140-2 | Roadworks | FALSE | N/A | 2021 | Portugal | N/A | N/A | N/A | N/A | 25-02-2019 | 06-04-2021 | 771 | 240 | N/A | 298341.58 | 2 | 320320.7 | -21979.12 | 93.1384 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions, combined with a pandemic crisis | complementary works
2079 | 5414101 | Sanitation Emissary - Connection of EM 619 to Avª Dr. antonio cerveira roll | 45232421-9 | Sewage treatment works | FALSE | 2018 | 2019 | Portugal | Anadia | Aveiro | 1 | 15 | 07-02-2019 | 03-09-2019 | 208 | 90 | 50494.57 | 32521.65 | 1 | 32521.65 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
2080 | 5414046 | Improvement of the electricity network on the main street of Castelo Bom | 45317000-2 | Other electrical installation work | FALSE | 2018 | 2021 | Portugal | Almeida | Guarda | 9 | 18 | 12-03-2019 | 29-01-2021 | 689 | 180 | 116768.15 | 104230.97 | 1 | 89664.47 | 14566.5 | 116.2456 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal in the modality provided for in paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | for delays the responsibility of which was imputed to the contractor of the contract | underwork
2081 | 5413869 | Construction of Training Control and Evaluation Center | 45400000-1 | Building completion work | FALSE | 2018 | 2019 | Portugal | Anadia | Aveiro | 1 | 15 | 26-10-2018 | 27-09-2019 | 336 | 150 | 349851.69 | 317948.84 | 2 | 313877.43 | 4071.41 | 101.2971 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | underwork
2082 | 5413615 | Landscape Arrangement of Horta do Pádua | 45112700-2 | Landscaping work | FALSE | 2018 | 2020 | Portugal | Olhão | Faro | 8 | 15 | 22-02-2019 | 14-05-2020 | 447 | 270 | 290000 | 261465.38 | 2 | 258715.38 | 2750 | 101.0629 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period. | underwork
2083 | 5412389 | Contract for the Anticorrosive Protection of the Coura Bridge, at Pk 104.941 of the Minho Line | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2018 | 2020 | Portugal | Caminha | Viana do Castelo | 18 | 39 | 21-03-2019 | 02-11-2020 | 592 | 250 | 1600000 | 1475049.65 | 3 | 1475049.65 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica: 25% - Safety Management - 10% - Quality Control - 5% - Environmental Management - 5% Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | anticipation 64-day execution period
2084 | 5412132 | Layouts in Loulé - Access Road to the CML Land, Next to the Industrial Zone | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Loulé | Faro | 8 | 24 | 21-02-2019 | 13-07-2020 | 508 | 120 | 190000 | 149409.99 | 1 | 149409.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the awarded contractor met the deadline established for the contract. the provisional acceptance took some time to be made due to an administrative error.
2085 | 5411022 | Execution contract for the subdivision in Aldeia de Martim Longo next to the 2nd phase of the access avenue to the elementary school | 45211360-0 | Urban development construction work | FALSE | 2018 | 2021 | Portugal | Alcoutim | Faro | 8 | 30 | 18-03-2019 | 19-02-2021 | 704 | 365 | 1061760.4 | 794076.71 | 2 | 796550.01 | -2473.3 | 99.6895 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | great difficulty in acquiring different materials from suppliers, taking into account the period of confinement due to the covid-19 virus pandemic. | due to final price revision.
2086 | 5409731 | Refurbishment contract for the Conselheiro António Cândido Home | 45215212-6 | Retirement home construction work | FALSE | 2018 | 2021 | Portugal | Amarante | Porto | 13 | 15 | 22-03-2019 | 02-05-2021 | 772 | 365 | 1150000 | 1090000 | 3 | 1323882.46 | -233882.46 | 82.3336 | Best value for money: Yes Criterion related to quality Name: Guarantee of Good Execution (30%) and Technical Valuation of the Proposal (10%) Weighting: 40% Criterion related to cost Name: Global Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | pandemic caused by the disease covid-19 | pandemic caused by the disease covid-19
2087 | 5407744 | Shipyard assembly and disassembly; Demolition of existing pavements – street layout and sidewalks; Earth movement; Milling in junction areas; Execution of various infrastructures | 45233224-5 | Dual carriageway construction work | FALSE | 2018 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 15-03-2019 | 17-04-2020 | 399 | 150 | 350000 | 291773.85 | 2 | 291773.85 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of Proposal (QTP) Weighting: 50% Criterion related to cost Name: Price (CP) Weighting: 50% | 1 | 50 | 3 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two notices of partial suspension of work were duly authorized.
2088 | 5405599 | Contract for the execution of outfalls and pumping stations in Rio de Moinhos | 45232431-2 | Wastewater pumping station | FALSE | 2018 | 2021 | Portugal | Borba | Évora | 7 | 60 | 20-02-2019 | 26-05-2021 | 826 | 270 | 900000 | 716955 | 2 | 592109.54 | 124845.46 | 121.0849 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: FACTORS AND SUBFACTORS COEFFICIENT WEIGHTING A. PRICE 70% B. TECHNICAL EVALUATION 30% B.1 Work execution methodology 20% B.2 Detail and consistency of the Work Plan 10% B.2.1 Work Schedule 5% B.2.2 Means Plan 5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | three partial consignments.
2089 | 5404731 | CP 002/2019 - Contract for paving streets in Portimão | 45233200-1 | Various surface works | FALSE | 2019 | 2021 | Portugal | Portimão | Faro | 8 | 14 | 15-03-2019 | 03-09-2021 | 903 | 657 | 105000 | 100000 | 1 | 98309.84 | 1690.16 | 101.7192 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the initial term of the contract was for a period of 2 years, until december 31, 2020, having been complied with, the provisional reception was made on 01/11/2021. | the underwork is due to the fact that we have reached the end of the contract, and we still have not reached the total amount foreseen, so, in agreement with the contractor, we decided not to extend the deadline, and to finish the contract, since the contractor was having great difficulties.
2090 | 5404353 | Loures Accessible City - Execution of the Accessibility Plan - Execution of section 2 | 45233160-8 | Paths and other metalled surfaces | FALSE | 2018 | 2019 | Portugal | Loures | Lisboa | 11 | 18 | 15-11-2018 | 15-10-2019 | 334 | 163 | 319712.15 | 284515.25 | 2 | 280229.93 | 4285.32 | 101.5292 | Best value for money: Yes Criterion related to quality Name: deadline of Execution Weighting: 30% Criterion related to cost Name: Bid Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | slowdown in the pace of work due to the development of work carried out by external entities. | value resulting from correct measurements.
2091 | 5399985 | Domestic drainage of streetJosé Monteiro de Vinais, streetParticular António Pinto da Silva and streetGago Coutinho. | 45232460-4 | Sanitary works | FALSE | 2018 | 2021 | Portugal | Barreiro | Setúbal | 17 | 7 | 22-02-2019 | 19-07-2021 | 878 | 180 | 255000 | 253205.88 | 2 | 257600.04 | -4394.16 | 98.2942 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty in opening the attack well for eear due to the water table. difficulty by groundwater level in the execution of reinforced concrete works. | price review
2092 | 5398805 | Process n.º CP/E89H/DOPM - Exterior rehabilitation of the houses in the social allotment of Malhadoura, in Milhazes | 45453100-8 | Refurbishment work | FALSE | 2018 | 2021 | Portugal | Barcelos | Braga | 3 | 30 | 19-02-2019 | 20-08-2021 | 913 | 365 | 648609 | 551318 | 2 | 510640.97 | 40677.03 | 107.9659 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions, pandemic and not allowing access to some houses. | no works were carried out in all the houses initially planned.
2093 | 5398587 | Reconstruction of the Fish Market | 45453100-8 | Refurbishment work | FALSE | 2018 | 2020 | Portugal | Ourém | Santarém | 16 | 15 | 31-01-2019 | 01-07-2020 | 517 | 210 | 280549.88 | 239958.7 | 1 | 245582.7 | -5624 | 97.7099 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution deadlines | the change in the final cost of the project is the result of the price review in accordance with clause 29 of the tender specifications
2094 | 5398358 | Refurbishment of the facades of Block J of the Carreira de Tiro in Faro | 45443000-4 | Facade work | TRUE | 2018 | 2020 | Portugal | Faro | Faro | 8 | 15 | 27-02-2019 | 08-07-2020 | 497 | 90 | 136428.2 | 96200 | 1 | 103881.86 | -7681.86 | 92.6052 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Does not apply Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
2095 | 5366842 | S. Martinho Secondary and Professional School - Work under Warranty | 45453100-8 | Refurbishment work | FALSE | 2018 | 2021 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 32 | 18-03-2019 | 25-10-2021 | 952 | 240 | 410000 | 385902.18 | 2 | 389022.5 | -3120.32 | 99.1979 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | TRUE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | partial suspension notice - 15 days | underwork and ordinary price revision (art.º 382.º)
2096 | 5365980 | Qualification of the Public Space on the Right Bank of the Tâmega, between Jardim do Tabolado and the São Roque Bridge | 45112700-2 | Landscaping work | FALSE | 2018 | 2021 | Portugal | Chaves | Vila Real | 19 | 24 | 15-03-2019 | 23-08-2021 | 892 | 365 | 917967 | 848988 | 2 | 861909.57 | -12921.57 | 98.5008 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension for a period of 66 days. | complementary works worth €32,736.88 underwork worth €35,729.60 and price revisions worth €15,914.29
2097 | 5363716 | CP 34/2018_DEGA - Wastewater in Agras de Baixo (PAR 003), Oliveira do Bairro | 45232460-4 | Sanitary works | TRUE | 2018 | 2020 | Portugal | Oliveira do Bairro | Aveiro | 1 | 40 | 15-03-2019 | 11-05-2020 | 423 | 150 | 570000 | 481800 | 2 | 481299.77 | 500.23 | 100.1039 | Best value for money: Yes Criterion related to quality Name: VALIA TÉCNICA Weighting: 45% Criterion related to cost Name: PRICE Weighting: 55% | 1 | 55 | 5 | TRUE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2098 | 5349534 | 2018/120-DGEP - (Re)painting of pedestrian crossings in several streets in the municipality of Oeiras | 45233221-4 | Road-surface painting work | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 16 | 08-03-2019 | 16-07-2020 | 496 | 120 | 117600 | 87515 | 1 | 87515 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2099 | 5348242 | Rehabilitation of Joaquim de Almeida elementary school Building number 2 and Enlargement of the Canteen | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Montijo | Setúbal | 17 | 30 | 06-11-2018 | 23-09-2020 | 687 | 270 | 620000 | 611947.78 | 2 | 626188.37 | -14240.59 | 97.7258 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award criterion to be established is the of the most economically advantageous proposal, with the proposals being analyzed based on the following factors and sub-factors, in order descending importance: Factors: - Price (75%) - Technical Value of the Proposal (25%) To dedeadlineine the technical value of the proposals, the following sub-factors will be considered: - Proposed construction processes; - Phased execution; - Human resources allocated to the work; - Equipment related to the work; The proposals of the competitors will be sorted in descending order, according to the score (T), being chosen the proposal that display the highest T-score: - T is defined by the polynomial: T = 0.75 x P + 0.25 x V On what, - P is the score assigned to the price factor of the proposal; - V is the score assigned to the "technical value" factor of the proposal; - P is dedeadlineined by the following formula: P = 20 x (Pmax - Pprop) / (Pmax - Pmin); On what, - Pmax is the base price of the tender; - Pmin is equivalent to the price of 372,000.00EUR, having as reference the price considered abnormally low, set in point 16 of the procedure program; - Pprop is the price of the proposal under analysis. The constant 20 results from the considered scale (0-20). - V is dedeadlineined as follows: V = pc + fe + mh + eq On what, - pc is the score assigned to the sub-factor "proposed construction processes"; - fe is the score assigned to the sub-factor "phasing of execution"; - mh is the score assigned to the sub-factor "human resources related to the work"; - eq is the score assigned to the sub-factor "equipment assigned to the work". In the technical value, the scoring scale is also from 0 to 20. As there are 4 sub-factors, they will be scored separately from 0 to 5 and the result of the score assigned to "technical value" will be the sum of the scores of the four sub-factors. Scoring form of the sub-factors: - 0 points - no approach is made in the proposal to the corresponding sub-factor; - 1 point - the corresponding sub-factor is mentioned in the proposal; - 2 points - the corresponding sub-factor is approached in a generic way; - 3 points - the sub-factor is sufficiently addressed, but little justified; - 4 points - the corresponding sub-factor is approached in a convenient and justified way; - 5 points - the corresponding sub-factor is fully justified, enlightening and does not raise doubts. The score attributed to the "technical value of the proposals" is not altered by this calculation method, which allows a better definition of way of scoring each sub-factor. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was an extension of the deadline | there was a price revision
2100 | 5344882 | Containment of Morro Lands next to street of Forno and Avenida Emídio Navarro, in Luso | 45111230-9 | Ground-stabilisation work | FALSE | 2019 | 2021 | Portugal | Mealhada | Aveiro | 1 | N/A | 20-02-2019 | 13-01-2021 | 693 | 150 | 170000 | 135396.76 | 1 | 157135.18 | -21738.42 | 86.1658 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 0 | FALSE | N/A | N/A | N/A | N/A | FALSE | extension of the execution period for the execution of complementary works, objective modification of the contract, existence of underwork. | the change in the value of the project resulted from the existence of complementary works, objective modification of the contract and underwork.
2101 | 5343005 | “Wastewater from the Canada Zone - Aguada de Cima - Águeda” | 45232411-6 | Foul-water piping construction work | TRUE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 20 | 07-03-2019 | 16-12-2019 | 284 | 45 | 200000 | 192118.82 | 1 | 173815.14 | 18303.68 | 110.5305 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Valuation of price or cost as the sole aspect of contract performance Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2102 | 5342811 | "Works of Conservation and Resolution of Pathologies, 1st Phase- Basements, North Slope and Exterior Arrangements of the District Archive of Bragança" | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Bragança | Bragança | 4 | N/A | 18-10-2018 | 06-11-2019 | 384 | 240 | 312000 | 308500 | 2 | 308500 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 1 | FALSE | N/A | N/A | N/A | N/A | FALSE | delay in delivery of equipment | small unforeseen works, not detectable in the design phase.
2103 | 5340444 | DPES-CPúblico-4/2018-Remodeling of the drainage network on part of the western slope of the Loreto neighborhood | 45232400-6 | Sewer construction work | FALSE | 2018 | 2021 | Portugal | Coimbra | Coimbra | 6 | 21 | 10-09-2018 | 12-02-2021 | 886 | 240 | 340000 | 321012.88 | 2 | 321012.88 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | be dependent on others | there was no change
2104 | 5339924 | Contract for Execution of Entrance Door / Connection of Vale do Tua - Refurbishment of the Building (São Mamede de RibaTua School). | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2020 | Portugal | Alijó | Vila Real | 19 | 14 | 25-02-2019 | 27-04-2020 | 427 | 306 | 275852.14 | 239462.59 | 1 | 239462.59 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in the delivery of materials by suppliers
2105 | 5339512 | Construction of roundabout in Ançada: E.N. 234 - KM102+800 - Geometric Intersection Reformulation | 45233128-2 | Roundabout construction work | FALSE | 2018 | 2021 | Portugal | Mangualde | Viseu | 20 | 20 | 11-03-2019 | 12-04-2021 | 763 | 120 | 184262.67 | 169846.59 | 1 | 183728.36 | -13881.77 | 92.4444 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: non-existent Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | according to information in the process | according to information in the process
2106 | 5338079 | S.e.c. - PROCº nº 202/A1/18 - Public Tender for the award of the contract for "Improvement of the coverage of the City Council warehouses and Requalification of the Building of the municipal housingfighters" | 45113000-2 | Siteworks | FALSE | 2018 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 08-03-2019 | 04-03-2020 | 362 | 90 | 600267.47 | 227384.17 | 1 | 222594.96 | 4789.21 | 102.1515 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | weather conditions | underwork
2107 | 5337948 | S.e.c. - PROCº nº 202/A1/18 - Public Tender for the award of the contract for "Improvement of the coverage of the City Council warehouses and Requalification of the Building of the municipal housingfighters" | 45113000-2 | Siteworks | FALSE | 2018 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 08-03-2019 | 13-12-2019 | 280 | 90 | 600267.47 | 302576.52 | 2 | 273891.72 | 28684.8 | 110.473 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | weather conditions | underwork
2108 | 5337618 | Rehabilitation of Vimieiro River Beach / Landscaping Intervention at Vimieiro River Beach - Phase 1 | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Penacova | Coimbra | 6 | 21 | 22-02-2019 | 27-04-2020 | 430 | 120 | 269419.96 | 268294.26 | 2 | 268294.26 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | change of topography in the implementation of the project and adverse weather conditions.
2109 | 5335883 | Machada street domestic drainage | 45232460-4 | Sanitary works | FALSE | 2018 | 2020 | Portugal | Barreiro | Setúbal | 17 | 20 | 21-02-2019 | 17-03-2020 | 390 | 180 | 350000 | 349502.67 | 2 | 352683.86 | -3181.19 | 99.098 | Best value for money: Yes Criterion related to quality Name: Quality of the proposal Weighting: 40% Criterion related to cost Name: bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extensions were requested by the contractor due to external factors | there was underwork in the contract because it was decided during the project that it would not be necessary to carry it out
2110 | 5335386 | Infrastructure Repair in the Vagos Industrial Zone | 45232130-2 | Storm-water piping construction work | FALSE | 2018 | 2020 | Portugal | Vagos | Aveiro | 1 | 15 | 12-03-2019 | 01-09-2020 | 539 | 150 | 325000 | 324755.78 | 2 | 234958.56 | 89797.22 | 138.2183 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions necessary for the completion of the project, due to the current scenario of the covid 19 pandemic, which has logistically affected production, both in terms of supplies of external materials, as well as the lack of the desired workforce, and bad weather conditions, thus conditioning the profitability in activities in order to meet established deadlines. | underwork worth €97,920.47, compensation for reducing the total value of work
2111 | 5334768 | Total refurbishment of the interior of two apartments in Porto and in Vila Nova de Gaia, owned by the Social services of the National Guard | 45400000-1 | Building completion work | FALSE | 2019 | 2020 | Portugal | N/A | N/A | N/A | 21 | 07-03-2019 | 06-01-2020 | 305 | 100 | 70000 | 69027.91 | 1 | 69027.91 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: cost/price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
2112 | 5332014 | 2018.116.01.C1 - SFP Setúbal - Replacement of fiber cement roofing with asbestos | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Setúbal | Setúbal | 17 | 21 | 15-01-2019 | 20-12-2019 | 339 | 180 | 200000 | 168494.28 | 1 | 168494.28 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
2113 | 5331927 | Contract for the rehabilitation of 6 social housing units in the 1º de Maio neighborhood in Tomar | 45453100-8 | Refurbishment work | FALSE | 2018 | 2021 | Portugal | Tomar | Santarém | 16 | 18 | 16-01-2019 | 14-01-2021 | 729 | 365 | 229955 | 217538.26 | 1 | 215756.19 | 1782.07 | 100.826 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | increase due to measurement error and decrease due to work not performed and measurement errors
2114 | 5331322 | Qualification of Accessibility of Torreira Tourist Cluster | 45259900-6 | Plant upgrade work | FALSE | 2019 | 2021 | Portugal | Murtosa | Aveiro | 1 | 21 | 11-03-2019 | 10-03-2021 | 730 | 90 | 151163.52 | 144999 | 1 | 157375.6 | -12376.6 | 92.1356 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspensions. | complementary work and work suppression (underwork)
2115 | 5330493 | Urban Regeneration of Largo da República and Surroundings in Reguengos de Monsaraz | 45233252-0 | Surface work for streets | FALSE | 2018 | 2020 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 22-02-2019 | 16-12-2020 | 663 | 300 | 486411.15 | 445826.82 | 2 | 430302.28 | 15524.54 | 103.6078 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the deadline for carrying out work on another contract that conditioned its normal execution (45 days); extension due to normal working difficulties due to the pandemic conditions (45 days) and suspension due to works carried out by the municipality that collided and constrained the development of the project (30 days). | execution of complementary works and deletion of works (underwork).
2116 | 5330017 | Replacement of existing road pavements, reformulation/rehabilitation of electricity, telephone, rainwater, and other infrastructure networks. | 45233251-3 | Resurfacing works | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 27-02-2019 | 19-07-2021 | 873 | 270 | 725762.56 | 593835.02 | 2 | 613928.87 | -20093.85 | 96.727 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 60 days - graceful extension 45 days - deadline for execution of the 1st additional contract of 06.08.2019; 45 days - deadline for execution of the 2nd additional contract of 06.17.2020. note: the last measurement report dates from 30.06.2020. there was a delay in scheduling the inspection for the purposes of provisional acceptance of the project. | €92,796.35 - additional work - 1st and 2nd additional contracts €83,351.80 - underwork included in the 2nd additional contract €10,649.30 - price review
2117 | 5326589 | 2018/165 - DGEP - Requalification of the sidewalks in streetConde de Alcáçovas, Paço-de-Arcos | 45233142-6 | Road-repair works | FALSE | 2018 | 2021 | Portugal | Oeiras | Lisboa | 11 | 30 | 28-02-2019 | 12-07-2021 | 865 | 90 | 199346.44 | 194954.88 | 1 | 140737.05 | 54217.83 | 138.5242 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work and graceful extension | underwork
2118 | 5315862 | Cpn 47/2018/dicp - t-40//2018 - conservation and maintenance contract for municipal roads in the municipality of leiria | 45233141-9 | Road-maintenance works | FALSE | 2018 | 2020 | Portugal | Leiria | Leiria | 10 | 22 | 30-01-2019 | 17-03-2020 | 412 | 365 | 300265 | 289946 | 2 | 289946 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2119 | 5315364 | Proc. No. 21/EOP/DCOP/2018 - Paving of the Marginal Road | 45233294-6, 45100000-8, 45111100-9, 45232410-9, 45233200-1 | Installation of road signals, Site preparation work, Demolition work, Sewerage work, Various surface works | FALSE | 2018 | 2019 | Portugal | Cascais | Lisboa | 11 | 14 | 29-01-2019 | 18-11-2019 | 293 | 162 | 758761.5 | 607009.2 | 2 | 607009.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Deadline Weighting: 10% Criterion related to cost Name: Price Weighting: 90% | 1 | 90 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2120 | 5315196 | Execution of Sidewalks on the EN234 in Murtede, by Contract - CP-CCP-EMP n.º 12/2018 | 45113000-2 | Siteworks | FALSE | 2018 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 07-03-2019 | 22-09-2020 | 565 | 270 | 154785.8 | 143974.52 | 1 | 61188.9 | 82785.62 | 235.2952 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of underworks.
2121 | 5314627 | Urban Requalification of the Surroundings of the Chapel of S. Bento and Sports Complex in Ançã, by Contract - CP-CCP-EMP n.º 11/2018 | 45111290-7 | Primary works for services | FALSE | 2018 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 20 | 07-03-2019 | 30-09-2019 | 207 | 120 | 187014.8 | 175403.08 | 1 | 172215.97 | 3187.11 | 101.8506 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of work to be done | existence of additional work and underwork
2122 | 5313424 | Execution of Exterior Spaces in the Madame Faber District - Trafaria | 45112700-2 | Landscaping work | FALSE | 2018 | 2020 | Portugal | Almada | Setúbal | 17 | 30 | 26-02-2019 | 03-11-2020 | 616 | 150 | 298076.55 | 297940.74 | 2 | 297940.74 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work.
2123 | 5312056 | Garden of Casa da Música Jorge Peixinho at Quinta das Nascentes | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2021 | Portugal | Montijo | Setúbal | 17 | 30 | 02-10-2018 | 29-01-2021 | 850 | 365 | 1567244.78 | 1218606.86 | 3 | 1218606.86 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective coefficients of weighting: - Price (P) - 75% (Fp); - Technical Quality of the Proposal (Q) - 25% (Fq) (Refer to point 17 of the Program of the Procedure) | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - land with an unusual degree of dirt; - adverse weather conditions; - indefinition in the design of stability, drainage and water elements; - intervention by other companies (edp and telecommunications network); - situation of the world pandemic; - widespread delay in the supply of materials; - edp took a while to remove the pole that was in the middle of the cycle path. | there was a price review
2124 | 5307917 | Public Tender No. 24/DRL/DA/2018 - Contract to replace the roof, repair and paint the facades in the preventive medicine building - Clinical Center - Janelas Verdes, Lisbon. | 45260000-7 | Roof works and other special trade construction works | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 15 | 17-09-2018 | 20-11-2019 | 429 | 90 | 143000 | 143000 | 1 | 139985 | 3015 | 102.1538 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | meteorological conditions, delay in the delivery of materials. | consult procedure
2125 | 5307645 | Rehabilitation of street of Freixo - Budget | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2019 | Portugal | Aveiro | Aveiro | 1 | 25 | 01-02-2019 | 16-10-2019 | 257 | 90 | 144000 | 94850 | 1 | 94850 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was started after the approval of the dpss (05/27/2019) and completed on 08/26/2019
2126 | 5304015 | Refurbishment and improvement of the residential structure for the elderly (erpi) | 45320000-6 | Insulation work | FALSE | N/A | 2020 | Portugal | Moimenta da Beira | Viseu | 20 | N/A | 26-02-2019 | 26-06-2020 | 486 | 180 | N/A | 229200.01 | 1 | 226025 | 3175.01 | 101.4047 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | extension granted to the successful tenderer due to impossibility of execution due to adverse weather conditions; delays by companies supplying materials and the covid-19 pandemic | deletion of some works
2127 | 5303383 | Creation of a cycle path, 2.25m wide and in two directions, in the parish of Valongo, between Av.ª dos Lagueirões and the stop at Susão, referring to the 1st phase of the project. | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 21 | 25-02-2019 | 23-07-2021 | 879 | 90 | 175000 | 159888.4 | 1 | 237538.39 | -77649.99 | 67.3106 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of a 30-day extension; allocation of 45 days to carry out additional work - additional contract dated 07.03.2019 | approval of: - additional work: €68,472.60 + €9,216.39 - underwork – €39.00
2128 | 5302445 | Contract for "Intervention in the East Cloth of the Medieval Fence of the Walls of Lagos" | 45454100-5 | Restoration work | FALSE | 2018 | 2019 | Portugal | Lagos | Faro | 8 | 48 | 25-02-2019 | 11-11-2019 | 259 | 120 | 140000 | 79952 | 1 | 81825.7 | -1873.7 | 97.7101 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1 - b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | by order of mr. president of the chamber of 07/30/2019, the deadline for the execution of the project, was extended for another 60 days, as a grace. | the value of the project has not changed
2129 | 5302436 | Preventive Maintenance Works for the Rainha D. Leonor Housing Group phase 1 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 25 | 22-02-2019 | 30-07-2020 | 524 | 390 | 660000 | 640133.69 | 2 | 641340.67 | -1206.98 | 99.8118 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the contractually foreseen | additional work and work not performed
2130 | 5302070 | Replacement of b. Neurosurgery operator and neoclassical | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 15 | 20-09-2018 | 17-06-2020 | 636 | 90 | 42500 | 34863 | 1 | 34863 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Global Proposal Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climatic and structural causes
2131 | 5301027 | Public Tender for the execution contract for the expansion of the general water supply network - south west subsystem Vale da Ursa and Ilha da Madeira - phase 1. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 27-02-2019 | 13-11-2020 | 625 | 90 | 131937.94 | 119123.35 | 1 | 126852.99 | -7729.64 | 93.9066 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to the height of high season and parties | due to existing errors in the registration of the general water supply network in the intervention zones
2132 | 5299789 | "Requalification of Viewpoints on Municipal Road 323" | 45233142-6 | Road-repair works | FALSE | 2019 | 2020 | Portugal | Sabrosa | Vila Real | 19 | 6 | 04-02-2019 | 30-10-2020 | 634 | 270 | 802021.91 | 787209.05 | 2 | 724984.47 | 62224.58 | 108.5829 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the project started with the date of the consignment | it was verified that there was no need for some works
2133 | 5299367 | Improvement of the Rural Path between Bemposta and Águas | 45432110-8 | Floor-laying work | FALSE | 2018 | 2020 | Portugal | Penamacor | Castelo Branco | 5 | 15 | 19-12-2018 | 28-11-2020 | 710 | 75 | 257994.78 | 203881.25 | 1 | 201819.6 | 2061.65 | 101.0215 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of complementary works. | complementary work due to unforeseeable circumstances: €51,187.50; underwork: €55,313.92; price revision: €2,064.77.
2134 | 5299359 | Requalification of the public space of Cidade de Tulle Avenue - Rehabilitation of Cidade de Tulle Avenue | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Lousada | Porto | 13 | 21 | 21-02-2019 | 05-02-2020 | 349 | 150 | 212356.95 | 193329.06 | 1 | 183895.04 | 9434.02 | 105.1301 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 16 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | delay in carrying out infrastructure by external entities | underwork
2135 | 5299233 | Ditch opening and closing and infrastructure installation | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2019 | Portugal | Lousada | Porto | 13 | 9 | 21-02-2019 | 11-10-2019 | 232 | 90 | 68910 | 49915 | 1 | 49915 | 0 | 100 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion date of the project 07/15/2019
2136 | 5299009 | Refurbishment and energy efficiency works for the Library building | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2018 | 2020 | Portugal | Lousada | Porto | 13 | 3 | 21-02-2019 | 01-06-2020 | 466 | 180 | 234014.57 | 219783.67 | 1 | 232910.03 | -13126.36 | 94.3642 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | hvac project indefinitions | complementary works
2137 | 5291483 | Urban Requalification of Av. Manuel dias machado - 3rd phase | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Santo Tirso | Porto | 13 | 21 | 20-02-2019 | 16-01-2020 | 330 | 180 | 360865.64 | 283125.34 | 2 | 253024.47 | 30100.87 | 111.8964 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal, safety management systems, quality control and environmental management Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | doing more work. | the existence of extra work and underwork.
2138 | 5291108 | Subdivision Infrastructures - Lugar das Eiras de Baixo/Casal, Avenida 25 de Abril | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 24 | 22-02-2019 | 04-03-2020 | 376 | 90 | 104463 | 84754.74 | 1 | 94216.48 | -9461.74 | 89.9574 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 30 days due to complementary works 28 days delay on contractor's responsibility 149 days period between the 1st inspection and the provisional acceptance, in corrections of deficiencies | complementary and less approved works
2139 | 5287332 | Refurbishment, Expansion and Refurbishment of the Exploration Building of the Ílhavo WWTP | 45454000-4 | Restructuring work | FALSE | 2018 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 30 | 14-01-2019 | 06-02-2020 | 388 | 210 | 700000 | 692835.37 | 2 | 746391.12 | -53555.75 | 92.8247 | Best value for money: No Criterion related to quality Name: - Weighting: 0% Criterion related to cost Name: Total Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the contract physically ended within the deadline, leaving the delivery of technical elements missing, such as the technical compilation of the project, which includes final screens and maintenance and operation manuals. | replacement of the coverage of the operation building and the continuous workshop building
2140 | 5286599 | Cabeda Road / Cova de Lobos - Repaving and Water Supply | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2020 | Portugal | Alijó | Vila Real | 19 | 14 | 08-02-2019 | 11-06-2020 | 489 | 150 | 186716.3 | 186701.3 | 1 | 186701.23 | 0.07 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to covid and weather conditions that made paving impossible
2141 | 5280925 | Requalification of the Local Market of Producers | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2018 | 2020 | Portugal | Chaves | Vila Real | 19 | 18 | 21-02-2019 | 23-09-2020 | 580 | 120 | 155710 | 143794.06 | 1 | 146058.13 | -2264.07 | 98.4499 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension | underwork and price revision
2142 | 5280169 | Rehabilitation of public spaces and infrastructure in the sobreiro neighborhood - green areas for fruition and landscaping, including Sobreiro Urban Park and new road connection | 45211360-0 | Urban development construction work | FALSE | 2018 | 2021 | Portugal | Maia | Porto | 13 | 13 | 08-02-2019 | 22-06-2021 | 865 | 600 | 2305669.82 | 1844535.91 | 3 | 1788621.9 | 55914.01 | 103.1261 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | work can only start after the prior approval of the court of auditors that was granted on may 8, 2019. | the resulting value according to measurements taken on site.
2143 | 5276556 | T-05/2018 - Replacement of the Main Conduct of the Irrigation Network in the Urbanization of Santa Clara - União de Freguesias de Parceiros and Azoia | 45113000-2 | Siteworks | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 14 | 23-01-2019 | 06-06-2019 | 134 | 90 | 80228.05 | 77392.47 | 1 | 77392.47 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2144 | 5275048 | Requalification of the School Park of the Municipality - Several Schools - Escola do Calvário (1st Phase). | 45454100-5 | Restoration work | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 15 | 25-01-2019 | 06-12-2021 | 1046 | 60 | 62500 | 48661.06 | 1 | 49385.41 | -724.35 | 98.5333 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the deadline. | additional contract (additional work + underwork) final price review
2145 | 5272953 | PRC_0227/2018_AAD - Rehabilitation contract for the Salgueiral and Vale Ferreiros dams | 45247212-9 | Dam-reinforcement works | FALSE | 2018 | 2020 | Portugal | Torre de Moncorvo | Bragança | 4 | 7 | 18-02-2019 | 17-08-2020 | 546 | 180 | 437500 | 433405.58 | 2 | 434064.36 | -658.78 | 99.8482 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | suppression works
2146 | 5272393 | Repair of the Roof of the Convent of S. Agostinho and Other Works" | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2018 | 2019 | Portugal | Portalegre | Portalegre | 12 | 14 | 14-02-2019 | 22-11-2019 | 281 | 120 | 98687.5 | 83840 | 1 | 83380.49 | 459.51 | 100.5511 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | metrological conditions and delay in communicating the approval of occupation of public space | underwork and price revision
2147 | 5271804 | CP 33/2018_DEGA - Wastewater drainage network in Parcel A of ZI de Sosa - Vagos | 45232460-4 | Sanitary works | TRUE | N/A | 2019 | Portugal | Vagos | Aveiro | 1 | N/A | 07-02-2019 | 13-12-2019 | 309 | 120 | N/A | 107267.57 | 1 | 102451.8 | 4815.77 | 104.7005 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
2148 | 5271712 | Water Supply in Silva Escura (PAA 002) - Bouças - Sever do Vouga_x000D_ | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2018 | 2020 | Portugal | Sever do Vouga | Aveiro | 1 | 45 | 22-01-2019 | 10-11-2020 | 658 | 180 | 600000 | 491000 | 2 | 488419.02 | 2580.98 | 100.5284 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2149 | 5271327 | Restoration and conservation works at the bobbin lace museum, José Régio's house and the Centro de Estudos Regianos | 45212313-3 | Museum construction work | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 20 | 29-11-2018 | 30-10-2019 | 335 | 300 | 140000 | 134843.6 | 1 | 133443.6 | 1400 | 101.0491 | Best value for money: Yes Criterion related to quality Name: TECHNICAL QUALITY OF THE PROPOSAL Weighting: 50% Criterion related to cost Name: PRICE Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | there was underwork
2150 | 5269030 | Requalification contract for the Municipal Museum | 45261213-0 | Metal roof-covering work | FALSE | 2018 | 2021 | Portugal | Arouca | Aveiro | 1 | 30 | 19-02-2019 | 08-07-2021 | 870 | 120 | 136012.1 | 120203.65 | 1 | 131509.95 | -11306.3 | 91.4027 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | final report on 09.23.219 | complementary works and price revision
2151 | 5268304 | Total refurbishment of ten apartments and execution of a draining ditch in Ajuda, owned by the Social services of the National Guard | 45400000-1 | Building completion work | TRUE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 14 | 04-02-2019 | 06-01-2020 | 336 | 150 | 285000 | 282265.9 | 2 | 282265.9 | 0 | 100 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to point out
2152 | 5268157 | Contract for the Design and Construction of the Jardim do Bem Estar, an Intergenerational Sensory Park, integrated in Aldeia de Santa Isabel, located at Av. Of combatants, Albarraque, Sintra | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 15 | 28-01-2019 | 04-09-2020 | 585 | 150 | 230000 | 207722 | 1 | 207722 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no deadline extension.
2153 | 5267804 | Solar thermal system and replacement of lighting in the Municipal Sports Pavilion - Santo Tirso | 45261215-4 | Solar panel roof-covering work | FALSE | 2018 | 2020 | Portugal | Santo Tirso | Porto | 13 | 20 | 29-01-2019 | 12-11-2020 | 653 | 90 | 171850.5 | 151936.62 | 1 | 180261.01 | -28324.39 | 84.287 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal, safety, quality and environmental management system Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the need to carry out complementary works for the good finish of the project. | the existence of complementary works.
2154 | 5266938 | Public space requalification intervention in the urbanization of Mira Serra in Loulé | 45233262-3 | Pedestrian zone construction work | FALSE | 2018 | 2021 | Portugal | Loulé | Faro | 8 | 21 | 21-09-2018 | 19-09-2021 | 1094 | 365 | 400000 | 391955.65 | 2 | 400306.5 | -8350.85 | 97.9139 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contractor delay | works less at 680.14euros
2155 | 5266465 | Contract 25/GEBALIS/2018 - Bairro Quinta dos Ourives, Rehabilitation of 13 municipal dwellings - Parish of Beato - Affordable Lease Program at addresses: streetDr. Manuel Espírito Santo, Lot F | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 15-02-2019 | 13-11-2019 | 271 | 180 | 290000 | 245189 | 1 | 245189 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in the execution (beginning/completion) of works in view of processes inherent to heritage management (inhabited units / vacancies, others)
2156 | 5250969 | Largo do Terreiro de Cavalaria – Functional and Landscape Remodeling (PARU 5 – Intervention 2.5) and Requalification of Av. From allies (pamus 7) | 45233252-0 | Surface work for streets | FALSE | N/A | 2021 | Portugal | Chaves | Vila Real | 19 | N/A | 14-02-2019 | 10-12-2021 | 1030 | 240 | N/A | 774832.27 | 2 | 815511.72 | -40679.45 | 95.0118 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | three extensions of the execution period for another 531 days, 60 days of deadline associated with complementary works and partial suspension of the projects | more work worth €44,648.00, underwork worth €7,130.00 and price review worth €3,161.45
2157 | 5249395 | Expansion of the Industrial Zone of Penamacor | 45111290-7 | Primary works for services | FALSE | 2018 | 2021 | Portugal | Penamacor | Castelo Branco | 5 | 15 | 21-12-2018 | 05-08-2021 | 958 | 480 | 801274.03 | 523524.85 | 2 | 571795.83 | -48270.98 | 91.558 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed only on july 12, 2021, due to the dates relating to suspension and extension. | value changes: complementary works; work-less; pricing review.
2158 | 5247173 | Cpn 44/2018/dicp - t-33/2018 - execution of a car park in the area surrounding the caxieira school - union of parishes of santa eufémia and boa vista | 45223300-9 | Parking lot construction work | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 31-01-2019 | 20-11-2019 | 293 | 60 | 93949.5 | 81570.07 | 1 | 89977.65 | -8407.58 | 90.6559 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existing soils on the ground at the project site, not having the load capacity and resistance to support the equipment necessary for the execution of the project | over and underwork
2159 | 5246566 | Rehabilitation of streetDireita - Budget | 45233142-6 | Road-repair works | FALSE | 2018 | 2021 | Portugal | Aveiro | Aveiro | 1 | 23 | 11-02-2019 | 17-02-2021 | 737 | 180 | 470000 | 433700 | 2 | 485214.87 | -51514.87 | 89.3831 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions and bad behavior of the base of the pavement | existing pavement base deteriorated prematurely
2160 | 5244726 | Contract for the execution of paintings on the pavement in the Municipality of Albufeira | 45233221-4 | Road-surface painting work | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 15 | 12-02-2019 | 31-10-2019 | 261 | 550 | 200000 | 184158 | 1 | 184158 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
2161 | 5241262 | Requalification of the Public Space in Ferreira do Zêzere - 1st Phase | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Ferreira do Zezere | Santarém | 16 | 14 | 21-12-2018 | 23-11-2020 | 703 | 360 | 1137248.02 | 186292.25 | 1 | 256982.44 | -70690.19 | 72.4922 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | extensions granted due to complementary work | due to the existence of complementary work and price revision
2162 | 5241199 | Requalification of the Public Space in Ferreira do Zêzere - 1st Phase | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Ferreira do Zezere | Santarém | 16 | 14 | 21-12-2018 | 23-11-2020 | 703 | 360 | 1137248.02 | 318409.79 | 2 | 382753.34 | -64343.55 | 83.1893 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | granted extensions and term as well as due to complementary work | complementary works due to changes to the project resulting from: • compatibility of the public space with the pre-existing buildings and respective fence walls; • compatibility of public space with adjacent vacant buildings: • improved pedestrian mobility, in particular with regard to people with disabilities; • compatibility of pre-existing water supply infrastructure with the project in progress; • compatibility of the projected electrical infrastructures with the pre-existing ones, including the lowering of the buildings; • compatibility of the projected telecommunications infrastructures with the pre-existing ones, including the lowering of buildings; • improved storm drainage.
2163 | 5240777 | Requalification of the Public Space in Ferreira do Zêzere - 1st Phase | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Ferreira do Zezere | Santarém | 16 | 14 | 21-12-2018 | 23-11-2020 | 703 | 360 | 1137248.02 | 361546.41 | 2 | 453142 | -91595.59 | 79.7866 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The price or cost as the only aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | due to additional work and deadline extensions granted | complementary works and price revision
2164 | 5239155 | Improvement contract at the Pegões-Gare Outfall Associated with the Rainwater Tank | 45232400-6 | Sewer construction work | TRUE | 2018 | 2019 | Portugal | Montijo | Setúbal | 17 | 18 | 04-02-2019 | 20-11-2019 | 289 | 60 | 27000 | 22520.16 | 1 | 22520.16 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline deviation related to inspections for the purposes of provisional acceptance. work physically completed on 7/5/2019.
2165 | 5237665 | Contract for the Rehabilitation and Expansion of Sports Equipment and Support Buildings for the entire complex of the University Stadium of the University of Porto | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 16 | 23-11-2018 | 20-10-2020 | 697 | 300 | 2569800 | 2259921.43 | 3 | 2445060.11 | -185138.68 | 92.4281 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties in the acquisition and execution of the lawn in the market. | design errors and the need to carry out additional work.
2166 | 5234974 | Improvement and requalification of the Municipal Housing Building l- Roriz | 45259000-7 | Repair and maintenance of plant | FALSE | N/A | 2020 | Portugal | Santo Tirso | Porto | 13 | N/A | 30-01-2019 | 29-06-2020 | 516 | 180 | N/A | 245190 | 1 | 269934.2 | -24744.2 | 90.8332 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | the existence of complementary works. | the existence of complementary works.
2167 | 5232737 | Improvement of the Cantanhede Tennis and Padel Courts, by Contract - CP-CCP-EMP No. 06/2018 | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2018 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 16 | 08-02-2019 | 08-11-2019 | 273 | 60 | 155087.18 | 155033.92 | 1 | 158560.48 | -3526.56 | 97.7759 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conclusion work | existence works more and less
2168 | 5231644 | Intervention contract at Vitorino Nemésio High school | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 39 | 14-12-2018 | 12-07-2019 | 210 | 90 | 493450 | 180011.6 | 1 | 180011.6 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | too harsh winter/unavailability of some work fronts due to teaching activities.
2169 | 5231618 | Intervention contract at Jerónimo Emiliano de Andrade High school | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 39 | 14-12-2018 | 14-10-2019 | 304 | 120 | 493450 | 294900 | 2 | 289840.98 | 5059.02 | 101.7454 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | free term extensions | underwork and correct measurements
2170 | 5227918 | Contract nº 34/18 - Estrada da Brandoa/Feira da Brandoa - Work Execution | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 04-02-2019 | 17-10-2019 | 255 | 175 | 356954.93 | 354810.11 | 2 | 354810.11 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delay in the deadline (12 days) of the contract resulted from the waiting time of the "plan for the prevention and management of construction and demolition waste" for the preparation of the provisional acceptance notice of the project.
2171 | 5227764 | Construction of support walls in granite masonry | 45262512-3 | Dressed stonework | FALSE | N/A | 2020 | Portugal | Lousada | Porto | 13 | N/A | 29-01-2019 | 23-01-2020 | 359 | 90 | N/A | 67440 | 1 | 67080 | 360 | 100.5367 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions. | underwork worth €360.00.
2172 | 5222929 | Construction of the Oficinas Gerais car park - Union of the parishes of Esmeriz and Cabeçudos | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 16-11-2018 | 29-04-2019 | 164 | 180 | 79795 | 65200 | 1 | 65200 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed ahead of schedule.
2173 | 5219052 | Public tender for the contract for the rehabilitation of a building for the installation of the Social Center of Covilhã | 45211350-7 | Multi-functional buildings construction work | FALSE | 2018 | 2020 | Portugal | Covilhã | Castelo Branco | 5 | 30 | 28-01-2019 | 24-07-2020 | 543 | 300 | 739860 | 732750.2 | 2 | 804938.83 | -72188.63 | 91.0318 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal / Period of execution Weighting: 35% Criterion related to cost Name: Proposed price Weighting: 65% | 1 | 65 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works.
2174 | 5217346 | Execution of Cyclable School Routes - Phase C | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Almada | Setúbal | 17 | 30 | 07-01-2019 | 06-03-2020 | 424 | 180 | 369988.5 | 366794.74 | 2 | 289127.45 | 77667.29 | 126.8626 | Best value for money: Yes Criterion related to quality Name: technical value of the Proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out work | underwork
2175 | 5204270 | Refurbishment of spaces in Jardim da República, including water, sewage, telecommunications and electricity infrastructure, and building for a cafeteria. | 45233160-8 | Paths and other metalled surfaces | FALSE | N/A | 2021 | Portugal | Silves | Faro | 8 | N/A | 30-10-2018 | 29-11-2021 | 1126 | 420 | N/A | 1729766.87 | 3 | 1851256.95 | -121490.08 | 93.4374 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | complementary works. works less. price review
2176 | 5202302 | Installation of Floating Equipment in the Nascent Sector of the Port of Povoação | 45241100-9 | Quay construction work | FALSE | 2018 | 2019 | Portugal | Povoação | Região Autónoma dos Açores | 15 | N/A | 28-12-2018 | 02-09-2019 | 248 | 122 | 250000 | 245010 | 1 | 245010 | 0 | 100 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 0 | FALSE | N/A | N/A | N/A | N/A | FALSE | compatibility and adaptation of the projects in order to allow the installation of electricity and water networks to supply the vessels
2177 | 5200028 | Restructuring of hangar 5 for the installation of a flight simulator at Cascais municipal aerodrome | 45210000-2 | Building construction work | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 15 | 29-01-2019 | 10-05-2019 | 101 | 100 | 750000 | 595156.24 | 2 | 595156.24 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Execution Time (30%) and Technical Quality (40%) Weighting: 70% Criterion related to cost Name: Price Weighting: 30% | 1 | 30 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline met
2178 | 5197175 | EMP-R/9/2017 - Fiber cement removal contract for Projects I, II, IV-A and IV-B in the Nazaré neighborhood | 45261213-0 | Metal roof-covering work | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 25 | 09-01-2018 | 27-05-2019 | 503 | 210 | 690000 | 414000.01 | 2 | 414000.01 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project were carried out within the deadline
2179 | 5196754 | Intervention in the Surroundings of the Old CP Station and Praça da Republica - Phase A - Praça da República | 45112712-9 | Landscaping work for gardens | FALSE | N/A | 2021 | Portugal | Monção | Viana do Castelo | 18 | N/A | 04-01-2019 | 15-10-2021 | 1015 | 365 | N/A | 699970.5 | 2 | 778952.8 | -78982.3 | 89.8605 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | changes due to lack of definitions in the electrical and telecommunications project. | need to carry out additional work
2180 | 5193452 | 2018/167 - DGEP - Rehabilitation of the Fuel Pier at Porto Recreio de Oeiras | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 18-01-2019 | 06-03-2020 | 413 | 90 | 67500 | 66150 | 1 | 79317.76 | -13167.76 | 83.3987 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | additional work worth €11,700.00
2181 | 5193023 | Improvement of Autonomous Systems for Water Quality Assurance - Ortiga System (Mação Municipality) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2021 | Portugal | Mação | Santarém | 16 | 48 | 24-01-2019 | 29-12-2021 | 1070 | 210 | 670000 | 636864.64 | 2 | 625412.7 | 11451.94 | 101.8311 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% and Technical value - 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the 61-day period to study an alternative solution to guarantee the normal supply of water to the population through a temporary reservoir and new connections, which was not properly defined in the project. | change in value caused by underwork and the price review carried out.
2182 | 5192245 | Public Tender for the Rehabilitation and Improvement of the Velas Health Center Building | 45215100-8 | Construction work for buildings relating to health | FALSE | 2018 | 2021 | Portugal | N/A | Região Autónoma dos Açores | 15 | 30 | 22-01-2019 | 24-02-2021 | 764 | 548 | 1400000 | 1320000 | 3 | 108502.41 | 1211497.59 | 1216.5628 | Best value for money: Yes Criterion related to quality Name: Global Price Weighting: 40% Criterion related to cost Name: Technical Quality of the Proposal Weighting: 60% | 1 | 40 | 2 | TRUE | Non-fulfilment of the contract (Revocation of the Contract) | 5 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | unforeseen events associated with a phased intervention in a health facility that remained in operation. | unforeseen events associated with a phased intervention in a health facility that remained in operation.
2183 | 5189945 | Contract for repairing ruptures in pipes and branches of the water supply network in the municipality of Albufeira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 15 | 22-01-2019 | 20-05-2020 | 484 | 180 | 116037.74 | 115842 | 1 | 115842 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2184 | 5189407 | Rehabilitation / Improvement Buildings for Social Action: street of Igreja in Ançã - CP-CCP-EMP n.º 09/2018 | 45211300-2 | Houses construction work | FALSE | 2018 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 15 | 28-01-2019 | 30-12-2021 | 1067 | 180 | 53000 | 51698.09 | 1 | 51254.18 | 443.91 | 100.8661 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works. | existence of additional work and underwork.
2185 | 5184097 | Ciclopset - reprofiling of the av. Manuel Maria Portela and the Ciprestes Road between Av. October 5th and the boundary of the county" _x000D_ | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2020 | Portugal | Setúbal | Setúbal | 17 | 30 | 26-11-2018 | 23-11-2020 | 728 | 300 | 475722.47 | 389718.17 | 2 | 440963.77 | -51245.6 | 88.3787 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: evaluation of price or cost as the sole aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | study carried out by cms with a view to optimizing circulation on the road axis. | unforeseen work and work in unforeseen circumstances
2186 | 5183533 | Contract for leveling covers and raising sanitation tanks | 45259000-7 | Repair and maintenance of plant | FALSE | 2018 | 2020 | Portugal | Benavente | Santarém | 16 | 14 | 26-07-2018 | 21-09-2020 | 788 | 730 | 240000 | 240000 | 1 | 207151.81 | 32848.19 | 115.8571 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | there were no changes to the project deadline. | it was not necessary to invoice all the quantities of the articles.
2187 | 5182912 | Quality 100% - Public tender for paving sidewalks | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 15 | 21-01-2019 | 22-08-2019 | 213 | 45 | 415820 | 166268 | 1 | 166268 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
2188 | 5182835 | Quality 100% - Public tender for paving sidewalks | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 15 | 17-01-2019 | 19-07-2019 | 183 | 45 | 415820 | 166328.01 | 1 | 166328.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no change | no change
2189 | 5182831 | Canal de S. Roque - Requalification of the Continuous Zone to the Bridge of São João | 45112700-2 | Landscaping work | FALSE | 2018 | 2021 | Portugal | Aveiro | Aveiro | 1 | 25 | 15-01-2019 | 21-12-2021 | 1071 | 60 | 57287.31 | 46492.99 | 1 | 46492.99 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extensions and suspension
2190 | 5182244 | E201811 - Rehabilitation of Vouzela High school | 45214200-2 | Construction work for school buildings | FALSE | 2018 | 2021 | Portugal | Vouzela | Viseu | 20 | 14 | 17-01-2019 | 10-12-2021 | 1058 | 570 | 1273616.46 | 1137787.93 | 3 | 1111803.72 | 25984.21 | 102.3371 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the change was due to a partial suspension of the execution period. | the value of the project was changed due to underwork.
2191 | 5181072 | 5010035380 - Contract for "Renovation of the Track Superstructure between km 147.165/148.404 of the VA and RV of the North Line | 45234100-7 | Railway construction works | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 21 | 23-01-2019 | 25-03-2020 | 427 | 120 | 935000 | 798172.4 | 2 | 771982.29 | 26190.11 | 103.3926 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (65% weighting) - FPRECIO b) Technical value (20% weighting) - FVT c) Safety Management System (10% weighting) - FSGS d) Environmental Monitoring System (5% weighting) - FSGA | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | nothing to register
2192 | 5177689 | Current Conservation Contract - Covering of Graves - 1st Action | 45432110-8 | Floor-laying work | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 18 | 08-01-2019 | 07-11-2019 | 303 | 365 | 188000 | 139996.25 | 1 | 139555.45 | 440.8 | 100.3159 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | work anticipation | underwork
2193 | 5173547 | Requalification of the elementary school of Lousada Centro - 1st Phase | 45453100-8 | Refurbishment work | FALSE | 2018 | 2021 | Portugal | Lousada | Porto | 13 | 7 | 14-01-2019 | 26-04-2021 | 833 | 450 | 1200852.1 | 1087379.03 | 3 | 1133383.08 | -46004.05 | 95.941 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | constraints due to the pandemic caused by covid-19 | additional work / underwork
2194 | 5173280 | Urban regeneration of the public space surrounding street of Picoto - 1st Phase | 45233120-6 | Road construction works | FALSE | 2018 | 2020 | Portugal | Lousada | Porto | 13 | 21 | 17-01-2019 | 20-07-2020 | 550 | 360 | 523840.27 | 466775.19 | 2 | 446305.35 | 20469.84 | 104.5865 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | delays in releasing a building to be demolished; adverse weather conditions | underwork.
2195 | 5172965 | Requalification of the public space of Av. From Sanctuary and Av. From Alto do Fogo | 45233140-2 | Roadworks | FALSE | 2018 | 2020 | Portugal | Lousada | Porto | 13 | 21 | 17-01-2019 | 19-06-2020 | 519 | 270 | 569917.36 | 519794.1 | 2 | 415039.79 | 104754.31 | 125.2396 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | changes to the project. | underwork
2196 | 5165813 | Requalification of street5 de Outubro - Sabugal | 45432110-8 | Floor-laying work | FALSE | 2018 | 2020 | Portugal | Sabugal | Guarda | 9 | 10 | 16-01-2019 | 04-05-2020 | 474 | 180 | 300460.05 | 270250 | 2 | 273438.52 | -3188.52 | 98.8339 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in delivery of construction materials. | ordinary price review.
2197 | 5165096 | Contract for the Rehabilitation of Water Supply Infrastructures and Requalification of Road Infrastructures at streetArade, Mira and Álamo, in Quinta do Lago | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2019 | Portugal | Loulé | Faro | 8 | 24 | 18-09-2018 | 19-07-2019 | 304 | 90 | 300000 | 258980.24 | 2 | 258980.24 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of the deadline for 30 days
2198 | 5162674 | Urban Requalification of the surroundings of the São Caetano Pavilion, by Contract - CP-CCP-EMP n.º 08/2018 | 45113000-2 | Siteworks | FALSE | 2018 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 18-01-2019 | 08-04-2020 | 446 | 120 | 50548.19 | 42751.71 | 1 | 43386.04 | -634.33 | 98.5379 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | during the course of the project, some unforeseen events arose and adverse weather conditions also delayed the project. | existence of complementary work and underwork
2199 | 5162424 | Execution of Sidewalks on the EN234 in Ourentã, by Contract - CP-CCP-EMP n.º 04/2018 | 45113000-2 | Siteworks | FALSE | 2018 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 18-01-2019 | 27-01-2020 | 374 | 180 | 93300 | 79454.7 | 1 | 78613.31 | 841.39 | 101.0703 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of over and underwork
2200 | 5162224 | Floating platform to support artisanal fishing at the Fishing Port of Peniche | 45241500-3 | Wharf construction work | FALSE | 2018 | 2019 | Portugal | Peniche | Leiria | 10 | 14 | 17-09-2018 | 12-02-2019 | 148 | 95 | 57300 | 57270 | 1 | 57270 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2201 | 5161657 | Floating platform to support artisanal fishing at the Fishing Port of Vila Praia de Âncora | 45241500-3 | Wharf construction work | FALSE | 2018 | 2019 | Portugal | Caminha | Viana do Castelo | 18 | 14 | 11-12-2018 | 01-07-2019 | 202 | 180 | 145000 | 128270 | 1 | 128270 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: QTP Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes to the execution period | there were no changes to the contract value
2202 | 5160999 | Requalification of the Castle Stop | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Elvas | Portalegre | 12 | 15 | 18-12-2018 | 28-08-2019 | 253 | 120 | 263000 | 184100.01 | 1 | 183486.52 | 613.49 | 100.3344 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need to lower medium voltage cables by edp | no need to perform planting work
2203 | 5156880 | Renovation of Water Supply Networks - Phase 2 - Ílhavo | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2018 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 20 | 28-12-2018 | 18-11-2020 | 691 | 365 | 249000 | 199002.78 | 1 | 199002.78 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2204 | 5156745 | Implementation of Energy Efficiency Measures in the Sabugal Swimming Pools and Gym Building | 45310000-3 | Electrical installation work | FALSE | 2018 | 2019 | Portugal | Sabugal | Guarda | 9 | 14 | 04-01-2019 | 05-04-2019 | 91 | 59 | 232176.19 | 60875.67 | 1 | 60875.67 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Most Economically Advantageous Proposal: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Economically most advantageous proposal: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there was no change in the execution period | there was no change to the awarded value.
2205 | 5156736 | Renewal of Water Supply Networks - Phase 2 - Águeda | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2018 | 2020 | Portugal | Águeda | Aveiro | 1 | 20 | 28-12-2018 | 20-11-2020 | 693 | 365 | 249000 | 199091.2 | 1 | 199091.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2206 | 5156709 | Implementation of Energy Efficiency Measures in the Sabugal Swimming Pools and Gym Building | 45310000-3 | Electrical installation work | FALSE | 2018 | 2019 | Portugal | Sabugal | Guarda | 9 | 14 | 14-01-2019 | 04-06-2019 | 141 | 59 | 232176.19 | 84427.4 | 1 | 92526.9 | -8099.5 | 91.2463 | Best value for money: Yes Criterion related to quality Name: Most Economically Advantageous Proposal: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Economically most advantageous proposal: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there was no change to the deadline for carrying out the project. | there were additional and underwork.
2207 | 5156653 | Implementation of Energy Efficiency Measures in the Sabugal Swimming Pools and Gym Building | 45310000-3 | Electrical installation work | FALSE | 2018 | 2019 | Portugal | Sabugal | Guarda | 9 | 14 | 04-01-2019 | 01-07-2019 | 178 | 60 | 232176.19 | 62997.19 | 1 | 64207.69 | -1210.5 | 98.1147 | Best value for money: Yes Criterion related to quality Name: Most Economically Advantageous Proposal: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Economically most advantageous proposal: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | complementary work and atmospheric conditions. | additional and underwork.
2208 | 5154720 | Contract for the execution of the second Cascais ring road - Connection of Avenida Adelino Amaro da Costa/streetde Santana | 45112000-5, 45316110-9, 45233294-6, 45232410-9, 45100000-8, 45233200-1 | Excavating and earthmoving work, Installation of road lighting equipment, Installation of road signals, Sewerage work, Site preparation work, Various surface works | FALSE | 2017 | 2020 | Portugal | Cascais | Lisboa | 11 | 30 | 13-11-2018 | 23-03-2020 | 496 | 162 | 889188.8 | 711351.04 | 2 | 711351.04 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change to the project
2209 | 5148076 | The work consists of carrying out all the work necessary to qualify the development's buildings, through the improvement of the thermal behavior characteristics of the insulation of the facades | 45321000-3 | Thermal insulation work | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 21 | 09-01-2019 | 17-01-2020 | 373 | 150 | 277000 | 268324.94 | 2 | 277426.97 | -9102.03 | 96.7191 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the project execution period of 17 days (addendum to the contract entered into on 05.30.2019) a 21-day execution period was assigned to complementary work | approval of: - complementary works - 05.10.2019 - underwork – 08.08.2019. - calculation of the provisional price revision - 11.22.2019 - 2nd price revision calculation (definitive) - approved on 14.05.2020 ↔ credit in favor of the city council in the amount of €112.84 + vat
2210 | 5147961 | Reformulation of the urró wastewater treatment system. | 45259100-8 | Wastewater-plant repair and maintenance work | FALSE | N/A | 2020 | Portugal | Mogadouro | Bragança | 4 | N/A | 09-11-2018 | 19-02-2020 | 467 | 150 | N/A | 388539.04 | 2 | 419582.12 | -31043.08 | 92.6014 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complementary work resulting from unforeseen circumstances | execution of complementary work resulting from unforeseen circumstances
2211 | 5147438 | Construction / Improvement / Repair of School Buildings (JI / elementary school / CE), by Contract: Execution of a tensioned canvas cover to close the slab in the playgrounds of the School Centers of Ançã | 45113000-2 | Siteworks | FALSE | 2018 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 16 | 15-01-2019 | 23-09-2019 | 251 | 30 | 42321.67 | 36784.5 | 1 | 40384.5 | -3600 | 91.0857 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of normal work and complementary work | existence of complementary work
2212 | 5144864 | Construction of a Rainwater Drainage Collector in Figueira dos Cavaleiros | 45232410-9 | Sewerage work | FALSE | 2018 | 2019 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 04-12-2018 | 29-07-2019 | 237 | 100 | 145000 | 139780.65 | 1 | 90243.69 | 49536.96 | 154.8924 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to study changes to the project, given the projecting conditions in situ. | there was underwork due to design measurement errors.
2213 | 5139382 | Improvement of Estrada de S. Filipe, in the Parish of Beduído e Veiros, in the Municipality of Estarreja | 45233142-6 | Road-repair works | FALSE | 2018 | 2021 | Portugal | Estarreja | Aveiro | 1 | 27 | 27-12-2018 | 06-08-2021 | 953 | 240 | 339806 | 309751.35 | 2 | 304708.35 | 5043 | 101.655 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
2214 | 5136782 | Enhancement and recovery of the Elementary School in Montalvão - Montalvão Vintage | 45262700-8 | Building alteration work | FALSE | 2018 | 2020 | Portugal | Nisa | Portalegre | 12 | 30 | 21-12-2018 | 18-08-2020 | 606 | 180 | 324725.6 | 275234.87 | 2 | 280105.71 | -4870.84 | 98.2611 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension of the project in 90 days. | pricing revisions.
2215 | 5136232 | Warehouse Rehabilitation Contract - Blocks D and E of the Sines Fishing Port | 45442110-1 | Painting work of buildings | FALSE | N/A | 2019 | Portugal | Sines | Setúbal | 17 | N/A | 05-12-2018 | 05-03-2019 | 90 | 60 | N/A | 32169.88 | 1 | 32169.88 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution date - 60 days from the consignment date - january 7, 2019
2216 | 5135908 | Arrangement of sidewalks and interior of the block - street Travessa Gaspar Manuel / street and cross street João Ribeiro Gaio | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Vila do Conde | Porto | 13 | 20 | 05-11-2018 | 14-05-2020 | 556 | 274 | 430000 | 324809.34 | 2 | 329905.54 | -5096.2 | 98.4553 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2217 | 5134792 | CPN 30/2018/DICP - T-30/2018- Contract for carrying out post-fire emergency interventions, Parish of Coimbrão and Union of Parishes of Monte Real and Carvide | 45111220-6 | Scrub-removal work | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 21 | 12-12-2018 | 30-05-2019 | 169 | 180 | 75570 | 75470 | 1 | 75470 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: 0 Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2218 | 5133889 | Construction contract for the building - auction of the fishing port of Castelo do Neiva | 45243000-2 | Coastal-defence works | FALSE | 2018 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 27-12-2018 | 08-07-2021 | 924 | 180 | 489000 | 470975 | 2 | 505849.59 | -34874.59 | 93.1057 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 70% Criterion related to cost Name: Price Weighting: 30% | 1 | 30 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | carrying out additional work claimed under art. 378.º "public procurement code", requests for extension by the contractor, suspension of work, weather conditions, shortage of labour, additional work due to unforeseen circumstances. | carrying out additional work claimed under art. 378.º "public procurement code", complementary work due to unforeseen circumstances.
2219 | 5130766 | Proc. T-28/2018 - Requalification of Avenida da Recuperação - Union of Parishes of Colmeias and Memória - Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 21 | 03-12-2018 | 21-06-2019 | 200 | 120 | 113750 | 103995.02 | 1 | 103995.02 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension
2220 | 5130187 | Hammock and Parking Hanger | 45223300-9 | Parking lot construction work | FALSE | 2018 | 2019 | Portugal | Sesimbra | Setúbal | 17 | 15 | 12-11-2018 | 11-04-2019 | 150 | 90 | 140000 | 112000 | 1 | 112875 | -875 | 99.2248 | Best value for money: Yes Criterion related to quality Name: Technical Quality Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unspecified contingencies | unspecified contingencies
2221 | 5108914 | It consists of rehabilitating one of the centers in Venda Nova, in terms of painting the facades of buildings, cleaning sidewalks, recovering the garden in the square, urban furniture and raising crosswalks | 45453100-8 | Refurbishment work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 14 | 18-12-2018 | 17-03-2020 | 455 | 270 | 379382.05 | 328340.45 | 2 | 328340.45 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | abnormal and unpredictable change in circumstances (art. 312.º, paragraph a) of the "public procurement code" | corresponding to article 3.2 (€15,625.00) and chapter 6.2 (€13,610.56), which represents 8.9% of the contractual price.
2222 | 5108560 | Requalification and modernization of the premises of the elementary and High school of Miranda do Douro | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2021 | Portugal | Miranda do Douro | Bragança | 4 | 18 | 28-12-2018 | 31-05-2021 | 885 | 365 | 1006289.67 | 924759.57 | 2 | 924759.57 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reasons caused by the covid 19 pandemic | price review in the worth of €24,645.31
2223 | 5106638 | Faro Dock maintenance dredging | 45245000-6 | Dredging and pumping works for water treatment plant installations | FALSE | N/A | 2019 | Portugal | Faro | Faro | 8 | N/A | 12-12-2018 | 26-07-2019 | 226 | 70 | N/A | 335700 | 2 | 384805.22 | -49105.22 | 87.2389 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complementary works (art. 370 of the "public procurement code") | complementary works (art. 370 of the "public procurement code")
2224 | 5106043 | Arrangements for sidewalks and street layout - street Vasco da Gama/ street Emífio Guerra | 45233100-0 | Construction work for highways, roads | FALSE | 2018 | 2020 | Portugal | N/A | N/A | N/A | 15 | 26-10-2018 | 09-03-2020 | 500 | 243 | 280000 | 273973 | 2 | 225135.66 | 48837.34 | 121.6924 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2225 | 5102326 | Contract for "Requalification of the Public Space (street Filarmónica 1.º de Maio/street Cooperativa Chesgal)" | 45112711-2 | Landscaping work for parks | FALSE | 2018 | 2020 | Portugal | Lagos | Faro | 8 | 30 | 21-12-2018 | 23-01-2020 | 398 | 180 | 243000 | 242664.63 | 1 | 253679.92 | -11015.29 | 95.6578 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1 - b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for execution of the project was extended for another 120 days, as a grace, due to the execution of complementary works, the lack of qualified labor available in the market for civil construction works and non-compliance with the delivery dates of material specific | complementary works in the amount of €12,253.23, plus vat approved, underwork accepted in the amount of €3,306.03, plus vat and calculated as provisional value of the price revision €2,068.09, plus vat
2226 | 5102031 | Requalification of street António Feliciano Castilho and Adjacent - Anadia | 45233141-9 | Road-maintenance works | FALSE | 2018 | 2020 | Portugal | Anadia | Aveiro | 1 | 15 | 24-09-2018 | 02-04-2020 | 556 | 122 | 175094.71 | 174732.4 | 1 | 174732.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2227 | 5100251 | Improvement of Several Rural Paths in the Municipality of Anadia | 45111230-9 | Ground-stabilisation work | FALSE | 2018 | 2018 | Portugal | Anadia | Aveiro | 1 | 15 | 02-08-2018 | 15-11-2018 | 105 | 91 | 109516.8 | 65710.1 | 1 | 64110.1 | 1600 | 102.4957 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | underwork since there was no need to apply shackles on the ground
2228 | 5099785 | Contract for the Requalification and Enhancement of Pateira de Fermentelos - Creation of Pedestrian and Cycling Routes in the Municipalities of Aveiro and Oliveira do Bairro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | N/A | 2020 | Portugal | Aveiro | Aveiro | 1 | N/A | 31-12-2018 | 10-08-2020 | 588 | 150 | N/A | 433693.82 | 2 | 53577.42 | 380116.4 | 809.4713 | Contract without details about the ad | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Revocation of the Contract) | 3 | N/A | N/A | N/A | N/A | N/A | N/A | two deadline extensions were approved | underwork
2229 | 5099382 | Contract for cleaning and clearing water lines in the municipality of Albufeira | 45111240-2 | Ground-drainage work | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 15 | 19-12-2018 | 02-06-2020 | 531 | 365 | 319267.16 | 241317.22 | 1 | 241317.22 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2230 | 5098648 | Refurbishment of the Lota Building in Costa da Caparica | 45262700-8 | Building alteration work | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 21 | 05-11-2018 | 02-11-2019 | 362 | 183 | 275000 | 273500 | 2 | 295170.65 | -21670.65 | 92.6583 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
2231 | 5095986 | Reinforcement of the Water Supply to Vagos - Circular Adductor | 45232151-5 | Water-main refurbishment construction work | TRUE | 2018 | 2019 | Portugal | Vagos | Aveiro | 1 | 20 | 26-12-2018 | 25-10-2019 | 303 | 201 | 249000 | 209621.57 | 1 | 200249.85 | 9371.72 | 104.68 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2232 | 5095538 | Rehabilitation of Mrs. From Monte, Salreu, Estreja_x000D_ | 45247270-3 | Reservoir construction works | TRUE | 2018 | 2021 | Portugal | Estarreja | Aveiro | 1 | 41 | 02-01-2019 | 14-10-2021 | 1016 | 60 | 100000 | 82141.28 | 1 | 78500.88 | 3640.4 | 104.6374 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2233 | 5094523 | 2018/109 - DGEP - Conservation/Execution of pedestrian and road pavements in the Municipality | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Oeiras | Lisboa | 11 | 12 | 13-12-2018 | 16-03-2021 | 824 | 365 | 163758.4 | 123358.25 | 1 | 123685.03 | -326.78 | 99.7358 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2234 | 5091939 | Supply and installation of charging stations for electric vehicle power systems | 45453100-8 | Refurbishment work | FALSE | 2018 | 2018 | Portugal | N/A | N/A | N/A | 9 | 14-09-2018 | 10-12-2018 | 87 | 20 | 68250 | 18405.45 | 1 | 18405.45 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
2235 | 5091593 | 2018/119 - DGEP - Exterior repairs in Nova Oeiras - Parking at Torre H | 45231300-8, 45316100-6, 45111000-8, 45112700-2, 45233200-1 | Construction work for water and sewage pipelines, Installation of outdoor illumination equipment, Demolition, site preparation and clearance work, Landscaping work, Various surface works | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 14-12-2018 | 14-02-2020 | 427 | 120 | 270773.45 | 199959.87 | 1 | 199959.87 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2236 | 5090334 | Exterior Painting of the School EB 2,3 Dr. António da Costa Contreiras Armação de Pêra. | 45442110-1 | Painting work of buildings | FALSE | 2018 | 2020 | Portugal | Silves | Faro | 8 | 30 | 10-12-2018 | 17-11-2020 | 708 | 60 | 79514.5 | 77200 | 1 | 79644.87 | -2444.87 | 96.9303 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no references | price review
2237 | 5090215 | Installation of the natural gas network and replacement of boilers in the Viseu District Center building | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Viseu | Viseu | 20 | 6 | 15-10-2018 | 30-12-2018 | 76 | 60 | 100480 | 89843.56 | 1 | 89843.56 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
2238 | 5087623 | Modernization of the s.c. from beautiful village | 45453100-8 | Refurbishment work | FALSE | 2018 | 2020 | Portugal | Almeida | Guarda | 9 | 21 | 19-12-2018 | 17-12-2020 | 729 | 300 | 225540 | 203777.36 | 1 | 236529.29 | -32751.93 | 86.1531 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underwork, complementary work
2239 | 5086907 | 100% QUALITY– S. Mamede Urban Park - Activity Fields | 45260000-7 | Roof works and other special trade construction works | FALSE | N/A | 2019 | Portugal | N/A | N/A | N/A | N/A | 21-12-2018 | 22-08-2019 | 244 | 30 | N/A | 26193 | 1 | 26193 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
2240 | 5085902 | Rehabilitation of the Health Extension of Campo de Besteiros | 45262800-9 | Building extension work | FALSE | 2018 | 2021 | Portugal | Tondela | Viseu | 20 | 15 | 14-12-2018 | 05-11-2021 | 1057 | 365 | 201971.26 | 169514.97 | 1 | 228707.56 | -59192.59 | 74.1187 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as a single aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project underwent changes in the execution period due to the suspensions. | the project underwent alterations due to complementary works and the calculation of the price revision.
2241 | 5084937 | Rehabilitation of the Public Space of Bairro da Coxa | 45211360-0 | Urban development construction work | FALSE | 2018 | 2020 | Portugal | Bragança | Bragança | 4 | 30 | 08-10-2018 | 20-07-2020 | 651 | 270 | 175000 | 171831.13 | 1 | 171831.13 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | changes to the planned execution project.
2242 | 5073569 | The object of this contract is to carry out the work defined, as to its type, quantity and technical conditions of execution, in the project and in the specifications | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 8 | 21-12-2018 | 22-05-2020 | 518 | 120 | 294202.7 | 249000 | 1 | 249000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - the project was located in a connection zone with houses of illegal origin and it was necessary to change the medium and low voltage networks in these houses; - multiplicity of interactions with the affected services; -delay by the contractor in delivering the "plan for the prevention and management of construction and demolition waste".
2243 | 5071514 | Public works contract for the exterior requalification and/or individualization of functional areas in the premises of Pombal/AREPAL, Barbadinhos and Mãe de Água in Amoreiras | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Lisboa | Lisboa | 11 | 60 | 24-10-2018 | 29-04-2020 | 553 | 150 | 225000 | 224863.04 | 1 | 224863.05 | -0.01 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | in the first inspection carried out, it was verified the existence of some anomalies, not significant, and the lack of execution of the electrical connections. in this way, the inspection for the purposes of provisional acceptance of the project only took place after verifying that there was no anomaly in the project, as well as the correct execution of the plan for the prevention and management of construction and demolition waste.
2244 | 5067534 | 2017.158.07.C1 - SFP Évora - Intervention in the Social Block air conditioning system | 45000000-7 | Construction work | TRUE | 2018 | 2018 | Portugal | Évora | Évora | 7 | 15 | 04-07-2018 | 15-10-2018 | 103 | 60 | 70000 | 45975 | 1 | 45975 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Tecnica of the proposal Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed before deadline
2245 | 5067516 | Refurbishment of the facades of blocks A, C1, C2, D1 and D2 of the 96 Housing Developments in Faro | 45443000-4 | Facade work | TRUE | 2018 | 2020 | Portugal | Faro | Faro | 8 | 15 | 28-11-2018 | 10-07-2020 | 590 | 90 | 148113.2 | 113600.96 | 1 | 122565.47 | -8964.51 | 92.6859 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2246 | 5067452 | This contract consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution, in the project and in the specifications | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 18-12-2018 | 10-03-2020 | 448 | 90 | 207232.56 | 184800 | 1 | 184800 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the causes are due to the nature of the contract itself – uncertainty in the parameters listed below. to know: - diversity/deployment of required work; it should be remembered the variability in the implantation (containment of small properties) necessary for the execution of this type of works and the consequent mobilizations (means and resources); - multiplicity of interactions with the affected services; - scheduling/priorities according to the pressing needs of the moment; complementarity / multidisciplinarity with other works. as a corollary, the simple linear sum of these facts, invariably always under the uncertainty factor, which in the present case, led to the extension of the execution period of the contract.
2247 | 5063190 | Renovation of Villages - Fountain Route | 45453100-8 | Refurbishment work | FALSE | 2018 | 2020 | Portugal | Carregal do Sal | Viseu | 20 | 21 | 22-10-2018 | 05-02-2020 | 471 | 180 | 88000 | 87466.72 | 1 | 80274.93 | 7191.79 | 108.9589 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for execution of the project was changed with the extension of the period necessary for the execution of the complementary works | the changes in the value of the project are due to the fact that some quantities estimated in the project were not fully executed, which led to a value of underwork, the need to carry out some complementary work and with the increase in the value of the revision of prices as shown on the final bill.
2248 | 5062620 | 100% QUALITY- Installation of a rainwater network on R. De s. Brás and Aldeia de Baixo | 45240000-1 | Construction work for water projects | TRUE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 18-12-2018 | 18-07-2019 | 212 | 45 | 53000 | 40820 | 1 | 40820 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2249 | 5059179 | 5010020901 - Contract named "Cascais Line - Improvement of track superstructure between KP 9+600 and 11+973" | 45234100-7 | Railway construction works | FALSE | 2015 | 2018 | Portugal | N/A | N/A | N/A | 35 | 26-04-2016 | 23-01-2018 | 637 | 240 | 1300000 | 1288747.58 | 3 | 1190954.94 | 97792.64 | 108.2113 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60% 2. Technical Valuation - 20% 3. Safety Management System - 10% 4. Quality Management System - 5% 5. Environmental Management System - 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2250 | 5058782 | Rehabilitation of the Public Space of Bairro Novo da Previdência | 45211360-0 | Urban development construction work | FALSE | 2018 | 2020 | Portugal | Bragança | Bragança | 4 | 30 | 02-08-2018 | 24-06-2020 | 692 | 304 | 432690.67 | 419081.38 | 2 | 418803.49 | 277.89 | 100.0664 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | motivated by the need to wait for the sown grass to grow, strengthening it in areas of low growth and the respective removal of stones and other elements, as well as the need to be alert to find out if the bushes and trees would sprout in the spring. | underwork
2251 | 5057852 | Urbanization Works for the Industrial Zone of Picaria | 45233120-6 | Road construction works | FALSE | 2018 | 2020 | Portugal | Santo Tirso | Porto | 13 | 14 | 10-12-2018 | 30-07-2020 | 598 | 120 | 993528.09 | 712843.73 | 2 | 618163.19 | 94680.54 | 115.3164 | Best value for money: Yes Criterion related to quality Name: Valia Técnica, Safety Management Systems, Quality Control and Environmental Management Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the suspension of work under article 365 | the existence of less expendable work during the course of the project.
2252 | 5057528 | 2018/129 - DGEP - Requalification of Bartolomeu Gusmão, Alfredo Keil and Dr. Flavio de Resende, Oeiras | 45316110-9, 45233142-6, 45233294-6 | Installation of road lighting equipment, Road-repair works, Installation of road signals | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 07-12-2018 | 16-02-2020 | 436 | 150 | 201351.93 | 174900.01 | 1 | 157827.88 | 17072.13 | 110.8169 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
2253 | 5055842 | Contract for the Rehabilitation of Reservoirs - Phase I - Lot 3 - Polo Alentejo | 50514200-3 | Repair and maintenance services of reservoirs | FALSE | 2018 | 2020 | Portugal | Portalegre | Évora | 7 | 30 | 30-11-2018 | 29-01-2020 | 425 | 240 | 995000 | 228860.83 | 1 | 223835.31 | 5025.52 | 102.2452 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | inspection for the purposes of provisional acceptance of the project took place after the successful tenderer had delivered all the documentation necessary for this purpose, namely the final screens, technical compilation and "plan for the prevention and management of construction and demolition waste". | resulting from work not carried out and the price review carried out.
2254 | 5053516 | A Sustainable Territory - Water - Repairing the Water Network - Vale de Janes / A Sustainable Territory - Sanitation - Sanitation and Wastewater Network - Vale de Janes | 45232460-4 | Sanitary works | FALSE | 2018 | 2021 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 15 | 07-09-2018 | 20-07-2021 | 1047 | 180 | 331900 | 329265.82 | 2 | 307482.07 | 21783.75 | 107.0846 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% - Technical value 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions and suspensions of the period of execution of the project were granted | additional work, underwork and price revisions
2255 | 5052158 | Reservoir Rehabilitation Contract - Phase I - Lot I - Beira Alta Pole | 50514200-3 | Repair and maintenance services of reservoirs | FALSE | 2018 | 2020 | Portugal | Celorico da Beira | Guarda | 9 | 30 | 30-11-2018 | 27-05-2020 | 544 | 240 | 995000 | 338913.15 | 2 | 345946.78 | -7033.63 | 97.9668 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the period of 21 days associated with the execution of work to correct errors and omissions, and graceful extension of the period by 26 days associated with a reduction of the means present in the contract over time, with there also being a delay in the beginning of the projects. | resulting from underwork, errors and omissions supply work, as well as price revisions.
2256 | 5051378 | A Sustainable Territory - Sanitation - Sewage Network in the West Zone of the Parish of Anobra - Lameira / A Sustainable Territory - Water - Water Network in the West Zone of the Parish of Anobra - Lameira | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2021 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 15 | 12-03-2018 | 10-05-2021 | 1155 | 240 | 350000 | 314634.8 | 2 | 310115.87 | 4518.93 | 101.4572 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions granted | complementary work and underwork and price revision
2257 | 5048525 | Repair of Public Lighting on the Marginal Atlantica from Leça da Palmeira to Lavra | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2021 | Portugal | N/A | N/A | N/A | 21 | 10-12-2018 | 11-08-2021 | 975 | 122 | 392000 | 273774.59 | 2 | 294316.85 | -20542.26 | 93.0204 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2258 | 5048050 | Execution of covered playgrounds and exterior painting at EB Louro Artur, EB Vila Nova and JI de Vale Rosal | 45236290-9 | Repair work on recreational areas | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 30 | 15-11-2018 | 30-09-2019 | 319 | 180 | 375436.86 | 327750 | 2 | 311575.99 | 16174.01 | 105.191 | Best value for money: No Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work. | underwork.
2259 | 5048039 | Rehabilitation of the central street of Sobreiro, including partial renovation of infrastructure, accessible sidewalks and cycle routes, in the parish of Cidade da Maia | 45233142-6 | Road-repair works | FALSE | 2018 | 2021 | Portugal | Maia | Porto | 13 | 32 | 23-11-2018 | 31-08-2021 | 1012 | 420 | 1689445.58 | 1351556.45 | 3 | 1340260.39 | 11296.06 | 100.8428 | Best value for money: No Criterion related to quality Name: VALIA TECNICA Weighting: 0% Criterion related to cost Name: PRICE Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | this contract had a graceful extension of the deadline for a period of 62 (sixty-two) days, as it was not possible on the scheduled date to carry out the roundabout between rua central do sobreiro and rua dos plátanos, foreseen in the project, without it being relocated a pt from edp; and also, the demolition of block 63, all this in addition to the flood phenomena that the municipality suffered in october and december 2019. | the total value of this contract is the result of the projects carried out in it.
2260 | 5045728 | The contract includes, in its general lines, the construction of the Casais das Boiças interceptor (and connections to the network downstream), with an extension of about 1,880 m, in HDPE DN200. | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2020 | Portugal | Azambuja | Lisboa | 11 | 48 | 27-11-2018 | 04-03-2020 | 463 | 100 | 246000 | 227820.2 | 1 | 250925.97 | -23105.77 | 90.7918 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 40% price 60% technical value. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | conditioning access to land for conditioning access and execution of some parts of the project, due to excess water in the land. | occasional adjustments to the interceptor layout and unforeseen deforestation work.
2261 | 5044701 | Replacement of the breakwater in the port of Porto das Barcas. | 45243200-4 | Breakwater construction work | TRUE | N/A | 2019 | Portugal | Lourinhã | Lisboa | 11 | N/A | 26-11-2018 | 12-07-2019 | 228 | 63 | N/A | 257808.01 | 2 | 257808.01 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline did not change in terms of execution days, there was only a suspension due to lack of security conditions. | no change
2262 | 5040246 | Vila Franca de Xira - People's Axis - Quinta da Grinja - Requalification of public space | 45112700-2 | Landscaping work | FALSE | 2018 | 2021 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 14-06-2018 | 30-03-2021 | 1020 | 396 | 2829000 | 2215000 | 3 | 2261857.81 | -46857.81 | 97.9283 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork
2263 | 5039036 | AA 008 E1 - New South Lever Reserve | 45223500-1 | Reinforced-concrete structures | FALSE | 2018 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 07-11-2018 | 10-08-2020 | 642 | 365 | 2225000 | 1999992.67 | 3 | 2101035.7 | -101043.03 | 95.1908 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | lack of labor in the national market / changes/undefined in the execution project / delays in deliveries from the performing entity's suppliers / execution of complementary work | execution of complementary works / deletion of works / errors and omissions
2264 | 5038719 | Execution contract for the recycling stations in the municipalities of Castelo Branco, Idanha-a-Nova and Vila Velha de Rodão | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2021 | Portugal | Idanha-a-Nova | Castelo Branco | 5 | 48 | 10-09-2018 | 06-12-2021 | 1183 | 240 | 740000 | 668697.37 | 2 | 664141.42 | 4555.95 | 100.686 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE 70% TECHNICAL EVALUATION 30% B.1 Work execution methodology 20% B.2 Detail and consistency of the Work Plan 10% B.2.1 Work Schedule 5% B.2.2 Means Plan 5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline due to the unavailability of land and impracticability of water supply cuts. | changes in the value of the project resulting from underwork and price revisions.
2265 | 5037549 | Reconversion of the former Volunteer Fire Station | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Sernancelhe | Viseu | 20 | 30 | 03-12-2018 | 27-02-2020 | 451 | 240 | 285733.8 | 285680.8 | 2 | 322270.35 | -36589.55 | 88.6463 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost name: price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | additional work, underwork and price revisions
2266 | 5036245 | PRC_0315/2018_GAE-AR0406 - FSC installation contract in Codessoso (Celorico de Basto) | 45232400-6 | Sewer construction work | TRUE | 2018 | 2020 | Portugal | Celorico de Basto | Braga | 3 | 21 | 29-11-2018 | 05-02-2020 | 433 | 56 | 110000 | 79047.14 | 1 | 48249.8 | 30797.34 | 163.8289 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | supply of installation work for electrical equipment and installations
2267 | 5034572 | Access control gates to the floating quays at the Fishing Ports of St.ª Luzia and Cabanas de Tavira | 45340000-2 | Fencing, railing and safety equipment installation work | FALSE | 2018 | 2019 | Portugal | Tavira | Faro | 8 | 14 | 23-10-2018 | 01-07-2019 | 251 | 30 | 25000 | 22700 | 1 | 22700 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 60% Criterion related to cost Name: Technical quality of the proposal Weighting: 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2268 | 5033838 | Building Recovery | 45453100-8 | Refurbishment work | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 40 | 13-10-2016 | 27-06-2019 | 987 | 540 | 1740205 | 1229987.79 | 3 | 1222037.79 | 7950 | 100.6506 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | specific rehabilitation work, namely structural effort and intrusive work to frame and make the various infrastructures compatible with the vertical and horizontal walls of the building. | underwork
2269 | 5033416 | 100% Quality - Public Tender for bituminous paving of streets in 2018 - Union of Parishes of Custóias, Leça do Balio and Guifões | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 05-12-2018 | 19-07-2019 | 226 | 122 | 220000 | 157889 | 1 | 173676 | -15787 | 90.9101 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2270 | 5032733 | Construction work no. 07/2018/dpgom - renovation of the Várzea bridge | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Alcanena | Santarém | 16 | 14 | 04-12-2018 | 14-08-2019 | 253 | 120 | 185000 | 174470.46 | 1 | 174470.46 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | measurement report no. 6, of 06/24/2019. schedule for provisional reception
2271 | 5032525 | Requalification of the Alto-do-Índio Nursery Workers' Facilities | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 15 | 04-12-2018 | 20-09-2019 | 290 | 150 | 193926.64 | 179063.36 | 1 | 179063.36 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work.
2272 | 5030707 | Work Contract for the Execution of the New Pipeline for the Supply of Water to the Vila Alta Reservoir - Municipality of Alenquer | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Alenquer | Lisboa | 11 | 60 | 06-09-2018 | 28-10-2020 | 783 | 210 | 290000 | 261273.8 | 2 | 305150.09 | -43876.29 | 85.6214 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% + Technical value - 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the execution of the project it was verified the existence of several private constructions adjacent to the public road, where the elevating conduit was implanted, which suffer from pathologies, namely the presence of a wall built with cement blocks with threat of imminent ruin. it was necessary to demolish the aforementioned wall in all its extension for the resumption of the project. | changes in the value of the project resulting from the additional work carried out, price revisions and compensation paid to the contractor due to the need to suspend the project.
2273 | 5026845 | PRC_0099/2018_GAE-AA0386 - Contract for the Supply and Installation of a New Elevation System in Capração and EE of Crueiro (Murça) | 45232152-2 | Pumping station construction work | FALSE | 2018 | 2020 | Portugal | Murça | Vila Real | 19 | 14 | 15-11-2018 | 06-04-2020 | 508 | 45 | 145000 | 139690.69 | 1 | 143005.68 | -3314.99 | 97.6819 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | price review
2274 | 5026329 | Contract nº 30/18 - "Horizontal Signage 2018/2019 - Lot 1 - North Zone and Lot 2 - South Zone" | 45233221-4 | Road-surface painting work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 29-11-2018 | 18-03-2020 | 475 | 364 | 395150 | 316122 | 2 | 322494.33 | -6372.33 | 98.024 | Best value for money: Yes Criterion related to quality Name: Quality of work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the delay was due to weather conditions not being ideal for the application of paints with specific chemical components. rain, humidity and heat influence the carrying out of horizontal signage work. | provisional price review in the amount of €1,359.00; definitive price revision worth €5,013.33
2275 | 5024409 | Rehabilitation of the aqueduct in the access of Avenida Robert Smith to Avenida Frei Bartolomeu dos Mártires | 45232451-8 | Drainage and surface works | TRUE | 2018 | 2019 | Portugal | Braga | Braga | 3 | 16 | 04-12-2018 | 20-12-2019 | 381 | 180 | 520000 | 484254.84 | 2 | 418368.18 | 65886.66 | 115.7485 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | emergence of unpredictable circumstances at work | emergence of unpredictable circumstances at work
2276 | 5023226 | New Distributor Conduct for the Azoia Sector | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2021 | Portugal | Sesimbra | Setúbal | 17 | 15 | 09-10-2018 | 22-01-2021 | 836 | 210 | 464517.26 | 416291.16 | 2 | 545178 | -128886.84 | 76.3588 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 210 days of initial execution period; 208 days of term extension under the terms of article 374 of the "public procurement code" and 61 days of term extension under the terms of al. a), paragraph 1, article 311 and al. b), of article 312 of the "public procurement code". the communication of approval of the pss to the contractor occurred on 11/08/2018 and the end of the contract, considering the described deadline extensions, occurred on 03/01/2020. | overwork, errors and omissions, and underwork
2277 | 5022494 | Reconversion of the adães bermudes da sandia school into an intergenerational cultural and creative center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2018 | 2020 | Portugal | Felgueiras | Porto | 13 | 15 | 28-11-2018 | 28-04-2020 | 517 | 236 | 419315.55 | 385617.18 | 2 | 384296.3 | 1320.88 | 100.3437 | Best value for money: Yes Criterion related to quality Name: Technical Evaluate Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of term extension | smaller quantities executed
2278 | 5019643 | Civic Center (paru 2.3) | 45454000-4 | Restructuring work | FALSE | 2018 | 2020 | Portugal | Chaves | Vila Real | 19 | 21 | 16-11-2018 | 04-02-2020 | 445 | 180 | 239934.9 | 228917.02 | 1 | 240041.95 | -11124.93 | 95.3654 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | complementary work to supply errors and omissions, underwork and price revision
2279 | 5018717 | Construction of a building with drawers for aerobic consumption at Cemitério Novo de Faro - 2nd Phase | 45215400-1 | Cemetery works | TRUE | 2018 | 2020 | Portugal | Faro | Faro | 8 | 15 | 21-11-2018 | 13-07-2020 | 600 | 90 | 191509.43 | 189798.2 | 1 | 185628.2 | 4170 | 102.2464 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Does not apply Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | additional work and underwork
2280 | 5016966 | Rehabilitation of the Mar e Guerra Road – Patacão | 45233141-9 | Road-maintenance works | TRUE | N/A | 2019 | Portugal | Faro | Faro | 8 | N/A | 04-12-2018 | 14-11-2019 | 345 | 90 | N/A | 106351.3 | 1 | 106351.3 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the project deadline
2281 | 5016149 | Rehabilitation of the pavilion of E. B. 2, 3 Dr. Nuno Simões - Union of parishes of V. N. De Famalicão and Calendar | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2018 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 13-09-2018 | 18-01-2019 | 127 | 60 | 107042 | 98188.29 | 1 | 98188.29 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2282 | 5014294 | Restructuring of the External Consultation ENT Office | 45454000-4 | Restructuring work | FALSE | 2018 | 2018 | Portugal | Barcelos | Braga | 3 | 14 | 15-11-2018 | 31-12-2018 | 46 | 30 | 13750 | 13745 | 1 | 13745 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valuation of the Proposal (30%) + Deadline for Execution and Proof of Feasibility (20%) Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2283 | 5011340 | Contract for various repairs at ICBAS and FFUP facilities | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 24 | 16-11-2018 | 18-02-2020 | 459 | 150 | 320000 | 274343.72 | 2 | 315704 | -41360.28 | 86.899 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 60% Criterion related to cost Name: Global price proposed for the Contract Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension approved on 13-06-2019. | as a result of the published changes.
2284 | 5010989 | Rehabilitation of the Luís Campos Building and Adaptation to the Municipal Library | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2021 | Portugal | Estremoz | Évora | 7 | 5 | 04-12-2018 | 20-05-2021 | 898 | 540 | 1517873.15 | 1517000 | 3 | 1968627.03 | -451627.03 | 77.0588 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | project review - complementary works | complementary works
2285 | 5009385 | A Sustainable Territory - Sanitation - Sewerage Networks and Wastewater - Ega and Venda da Luísa / A Sustainable Territory - Water - Repair of the Water Network - Ega | 45232421-9 | Sewage treatment works | FALSE | 2018 | 2021 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 6 | 10-04-2018 | 27-01-2021 | 1023 | 300 | 300000 | 294851.72 | 2 | 261229.54 | 33622.18 | 112.8707 | Procedure announcement without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | additional work, underwork and price revisions
2286 | 5005352 | Public Tender for the Dredging Contract with Reinforcement of the Dune Cord | 45252124-3 | Dredging and pumping works | FALSE | 2018 | 2019 | Portugal | Figueira da Foz | Coimbra | 6 | 13 | 30-11-2018 | 02-12-2019 | 367 | 20 | 742200 | 599200 | 2 | 599200 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Performance Quality Assurance Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the contractual period of 20 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective provisional acceptance certificate.
2287 | 5004673 | Quality 100% - Superelevation of Pedestrian Crossings | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 15 | 27-11-2018 | 25-03-2019 | 118 | 61 | 142500 | 117079.5 | 1 | 117079.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2288 | 5004532 | Contract for the supply and assembly of sieves for the alcantara, chelas and eaves subsystems | 45232460-4 | Sanitary works | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 48 | 03-09-2018 | 11-09-2019 | 373 | 360 | 1110000 | 1009989.39 | 3 | 1009989.39 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A. - PRICE: 40% B. - TECHNICAL VALUE: 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the execution of the project took place on time, with the final account only being approved on 7/11/19
2289 | 5003457 | The object of this contract is the execution of a set of small works for the requalification of outdoor spaces/green areas in the municipality, in accordance with the defined works to be carried out | 45112710-5 | Landscaping work for green areas | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 10 | 26-11-2018 | 02-04-2020 | 493 | 364 | 537726 | 456567.1 | 2 | 462652.99 | -6085.89 | 98.6846 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no cause to report. | due to the definitive price revision in the amount of €6,085.89 - lot 1 - €2,049.52; lot 2 - €1,999.68; lot 3 - €2,036.69 and due to this an addendum was made to the project account on 01/25/2022.
2290 | 5003419 | Contract for "Remodeling of the Ferrel-Espiche drainage networks/Deactivation of the Ferrel collective septic tanks and Connection to the system in Alta Espiche/WWTP in Lagos" | 45232400-6, 45233251-3 | Sewer construction work, Resurfacing works | FALSE | 2018 | 2020 | Portugal | Lagos | Faro | 8 | 33 | 26-11-2018 | 27-11-2020 | 732 | 180 | 500000 | 416422.55 | 2 | 466375.68 | -49953.13 | 89.2891 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1 - b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was extended for 135 days | approved complementary works in the total amount of €44,050.00, plus vat and calculated as the total amount of price revision the amount of €5,903.13, plus vat
2291 | 5000844 | Social Housing Rehabilitation PER Valado | 45321000-3 | Thermal insulation work | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 24 | 23-11-2018 | 17-01-2020 | 420 | 150 | 428000 | 328965.5 | 2 | 348228.81 | -19263.31 | 94.4682 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension of the project execution period of 17 days (addendum to the contract entered into on 05.30.2019) a 20-day execution period was assigned to complementary work | - complementary work - approved on 05.08.2019 - underwork - approved on 08.14.2019. - calculation of the provisional price revision - approved on 11.26.2019 - calculation of the definitive price revision - approved on 08.17.2020
2292 | 5000182 | The object of this contract is the repair and requalification of the streets and respective surrounding areas located in the municipality, in accordance with the defined works to be carried out | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 21-11-2018 | 16-04-2020 | 512 | 364 | 594328.5 | 505179.27 | 2 | 507125.18 | -1945.91 | 99.6163 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 65% Criterion related to cost Name: Price Weighting: 35% | 1 | 35 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | no cause to report. | definitive price revision worth €1,945.91
2293 | 5000123 | Paving from street Maria Gil to street António Monteiro in the industrial zone of Tuias | 45233220-7 | Surface work for roads | FALSE | N/A | 2019 | Portugal | Marco de Canaveses | Porto | 13 | N/A | 26-11-2018 | 13-03-2019 | 107 | 75 | N/A | 91127.5 | 1 | 89077.5 | 2050 | 102.3014 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project finished ahead of schedule. | underwork.
2294 | 5000093 | Contract for the Refurbishment of Offices at Tagus Park | 45262700-8 | Building alteration work | FALSE | 2018 | 2019 | Portugal | Oeiras | Lisboa | 11 | 30 | 22-11-2018 | 11-07-2019 | 231 | 150 | 137000 | 135914.2 | 1 | 134945.14 | 969.06 | 100.7181 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 20% Criterion related to cost Name: Bid price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | fulfilled the deadline of the project | there was a cost reduction of €969.06 (not necessary work, as it is a pre-existing article)
2295 | 4998683 | CPR 069/17 - Contract for the remodeling of infrastructures in Três Bicos - 2nd Phase | 45432110-8, 45231300-8 | Floor-laying work, Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Portimão | Faro | 8 | 30 | 05-01-2018 | 05-12-2019 | 699 | 140 | 256015.16 | 212697.15 | 1 | 211076.96 | 1620.19 | 100.7676 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | "the extension was motivated by the difficulty of the contractor to complete the stipulated deadline due to the great difficulty of carrying out the project, motivated by the large amount of electrical cables and the gas network that were found on the boxes of the existing water and sewage branches to be connected to the new network, so much of the project in the promenade area was carried out manually, without the expected yield for carrying it out mechanically, and because of the great difficulty of labour, and the weather conditions, as this is not entirely attributable to the successful bidder, and because the delay does not cause damage to the owner of the project."
2296 | 4998001 | The purpose of the contract is the construction of water supply networks, sewage drainage and a complementary and treatment body in the village of Alves. It also includes the paving of streets . | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Mértola | Beja | 2 | 30 | 27-11-2018 | 27-11-2020 | 731 | 270 | 975000 | 878766.3 | 2 | 803973.19 | 74793.11 | 109.3029 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unavailability of human resources and supply of materials on site as a result of the pandemic situation. | underwork
2297 | 4996918 | S.e.c. - PROCº Nº 167/A1/18 - Public Tender for the contract award of "Viana do Castelo Urban Cycle Path Network - Riverside Section" | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 28-11-2018 | 21-09-2021 | 1028 | 240 | 494000 | 493009.37 | 2 | 484242.28 | 8767.09 | 101.8105 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a need to suspend work due to edp distribuição placing the medium/high voltage cables on the section of the cycle path on avenida do atlântico, which are intended to supply energy to the submarine cable from the wind located at sea. | underwork was carried out than previously defined.
2298 | 4992243 | Ecovia do Rio Minho - Caldas de Monção/Bela Section - 1st Phase | 45233260-9 | Pedestrian ways construction work | FALSE | 2018 | 2020 | Portugal | Monção | Viana do Castelo | 18 | 35 | 08-10-2018 | 02-07-2020 | 633 | 180 | 113393.66 | 112984.57 | 1 | 124242.79 | -11258.22 | 90.9385 | Best value for money: Yes Criterion related to quality Name: Valia Técnica/Warranty/Exceptional conditions given to the work and its equipment Weighting: 35% Criterion related to cost Name: Bid Price Weighting: 65% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | need to carry out additional work and suspension notice due to lack of safety conditions. | execution of complementary works and revision of prices.
2299 | 4991452 | Rehabilitation and Requalification of Riverside Ecosystems - Works to protect the riverside margins. | 45246200-5 | Riverbank protection works | FALSE | 2018 | 2019 | Portugal | Monção | Viana do Castelo | 18 | 14 | 24-10-2018 | 26-09-2019 | 337 | 90 | 147000 | 138646 | 1 | 138646 | 0 | 100 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | it took longer as a result of the fires that occurred until the end of october 2017, and given the existing emigration in this geographical area and the articulation between the apa / arh in the north was not reasonably easy. | the contractual value was maintained
2300 | 4987676 | Rehabilitation of Pavements in Various streets in the Municipality - 2018/2019 | 45233223-8 | Carriageway resurfacing works | FALSE | 2018 | 2020 | Portugal | Odivelas | Lisboa | 11 | 14 | 22-11-2018 | 21-01-2020 | 425 | 120 | 259000 | 259000 | 2 | 259000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes in the execution period of the project. | there were no changes to the value of the project
2301 | 4987620 | 2018.086.01.C1 - SFP Alverca - Improvement of PT and Electric Panels | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Vila Franca de Xira | Lisboa | 11 | 15 | 24-07-2018 | 04-02-2019 | 195 | 75 | 70000 | 58906.5 | 1 | 58906.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Bid Price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | concluded
2302 | 4977185 | Clearing terrain; construction of walls, rockfills and crossings; land movement; reinforced concrete work on various elements; waterproofing works; | 45246000-3 | River regulation and flood control works | FALSE | 2018 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 26-11-2018 | 06-07-2020 | 588 | 180 | 470000 | 386355.26 | 2 | 426565.67 | -40210.41 | 90.5735 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (Cp) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a work suspension notice was duly authorized. | the completion of the project resulted in more work worth €44,049.90, underwork worth €14,100.00 and a final price review worth €10,260.51.
2303 | 4976992 | Various works in unfinished urbanizations | 45233222-1 | Paving and asphalting works | FALSE | 2012 | 2018 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 08-11-2012 | 11-09-2018 | 2133 | 40 | 347500 | 228413.39 | 1 | 228413.39 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report
2304 | 4976576 | Requalification of Buildings for University Residences. | 45214700-7 | Construction work for halls of residence | FALSE | 2016 | 2021 | Portugal | Águeda | Aveiro | 1 | 30 | 26-11-2018 | 22-06-2021 | 939 | 365 | 775665.55 | 592862.7 | 2 | 630210.38 | -37347.68 | 94.0738 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the project execution deadline were motivated by the partial suspension of works and also by two extensions of deadlines authorized following the approval of additional works. | the causes for the change in the value of the project were the approval of more work maps and the supply of errors and/or omissions
2305 | 4974975 | Public Tender No. PLN.18.PC03/AE - Contract for the protection of the coastal system at Praia da Amorosa | 45243000-2 | Coastal-defence works | FALSE | 2018 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 21 | 30-10-2018 | 21-01-2021 | 814 | 210 | 1143000 | 1057365.62 | 3 | 938396.44 | 118969.18 | 112.6779 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | after the consignment of the contract, and following the geotechnical recognition, in view of the necessary preparation of the project, it was detected that under a sand layer of variable thickness, a rocky substrate occurred in the area of implementation of the geocylinders (section i), as well as the appearance of silty sands and section ii and iii), instead of the sand initially provided, whose roof is at levels that prevent the construction of the projects as defined in the execution project. the actual geological conditions of the terrain were immediately sent to the designer, in order to adapt the project to the existing underground, therefore, an addition was produced to the project, with the changes to be introduced to the projects to adapt them to the actual conditions of the site. as a result of this amendment to the agreement, there was the need to suppress work and carry out work to reply errors and omissions, which thus justifyed the granted extension. | after the consignment of the contract, and following the geotechnical recognition, in view of the necessary preparation of the project, it was detected that under a sand layer of variable thickness, a rocky substrate occurred in the area of implementation of the geocylinders (section i), as well as the appearance of silty sands and section ii and iii), instead of the sand initially provided, whose roof is at levels that prevent the construction of the projects as defined in the execution project. the actual geological conditions of the terrain were immediately sent to the designer, in order to adapt the project to the existing underground, therefore, an addition was produced to the project, with the changes to be introduced to the projects to adapt them to the actual conditions of the site. as a result of this amendment to the agreement, there was the need to suppress work and carry out work to replace errors and omissions, which resulted in the change in the value of the project
2306 | 4974541 | Requalification of pavements in municipal streets | 45233200-1 | Various surface works | FALSE | 2012 | 2018 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 20-02-2013 | 11-09-2018 | 2029 | 60 | 455000 | 273000.01 | 2 | 273000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | a 30-day suspension of work was approved at the board meeting on 04/17/2013, pursuant to article no. 297, paragraph a) of dl no.
2307 | 4973475 | PRC_0198/2018_GAE-EB0399 - Contract for the construction of the pipeline to the Telhe reservoir (Arouca) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Arouca | Aveiro | 1 | 14 | 26-10-2018 | 26-04-2020 | 548 | 150 | 180500 | 169016.37 | 1 | 173773.9 | -4757.53 | 97.2622 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delays caused by the unavailability of the electricity grid were not reflected by the fact that on 06/12/2019 the infrastructure came into operation (mode: manual), a fact that led to that date being considered for provisional acceptance | need to introduce improvements in the design solution: - increase in the capacity to lift the flow of each pump (they can now lift 3 m3/h, instead of 1 m3/h, as defined in the execution project; in this way, in the event of a breakdown in the network, the replenishment of supply will be greatly improved
2308 | 4973116 | PRC_0277/2018_GAE-O0403 - General Contract for Maintenance and Repair Interventions in the SAA and SAR in Alta da Águas do Norte, S.A. And Other interventions - Lot A (Trás-os-Montes and Douro Superior) | 45232000-2 | Ancillary works for pipelines and cables | FALSE | 2018 | 2021 | Portugal | N/A | N/A | N/A | 14 | 02-11-2018 | 17-02-2021 | 838 | 365 | 735000 | 165000 | 1 | 461423.8 | -296423.8 | 35.7589 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | underwork
2309 | 4970831 | PRC_0188/2018_GAE-EB0396 - FSC installation contract in Guarda, Pardinhas and Travanca do Monte - Carvalho de Rei (Amarante) | 45232400-6 | Sewer construction work | TRUE | 2018 | 2020 | Portugal | Amarante | Porto | 13 | 21 | 06-11-2018 | 17-11-2020 | 742 | 90 | 120000 | 105248.82 | 1 | 105483.32 | -234.5 | 99.7777 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to indicate | it results from adjustments in landscaping due to the plots acquired
2310 | 4970314 | Rehabilitation of the Football Fields (Main and No. 2) - Parque Desportivo de Grândola | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2018 | 2019 | Portugal | Grandola | Setúbal | 17 | 15 | 23-10-2018 | 23-09-2019 | 335 | 60 | 299942.2 | 273000 | 2 | 328376.58 | -55376.58 | 83.1363 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award will be made according to the criterion of the most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | term extension | complementary works
2311 | 4970111 | Requalification of Camilo Castelo Branco Square and adjacent spaces -2nd PHASE | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2019 | Portugal | Santo Tirso | Porto | 13 | 20 | 20-11-2018 | 14-11-2019 | 359 | 150 | 439533.13 | 368128.48 | 2 | 400454.62 | -32326.14 | 91.9276 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: A - Price with a weighting of «A__Price»60% of the overall assessment; B - Technical Value of the Proposal with a weighting of 40% «B__Valia_Técnica» in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: B1 Schedule of Works with a weighting of 25% «B1__Programação_dos_works» in the overall classification; B2 Meios Afectos à Obra with a «B2__Meios_Afectos_à_obra» weighting of 10% in the overall classification; B3 Risk Management for Occupational Safety and Health with a weighting of 5% «B3__Segurança_a_implementar na_obra» in the classification as a whole. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need for more work. | the existence of under and extra work.
2312 | 4969315 | PRC_0140/2018_GAE - AA0390 - Design/construction contract for improving the quality of water produced at the Areias de Vilar ETA (Barcelos) | 45351000-2 | Mechanical engineering installation works | TRUE | 2018 | 2020 | Portugal | Barcelos | Braga | 3 | 15 | 30-10-2018 | 19-05-2020 | 567 | 196 | 1000000 | 465000 | 2 | 464999.98 | 0.02 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | there was a slight reduction due to rounding error, which it was not possible to overcome.
2313 | 4967705 | Contract for the rehabilitation of the pavement and coating of the fish market at the Fishing Port of Quarteira | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Loulé | Faro | 8 | 14 | 09-10-2018 | 04-04-2019 | 177 | 60 | 75000 | 74862.22 | 1 | 90083.4 | -15221.18 | 83.1032 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works | complementary works
2314 | 4967680 | Lots 8 and 12 - Requalification of Avenidas Dr. Francisco Sá Carneiro, Xavier Teixeira and Raposeira, Linha do Comboio and Aregos streets and the Raposeira Viaduct | 45233220-7 | Surface work for roads | FALSE | 2018 | 2021 | Portugal | Chaves | Vila Real | 19 | 30 | 20-11-2018 | 08-02-2021 | 811 | 240 | 883420.05 | 785793.99 | 2 | 759269.83 | 26524.16 | 103.4934 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | two term extensions (281 days) | underwork for the amount of €35,330.60 and price revision for the amount of €8,806.44
2315 | 4963405 | Reconversion of plant cover in municipal green spaces - in the context of adapting to climate change | 71421000-5 | Landscape gardening services | TRUE | N/A | 2021 | Portugal | Viseu | Viseu | 20 | N/A | 29-10-2018 | 22-03-2021 | 875 | 42 | N/A | 20883.93 | 1 | 19716.98 | 1166.95 | 105.9185 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | does not exist | works less
2316 | 4962548 | Contract for the Requalification of Caminho das Areias, Parish of Santo Amaro, Municipality of Velas | 45233120-6 | Road construction works | FALSE | 2018 | 2020 | Portugal | Velas | Região Autónoma dos Açores | 15 | N/A | 16-11-2018 | 30-11-2020 | 745 | 120 | 637862.4 | 594000 | 2 | 619401.84 | -25401.84 | 95.899 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 75% Price and 25% Period of execution of the endeavor. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspension: omitted elements, time between contractor communication and inspection response, implementation with the new elements delivered. graceful extensions (4): adverse weather conditions, covid-19 pandemic that conditioned the movement of goods and people, carrying out unforeseen work (cleaning, etc.), work conditioned by carrying out work on a 2nd contract on the critical path of the constructions . | need to carry out work (more) complementary to the contract, namely, reductions in the pavement, future interventions in new walls, and problems with rainwater on the regional road.
2317 | 4962292 | Reconversion of plant cover in municipal green spaces - in the context of adapting to climate change | 71421000-5 | Landscape gardening services | TRUE | N/A | 2021 | Portugal | Viseu | Viseu | 20 | N/A | 22-10-2018 | 17-03-2021 | 877 | 42 | N/A | 52525.2 | 1 | 52525.2 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | does not exist | does not exist
2318 | 4962136 | Reconversion of plant cover in municipal green spaces - in the context of adapting to climate change | 71421000-5 | Landscape gardening services | TRUE | N/A | 2021 | Portugal | Viseu | Viseu | 20 | N/A | 25-10-2018 | 09-02-2021 | 838 | 42 | N/A | 65999 | 1 | 65999 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | does not exist | does not exist
2319 | 4962138 | Public tender for the contract for the replacement of pavements in the Municipality of Oeiras in the years 2018/2019. | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Oeiras | Lisboa | 11 | 20 | 05-11-2018 | 20-11-2019 | 380 | 365 | 100000 | 90571.99 | 1 | 90569.44 | 2.55 | 100.0028 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | billing settlements worth 2.55 euros
2320 | 4961749 | Kitchen remodeling at EB 2/3 Dr. Joao Lucio - Fuseta | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Olhão | Faro | 8 | 15 | 16-11-2018 | 13-03-2019 | 117 | 45 | 110000 | 104416.04 | 1 | 103374.76 | 1041.28 | 101.0073 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for carrying out the project was subject to a 15-day extension, as a grace, due to delays by suppliers in the delivery of equipment. | the project was the subject of less approved work in the amount of €1,041.28 + vat.
2321 | 4961147 | Modernization of the water supply network systems of the Municipality of Mangualde - Freixiosa, Corvaceira and Chãs de Tavares System | 45317100-3 | Electrical installation work of pumping equipment | FALSE | 2018 | 2020 | Portugal | Mangualde | Viseu | 20 | 14 | 14-11-2018 | 11-05-2020 | 544 | 180 | 206000 | 189775.14 | 1 | 192599.02 | -2823.88 | 98.5338 | Best value for money: No Criterion related to quality Name: nonexistent Weighting: 0% Criterion related to cost Name: non-existent Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | according to information contained in the process. | according to information contained in the process.
2322 | 4960180 | Rehabilitation of Social Housing Developments Canedo | 45210000-2 | Building construction work | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-11-2018 | 13-07-2020 | 605 | 120 | 223954.96 | 220581.57 | 1 | 219256.57 | 1325 | 100.6043 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 34 days of free extension of the deadline, 19 days regarding scheduling the inspection for provisional acceptance and 259 days regarding rectifications carried out between the 1st and 2nd inspection | less approved works
2323 | 4957261 | Repaving of Estrada dos Gorjões between the intersection of Goldra and the Council limit | 45432110-8 | Floor-laying work | TRUE | 2018 | 2019 | Portugal | Faro | Faro | 8 | 20 | 15-11-2018 | 29-08-2019 | 287 | 60 | 175000 | 157451.81 | 1 | 152658.56 | 4793.25 | 103.1399 | Best value for money: No Criterion related to quality Name: Does not apply Weighting: 0% Criterion related to cost Name: Does not apply Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the project deadline | underwork (nº 2, article 379 of the "public procurement code"): €4,793.25
2324 | 4952888 | Contract to improve streets , roads and paths - street Maria Teresa Semedo de Azevedo | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 09-11-2018 | 19-06-2019 | 222 | 30 | 50370.93 | 40000 | 1 | 40000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2325 | 4952081 | Requalification of the public space, essentially with regard to pedestrian mobility and modernization of water infrastructure and domestic and rainwater drainage | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2021 | Portugal | Coimbra | Coimbra | 6 | 24 | 17-05-2018 | 09-02-2021 | 999 | 168 | 727625.55 | 697947.75 | 2 | 696890.38 | 1057.37 | 100.1517 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price, with a weight of 60% and Deadline, with the weighting of 40%, under the deadlines of article 16 of the Program of the Procedure. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal term extension | value of additional work, underwork and price revision.
2326 | 4951696 | Rehabilitation and improvement of the buildings of the Municipal Public Housing of Agrupamento do Falcão | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 05-11-2018 | 29-11-2019 | 389 | 570 | 1390000 | 519663.26 | 2 | 518972.94 | 690.32 | 100.133 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project had two deadline extensions. it was executed with the required quality, in safe conditions and the necessary actions were implemented in order to minimize the environmental impact of the contract. | complementary work worth €3,747.02 and unfinished work worth €4,437.34
2327 | 4951581 | Rehabilitation and improvement of blocks B1 to B4 of the Municipal Public Housing of Agrupamento do Falcão - Lot 2 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 05-11-2018 | 28-10-2019 | 357 | 570 | 1390000 | 469895.55 | 2 | 471839.75 | -1944.2 | 99.588 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | deadline extension | less and additional work
2328 | 4951367 | Rehabilitation and improvement of blocks A1, A2 and C of the Municipal Public Housing complex of Agrupamento do Falcão - Lot 1 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 05-11-2018 | 21-10-2019 | 350 | 570 | 1390000 | 399899.41 | 2 | 399412.34 | 487.07 | 100.1219 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | term extension | less and additional work
2329 | 4951124 | Contract for remodeling the rainwater wastewater network - Zona dos Brejos | 45232130-2 | Storm-water piping construction work | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 09-11-2018 | 04-07-2019 | 237 | 30 | 20530.9 | 17000 | 1 | 17000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to being a tourist area and being in height of festive seasons
2330 | 4950238 | 2016.163.01.C1 - Beja Employment Service - Refurbishment of facilities | 45259900-6 | Plant upgrade work | TRUE | 2018 | 2019 | Portugal | Beja | Beja | 2 | 21 | 22-06-2018 | 04-07-2019 | 377 | 180 | 403989 | 388883 | 2 | 388883 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | definition of elevator assembly works.
2331 | 4949384 | Soft Mobility Infrastructure Improvement Program - Correction of discontinuities in the Susão and Reprofiling of street Gandra do Paciência - Valongo | 45233262-3 | Pedestrian zone construction work | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 15 | 06-11-2018 | 31-03-2020 | 511 | 240 | 320000 | 252766.89 | 2 | 287247.41 | -34480.52 | 87.9962 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution period, the last measurement report dates from 10.10.2019, there was only a delay in scheduling the inspection for the purpose of provisional acceptance of the project. | - complementary work - approved on 27.09.2019 (€32,390.29) - underwork - approved on 22.10.2019 (- € 2,766.76) - calculation of the provisional price revision - approved on 03.03.2020 (€4,856.99)
2332 | 4949186 | Cp/05/dom/2018 - paving streets in bituminous carpet - 2018 | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 16-10-2018 | 10-07-2019 | 267 | 60 | 142000 | 128908.9 | 1 | 128908.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | execution of works conditioned by weather conditions.
2333 | 4949155 | S.e.c. - PROCº nº 150/A1/18 - Public Tender for the award of the contract for "Pedonalization of street of Palha, street of Videira, street of Gramática and street of Santo António" | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 14-11-2018 | 15-11-2019 | 366 | 240 | 766613.13 | 696292.52 | 2 | 592977.03 | 103315.49 | 117.4232 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
2334 | 4948519 | T-15/2017 - execution of the 2016/2017 participatory budget - project execution contract - proposal n.º 9 rehabilitation of space and construction of padel courts in the sports, educational area | 45212200-8 | Construction work for sports facilities | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 14 | 02-10-2018 | 25-09-2019 | 358 | 120 | 93523.2 | 92464.32 | 1 | 92464.32 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: 0 Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2335 | 4948517 | 2018.084.01.C1 - crp alcoitão - transformation station | 45310000-3 | Electrical installation work | FALSE | N/A | 2020 | Portugal | N/A | N/A | N/A | N/A | 09-11-2018 | 24-03-2020 | 501 | 120 | N/A | 190000 | 1 | 190000 | 0 | 100 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension
2336 | 4948152 | 2015.116.02.C1 - SE and SFP Setúbal - improvement of electrical switchboards | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Setúbal | Setúbal | 17 | 15 | 04-09-2018 | 05-02-2019 | 154 | 120 | 156000 | 128128 | 1 | 128128 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed on time
2337 | 4946233 | Contract nº 31/18 - Conservation and Improvement of Municipal Buildings/Municipal School Park - Drainage | 45232450-1 | Drainage construction works | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 15 | 07-11-2018 | 18-12-2019 | 406 | 364 | 190633.5 | 162038.49 | 1 | 164979.38 | -2940.89 | 98.2174 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delay in the project was due to: 1- difficulty in delivery and meeting deadlines by suppliers 2- school schedule that came to mark out and condition the normal execution of work safely in the case of interventions in school equipment 3- adverse weather conditions | it was due to the provisional price revision in the amount of €2,639.39 and the definitive price revision in the amount of €301.50.
2338 | 4945163 | Construction of a compact WWTP on the site of Curral dos Romeiros | 45232421-9 | Sewage treatment works | FALSE | 2018 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 10-10-2018 | 31-10-2019 | 386 | 240 | 272869 | 232482.54 | 1 | 231066.27 | 1416.27 | 100.6129 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions led to changes in the execution of the contract term | difference between measurements in design and measurements on site
2339 | 4943198 | Creation of a parking lot for tourist buses, at the north entrance of the city | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Portalegre | Portalegre | 12 | 7 | 05-11-2018 | 05-06-2019 | 212 | 120 | 267073.84 | 215000 | 1 | 215000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | adjustment of concordances in the project
2340 | 4942541 | Work against fires "2ªphase" - Compartmentation firebreak (communication routes) | 45343000-3 | Fire-prevention installation works | FALSE | 2018 | 2019 | Portugal | Barcelos | Braga | 3 | 16 | 02-10-2018 | 26-02-2019 | 147 | 152 | 56000 | 55640 | 1 | 55640 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal 25% + Deadline for execution and proof of feasibility 25% Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2341 | 4941416 | Contract nº 22/2018 - "Execution of the Parking Marking Plan - 2018/2019" | 45233221-4 | Road-surface painting work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 05-11-2018 | 16-03-2020 | 497 | 364 | 160150 | 160000 | 1 | 163072.22 | -3072.22 | 98.116 | Best value for money: Yes Criterion related to quality Name: Quality of work and material Weighting: 45% Criterion related to cost Name: Price Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delay was due to weather conditions not being ideal for the application of paints with specific chemical components. rain, humidity and heat influence the carrying out of horizontal signage work. | provisional price revision in the amount of €608.80; definitive price review in the amount of €2,463.42; price review in the total amount of 3,072.22.
2342 | 4938819 | Rehabilitation of social housing developments - Lourosa - Cadinha | 45210000-2 | Building construction work | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 07-11-2018 | 26-11-2020 | 750 | 180 | 295296.82 | 273278.8 | 2 | 270905.81 | 2372.99 | 100.8759 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 40 days of graceful extension, 162 days of delay under the responsibility of the contractor and 265 days between the 1st inspection and the provisional reception of the contract in the correction of deficiencies | underwork
2343 | 4938689 | Rehabilitation of social housing development - caldas de s. Jorge - Santa Maria da Feira | 45211000-9 | Construction work for multi-dwelling buildings and individual houses | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 07-11-2018 | 27-04-2020 | 537 | 120 | 225754.17 | 198585.7 | 1 | 196514.31 | 2071.39 | 101.0541 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 50 days gracefully granted extension; 90 days of delay under the responsibility of the contractor, 147 days between inspections for provisional rectification purposes | underwork
2344 | 4937540 | Urban regeneration - access and surroundings to the watchtower | 45432110-8 | Floor-laying work | FALSE | 2018 | 2019 | Portugal | Vimioso | Bragança | 4 | 24 | 07-11-2018 | 09-12-2019 | 397 | 183 | 320752.69 | 241200.7 | 1 | 241200.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | extension for 70 days
2345 | 4937071 | Refurbishment of E.T.A. From Sesimbra for Installation of Pre-Oxidation, Filtering and Distribution Stages | 45232100-3 | Ancillary works for water pipelines | FALSE | 2018 | 2019 | Portugal | Sesimbra | Setúbal | 17 | 20 | 04-10-2018 | 18-11-2019 | 410 | 160 | 126700 | 125738 | 1 | 125738 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: QTP, Pr Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | date of the final account of the contract
2346 | 4936241 | Cp/01/dom/2018 - "rehabilitation of a building at the olive creative factory" | 45210000-2 | Building construction work | FALSE | 2018 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 16-07-2018 | 26-02-2021 | 956 | 150 | 120000 | 119513.11 | 1 | 127781.13 | -8268.02 | 93.5295 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | verification of the need to study changes to be introduced to the project | complementary works
2347 | 4936027 | Cp/03/dom/2018 - "rehabilitation of the pedestrian area floor - phase c" | 45112700-2 | Landscaping work | FALSE | 2018 | 2019 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 12-09-2018 | 08-04-2019 | 208 | 180 | 250000 | 226811.1 | 1 | 220440.7 | 6370.4 | 102.8898 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project proceeded normally within the execution period of the project | job suppression
2348 | 4933520 | Execution of the contract for the requalification of the Sports Pavilion - Vizela High school. | 45210000-2 | Building construction work | FALSE | 2018 | 2021 | Portugal | Vizela | Braga | 3 | 11 | 07-11-2018 | 12-07-2021 | 978 | 45 | 216958.87 | 216950 | 1 | 216950 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extension
2349 | 4933449 | CP/02/Sun/2018 - Replacement of fiber cement roofing | 45210000-2 | Building construction work | FALSE | 2018 | 2019 | Portugal | São João da Madeira | Aveiro | 1 | 15 | 30-07-2018 | 25-07-2019 | 360 | 150 | 350000 | 288296.85 | 2 | 288296.85 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension by the owner of the project to carry out tests at the paulo pinto pavilion
2350 | 4933107 | Public Tender 263/2018 - Contract for Replacement of the roof of the MF Headquarters Building (Government Archive and Area) for the conservation and maintenance of the roofing | 45453100-8 | Refurbishment work | TRUE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 21-09-2018 | 31-12-2018 | 101 | 120 | 331706 | 217306.62 | 1 | 217306.62 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2351 | 4932673 | Public Tender for the contract for the construction of Trenches. | 45232452-5 | Drainage works | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 31-10-2018 | 02-05-2019 | 183 | 60 | 100000 | 94062.5 | 1 | 94062.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
2352 | 4932461 | Contract for the installation of a SCIE project at the Centro Hospitalar Psiquiátrico de Coimbra .- Sobral Cid Unit | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Coimbra | Coimbra | 6 | 21 | 15-10-2018 | 14-10-2019 | 364 | 150 | 295100 | 253649.58 | 2 | 269587.78 | -15938.2 | 94.0879 | Best value for money: No Criterion related to quality Name: N/A Weighting: N/A Criterion related to cost Name: N/A Weighting: N/A | 0 | 0 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in provisional acceptance due to the marking of the certification by the anpc. | errors and omissions not foreseen in the contract.
2353 | 4928967 | Public Tender No. 25/DRL/DA/2018 - Repaving of Parade and streets in the Territorial Command of Bragança | 71000000-8 | Architectural, construction, engineering and inspection services | FALSE | 2018 | 2018 | Portugal | Bragança | Bragança | 4 | 14 | 20-09-2018 | 05-11-2018 | 46 | 45 | 90000 | 90000 | 1 | 90000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to register
2354 | 4927137 | Cpn 18/2018/dicp - t-07/2018 - improvement of several streets in the urbanization of telheiro - union of parishes of leiria, landings, barrier and cuts | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 28 | 30-10-2018 | 02-01-2019 | 64 | 150 | 149982.85 | 126414.4 | 1 | 126414.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: 0 Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no deadline changes | there were no changes
2355 | 4926121 | Contract to redesign the exterior lighting of the Alcoitão Medicine and Rehabilitation Center | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2018 | 2019 | Portugal | Cascais | Lisboa | 11 | 21 | 23-10-2018 | 15-05-2019 | 204 | 75 | 190000 | 143767.97 | 1 | 143767.97 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no extension of the period for carrying out the project.
2356 | 4924166 | Public works contract for repaving the ESEP HEADQUARTERS car park | 45233251-3 | Resurfacing works | FALSE | 2018 | 2018 | Portugal | Porto | Porto | 13 | 17 | 07-08-2018 | 08-10-2018 | 62 | 30 | 80000 | 57819.73 | 1 | 61827.86 | -4008.13 | 93.5173 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Non-fulfilment of the contract (Contract Termination) | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the painting implies the unavailability of access to the park, which would condition the normal opening of the school year. its execution was agreed for a day without activities.
2357 | 4920692 | 2013.178.01.C1 - Polo de Lagos - Infrastructure refurbishment and adaptation of training spaces | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Lagos | Faro | 8 | 20 | 06-09-2018 | 18-11-2019 | 438 | 120 | 349000 | 326500 | 2 | 326500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no data
2358 | 4919302 | Trafaria Primary School - Avª 25 de Abril - Outdoor Covered Spaces | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 24 | 14-09-2018 | 29-10-2019 | 410 | 150 | 95075.81 | 92954.53 | 1 | 99281.19 | -6326.66 | 93.6275 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 45% Criterion related to cost Name: Bid price Weighting: 55% | 1 | 55 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in work. | additional work
2359 | 4918208 | EGA-AR0320 - Contract for Execution of Mesão Frio Elevator System | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Mesão Frio | Vila Real | 19 | 24 | 30-01-2018 | 15-03-2019 | 409 | 84 | 220000 | 197725.15 | 1 | 186287.54 | 11437.61 | 106.1398 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to wait for edp to provide the necessary electrical power boost for the operation of the new hydropressor group | settlement of quantities of work performed
2360 | 4917236 | Execution and reformulation of road sections, including the construction of an underpass (“Box-Culvert”), retaining walls, drainage, public lighting, water and sewage and landscaping. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2020 | Portugal | Coimbra | Coimbra | 6 | 24 | 04-04-2018 | 16-04-2020 | 743 | 240 | 492045 | 487994.06 | 2 | 481512.72 | 6481.34 | 101.346 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | gracious term extension | work not performed and price revision value
2361 | 4916637 | Pragal Urban Park - South Access | 45262522-6 | Masonry work | TRUE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 24 | 22-10-2018 | 28-08-2019 | 310 | 180 | 279875.71 | 238313.6 | 1 | 238313.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Proposed Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2362 | 4913535 | Repairs to Social Housing Properties Owned by the Municipality of Portalegre - Phase II | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2018 | 2020 | Portugal | Portalegre | Portalegre | 12 | 20 | 24-10-2018 | 19-10-2020 | 726 | 240 | 256667.5 | 252710 | 2 | 256130.89 | -3420.89 | 98.6644 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to an eviction action that took place in one of the properties | there was underwork and price revision
2363 | 4912503 | Contract for Smooth Access to the Boavista School | 45262310-7 | Reinforced-concrete work | FALSE | N/A | 2020 | Portugal | Arouca | Aveiro | 1 | N/A | 29-10-2018 | 28-10-2020 | 730 | 270 | N/A | 521736.9 | 2 | 642147.41 | -120410.51 | 81.2488 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | verification of the impossibility of maintaining the bridge abutment, which made the execution of the initial project unfeasible. | occurrence of complementary work resulting from unforeseen circumstances and unforeseen circumstances (article 373(4) and (2) of the "public procurement code").
2364 | 4909766 | Installation of a heat pump at the Luís de Camões School Center - União das parishes of V. N. De Famalicão and Calendar | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2018 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 24-10-2018 | 31-01-2019 | 99 | 45 | 65352.91 | 54582.57 | 1 | 54582.57 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2365 | 4909602 | The object of this contract is the construction of the water reservoir to reinforce the supply to the airfield on the island of Graciosa, with a view to providing this airport infrastructure with a system | 45213330-5 | Construction work for buildings relating to air transport | FALSE | 2018 | 2019 | Portugal | Santa Cruz da Graciosa | Região Autónoma dos Açores | 15 | 33 | 12-10-2018 | 15-10-2019 | 368 | 300 | 285000 | 284950 | 2 | 284950 | 0 | 100 | most economically advantageous proposal If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) The award is made according to the criterion of the most economically advantageous proposal, dedeadlineined for the modality with the best price-quality ratio, considering the factors submitted to competition that are indicated below with the mention of the respective weights: K1 - Price: 60 % 🇧🇷 K2 - Technical Quality of the Proposal: 40% K = (0.60 x k1) + (0.40 x K2); K2 - Densification of the Quality Factor Proposal Technique (40%) and respective Partial Score: This factor is subdivided into two sub-factors, with the following weighting: K2.1 - Work Plan: 60%; K2.2 - Descriptive and Justification Work Execution Mode: 40%; K2 = (0.60 x K2.1) + (0.40 x K2. two). | 1 | 60 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | not verified | not verified
2366 | 4909361 | Construction and Conservation of Urban Infrastructures - Requalification of Pavements and Complementary Works in the Riverside Area of ​​Ponte de Sor | 45233251-3 | Resurfacing works | FALSE | 2018 | 2021 | Portugal | Ponte de Sor | Portalegre | 12 | 15 | 29-08-2018 | 09-09-2021 | 1107 | 30 | 57000 | 54820.5 | 1 | 54820.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2367 | 4908859 | Reformulation of the University Avenue Junction (ISCA-UA) | 45233128-2 | Roundabout construction work | FALSE | 2018 | 2019 | Portugal | Aveiro | Aveiro | 1 | 23 | 09-10-2018 | 17-10-2019 | 373 | 180 | 254000 | 228000 | 1 | 244440.25 | -16440.25 | 93.2743 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work and deadline extension | underwork and more work
2368 | 4906420 | PRC_0184/2018_GAE-AA0395 - Work contract for supplying Agilde and Borba da Montanha (Celorico de Basto) - SAA Queimadela | 45232150-8 | Works related to water-distribution pipelines | TRUE | 2018 | 2020 | Portugal | Celorico de Basto | Braga | 3 | 30 | 11-10-2018 | 29-05-2020 | 596 | 140 | 500000 | 434206.19 | 2 | 401454.08 | 32752.11 | 108.1584 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the need to combine the contract works with infrastructures in service, being crucial not to affect the functioning of the existing network, conditioned the projects | underwork due to optimization of the intended solution according to system exploitation.
2369 | 4905954 | Sanitation and Paving in Picoitos | 45232460-4 | Sanitary works | FALSE | 2017 | 2021 | Portugal | Mértola | Beja | 2 | 30 | 18-10-2018 | 15-07-2021 | 1001 | 315 | 1140000 | 989030.88 | 2 | 914006.07 | 75024.81 | 108.2083 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unavailability/difficulty in mobilizing human resources and guaranteeing the supply of materials on site, aggravated by the pandemic situation, delays in connecting electrical infrastructure and supplying electricity. | underwork
2370 | 4905878 | Public Tender for the execution of the access ramp to the canteen of EB 1 of Avª do Ténis | 45454000-4 | Restructuring work | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 19-10-2018 | 07-10-2020 | 719 | 70 | 175732.04 | 169300.35 | 1 | 178879.58 | -9579.23 | 94.6449 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | legal extension of the deadline 45 days, ramp (to be built) and the fence wall and street sidewalk (existing), being implanted in a landfill area, being necessary to build an additional wall | complementary works and suppressed works
2371 | 4903371 | 2017.158.06.C1 - SFP Évora - Pavilion 1 - completion of the two interventions | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Évora | Évora | 7 | 17 | 06-09-2018 | 30-05-2019 | 266 | 120 | 147000 | 146999 | 1 | 146999 | 0 | 100 | Best value for money: No Criterion related to quality Name: Technical Valia Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work coordination
2372 | 4902558 | Public Tender for the contract to integrate wastewater pumping stations into the remote management system. | 45232470-7 | Waste transfer station | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 21-09-2018 | 23-09-2020 | 733 | 150 | 195000 | 141975.04 | 1 | 141975.04 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2373 | 4902075 | Pedestrian path between Av. Camilo Tavares de Matos, Town Hall and S. P. Castelões | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 05-07-2018 | 10-10-2019 | 462 | 180 | 383620.01 | 357525 | 2 | 326604.91 | 30920.09 | 109.4671 | Best value for money: No Criterion related to quality Name: Not Applicable Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in article 74, paragraph 1, al. B) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2374 | 4900752 | Conservation and rehabilitation of the church of s. Peter (iti) - Leiria | 45454100-5 | Restoration work | FALSE | 2018 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 23-10-2018 | 30-09-2019 | 342 | 270 | 185679.86 | 179991.08 | 1 | 179991.08 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2375 | 4898432 | 2018/300.10.001/37 - Public Tender - Contract for the Remodeling of the Water Network and Domestic Wastewater Drainage Network on Ladeira de São Bento. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2020 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 15 | 15-10-2018 | 16-04-2020 | 549 | 150 | 140000 | 118998.73 | 1 | 119925.54 | -926.81 | 99.2272 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unforeseeable circumstances during the execution phase of the project. | contract price = €118,998.73; uncompleted contractual work = -2,688.52 €; complementary work = €3,882.76; price revision = -267.42 €.
2376 | 4898259 | Repair and conversion to LED light fixtures in the Costa Polis area in Costa de Caparica and Cacilhas | 45316100-6 | Installation of outdoor illumination equipment | TRUE | 2018 | 2019 | Portugal | Almada | Setúbal | 17 | 8 | 11-09-2018 | 08-05-2019 | 239 | 90 | 125850 | 114300 | 1 | 114300 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay of works.
2377 | 4898056 | Generic Works in Public Space | 45233140-2 | Roadworks | FALSE | 2018 | 2019 | Portugal | Loures | Lisboa | 11 | 21 | 14-08-2018 | 22-07-2019 | 342 | 760 | 330188.68 | 330188.68 | 2 | 330188.68 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Unweighted Weighting: 0% Criterion related to cost Name: Point 17 of the Tender Program Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | exhaustion of the budget before the end of the term - 760 days - ended on 09/14/2020
2378 | 4896093 | Repaving of the municipal road 1355 - executioner | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Silves | Faro | 8 | 30 | 24-09-2018 | 05-06-2020 | 620 | 60 | 187868.75 | 162336.77 | 1 | 171818.86 | -9482.09 | 94.4813 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no references | execution of complementary works in the amount of €8,465.07 and price revision in the amount of €1,017.02
2379 | 4895519 | Application of Microagglomerate at CM 1150 between Urra and Assumar and at other locations in the Municipality | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Portalegre | Portalegre | 12 | 14 | 18-10-2018 | 13-03-2019 | 146 | 90 | 126000 | 103850.49 | 1 | 93983.36 | 9867.13 | 110.4988 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change in the execution period of the project | underwork worth €9867.13 were approved
2380 | 4893281 | PRC_0186/2017_GAE - EGA-AA0345 - S. Jorge Water Supply Subsystem. Vilar de Lobos, Vilarinho do Souto, Ermelo and Vale Reservoirs and Respective Supply Connections | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 47 | 09-10-2018 | 30-08-2020 | 691 | 365 | 2500000 | 2477280.86 | 3 | 2359891.19 | 117389.67 | 104.9744 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50%; Technical value of the proposal - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays by the contracting authority, essentially due to a shortage of labour and due to the covid-19 pandemic. delays by the energy supply company (edp) in the execution of the extensions to the built infrastructures, which greatly delayed the start of operations. | suppression of works and works not foreseen in ermelo, dealt with in the objective modification to the contract entered into between the parties.
2381 | 4891340 | Conservation works in the WWTP | 45213000-3 | Construction work for commercial buildings, warehouses and industrial buildings, buildings relating to transport | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 12 | 15-03-2017 | 22-10-2018 | 586 | 90 | 268000 | 181584.69 | 1 | 223580.84 | -41996.15 | 81.2166 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: As mentioned in point 16 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the execution period of the project was strongly conditioned by the need to keep the wwtp in operation, guaranteeing treatment levels during the course of the projects. | during the course of the projects, some circumstances were verified that were not foreseen in the project, but necessary for the proper execution of the projects.
2382 | 4891140 | Preventive Intervention in Pavements 2018 - Centro Operacional Sul Center (7 lots) - (E-contracts 5010036884) | 45233142-6 | Road-repair works | FALSE | 2018 | 2020 | Portugal | Nisa | Leiria | 10 | 9 | 24-09-2018 | 20-02-2020 | 514 | 90 | 4780000 | 647479.13 | 2 | 650298.88 | -2819.75 | 99.5664 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | adjustment of quantities and deletion of a job due to impossibility of execution.
2383 | 4890235 | Repair works and interior adaptations at Escola Infante D.Henrique to create the minimum conditions to receive EB Bom Sucesso students - Phase 2 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 15 | 28-09-2018 | 04-01-2019 | 98 | 60 | 200000 | 199016.78 | 1 | 199016.78 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | an inspection was carried out on 11/30/2018 for the purpose of provisional acceptance, this inspection found anomalies and 15 days were given to make the necessary corrections.
2384 | 4886529 | Paving street of Vilarinho, street of Agra and street of Sub-Carreira - U.F. From Tagilde and Vizela (S. Paio) - PPI: 15/2018 - Lot 1;-Repaving of street of Nora - Parish of Sta. Eulalia - | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2018 | Portugal | Vizela | Braga | 3 | 15 | 09-10-2018 | 30-11-2018 | 52 | 35 | 203944.32 | 49582.45 | 1 | 44013.79 | 5568.66 | 112.6521 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | the project was carried out within the established time frame. | underwork.
2385 | 4886472 | Paving street of Vilarinho, street of Agra and street of Sub-Carreira - U.F. From Tagilde and Vizela (S. Paio) - PPI: 15/2018 - Lot 1;-Repaving of street of Nora - Parish of Sta. Eulalia | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2019 | Portugal | Vizela | Braga | 3 | 15 | 09-10-2018 | 29-03-2019 | 171 | 35 | 203944.32 | 114405.6 | 1 | 114405.6 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | weather and security reasons
2386 | 4886364 | Requalification of the surroundings of the Primary School of São João da Pesqueira | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | São João da Pesqueira | Viseu | 20 | 12 | 04-09-2018 | 28-10-2019 | 419 | 60 | 155432.48 | 151301.07 | 1 | 151301.07 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project had three extensions of time requested by the contractor, for reasons related to the final works to close the project, it was convenient to carry out the provisional reception after the end date of the project plan and with the delivery of the management plan of waste | the project had three extensions of time requested by the contractor, for reasons related to the final works to close the project, it was convenient to carry out the provisional reception after the end date of the project plan and with the delivery of the management plan of waste
2387 | 4886354 | Requalification of the Sé Kindergarten | 45214200-2 | Construction work for school buildings | FALSE | 2018 | 2020 | Portugal | Guarda | Guarda | 9 | 18 | 17-10-2018 | 30-03-2020 | 530 | 75 | 153594.62 | 137276.86 | 1 | 156273.52 | -18996.66 | 87.844 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existence of extension of term. the contract ended on 01/21/2019, as stated in the project book. | existence of complementary work
2388 | 4885604 | Demolition of the signal tower in the fishing port of Olhão | 45111100-9 | Demolition work | FALSE | 2018 | 2019 | Portugal | Olhão | Faro | 8 | 14 | 18-09-2018 | 09-01-2019 | 113 | 60 | 99000 | 85631.51 | 1 | 85631.51 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Price Weighting: 60% Criterion related to cost Name: Technical quality of the proposal Weighting: 40% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2389 | 4885164 | Requalification ofelementary school from bonfim | 45214200-2 | Construction work for school buildings | FALSE | 2018 | 2020 | Portugal | Guarda | Guarda | 9 | 18 | 17-10-2018 | 30-03-2020 | 530 | 75 | 109405.6 | 73986.85 | 1 | 77951.44 | -3964.59 | 94.914 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | despite the provisional acceptance notice being dated 01/22/2019, the contract ended on 01/07/2019, as stated in the project book. | existence of complementary work
2390 | 4884291 | Urban Enhancement and Reconversion Contract (street of Baluarte/Avenida das Comunidades Portuguesas) | 45223300-9 | Parking lot construction work | FALSE | 2018 | 2020 | Portugal | Lagos | Faro | 8 | 32 | 12-10-2018 | 02-12-2020 | 782 | 120 | 180000 | 174041.48 | 1 | 182546.44 | -8504.96 | 95.3409 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the period for execution of the project, for another 90 days, by way of grace, by order of mrs. president of the chamber, dr. joaquina matos from 03/26/2019 | approval of the proposal for the correction of errors and omissions in the amount of €8,516.43 plus vat, and acceptance of underwork in the amount of €2,498.88, plus vat, by order of mrs. president of the chamber dr. joaquina matos from 05/21/2019. determined the final value of price revision in the amount of € 2,487.41, plus vat
2391 | 4883480 | Replacement of the Automatic Fire Extinguishing System in the Paços do Concelho Building | 45343000-3 | Fire-prevention installation works | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 30 | 03-10-2018 | 16-01-2019 | 105 | 60 | 88000 | 52943.38 | 1 | 52943.38 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | the project on the contract proceeded normally, in accordance with what was specified in the tender specifications and without incidents worth mentioning.
2392 | 4883450 | Contract to repave paths in the parish of Ferreiras. | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 17-10-2018 | 11-03-2019 | 145 | 60 | 610000 | 413520.5 | 2 | 413520.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
2393 | 4883305 | Correction of the Automatic Extinguishing and Fire Detection System in Ed. Post Office Palace | 45343200-5 | Firefighting equipment installation work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 30 | 12-09-2018 | 03-06-2019 | 264 | 60 | 50000 | 33051.03 | 1 | 33051.03 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the projects took place within the contractually foreseen.
2394 | 4882329 | Execution of the Dog Park in Forca-Vouga | 45112723-9 | Landscaping work for playgrounds | FALSE | 2018 | 2019 | Portugal | Aveiro | Aveiro | 1 | 21 | 15-10-2018 | 17-10-2019 | 367 | 90 | 33341.09 | 26912.48 | 1 | 27872.08 | -959.6 | 96.5571 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | auto suspend and auto restart | complementary works
2395 | 4881857 | Construction contract for the Recreational and Leisure Park - Mãe de Deus | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Vila Franca do Campo | Região Autónoma dos Açores | 15 | 32 | 11-09-2018 | 29-11-2019 | 444 | 180 | 280000 | 275033.5 | 2 | 331075.75 | -56042.25 | 83.0727 | most economically advantageous proposal If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) They are those contained in the item (Award Criteria) of the Tender Program | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions (hurricane leslie) and expansion of the campo de jogos area. | increased game platform (infrastructures and synthetic floor)
2396 | 4880082 | Construction of the Freixiosa WWTP and the Chãs de Tavares WWTP | 45232421-9 | Sewage treatment works | FALSE | 2018 | 2021 | Portugal | Mangualde | Viseu | 20 | 20 | 14-08-2018 | 16-07-2021 | 1067 | 365 | 271000 | 268309.11 | 2 | 259880.72 | 8428.39 | 103.2432 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: non-existent Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | according to information in the process | according to information in the process
2397 | 4877924 | Contract to repave paths in the parish of Albufeira and Olhos de Água | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 2 | 12-10-2018 | 26-07-2019 | 287 | 60 | 610000 | 449351.9 | 2 | 449351.9 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the execution period of the project is due to delays on the part of the contractor.
2398 | 4877499 | Manhole Rehabilitation Contract - Pólo Ria | 45262330-3 | Concrete repair work | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | N/A | 20-09-2018 | 13-05-2020 | 601 | 455 | 400000 | 389283.72 | 2 | 216419.19 | 172864.53 | 179.8749 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Revocation of the Contract) | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | revocation of the contract (05/13/2020) | contract revocation
2399 | 4877460 | Contract to repave paths in the parish of Paderne. | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 2 | 12-10-2018 | 10-05-2019 | 210 | 60 | 610000 | 370484 | 2 | 370484 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the deadline are due to delays on the part of the contractor
2400 | 4877372 | Requalification of Largo do Ribeirinho, street Dr. Elias de Aguiar and Joaquim Maria de Melo - Vila do Conde | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Vila do Conde | Porto | 13 | 15 | 02-10-2018 | 30-11-2020 | 790 | 274 | 350000 | 303035.5 | 2 | 303955.62 | -920.12 | 99.6973 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2401 | 4876183 | Contract work for paving in bituminous concrete on the Rural Path of Caldeira Rasa - Terreiros, parishes of Mosteiro and Fajãzinha, council of Lajes das Flores, island of Flores | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Lajes das Flores | Região Autónoma dos Açores | 15 | 20 | 03-09-2018 | 25-10-2019 | 417 | 210 | 350000 | 337450 | 2 | 347270.56 | -9820.56 | 97.1721 | The most economically advantageous proposal in deadlines of the best quality-price ratio, in which the award criterion is composed of the set of factors and any sub-factors contained in the Annex IV of the tender procedure program. PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 75 TUESDAY, APRIL 17, 2018 🇧🇷 | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the deadline for carrying out the project. | complementary works
2402 | 4876012 | Contract to repave paths in the parish of Guia. | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 12-10-2018 | 29-07-2019 | 290 | 60 | 610000 | 388670.3 | 2 | 371943.3 | 16727 | 104.4972 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor. | the effective value of the project reflects the total work carried out.
2403 | 4876002 | Construction of the Rehabilitation of Basic Sanitation Infrastructures in Feteira Pequena- Parish of Santana | 90000000-7 | Sewage-, refuse-, cleaning-, and environmental services | FALSE | 2017 | 2021 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 36 | 28-05-2018 | 04-08-2021 | 1164 | 180 | 730000 | 543575.61 | 2 | 472825.8 | 70749.81 | 114.9632 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: In accordance with article 12 of the contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | restrictions imposed due to the pandemic situation | underwork
2404 | 4874158 | Domestic Sanitation in Vidoeira, Gracieira, Fétil and Vila Gateira - Proc. No. 05/2017 | 45232400-6 | Sewer construction work | FALSE | 2017 | 2020 | Portugal | Pombal | Leiria | 10 | 30 | 15-05-2017 | 03-08-2020 | 1176 | 270 | 695394 | 509659.54 | 2 | 512163.54 | -2504 | 99.5111 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the causes for the delay in the above-mentioned contract were due to constraints in access to work on the installation of collectors on private land and in the stabilization of ditches for full paving of roads. | price revision value.
2405 | 4874077 | Enlargement and Improvement of street of Carvalhos, parish of Avanca, in the municipality of Estarreja | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Estarreja | Aveiro | 1 | 15 | 04-10-2018 | 09-12-2019 | 431 | 120 | 92492.91 | 72864.81 | 1 | 74654.86 | -1790.05 | 97.6022 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of works | price review
2406 | 4872810 | Replacement of the water distribution networks in the western sector of Funchal - Fiber cement network on the Caminho de são Roque and surrounding areas | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2020 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 31 | 10-10-2018 | 31-01-2020 | 478 | 270 | 684693 | 571650.6 | 2 | 489037.22 | 82613.38 | 116.8931 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were 48 days of authorized deadline extensions and 35 days due to various suspensions caused by adverse weather conditions. | underwork caused due to the type of work the measurements taken on site differ from the design measurements
2407 | 4872755 | Requalification of the Águeda River Bed Section and Weed Cleaning | 45112710-5, 45112200-7 | Landscaping work for green areas, Soil-stripping work | FALSE | 2018 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 21-09-2018 | 27-04-2020 | 584 | 90 | 265676.04 | 159405.63 | 1 | 159613.33 | -207.7 | 99.8699 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline was due to the need to carry out several total and partial suspensions of the projects on the contract due to the fact that the weather conditions did not allow the execution of the projects in the necessary safety conditions | the change in the value of the project was residual and refers only to work not carried out related to the presentation of final screens.
2408 | 4872731 | Contract for the Requalification and Improvement of the North area of ​​the City - connection of street Eng. António Campos to the Municipal Market, Bus Station, Volunteer Firefighters and Avª Carlos Campos | 45233200-1 | Various surface works | FALSE | 2018 | 2020 | Portugal | Oliveira do Hospital | Coimbra | 6 | 18 | 12-10-2018 | 01-09-2020 | 690 | 180 | 751000 | 715669.37 | 2 | 721458.21 | -5788.84 | 99.1976 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Criterion of the most economically advantageous proposal in the lowest price modality. Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | non-compliance with the contract term. | less and more work.
2409 | 4871157 | Contract for Access in Smooth Modes to the Center of Resumil - Fermedo | 45233160-8 | Paths and other metalled surfaces | FALSE | 2018 | 2019 | Portugal | Arouca | Aveiro | 1 | 30 | 11-10-2018 | 13-03-2019 | 153 | 122 | 144633.8 | 122898.5 | 1 | 121838.7 | 1059.8 | 100.8698 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or Cost as the only aspect of the execution of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | auto final carried out on march 8, 2019 | underwork
2410 | 4870428 | Public Tender for the Maintenance Contract for Stairs, Mooring Bollards and Fenders of the Solid Bulk Terminal | 45442121-1 | Painting work of structures | FALSE | 2018 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 42 | 10-10-2018 | 03-04-2020 | 541 | 75 | 59000 | 58693 | 1 | 56669.1 | 2023.9 | 103.5714 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | suppression
2411 | 4868329 | Pombal Biopark – Charneca Urban Park – Proc. No. 35/2017 | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 29-11-2017 | 12-11-2021 | 1444 | 180 | 299904.42 | 298915.62 | 2 | 304120.59 | -5204.97 | 98.2885 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to contact all the owners of the adjacent land for the opening of the access services, as well as the weather conditions caused by the heavy rainfall and the high water table in the area, making it impossible to carry out some works, delaying the end of the project. | price revision amount.
2412 | 4868317 | Flooring in the Parish of Lorvão - Improvement of the main streets of São Mamede | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Penacova | Coimbra | 6 | 6 | 10-11-2016 | 12-09-2018 | 671 | 240 | 547617.28 | 546999.99 | 2 | 475193.38 | 71806.61 | 115.111 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | at the end of the execution period of the project, an inspection was carried out where it was verified that the projects of the contract were fully concluded. however, there was a need to clean the entire rainwater network in order to remove all waste resulting from paving work, cleaning and repairing damage caused to private properties, verifying by video inspection the state of operation of the existing sewage network , deliver waste guides, present results of tests carried out, etc. | existence of underwork and price revision
2413 | 4868270 | 2018/107 - DGEP - Conservation and repair of road pavements in Oeiras and Paço de Arcos | 45233140-2 | Roadworks | FALSE | 2018 | 2021 | Portugal | Oeiras | Lisboa | 11 | 15 | 04-10-2018 | 22-03-2021 | 900 | 365 | 299294.1 | 268369.9 | 2 | 268369.9 | 0 | 100 | Best value for money: No Criterion related to quality Name: . Weighting: 0% Criterion related to cost Name: . Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2414 | 4868035 | Construction of walkways and bridge at Penedo Furado | 45246510-1 | Boardwalk construction work | FALSE | 2018 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 10-10-2018 | 26-03-2019 | 167 | 122 | 100000 | 90484 | 1 | 90484 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline has been met, extension until 14.03.2019
2415 | 4867236 | Public Tender for the contract for the requalification of the storm drain at Praia da Oura | 45232454-9 | Rain-water basin construction work | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 08-10-2018 | 14-11-2019 | 402 | 60 | 69090.54 | 66578.7 | 1 | 66578.7 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays by the contractor
2416 | 4866939 | Parish of Pombal / Asphalting of Roads and Paths in the Parish (Guístola - Ponte de Assamaça, Pousios - Cumieira, Outeiro Galegas, Escoural and Melga) - Proc. No. 10/2018 | 45233220-7 | Surface work for roads | FALSE | 2018 | 2021 | Portugal | Pombal | Leiria | 10 | 24 | 31-07-2018 | 18-10-2021 | 1175 | 90 | 144170.62 | 121479.04 | 1 | 128222.59 | -6743.55 | 94.7407 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the delay in the contract refers to the clearance of all works carried out by the contractor, recorded in the measurement report after the end of the project term. in accordance with the provisions of article 390 of the "public procurement code", measurement errors, faults were detected in the previously drawn up measurement records, which were corrected and replaced in the subsequent measurement report, in collaboration with the contractor in relation to the object and the quantities to be corrected. this work has the provisional reception on 02/12/2019 due to the fact that it was only on that date that the contractor verbally requested it to the inspection in accordance with article 394 of the "public procurement code", when he delivered the duly completed rcd plan, and the inspection and signed the auto. | existence of price revision.
2417 | 4866792 | Improvement of street of Cabanas - Fânzeres | 45233222-1 | Paving and asphalting works | FALSE | 2018 | 2019 | Portugal | Gondomar | Porto | 13 | 22 | 26-07-2018 | 04-01-2019 | 162 | 120 | 206909.89 | 171620.19 | 1 | 162646.01 | 8974.18 | 105.5176 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension due to difficult weather conditions. | the value of the contract was less than the value of the award.
2418 | 4866599 | Improvement of the Municipal Library and Auditorium (Requalification) - Proc. No. 12/2018 | 45000000-7 | Construction work | FALSE | 2018 | 2021 | Portugal | Pombal | Leiria | 10 | 30 | 28-08-2018 | 24-08-2021 | 1092 | 180 | 306380.96 | 279470.24 | 2 | 282707.24 | -3237 | 98.855 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out on time, the provisional acceptance was requested by the contractor, verbally, to the inspection taking into account the end of the project, and the inspection for the purposes of provisional acceptance was carried out as soon as possible by the parties on the earliest date after the completion of the project, and on the inspection date the provisional acceptance document was drawn up and signed. | existence of price revision value.
2419 | 4866374 | Contract nº 23/18 - Execution of Works to Consolidate Support Walls on Public Roads | 45262310-7 | Reinforced-concrete work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 15 | 01-10-2018 | 25-03-2020 | 541 | 364 | 197975 | 168278.76 | 1 | 168278.76 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | atmospheric conditions, technical characteristics of the drying time of reinforced concrete, delays in the delivery of materials and time for scheduling an inspection to prepare the provisional acceptance notice.
2420 | 4866302 | 2018.451.01.C1 - Quarteira service counter - facilities refurbishment | 45000000-7 | Construction work | TRUE | 2018 | 2018 | Portugal | Loulé | Faro | 8 | 21 | 04-07-2018 | 31-10-2018 | 119 | 75 | 49500 | 48169.21 | 1 | 48169.21 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Bid price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed before the deadline.
2421 | 4866081 | Acquisition, Construction and Maintenance of Buildings - School Buildings - Execution of Exterior Roofing at the elementary school of Ponte de Sor | 45261213-0 | Metal roof-covering work | FALSE | 2018 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 6 | 25-09-2018 | 28-02-2019 | 156 | 30 | 44857.75 | 43413.21 | 1 | 43413.21 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal dedeadlineined by the lowest price modality Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the works related to this contract were completed during the contractually defined period. the time lapses recorded are only due to delays in the request for provisional acceptance by the contractor.
2422 | 4865712 | Water Network to Várzea do Homem | 45000000-7 | Construction work | FALSE | 2018 | 2021 | Portugal | Tondela | Viseu | 20 | 6 | 27-09-2018 | 18-11-2021 | 1148 | 240 | 205097 | 200210.11 | 1 | 167855.92 | 32354.19 | 119.275 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the project underwent changes in execution deadlines due to suspensions. | the project underwent changes in the execution value due to underwork and price revisions.
2423 | 4863021 | Improvement of the Pedestrian Paths Network of Vila de Boticas - Phase II | 45233251-3 | Resurfacing works | FALSE | 2018 | 2020 | Portugal | Boticas | Vila Real | 19 | 14 | 03-10-2018 | 05-06-2020 | 611 | 90 | 122700 | 116634.3 | 1 | 116634.3 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 30% Criterion related to cost Name: Price Weighting: 70% | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2424 | 4861869 | Public Tender for the Construction Works for the Implementation of the Bike Path of the Cycling Network in the City of Covilhã | 45233162-2 | Cycle path construction work | FALSE | 2018 | 2021 | Portugal | Covilhã | Castelo Branco | 5 | 30 | 01-10-2018 | 02-09-2021 | 1067 | 150 | 344235 | 294836.33 | 2 | 306946.78 | -12110.45 | 96.0545 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes.
2425 | 4860307 | Extension of the Cemetery of Ade | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Almeida | Guarda | 9 | 18 | 04-10-2018 | 26-06-2020 | 631 | 120 | 64514.7 | 38725.94 | 1 | 35632.86 | 3093.08 | 108.6804 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The most economically advantageous proposal, as provided for in paragraph b) of paragraph 1 of article 74 Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contractor's responsibility | underwork and price revision
2426 | 4860155 | Paving of the Fuste Access Road - Moldes | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Arouca | Aveiro | 1 | 14 | 08-10-2018 | 01-03-2019 | 144 | 30 | 116650 | 96750 | 1 | 96750 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension
2427 | 4858579 | Paving contract for the link between Caminho dos Brejos and Poço de Paderne. | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 13 | 26-09-2018 | 18-07-2019 | 295 | 90 | 600000 | 395179.97 | 2 | 395179.97 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the execution period of the project is due to delays on the part of the contractor
2428 | 4857905 | Paving streets and paths in Vale de Margin and Benagaia | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Silves | Faro | 8 | 30 | 06-09-2018 | 17-11-2020 | 803 | 61 | 118550.5 | 101415.42 | 1 | 106428.68 | -5013.26 | 95.2896 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without references | due to price revision
2429 | 4857699 | Troubleshooting and Maintenance at BMEL | 45259000-7 | Repair and maintenance of plant | FALSE | 2018 | 2020 | Portugal | Guarda | Guarda | 9 | 20 | 03-10-2018 | 30-03-2020 | 544 | 120 | 197144.55 | 179749.34 | 1 | 196371.26 | -16621.92 | 91.5355 | Best value for money: No Criterion related to quality Name: Not Applicable Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | due to adverse weather conditions, the deadline was extended by 32 days. | existence of complementary work, underwork and price revision
2430 | 4856540 | Acquisition of Equipment and Works | 33100000-1 | Medical equipments | FALSE | 2018 | 2018 | Portugal | Barcelos | Braga | 3 | 19 | 07-09-2018 | 24-12-2018 | 108 | 60 | 350000 | 305656.45 | 2 | 305656.45 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
2431 | 4855604 | Public tender for the conclusion of the contract for ""construction contract for the construction of a support tower and command module for the installation and operation of a 15-meter paraboloid antenna"" | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | 24 | 28-09-2018 | 30-09-2019 | 367 | 150 | 626650 | 575000.01 | 2 | 591751.97 | -16751.96 | 97.1691 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension requests made by the contractor | the value of the project reflects the underwork and the replacement of the financial rebalancing
2432 | 4854045 | Quality 100% - Public Tender for bituminous paving of streets in 2018 - Union of Parishes of São Mamede de Infesta and Senhora da Hora | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 02-10-2018 | 12-03-2019 | 161 | 61 | 330000 | 271781.23 | 2 | 271781.23 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2433 | 4853647 | Improvement of the Baságueda Dam | 45112000-5 | Excavating and earthmoving work | FALSE | 2018 | 2019 | Portugal | Penamacor | Castelo Branco | 5 | 15 | 28-09-2018 | 18-01-2019 | 112 | 180 | 476855.77 | 197494.34 | 1 | 197494.34 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work completed on december 6, 2018.
2434 | 4853588 | Preventive Intervention on Pavements 2018 - South Operational Center (4 Lots) E-contracts 5010036882 | 45233142-6 | Road-repair works | FALSE | 2018 | 2020 | Portugal | Évora | Beja | 2 | 30 | 27-09-2018 | 13-05-2020 | 594 | 90 | 3145000 | 687110.9 | 2 | 661215.33 | 25895.57 | 103.9164 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | the change in the value of the project is due to the calculation of underwork in the amount of €63,327.72 and the value of the final price revision in the amount of €37,432.15
2435 | 4853529 | Urban Requalification of the Aranhas Center | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Penamacor | Castelo Branco | 5 | 15 | 28-09-2018 | 06-12-2019 | 434 | 150 | 165500 | 124624 | 1 | 140024.11 | -15400.11 | 89.0018 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay in carrying out the project. | underwork in the amount of €4,338.18; additional work resulting from unforeseen circumstances at contract prices worth €12,218.00; complementary work resulting from unforeseeable circumstances in the amount of €5,775.00; price revision worth €1,463.76.
2436 | 4852077 | Leveling of Platforms, Tout-Venant Layer, Settlement of Drains and Wear Layer in Bituminous | 45211360-0 | Urban development construction work | FALSE | 2018 | 2019 | Portugal | Mogadouro | Bragança | 4 | 11 | 24-09-2018 | 05-08-2019 | 315 | 180 | 317244.45 | 294417.68 | 2 | 340243.23 | -45825.55 | 86.5315 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: criteria for the most economically advantageous proposal, art. 74. nº. 1 line b) Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work stopped in the summer due to the constraint caused by the increased flow of traffic | execution of complementary works
2437 | 4850335 | Dredging contract on the River Gilão, between Lota and the bridge | 45252124-3 | Dredging and pumping works | FALSE | 2018 | 2019 | Portugal | Tavira | Faro | 8 | 20 | 02-10-2018 | 05-01-2019 | 95 | 45 | 330000 | 281650 | 2 | 286355.08 | -4705.08 | 98.3569 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unspecified contingencies | price review
2438 | 4847312 | Contract "Completion Work of the Infrastructures of the Urbanization of Campo das Cordoarias - 2nd Phase" | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Barreiro | Setúbal | 17 | 20 | 24-08-2018 | 17-06-2019 | 297 | 120 | 190000 | 189888.78 | 1 | 171235.15 | 18653.63 | 110.8936 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 40% Criterion related to cost Name: Cost Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | security reasons | underwork
2439 | 4845937 | 2018/300.10.001/34 - Public Tender - Contract for the Remodeling of the Water Network on Ladeira Ruída | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 15 | 06-09-2018 | 16-05-2019 | 252 | 150 | 146000 | 137834.76 | 1 | 137834.76 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | in the 1st, 2nd and 3rd inspection notices for the purposes of provisional acceptance, defects were detected in the project and, in both cases, a period of 30 days was given for their correction.
2440 | 4844032 | Contract nº 3/18 - "Pedestrian Routes Between the Reboleira Interface and the Employer and Training Center of the Industrial Zone of Venda Nova - Work Execution" | 45233226-9 | Access road construction work | FALSE | 2018 | 2021 | Portugal | Amadora | Lisboa | 11 | 20 | 21-09-2018 | 18-06-2021 | 1001 | 280 | 1492133.16 | 1299811.54 | 3 | 1299811.54 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - delay in delivery of final screens; - delay in the delivery of the "plan for the prevention and management of construction and demolition waste"; - restrictions derived from the pandemic related to covid-19.
2441 | 4843993 | Preventive Intervention on Pavements 2018 - North Operational Center (6 Lots) E-contracts 5010036885 | 45233142-6 | Road-repair works | FALSE | 2018 | 2020 | Portugal | Vila Real | Viana do Castelo | 18 | 30 | 14-09-2018 | 01-01-2020 | 474 | 90 | 2900000 | 94763.5 | 1 | 101216.57 | -6453.07 | 93.6245 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | pricing review.
2442 | 4843991 | hub paving - Proximity works - 2018 | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 07-09-2018 | 22-03-2019 | 196 | 122 | 322350.27 | 94737 | 1 | 93937 | 800 | 100.8516 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | underwork.
2443 | 4843883 | hub paving - Proximity works - 2018 | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 07-09-2018 | 22-03-2019 | 196 | 122 | 322350.27 | 105183.09 | 1 | 103972.79 | 1210.3 | 101.1641 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE |  | underwork.
2444 | 4842944 | hub paving - Proximity works - 2018 | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 07-09-2018 | 22-03-2019 | 196 | 122 | 322350.27 | 110499.8 | 1 | 110499.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
2445 | 4840580 | Execution of the pumping system in Malhapãozinho, Mamarrosa, Oliveira do Bairro_x000D_ | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2018 | 2020 | Portugal | Oliveira do Bairro | Aveiro | 1 | 49 | 17-09-2018 | 03-04-2020 | 564 | 60 | 130000 | 103994.26 | 1 | 103994.26 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2446 | 4840458 | Revitalization, requalification and modernization of the public spaces surrounding the PER de Balselhas housing development, namely the pedestrian paths, green and leisure spaces | 45432100-5 | Floor laying and covering work | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 24 | 20-09-2018 | 24-04-2020 | 582 | 210 | 262062.3 | 259163.64 | 2 | 260942.66 | -1779.02 | 99.3182 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of two extensions of 46 and 23 days, respectively, on 05.10.2019 and 07.10.2019. | approval of the definitive price revision in the amount of €1,779.02
2447 | 4840311 | Expansion of AR and AA networks - 2018. | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2018 | 2019 | Portugal | Oliveira do Bairro | Aveiro | 1 | 25 | 21-09-2018 | 11-10-2019 | 385 | 730 | 249000 | 198580.42 | 1 | 198580.42 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2448 | 4840082 | Refurbishment of Carregal Pumping Pipe - Furadouro - Ovar_x000D_ | 45232151-5 | Water-main refurbishment construction work | TRUE | 2018 | 2019 | Portugal | Ovar | Aveiro | 1 | 25 | 21-09-2018 | 09-09-2019 | 353 | 90 | 125000 | 95588.3 | 1 | 95588.3 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the execution of the contract to be concluded" Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conditions motivated by the existence of another municipal contract in the place. | contracted work not performed
2449 | 4837928 | PRC_0127/2018_GAE-AR0378 - Decommissioning contract for FSC do Picoto and FSC do Fojo and construction of the Interceptor in Vila Nova - Amarante | 45232411-6, 45232423-3 | Foul-water piping construction work, Sewage pumping stations construction work | TRUE | 2018 | 2021 | Portugal | Amarante | Porto | 13 | 14 | 07-09-2018 | 22-01-2021 | 868 | 150 | 306000 | 240346.35 | 1 | 223680.83 | 16665.52 | 107.4506 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | partial suspension of work due to lack of energy supply to the picoto eear | adjustment of the layout of the collectors allowed the reduction of earthworks and manholes
2450 | 4837281 | Construction contract for the Senhora da Graça pontoon | 45241500-3 | Wharf construction work | FALSE | 2018 | 2019 | Portugal | Alenquer | Lisboa | 11 | N/A | 14-09-2018 | 07-11-2019 | 419 | 60 | 197963 | 187954.69 | 1 | 187414.69 | 540 | 100.2881 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 4 | FALSE | N/A | N/A | N/A | N/A | FALSE | constraints in the adjustments and respective approval by the inspection regarding the positioning (planimetric and altimetric) of the box-culvert due to impressions of the execution project, which in turn led to delays in the production of prefabricated elements (specific to the project). existence of two communication poles and an electricity pole installed in the project zone whose location prevented the execution of curbs and pavements and the municipality's intention to open traffic before the completion of the project. | it was not necessary to create a manhole as planned, as the collector and rainwater piping was in straight alignment and in good condition. as a matter of symmetry in the installation of public lighting poles, an element originally planned was eliminated.
2451 | 4836349 | EP-2018(5001)/10018 Miscellaneous Benefits in Rooms and IS - CED AACF | 45113000-2 | Siteworks | TRUE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 21-09-2018 | 02-01-2019 | 103 | 50 | 50000 | 44239.84 | 1 | 44239.84 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no deadline change | no change
2452 | 4836026 | PdS/Urban qualification and treatment of environmental liabilities in the former warehouse area and creation of a new access to the Park | 45233250-6 | Surfacing work except for roads | FALSE | 2014 | 2019 | Portugal | Aveiro | Aveiro | 1 | 21 | 08-01-2018 | 02-09-2019 | 602 | 180 | 204000 | 154000 | 1 | 85696.54 | 68303.46 | 179.7039 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | we awaited the delivery of compliance with the "plan for the prevention and management of construction and demolition waste" of the technical compilation and respective validations
2453 | 4835987 | Rehabilitation of social housing development - Escapães - Santa Maria da Feira | 45210000-2 | Building construction work | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 21-09-2018 | 20-10-2020 | 760 | 120 | 224079.25 | 198076.14 | 1 | 185395.01 | 12681.13 | 106.8401 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 42 days of graceful extension; 42 days for the contractor to complete the project and schedule an inspection; 479 in carrying out inspections for the purpose of provisional acceptance and correction of defects | complementary work on readjusting the access system for people with reduced mobility.
2454 | 4835261 | Opening of Roads in the Expansion Zone of the Casarão Business Park | 45112000-5 | Excavating and earthmoving work | FALSE | 2017 | 2021 | Portugal | Águeda | Aveiro | 1 | 30 | 17-04-2018 | 24-03-2021 | 1072 | 150 | 300473.38 | 179780.14 | 1 | 154288.53 | 25491.61 | 116.522 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the deadline are due to the extension of the deadline due to the fact that Extra work has been carried out. | doing more work.
2455 | 4834430 | Requalification and modernization of the Marco de Canaveses elementary school facilities | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2021 | Portugal | Marco de Canaveses | Porto | 13 | 24 | 31-08-2018 | 24-02-2021 | 908 | 304 | 559248.92 | 559238.47 | 2 | 617793.44 | -58554.97 | 90.5219 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | suspensions and extensions described above | complementary works
2456 | 4833782 | Rehabilitation of the São Bernardo Road | 45233141-9 | Road-maintenance works | FALSE | 2018 | 2020 | Portugal | Aveiro | Aveiro | 1 | 30 | 03-09-2018 | 17-01-2020 | 501 | 120 | 330791.34 | 235393.75 | 1 | 253435.63 | -18041.88 | 92.8811 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspensions and extensions | complementary work, underwork and price revisions
2457 | 4832829 | Renewal of Water Supply Networks - Phase 1 - Águeda | 45231300-8 | Construction work for water and sewage pipelines | TRUE | 2018 | 2019 | Portugal | Águeda | Aveiro | 1 | 24 | 14-08-2018 | 26-12-2019 | 499 | 365 | 249000 | 189506.95 | 1 | 189506.9 | 0.05 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2458 | 4832692 | Preventive Intervention in Pavements 2018 - Greater Lisbon Operational Center (5 lots) - (E-contracts 5010036883) | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Sintra | Setúbal | 17 | 32 | 10-09-2018 | 11-10-2019 | 396 | 90 | 3690000 | 467201.36 | 2 | 495879.72 | -28678.36 | 94.2167 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
2459 | 4832634 | Preventive Intervention in Pavements 2018 - Greater Lisbon Operational Center (5 lots) - (E-contracts 5010036883) | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Grandola | Lisboa | 11 | 32 | 10-09-2018 | 11-10-2019 | 396 | 90 | 3690000 | 610787.74 | 2 | 649183.22 | -38395.48 | 94.0856 | Best value for money: No Criterion related to quality Name: Valia Técnica Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
2460 | 4832444 | Urban arrangement of the area surrounding the church of St. Isidoro (phase 1) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 14 | 16-07-2018 | 29-11-2019 | 501 | 152 | 138940.7 | 109345 | 1 | 113507.32 | -4162.32 | 96.333 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 21 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension, paragraph b) of article 365 of the "public procurement code" | more work worth 5,967.20 and underwork worth 1,804.88
2461 | 4831664 | CP 272/2018 - Contract for Removal of roofing in fiber cement tiles and Exterior Improvement of the Silves Health Center | 45262660-5 | Asbestos-removal work | FALSE | 2018 | 2019 | Portugal | Silves | Faro | 8 | 14 | 12-09-2018 | 04-02-2019 | 145 | 90 | 245000 | 192507.65 | 1 | 192507.65 | 0 | 100 | Best value for money: No Criterion related to quality Name: Compliance with the mandatory minimum requirements of the specifications Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | occurrence of adverse atmospheric phenomena, with a lot of rain and wind.
2462 | 4831631 | São Jacinto Fishing Support Center - Maritime Infrastructures | 45244100-0 | Marine installations | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | 24 | 06-04-2018 | 09-09-2019 | 521 | 180 | 345500 | 319297 | 2 | 328486.66 | -9189.66 | 97.2024 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | complementary works
2463 | 4831495 | Rehabilitation of the Axis Connection - Aveiro | 45432000-4 | Floor-laying and covering, wall-covering and wall-papering work | FALSE | 2018 | 2021 | Portugal | Aveiro | Aveiro | 1 | 25 | 14-08-2018 | 28-01-2021 | 898 | 180 | 210000 | 188216.7 | 1 | 195966.37 | -7749.67 | 96.0454 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | adverse weather conditions, difficulty in hiring labor | additional work and underwork
2464 | 4828517 | Repair of Malfunctions in the RDA and execution of other works in the NOC - 4th Phase” | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Murtosa | Aveiro | 1 | N/A | 14-09-2018 | 14-09-2020 | 731 | 730 | 700000 | 605930.02 | 2 | 605930.02 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2465 | 4828075 | Execution contract for “Repair of Malfunctions in the RDA and execution of other works in the COC - 2nd Phase” | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | N/A | 30-08-2018 | 29-10-2020 | 791 | 730 | 700000 | 551200.02 | 2 | 514905 | 36295.02 | 107.0489 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | contract for contract value not reached
2466 | 4827938 | Contract for the expansion of the general water supply network - south west subsystem - Phase 1/ Espiche stream. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 13-09-2018 | 04-07-2019 | 294 | 60 | 63571.78 | 50000 | 1 | 50000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2467 | 4827898 | Contract to carry out rupture repair work at RDAR - 3rd Phase | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Ílhavo | Aveiro | 1 | N/A | 06-09-2018 | 27-11-2020 | 813 | 1095 | 249000 | 183177.3 | 1 | 183176.29 | 1.01 | 100.0006 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2468 | 4826861 | Execution of the contract for sidewalk/pave walkways in the municipality of Albufeira | 45233253-7 | Surface work for footpaths | FALSE | 2017 | 2019 | Portugal | Albufeira | Faro | 8 | 21 | 11-09-2018 | 19-12-2019 | 464 | 365 | 250000 | 210500 | 1 | 210500 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the execution period of the project is due to delays on the part of the contractor
2469 | 4826450 | Its purpose is to carry out work, namely the replacement of existing window frames by placing aluminum window frames, interior and exterior painting; rehabilitation | 50000000-5 | Repair and maintenance services | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 15 | 04-09-2018 | 13-03-2019 | 190 | 60 | 280175.87 | 238149.51 | 1 | 238149.51 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1 - given the type of intervention site, being a school equipment it was necessary to carry out the project outside the school's opening hours, a fact that led to a substantial reduction in the daily workload. 2 - delay due to atmospheric conditions that had a significant impact, namely on the drying time of the materials, as well as on the degree of humidity in the application support layers. 4 - delay in scheduling the inspection, which was awaiting the delivery of the "plan for the prevention and management of construction and demolition waste", in order to proceed with the preparation of the provisional acceptance document (bureaucratic issues).
2470 | 4825340 | Public tender for the execution of the contract for the Remodeling of the Rainwater Wastewater Network in Albufeira - Texugueiras area. | 45232452-5 | Drainage works | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 30-08-2018 | 24-01-2019 | 147 | 60 | 88900 | 54500 | 1 | 57682.52 | -3182.52 | 94.4827 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays by the contractor
2471 | 4825233 | E201521 - Installation of Ecological Islands in the municipality of Vouzela | 45222110-3 | Waste disposal site construction work | FALSE | 2017 | 2020 | Portugal | Vouzela | Viseu | 20 | 18 | 05-09-2018 | 21-10-2020 | 777 | 365 | 370000 | 338654.62 | 2 | 338654.62 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the value of the project has not changed.
2472 | 4825213 | "Repair contract for the western breakwater of Vila Real de Santo António" | 45241300-1 | Pier construction work | FALSE | 2018 | 2020 | Portugal | Vila Real Sto Antonio | Faro | 8 | 6 | 13-09-2018 | 04-09-2020 | 722 | 107 | 445000 | 397975.77 | 2 | 394975.78 | 2999.99 | 100.7595 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | 3 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | bad sea conditions observed during the maritime winter. | underwork
2473 | 4825073 | Contract aimed at replacing existing pipelines and branches in the ZMC of Amadora City Council, parish of Mina de Água, in the municipality of Amadora. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 20 | 05-09-2018 | 09-10-2020 | 765 | 120 | 181000 | 162778.3 | 1 | 162778.3 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline was met in full.
2474 | 4823940 | Contract for the Rehabilitation of Public Spaces in social housing areas - Bairro de S. Pedro | 45233160-8 | Paths and other metalled surfaces | FALSE | 2018 | 2020 | Portugal | Arouca | Aveiro | 1 | 30 | 13-09-2018 | 04-11-2020 | 783 | 274 | 386560.51 | 293915 | 2 | 264889.46 | 29025.54 | 110.9576 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions | underwork and additional work and price revision.
2475 | 4823646 | 2018.151.01.C1 - DR Alentejo - Reinforcement of power outlets | 45000000-7 | Construction work | TRUE | 2018 | 2018 | Portugal | Évora | Évora | 7 | 15 | 06-09-2018 | 24-10-2018 | 48 | 60 | 18000 | 12042.5 | 1 | 12042.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | not included in the process
2476 | 4821153 | Public Tender for the Sealing Contract for the North Terminal and VTS of the Port of Aveiro | 45342000-6 | Erection of fencing | FALSE | 2018 | 2019 | Portugal | Ílhavo | Aveiro | 1 | 26 | 13-08-2018 | 05-04-2019 | 235 | 60 | 110000 | 88966.15 | 1 | 88966.15 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out an inspection and sign the respective receipt and contractual penalties.
2477 | 4820854 | Requalification of the Elementary School Building in Infias - Major Repairs to Elementary School Buildings | 45220000-5 | Engineering works and construction works | FALSE | 2018 | 2019 | Portugal | Vizela | Braga | 3 | 14 | 10-08-2018 | 21-01-2019 | 164 | 45 | 113502.43 | 109408.2 | 1 | 109408.2 | 0 | 100 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works
2478 | 4820814 | Public Tender for the Maintenance Contract for Road Signaling between the A25 and Forte da Barra | 45233221-4 | Road-surface painting work | FALSE | 2018 | 2019 | Portugal | Ílhavo | Aveiro | 1 | 33 | 16-08-2018 | 12-04-2019 | 239 | 30 | 30000 | 23723.84 | 1 | 23723.84 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the contractual period of 30 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective receipt.
2479 | 4820779 | Construction, Reconstruction and Major Repair of Roads, Car Parks, Sidewalks and Trenches in Several Parishes - streets of Termas | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Vizela | Braga | 3 | 14 | 05-09-2018 | 04-04-2019 | 211 | 35 | 115300 | 105743.8 | 1 | 80705 | 25038.8 | 131.0251 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions and additional work | underwork and more work
2480 | 4820574 | Requalification and Modernization of the Vizela High school Facilities and Requalification of the Sports Pavilion - Vizela High school | 45454100-5 | Restoration work | FALSE | 2018 | 2020 | Portugal | Vizela | Braga | 3 | 25 | 16-08-2018 | 17-04-2020 | 610 | 270 | 2974977.87 | 2507175.68 | 3 | 3053886.11 | -546710.43 | 82.0979 | Best value for money: No Criterion related to quality Name: Price Weighting: 100% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | complementary works | complementary works + price revision
2481 | 4820020 | 2014.158.04.C1 - sf évora - refurbishment of pavilion 1 - 1st phase | 45210000-2 | Building construction work | FALSE | 2015 | 2019 | Portugal | Évora | Évora | 7 | 21 | 21-09-2015 | 20-11-2019 | 1521 | 120 | 895547 | 757403.61 | 2 | 782901.83 | -25498.22 | 96.7431 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price: 50%, VT Proposal: 40%, Deadline: 10% | 1 | 5 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | price review
2482 | 4819411 | Intervention contract for requalification of Ilha da culatra - nucleus da culatra, within the scope of the polis littoral ria formosa intervention | 45262640-9 | Environmental improvement works | FALSE | 2017 | 2020 | Portugal | Olhão | Faro | 8 | 30 | 16-01-2018 | 15-12-2020 | 1064 | 240 | 1237667 | 1232407.84 | 3 | 1070561.03 | 161846.81 | 115.1179 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award is made according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors, with the indicated weighting: a) Price (P) fP = 60% b) Technical value of the proposal (Q) fQ = 40% b.1) Descriptive and justification (Q1) fQ1 = 10% b.2) Work plan (Q2) fQ2 = 30% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in submitting materials for approval and consequent delay in carrying out the project | several articles with quantities greater than those that were executed.
2483 | 4819185 | 2018/59 - DGEPIM - Slope stabilization in the back parking lot of R. Amélia rey colaço, carnaxide | 45111230-9 | Ground-stabilisation work | FALSE | 2018 | 2019 | Portugal | Oeiras | Lisboa | 11 | 30 | 17-08-2018 | 15-10-2019 | 424 | 90 | 141475.49 | 135718.48 | 1 | 135718.48 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2484 | 4818431 | Axis for Competitiveness - ZIV South Entrance | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Vagos | Aveiro | 1 | 30 | 10-09-2018 | 12-09-2019 | 367 | 150 | 300000 | 284963.52 | 2 | 209206.97 | 75756.55 | 136.2113 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of several mechanical failures in the equipment that were prolonged in their repair, having caused logistical blockages and work progress. lack of human resources in most of the country and conditioning the profitability of activities in order to meet the established deadlines. questions raised regarding the project and corrections proposed to improve it. | resulting from the measurements of the quantities of work actually carried out during the course of the project, underwork due to the non-execution of the roundabout foreseen in the project, more work necessary for the correct intersection of rua das abelhas with rua borda d'água, price revision calculation and compensation to the contractor for reducing the contractual value of the projects.
2485 | 4817887 | Improvement of Forest Road n.º 1 | 45233140-2 | Roadworks | FALSE | 2018 | 2019 | Portugal | Vagos | Aveiro | 1 | 30 | 10-09-2018 | 05-08-2019 | 329 | 180 | 220000 | 218428.29 | 1 | 263205.29 | -44777 | 82.9878 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline and delay of the executing entity | value of errors and omissions in the terms of reference, revision of prices and work to be done
2486 | 4816751 | Public Works Contract - Rehabilitation works on the roof and exterior walls of the Aguiar da Beira Local Service building - Guarda District Center | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Aguiar da Beira | Guarda | 9 | 14 | 21-08-2018 | 11-12-2018 | 112 | 90 | 69500 | 55635.6 | 1 | 55635.6 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2487 | 4814995 | Replacement of Chillers in the Central HVAC System and Reconversion of the HVAC System in the IT Room of the District Center of Bragança | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Bragança | Bragança | 4 | 6 | 06-08-2018 | 10-12-2018 | 126 | 90 | 128000 | 102104.33 | 1 | 102104.33 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A
2488 | 4814808 | EP-2018(5001)/10017 Miscellaneous Improvements in the Building of CED SCT | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 04-09-2018 | 10-01-2019 | 128 | 80 | 130000 | 127117.47 | 1 | 126993.25 | 124.22 | 100.0978 | Best value for money: No Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | existence of complementary work and work to be suppressed in the amount of 2,633.80.
2489 | 4814630 | Requalification and Expansion of the Primary School of Cabeça Gorda | 45214200-2 | Construction work for school buildings | TRUE | 2018 | 2019 | Portugal | Lourinhã | Lisboa | 11 | 14 | 06-08-2018 | 15-10-2019 | 435 | 214 | 295744.27 | 273000 | 2 | 295542.34 | -22542.34 | 92.3726 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: The award criterion is the assessment of price or cost, paragraph b), paragraph 1 of article 74 CCP Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | errors and omissions detected during the execution of the contract accepted by the owner that jeopardized the normal development of the approved work plan. | errors and omissions detected during the execution of the contract accepted by the client with quantities and types of work not foreseen in the initial contract.
2490 | 4814451 | Paving of paths in several places in the Municipality | 50000000-5 | Repair and maintenance services | FALSE | 2018 | 2018 | Portugal | São Brás de Alportel | Faro | 8 | 7 | 29-08-2018 | 06-11-2018 | 69 | 60 | 127330 | 103133.4 | 1 | 103133.4 | 0 | 100 | Best value for money: No Criterion related to quality Name: Not applicable Weighting: 0% Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2491 | 4813300 | Contract for widening crossstreet ofAreinho, Largo do Areinho and Alameda do Areinho - Oliveira do Douro | 45233140-2 | Roadworks | TRUE | 2018 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 14 | 05-09-2018 | 09-05-2019 | 246 | 122 | 84660 | 77122.85 | 1 | 80061.63 | -2938.78 | 96.3294 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | a notice of suspension of the projects was authorized, due to the temporary impossibility of fulfilling the contract, due to adverse weather conditions that did not allow the execution of the projects, in safety conditions, given the nature of the projects. | the completion of the project resulted in additional works worth €1,750.00 and a final price review worth €1,188.78.
2492 | 4813298 | Improvement of Sertã High school | 45214220-8 | Secondary school construction work | FALSE | 2018 | 2021 | Portugal | Sertã | Castelo Branco | 5 | 11 | 10-08-2018 | 22-11-2021 | 1200 | 365 | 775100 | 747215.14 | 2 | 769504.71 | -22289.57 | 97.1034 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to problems resulting from the period of suspension of works and yield losses caused by this suspension in the progress of the project and difficulties with available personnel and delays in various supplies caused by the covid 19 pandemic | the alterations due to underwork had to do, above all, with work not carried out due to a structural reinforcement intervention in the main building of the secondary school, in accordance with a project ordered to be carried out by the ministry of education, and whose work led to the non-execution of works foreseen in this contract since they would later be destroyed.
2493 | 4812679 | Contract for Major Repairs of Sanitation Networks | 45259000-7 | Repair and maintenance of plant | FALSE | 2018 | 2020 | Portugal | Alpiarça | Santarém | 16 | 14 | 09-08-2018 | 04-09-2020 | 757 | 730 | 110000 | 110000 | 1 | 90198.72 | 19801.28 | 121.953 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the time that elapsed between the end of the contract and provisional acceptance was for repairing defects | the contract ended by value or term, whichever came first.
2494 | 4811999 | Contract 2/GEBALIS/2018 - Contract for the Maintenance and Repair of housing and Common Areas in Neighborhoods in the North West Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 15 | 14-08-2018 | 31-12-2019 | 504 | 730 | 600000 | 510000 | 2 | 510000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work proceeded normally.
2495 | 4810840 | Construction contract for the Sports Zone | 45212200-8 | Construction work for sports facilities | FALSE | 2017 | 2019 | Portugal | Arouca | Aveiro | 1 | 30 | 10-09-2018 | 23-07-2019 | 316 | 180 | 245824 | 223897.11 | 1 | 225561.75 | -1664.64 | 99.262 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | elimination of weeds on the grass mat. | underwork
2496 | 4810763 | Public tender for the contract for the Replacement of the Sewer Networks in Alto da Barra in Oeiras -2nd Phase | 45232410-9 | Sewerage work | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 20 | 04-09-2018 | 19-10-2020 | 776 | 90 | 204517 | 197500 | 1 | 197500 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | lack of safety at work | vat settlement
2497 | 4810221 | Quality 100% - Public Tender for bituminous paving of streets in 2018 - Union of Parishes of Matosinhos and Leça da Palmeira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 05-09-2018 | 21-05-2019 | 258 | 61 | 190000 | 137600.21 | 1 | 137600.21 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2498 | 4809517 | Quality 100% - Public tender for hub paving of streets in 2018 - Union of Parishes of Custóias, Leça do Balio and Guifões | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 05-09-2018 | 09-04-2019 | 216 | 61 | 110000 | 64236 | 1 | 89897 | -25661 | 71.4551 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 22 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2499 | 4809339 | A Sustainable Territory - Sanitation - Sewerage and Wastewater Networks - Ameixeira / A Sustainable Territory - Waters - Repair of the Water Network - Ameixeira | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Condeixa-a-Nova | Coimbra | 6 | 21 | 08-06-2018 | 17-09-2020 | 832 | 300 | 275000 | 260946.1 | 2 | 226385.03 | 34561.07 | 115.2665 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension granted | additional work and underwork
2500 | 4808363 | Improvement of roadways in the Parish of Pala | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Mortágua | Viseu | 20 | 3 | 24-08-2018 | 19-08-2020 | 726 | 120 | 287696.28 | 228578.82 | 1 | 302790.49 | -74211.67 | 75.4908 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | climatic reasons | complementary work.
2501 | 4808230 | The object of this contract concerns the execution of buildings intended for an animal collection center | 45223600-2 | Dog kennels construction work | FALSE | 2018 | 2021 | Portugal | Cadaval | Lisboa | 11 | 6 | 31-08-2018 | 15-02-2021 | 899 | 180 | 400000 | 397900 | 2 | 381738.7 | 16161.3 | 104.2336 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | due to deadline extensions | due to the existence of complementary work and underwork
2502 | 4808051 | Quality 100% - Public Tender for paving roads in bituminous in 2018 - Union of Parishes of Perafita, Lavra and Santa Cruz do Bispo | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 15 | 05-09-2018 | 29-01-2019 | 146 | 61 | 330000 | 237075.35 | 1 | 237075.35 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2503 | 4807913 | Painting and execution of treadmills | 45233140-2 | Roadworks | FALSE | 2018 | 2019 | Portugal | Vila Verde | Braga | 3 | 12 | 04-09-2018 | 07-05-2019 | 245 | 90 | 87448 | 76330 | 1 | 76330 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of the price as the only aspect of the execution of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2504 | 4807081 | Public tender for the Contract for Miscellaneous Repairs and Installation of Spill System in the Logistic Park | 45259000-7 | Repair and maintenance of plant | FALSE | 2018 | 2019 | Portugal | Ílhavo | Aveiro | 1 | 40 | 23-07-2018 | 12-04-2019 | 263 | 90 | 70000 | 65045.5 | 1 | 65045.5 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project ended within the contractual period of 90 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective receipt.
2505 | 4805670 | Construction of Kiosk in the Urban Park of Ribeira da Vila | 45210000-2 | Building construction work | FALSE | 2018 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 03-09-2018 | 05-11-2019 | 428 | 213 | 100000 | 96300 | 1 | 99973.91 | -3673.91 | 96.3251 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions and suspension | complementary work and less
2506 | 4805026 | Rehabilitation Works for Blocks 1 to 4 in the Mouteira Public Housing Complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 30-08-2018 | 06-12-2019 | 463 | 330 | 1020000 | 969735.43 | 2 | 935571.14 | 34164.29 | 103.6517 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the contractually foreseen | work not carried out worth €34,164.29
2507 | 4804969 | Contract for the construction of a large material storage warehouse. | 45223100-7 | Assembly of metal structures | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 29-08-2018 | 07-03-2019 | 190 | 90 | 110000 | 108403.36 | 1 | 108403.36 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | alteration of the term is due to delays by the contractor.
2508 | 4804661 | Rehabilitation / Works at the Milreu Wastewater Treatment Plant | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 12-07-2018 | 05-11-2019 | 481 | 243 | 187000 | 179493.29 | 1 | 180049.01 | -555.72 | 99.6914 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work suspensions and extensions | complementary work and less
2509 | 4804321 | Rehabilitation contract / Works at the Carrascal Wastewater Treatment Plant | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2018 | 2020 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 30-07-2018 | 09-03-2020 | 588 | 122 | 82000 | 81706.9 | 1 | 83305.44 | -1598.54 | 98.0811 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of work due to the fact that equipment was installed in the area to be intervened to clean the sludge by means of a “geotube”. provided for in article 16.7 of the project map. | works and more worth 2700€ and works less than -1101.46€
2510 | 4803275 | Building improvement works for installation of the Wholesale Horticultural Resale - Creixomil | 45453100-8 | Refurbishment work | TRUE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 14 | 03-09-2018 | 22-04-2019 | 231 | 120 | 280500 | 219320.81 | 1 | 218649.9 | 670.91 | 100.3068 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | - the approval of the safety and health plan for the project was communicated on 10/15/2018; - notice of partial suspension of work: 12/10/2018; - work restart notice: 1/9/2018 | existence of underwork due to the foreseen quantities not being used up.
2511 | 4803261 | Rehabilitation contract / Works at the São João do Peso Wastewater Treatment Plant | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2018 | 2020 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 30-07-2018 | 17-07-2020 | 718 | 365 | 265000 | 199209.18 | 1 | 199209.18 | 0 | 100 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension due to the state of emergency and term extensions | there were no changes
2512 | 4800868 | EMP-R/5/2018 - Contract for the Rehabilitation of the Blocks of the Galeão Housing Complex | 45453100-8, 45442100-8 | Refurbishment work, Painting work | FALSE | 2018 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 02-07-2018 | 03-01-2019 | 185 | 120 | 220000 | 185421.11 | 1 | 185421.11 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project were carried out within the deadline
2513 | 4799504 | Repaving of the Municipal Section of the EN332, at the South Exit of Vilar Formoso _x000D_ | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Almeida | Guarda | 9 | 18 | 31-08-2018 | 06-08-2019 | 340 | 45 | 64387 | 43000.27 | 1 | 39020.92 | 3979.35 | 110.198 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal, modality provided for in paragraph b) of paragraph 1 of article 74 of the CCP Weighting: 100% | 2 | 100 | 10 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork
2514 | 4798138 | Public Tender for the Restructuring of Avenida João Bosco Mota Amaral, in the section between Hotel Marina and Clube Naval | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 13 | 02-08-2018 | 21-03-2019 | 231 | 120 | 341000 | 319500 | 2 | 327693.26 | -8193.26 | 97.4997 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the deadline for carrying out the project.
2515 | 4797948 | Public tender for the works to repave street ofs Azáleas and street of Lírio, Relva | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 17 | 03-08-2018 | 07-05-2019 | 277 | 180 | 285000 | 280509.7 | 2 | 280460.84 | 48.86 | 100.0174 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | existence of underworks.
2516 | 4794181 | Replacement of water distribution networks in the western sector of Funchal - fiber cement network in Caminho da Terra Chã and surroundings | 45232151-5 | Water-main refurbishment construction work | FALSE | 2018 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 30 | 10-08-2018 | 28-02-2019 | 202 | 150 | 240651 | 215503.74 | 1 | 201777.39 | 13726.35 | 106.8027 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 2 | TRUE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather conditions | there were more works worth €6.27 and there were works less than €13,732.62
2517 | 4791128 | Design-construction of an aqueduct and repair of a section of the Rio Velho in Luso" | 45247130-0 | Aqueduct construction work | FALSE | 2018 | 2020 | Portugal | Mealhada | Aveiro | 1 | N/A | 17-07-2018 | 17-07-2020 | 731 | 105 | 275000 | 274750 | 2 | 273908.08 | 841.92 | 100.3074 | Price | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 1 | FALSE | N/A | N/A | N/A | N/A | FALSE | suspension of work for reasons beyond the control of the contractor | revision of prices and underwork
2518 | 4790197 | Rehabilitation and refurbishment of corral doors and adjacent walls | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Estremoz | Évora | 7 | 5 | 29-08-2018 | 10-09-2019 | 377 | 180 | 731857.17 | 669330.18 | 2 | 648826.69 | 20503.49 | 103.1601 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | approval of complementary works | approval of complementary works
2519 | 4787074 | Rehabilitation of social housing developments - Milheirós de Poiares | 45210000-2 | Building construction work | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 21 | 27-08-2018 | 20-10-2020 | 785 | 90 | 259844.61 | 241079.96 | 1 | 242605.89 | -1525.93 | 99.371 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 82 days of graceful extension; 65 days for the contractor to complete the project and schedule an inspection; 480 days to carry out inspections for the purpose of provisional acceptance and correction of deficiencies | supplementary work for errors and omissions supplies
2520 | 4784761 | Reprofiling of street of Francos and new access to the University of Minho - Azurém | 45233120-6 | Road construction works | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 04-04-2017 | 27-07-2018 | 479 | 180 | 1590592.18 | 1149832.85 | 3 | 1090849 | 58983.85 | 105.4072 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | under the terms of art. a) of article 297 of the "public procurement code": work suspension notice 01: 07/07/2017; auto restart of work 01: 10/27/2017; work suspension notice 02: 03/07/2018; auto restart of work 02: 04/16/2018 partial provisional acceptance notice 01: 12/18/2017; partial inspection notice 02: 03/19/2018 (correction of anomalies (45 days)); partial inspection notice 03: 04/30/2018 (correction of anomalies (30 days)); partial inspection notice 04: 03/05/2018: correction of anomalies (30 days)); partial provisional acceptance notice 02: 05/30/2018. final provisional acceptance notice: 06/01/2018. | existence of underwork due to the foreseen quantities not being used up.
2521 | 4784647 | Urban Requalification – Praceta das Chãs, R. Dr. Manuel Alegre and R. 15 de Agosto | 45233142-6 | Road-repair works | FALSE | 2017 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 26-07-2018 | 29-10-2020 | 826 | 300 | 348993.81 | 328671.85 | 2 | 233340.05 | 95331.8 | 140.8553 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the execution time of the project was due to the need to carry out more work, namely, replacement of lids of infrastructure boxes, execution of a concrete slab in accesses to vehicles, displacement of public lighting poles, supply and application of luminaires, insulation and drainage of walls, painting of walls, execution of gutters, execution of benches and road painting. | the change in the value of the project was due to the need to carry out the additional works described above and the suppression of works foreseen in the project.
2522 | 4783016 | Public Tender for the contract to carry out pantries for the kitchen and various repairs at EB. 2,3 Francisco Cabrita. | 45454000-4 | Restructuring work | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 4 | 16-08-2018 | 11-08-2020 | 726 | 70 | 268905.99 | 262251.01 | 2 | 273394.86 | -11143.85 | 95.9239 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | in this undertaking there was over and underwork | in this undertaking there was over and underwork
2523 | 4782745 | Construction of an WWTP in the southern part of the municipality of Barcelos - Macieira de Rates | 45232421-9 | Sewage treatment works | FALSE | 2018 | 2020 | Portugal | Barcelos | Braga | 3 | 24 | 23-08-2018 | 30-12-2020 | 860 | 270 | 1555778.44 | 1354183.58 | 3 | 1350830.21 | 3353.37 | 100.2482 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (35%); b2) "PM" Labor Plan (35%); b3) "PE" Equipment Plan (30%); | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the term of the contract provided for in the terms of reference is 270 days, starting on march 8, 2019 and ending on december 3, 2019. due to several delays during the execution of the contract, reported and approved in registrations nº 34.18/20, 37.805/20, 38.526/20, 40.878/20, 57.012/20 and 61.991/20, the last deadline for the completion of the contract was approved for december 15, 2020 and the financing period for the contract is extended until december 31, 2020, registration n.º 29.997/20, and approved by the funding entity poseur, on june 24, 2020 , registration no. 33.921/20. | in this contract there were underwork, in the amount of € 3,353.35. they resulted from an impediment outside the municipality. the deactivation work of the existing compact wwtp and its transport to the wwtp in barcelos, foreseen in the execution project, cannot be carried out. this work requires licensing for the discharge of the treated effluent, which awaits approval by the apa.
2524 | 4779940 | Public Tender for the contract for the execution of a domestic wastewater network - Solar do Castelo. | 45232400-6 | Sewer construction work | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 13 | 16-08-2018 | 07-06-2019 | 295 | 60 | 108351.44 | 90000 | 1 | 90000 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
2525 | 4779484 | Completion of the Urbanization Works on the allotment with Permit No. 2/2002; Construction of Children's Park and Ecological Island; Execution and Repair of Pavements on Sidewalks; Construction of Walkways | 45233200-1 | Various surface works | FALSE | 2018 | 2021 | Portugal | Ferreira do Zezere | Santarém | 16 | 14 | 02-08-2018 | 28-01-2021 | 910 | 120 | 182654 | 177857.04 | 1 | 197867.72 | -20010.68 | 89.8868 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary works and extensions granted | additional work, underwork and price revisions
2526 | 4778105 | 16EP00002386 - Contract for the rehabilitation of the north wing of the former Palace of Justice of Santa Maria da Feira | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | N/A | 22-06-2018 | 13-07-2020 | 752 | 270 | 619500 | 612760.18 | 2 | 622678.49 | -9918.31 | 98.4072 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | waiting for power supply to test the machines | additional work, underwork and price revisions
2527 | 4775979 | Rehabilitation of the Town Hall Building | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Montijo | Setúbal | 17 | 30 | 20-08-2018 | 24-06-2019 | 308 | 240 | 323000 | 246914.19 | 1 | 317030.4 | -70116.21 | 77.8834 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | by necessity to suppress some errors and omissions | by necessity to suppress some errors and omissions
2528 | 4775600 | Public Tender for the remodeling contract for the general water supply network - street of Sol - Ferreiras | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 13 | 16-08-2018 | 24-01-2019 | 161 | 90 | 70000 | 68500 | 1 | 68500 | 0 | 100 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | delays by the contractor
2529 | 4774736 | New floating dock and access bridge at the core of the hangars on Ilha da Culatra | 45241500-3 | Wharf construction work | FALSE | 2018 | 2020 | Portugal | Faro | Faro | 8 | 14 | 25-06-2018 | 13-01-2020 | 567 | 114 | 50000 | 49860 | 1 | 49860 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of the project due to the need for a favorable binding determination by the competent administrative entities. | no change
2530 | 4774324 | Requalification of street of Faceira da Cisterna | 45233252-0 | Surface work for streets | FALSE | 2018 | 2020 | Portugal | Elvas | Portalegre | 12 | 15 | 17-08-2018 | 26-10-2020 | 801 | 90 | 256000 | 204960.4 | 1 | 200704.26 | 4256.14 | 102.1206 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Most economically advantageous tender for the contracting authority Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a need to reconcile the contract with the execution of a contract taking place in a hotel in the vicinity of the said contract. | it was verified the existence of excessive measurements and the existence of work not necessary for the contract.
2531 | 4774131 | Contract for requalification of the waterline of Maria Luísa beach - 1st phase. | 45232451-8 | Drainage and surface works | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 16-08-2018 | 14-11-2019 | 455 | 90 | 141500 | 101260.11 | 1 | 99122.15 | 2137.96 | 102.1569 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | works have not been performed.
2532 | 4769375 | Ortiga Museum Nucleus | 45212313-3 | Museum construction work | FALSE | 2018 | 2019 | Portugal | Mação | Santarém | 16 | 14 | 30-07-2018 | 02-10-2019 | 429 | 240 | 159936.34 | 148695.95 | 1 | 151645.05 | -2949.1 | 98.0553 | Best value for money: No Criterion related to quality Name: none Weighting: 0% Criterion related to cost Name: Price or cost Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension | complementary works
2533 | 4768017 | Improvement of the DCPM building at the Lisbon Naval Base | 45261900-3 | Roof repair and maintenance work | FALSE | 2018 | 2018 | Portugal | Almada | Setúbal | 17 | 12 | 09-07-2018 | 18-12-2018 | 162 | 30 | 60980 | 51500 | 1 | 51500 | 0 | 100 | Best value for money: No Criterion related to quality Name: The constants of the procedure parts Weighting: 0% Criterion related to cost Name: The constants of the procedure parts Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties
2534 | 4767448 | Pedestrian circuit of Albufeira da Pala - 1st phase | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Baião | Porto | 13 | 30 | 27-07-2018 | 03-12-2019 | 494 | 180 | 272180 | 250080.68 | 2 | 250080.68 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of works between 11/31/2018 and 01/01/2019, due to changes in the fiber optic line; suspension of works between 02/18/2019 and 07/17/2019, due to changes in the public lighting line by edp. | there were no changes to the value of the project
2535 | 4767353 | The object of the work is the demolition of existing illegal constructions, as well as any structures attached to them, in the territory of the municipality of Amadora. | 45000000-7 | Construction work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 14 | 07-08-2018 | 03-04-2020 | 605 | 150 | 117764.16 | 94211.47 | 1 | 94211.47 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 25% Criterion related to cost Name: Price Weighting: 75% | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was a change to the execution period for less (140 days), due to the early completion of the project on 01/22/2019. the effective date of execution of the project does not correspond to the date of provisional acceptance, as this was only carried out after 01/27/2020. | existence of price revision
2536 | 4765674 | CP 027/17 Refurbishment of AA/AR infrastructures in Mexilhoeira Grande | 45233220-7, 45231300-8 | Surface work for roads, Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Portimão | Faro | 8 | 30 | 18-10-2017 | 19-12-2019 | 792 | 120 | 209000 | 182642.48 | 1 | 178742.08 | 3900.4 | 102.1821 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | "the extension was motivated by the difficulty of the contractor to complete the stipulated period due to the great difficulty of carrying out the project, motivated by the large amount of electrical and telecommunications cables on the sidewalks without registration, which were found in the area of ​​the boxes of the existing water and sewage branches to connect to the new network, so much of the project in the sidewalk area was carried out manually, without the expected performance for it to be carried out by mechanical means, and due to the great difficulty of labour, and the atmospheric conditions in which some days the project was stopped, due to the soggy land not allowing the roads to be paved, and because access to the eb123 school was maintained, with the project being carried out in stages, and because of the permanent water supply to the population, as this is not entirely attributable to the contractor, and because the delay did not cause damage to the developer, the extension was granted." | underwork according to the map of works presented.
2537 | 4765505 | Carrying out maintenance work on the rda and rdar in the coc | 45232100-3 | Ancillary works for water pipelines | FALSE | 2017 | 2021 | Portugal | Vagos | Aveiro | 1 | N/A | 01-08-2018 | 31-10-2021 | 1187 | 1095 | 700000 | 476200.02 | 2 | 365352.52 | 110847.5 | 130.3399 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | contract carried out for the contractual value not reached
2538 | 4765210 | The purpose of the project is to provide a wastewater drainage network for the areas of Rio Tinto and Tabuaço in the Parish of Ouca, with the construction of 7.9 km of gravity network, 319 domestic branches | 45232400-6 | Sewer construction work | FALSE | 2017 | 2019 | Portugal | Vagos | Aveiro | 1 | N/A | 07-08-2018 | 29-11-2019 | 479 | 365 | 1787400 | 1072440.01 | 3 | 1039217.89 | 33222.12 | 103.1968 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | TRUE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2539 | 4764721 | Renovation of the CE24 de AR de Valmaior and other works - Albergaria-a-Velha | 45232400-6 | Sewer construction work | TRUE | 2018 | 2019 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 44 | 10-08-2018 | 18-11-2019 | 465 | 60 | 140000 | 98000.01 | 1 | 96565.51 | 1434.5 | 101.4855 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as the only aspect of the execution of the contract to be signed - FORMULA Weighting: 100% | 2 | 100 | No | TRUE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2540 | 4764629 | The object of the contract is the execution of various works, with works related to masonry, stonework, waterproofing, painting, flooring, coatings, metalwork, carpentry | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 15 | 08-08-2018 | 22-10-2019 | 440 | 420 | 182348 | 154995.81 | 1 | 154995.81 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the projects related to the continuation of the contract were strongly conditioned by the constraints of some of the intervened equipment. several equipments had the activities in the spaces where the projects took place and the normal functioning of the same could not be disturbed in certain occasions.
2541 | 4761582 | New coverage of the 4 waters pier - Tavira | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2019 | Portugal | Tavira | Faro | 8 | 14 | 03-07-2018 | 10-01-2019 | 191 | 50 | 40000 | 39867.5 | 1 | 39867.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | unspecified contingencies
2542 | 4761156 | Preventive maintenance works in blocks 25 to 31 of Bairro das Campinas | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 31-07-2018 | 17-04-2019 | 260 | 150 | 480000 | 466583.73 | 2 | 466692.5 | -108.77 | 99.9767 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the contractually foreseen | eo in the amount of €5,605.25 and work not carried out in the amount of €5,496.48
2543 | 4760729 | Execution of the Barrel junction roundabout - EN 234/EN 228_x000D_ | 45000000-7 | Construction work | TRUE | 2018 | 2019 | Portugal | Mortágua | Viseu | 20 | 10 | 17-07-2018 | 16-10-2019 | 456 | 120 | 193116.93 | 154541.47 | 1 | 130568.65 | 23972.82 | 118.3603 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | climatic reasons | job suppression
2544 | 4760365 | Construction of the Mortazel ​​and Vila Pouca WWTPs | 45000000-7 | Construction work | TRUE | 2018 | 2020 | Portugal | Mortágua | Viseu | 20 | 11 | 16-07-2018 | 13-11-2020 | 851 | 120 | 269711.54 | 229987.6 | 1 | 126960.32 | 103027.28 | 181.1492 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was an alteration to the execution period of the project due to climatic reasons. | in the present procedure, the construction of the project in vila pouca was suppressed.
2545 | 4760226 | Ribeira da Vila Park - Exterior Arrangements | 45111000-8 | Demolition, site preparation and clearance work | FALSE | 2018 | 2020 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 13-07-2018 | 08-01-2020 | 544 | 243 | 150000 | 144950.5 | 1 | 144246.45 | 704.05 | 100.4881 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | suspension of the project for 73 days since two works were being carried out at the same time, the exterior arrangements and the kiosk. for the latter, it was necessary to enter the project with a heavy vehicle to unload the tile, and for this reason the final work of laying the curb in this area could not be completed. | underwork derived from measurement. additional work to create a rainwater drainage method in some areas of the park.
2546 | 4758940 | EGA-AR0240 - Contract for the Rehabilitation of the Moledo Gravity Interceptor – Vila Praia de Âncora (CAMINHA) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Caminha | Viana do Castelo | 18 | 47 | 29-06-2018 | 04-09-2019 | 432 | 112 | 457000 | 285427.85 | 2 | 308222.13 | -22794.28 | 92.6046 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical value of the proposal - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractual term of the contract increased, compared to what was foreseen, mainly due to the suspension of the execution period of the constructions. in any case, it should be noted that the extension of the contractual term did not translate into greater costs for the owner of the project, nor did it conditioned the normal development of the undertaking and the functioning of the interceptor (in the exploration state). | the final value of the project, compared to the value of the award, suffered a slight increase, as a result of the determination of errors and omissions supply work. no more or underwork was recorded.
2547 | 4757544 | Rehabilitation of the pavement of Av.ª 25 de Abril, in the Parish of Alfena, by carrying out milling and paving with bituminous concrete, including the execution of undercutting of sidewalks | 45233251-3 | Resurfacing works | FALSE | 2018 | 2021 | Portugal | Valongo | Porto | 13 | 12 | 08-08-2018 | 23-12-2021 | 1233 | 90 | 132000 | 99106.51 | 1 | 101443.74 | -2337.23 | 97.696 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | allocation of 5 days for carrying out the complementary work (1st additional contract). note: last measurement report dated 11.30.2018. there was some delay in the provisional reception of the project (works received only in the 2nd inspection - 07.02.2019). | approval of additional work, underwork and final calculation of the price revision.
2548 | 4753036 | Rehabilitation of elementary school nº 3 Luis de Camões | 45453100-8 | Refurbishment work | FALSE | 2017 | 2018 | Portugal | Montijo | Setúbal | 17 | 30 | 09-07-2018 | 28-12-2018 | 172 | 180 | 230720.19 | 185490.51 | 1 | 185490.51 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place in good weather conditions, achieving a reduction in the deadline | changes to the value of the project resulted from the non-execution of some works (supply of topsoil, sowing, supply of platforms, repair of wooden doors and children's equipment); with regard to additional work resulted from the removal of asbestos-containing sheets and the placement of new sandwich-type sheets)
2549 | 4752357 | Contract for the New Facilities of the Faculty of Nutrition and Food Sciences of the University of Porto | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 48 | 13-07-2018 | 15-10-2019 | 459 | 240 | 2200000 | 1889797.25 | 3 | 1950512.63 | -60715.38 | 96.8872 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Contract_40 🇧🇷 b) Technical value of the proposal_60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for the project was extended by 45 days due to the detection of an unforeseen work. | due to design errors.
2550 | 4718047 | Wastewater from Casal de Álvaro (PAR-020) - Águeda | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Águeda | Aveiro | 1 | N/A | 03-08-2018 | 22-01-2020 | 537 | 270 | 886000 | 719599.47 | 2 | 716527.32 | 3072.15 | 100.4288 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2551 | 4717619 | The work to be carried out involves all the work necessary for the complete rehabilitation of the building, comprising the ground floor, 1st and 2nd floor, namely wall coverings, floors, roofs, ceilings | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 15 | 03-08-2018 | 01-07-2020 | 698 | 240 | 639000 | 614938.26 | 2 | 656120.25 | -41181.99 | 93.7234 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of two amendments to the initial contract - extensions to the execution period (67 +15 days) - and the period assigned for the execution of the two additional contracts - complementary works (128 + 165 days), indicated in the respective fields | approval of additional work, underwork and the provisional calculation of the price revision, indicated in the respective fields
2552 | 4717599 | Reformulation of the drainage system and treatment of faralhão and bridges, 2nd phase - bridge system | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Setúbal | Setúbal | 17 | 30 | 19-04-2017 | 15-03-2018 | 330 | 210 | 488158.53 | 353994.6 | 2 | 353994.6 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended due to lack of timely delivery by the supplier of electromechanical equipment | there were no changes to the value of the project
2553 | 4715257 | 5010029423 - Beira Baixa Line - KP 106.880/107.980 - Migration of Wooden Sleepers to Concrete | 45234100-7 | Railway construction works | FALSE | 2017 | 2019 | Portugal | Entroncamento | Santarém | 16 | 50 | 16-02-2018 | 16-01-2019 | 334 | 120 | 335462 | 334930.8 | 2 | 334930.8 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2554 | 4713902 | EP-2018(5001)/10014 Rehabilitation of the Gym, Changing Rooms and IS of CED JRP | 45113000-2 | Siteworks | TRUE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 02-08-2018 | 21-12-2018 | 141 | 90 | 82000 | 81111.11 | 1 | 81111.11 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes | there were no changes
2555 | 4710457 | Intervention in the Ribeira Market | 45453100-8 | Refurbishment work | FALSE | 2018 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 27-06-2018 | 08-11-2019 | 499 | 120 | 173782.84 | 153852.27 | 1 | 134277.48 | 19574.79 | 114.5779 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension due to incompatibility of space release with summer cultural programs. | underwork
2556 | 4710179 | ecopark of sangalhos | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Anadia | Aveiro | 1 | 15 | 27-06-2018 | 14-12-2018 | 170 | 152 | 98578.22 | 94529.89 | 1 | 94529.89 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2557 | 4709491 | Requalification of pedestrian accesses in the area surrounding the center of Eiriz | 45000000-7 | Construction work | FALSE | 2018 | 2019 | Portugal | Baião | Porto | 13 | 30 | 30-07-2018 | 02-05-2019 | 276 | 180 | 273960 | 273953.5 | 2 | 273953.5 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Valia Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there are no changes to the time for completion of the project. | there were no changes to the value of the project
2558 | 4709334 | 2018/2 - DGEPIM - Requalification of the Barcarena Municipal Pool parking lot | 45233142-6, 45315600-4 | Road-repair works, Low-voltage installation work | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 21 | 27-07-2018 | 09-01-2020 | 531 | 90 | 176313.82 | 147201.01 | 1 | 152712.95 | -5511.94 | 96.3907 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | are the complementary works
2559 | 4708560 | Contract nº 6/18 - Conservation and Improvement of Municipal Buildings/Municipal School Park - Miscellaneous Waterproofing and Painting Works | 45261420-4 | Waterproofing work | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 15 | 25-07-2018 | 13-09-2019 | 415 | 420 | 190219 | 161686.16 | 1 | 161686.16 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the conclusion was brought forward due to the need for work in this area of ​​intervention being greater than expected.
2560 | 4708357 | Restoration, enhancement and expansion of the Portalegre Tapestry Museum - Guy Fino | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2018 | 2019 | Portugal | Portalegre | Portalegre | 12 | 14 | 13-07-2018 | 13-05-2019 | 304 | 210 | 354958.39 | 340050.48 | 2 | 326282.76 | 13767.72 | 104.2196 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Rating Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays in archeology work, ruin in worse condition than expected and finally need to detail the museology project | some works from the museology part were withdrawn, which resulted in underwork
2561 | 4706378 | Interventions on tours in various locations in the Municipality - Year 2018 | 45233160-8 | Paths and other metalled surfaces | FALSE | 2018 | 2019 | Portugal | Odivelas | Lisboa | 11 | 15 | 20-07-2018 | 28-06-2019 | 343 | 274 | 140000 | 140000 | 1 | 46329.55 | 93670.45 | 302.1829 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to add | there was a reversal in the amount of €93,670.45. this value was not used in the project because the end of the 2018 financial year was reached.
2562 | 4706069 | Contract for the Requalification of the New Social and Services Building at Ecoparque de Trajouce | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Cascais | Lisboa | 11 | 30 | 18-07-2018 | 02-04-2019 | 258 | 120 | 890000 | 790000 | 2 | 790000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change
2563 | 4700729 | Construction of the Headquarters Building of the Parish Council of Água Longa | 45210000-2 | Building construction work | FALSE | 2017 | 2021 | Portugal | Santo Tirso | Porto | 13 | 20 | 19-07-2018 | 22-12-2021 | 1252 | 180 | 492645.1 | 411111.32 | 2 | 344771.06 | 66340.26 | 119.2418 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: A - Price - with a weighting of 60% in the overall evaluation; B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: B1 - Work Schedule - with a weighting of 25% in the overall classification; B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the project there was a need to change constant works in the project as well as define new works in the project. | the need for some complementary work during the course of the project, as well as other project work was not carried out (underwork)
2564 | 4697351 | Contract nº 7/18 - Conservation and Improvement of Municipal Buildings/Municipal School Park - Electricity | 45315100-9 | Electrical engineering installation works | FALSE | 2018 | 2019 | Portugal | Amadora | Lisboa | 11 | 15 | 19-07-2018 | 18-12-2019 | 517 | 420 | 190626.1 | 162032.2 | 1 | 162032.2 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 60% Criterion related to cost Name: Price Weighting: 40% | 1 | 40 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | contingencies that led to the delay of the project: - the projects were conditioned by the unavailability of some of the intervened equipment. - various equipment held activities in the spaces where the projects took place and their normal functioning could not be disturbed on certain occasions.
2565 | 4695379 | EP-2018(5001)/10015 Improvement of IS and Recreation of the 1st Cycle of CED NAP | 45200000-9 | Works for complete or part construction and civil engineering work | TRUE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 26-07-2018 | 22-10-2018 | 88 | 80 | 105000 | 48880 | 1 | 48880 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | there were no changes | there were no changes
2566 | 4694481 | Construction contract for "Covered space for the EBI de Abrigada sports field" | 45223100-7 | Assembly of metal structures | FALSE | 2018 | 2019 | Portugal | Alenquer | Lisboa | 11 | 14 | 25-07-2018 | 07-11-2019 | 470 | 90 | 171967.73 | 171666.24 | 1 | 171456.26 | 209.98 | 100.1225 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | changes to the "field marking" project; material approval; reapplication of damaged infrastructure; non-integration of the project with the existing floor, with a constant floor dimension being represented in the elevations and sections of the project; analysis and acceptance on the part of the inspection consume time which in turn had the consequences of delays in production. | there were changes in the positioning of the volleyball field that did not allow the application of the posts. the projects related to the pine cone drains will be carried out by the cma.
2567 | 4692648 | Contract for Replacement of the Biogas Circuits of the WWTPs of Coimbrão and Ílhavo | 45222000-9 | Construction work for engineering works except bridges, tunnels, shafts and subways | FALSE | 2017 | 2019 | Portugal | Leiria | Aveiro | 1 | 44 | 20-04-2018 | 09-10-2019 | 537 | 135 | 350000 | 347755.74 | 2 | 384287.84 | -36532.1 | 90.4936 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension due to hurricane leslie and related to overworks | work related to improving installations (injection pipes, pots, valves and accessories) and underwork.
2568 | 4684055 | Requalification of the playground - grass synthetic floor - Paços de Gaiolo | 45236119-7 | Repair work on sports fields | TRUE | 2018 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 14 | 06-06-2018 | 29-11-2019 | 541 | 91 | 249768.74 | 249000 | 1 | 254071.17 | -5071.17 | 98.004 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0 Criterion related to cost name: price Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | graceful extension of term. | complementary works
2569 | 4683983 | Supply and replacement of the thermal production unit - chiller, in the headquarters building of the District Center of Portalegre | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Portalegre | Portalegre | 12 | 20 | 21-06-2018 | 28-11-2018 | 160 | 90 | 50000 | 24238.63 | 1 | 24238.63 | 0 | 100 | Best value for money: No Criterion related to quality Name: No Weighting: No Criterion related to cost Name: Price or cost assessment Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | without changes. | without changes.
2570 | 4682396 | The contract includes, in its general lines, the execution of the drainage and transport system of Carvalhal, which includes a set of five outfalls, an interceptor and an elevator system | 45232460-4 | Sanitary works | FALSE | 2018 | 2020 | Portugal | Mafra | Lisboa | 11 | 30 | 04-07-2018 | 19-03-2020 | 624 | 270 | 1035900 | 966968.51 | 2 | 929745.87 | 37222.64 | 104.0035 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40% Technical Value - 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | conditioning access to land for the execution of some parts of the project. | punctual optimization of the interceptor and outfall routes.
2571 | 4681176 | 5010021501/Drf-coms/2018 - "southern line - pine / somincor section - installation of the rct+tp system" | 45234160-5 | Catenary's construction works | FALSE | 2017 | 2020 | Portugal | Alcácer do Sal | Setúbal | 17 | 46 | 23-04-2018 | 06-07-2020 | 805 | 210 | 710000 | 539505 | 2 | 549695.85 | -10190.85 | 98.1461 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 50% - Technical value 30% - Security Management System 10% - Quality Control System 5% - Environmental Management System 5% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2572 | 4680945 | Urban Regeneration of Praça da Liberdade - Building - 1st Phase - Reguengos de Monsaraz Tourist Reception Center - Central Café | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2018 | 2019 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 13-07-2018 | 29-05-2019 | 320 | 180 | 190393.41 | 179831.85 | 1 | 179480.86 | 350.99 | 100.1956 | Best value for money: Yes Criterion related to quality Name: Valia Técnica Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the stipulated time frame. | underwork
2573 | 4680004 | Work contract n.º 04/2018/dpgom - requalification of the municipal market of alcanena | 45213141-3 | Covered market construction work | FALSE | 2018 | 2021 | Portugal | Alcanena | Santarém | 16 | 24 | 23-07-2018 | 11-02-2021 | 934 | 365 | 1615758.33 | 1609752.31 | 3 | 1734796.62 | -125044.31 | 92.792 | Best value for money: No Criterion related to quality Name: 0 Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | last measurements 03/19/2020. | underwork worth €11,950.91
2574 | 4679748 | Electricity production system using photovoltaic panels (Buildings: C, E and G, Lumiar Campus) | 45261215-4 | Solar panel roof-covering work | FALSE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 18-07-2018 | 17-10-2018 | 91 | 60 | 287000 | 169015.61 | 1 | 169015.61 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Evaluation of price or cost as a single aspect Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project took place within the established maximum execution period.
2575 | 4679205 | Work to improve streets , roads and paths in specific areas of the municipality of Albufeira. | 45233252-0 | Surface work for streets | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 17-07-2018 | 28-08-2019 | 407 | 365 | 250000 | 191000 | 1 | 191000 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the alteration to the execution period of the project is due to delays on the part of the contractor.
2576 | 4678263 | Work contract n.º 05/dpgom/2018 - requalification of the minde road - serra de santo antónio | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Alcanena | Santarém | 16 | 14 | 09-07-2018 | 09-01-2019 | 184 | 90 | 295000 | 265882.52 | 2 | 265882.52 | 0 | 100 | Best value for money: No Criterion related to quality Name: No Weighting: 0% Criterion related to cost Name: Most economically advantageous proposal Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | schedule for provisional acceptance
2577 | 4678068 | Exterior work - E. B. 1st cycle of Além - Gavião | 45236290-9 | Repair work on recreational areas | FALSE | 2018 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 6 | 10-07-2018 | 08-10-2018 | 90 | 90 | 112822.87 | 105073.31 | 1 | 101664.13 | 3409.18 | 103.3534 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | underwork worth €3,409.18.
2578 | 4677406 | EP-2018(5001)/10013 Rehabilitation of the I. S. Cappa st.ª Isabel | 45113000-2 | Siteworks | TRUE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 18-07-2018 | 12-11-2018 | 117 | 80 | 60000 | 52631.3 | 1 | 52631.3 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2579 | 4677319 | Contract for "Expansion of the coverage of the IGOT Building" | 45000000-7 | Construction work | FALSE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 14 | 08-05-2018 | 30-10-2018 | 175 | 90 | 341578.98 | 341408.89 | 2 | 349771.86 | -8362.97 | 97.609 | Best value for money: No Criterion related to quality Name: N/A Weighting: N/A Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the execution of the contract to be concluded-n.º1b) art.º74 Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | during the execution of the project it was verified that a fixing base that was thought to be a concrete structural element was not, a fact that was not possible to detect in the design phase | the need to carry out complementary work
2580 | 4677131 | Work to Rehabilitate the Barrada Radical Space | 45112711-2 | Landscaping work for parks | FALSE | 2018 | 2020 | Portugal | Alenquer | Lisboa | 11 | N/A | 26-06-2018 | 26-08-2020 | 792 | 90 | 219304.39 | 218920.07 | 1 | 201399.62 | 17520.45 | 108.6993 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | verification of the need to study changes to be introduced to the project and covid-19. | measurement errors, changes to the initial project, works by decision of the client.
2581 | 4674866 | The objective of this undertaking consists in the construction of a gravity network in a extension of 3,537.0 meters of wastewater collectors, 165 home extensions, including still the construction of 4 stations | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Vagos | Aveiro | 1 | N/A | 05-07-2018 | 28-06-2019 | 358 | 180 | 1009000 | 605400.01 | 2 | 576306.29 | 29093.72 | 105.0483 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline is conditioned by project reasons | contracted works not performed
2582 | 4674271 | Contract 12/2017/dpgom - urban requalification of the square surrounding the public transport stop in the village of alcanena | 45211360-0 | Urban development construction work | FALSE | 2018 | 2019 | Portugal | Alcanena | Santarém | 16 | 30 | 19-07-2018 | 20-11-2019 | 489 | 270 | 487422.32 | 450423.66 | 2 | 475569.93 | -25146.27 | 94.7124 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension 57 days | over and underwork
2583 | 4673968 | Construction of WWTP's and EE's. | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | São João da Pesqueira | Viseu | 20 | 20 | 02-07-2018 | 01-04-2020 | 639 | 300 | 926711.04 | 733435.56 | 2 | 709078.89 | 24356.67 | 103.435 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 70%; Planning 30%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | construction of the wwtp of riodades lot no. 1, the contract had the provisional reception on february 10, 2020, as well as the final bill, with two extensions of the term of 60 days and another of 24 days. construction of the wwtp in casais do douro lot no. 2, the contract had the provisional reception on april 1, 2020, as well as the final bill, with an extension of 86 days. construction of sarzedinho lot 3 wwtp, the contract had the provisional reception on march 9, 2020, as well as the final bill, with two extensions, one of 60 days and the other of 30 days. | construction of the wwtp in riodades lot 1, the contract had underwork worth €16,076.18. construction of the wwtp in casais do douro lot 2, the contract had underwork worth €3,610.00. construction of sarzedinho wwtp lot 3, the contract had underwork worth €4,670.00.
2584 | 4673856 | Rehabilitation works of a residential building in the Historic Area of ​​Porto, located at street of Reboleita nº 29 (EM.001.2018.058) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2020 | Portugal | Porto | Porto | 13 | 21 | 12-07-2018 | 20-05-2020 | 678 | 270 | 390000 | 388847.29 | 2 | 385286.73 | 3560.56 | 100.9241 | Best value for money: Yes Criterion related to quality Name: technical value of the proposal Weighting: 80% Criterion related to cost Name: N/A Weighting: 20% | 1 | 20 | 5 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was delayed, and the deadline was not met, a contractual sanction was applied. | eo in the amount of €4,175.27 and work not carried out in the amount of €7,735.83
2585 | 4673779 | Rehabilitation works of blocks A to F of Bairro do Carvalhido (EM.001.2018.050) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 16 | 16-07-2018 | 17-05-2019 | 305 | 270 | 600000 | 587515.66 | 2 | 589833.14 | -2317.48 | 99.6071 | Deadline extension notice | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A |  | complementary work worth €9,504.87 and unfinished work worth €7,187.39
2586 | 4673638 | Assembly and disassembly of the support site for the work in general; Demolitions; Masonry Construction; Construction of plasterboard walls and ceilings; Coatings; Full cover replacement | 45454000-4 | Restructuring work | TRUE | 2018 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 17-07-2018 | 13-06-2019 | 331 | 122 | 220000 | 219902.04 | 1 | 219902.04 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | a work suspension notice was duly approved.
2587 | 4672493 | Repaving of a section of the Ribeira/Soalhães road | 45233223-8 | Carriageway resurfacing works | FALSE | 2018 | 2018 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 06-06-2018 | 23-10-2018 | 139 | 120 | 262300 | 244553.65 | 1 | 244553.65 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project finished ahead of schedule.
2588 | 4670797 | Refurbishment contract for the Cerco Health Unit (USF Novo Sentido) | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2021 | Portugal | Porto | Porto | 13 | 24 | 26-06-2018 | 15-04-2021 | 1024 | 270 | 1096326.52 | 1090382.38 | 3 | 1090382.38 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70% B - Technical value of the proposal 30%: B1 - Descriptive memory 10% B2 - Work, labor, equipment and payment plans 10% B3 - Safety to be implemented in the work (technical note) 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - difficulties in hiring labor; - covid-19 pandemic | underwork
2589 | 4670575 | AE019-E1 - Ortigosa Interceptor - The contract aims to build a gravity interceptor in the parish of Rossas, Municipality of Arouca. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Arouca | Aveiro | 1 | N/A | 12-07-2018 | 30-04-2019 | 292 | 120 | 236100 | 204587.15 | 1 | 195463.5 | 9123.65 | 104.6677 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: A) price = 60%; B) Technical value of Proposal = 40%, with the following subfactors: B1) Work execution methodology = 20%; B2) Detail and consistency of the work plan = 20%, containing the sub-subfactors B.2.1) Work schedule 10% and B.2.2) Means plan = 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract started at a slow pace in order to allow the owners to harvest the corn, which was only concluded in mid-october
2590 | 4670475 | Contract 28 - EB School Interface - 2,3 Miguel Torga in Sabrosa | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Sabrosa | Vila Real | 19 | 20 | 17-07-2018 | 17-01-2019 | 184 | 90 | 188524.24 | 185603.18 | 1 | 199797.18 | -14194 | 92.8958 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension requests nipg 9841/18 and 11307/18. (time)
2591 | 4669570 | Rehabilitation / Works on the Sanitation Network, water network and ETAR of the Founded | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2021 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 17-07-2018 | 15-03-2021 | 972 | 730 | 1839000 | 1563715.87 | 3 | 1537239.04 | 26476.83 | 101.7224 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of some connections, adverse weather conditions, tests, rehearsals, training. | underwork
2592 | 4668713 | The work to be carried out involves all the work necessary to remove the existing fiber cement covering and replace it with a new sandwich panel covering. | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2019 | Portugal | Valongo | Porto | 13 | 9 | 12-07-2018 | 13-09-2019 | 428 | 60 | 84000 | 76432.5 | 1 | 71402.18 | 5030.32 | 107.0451 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | the approval of suppression of works in the amount of € 5,030.36
2593 | 4668656 | The object of this contract is the qualification and expansion of the pedestrian network in Vila Verde - south entrance | 45233161-5 | Footpath construction work | FALSE | 2017 | 2019 | Portugal | Vila Verde | Braga | 3 | N/A | 17-07-2018 | 06-12-2019 | 507 | 150 | 221245.86 | 175950 | 1 | 178661.73 | -2711.73 | 98.4822 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | due to issues associated with the development of the project, namely those raised by the infraestruturas de portugal entities, it became necessary to suspend the project for a period of 171 days | non-execution of all work on some items (work and less worth €2,436.85). and final price review (addition of €5,248.58.
2594 | 4667008 | 100% Quality - Reconstruction of the retaining wall at street of Igreja Velha, S. Mamede of Infesta - EDOC/2016/55712 | 45220000-5 | Engineering works and construction works | FALSE | 2016 | 2018 | Portugal | Matosinhos | Porto | 13 | 36 | 28-03-2017 | 05-07-2018 | 464 | 90 | 350000 | 210000.01 | 1 | 210000.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (60% weighting) b) Technical value (40% weighting) | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
2595 | 4655399 | landscaping jobs for parks | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2021 | Portugal | Lagos | Faro | 8 | 40 | 07-02-2018 | 20-08-2021 | 1290 | 540 | 1417501.11 | 1157283.18 | 3 | 1198728.67 | -41445.49 | 96.5425 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to difficulties in obtaining qualified labor and delays in the delivery of materials and equipment by suppliers in some phases of the project
2596 | 4655065 | Contract for the execution of water supply lines. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 25-05-2018 | 09-12-2019 | 563 | 213 | 30000 | 26300 | 1 | 26300 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the execution of the contract to be concluded. Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2597 | 4654203 | Floating pier to support fishing on Ilha da Culatra | 45241500-3 | Wharf construction work | FALSE | 2018 | 2019 | Portugal | Faro | Faro | 8 | 18 | 25-06-2018 | 11-02-2019 | 231 | 115 | 216500 | 211320 | 1 | 211320 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | consignment date 07/25/2018
2598 | 4643884 | 2017.116.08.C1 - SFP Setúbal - Structured Network in the Aeronautics Section | 45000000-7 | Construction work | TRUE | 2018 | 2018 | Portugal | Setúbal | Setúbal | 17 | 15 | 11-06-2018 | 21-09-2018 | 102 | 60 | 25000 | 21279.12 | 1 | 21279.12 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 10 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2599 | 4643613 | The work to be carried out involves all the work necessary to remove the existing fiber cement covering and replace it with a new sandwich panel covering. | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2018 | Portugal | Valongo | Porto | 13 | 9 | 12-07-2018 | 15-11-2018 | 126 | 60 | 59300 | 49909.68 | 1 | 49836.58 | 73.1 | 100.1467 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of additional work and underwork (additional contract on 10.12.2018 | approval of additional work worth €1,565.45 and underwork worth €1,639.19
2600 | 4641938 | Contract for the repair of ruptures in pipes and branches of the water supply network in the municipality of Albufeira | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Albufeira | Faro | 8 | 14 | 11-07-2018 | 20-05-2020 | 679 | 152 | 141000 | 115255 | 1 | 115255 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: price as the only aspect of the performance of the contract to be concluded Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change | no change
2601 | 4641327 | Execution of remodeling work, including demolition, masonry, roofing (waterproofing and finishing), replacement of gaps, finishing. Exterior arrangements are also contemplated | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Póvoa de Lanhoso | Braga | 3 | 24 | 21-03-2018 | 01-10-2019 | 559 | 365 | 2250000 | 2249499.92 | 3 | 2435950.31 | -186450.39 | 92.3459 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical Quality - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need for a partial suspension of work in blocks a, c and d and exterior repairs, due to the need to award the project for the "contract work to supply errors and omissions for the requalification of the eb 2,3 school professor gonçalo sampaio " that interfered with the projects of the present contract. despite the suspension lasting 72 days, the contractor was able to anticipate the completion of the project by 8 days, enabling the start of the 2019/2020 school year. | the occurrence of the need to order the execution of work to supply errors and omissions in the project and also the need to order the execution of unpredictable work.
2602 | 4640807 | On the Escarpment: cleaning and removal of loose materials, installation of a system of slope protection nets, execution of nailing and anchoring, dismantling of rocky material, construction / reconstruction | 45243110-6 | Cliff-stabilisation works | FALSE | 2016 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 11-07-2018 | 17-09-2021 | 1164 | 240 | 3500000 | 2911024.46 | 3 | 3298623.44 | -387598.98 | 88.2497 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical quality of the proposal - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | prorogation and work suspension notices were duly approved. | the completion of the project resulted in more work worth €235,954.70, work due to errors and omissions worth €7,258.22, underwork worth €16,879.50 and a price review with definitive indices was determined in the amount of €161,265.53.
2603 | 4619957 | The work to be carried out involves all the work necessary to remove the existing fiber cement covering and replace it with a new sandwich panel covering. | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2019 | Portugal | Valongo | Porto | 13 | 9 | 06-07-2018 | 28-05-2019 | 326 | 60 | 89400 | 79959.86 | 1 | 74314.62 | 5645.24 | 107.5964 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approved a grace period extension of 30 days. the last measurement report dates from 12.10.2018, however there was some delay in scheduling the provisional reception. | approved by order of 09.11.2018 underwork worth €5,645.24
2604 | 4617788 | Contract for "Beira Baixa Line - Rehabilitation of Santa Margarida Line I" (contracts No. 5010029465) | 45234100-7 | Railway construction works | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 40 | 25-06-2018 | 10-10-2019 | 472 | 120 | 336562 | 242615.55 | 1 | 261311.23 | -18695.68 | 92.8454 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | during the course of the project, there was a need to carry out more work in an amount not foreseen in the contract, which was due to an unforeseen circumstance and which cannot be technically inseparable from the object of the contract and which are strictly necessary for the completion of the project, pursuant to paragraph 1 of article 370 of the "public procurement code". during the course of the project, when the replacement work of wooden sleepers for concrete and the stripping of ballast on line i of santa margarida were being finalized, and taking into account that amv 4 and 5 of the station were going to be mechanically attacked, it was verified that in an extension of about 27 mlv from the heel of the cross of both amvs to the connection with the v line, the wooden sleepers were in very bad condition, a situation that would not allow the execution of the heavy mechanical attack accordingly. in this sense, a total of 54 mlv of the track were stripped and 50 wooden sleepers were replaced with regenerated bi-block concrete. with this need for work, there was an increase of 50 un in replacing wooden sleepers with biblock concrete (item 2.1.1); 54 mlv of ballast stripping (item 2.6.1); 54 mlv from filling attacks (item 2.3.1) and 54 mlv from conservation attack (item 2.4.1). the value of the additional work due to unforeseen circumstances, in accordance with paragraph 1 of article 370, was calculated at eur 6,574.68, representing 2.71% of the value of the contract.
2605 | 4616778 | The work to be carried out involves all the work necessary to remove the existing fiber cement covering and replace it with a new sandwich panel covering. | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2019 | Portugal | Valongo | Porto | 13 | 9 | 06-07-2018 | 13-09-2019 | 434 | 60 | 114600 | 97073.14 | 1 | 90630.05 | 6443.09 | 107.1092 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | was due to graceful extensions of 20 and 37 days respectively. the 20-day one due to out of stock at the factories and the 17-day one due to bad weather conditions | approval of suppression of work (€ 6,443.10)
2606 | 4615917 | 5010032000/Drf-ee/2018 - "anticorrosive protection of metal bridges on the lower edge line, phase 1" | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2017 | 2020 | Portugal | Abrantes | Santarém | 16 | 42 | 14-05-2018 | 29-10-2020 | 899 | 210 | 900000 | 614957.46 | 2 | 627309.69 | -12352.23 | 98.0309 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | anticipation work execution deadline of 32 days | price review
2607 | 4615463 | The purpose of this contract is to carry out all the work necessary to remove the existing fiber cement roof and replace it with a new sandwich panel roof | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2019 | Portugal | Valongo | Porto | 13 | 9 | 06-07-2018 | 07-06-2019 | 336 | 60 | 131000 | 115516.35 | 1 | 110528.3 | 4988.05 | 104.5129 | Best value for money: Yes Criterion related to quality name: quality Weighting: 0% Criterion related to cost name: price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | free extension of the 20-day period, due to the outage of stock at the factories in august, a fact that made the delivery of materials unfeasible, resulting in the delay of the project on the contract | approval of works at 4,988.05 less
2608 | 4614413 | Improvement of housing in Sta. Cross of Flowers | 45262500-6 | Masonry and bricklaying work | FALSE | 2018 | 2018 | Portugal | Santa Cruz das Flores | Região Autónoma dos Açores | 15 | 12 | 10-07-2018 | 18-12-2018 | 161 | 60 | 138800 | 138800 | 1 | 133981.26 | 4818.74 | 103.5966 | Best value for money: No Criterion related to quality Name: The constants of the Procedure Program Weighting: 0% Criterion related to cost Name: The constants of the Procedure Program Weighting: 0% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | agreement between the parties | according to the bidder's proposal
2609 | 4613494 | Preventive maintenance works in blocks 15 to 24 of Bairro das Campinas | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 29-06-2018 | 30-01-2019 | 215 | 180 | 790000 | 770053.11 | 2 | 765815.52 | 4237.59 | 100.5533 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 80% Criterion related to cost Name: Price Weighting: 20% | 1 | 20 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the stipulated time frame. | work not carried out worth €4,237.59
2610 | 4613269 | Rehabilitation of the Residential Building in the Historic Area of ​​Porto, located at street of Cima do Muro n.º 18 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 21 | 19-06-2018 | 11-06-2019 | 357 | 210 | 269000 | 267214.4 | 2 | 278013.42 | -10799.02 | 96.1156 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal (methodology, work program and safety) Weighting: 20% Criterion related to cost Name: Price Weighting: 80% | 1 | 80 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extension | complementary work worth €13,924.86 and unfinished work worth €3,125.84
2611 | 4612302 | Contract " Leixões Line - Leixões Station - Complete replacement of rail and sleepers on lines R6 and R10 " (eContracts n.º 5010034424) | 45234100-7 | Railway construction works | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 20 | 09-07-2018 | 04-06-2019 | 330 | 90 | 350000 | 298425.85 | 2 | 298425.85 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (80% weighting) - FPRECIO b) Technical value (20% weighting) - FVT | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register
2612 | 4611850 | Construction of 256 Catacombs in the Cemetery June 16 - Year 2018 | 45215400-1 | Cemetery works | FALSE | 2018 | 2018 | Portugal | Olhão | Faro | 8 | 15 | 03-07-2018 | 13-11-2018 | 133 | 90 | 75000 | 62840 | 1 | 62840 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there were no changes. | there were no changes.
2613 | 4610212 | Improvement of the M 544 from Fornos do Pinhal to Santa Valha | 45233220-7 | Surface work for roads | FALSE | 2018 | 2018 | Portugal | Valpaços | Vila Real | 19 | 15 | 04-07-2018 | 23-11-2018 | 142 | 90 | 103826.1 | 80915 | 1 | 80915 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2614 | 4596665 | PRC_0398/2017_GAE-AR0373 - Contract for the execution of the Interception and Elevation System in Argela | 45232411-6 | Foul-water piping construction work | FALSE | 2018 | 2020 | Portugal | Caminha | Viana do Castelo | 18 | 47 | 29-06-2018 | 13-03-2020 | 623 | 120 | 250000 | 204944.54 | 1 | 244093.28 | -39148.74 | 83.9616 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractual term of the contract increased significantly, compared to what was foreseen, mainly due to the two suspensions of the execution of the project carried out. in any case, it should be noted that the extension of the contractual term did not translate into greater charges for the owner of work, nor conditioned the connections of the waste water network in "low" of the municipality of caminha | the extra work (which changed the estimated award value) was due to an “imposition” by infraestruturas de portugal, s.a., for which they became necessary for the completion of the project following an unforeseen circumstance and also because they were not technical and economically separable from the initial contract without serious inconvenience to the developer. underwork has been cleared
2615 | 4596533 | PRC_0014/2017_EGA-AA0350 - Contract for the Supply and Assembly of Medium Voltage Frequency Converters in the Pumping Station of Casais (Vila do Conde) | 45232100-3 | Ancillary works for water pipelines | FALSE | 2018 | 2019 | Portugal | Vila do Conde | Porto | 13 | 20 | 28-06-2018 | 12-11-2019 | 502 | 240 | 600000 | 570696 | 2 | 570696 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | no change
2616 | 4596111 | Contract for various repairs on E B 2,3 in the municipality of Albufeira | 45454000-4 | Restructuring work | FALSE | 2018 | 2019 | Portugal | Albufeira | Faro | 8 | 14 | 19-06-2018 | 08-10-2019 | 476 | 70 | 180135.64 | 143600 | 1 | 149924 | -6324 | 95.7819 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reasons not attributable to the contractor
2617 | 4591089 | EP-2018(5001)/10004 Replacement of Mechanics Workshop Cover - CED PM | 45261200-6 | Roof-covering and roof-painting work | FALSE | 2018 | 2019 | Portugal | Lisboa | Lisboa | 11 | 14 | 02-07-2018 | 29-04-2019 | 301 | 120 | 140000 | 99985 | 1 | 103427.29 | -3442.29 | 96.6718 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | existence of complementary work | complementary work in the amount of €3,842.29 and penalty for non-compliance with the contractual term in the amount of €400.00
2618 | 4589883 | Execution of pedestrian routes in the towns of Cotovia and Sampaio, located in the parish of Castelo, municipality of Sesimbra. | 45233161-5 | Footpath construction work | FALSE | 2017 | 2020 | Portugal | Sesimbra | Setúbal | 17 | 30 | 19-01-2018 | 06-10-2020 | 991 | 120 | 239398.53 | 230716.63 | 1 | 256608.31 | -25891.68 | 89.91 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 120 days of initial execution period; 105 days of deadline extension, under the terms of article 374 of the "public procurement code" and 150 days of deadline extension under the terms of art. a), paragraph 1, article 311 and al. b), of article 312 of the "public procurement code". the communication of approval of the pss to the contractor occurred on 04/09/2018 and the end of the contract, considering the described deadline extensions, occurred on 04/18/2019. | overwork, errors and omissions, underwork and price revisions.
2619 | 4585351 | The object of this contract is the design and construction of the Rio de Moinhos wastewater treatment plant, including the work phase, carrying out the commissioning activities | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2018 | 2021 | Portugal | Borba | Évora | 7 | 25 | 25-06-2018 | 10-11-2021 | 1234 | 480 | 1350000 | 1114368.62 | 3 | 1137359.92 | -22991.3 | 97.9785 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | legal extension of the 60-day deadline for completing civil construction works. | change in the value of the project resulting from the price review carried out.
2620 | 4583561 | FMUP Floor 3 and Floor 4 Renovation Contract | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2021 | Portugal | Porto | Porto | 13 | 37 | 14-06-2018 | 25-02-2021 | 987 | 360 | 494500 | 493952.58 | 2 | 504636.89 | -10684.31 | 97.8828 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Global price proposed for the Contract - 40 🇧🇷 Technical value of the proposal - 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | constraints in the execution of some works, due to the fact that the building is always in operation. | need to perform additional work and mandatory price review.
2621 | 4583425 | Contract for: "Improvement / Rehabilitation of the Pavement of Estrada do Miradouro, in Benavente - 1st Phase" | 45233220-7 | Surface work for roads | FALSE | 2018 | 2019 | Portugal | Benavente | Santarém | 16 | 24 | 12-06-2018 | 18-12-2019 | 554 | 60 | 160300 | 124784.5 | 1 | 132321.82 | -7537.32 | 94.3038 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was carried out within the deadline, however, the provisional reception was scheduled after the deadline. | the value of the price review is added to the value of the award, in the amount of €7,537.32.
2622 | 4582104 | Rehabilitation contract for the UP Faculty of Law building | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2021 | Portugal | Porto | Porto | 13 | 48 | 25-06-2018 | 24-02-2021 | 975 | 365 | 852132.14 | 722241.01 | 2 | 793071.32 | -70830.31 | 91.0689 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Contract - 40 🇧🇷 b) Technical value of the proposal - 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the project schedule. | need to perform more work and mandatory price review
2623 | 4580320 | AA009-E1 - Reformulation of the Bateira Bridge intake | 45240000-1 | Construction work for water projects | TRUE | 2018 | 2019 | Portugal | Castelo de Paiva | Aveiro | 1 | 24 | 14-06-2018 | 30-12-2019 | 564 | 150 | 180000 | 177854.72 | 1 | 177854.72 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | weather and river flow conditions conditioned the submerged works
2624 | 4579769 | Urban Revitalization Contract in the Village of Martim Longo | 45112700-2 | Landscaping work | FALSE | 2018 | 2019 | Portugal | Alcoutim | Faro | 8 | 20 | 22-06-2018 | 06-11-2019 | 502 | 365 | 341556.7 | 281895.79 | 2 | 277649.87 | 4245.92 | 101.5292 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 50% Criterion related to cost Name: Price Weighting: 50% | 1 | 50 | 5 | FALSE | Complete fulfillment of the contract | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the change to the deadline for the project was due to the provisional reception. | due to underwork and revision of prices
2625 | 4578846 | 2017/193 - DGEPIM - Exterior work on street Eugénio dos Santos, José Régio and Carlos Mardel, Oeiras | 45233200-1, 45212100-7, 45112700-2, 45316100-6, 45262310-7, 45232452-5, 45111000-8 | Various surface works, Construction work of leisure facilities, Landscaping work, Installation of outdoor illumination equipment, Reinforced-concrete work, Drainage works, Demolition, site preparation and clearance work | FALSE | 2017 | 2021 | Portugal | Oeiras | Lisboa | 11 | 30 | 18-06-2018 | 05-05-2021 | 1052 | 120 | 437902 | 306531.41 | 2 | 263317.39 | 43214.02 | 116.4114 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2626 | 4577680 | 2018/12 - DGEPIM - Conservation and repair of pavements in Barcarena and Queijas | 45233142-6 | Road-repair works | FALSE | 2018 | 2020 | Portugal | Oeiras | Lisboa | 11 | 24 | 04-06-2018 | 16-11-2020 | 896 | 730 | 299449.5 | 219885.32 | 1 | 219885.32 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: N/A Criterion related to cost Name: N/A Weighting: N/A | 0 | 0 | 5 | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2627 | 4575513 | The work to be carried out involves all the work necessary for waterproofing the roofs, rainwater, treatment of platbands, gutters, lanterns, painting, accessory works, lighting equipment | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2018 | 2020 | Portugal | Valongo | Porto | 13 | 15 | 18-06-2018 | 06-02-2020 | 598 | 120 | 329584.99 | 240821.3 | 1 | 219991.3 | 20830 | 109.4686 | Best value for money: No Criterion related to quality name: quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | there was no change to the execution deadline, the last measurement report dates from 07.11.2018, however there was a delay in scheduling the provisional reception for reasons relating to constraints on the financing of the contract. | approval of underwork, in the amount of €20,830.00 (order of 20.02.2019)
2628 | 4575381 | 2017.116.05.C1. - SFP Setubal - Replacement of exterior lighting and emergency lighting | 45000000-7 | Construction work | TRUE | 2018 | 2018 | Portugal | Setúbal | Setúbal | 17 | 15 | 18-05-2018 | 30-08-2018 | 104 | 90 | 65000 | 39000.01 | 1 | 39000.01 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30% Criterion related to cost Name: Price+deadline Weighting: 50%+20% | 1 | 50 | 10 | FALSE | Complete fulfillment of the contract | 15 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completed before contractual deadline
2629 | 4573842 | DPES-CP-9/2017 - Improvement of pressure management and occasional rehabilitation of pipelines in various locations in the municipality of Coimbra | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2021 | Portugal | Coimbra | Coimbra | 6 | 28 | 20-06-2018 | 28-01-2021 | 953 | 270 | 450000 | 413803.01 | 2 | 396766.51 | 17036.5 | 104.2938 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: Those indicated in point 15 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there are always delays due to being dependent on other entities and the weather not allowing work | underwork has taken place
2630 | 4573626 | Refurbishment contract for the Peniche Health Center - ACES Oeste Norte | 45113000-2 | Siteworks | FALSE | 2017 | 2019 | Portugal | Peniche | Leiria | 10 | 40 | 01-03-2018 | 20-08-2019 | 537 | 180 | 798500 | 773000 | 2 | 773000 | 0 | 100 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the total term of the contract remained at 180 days, however it was suspended, due to changes in the health units, to make available the spaces to be intervened | price review
2631 | 4572185 | PO 235/2017 - Himalaya Creativity Workshops (Building Rehabilitation) | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2018 | 2021 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 26 | 22-06-2018 | 22-11-2021 | 1249 | 395 | 1073580 | 1000608.65 | 3 | 1106858.57 | -106249.92 | 90.4008 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: 50% - Lowest global price 50% - Technical value of the proposal These criteria are decomposed into sub-criteria, in accordance with article 12 of the Procedure Program | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | objective modifications to the project, errors and omissions and delays attributable to the contractor.
2632 | 4571248 | Reconstruction and Expansion of the Elementary School of Santa Luzia - Reception School | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2019 | Portugal | Celorico da Beira | Guarda | 9 | 73 | 18-06-2018 | 30-10-2019 | 499 | 365 | 323319.32 | 304439.36 | 2 | 302897.18 | 1542.18 | 100.5091 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the execution period of the contract for 45 days. | underwork worth €1,542.21.
2633 | 4568510 | The object of this contract is the execution of the grooving of the runway at the airfield on the island of Pico, with a view to improving the grip conditions, as well as the conditions for draining dry water. | 45235111-4 | Airfield pavement construction work | FALSE | 2017 | 2018 | Portugal | São Roque do Pico | Região Autónoma dos Açores | 15 | 18 | 28-03-2018 | 28-09-2018 | 184 | 90 | 349000 | 327250 | 2 | 327250 | 0 | 100 | lowest price If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) Click here to enter text. | 2 | 100 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
2634 | 4567853 | Rehabilitation of Children's Playgrounds in the Municipality | 45112700-2 | Landscaping work | FALSE | 2017 | 2021 | Portugal | Tavira | Faro | 8 | 24 | 25-05-2018 | 16-07-2021 | 1148 | 180 | 272873.39 | 199602.38 | 1 | 203550.81 | -3948.43 | 98.0602 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of deadline and delivery of documentation | underwork worth -40.00€ and definitive price review worth €3,988.43 (positive).
2635 | 4566811 | Contract 24/2017/dpgom - alcanena school center | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2021 | Portugal | Alcanena | Santarém | 16 | 30 | 08-06-2018 | 21-07-2021 | 1139 | 450 | 3016845.43 | 2956077.89 | 3 | 3192510.57 | -236432.68 | 92.5941 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 244 day extension | additional contracts
2636 | 4566076 | Contract for a rainwater wastewater network - street of Alegria - Ferreiras. | 45232450-1 | Drainage construction works | FALSE | 2018 | 2018 | Portugal | Albufeira | Faro | 8 | 14 | 20-06-2018 | 27-11-2018 | 160 | 60 | 72040.27 | 54624.36 | 1 | 54624.36 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price as the only aspect of the performance of the contract to be signed Weighting: 100% | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 12 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delays by the contractor
2637 | 4564718 | Requalification of Cais do Carvão | 45236290-9 | Repair work on recreational areas | FALSE | 2018 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 15 | 17-05-2018 | 08-03-2019 | 295 | 180 | 341890 | 277000 | 2 | 277000 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 3 | FALSE | Complete fulfillment of the contract | 11 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | work on the coastline subject to weather conditions unfavorable to the continuous execution of the contract.
2638 | 4564564 | PEDU - Strategic Urban Development Plan: Social Housing Rehabilitation PER Sampaio | 45321000-3 | Thermal insulation work | TRUE | 2018 | 2019 | Portugal | Valongo | Porto | 13 | 24 | 18-06-2018 | 31-05-2019 | 347 | 180 | 339000 | 322862.04 | 2 | 322862.04 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | approval of a 52-day deadline extension
2639 | 4561752 | Improvement of protection structures and access to Pier Bridges n.º 1 and 2 - Matosinhos Fishing Port | 45223110-0 | Installation of metal structures | FALSE | 2018 | 2019 | Portugal | Matosinhos | Porto | 13 | 14 | 01-06-2018 | 18-11-2019 | 535 | 90 | 92000 | 91936.62 | 1 | 91936.62 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Quality of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | date of the final account of the project
2640 | 4561496 | Execution of urban wastewater collectors in PVC pipes; execution of standard and special model manholes and drop boxes; execution of wastewater lift pipes | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Sesimbra | Setúbal | 17 | 30 | 05-02-2018 | 02-11-2020 | 1001 | 360 | 543700 | 519730.19 | 2 | 594079.81 | -74349.62 | 87.4849 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 360 days of initial lead time; 145 days of extension of the deadline, under the terms of article 374 of the "public procurement code" and another 19 days of extension of the deadline under the terms of paragraph a), paragraph 1, article 311 and paragraph b), article 312 .º of the "public procurement code". the communication of approval of the pss to the contractor occurred on 05/14/2018 and the end of the contract, considering the described deadline extensions, occurred on 10/19/2019. | overwork, errors and omissions, restoring financial balance, underwork and regular price revisions
2641 | 4559470 | EP-2018(5001)/10009 Rehabilitation of the Outdoor Sports Area of ​​the CED MP | 45112720-8 | Landscaping work for sports grounds and recreational areas | TRUE | 2018 | 2020 | Portugal | Lisboa | Lisboa | 11 | 14 | 12-06-2018 | 09-01-2020 | 576 | 120 | 315000 | 313799.48 | 2 | 313799.48 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical Value of the Proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A | adverse weather conditions
2642 | 4559111 | Urban infrastructures of the Souto Industrial Zone | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2018 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 05-06-2018 | 26-11-2019 | 539 | 243 | 500000 | 454187.58 | 2 | 467477.5 | -13289.92 | 97.1571 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | deadline extensions | over and underwork
2643 | 4557641 | Rehabilitation of water and electricity supply networks on the wharf bridges | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2019 | Portugal | Portimão | Faro | 8 | 20 | 23-05-2018 | 07-01-2019 | 229 | 60 | 119805.63 | 118784 | 1 | 127310.1 | -8526.1 | 93.3029 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | complementary work and suspension of work resulting from the need to study changes to the project. | complementary works
2644 | 4552950 | Improvement of cube pavements in urban streets - Paving on street and cross-street of Moinhos, street of Paços de Cima and street of Escola - Parish of Torno | 45233140-2 | Roadworks | FALSE | 2018 | 2019 | Portugal | Lousada | Porto | 13 | 9 | 11-06-2018 | 04-01-2019 | 207 | 40 | 30541 | 22247.5 | 1 | 16197.3 | 6050.2 | 137.3531 | Best value for money: No Criterion related to quality Name: No criteria Weighting: 0% Criterion related to cost Name: Lowest price (point b) article 74 CCP) Weighting: 100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 23 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A |  | underwork
2645 | 4550921 | Requalification of the Kindergarten Building | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2017 | 2018 | Portugal | Vila Nova de Cerveira | Viana do Castelo | 18 | 17 | 28-05-2018 | 31-10-2018 | 156 | 120 | 250000 | 220408.79 | 1 | 220408.79 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: In accordance with article 21 of the Program of Contest. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2646 | 4547765 | Removal of the existing roof, with the exception of the main support structure, which will be duly treated and supply and installation of a new roof, including the secondary support structure | 45261213-0 | Metal roof-covering work | FALSE | 2017 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 11-06-2018 | 07-01-2020 | 575 | 90 | 435000 | 381053.81 | 2 | 386542.22 | -5488.41 | 98.5801 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Quality of the Proposal (QTP) - 50%; Price (Cp) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two deadline extensions were duly approved. it was also verified that there were defects in the project, which were the responsibility of the contractor, and the provisional acceptance notice was drawn up only after the anomalies had been corrected. | a definitive price revision in the amount of €5,488.41 was calculated.
2647 | 4547028 | Rehabilitation of a Residential Building in the Historic Area of ​​Porto, located at streetde Trás n.º 123 (EM.004.2017.262) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2019 | Portugal | Porto | Porto | 13 | 20 | 07-06-2018 | 30-05-2019 | 357 | 180 | 225000 | 210280.91 | 1 | 213881.68 | -3600.77 | 98.3165 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractually stipulated period was not complied with, and the notification of application of financial contract sanction was issued | objective modification works in the contract worth €4,539.57, eo in the amount of €1,891.80 and work not carried out in the amount of €2,830.60
2648 | 4546945 | Contract for the installation or replacement of water supply networks and connection branches in the municipality of Amadora, for the years 2018 and 2019 . | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 11 | 04-06-2018 | 17-03-2020 | 652 | 365 | 346000 | 309940 | 2 | 309940 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to Clause 28 of the Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2649 | 4546261 | Municipal swimming pool complex on the highway - refurbishment of changing rooms and construction of a support building | 45212200-8 | Construction work for sports facilities | TRUE | 2018 | 2021 | Portugal | Braga | Braga | 3 | 20 | 06-06-2018 | 24-09-2021 | 1206 | 250 | 949419.79 | 898771.71 | 2 | 843672.02 | 55099.69 | 106.5309 | Best value for money: No Criterion related to quality Name: -- Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 6 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | delay attributable to the developer due to the need to change the execution project, as well as the existence of objective contractual modifications. the delay attributable to the executing entity was a consequence of the failure of the subcontractors to start work. difficulty in hiring labor and supplying some materials. | complementary work resulting from unforeseen circumstances, work to correct errors and omissions under the responsibility of the developer and resulting from unforeseen circumstances (article 370).
2650 | 4544213 | 2018/17 - DGEPIM - Execution of speed bumps in the Municipality | 45233140-2 | Roadworks | FALSE | 2018 | 2019 | Portugal | Oeiras | Lisboa | 11 | 12 | 16-05-2018 | 24-09-2019 | 496 | 180 | 68153.3 | 67619.46 | 1 | 67619.46 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: N/A Weighting: 0% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | N/A
2651 | 4543379 | Improved Maritime Accessibility to the Port of Setúbal | 45252124-3 | Dredging and pumping works | FALSE | 2017 | 2021 | Portugal | Setúbal | Setúbal | 17 | 47 | 08-06-2018 | 31-03-2021 | 1027 | 180 | 25000000 | 15988000 | 3 | 16655892.71 | -667892.71 | 95.9901 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The contract award criterion is that of economically most advantageous proposal, based on the following variable assessment factors and respective weights: a) Price 65% b) Deadline 25% c) Execution Methodology 10% | 1 | 65 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | mandatory stop times, unforeseen situations | mandatory stop times at dia, unforeseen situations
2652 | 4543006 | 2017.502.01.C1 - SFP de Bragança - Miscellaneous rehabilitation works | 45261420-4 | Waterproofing work | FALSE | 2017 | 2018 | Portugal | Bragança | Bragança | 4 | 21 | 16-11-2017 | 21-09-2018 | 309 | 75 | 165000 | 153789.6 | 1 | 153789.6 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climate conditions
2653 | 4542127 | Construction of a pipeline between the villages of Chosendo and Seixo | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Sernancelhe | Viseu | 20 | 30 | 29-05-2018 | 05-06-2019 | 372 | 240 | 373798.23 | 317728.51 | 2 | 315000.51 | 2728 | 100.866 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The provisions of point 12 and following of the Procedure Program - 100.00%. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | underwork and price revision
2654 | 4539527 | Varzea School Center. | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2021 | Portugal | Barcelos | Braga | 3 | 36 | 05-06-2018 | 28-06-2021 | 1119 | 365 | 2224857.12 | 2174658.71 | 3 | 2115655.06 | 59003.65 | 102.7889 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delays verified in the contract period were motivated by the pandemic state during which the project was carried out. | there is underwork with spatial relevance in architecture, and in the specialties of rainwater drainage and gas network, specialties that contributed the most to the value of underwork that globally reached the amount of 59,003.68 € .
2655 | 4536822 | Contract work for "Cascais Line - Improvement of track superstructure on the section between Pk 20+430 and Pk 21+600 VA and RV excluding S. Pedro do Estoril Station" (contracts No. 5010033315) | 45234100-7 | Railway construction works | FALSE | 2018 | 2019 | Portugal | N/A | N/A | N/A | 26 | 30-05-2018 | 14-10-2019 | 502 | 150 | 470000 | 423374.23 | 2 | 426066.96 | -2692.73 | 99.368 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Management System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2656 | 4535056 | Rehabilitation of the biological reactor of the WWTP in Valmaior - 2017 | 45262300-4 | Concrete work | TRUE | 2018 | 2019 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 34 | 28-05-2018 | 06-12-2019 | 557 | 60 | 65000 | 62680.52 | 1 | 62680.52 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0 Criterion related to cost Name: price assessment as the only aspect of the performance of the contract to be concluded Weighting: 100 | 2 | 100 | No | FALSE | Complete fulfillment of the contract | 2 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | nothing to report | nothing to report
2657 | 4534655 | The object of this contract is the construction of the wastewater drainage network with a total length of 5.6 km and 100 home branches with the respective manholes and branch | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | N/A | 25-05-2018 | 07-10-2019 | 500 | 120 | 240000 | 159982.94 | 1 | 141498.96 | 18483.98 | 113.063 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2658 | 4533112 | "​17CP-DGIP/12129 - “Contract work for the construction of the Santa Casa Residences, at the Alcoitão Medicine and Rehabilitation Center – 2nd phase”. " | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 23-05-2018 | 30-04-2019 | 342 | 180 | 300000 | 272109.31 | 2 | 272109.31 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the fact that there was a period of suspension during the performance of the contract.
2659 | 4532653 | Contract for thermal insulation of school building | 45321000-3 | Thermal insulation work | FALSE | 2018 | 2018 | Portugal | Guarda | Guarda | 9 | 15 | 23-05-2018 | 30-11-2018 | 191 | 60 | 75000 | 57737.46 | 1 | 57737.46 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 2 | FALSE | Complete fulfillment of the contract | 5 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2660 | 4531446 | Marco de Canaveses Cultural Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2017 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 20 | 25-05-2018 | 30-03-2020 | 675 | 270 | 1273198.2 | 1273000 | 3 | 1306174.36 | -33174.36 | 97.4602 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was extended | the project had complementary works and underwork.
2661 | 4531396 | Rehabilitation of Municipal Buildings in the Torreão area (old tower) Social Interaction | 45210000-2 | Building construction work | FALSE | 2017 | 2021 | Portugal | Guarda | Guarda | 9 | 20 | 22-02-2018 | 22-11-2021 | 1369 | 365 | 550000 | 494100 | 2 | 518883.7 | -24783.7 | 95.2237 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of extensions in the execution period and of additional works | existence of extra work, underwork and price revisions
2662 | 4531135 | Requalification and Expansion of the elementary school of Marquiteira | 45214200-2 | Construction work for school buildings | FALSE | 2018 | 2019 | Portugal | Lourinhã | Lisboa | 11 | 14 | 05-06-2018 | 12-06-2019 | 372 | 196 | 224579.42 | 196500 | 1 | 214898.28 | -18398.28 | 91.4386 | Best value for money: No Criterion related to quality Name: non-existent Weighting: 0% Criterion related to cost Name: The award criterion is the assessment of price or cost, paragraph b), paragraph 1 of article 74 CCP Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | errors and omissions detected during the execution of the contract accepted by the owner, which jeopardized the normal development of the approved work plan - inf. no. 11045/2018 of 11/21/2018, 30-day extension | errors and omissions detected during the execution of the contract accepted by the client, quantities of work not foreseen in the initial contract - complementary works n.º 1 (inf. n.º9446/2018 of 15/10/2018) and complementary works n. 2 (inf. no. 10599/2018 of 11/09/2018)
2663 | 4530398 | Public tender for the contract for the duplication of a section of the Falagueira-Venda-Nova waterway, in the Bairro do Bosque area, Amadora-1st Phase. | 45232410-9 | Sewerage work | FALSE | 2018 | 2020 | Portugal | Amadora | Lisboa | 11 | 11 | 04-05-2018 | 07-10-2020 | 887 | 90 | 180725.8 | 177000 | 1 | 177000.01 | -0.01 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to clause 28 of the procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the projects were carried out on the date of provisional acceptance | vat settlement
2664 | 4530128 | CP/2/2018 - Requalification and Expansion of the elementary school of Seixal | 45214200-2 | Construction work for school buildings | TRUE | 2018 | 2019 | Portugal | Lourinhã | Lisboa | 11 | 14 | 05-06-2018 | 29-04-2019 | 328 | 196 | 235840.24 | 210000 | 1 | 231805.28 | -21805.28 | 90.5933 | Best value for money: No Criterion related to quality Name: N/A Weighting: 0% Criterion related to cost Name: The award criterion is the assessment of price or cost, paragraph b), paragraph 1 of article 74 CCP Weighting: 100% | 2 | 100 | 4 | FALSE | Complete fulfillment of the contract | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | errors and omissions detected during the execution of the contract accepted by the owner, which jeopardized the normal development of the approved work plan - proc.º2 e&o inf. no. 11353/2018 of 11/29/2018, extension of 43 days | errors and omissions detected during the execution of the contract accepted by the client, quantities of work not foreseen in the initial contract - proc. no. 1 e&o inf. no. 7647/2018 of 08/14/2018 and proc. no. 2 e&o inf. no. 11353/2018 of 11/29/2018
2665 | 4528299 | Contract for "Requalification and improvement of streetDr Virgílio Ferreira and streetAlexandre Herculano, in Oliveira do Hospital | 45233223-8 | Carriageway resurfacing works | FALSE | 2018 | 2020 | Portugal | Oliveira do Hospital | Coimbra | 6 | N/A | 04-06-2018 | 22-09-2020 | 841 | 270 | 838000 | 718378.9 | 2 | 815131.6 | -96752.7 | 88.1304 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional works and work suspension. | additional work
2666 | 4527287 | Rehabilitation and improvement of the thermal behavior characteristics, insulation of the facades and roofs of the buildings, which make up the municipal social housing development | 45321000-3 | Thermal insulation work | FALSE | 2017 | 2020 | Portugal | Valongo | Porto | 13 | 24 | 01-06-2018 | 29-04-2020 | 698 | 180 | 452671.25 | 417002.34 | 2 | 422196.09 | -5193.75 | 98.7698 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the deadline (last measurement report dated 02.28.2019). there was only a delay in scheduling the inspection for the purposes of provisional acceptance of the project. | approval of price revision calculations (provisional and definitive
2667 | 4527263 | Link from mondin de basto to en210 - e-contracts 5010032298 | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2017 | 2021 | Portugal | N/A | N/A | N/A | 45 | 07-05-2018 | 23-12-2021 | 1326 | 548 | 8000000 | 7627891 | 3 | 8140838.79 | -512947.79 | 93.6991 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% - Technical value: 20% | 1 | 80 | N/A | TRUE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline change resulted from: positive complementary works; adverse weather conditions; covid19 pandemic | the increase in the cost of the contract resulted fundamentally from three factors: impositions by external entities (drcn and icnf) which determined an increase in the volumes of archaeological surveys and the need to plant cork oaks; geological and geotechnical conditions of the land that forced the adjustment of volumes of earthworks and foundation conditions; need to guarantee accessibility and irrigation conditions to remaining plots
2668 | 4526625 | Circular variant josé amaro - 2nd phase | 45233122-0 | Ring road construction work | FALSE | 2017 | 2021 | Portugal | Grandola | Setúbal | 17 | 30 | 28-05-2018 | 26-04-2021 | 1064 | 365 | 1218434.23 | 1075948.17 | 3 | 1543260.73 | -467312.56 | 69.7191 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | considering the troubled period of the covid 19 pandemic, difficulty in obtaining opinions from outside entities and also due to adverse rainfall conditions | during the construction, it was verified the need to carry out various adaptations of the projected infrastructures and the existing infrastructures
2669 | 4522807 | Demolitions, construction of new roofs in sandwich sheet, rehabilitation of facades, replacement of window frames, minor rectifications in terms of interior divisions, new cladding | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 48 | 28-05-2018 | 03-02-2021 | 982 | 545 | 2501834.13 | 2130944.3 | 3 | 2353790.46 | -222846.16 | 90.5325 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: CP-50% QTP-50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contracted period, however the provisional acceptance notice was only drawn up on the date indicated, given the need for the contractor to make corrections to the project carried out. | the completion of the project resulted in more work worth €64,247.44, errors and omissions worth €82,755.80, underwork worth €8,413.24 and a price review with definitive indices worth €86,073.37.
2670 | 4519474 | The purpose of this contract is to repair ruptures in the water supply network and carry out various maintenance works in civil construction. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2020 | Portugal | Oliveira do Bairro | Aveiro | 1 | N/A | 25-05-2018 | 24-05-2020 | 730 | 730 | 700000 | 502910.02 | 2 | 502910.02 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2671 | 4519393 | The object of this contract is the construction of the wastewater drainage network with a total length of 1012 m and 28 home branches with the respective manholes and branch. | 45000000-7 | Construction work | FALSE | 2017 | 2021 | Portugal | Ovar | Aveiro | 1 | N/A | 11-05-2018 | 23-04-2021 | 1078 | 120 | 220000 | 158885 | 1 | 158885 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2672 | 4519350 | The object of this contract is the renovation of the water supply networks in Aveiro | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | N/A | 18-05-2018 | 04-10-2019 | 504 | 1095 | 249000 | 185764.54 | 1 | 185764.52 | 0.02 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2673 | 4519297 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Sever do Vouga | Aveiro | 1 | N/A | 25-05-2018 | 31-01-2019 | 251 | 1095 | 249000 | 199921.4 | 1 | 199921.35 | 0.05 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2674 | 4518336 | Floating pier to support fishing in the fishing port of Baleeira - Sagres | 45241500-3 | Wharf construction work | FALSE | 2018 | 2018 | Portugal | Vila do Bispo | Faro | 8 | 18 | 11-05-2018 | 25-10-2018 | 167 | 80 | 122100 | 112960 | 1 | 112960 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical quality of the proposal Weighting: 40% Criterion related to cost Name: Price Weighting: 60% | 1 | 60 | No | FALSE | Complete fulfillment of the contract | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | consignment date 06/11/2018
2675 | 4514375 | Rehabilitation and expansion of the elementary school of Macieira de Rates | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2019 | Portugal | Barcelos | Braga | 3 | 12 | 17-05-2018 | 16-10-2019 | 517 | 180 | 398254.11 | 382266.42 | 2 | 382266.42 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the successful tenderer presented the following causes: unfavorable weather conditions that conditioned the fulfillment of the established deadlines (...) ; difficulties we face planning and urban management department municipal works and projects division information 3/3 daily with the lack of labour and which has systematically delayed the entry of subcontractors hired for the finishing phase; difficulties we have encountered in delivery of some materials. | the causes for changes in the value of the project were the project to supply errors and omissions, accepted by the design team, supervision and client, changes introduced in the work as well as the rectification of measurements.
2676 | 4510369 | Flooring, Water Supply Network, Domestic Wastewater and Rainwater Network, Electricity, Urban Furniture, construction of Sculptural Element, remodeling of Sanitary Installations | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Nisa | Portalegre | 12 | 30 | 22-05-2018 | 04-07-2019 | 408 | 120 | 339999.34 | 283026.73 | 2 | 277494.16 | 5532.57 | 101.9938 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work (article 365 of the "public procurement code") of 45 days. | ordinary price revision in the amount of €3,584.29. auto de trabalhos less in the amount of €9,116.86.
2677 | 4509404 | Improvement and Requalification of the E.M 506 between S. Barnabé and the junction with the E.M 543 | 45233140-2 | Roadworks | FALSE | 2017 | 2020 | Portugal | Almodovar | Beja | 2 | 30 | 17-05-2018 | 05-06-2020 | 750 | 240 | 760000 | 643916.98 | 2 | 640070.41 | 3846.57 | 100.601 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline due to delay in the 2nd partial assignment, and the geological characteristics of the land | price revision worth €22,791.32 and underwork worth €26,637.92
2678 | 4509294 | Contract for the Conception-Construction of the Ortiga WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | Mação | Santarém | 16 | 32 | 16-05-2018 | 29-01-2020 | 623 | 330 | 600000 | 594125.65 | 2 | 601406.48 | -7280.83 | 98.7894 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A - PRICE - 60% B - TECHNICAL EVALUATION - 40% B.1 -Conception and justification of the proposed solution- 25% B.1.1 - Treatment process -12% B.1.2 - Equipment (mechanical, electromechanical, instrumentation and electrical installations) - 5% B.1.3 - Civil construction - 4% B.1.4 - Consistency and adequacy of operating costs and guarantees provided - 3% B.1.5 - Command and Automation Philosophy - 1% B.2 - Work execution methodology - 10% B.3 Detail and consistency of the work plan - 5% B.3.1 - Work Schedule - 2.5% B.3.2 - Means Plan - 2.5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the 31-day period due to the need to carry out work in quantities and types not foreseen in the initial planning. there was also a change in the execution period during the start-up period due to the existence of pending situations to be corrected. subsequently, some pending situations, namely the delivery and final validation of the final screens and the technical compilation prevented the provisional reception of the project within the stipulated period.
2679 | 4507929 | Rehabilitation of the Municipal Library Building | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 13-03-2018 | 21-12-2018 | 283 | 150 | 491935.85 | 424563.47 | 2 | 424513.06 | 50.41 | 100.0119 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2680 | 4505133 | For the construction of the sports center, demolition work, earthworks, reinforced concrete and metal structures, masonry, coatings, window frames, waterproofing, supplies | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 100 | 22-05-2018 | 18-11-2021 | 1276 | 545 | 2880924.51 | 2738506.83 | 3 | 2956407.55 | -217900.72 | 92.6295 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | a work suspension notice was duly approved, as well as 5 deadline extensions resulting from additional work to the initial contract. | the completion of the project resulted in: - additional work worth €136,314.46; - work to correct errors and omissions in the amount of €7,880.80; - underwork worth €23,959.94; - definitive price revision in the amount of €97,665.38.
2681 | 4499841 | Extension of street25 de Abril - 2nd phase, Lomar | 45233100-0 | Construction work for highways, roads | TRUE | 2018 | 2019 | Portugal | Braga | Braga | 3 | 15 | 17-05-2018 | 19-06-2019 | 398 | 120 | 532630.5 | 414016.22 | 2 | 463318.61 | -49302.39 | 89.3589 | Best value for money: No Criterion related to quality Name: -- Weighting: 0% Criterion related to cost Name: lowest price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the deadline for the project was extended due to the execution of complementary works. | the value of the project was changed due to the objective modification of the contract referring to the complementary works.
2682 | 4499134 | The object of the contract is the execution of works for the rehabilitation of the municipal building Teatro Luís de Camões, located at Calçada da Ajuda, n.º 76 to 80, parish of Belém, municipality of Lisbon. | 45453100-8 | Refurbishment work | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 22-10-2015 | 20-04-2018 | 911 | 450 | 1700000 | 1111252.25 | 3 | 1194191.41 | -82939.16 | 93.0548 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the causes of the alterations to the execution period of the project are essentially related to delays in the execution of the projects not attributable to the owner of the project, due to the granting of a period of 80 days requested by the contractor and also a delay of about two months resulting inspection by the licensing entity. | overwork, underwork, and errors and omissions supply work
2683 | 4498958 | Contract for the execution of paintings on the pavement in the municipality of Albufeira | 45233221-4 | Road-surface painting work | FALSE | 2017 | 2019 | Portugal | Albufeira | Faro | 8 | 21 | 16-05-2018 | 04-06-2019 | 384 | 488 | 170000 | 160301.5 | 1 | 160301.5 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline is due to delays on the part of the contractor.
2684 | 4497871 | For the construction of the sports center, demolition work, earthworks, indirect foundations, reinforced concrete and metallic structures, masonry, coatings, window frames, waterproofing are foreseen. | 45212225-9 | Sports hall construction work | FALSE | 2017 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 48 | 16-05-2018 | 16-04-2021 | 1066 | 365 | 1286000 | 1264970.84 | 3 | 1318259.37 | -53288.53 | 95.9577 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (Cp) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the foreseen period, however, it was necessary for the contractor to proceed with the correction of some works carried out, having drawn up the provisional acceptance notice on the indicated date, after correction of the same. | a final price revision calculation was calculated in the amount of €53,288.53
2685 | 4495654 | Repair of Via Espargo-Paços de Brandão | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2018 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-05-2018 | 15-11-2019 | 548 | 90 | 356375 | 248223.52 | 1 | 218447.42 | 29776.1 | 113.6308 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 129 days of graceful extension, 27 days between the request and the 1st inspection, 28 days to correct detected deficiencies until provisional acceptance of the project | over and underwork resulting from unforeseen circumstances.
2686 | 4495617 | Rehabilitation of fires in Per de Povos - Vila Franca de Xira | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 13-03-2018 | 27-05-2020 | 806 | 330 | 726500 | 661934.45 | 2 | 609540.21 | 52394.24 | 108.5957 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | short work approval and price review approval
2687 | 4494262 | Construction of water mains between Vila da Ponte, Freixinho and Pensao | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Sernancelhe | Viseu | 20 | 30 | 14-05-2018 | 12-06-2019 | 394 | 180 | 239982.44 | 203985.08 | 1 | 207871 | -3885.92 | 98.1306 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: As provided for in point 12 and following of the program of procedure - 100.00%. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | price review worth €3885.92
2688 | 4486959 | Contract for the Connection of the Autonomous Systems of the South Zone of the Municipality of Abrantes to the Castelo de Bode System - Adductor Section between Vale das Donas and the Concavada Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Abrantes | Santarém | 16 | 30 | 17-05-2018 | 20-04-2020 | 704 | 210 | 2250000 | 1895000 | 3 | 1941382.52 | -46382.52 | 97.6109 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) - Price - 60% b) - Technical Valuation of the Proposal - 40% According to criteria defined in clause 20 of the Tender Program | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | article 365, paragraph b) of the "public procurement code"
2689 | 4485436 | Alfândega da Fé air resources center – Host base for the Protection and Relief Intervention Group | 45210000-2 | Building construction work | FALSE | 2017 | 2020 | Portugal | Alfandega da Fé | Bragança | 4 | N/A | 08-01-2018 | 13-06-2020 | 887 | 365 | 470644.76 | 467858.92 | 2 | 498661.34 | -30802.42 | 93.823 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to weather issues, it was necessary to extend the deadline for the execution of the contract | additional work and price revision
2690 | 4473627 | Infrastructures of the Tocha Industrial Zone - Expansion 2018, by Contract - CP-CCP-EMP No. 02/2018 | 45111290-7 | Primary works for services | FALSE | 2018 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 15 | 14-05-2018 | 14-11-2019 | 549 | 240 | 306000 | 285501.11 | 2 | 270919.65 | 14581.46 | 105.3822 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0 Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100 | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | completion of works | existence of over and underwork
2691 | 4473288 | Infrastructures of the Industrial Zone of Cantanhede - Expansion 2018, by Contract - CP-CCP-EMP No. 01/2018 | 45111290-7 | Primary works for services | FALSE | 2018 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 15 | 14-05-2018 | 29-05-2020 | 746 | 240 | 349975 | 326999.01 | 2 | 336199.42 | -9200.41 | 97.2634 | Best value for money: Yes Criterion related to quality Name: N/A Weighting: 0 Criterion related to cost Name: Evaluation of the price or cost as the only aspect of the performance of the contract to be concluded Weighting: 100 | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 13 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | conclusion work | existence of over and underwork
2692 | 4467857 | Construction of the Pinhel Urban Park | 45000000-7 | Construction work | FALSE | 2017 | 2019 | Portugal | Pinhel | Guarda | 9 | N/A | 07-02-2018 | 18-09-2019 | 588 | 330 | 586264.04 | 497858.85 | 2 | 508700.72 | -10841.87 | 97.8687 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractor's responsibility | supply of errors and omissions
2693 | 4466393 | Construction of the Conceição sports complex | 45212225-9 | Sports hall construction work | FALSE | 2017 | 2020 | Portugal | Faro | Faro | 8 | 20 | 30-04-2018 | 31-08-2020 | 854 | 270 | 341183.1 | 269574.23 | 2 | 292136.63 | -22562.4 | 92.2768 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2694 | 4466279 | Pedestrian accesses and proximity relations/Vila de Sesimbra: Access stairs (cemetery) | 45233161-5 | Footpath construction work | FALSE | 2017 | 2020 | Portugal | Sesimbra | Setúbal | 17 | 30 | 26-01-2018 | 14-08-2020 | 931 | 150 | 167407.11 | 159216.68 | 1 | 175834.6 | -16617.92 | 90.5491 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 150 days of initial execution period; 75-day extension of the deadline under the terms of article 374 of the "public procurement code"; 135 days of term extension under the terms of art. a), paragraph 1, article 311 and al. b), of article 312 of the "public procurement code" and 10 days of suspension of the execution period, under the terms of al. a), of article 297 of the "public procurement code". communication of approval of the pss to the contractor took place on 06/03/2018 and the end of the contract, considering the extensions of the term described, as well as the postponement of the end of the execution period by 10 days due to the suspension mentioned above, occurred on the 11 /03/2019. | overwork, errors and omissions, underwork and price revisions.
2695 | 4462689 | The repaving of Largo de S. Salvador in Coimbra and adjacent streets , and the remodeling of infrastructures, namely, the drainage networks for rainwater, wastewater and water distribution. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 28-02-2018 | 19-12-2019 | 659 | 240 | 204907.87 | 199985.04 | 1 | 198470.32 | 1514.72 | 100.7632 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the deadline | due to the price revision amount, and the quantity of work not carried out after the final measurements of the project and due to adjustments to the execution project.
2696 | 4462382 | Rehabilitation of building at streetInfante D. Henrique n.ºs 103 and 107 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 20 | 03-05-2018 | 03-12-2019 | 579 | 390 | 430000 | 429622.14 | 2 | 449463.38 | -19841.24 | 95.5856 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 96 day extension | eo in the amount of €28,225.53 and work not performed in the amount of €8,384.29
2697 | 4461481 | Contract for the execution of the civil construction work for the renovation of coatings in public areas, interior and exterior, and of the technical installations of the Pousada da Serra da Estrela building | 45212400-0 | Accommodation and restaurant buildings | FALSE | 2018 | 2020 | Portugal | Covilhã | Castelo Branco | 5 | 16 | 19-03-2018 | 15-07-2020 | 849 | 75 | 210000 | 189850 | 1 | 189850 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: N/A Criterion related to cost Name: Price Weighting: 100% | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 0 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | reconciliation of 3 factors: occupancy rate of the inn, weather conditions and the contractor's shortage of means.
2698 | 4459151 | Rehabilitation of Residential Buildings in the Historic Area of ​​Porto, located at streetde Trás nº 9 and street of Caldeiros nº 64 (EM.004.2017.256) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2020 | Portugal | Porto | Porto | 13 | 20 | 04-05-2018 | 27-01-2020 | 633 | 450 | 850000 | 812248.74 | 2 | 810112.74 | 2136 | 100.2637 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension by 30 days | work not carried out in the amount of €2,136.00 and eo in the amount of €36,626.21
2699 | 4458705 | Rehabilitation of a Residential Building in the Historic Area of ​​Porto, located at street of Reboleira n.º 13 (EM.004.2017.255) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2020 | Portugal | Porto | Porto | 13 | 20 | 24-04-2018 | 06-01-2020 | 622 | 330 | 340000 | 335997.82 | 2 | 341945.77 | -5947.95 | 98.2606 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension of 30 days (06/02/2019 to 07/02/2019); 45 days (email dated 25-10-2018) and 90 days (email dated 05-04-2019) | eo in the amount of €13,839.24 and work not carried out in the amount of €7,891.29
2700 | 4456588 | Expansion of the Water Supply Network | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Odemira | Beja | 2 | 30 | 03-05-2018 | 03-02-2020 | 641 | 120 | 364052.86 | 348873.6 | 2 | 262393.01 | 86480.59 | 132.9584 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The criterion on which the award is based is the the most economically advantageous proposal, taking into account the Price factor; a) In case of a tie, the proposals will be evaluated taking into account the following factors, with the indicated weighting: a.1) Descriptive and justification - 40% a.2) Work plan - 60% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | small adaptations to the project and some constraints on local traffic. | because it avoided cutting the bituminous pavement in the pipeline along the road.
2701 | 4454588 | Contract for "Rehabilitation of the Caparide Outfall in the Sintra area" | 45232410-9 | Sewerage work | FALSE | 2015 | 2020 | Portugal | Sintra | Lisboa | 11 | 30 | 02-05-2018 | 19-03-2020 | 687 | 300 | 2250000 | 1516108.9 | 3 | 1571284.05 | -55175.15 | 96.4885 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 40% Global Price - 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution period, due to the need to articulate agendas and with the agreement of the parties, the reception took place on a date different from that foreseen | art 379 nº 2 "public procurement code"
2702 | 4453279 | Contract for "Rehabilitation and Refurbishment of the Municipal Warehouse, in the place of São Pedro, parish and municipality of Velas" | 45113000-2 | Siteworks | FALSE | 2017 | 2019 | Portugal | Velas | Região Autónoma dos Açores | 15 | 35 | 04-05-2018 | 09-12-2019 | 584 | 180 | 268450.66 | 266422.13 | 2 | 293880.92 | -27458.79 | 90.6565 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 60% Price and 40% Period of execution of the undertaking | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project had an execution period of 180 days, however the execution period was subject to 3 extension requests, 1st extension of 120 days, 2nd extension of 89 days and 3rd extension of 64 days. | the contractual price was €266,422.13, which, as a result of the objective modification due to the additional work, amounted to €27,458.79, totaling the final value of the project at €293,880.92.
2703 | 4452831 | Construction of the sendim wastewater treatment plant | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | Miranda do Douro | Bragança | 4 | 24 | 06-04-2018 | 20-03-2020 | 714 | 365 | 999752.77 | 942539.73 | 2 | 942539.73 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climatic causes | price review
2704 | 4450328 | Intervention projects for urban rehabilitation – requalification of public space in Praceta Joaquim Pires in Loulé | 45233262-3 | Pedestrian zone construction work | FALSE | 2017 | 2019 | Portugal | Loulé | Faro | 8 | 21 | 20-04-2018 | 21-11-2019 | 580 | 180 | 240000 | 235956.08 | 1 | 312268.45 | -76312.37 | 75.5619 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractor's delay and implementation difficulties with buried networks. | need for replacement and construction at the highest level, of a water supply network conduit and respective nodes, a network that was unknown.
2705 | 4446760 | Reconversion of spaces for 4 new classrooms and complete refurbishment of the electrical installations of Escola Básica nº 1 and ATL do Laranjeiro (R. Francisco sousa tavares)" | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2018 | Portugal | Almada | Setúbal | 17 | 24 | 16-04-2018 | 28-11-2018 | 226 | 240 | 780422.16 | 697000 | 2 | 644979.52 | 52020.48 | 108.0654 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factor 1 - Technical value of the proposal - 40% with the subfactors "Work execution plan" - 30 points and "Equipment and labor means" - 10 points. Factor 2 - Bid price - 60%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | anticipation of work. | underwork.
2706 | 4446264 | Rehabilitation contract for the municipal housing building located at streetAntónio Aleixo, 1, Póvoa de Santo Adrião. | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Odivelas | Lisboa | 11 | 30 | 06-04-2018 | 02-10-2020 | 910 | 120 | 255000 | 221636.84 | 1 | 221636.84 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: In accordance with point 12 of the Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2707 | 4444436 | Construction of a pedestrian bridge over the Mondego River, and respective junctions, to ensure the connection between the two banks in accessibility to the Fluvial Beach of Palheiros and Zorro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 27-11-2017 | 31-05-2019 | 550 | 180 | 592660.21 | 547091.16 | 2 | 579755.53 | -32664.37 | 94.3658 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension due to work to correct errors and omissions and as a result of the suspension of the term | value of errors and omissions in the construction phase, restoration of financial balance and price revision
2708 | 4443165 | Repair of agricultural roads to carry out WRC training (Section 1- East Zone (Pinho and Sr. Monte) | 45233200-1 | Various surface works | FALSE | 2018 | 2018 | Portugal | Boticas | Vila Real | 19 | 6 | 26-04-2018 | 07-05-2018 | 11 | 10 | 32500 | 24000 | 1 | 24000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30 Criterion related to cost Name: Price Weighting: 70 | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2709 | 4443128 | Repair of agricultural paths for WRC training (Section 2- West Zone ( Dornelas A, B and Wall) | 45233200-1 | Various surface works | FALSE | 2018 | 2018 | Portugal | Boticas | Vila Real | 19 | 6 | 26-04-2018 | 07-05-2018 | 11 | 10 | 30000 | 22000 | 1 | 22000 | 0 | 100 | Best value for money: Yes Criterion related to quality Name: Technical value of the proposal Weighting: 30 Criterion related to cost Name: Price Weighting: 70 | 1 | 70 | No | FALSE | Complete fulfillment of the contract | 7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2710 | 4442831 | Requalification of the surroundings of the Convent of Jesus | 45112700-2 | Landscaping work | FALSE | 2017 | 2021 | Portugal | Setúbal | Setúbal | 17 | 30 | 20-02-2018 | 30-07-2021 | 1256 | 365 | 1473332.8 | 1469655.96 | 3 | 1470225.65 | -569.69 | 99.9613 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspensions (162 days) and term extensions (206 days) which makes a total of 733 days beyond the initial term | more work identified during the course of the project (6,885.56€) and underwork not carried out (6,315.80€)
2711 | 4440792 | The object of this contract is the construction of a gravity network in an extension of 7,100 meters of wastewater collectors, 245 home extensions, also including the construction of 1 station | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | N/A | 27-04-2018 | 23-11-2019 | 575 | 180 | 789200 | 584008 | 2 | 534619.7 | 49388.3 | 109.238 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2712 | 4440181 | Requalification of the elementary school of Ave - Vila das Aves | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2021 | Portugal | Santo Tirso | Porto | 13 | 20 | 23-04-2018 | 05-05-2021 | 1108 | 365 | 1138953.86 | 1057549.67 | 3 | 1072924.45 | -15374.78 | 98.567 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: A - Price - with a weighting of 60% in the overall evaluation; B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: B1 - Work Schedule - with a weighting of 25% in the overall classification; B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | alteration, definition and execution of works during the contract. | the need to carry out complementary work and the exclusion of other work (underwork) during the course of the project.
2713 | 4435284 | Supply network maintenance contract | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2018 | 2020 | Portugal | Chamusca | Santarém | 16 | 14 | 04-04-2018 | 04-08-2020 | 853 | 730 | 150000 | 150000 | 1 | 115016.3 | 34983.7 | 130.4163 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price -100% | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of the contract due to the declaration of a state of emergency | the contract ends for the term or the contract value is almost exhausted.
2714 | 4433969 | Urban Requalification Contract for the West Zone of Vila de Arouca | 45233160-8 | Paths and other metalled surfaces | FALSE | 2017 | 2021 | Portugal | Arouca | Aveiro | 1 | 30 | 26-04-2018 | 15-11-2021 | 1299 | 540 | 2601847.76 | 2389796.53 | 3 | 2191768.7 | 198027.83 | 109.0351 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | existence of over and underwork.
2715 | 4429117 | 5010022969 - Contract "Implementation of Definitive Measures for Return of Traction Current and Protective Lands (RCT+TP) on the Albergaria - Alfarelos Section of the North Line" | 45234115-5 | Railway signalling works | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 30 | 19-04-2018 | 12-11-2020 | 938 | 303 | 2110000 | 1649649.05 | 3 | 1580795.7 | 68853.35 | 104.3556 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price (50% weighting) - FPRECIO b) Execution period (10% weighting) - Fdeadline c) Technical value (20% weighting) - FVT d) Safety Management System (10% weighting) - FSGS e) Quality Control System (5% weighting) - FSQ f) Environmental Management System (5% weighting) - FSGA | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was necessary to extend the project for 240 days | there were errors and omissions but there was also underwork
2716 | 4427328 | CONTRACT FOR REHABILITATION OF BLOCKS II, IV-A, IV-B and V - BAIRRO DA NAZARÉ" | 45453100-8, 45442110-1 | Refurbishment work, Painting work of buildings | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 19-03-2018 | 28-10-2019 | 588 | 210 | 550000 | 394750.94 | 2 | 394576.31 | 174.63 | 100.0443 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | labor shortage. | quantities difference.
2717 | 4427207 | CONSTRUCTION CONTRACT FOR REHABILITATION OF BLOCKS I and II - BAIRRO DA NAZARÉ | 45453100-8, 45442110-1 | Refurbishment work, Painting work of buildings | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 19-03-2018 | 28-10-2019 | 588 | 240 | 750000 | 545772.95 | 2 | 545755.39 | 17.56 | 100.0032 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | labor shortage. | quantities difference.
2718 | 4425399 | Plot 2 - Urban Regeneration of street ofs Quintães in São Martinho de Anta - Paving | 45233251-3 | Resurfacing works | FALSE | 2017 | 2019 | Portugal | Sabrosa | Vila Real | 19 | 21 | 13-04-2018 | 22-10-2019 | 557 | 180 | 1090072.12 | 483793.35 | 2 | 504171.35 | -20378 | 95.9581 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | <deadline extensions | the sum of over and under works.
2719 | 4425226 | Lot 1 Urban Regeneration of streetFundo do Povo in S. Martinho de Anta Lot - Flooring | 45233251-3 | Resurfacing works | FALSE | 2017 | 2019 | Portugal | Sabrosa | Vila Real | 19 | 21 | 13-04-2018 | 22-10-2019 | 557 | 180 | 1090072.12 | 499946.48 | 2 | 493006.48 | 6940 | 101.4077 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to deadline extensions | underwork worth €6940.00
2720 | 4424211 | Closure of Sanitation Networks in the Municipality of Mealhada - WWTP Mealhada | 45232440-8 | Construction work for sewage pipes | FALSE | 2017 | 2021 | Portugal | Mealhada | Aveiro | 1 | 20 | 18-04-2018 | 01-09-2021 | 1232 | 180 | 199500 | 180088.22 | 1 | 152096.63 | 27991.59 | 118.4038 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for the project was changed due to the approval of the pumping station equivalence, communication to the contractor of additional work and the suppression of errors and omissions. | the value of the contract underwent changes related to errors and omissions and more work resulting from unpredictable situations and contractual fines.
2721 | 4421593 | Anticorrosive Protection of Metallic Bridges on the South Line, Phase 1" (eContracts No. 5010026098) | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 40 | 16-04-2018 | 25-09-2020 | 893 | 210 | 800000 | 794140 | 2 | 807019.75 | -12879.75 | 98.404 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 55% - Technical value 25% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2722 | 4420346 | Reconstruction of the walls of Senior Residences and public space in Colapso, in Odivelas - Coercive Execution | 45262212-0 | Trench sheeting work | FALSE | 2017 | 2018 | Portugal | Odivelas | Lisboa | 11 | 20 | 17-04-2018 | 17-12-2018 | 244 | 90 | 190000 | 189996.85 | 1 | 189996.85 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change in the execution period of the project. | there were no changes to the value of the project
2723 | 4419058 | 5010030542 - Contract for the "Algarve Line - Replacement of wooden sleepers with concrete sleepers and rails and construction of Long Welded Bars, on Loulé's IV line and on lines III | 50225000-8 | Railway-track maintenance services | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 42 | 12-04-2018 | 30-12-2019 | 627 | 120 | 323967 | 285445.09 | 2 | 268953.21 | 16491.88 | 106.1319 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2724 | 4418392 | Rye Island road repair | 45233220-7 | Surface work for roads | FALSE | 2018 | 2020 | Portugal | Grandola | Setúbal | 17 | 8 | 16-04-2018 | 30-09-2020 | 898 | 120 | 200868.77 | 167957.5 | 1 | 176300.78 | -8343.28 | 95.2676 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the existence of an additional term, there was changes in the time for completion of the project | during the project, the need to perform works not initially foreseen was verified
2725 | 4417483 | Construction of sanitation networks and respective treatment system | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Resende | Viseu | 20 | 20 | 22-12-2017 | 09-07-2019 | 564 | 180 | 719500 | 673315 | 2 | 673315 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | characteristics of the terrain, namely with regard to the opening of a trench in hard rock whose length proved to be greater than expected in the project and the adverse weather conditions that were felt during the execution of the contract. | pricing review.
2726 | 4416679 | Execution contract for the Connection Pipelines between the Upstream System and Downstream Systems in the Municipality of Alcoutim | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Alcoutim | Faro | 8 | 21 | 19-03-2018 | 26-02-2019 | 344 | 240 | 455027.08 | 434850.21 | 2 | 434850.21 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and subfactors are in accordance with the stipulated in number 12.3 of the tender program - 100.00%. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to provisional acceptance
2727 | 4416247 | Acquisition of a public works contract for the creation of a Sociocultural Center. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2018 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 16-04-2018 | 12-12-2018 | 240 | 90 | 299000 | 267620.31 | 2 | 267620.31 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 70% Period of execution of the work 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | motivated by the extra work and delay in the delivery of some materials. | there was a need to make some changes to the project
2728 | 4416167 | Rehabilitation of four buildings in the orreiro neighborhood | 45320000-6 | Insulation work | FALSE | 2017 | 2020 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 24-01-2018 | 29-05-2020 | 856 | 180 | 971491.36 | 797395 | 2 | 766795.3 | 30599.7 | 103.9906 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 70% Technical value of the proposal 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in the project due to economic and financial difficulties | due to an error in the award value, €797395.00 was published when in reality the correct value is €767395.00.
2729 | 4416055 | Public Works Contract No. 13/DRA/2018 for the "CONSTRUCTION CONTRACT FOR A SUPPORT AREA FOR THE DESCENT OF MOUNTAIN DO PICO AND VEHICLE PARKING AREA | 45210000-2 | Building construction work | FALSE | 2017 | 2019 | Portugal | Madalena | Região Autónoma dos Açores | 15 | 23 | 16-04-2018 | 13-06-2019 | 423 | 365 | 349000 | 348900 | 2 | 348900 | 0 | 100 | most economically advantageous proposal If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 217 FRIDAY, NOVEMBER 17, 2017 40%- price; 60% technical quality. | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extensions
2730 | 4414251 | EGA-AR0312 - Contract for the Conception-Construction of the Chapa WWTP (Amarante) | 45252000-8 | Construction works for sewage treatment plants, purification plants and refuse incineration plants | FALSE | 2017 | 2020 | Portugal | Amarante | Porto | 13 | 47 | 23-03-2018 | 18-08-2020 | 879 | 273 | 760000 | 610500 | 2 | 627608.13 | -17108.13 | 97.2741 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: PRICE - 40% TECHNICAL EVALUATION - 60% | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 1 - lack of availability of private plots; 2 - the suspension of the project due to lack of electricity and sanitation; 3 - low flow recorded at the beginning of the pre-start-up period, with implications for the formation and maintenance of biomass in the biological reactor.
2731 | 4412979 | 2017/252 - DGEPIM - Conservation/Execution of pedestrian and road pavements in the Municipality. | 45233200-1 | Various surface works | FALSE | 2018 | 2019 | Portugal | Oeiras | Lisboa | 11 | 24 | 09-04-2018 | 21-10-2019 | 560 | 365 | 149858.4 | 103898.8 | 1 | 103898.8 | 0 | 100 | Best value for money: No Criterion related to quality Name: N/A Weighting: N/A Criterion related to cost Name: N/A Weighting: N/A | 0 | 0 | 5 | FALSE | Complete fulfillment of the contract | 14 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2732 | 4411908 | Requalification of the elementary school of Santo Tirso (S. Rosendo) | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2021 | Portugal | Santo Tirso | Porto | 13 | 20 | 05-04-2018 | 10-03-2021 | 1070 | 365 | 939766.78 | 844859.57 | 2 | 860299.76 | -15440.19 | 98.2053 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: A - Price - with a weighting of 60% in the overall evaluation; B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: B1 - Work Schedule - with a weighting of 25% in the overall classification; B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need arose for definitions regarding the carrying out of additional work. | the existence of over and underwork.
2733 | 4410020 | Prc_0043/2017 - ega-aa0295 – water supply subsystem of s. George. Village reservoirs – deocriste, deocriste and freixeiro de soutelo and respective supply connections | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 47 | 13-03-2018 | 30-09-2020 | 932 | 365 | 1975000 | 1720724.76 | 3 | 1632311.44 | 88413.32 | 105.4164 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work | suppression of the planned works in the parish of âncora and also the connection works to the cadinho reservoir
2734 | 4409535 | Mixed works and supply contract for "requalification of playgrounds in the municipality of matosinhos | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2019 | Portugal | Matosinhos | Porto | 13 | 47 | 09-04-2018 | 13-03-2019 | 338 | 90 | 329999 | 274967.08 | 2 | 375798.77 | -100831.69 | 73.1687 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
2735 | 4407879 | Excavation and placement of base for widening, drainage, paving and safety equipment. | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Nisa | Portalegre | 12 | 30 | 29-03-2018 | 22-10-2019 | 572 | 120 | 699942.5 | 419965.51 | 2 | 438943.75 | -18978.24 | 95.6764 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | notice of temporary suspension of works. | pricing revisions.
2736 | 4407242 | Varche outfalls and pumping stations | 45232400-6 | Sewer construction work | FALSE | 2017 | 2019 | Portugal | Elvas | Portalegre | 12 | 24 | 11-04-2018 | 17-04-2019 | 371 | 180 | 384000 | 304753.52 | 2 | 297393.34 | 7360.18 | 102.4749 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: These are those contained in Article 5 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | there was €7,360.00 underwork.
2737 | 4406582 | The object of the contract is the earthworks of designated plot 26, located in the Industrial Zone of Monte Cavalo – Vouzela. | 45112000-5 | Excavating and earthmoving work | FALSE | 2018 | 2019 | Portugal | Vouzela | Viseu | 20 | 9 | 01-03-2018 | 01-08-2019 | 518 | 120 | 350000 | 294998.87 | 2 | 294998.87 | 0 | 100 | Best value for money: No Criterion related to quality Name: Quality Weighting: 0 Criterion related to cost Name: Price Weighting: 100 | 2 | 100 | 5 | FALSE | Complete fulfillment of the contract | 10 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | the project was completed within the contractually established period. | no change.
2738 | 4404263 | Construction Home for the Elderly | 45215212-6 | Retirement home construction work | FALSE | 2013 | 2018 | Portugal | Amarante | Porto | 13 | 30 | 30-07-2013 | 15-05-2018 | 1750 | 365 | 349000 | 254636.79 | 2 | 249793.88 | 4842.91 | 101.9388 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | time elapsed between the deadline for the project and the necessary inspections | work not done
2739 | 4403869 | Public Works Contract for the Execution of the Vila Franca de Xira/Telheiras Pipeline - Recovery of Sections 2 and 3 - Bairro da Mata and São João dos Montes | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2021 | Portugal | Lisboa | Lisboa | 11 | 60 | 27-02-2018 | 14-04-2021 | 1142 | 350 | 4000000 | 3266121.33 | 3 | 3446981.63 | -180860.3 | 94.7531 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1. Global Price - 70% 2. Technical Value of the Proposal -30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the contract period by 48 days. two inspections were carried out for the purposes of provisional acceptance, on 13/05/2019 and 27/06/2019, where defects in the project were detected, with a period of 30 days being given, in both cases, to proceed with their correction . on 12/15/2019, a new inspection was carried out where it was found that the previously detected defects had been corrected and, as such, the inspection notice was drawn up for the purposes of provisional acceptance. | the change in the value of the project resulted from the suppression of contractual work, the carrying out of additional work and work to correct errors and omissions not previously detected, as well as the price review carried out.
2740 | 4403346 | Milling and Replacement of Bituminous Pavements | 45233222-1 | Paving and asphalting works | FALSE | 2017 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 23-03-2018 | 24-01-2020 | 672 | 365 | 400000 | 259540 | 2 | 257429.57 | 2110.43 | 100.8198 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to adverse weather conditions that affected the initially scheduled deadline | the project carried out was lower than the project planned.
2741 | 4401069 | 5010033243 - Contract for "Belt Line - Replacement of the roof of the platforms at the Alcântara-Terra Station, in fiber cement, and treatment and painting of the metallic structure" | 45261920-9 | Roof maintenance work | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 39 | 03-04-2018 | 28-09-2020 | 909 | 180 | 490000 | 485430.5 | 2 | 483290.86 | 2139.64 | 100.4427 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of 12 days regarding the time elapsed between the inspection and the signature of the provisional receipt | failure to carry out planned work, contract valuations, referring to items 2.1 and 4.1, of the mqt
2742 | 4400253 | PRC_0141/2017 - EGA-AR0342 - Contract for the execution of the Rio Ave Pumping System (FD10): Retort Subsystem (Vila do Conde) | 45232411-6, 45232423-3 | Foul-water piping construction work, Sewage pumping stations construction work | FALSE | 2017 | 2020 | Portugal | Vila do Conde | Porto | 13 | 20 | 07-03-2018 | 09-06-2020 | 825 | 210 | 750000 | 558158.49 | 2 | 609680.08 | -51521.59 | 91.5494 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | phased availability of land needed for the contract, difficulties in executing the project due to the high water level of the land and delays in the execution of the projects by the contractor. | there was no need to carry out all the contractual work, namely bituminous paving and manholes, due to the optimization of the route at interceptor 10.ret.a and 10.ret.b, which implied underwork. however, there was a need to provide mechanical protection to the piping with reinforced concrete in a low-coverage area in interceptor 10.ret.b, due to the change in the morphology of the land caused by the landclient and the need for 1 reprofiling of 10.ret. a due to a water line, implying extra work and suppression of errors and omissions, respectively
2743 | 4399253 | Procedure no. 92/DSUMC/2017 - Contract for the refurbishment of buildings for the installation of the Protection and Rescue Intervention Group at the Pontinha headquarters of the National Guard Intervention Unit | 45454000-4 | Restructuring work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 23-03-2018 | 06-03-2019 | 348 | 150 | 469962 | 439600 | 2 | 439600 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: according to the criteria defined in the Annex IV of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the request was due to the constant unavailability of the ready-mix concrete plants to respond to the project's planning/needs. delay in the delivery of materials/equipment by suppliers/manufacturers in order to comply with the approved planning, specifically: delivery of specific electrical/ited material. system of partitions foreseen in projects with extended delivery times by the manufacturer subject to approved planning. bad weather during the month of november/2018, which made it impossible to carry out the coatings and waterproofing of the roofs provided for in the terms of reference subject to the approved planning.
2744 | 4396505 | Refurbishment of Avenida das Tílias and Largo das Bombas de Gasoline | 45211360-0 | Urban development construction work | FALSE | 2017 | 2019 | Portugal | Sernancelhe | Viseu | 20 | 30 | 04-04-2018 | 24-06-2019 | 446 | 240 | 630089.01 | 535575.67 | 2 | 530440.64 | 5135.03 | 100.9681 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - %; 🇧🇷 🇧🇷 🇧🇷 The provisions of point 12 and following procedures Program - 100.00%. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions of the deadline for the execution of the project | underwork
2745 | 4393930 | Replacement and improvement of pavements in streets of several villages | 45233142-6 | Road-repair works | FALSE | 2017 | 2018 | Portugal | Mortágua | Viseu | 20 | N/A | 06-02-2018 | 20-12-2018 | 317 | 60 | 214462.88 | 185775.3 | 1 | 188356.46 | -2581.16 | 98.6296 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the value of the price revision in the amount of €2,581.16
2746 | 4392768 | Torrão water supply network and wastewater drainage network - Alpendurada, Várzea and Torrão | 45000000-7 | Construction work | FALSE | 2017 | 2020 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 20-03-2018 | 02-10-2020 | 927 | 360 | 848747.5 | 698995 | 2 | 600133.5 | 98861.5 | 116.4733 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions and suspensions | underwork
2747 | 4392353 | Current conservation of the pavement of roads in the municipality of Guimarães - 2018 | 45233142-6 | Road-repair works | FALSE | 2018 | 2019 | Portugal | Guimarães | Braga | 3 | 20 | 29-03-2018 | 27-06-2019 | 455 | 365 | 368205.35 | 336745.5 | 2 | 336745.5 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was communicated on 5/7/2018.
2748 | 4392074 | Conservation of the Municipal Road Network - Repaving of the E.M. Nº 501 (France - Aveleda) | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Bragança | Bragança | 4 | 30 | 03-04-2018 | 14-08-2018 | 133 | 180 | 420000 | 333764.2 | 2 | 333764.2 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical quality of the proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | reinforcement of work teams and favorable weather conditions.
2749 | 4391939 | Construction of a viewpoint at the site called "TAPADA DA MAISA", in Gavião | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2019 | Portugal | Gavião | Portalegre | 12 | N/A | 23-03-2018 | 18-04-2019 | 391 | 210 | 339112.1 | 273298.14 | 2 | 273298.14 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | there were no changes to the value of the project
2750 | 4389468 | PRC_0219/2017_GAE - EGA-AR0360 - Execution contract for the Terras de Bouro Interceptor System | 45232411-6, 45232423-3 | Foul-water piping construction work, Sewage pumping stations construction work | FALSE | 2017 | 2020 | Portugal | Terras de Bouro | Braga | 3 | 20 | 22-02-2018 | 14-03-2020 | 751 | 224 | 900000 | 786854.09 | 2 | 686633.38 | 100220.71 | 114.596 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project contract had several vicissitudes that conditioned, in what way, the foreseen term. first of all, the conclusion of some of the expropriation processes of plots of land for the installation of the manholes and the interceptor during the execution of the projects meant that the contractor consortium demobilized human and material resources from the land, with repercussions on income. on the other hand, the execution project had several adaptations due to the conditions of the land, and the contractor consortium had, in this aspect, a preponderance in the aid to águas do norte, s.a. | the final value calculated for the contract, including the value of the project to correct errors and omissions and the value of the price revision, was below the value of the award (about 13%). this indicator results from the accounting/determination of underwork, a substantial part derived from the suppression of work, namely the e.e. from valbom, the c.e. de valbom and the rio homem gravity collector – p1, between manholes no. b13 and no. b10. there are no accounting deviations in relation to the projects of the initial contract.
2751 | 4383904 | The object of the contract is the execution of the construction contract for the Center for Active and Community Integration, Parish of São Sebastião, Ponta Delgada | 45215200-9 | Construction work for social services buildings | FALSE | 2017 | 2020 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 46 | 28-03-2018 | 10-03-2020 | 713 | 365 | 570000 | 555301.84 | 2 | 598600.29 | -43298.45 | 92.7667 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension and extension of term. | additional work and price revision.
2752 | 4382445 | Conservation and restoration of the bastion of S. Vicente | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Elvas | Portalegre | 12 | 24 | 28-03-2018 | 26-10-2020 | 943 | 120 | 285000 | 219711.57 | 1 | 219711.57 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: These are those contained in Article 5 of the Program of Procedure. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to carry out an inspection for verification and some works | price review worth €2206.90
2753 | 4380539 | Earth movement; Indirect foundations; Reinforced concrete structure; masonry; Waterproofing and insulation; stonework; Hidraulic instalations; smiths; Carpentry; Coatings; | 45215222-9 | Civic centre construction work | FALSE | 2017 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 60 | 22-03-2018 | 22-04-2021 | 1127 | 270 | 700000 | 557268.94 | 2 | 574248.09 | -16979.15 | 97.0432 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: CP factor - 50% QTP factor - 50% face-to-face draw | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two work suspension notices and a deadline extension notice were duly approved.
2754 | 4377295 | Rehabilitation/Remodeling of Buildings 4, 11, 12, 14, 15, 18, 23, 25, 27, 28 and 29, in Bairro do Cerco | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2020 | Portugal | Porto | Porto | 13 | 40 | 19-03-2018 | 19-02-2020 | 702 | 600 | 5600000 | 5492976.5 | 3 | 5547424.17 | -54447.67 | 99.0185 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | TRUE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | eo in the amount of €1,129,403.28 and work not carried out in the amount of €1,074,955.61
2755 | 4375989 | S.e.c. - PROCº nº 216/A1/17 - Public Tender for the contract award of "Requalification and Modernization of the elementary and High school of Barroselas" | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 26-03-2018 | 13-03-2020 | 718 | 450 | 1850000 | 1849238.82 | 3 | 1848114.4 | 1124.42 | 100.0608 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value of the Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions. | underwork
2756 | 4374219 | Contract for the Implementation of an Efficient LED Lighting System in the Aveiro Unit of the Centro Hospitalar do Baixo Vouga, E.P.E. | 45310000-3 | Electrical installation work | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | 22 | 09-03-2018 | 03-04-2019 | 390 | 210 | 998000 | 832830 | 2 | 955647.69 | -122817.69 | 87.1482 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a deadline extension was approved, the causes of which are identified below, namely: - on 09/10/2019 the extension of the deadline was approved, setting the completion date of the contract at 12/31/2018. | additional works and works to supply errors and omissions, not included in the initial contract.
2757 | 4373640 | Contract for the Requalification of Spaces for Public Usufruct of the Natural Reserve of Dunes of São Jacinto | 45220000-5 | Engineering works and construction works | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | 30 | 21-09-2017 | 08-10-2019 | 747 | 270 | 765000 | 761279.67 | 2 | 697398.35 | 63881.32 | 109.1599 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the course of the projects, there was always a slow pace in the execution of the projects, which was aggravating the delay in the execution period. | without changes
2758 | 4373315 | Execution of water supply networks. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Odemira | Beja | 2 | 24 | 21-02-2018 | 30-01-2020 | 708 | 180 | 414496.08 | 259086.92 | 2 | 278687.99 | -19601.07 | 92.9667 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in delivery of the construction waste management guide. | introduction of vat and price revision in the final price of the project.
2759 | 4373164 | S.e.c. - PROCº nº 181/A1/17 - Public Tender for the award of the contract for "Requalification of the Surroundings of Jardim D. Fernando and streetde Santiago" | 45233252-0 | Surface work for streets | FALSE | 2017 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 22-03-2018 | 31-07-2019 | 496 | 150 | 794200 | 773212.37 | 2 | 766802.27 | 6410.1 | 100.836 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the Proposal - 60%; Price - 40%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
2760 | 4371126 | Calçadinha outfalls and pumping stations | 45232400-6 | Sewer construction work | FALSE | 2017 | 2019 | Portugal | Elvas | Portalegre | 12 | 24 | 16-03-2018 | 17-04-2019 | 397 | 180 | 452000 | 381309.78 | 2 | 372059.78 | 9250 | 102.4862 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: These are those contained in Article 5 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climatic conditions. | there were €2,339.34 underwork
2761 | 4369970 | Rehabilitation contract for the Monte Formoso Reservoir | 45259000-7 | Repair and maintenance of plant | FALSE | 2017 | 2019 | Portugal | Coimbra | Coimbra | 6 | 42 | 29-01-2018 | 23-10-2019 | 632 | 270 | 700000 | 668271.35 | 2 | 744637 | -76365.65 | 89.7446 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60% 2. Technical Value - 40% | 1 | 60 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work resulting from alteration of the electrical project at the request of edp and dgeg | need to implement new solutions on site, which proved to be fundamental to the execution of the contract and emerged as a result of unforeseen circumstances.
2762 | 4368979 | Contract for the execution of waste and rainwater collectors and branches - 2018/2019. | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Albufeira | Faro | 8 | 20 | 21-03-2018 | 04-03-2020 | 714 | 600 | 300000 | 213250 | 1 | 213500 | -250 | 99.8829 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
2763 | 4368847 | Construction work n.º 18/2017/dpgom – territorial post of National Guard de alcanena | 45222300-2 | Engineering work for security installations | FALSE | 2017 | 2019 | Portugal | Alcanena | Santarém | 16 | 31 | 08-03-2018 | 16-07-2019 | 495 | 360 | 397113.37 | 357402.04 | 2 | 354063.24 | 3338.8 | 100.943 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | resolve minor issues.
2764 | 4368815 | Water supply system to miranda do douro - north sector | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Miranda do Douro | Bragança | 4 | 24 | 19-03-2018 | 23-06-2020 | 827 | 540 | 1902364.72 | 1784689.29 | 3 | 1756046.14 | 28643.15 | 101.6311 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions unfavorable to the execution of the project | underwork
2765 | 4364533 | Repair and Painting of Facades of Buildings in streetVale Formoso de Cima, Blocks A1 to A6 and B1 to B6, Chelas, Lisbon, Property of the Social services of the National Guard. | 45454000-4 | Restructuring work | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 08-03-2018 | 22-10-2018 | 228 | 150 | 299000 | 248200 | 1 | 248200 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to point out
2766 | 4363033 | The object of this contract is the construction of the wastewater drainage network with a total length of 21.3 km and 927 home branches with the respective manholes and branch. The company | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Ovar | Aveiro | 1 | N/A | 12-02-2018 | 27-05-2020 | 835 | 365 | 3250000 | 1950000.01 | 3 | 1877459.48 | 72540.53 | 103.8638 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B2 Work Plan detail and consistency: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2767 | 4362734 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2018 | Portugal | Sever do Vouga | Aveiro | 1 | N/A | 28-08-2017 | 20-09-2018 | 388 | 365 | 249000 | 198057.06 | 1 | 198057.06 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2768 | 4361242 | 5010033669 - Replacement of wooden sleepers with concrete and rail sleepers and construction of long welded bars between Barreiro - A and Lavradio, on roads A and D | 45234100-7 | Railway construction works | FALSE | 2017 | 2021 | Portugal | N/A | N/A | N/A | 20 | 15-03-2018 | 14-01-2021 | 1036 | 60 | 300000 | 289380.81 | 2 | 248790.81 | 40590 | 116.3149 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (65% weighting) - FPRECIO b) Technical value (weighting of 15%) - FVT c) Safety Management System (10% weighting) - FSGS d) Quality Control System for the provision of services (5% weighting) - FSGQ e) Technical Note on Environmental Monitoring (5% weighting) - FNTAA | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2769 | 4360926 | The object of the contract is the requalification of the central section of Vila de Vouzela, which comprises the street and square Morais de Carvalho and part of streetRibeiro Cardoso. | 45211360-0 | Urban development construction work | FALSE | 2017 | 2020 | Portugal | Vouzela | Viseu | 20 | 18 | 13-03-2018 | 20-01-2020 | 678 | 365 | 380000 | 349389.35 | 2 | 339735.77 | 9653.58 | 102.8415 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the change in the value of the project was due to less verified works.
2770 | 4360137 | The object of the contract is the requalification of the Vouzela cineteatro building. | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2016 | 2019 | Portugal | Vouzela | Viseu | 20 | 12 | 14-03-2018 | 01-08-2019 | 505 | 180 | 253726.08 | 202980.87 | 1 | 202980.87 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the contractually established period. | no change.
2771 | 4359261 | Carrying out of the contract “extension of vl7 (avenida eugénio de andrade) to street of loureiro (vl3 – avenida to the mar) | 45233225-2 | Single carriageway construction work | FALSE | 2017 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 13-03-2018 | 21-04-2020 | 770 | 275 | 418605.66 | 388708.1 | 2 | 388364.59 | 343.51 | 100.0885 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (CP) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractual breach. | a provisional price review of €17,263.65 was determined and the completion of the project resulted in underwork worth €17,607.16.
2772 | 4356190 | Urban Cyclable Network of Cantanhede, by Contract - CP-CCP-EMP No. 05/2017 | 45233162-2 | Cycle path construction work | FALSE | 2017 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 31 | 16-03-2018 | 30-09-2020 | 929 | 360 | 500621.95 | 434961.15 | 2 | 404394.22 | 30566.93 | 107.5587 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of works. | existence of more work and underwork.
2773 | 4355665 | Adaptation of pm010/elvas to a museum of archeology and ethnography | 45212313-3 | Museum construction work | FALSE | 2017 | 2021 | Portugal | Elvas | Portalegre | 12 | 24 | 14-03-2018 | 26-01-2021 | 1049 | 335 | 3100000 | 3066003.48 | 3 | 3019147.79 | 46855.69 | 101.552 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: These are those contained in Article 5 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the pandemic and the state of emergency in force during some months of 2020. | adaptability of the project to the project, so there was a need to remove some items that were in duplicate
2774 | 4348766 | Requalification of the Trucking Center | 45454100-5 | Restoration work | FALSE | 2017 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 28 | 13-03-2018 | 24-09-2021 | 1291 | 270 | 400510.55 | 399736.58 | 2 | 396786.59 | 2949.99 | 100.7435 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions and delay in the delivery of materials by suppliers. | deletion of works.
2775 | 4346064 | The object of this contract is the execution of the sanitation network of Vila de Prado | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Vila Verde | Braga | 3 | 30 | 08-03-2018 | 19-10-2020 | 956 | 365 | 877854.53 | 702283.63 | 2 | 702283.63 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70%; Technical value of the proposal - 30% [considering: Descriptive memory and justification of the mode of execution of the contract (50%) and the Work Program (50%] (as better explained in point 17 of the Tender Program | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
2776 | 4345845 | 5010027397 - Belt Line - Improvement of track superstructure on the TT Chelas - Braço de Prata section | 45234100-7 | Railway construction works | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 31 | 08-03-2018 | 19-12-2019 | 651 | 270 | 3720000 | 2821461.12 | 3 | 2959244.65 | -137783.53 | 95.344 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 65% Technical Valuation 15% Safety Management System 10% Quality Management System 5% Environmental Management System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2777 | 4345807 | Requalification of outdoor spaces (pavements and motorway) | 45432110-8 | Floor-laying work | FALSE | 2017 | 2018 | Portugal | Resende | Viseu | 20 | 20 | 15-11-2017 | 12-12-2018 | 392 | 180 | 223821.61 | 206110 | 1 | 206110 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | constant reformulations and adjustments to the project by the owner of work and adverse weather conditions.
2778 | 4344977 | Restoration contract for the Carlos Ramos Pavilion | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 36 | 22-02-2018 | 30-11-2018 | 281 | 180 | 264000 | 254890.93 | 2 | 285991.15 | -31100.22 | 89.1255 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Work _ 40%; b) Technical value of the proposal _ 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to carry out more work on the roof. | the extra work already mentioned, as well as the errors and omissions detected.
2779 | 4343916 | Improvement of the Pedestrian Walks Network in Vila de Boticas | 45233200-1 | Various surface works | FALSE | 2017 | 2020 | Portugal | Boticas | Vila Real | 19 | 21 | 08-03-2018 | 21-09-2020 | 928 | 180 | 300706.99 | 250578.82 | 2 | 250578.82 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 70% b) Technical Valuation of the Proposal - 30% To dedeadlineine the Technical Value of the Proposal, the following subfactors will be considered: - Descriptive Memory (MD) - 55% - Work Plan (PT) - 45% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | at the beginning of the contract, it was necessary to obtain the necessary authorizations and approval of the signage plan in advance, from infraestruturas de portugal, a process that proved to be time-consuming. cumulatively, there were demolition works and opening of ditches, corresponding to the beginning of the contract, which were carried out predominantly during the months in which there was a large influx of migrants and emigrants, who, during the vacation period, significantly increased the road flow, in the sections of the road. intervention target. thus, it became pertinent to increase safety conditions, both for workers and for other passers-by. in view of these circumstances, the movement of equipment allocated to the contract began to be carried out less quickly, causing significant delays in the course of the projects.
2780 | 4339239 | Requalification of the intersection of Avenida de S. Miguel and Avenida da Estação | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2021 | Portugal | Guarda | Guarda | 9 | 20 | 09-03-2018 | 29-04-2021 | 1147 | 60 | 356500 | 349900 | 2 | 361129.3 | -11229.3 | 96.8905 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Bid Price 60% Technical Valuation 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of work suspensions and deadline extensions | existence of price revision
2781 | 4333188 | Rehabilitation of the exterior spaces of the housing blocks on streetde arouca - lot c | 45112700-2 | Landscaping work | FALSE | 2017 | 2018 | Portugal | São João da Madeira | Aveiro | 1 | 36 | 16-02-2018 | 10-12-2018 | 297 | 120 | 228096.72 | 198885.28 | 1 | 198885.28 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
2782 | 4332998 | Construction of the threshing floor, oven house and restoration of the mill house, nature house and landscaping – rio ul urban park | 45212170-8 | Entertainment building construction work | FALSE | 2017 | 2021 | Portugal | São João da Madeira | Aveiro | 1 | 20 | 14-02-2018 | 20-04-2021 | 1161 | 240 | 205000 | 197109.78 | 1 | 211306.91 | -14197.13 | 93.2813 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% Technical value of the proposal 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions | extra work
2783 | 4327745 | Contract designation: Closure of the Water Supply Networks of the Agere/Ponte do Bico, Andorinhas and Rabagão Subsystems and of the wastewater networks of the Ave and Serzed Basin Subsystems | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Póvoa de Lanhoso | Braga | 3 | 21 | 13-11-2017 | 04-06-2020 | 934 | 450 | 4169431.05 | 3752487.96 | 3 | 3962062.1 | -209574.14 | 94.7105 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | additions had to be made. | more work and underwork.
2784 | 4324796 | Contract for the Modernization of the Fishing Port of Castelo do Neiva | 45244100-0 | Marine installations | FALSE | 2016 | 2021 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 60 | 21-02-2018 | 08-04-2021 | 1142 | 240 | 1256000 | 1098666.07 | 3 | 1038201.23 | 60464.84 | 105.824 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price: 30% b) Technical Quality of the Proposal: 70% b.1) Descriptive and Justification: 35% b.2) Work Plan: 20% b.3) Occupational Health and Safety Management: 15% | 1 | 30 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension for security reasons, both for performers and third parties; partial suspension of work; set of constraints, with greater relevance to those of a technical/constructive nature, which make it impossible to conclude the project on a date prior to the established date; and in the ongoing constraint of worsening weather conditions, since this circumstance made the execution of some of the tasks (which constituted the critical path) unfeasible by not guaranteeing the proper technical conditions for execution. | objective modification (pavement), underwork following the pronunciation of the entity docapesca portos e lotas s.a. regarding the provision of the crane and workshop equipment; work not carried out during the contract, due to not reaching the expected quantities.
2785 | 4303920 | The object of this contract is the construction of a domestic wastewater drainage system with approximately 10.4 km of gravity network, 430 home extensions and 10 pumping stations | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Estarreja | Aveiro | 1 | N/A | 14-02-2018 | 11-03-2020 | 756 | 365 | 2100000 | 1491503.52 | 3 | 1473943.74 | 17559.78 | 101.1913 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment - 10%) | 1 | 55 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
2786 | 4302255 | Requalification of streetD. Afonso Henriques, in Cantanhede, by Contract - CP-CCP-EMP n.º 04/2017 | 45113000-2 | Siteworks | FALSE | 2017 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 30 | 05-03-2018 | 29-06-2020 | 847 | 240 | 377358.49 | 342966.33 | 2 | 333130.1 | 9836.23 | 102.9527 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of works | existence of more work and underwork.
2787 | 4294095 | Contract for the Connection of the Autonomous Systems of the South Zone of the Municipality of Abrantes to the Albufeira System of Castelo de Bode - Adductor Section Between Vale das Donas and the Tramagal Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Abrantes | Santarém | 16 | 30 | 19-02-2018 | 20-04-2020 | 791 | 210 | 710000 | 709950 | 2 | 725014.56 | -15064.56 | 97.9222 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% b) Technical Valuation of the Proposal - 40% According to criteria defined in clause 20 of the Tender Programme. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the 29-day extension proposed by the contractor was due to the supplier's difficulty in complying with the supply of ducts and accessories in accordance with the normal progress of the projects
2788 | 4292625 | Execution contract for the Supply Subsystem of Salvaterra de Magos and Foros de Salvaterra - Supply line to Várzea Fresca | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Salvaterra de Magos | Santarém | 16 | 24 | 31-01-2018 | 16-04-2019 | 440 | 150 | 250000 | 239350.62 | 1 | 236550.62 | 2800 | 101.1837 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the objective of the project was fully achieved, not requiring the invoicing of all items.
2789 | 4289459 | EGA-AR0065 - Contract for the rehabilitation of the S. Romão Interceptor (Viana do Castelo - Industrial Zone) | 45232411-6 | Foul-water piping construction work | FALSE | 2016 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 42 | 09-01-2018 | 10-01-2020 | 731 | 168 | 490000 | 342995 | 2 | 369992.54 | -26997.54 | 92.7032 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract's contractual term has increased substantially compared to what was foreseen, mainly due to the suspension of the execution period of the project and the extensions of the execution period strictly granted due to the suspension of the projects. in any case, it should be noted that the extension of the contractual term did not translate into greater burdens for the owner of the project, nor did it conditioned the normal development of the contract and the operation of the interceptor (in the operating state), it stands out, with many operational problems (several ruptures and numerous water infiltrations) | the final value of the project, compared to the award value, did not increase significantly (only in the order of 4%, as a result of the clearance and approval of errors and omissions supply work). compensation (pecuniary value) was also approved, as a result of the greater permanence of the contractor in the project, after the end of the suspension of the term and resumption of the execution of the projects
2790 | 4288645 | PRC_0034_2017 - EGA-EB0315 - Contract works for Closing Waste Water Networks in the parishes of Arões S. Romão and Golães, Fafe (Sto. Ovídio) and Fornelos - Municipality of Fafe | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Fafe | Braga | 3 | 12 | 30-01-2018 | 05-11-2020 | 1010 | 240 | 1300000 | 1147324.22 | 3 | 1065133.75 | 82190.47 | 107.7164 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in the availability of private plots of land and in obtaining an intervention license on national roads 206 and 207. | optimization of the route on national roads allowed for underwork to be done
2791 | 4288001 | 5010030603 - En342 km65+000, intersection geometric reformulation | 45233128-2 | Roundabout construction work | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 30 | 23-02-2018 | 17-07-2020 | 875 | 89 | 360000 | 296908.16 | 2 | 302974.16 | -6066 | 97.9978 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% - Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | resulting from changes in the execution project. | due to errors and omissions and design change
2792 | 4283387 | Construction of the WWTP (Wastewater Treatment Station) in Ferreira do Alentejo" | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2021 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 02-02-2018 | 28-05-2021 | 1211 | 300 | 995000 | 829671.03 | 2 | 849825.82 | -20154.79 | 97.6284 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The criterion for evaluating the proposals will be that of economically most advantageous proposal, based on the following evaluation criteria: PF = 0.70xP + 0.30xVT, where, P - Price; VT - Technical Valuation; The Price Factor is calculated by the following formula: P = 100 - 50 x (Pp/Pb), where: P- price factor score; pp - Price of the proposal under analysis; Pb - Base price of the tender (base value of the tender which, under the deadlines of the law, is the maximum price of the proposals). The technical value factor of the proposal will be the result of 3 factors: A - Work Program (40%); B - Descriptive Memory of the mode of execution of work (40%); C - Occupational Health and Safety Management (20%). Which results in the following expression math: VT = 0.4 *A + 0.4*B + 0.2*C. The Work Program subfactor (A) is divided into 3 subfactors: A1- Work Plan (40%); A2 - Labor Plan (30%); A3 - Equipment Plan (30%). Which results in the following mathematical expression A = (0.4x(A1/4) + 0.3x(A2/4) + 0.3x(A3/4)) x 100. These criteria are broken down into sub-criteria, in accordance with point no. Contest Program. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a delay in the development of the project due to the covid 19 pandemic and a delay in the supply of energy by the distributor, essential energy for carrying out the final tests and commissioning. | underwork due to design measurement errors.
2793 | 4279365 | Contract for the Modernization of the Cabedelo Fishing Vessel Repair Shipyard, in Viana do Castelo | 45241400-2 | Dock construction work | FALSE | 2016 | 2021 | Portugal | Esposende | Braga | 3 | 60 | 21-02-2018 | 29-11-2021 | 1377 | 180 | 290000 | 249458.82 | 1 | 298230.51 | -48771.69 | 83.6463 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price: 30 % b) Technical Quality of the Proposal: 70% b.1) Descriptive and Justification: 35% b.2) Work Plan: 20% b.3) Occupational Health and Safety Management: 15% | 1 | 30 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | shortage of skilled labor available to carry out the necessary subcontracting; difficulty in finding suppliers for certain materials; difficulties experienced in ensuring the contracted delivery time for supplies; lack of definitions regarding the design details of certain situations and delay in resolving them. | objective modification to the contract; complementary works necessary for the execution of the project; errors and omissions supply works; works less.
2794 | 4278120 | Improvement and remodeling of streetDr. Manuel Ferreira, streetDr. Gonçalo Sampaio, streetCapitão Tinoco Faria, streetLuís de Camões, streetDr. Avelino Pereira de Carvalho, streetMartim Moniz, street1º de Maio | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Póvoa de Lanhoso | Braga | 3 | 24 | 08-08-2017 | 26-07-2019 | 717 | 545 | 830000 | 747000.01 | 2 | 784085.89 | -37085.88 | 95.2702 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | non-existent. | additional work
2795 | 4277220 | Exterior restoration of the church of santo antónio | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 06-02-2018 | 25-07-2019 | 534 | 240 | 571544.46 | 457235.58 | 2 | 542737.76 | -85502.18 | 84.2461 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2796 | 4274045 | Complete refurbishment of the IFT property in Braga, owned by the Social services of the National Guard. | 45454000-4 | Restructuring work | FALSE | 2017 | 2018 | Portugal | Braga | Braga | 3 | 21 | 29-01-2018 | 01-08-2018 | 184 | 120 | 180000 | 165662.12 | 1 | 165662.12 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to point out
2797 | 4272591 | Improvement of Urban Mobility and Road Safety in the Municipality of Reguengos de Monsaraz - Requalification and Modernization of Pedestrian Routes in the City of Reguengos de Monsaraz-1st Phase | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 12-02-2018 | 22-07-2019 | 525 | 210 | 361925.51 | 277793.58 | 2 | 293484.19 | -15690.61 | 94.6537 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price (70%) Subfactors: - Overall Price (90%); - Note justifying the Proposed Price (10%). | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work for 30 days. | price revision calculation
2798 | 4270107 | Quarteira Fishing Port Fence | 45340000-2 | Fencing, railing and safety equipment installation work | FALSE | 2017 | 2019 | Portugal | Loulé | Faro | 8 | N/A | 14-02-2018 | 19-02-2019 | 370 | 90 | 220000 | 211000 | 1 | 212843.47 | -1843.47 | 99.1339 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 50%; lead time 10%; quality proposal technique 40% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | price review - €1,843.47
2799 | 4268788 | Requalification of Largo de Santo António - Santiago de Piães | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Cinfães | Viseu | 20 | 20 | 20-09-2016 | 08-06-2018 | 626 | 180 | 300678.51 | 249494.26 | 1 | 222766.16 | 26728.1 | 111.9983 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather | over and underwork
2800 | 4264718 | Contract for the Urban Requalification of streetCorredoura do Mestre in Tomar | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Tomar | Santarém | 16 | 24 | 08-02-2018 | 28-09-2020 | 963 | 365 | 990000 | 594000.01 | 2 | 650705.73 | -56705.72 | 91.2855 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in carrying out the infrastructures by edp | increase in areas for demolition and reconstruction of fence walls; increase in the volume of excavation of trenches for infrastructure; reduction of paving costs
2801 | 4260722 | Public works contract for the Parking Area – Pedrouços | 45113000-2 | Siteworks | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | 41 | 07-12-2017 | 24-07-2018 | 229 | 120 | 350000 | 209428.8 | 1 | 187388.74 | 22040.06 | 111.7617 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there was no non-compliance with the established contractual term
2802 | 4253857 | Contract work for "Linha do Sul - Torre Vã to Funcheira and Funcheira to Tunes (Km 271,995 to 301,600) - Replacement of the existing fixing with NABLA fixing and regularization of the welded long bars" | 45234100-7 | Railway construction works | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 42 | 12-02-2018 | 14-05-2020 | 822 | 150 | 500000 | 387788.32 | 2 | 389681.35 | -1893.03 | 99.5142 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Management System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2803 | 4240376 | Maceira WWTP Remodeling Contract | 45232420-2 | Sewage work | FALSE | 2016 | 2019 | Portugal | Torres Vedras | Lisboa | 11 | 48 | 20-12-2017 | 27-06-2019 | 554 | 240 | 700000 | 652614.18 | 2 | 696715.66 | -44101.48 | 93.6701 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Price -50% b) Technical Valuation - 50% b.1. Work execution methodology - 25% b.2. Detail and consistency of the Work Plan - 15% b.2.1. Work Schedule - 10% b.2.2. Means Plan - 5% b.3. Characterization and quality of equipment and materials - 10% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | undertaking had an objective modification of the contract. inspections for provisional acceptance purposes. | abnormal and unforeseen changes in circumstances - objective modification of the contract
2804 | 4238754 | Contract for Adding to Amareleja - 2nd Phase | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2018 | Portugal | Moura | Beja | 2 | 20 | 29-12-2017 | 03-12-2018 | 339 | 270 | 720000 | 510191.74 | 2 | 513277.7 | -3085.96 | 99.3988 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: A. Price: 60% B. Technical Valuation: 40% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 10% B.2.1 Work Schedule: 7.5% B.2.2 Means Plan: 2.5% B.3 Characterization of equipment and materials: 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | underwork and price revision | underwork and price revision
2805 | 4234174 | Urban Requalification of the Sea Front of the City of Horta - Requalification of the Churchyard of the Church of Angustias, of Largo do Infante D. Henrique and execution of a car park | 45000000-7 | Construction work | FALSE | 2017 | 2020 | Portugal | Horta | Região Autónoma dos Açores | 15 | 36 | 04-12-2017 | 02-12-2020 | 1094 | 300 | 1491276.36 | 1400000 | 3 | 1406673.35 | -6673.35 | 99.5256 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1- Price -85% K2 - Technical Quality of the Proposal - 15%, subdivided into two sub-factors: K2.1 - Work Plan: 70%; K2.2 - Descriptive and Justification of the Work Execution Mode: 30%. | 1 | 85 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions of the execution period of the project | supply of errors and omissions and price review
2806 | 4233150 | EGA-EB0269 - Contract for the Conception-Construction of the Gralheira WWTP and extension of the wastewater drainage network (Cinfães) | 45252000-8, 45232411-6 | Construction works for sewage treatment plants, purification plants and refuse incineration plants, Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Cinfães | Viseu | 20 | 47 | 16-01-2018 | 16-07-2020 | 912 | 273 | 450000 | 418877.71 | 2 | 448693.97 | -29816.26 | 93.3549 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the main causes occurred in the start-up phase of the wwtp, namely due to the delay in the execution of the wwtp power branch by an entity external to the project, namely edp, and also during the start-up phase, which, as it started in the winter season , the quality of the gross affluent at the entrance of the wwtp: the conditions of flow at the entrance of the wwtp were very diluted, systematically entering the wwtp in bypass, not allowing, within the stipulated period of time, to draw conclusions in relation to the commitment of guarantees, and therefore to evaluate the performance of infrastructure. during the execution of the physical works, there was also an extension of the deadline due to the need to extend the emissary arriving at the wwtp and, together with this situation, there were also delays in the normal development of the projects under the responsibility of the contractor. | the only change in the billing of the contract resulted from the need for an additional number of errors and omissions due to the extension of the emissary arriving at the wwtp, essential for the installation to start operating.
2807 | 4227722 | Execution contract for the Montes do Rio Wastewater Treatment Plant | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2016 | 2019 | Portugal | Alcoutim | Faro | 8 | 30 | 07-02-2018 | 09-05-2019 | 456 | 270 | 201723.5 | 170912.19 | 1 | 183004.66 | -12092.47 | 93.3923 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with the provisions of number 12.3 of the tender program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to provisional reception.
2808 | 4226161 | The object of the contract is the refurbishment of the Coelho e Castro School in Fiães | 45210000-2 | Building construction work | FALSE | 2017 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 30-01-2018 | 21-07-2021 | 1268 | 365 | 2888854.56 | 2493412.34 | 3 | 2645953.31 | -152540.97 | 94.2349 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 112 days deadline for the execution of additional works, 220 days delay in the conclusion of the project, 338 days due to the partial suspension of the project, without interference in the critical path of the rest of the project 14 days to schedule the inspection and 161 days to correct physical and documental defects | need to carry out other works (+ / e&o) that went beyond the contractual work, taking into account that requalification works were involved and, as such, with special characteristics of unpredictability underwork resulting from the replacement of direct foundations by foundations using piles (new procedure) for the roof of the outdoor playground, and still surplus, based on the final calculation of all the amounts of work on the job
2809 | 4225435 | "Contract work for the execution of the Spas on Floor 0 and expansion of the Pharmacy of the Medicine and Rehabilitation Center of Alcoitão 🇧🇷 | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 29-01-2018 | 27-03-2019 | 422 | 120 | 205000 | 165000 | 1 | 185615.48 | -20615.48 | 88.8934 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adjustments were made to the execution project, in order to satisfy the technical requirements, resulting in extra and underwork and the supply of errors and omissions.
2810 | 4224916 | Expansion and requalification of the Julio Saul Dias Elementary School - Vila do Conde | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2021 | Portugal | Vila do Conde | Porto | 13 | 30 | 25-01-2018 | 25-03-2021 | 1155 | 360 | 1575000 | 1548543.76 | 3 | 1592830.64 | -44286.88 | 97.2196 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: TECHNICAL QUALITY OF THE PROPOSAL 40%; PRICE 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2811 | 4221016 | Installation of the Abrantes Citizen's Store in the Municipal Building | 45262700-8 | Building alteration work | FALSE | 2017 | 2019 | Portugal | Abrantes | Santarém | 16 | 36 | 02-02-2018 | 23-07-2019 | 536 | 210 | 716516.92 | 589751.35 | 2 | 578342.85 | 11408.5 | 101.9726 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | provisional acceptance took place on 24.01.2019 after correcting the anomalies found in the inspection carried out on 4.01.2019 | underwork and the ordinary revision of prices were considered.
2812 | 4218967 | The purpose of the contract is to expand the Urban Wastewater System in Cambra. | 45232460-4 | Sanitary works | FALSE | 2017 | 2021 | Portugal | Vouzela | Viseu | 20 | 36 | 01-02-2018 | 10-12-2021 | 1408 | 660 | 999500 | 991115.19 | 2 | 955574.96 | 35540.23 | 103.7193 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline was due to two partial suspensions of the deadline and consequent extensions. | the change in the value of the project resulted from underwork.
2813 | 4218920 | Refurbishment of the Lota de Tavira building | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2018 | Portugal | Tavira | Faro | 8 | N/A | 26-01-2018 | 02-11-2018 | 280 | 180 | 430000 | 398850 | 2 | 75878.79 | 322971.21 | 525.641 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the new auction was not built. only the existing building was demolished | the new auction was not built. only the existing building was demolished
2814 | 4217323 | Câmara de Lobos Highway/Câmara de Lobos Strait-Access from streetAlferes Manuel Joaquim Lopes | 45233226-9 | Access road construction work | FALSE | 2017 | 2020 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 47 | 15-12-2017 | 20-10-2020 | 1040 | 120 | 700000 | 675033.47 | 2 | 600271.39 | 74762.08 | 112.4547 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | in the procedure carried out to carry out the measurements, pursuant to paragraph 2 of article 388 of the "public procurement code", it was verified that the calculation of some quantities of work did not reach the contractually foreseen
2815 | 4217119 | Wastewater System (SAR) of Encoberta | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2019 | Portugal | Penalva do Castelo | Viseu | 20 | 22 | 05-02-2018 | 06-11-2019 | 639 | 365 | 160308.97 | 149972.19 | 1 | 146636.24 | 3335.95 | 102.275 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | over and underwork
2816 | 4216791 | Rehabilitation ofelementary school 1 de Areias | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 26-01-2018 | 17-12-2018 | 325 | 180 | 219823.53 | 209694.36 | 1 | 204889.63 | 4804.73 | 102.345 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to weather conditions. | planned works that did not add value to the completion of the project.
2817 | 4216126 | Wastewater System (SAR) of Castelo de Penalva | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | Penalva do Castelo | Viseu | 20 | 22 | 05-02-2018 | 19-11-2020 | 1018 | 365 | 228902.21 | 168977.98 | 1 | 180319.18 | -11341.2 | 93.7105 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | over and underwork
2818 | 4213890 | The contract comprises the remodeling of the R4 reserve system and the water supply to the Casarão Business Park (PEC), in the União das Freguesias de Borralha e Águeda | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2021 | Portugal | Águeda | Aveiro | 1 | N/A | 02-02-2018 | 07-07-2021 | 1251 | 180 | 600000 | 360000.01 | 2 | 360000.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price: 55% B - Technical Value: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance by the executing entity | nothing to report
2819 | 4209263 | Rehabilitation and total restoration works of the 16th century building with 3 floors with a view to adapting it to cultural facilities. | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2021 | Portugal | Amarante | Porto | 13 | 20 | 31-01-2018 | 14-07-2021 | 1260 | 270 | 233000 | 208639.29 | 1 | 209512.49 | -873.2 | 99.5832 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions due to work execution conditions | underwork and price revision
2820 | 4202840 | Solve existing pathologies on the surface of the pavement, in order to minimize the propagation of cracks from the old bituminous layers to the new layers, seal the existing pavement | 45235111-4 | Airfield pavement construction work | FALSE | 2017 | 2019 | Portugal | Corvo | Região Autónoma dos Açores | 15 | 19 | 26-01-2018 | 29-11-2019 | 672 | 150 | 1980000 | 1950000 | 3 | 1950000 | 0 | 100 | most economically advantageous proposal PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 123 WEDNESDAY, JULY 5, 2017 If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) The award is made to the most economically advantageous proposal, this being dedeadlineined by the assessment of the factors submitted to competition, which are indicated below with the mention of the respective weighting: K1 - Price: corresponding to a weighting of 50% of the overall assessment; K2 - Quality Proposal Technique: corresponding to a weighting of 50% of the overall evaluation, subdivided into two subfactors: K2.1 - Work Plan: 60%; K2.2 - Descriptive Memory and Justification of the Mode of Execution of the Work: 40%. K = (0.60 x k1) + (0.40 x K2). | 1 | 50 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to bad sea conditions, it was not possible to carry out the transport of the materials necessary for carrying out the transverse grooving of the runway on the scheduled dates.
2821 | 4200729 | Improvement of the municipal road network on the section between streetFrancisco Guerreiro and Pre-Escolar de Pechão | 45233140-2 | Roadworks | FALSE | 2017 | 2020 | Portugal | Olhão | Faro | 8 | 20 | 06-11-2017 | 02-07-2020 | 969 | 150 | 320000 | 265874.03 | 2 | 263914.03 | 1960 | 100.7427 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | request for extension and reception of public lighting works by edp | works less on the ip network
2822 | 4199972 | PC.131.2017.0000722 - Rehabilitation of the Technical School Zone Neighborhood, in Viana do Castelo. | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 05-01-2018 | 04-12-2020 | 1064 | 300 | 617900 | 589466.27 | 2 | 589466.27 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The most economically advantageous proposal having into account the following factors with the following weighting: Price ......................................... 80% Technical value of the proposal ..... 20% - Price factor: evaluated according to the application of the formula provided for in paragraph 26 of the Tender Program - Technical value of the proposal: evaluated by applying the following formula: Vti=0.50Pli+0.50Pci, regarding the following subfactors: Planning (Pli) - 50% and construction processes (Pci) - 50%, through the scoring method defined in nº 26 of the Tender Program. | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the alteration to the execution period of the contract was due to the 3 orders issued by the cd, authorizing the extension of the execution period of the contract by 346 days | no change
2823 | 4199315 | Pe_17100_cne - national public tender for the contract to adapt spaces at the marquês de pombal High school, in lisbon, for the provisional installation of the music school at the conservatory | 45210000-2 | Building construction work | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 26-01-2018 | 29-11-2018 | 307 | 120 | 680221.79 | 669239.52 | 2 | 687058.11 | -17818.59 | 97.4065 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | increase in the final value of the project, as a result of contracting 2 amendments to contracts for additional work on errors and omissions
2824 | 4199063 | Public Works Contract for the Execution of the Land Retaining Wall - Pombal Enclosure | 45222000-9 | Construction work for engineering works except bridges, tunnels, shafts and subways | FALSE | 2017 | 2020 | Portugal | Lisboa | Lisboa | 11 | 60 | 29-01-2018 | 29-01-2020 | 730 | 150 | 200000 | 199980 | 1 | 214605.13 | -14625.13 | 93.1851 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the alteration to the execution period of the project resulted, essentially, from the impossibility of carrying out the excavation work in the rainy season, from the alteration of the project methodology, as well as from the delay in the approval by the cml for the conditioning of the road and the availability of agents . | the alteration in the value of the project resulted from the carrying out of works to supply detected unforeseen errors and omissions, as well as the price revision carried out.
2825 | 4198195 | Hot bituminous concrete paving of several roads in the municipality, including in the city of Coimbra, which are very degraded, including the replacement of horizontal signage painting | 45233252-0 | Surface work for streets | FALSE | 2017 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 24-07-2017 | 26-11-2019 | 855 | 300 | 2099500 | 1598514.72 | 3 | 1647004.57 | -48489.85 | 97.0559 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work with extension of the deadline for a period of 45 days, due to adverse weather conditions that were recorded and the alteration of streets that allegedly conditioned the planning of the streets to intervene in the contract. | price revision amount
2826 | 4198091 | Conservation at Conceição Elementary School | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Tavira | Faro | 8 | 30 | 26-01-2018 | 21-12-2020 | 1060 | 270 | 282836.84 | 279900 | 2 | 297568.23 | -17668.23 | 94.0625 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of 47 days and delivery of the technical compilation. | correction of errors and omissions in the amount of €13,903.06, underwork in the amount of -600.99€ and definitive price revision in the amount of €4,366.16 (positive).
2827 | 4194946 | EGA-EB0299 - Contract for the Design and Construction of the Pinheiro WWTP (Baião) | 45252000-8 | Construction works for sewage treatment plants, purification plants and refuse incineration plants | FALSE | 2017 | 2021 | Portugal | Baião | Porto | 13 | 47 | 19-01-2018 | 04-02-2021 | 1112 | 273 | 425000 | 398500 | 2 | 416030.92 | -17530.92 | 95.7861 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to unforeseen circumstances beyond the control of those involved in the project, it was necessary to postpone the start-up of the pinheiro wwtp, in order to ensure the necessary conditions for its operation: - it remained to build an extension of the collector of about 130 meters, due to the unavailability of the land, awaiting the publication of the declaration of public utility (dup), for the conclusion of the collector; - there was no electricity supply to the pinheiro wwtp, due to delays in edp's response to the construction of the branch to supply electricity, without which the wwtp would not be able to start operating. - the start-up phase suffered constraints due to the increased difficulties caused by the pandemic caused by covid-19, with a higher incidence during the second quarter of 2020. suspension time to detain. binding or recommended relevant (art. 365, paragraph c) ) of 655 days | as a result of the unpredictable occurrence of new needs, which for reasons of public interest, it became imperative to proceed with the construction of a wall in dry stone masonry, to ensure safe conditions in the existing access to the pinheiro wwtp
2828 | 4194942 | EGA-AR0311 - Contract for the Design and Construction of the Telões WWTP (Amarante) | 45252000-8 | Construction works for sewage treatment plants, purification plants and refuse incineration plants | FALSE | 2017 | 2020 | Portugal | Amarante | Porto | 13 | 47 | 19-01-2018 | 01-04-2020 | 803 | 273 | 425000 | 388900 | 2 | 399853.14 | -10953.14 | 97.2607 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUES - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 1 - lack of availability of private plots; 2 - suspension of work due to lack of electricity and sanitation; 3 - low flow recorded at the beginning of the pre-start-up period, with implications for the formation and maintenance of biomass in the biological reactor
2829 | 4194860 | The object of this contract is the construction of 7.2 km of collectors in PP Corrugated SN8, 172 home extensions, five lift systems including the respective lift pipes in HDPE from the | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | N/A | 26-01-2018 | 15-07-2019 | 535 | 365 | 1447500 | 1037929.93 | 3 | 1037484.93 | 445 | 100.0429 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: A- PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contractual deadlines, the responsibility of the contracting company | contracted works, not performed
2830 | 4194633 | Contract for the renaturalization and recovery of the dune cord on Armona Island – core of Fuseta-Mar | 45262640-9 | Environmental improvement works | FALSE | 2017 | 2020 | Portugal | Olhão | Faro | 8 | 24 | 11-12-2017 | 30-10-2020 | 1054 | 120 | 425000 | 381884.6 | 2 | 378590.99 | 3293.61 | 100.87 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (P) .................................................................. ................................... fp = 50 °/o b) Technical value of the proposal (Q) ......................................... ..................... fa = 50 % b.1) Descriptive memory and justification (Q1) ...................:. ...............fa1 = 20% b.2) Work plan (Q2) .................................................................. .......fçn = 30% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in submitting materials for approval and consequent delay in carrying out the project. | several articles with quantities greater than those that were executed.
2831 | 4190016 | Cleaning and deforestation, earthmoving, reinforced concrete walls, construction of acoustic masonry, various infrastructures, paving and road signs. Creation of supporting structures | 45233120-6 | Road construction works | FALSE | 2017 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 24-01-2018 | 09-05-2019 | 470 | 120 | 314000 | 296320.68 | 2 | 353439.81 | -57119.13 | 83.8391 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (CP) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a work suspension notice was duly authorized. | a provisional price revision in the amount of €5,143.63 was calculated.
2832 | 4188401 | EGA-AR0255 - Execution contract for Mezio interceptors - Prolongation and Aparecida II (Lousada) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Lousada | Porto | 13 | 47 | 11-10-2017 | 08-01-2020 | 819 | 168 | 400000 | 308620.7 | 2 | 308587.84 | 32.86 | 100.0106 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | phased availability of land needed for the project | underwork
2833 | 4183860 | Requalification of the Car Park | 45223300-9 | Parking lot construction work | FALSE | 2016 | 2018 | Portugal | Anadia | Aveiro | 1 | 20 | 23-11-2016 | 10-01-2018 | 413 | 180 | 279972.14 | 261317.72 | 2 | 256538 | 4779.72 | 101.8632 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2834 | 4182673 | Improvement of streetNarciso da Marça - Sangalhos | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Anadia | Aveiro | 1 | 20 | 25-11-2016 | 03-01-2018 | 404 | 180 | 347679.77 | 336952.3 | 2 | 334620.8 | 2331.5 | 100.6968 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the numerous infrastructures and various constraints in the project | no need to perform some works
2835 | 4181099 | 5010017059/DRF-VGN/2018 - Contract for "stabilization of slopes between km 119.540 and km 145.800 (lot 4) of the douro line" | 45111230-9 | Ground-stabilisation work | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 42 | 16-01-2018 | 30-12-2020 | 1079 | 540 | 4000000 | 3550000 | 3 | 3229294.46 | 320705.54 | 109.9311 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price 50% 2. Technical Valuation 30% 3. Safety Management System 10% 4. Quality Management System 5% 5. Environmental Management System 5% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was necessary to grant a graceful extension of 56 days | it was not necessary to carry out all the planned work
2836 | 4178792 | 100% Quality - Urgent Repairs of Bituminous Paving 2015 - Union of Parishes of Perafita, Lavra and Santa Cruz do Bispo - EDOC 2014/78160 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2018 | Portugal | Matosinhos | Porto | 13 | 36 | 12-10-2015 | 16-01-2018 | 827 | 182 | 658490.57 | 395094.34 | 2 | 395094.34 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
2837 | 4146889 | EGA-EB0017 - Wastewater Drainage Network in Cepelos and Water Supply Network in S. Gonçalo, Várzea, Bustelo and Candemil (Amarante) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Amarante | Porto | 13 | 50 | 07-12-2017 | 15-11-2019 | 708 | 240 | 590000 | 535880 | 2 | 486120.75 | 49759.25 | 110.236 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the expropriation of the plot for the corvachã reservoir; delay in the issuance of the license by infraestruturas de portugal for the intervention in crossing the passagem agrícola | underwork resulting from adjustments to the layout and depth of the pipes
2838 | 4146398 | Urban Requalification of street1º de Maio - Plot 2 | 45453100-8 | Refurbishment work | FALSE | 2017 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 19-01-2018 | 25-11-2021 | 1406 | 270 | 332912.31 | 174609.67 | 1 | 175840.64 | -1230.97 | 99.3 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | impediment of work progress due to the need for prior execution of the natural gas network (not foreseen) and weather conditions. | job suppression and price revision.
2839 | 4140990 | Contract for the Partial Rehabilitation of the South Wing of Hospital Pulido Valente for the installation of an Integrated Care Unit (UCCI), located at Alameda Linhas de Torres, n.º 117 | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 11-01-2018 | 13-08-2019 | 579 | 180 | 3100000 | 2721734.11 | 3 | 3063665.99 | -341931.88 | 88.8391 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: in accordance with point 14 of the program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work was carried out, with a direct influence on the planning of the project and its completion date. | the need to do more work and to provide for errors and omissions.
2840 | 4139854 | "Requalification of the north access and south access of the Chança cluster". | 45233161-5 | Footpath construction work | FALSE | 2017 | 2019 | Portugal | Alter do Chão | Portalegre | 12 | 12 | 10-01-2018 | 26-07-2019 | 562 | 365 | 429126.43 | 318402.53 | 2 | 334776.72 | -16374.19 | 95.1089 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | alteration due to the execution of complementary works. | change in the value of the project due to the execution of complementary works.
2841 | 4136995 | EGA-AR0129 - Closing contract for existing sewage networks - SAR Ovelha (Amarante) - Phase 1 | 45232423-3, 45232411-6 | Sewage pumping stations construction work, Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Amarante | Porto | 13 | 20 | 07-12-2017 | 01-04-2019 | 480 | 120 | 242000 | 216880 | 1 | 166281.74 | 50598.26 | 130.4292 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical value of the proposal - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in land expropriation for the implementation of the areias wastewater pumping station | underwork resulting from the elimination of the lomba pumping station
2842 | 4136405 | Requalification of the Road from the Roundabout of Tecnopolo I to the Bridge of Vila Verde da Raia | 45233200-1 | Various surface works | FALSE | 2017 | 2020 | Portugal | Chaves | Vila Real | 19 | 30 | 16-01-2018 | 20-10-2020 | 1008 | 45 | 246000 | 221380 | 1 | 228920.47 | -7540.47 | 96.7061 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | price revision in the amount of €7,540.47
2843 | 4136332 | Prc_0033/2017 – ega-eb0314 - contracts for closing air networks In the parishes of storãos, fornelos and vinhós, fafe (fojo) and moreira de rei – municipality of fafe | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Fafe | Braga | 3 | 12 | 07-12-2017 | 19-11-2019 | 712 | 180 | 1100000 | 879068.73 | 2 | 810892.99 | 68175.74 | 108.4075 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | implementation difficulties on the part of the contractor, namely, in the dismantling of hard rock, which led to reduced income and the provision of private land. | existence of some underwork, by indication of the client, since there was no need to carry out all the contractual works.
2844 | 4136097 | EGA-AR0257 - Execution contract for the Rio Este Pumping System (FD10) - 2nd Phase (Part 1) - Vila do Conde | 45232411-6, 45232423-3 | Foul-water piping construction work, Sewage pumping stations construction work | FALSE | 2017 | 2020 | Portugal | Vila do Conde | Porto | 13 | 47 | 07-12-2017 | 30-11-2020 | 1089 | 280 | 1400000 | 1112898.77 | 3 | 1163526.9 | -50628.13 | 95.6487 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work | objective modification of contract) due to project errors, alteration of the real conditions of the land (bottom levels of the river beds), that is, due to abnormal and unpredictable changes in circumstances.
2845 | 4135509 | Water Supply and Wastewater Drainage Infrastructures in the Southern Area of ​​the Parishes of Rôge, Macieira de Cambra and Lugar de Cavião (S. Pedro de Castelões) | 45232460-4, 45232150-8 | Sanitary works, Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 31-10-2017 | 16-06-2020 | 959 | 320 | 3578297.33 | 2918842.5 | 3 | 2959598.57 | -40756.07 | 98.6229 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2846 | 4133486 | Rehabilitation / expansion of the vialonga eb1 n.º1 | 45214210-5 | Primary school construction work | FALSE | 2017 | 2018 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 15-11-2017 | 27-11-2018 | 377 | 150 | 675000 | 540169.97 | 2 | 546930.68 | -6760.71 | 98.7639 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | approval of price revision in the amount of €6,760.71
2847 | 4128078 | Execution of the emissary of A-do-Baço | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Arruda dos Vinhos | Lisboa | 11 | 48 | 12-12-2017 | 19-04-2019 | 493 | 365 | 710000 | 561778.2 | 2 | 574377.33 | -12599.13 | 97.8065 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A) Price = 70% B) Technical Value = 30% b.1 Work execution methodology = 20% b.2 Detail and consistency of the Work Plan=10% b.2.1. Work Schedule = 5% b.2.2 Means Plan=5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for the purpose of provisional acceptance | ordinary price review (article 382 of the "public procurement code")
2848 | 4120977 | 2017/71 - DGEPIM - Reformulation of streets acadura Cabral in Cruz Quebrada | 45233200-1 | Various surface works | FALSE | 2017 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 22-12-2017 | 22-01-2020 | 761 | 180 | 340865.8 | 274974.91 | 2 | 189810.21 | 85164.7 | 144.8683 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2849 | 4118474 | Requalification of em 593 - santa catarina da serra / quinta do salgueiro - union of parishes of santa catarina da serra and chaínça | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Leiria | Leiria | 10 | 20 | 08-01-2018 | 18-11-2020 | 1045 | 180 | 1019275.71 | 879142.12 | 2 | 879142.12 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work pursuant to paragraph c) of article 365 of the "public procurement code".
2850 | 4116895 | The object of this contract is the construction of a water supply network in an extension of about 4,165 meters and 95 home branches. | 45232100-3 | Ancillary works for water pipelines | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | N/A | 15-12-2017 | 21-03-2019 | 461 | 120 | 242000 | 228464.42 | 1 | 203298.1 | 25166.32 | 112.379 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with deadlines, due to constraints of the public road management entity | contracted works, not performed
2851 | 4116428 | The object of this contract is the construction of a gravity network in an extension of 5,500 meters of wastewater collectors, 166 home extensions, also including the construction of 2 stations | 45232400-6 | Sewer construction work | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | N/A | 13-12-2017 | 26-04-2019 | 499 | 365 | 678000 | 496462.28 | 2 | 463385.89 | 33076.39 | 107.138 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | contracted works, not performed
2852 | 4115574 | Contract for the execution, replacement, maintenance and conservation of sidewalks, curbs and other pavements | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Cascais | Lisboa | 11 | 20 | 10-01-2018 | 12-03-2019 | 426 | 365 | 641100 | 384660.01 | 2 | 176032.98 | 208627.03 | 218.5159 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | there was no need to perform all interventions as initially planned
2853 | 4115005 | Rehabilitation of the Pumping Stations in Vila Nova de Gaia | 45232431-2 | Wastewater pumping station | FALSE | 2017 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | N/A | 27-12-2017 | 15-03-2019 | 443 | 180 | 1900000 | 1898499.87 | 3 | 1696788.03 | 201711.84 | 111.8879 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 50%; b) Technical Valuation - 50%, of which: b1) Work execution methodology - 25%; b2) Work plan detail and consistency - 15%, b2.1) Work schedule - 10%, b2.2) Means plan 5%; b3) - Characterization of equipment and materials - 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the bathing season, no work was authorized | suppression of work in the washers ee
2854 | 4112037 | Urban Requalification of the Casal dos Matos Road, Pousos, Union of the Parishes of Leiria, Pousos, Barreira and Cortes | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 10-01-2018 | 21-03-2019 | 435 | 180 | 372427.76 | 316300 | 2 | 315465 | 835 | 100.2647 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | execution of works
2855 | 4108268 | Improvement of the Granja - Santa Marinha road. Execution of pavements, rainwater wastewater network and water supply network. | 45432100-5 | Floor laying and covering work | FALSE | 2017 | 2018 | Portugal | Monção | Viana do Castelo | 18 | N/A | 15-12-2017 | 19-11-2018 | 339 | 270 | 261000 | 255392.96 | 2 | 254752.94 | 640.02 | 100.2512 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | since the months of july and august are the most complicated in terms of traffic due to emigration, there was a change to the project plan so that the paving was carried out in june so that there were no constraints on traffic. | during the course of the contract there were works that were foreseen but that there was no need to carry them out.
2856 | 4107105 | 5010030199 - En14 - Santana improvement / victory and victory duplication / roundabout of the Famalicão variant | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2017 | 2021 | Portugal | Braga | Braga | 3 | 45 | 20-12-2017 | 10-05-2021 | 1237 | 330 | 4000000 | 2998997.93 | 3 | 3209930.92 | -210932.99 | 93.4287 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this contract was launched within the scope of the business areas enhancement program (pvae) under the management agreement signed between ip and vila nova de famalicão city council on 24 july 2017, with the aim of improving accessibility to the business location areas of famalicão sul (ribeirão and lousado). after awarding the contract, the municipality of famalicão decided to proceed with the construction of a new connection, of a municipal nature, to the business location area of ​​lousado, the nascente, whose insertion in the en14 is made at km 21+880. in this context, the owner opted to include the construction of a roundabout in the contract to ensure this connection, resulting in the need to extend the deadline by 30 days. since this is a work in an urban environment with significant marginal occupation with housing, commerce, services and industry, the projects to widen the road platform had to be compatible with the accesses to neighboring properties. the urban character was also manifested in the appearance of different unregistered infrastructures with subsequent interventions carried out by external entities, which disturbed the normal development of the projects. considering these factors and the proactivity shown by the contractor in its resolution, a 60-day extension of the deadline was granted (30 legal and 30 free of charge) | the value of the project was essentially changed by the incorporation of the roundabout at km 21+880 and by the restoration of the financial balance motivated by the legal extension of the term granted.
2857 | 4105440 | Rehabilitation of Blocks 5 to 9, 11 and 12 in the Municipal Public Housing Complex of Mouteira | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 03-01-2018 | 21-12-2018 | 352 | 240 | 850000 | 800000 | 2 | 797620.96 | 2379.04 | 100.2983 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | eo in the amount of €3,793.56 and work not carried out in the amount of €6,172.60
2858 | 4102875 | EMP-R/1/2017 - Contract for Removal of Fiber Cement from Blocks III and V - Bairro da Nazaré | 45261213-0 | Metal roof-covering work | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 20 | 08-11-2017 | 13-02-2019 | 462 | 210 | 630000 | 504000.01 | 2 | 504000.01 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project were carried out within the deadline
2859 | 4090486 | Water and sanitation network in Vale de Águia | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 28-12-2017 | 18-05-2020 | 872 | 365 | 436612 | 332000 | 2 | 295333.95 | 36666.05 | 112.4151 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unfavorable weather conditions | works less
2860 | 4089399 | Supply of port equipment and its installation on the various piers of the fishing port of Figueira da Foz. | 34931000-2 | Harbour equipment | FALSE | 2017 | 2019 | Portugal | Figueira da Foz | Coimbra | 6 | N/A | 20-12-2017 | 03-06-2019 | 530 | 98 | 230000 | 224899.04 | 1 | 229448.75 | -4549.71 | 98.0171 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Final Evaluation of the Proposal = 0.5Price+0.2Deadline+0.5Technical Quality of Proposal | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional 10 days | additional 10 days
2861 | 4078906 | Construction of the production center and building of the terra de miranda mycological ecocenter | 45211350-7 | Multi-functional buildings construction work | FALSE | 2017 | 2019 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 27-12-2017 | 15-02-2019 | 415 | 180 | 247862.39 | 239792.73 | 1 | 240428.34 | -635.61 | 99.7356 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climatic conditions | price review worth €635.61
2862 | 4078474 | E.M. 530-2 - Olalhas, paving street of Picoto and upgrading the main road in Vale do Pereiro | 45233140-2 | Roadworks | FALSE | 2017 | 2019 | Portugal | Tomar | Santarém | 16 | 30 | 06-12-2017 | 15-07-2019 | 586 | 180 | 348000 | 322978.32 | 2 | 344825.49 | -21847.17 | 93.6643 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline suspended. | price review
2863 | 4078465 | Contract for the Restoration of Primary Schools in the Centennial Plan for Tourist Purposes | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2019 | Portugal | Arouca | Aveiro | 1 | 30 | 03-01-2018 | 29-11-2019 | 695 | 270 | 191199.51 | 172218.68 | 1 | 161133.17 | 11085.51 | 106.8797 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | more works; errors and omissions; price review; underwork
2864 | 4078164 | 17EP00002844 - Contract for the Installation of an Air Conditioning System in the Palace of Justice in Portimão | 45350000-5 | Mechanical installations | FALSE | 2017 | 2018 | Portugal | Portimão | Faro | 8 | N/A | 15-12-2017 | 27-06-2018 | 194 | 90 | 315000 | 228609.46 | 1 | 227324.96 | 1284.5 | 100.5651 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work to be carried out outside normal working hours so as not to interfere with audiences | underwork
2865 | 4077189 | Contract for the Introduction of Soft Modes on street Egas Moniz | 45233140-2 | Roadworks | FALSE | 2017 | 2019 | Portugal | Arouca | Aveiro | 1 | 30 | 27-12-2017 | 29-03-2019 | 457 | 180 | 352182.62 | 294471.68 | 2 | 282096.14 | 12375.54 | 104.387 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays imputed to the contractor. | existence of deleted works.
2866 | 4076861 | Requalification limited to the interior spaces dedicated to the school collective, and of two classroom modules | 45430000-0 | Floor and wall covering work | FALSE | 2017 | 2020 | Portugal | Marinha Grande | Leiria | 10 | 20 | 28-11-2017 | 20-04-2020 | 874 | 150 | 412500 | 408833.2 | 2 | 436581.88 | -27748.68 | 93.6441 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for reasons attributable to the owner of the project | for effects of additional works, price revision and suppression of works
2867 | 4076784 | Building rehabilitation at street of Reboleira n.º 42 (EM.004.2017.165) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 20 | 11-12-2017 | 05-08-2019 | 602 | 270 | 250000 | 218000 | 1 | 218000 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspension | additional work worth €4,092.60, unfinished work worth €1,795.94 and eo worth €7,496.62
2868 | 4066566 | Technical Connection Contract for Water Supply and Wastewater in Guarda - Phase I | 45232460-4, 45232150-8 | Sanitary works, Works related to water-distribution pipelines | FALSE | 2017 | 2021 | Portugal | Guarda | Guarda | 9 | 48 | 15-11-2017 | 13-10-2021 | 1428 | 450 | 1399000 | 933000 | 2 | 952950.6 | -19950.6 | 97.9064 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A. Price: 70% B. Technical Valuation: 30% b.1 Work execution methodology: 20% b.2 Detail and Consistency of the Work Plan: 10% b.2.1 Work Schedule: 5% b.2.2. Means Plan: 5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the contract period of 60 days associated with work to correct errors and omissions. | change associated with underwork, supply of errors and omissions, as well as the price revision carried out.
2869 | 4064559 | Execution contract for the Nespereira 2 Pumping System and the Gouveia ZI Outfall | 45232460-4 | Sanitary works | FALSE | 2016 | 2019 | Portugal | Gouveia | Guarda | 9 | 50 | 09-11-2017 | 27-11-2019 | 748 | 180 | 220000 | 171061.26 | 1 | 151183.46 | 19877.8 | 113.1481 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: FACTORS AND SUBFACTORS COEFFICIENT WEIGHTING A. PRICE 50% B. TECHNICAL EVALUATION 50% B.1 Work execution methodology 25% B.2 Detail and consistency of the Work Plan 15% B.2.1 Work Schedule 10% B.2.2 Means Plan 5% B.3 Characterization and quality of equipment and materials 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | provisional acceptance of the project only took place after delivery of all the necessary documentation by the successful tenderer, namely, final screens, technical compilation and "plan for the prevention and management of construction and demolition waste". | changes in the value of the project result from underwork and the price revision carried out.
2870 | 4060730 | Contract for the Rehabilitation of DN 1250 MM Raw Water and Treated Water Pipelines in the Vale da Pedra Subsystem | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2021 | Portugal | Cartaxo | Santarém | 16 | 60 | 29-07-2015 | 17-03-2021 | 2058 | 330 | 990000 | 747226.94 | 2 | 849054.86 | -101827.92 | 88.0069 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were two graceful extensions of the deadline (the first of 120 days and the second of 75 days) due to the existence of Extra work, underwork and work to supply errors and omissions. | changes in the value of the project result from the existence of more work, underwork, work to supply errors and omissions, as well as the price revision carried out. several inspections took place for the purposes of provisional acceptance of the project, namely on 03/03/2017, 06/01/2017 and 08/30/2018, where defects in the project were detected, in which a period of 90 days was given, in every occasion, to correct them. only on 11/28/2017 was the 4th inspection notice effectively accepted and signed for the purposes of provisional acceptance.
2871 | 4059829 | 2014.082.01.C1 - SFP ÁGUEDA - Construction of warehouse and remodeling of training rooms | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | 21 | 26-10-2017 | 18-11-2019 | 753 | 120 | 348500 | 277800 | 2 | 277800 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no data
2872 | 4058910 | CP06/2017/GIE - Construction contract for the Alfena Health Unit_x000D_ | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2019 | Portugal | Valongo | Porto | 13 | 30 | 27-12-2017 | 28-06-2019 | 548 | 300 | 975305.65 | 805000 | 2 | 795207.85 | 9792.15 | 101.2314 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70% B - Technical value of the proposal 30%: B1 - Descriptive memory 10% B2 - Work, labor, equipment and payment plans 10% B3 - Safety to be implemented in the work (technical note) 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions | price review
2873 | 4057771 | Public Works Contract for the Rehabilitation and Planning of Car Parks in the Parque das Nações Precinct and Materials Park in the Camarate Precinct | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 30 | 22-11-2017 | 01-08-2018 | 252 | 90 | 350000 | 267973.12 | 2 | 240007.03 | 27966.09 | 111.6522 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | slight delay in delivery of covers for nr1 and nr2 floor boxes, class d400 | underwork.
2874 | 4055793 | Public Works Contract for "Requalification of Buildings in Vila Franca de Xira" | 45220000-5 | Engineering works and construction works | FALSE | 2016 | 2018 | Portugal | Vila Franca de Xira | Lisboa | 11 | 60 | 08-09-2017 | 26-09-2018 | 383 | 180 | 500000 | 412432.15 | 2 | 397010.48 | 15421.67 | 103.8844 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: See Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | outdoor work conditioned by weather conditions, delays in some supplies of equipment and materials. | deletion of some works
2875 | 4051097 | Year 2017_​Contract for the Conservation and Improvement of Chapels, Tombs and Graves owned by SCML in the 1st and 2nd cemeteries of Lisbon, Alhandra, Benfica, Cascais, Monte Caparica | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 30 | 15-12-2017 | 13-12-2019 | 728 | 285 | 300000 | 249500 | 1 | 251780.78 | -2280.78 | 99.0941 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were delays in obtaining the necessary permits to carry out work on one of the cemeteries. | there was the execution of more work in the amount of € 3,284.06, as well as underwork in the amount of € 1,003.28.
2876 | 4048671 | Construction of the Vale da Fontinha Car Park in Abrantes | 45223300-9 | Parking lot construction work | FALSE | 2017 | 2020 | Portugal | Abrantes | Santarém | 16 | 36 | 20-12-2017 | 04-08-2020 | 958 | 540 | 1254363.52 | 944450.97 | 2 | 1002369.28 | -57918.31 | 94.2219 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork and the ordinary revision of prices were considered
2877 | 4044876 | Public Works Contract for the Recovery of the Interior Section (over the Alcântara Valley) of the Águas Livres Aqueduct | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Lisboa | Lisboa | 11 | 50 | 17-11-2017 | 25-11-2020 | 1104 | 180 | 245000 | 193838.21 | 1 | 225014.25 | -31176.04 | 86.1449 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a graceful extension of the deadline by 80 days, requested by the contractor, moving the end date of the contract to september 2018. from the windows. after the deadline granted to the contractor to correct the anomalies, it was found that there were still anomalies to be corrected in terms of the doors. a long period passed during which the contractor was successively and insistently summoned to correct the anomalies that persisted. subsequently, these were corrected, for which reason an inspection was carried out at the project site and a provisional acceptance notice of the project was drawn up. | in view of the initially contracted price (€193,838.21), an additional contract was signed (1480-b) worth €31,176.04, with the contractual value being changed to €225,014.25
2878 | 4044613 | Construction of the Vilar Seco WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | Nelas | Viseu | 20 | 22 | 18-12-2017 | 01-05-2020 | 865 | 365 | 355000 | 317703.4 | 2 | 374228.83 | -56525.43 | 84.8955 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | more work, underwork and price revisions
2879 | 4043602 | Repair of infrastructure on several roads, in the municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 14-12-2017 | 21-06-2018 | 189 | 120 | 181900 | 177474.25 | 1 | 176278.28 | 1195.97 | 100.6785 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline changes
2880 | 4042844 | Work of "Funchalinho Emissary" | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Almada | Setúbal | 17 | N/A | 13-12-2017 | 20-01-2020 | 768 | 60 | 326000 | 308746.28 | 2 | 348150.69 | -39404.41 | 88.6818 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to point 23 of the procedures | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract had several suspensions of work motivated by the need to guarantee authorizations to cross private land and for authorization from the aebt and also due to project adjustments. | need to adapt the project to local conditions, perform a price review and financial rebalancing.
2881 | 4041164 | Urban rehabilitation of the central area of ​​Lourosa | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 19-12-2017 | 08-04-2020 | 841 | 60 | 233081 | 178195 | 1 | 171852.76 | 6342.24 | 103.6905 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 430 days due to more unforeseen work and the need to study the necessary changes, 213 days due to delay by the contractor in the subsequent completion of the project | over and underwork
2882 | 4041147 | Paving with bituminous mixture and infrastructures, in several streets of the municipality. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 19-12-2017 | 17-09-2020 | 1003 | 60 | 394024 | 289295.49 | 2 | 279617.75 | 9677.74 | 103.4611 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 679 days for breach of contract by the contractor and 129 days for correction of physical and documental defects | underwork
2883 | 4038466 | The object of the contract is the requalification of street of Igreja in São Paio de Oleiros | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 15-12-2017 | 28-05-2021 | 1260 | 120 | 472843.34 | 457660 | 2 | 400264.75 | 57395.25 | 114.3393 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 531 days of delay for the contractor's responsibility in completing small final works and 448 days to complete correction of deficiencies for the purposes of provisional acceptance | less and more work
2884 | 4038365 | Construction of ecopathway - extension from the tracks parallel to the mandim metro station | 45233161-5 | Footpath construction work | FALSE | 2017 | 2019 | Portugal | Maia | Porto | 13 | 23 | 14-12-2017 | 25-02-2019 | 438 | 300 | 837689 | 698353.43 | 2 | 675349.13 | 23004.3 | 103.4063 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the date of the provisional acceptance was set by mutual agreement, following the request of the winning company. | the final realized value of the contract resulted from the quantities measured on site.
2885 | 4016201 | Construction / Improvement and Repair of the Marquês de Marialva de Cantanhede Primary School, by Contract - CP-CCP-EMP n.º 03/2017 | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2017 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 20 | 19-12-2017 | 01-10-2021 | 1382 | 270 | 990560 | 894000.03 | 2 | 892537.26 | 1462.77 | 100.1639 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of works. | existence of additional work and underwork.
2886 | 3990537 | Rehabilitation of the olive industrial zone (zone II) | 45210000-2 | Building construction work | FALSE | 2017 | 2018 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 13-12-2017 | 04-10-2018 | 295 | 120 | 375000 | 324240 | 2 | 339759.94 | -15519.94 | 95.4321 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 70% Technical value of the proposal 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes introduced to the project | project changes
2887 | 3990371 | The object of this contract is the execution of the sanitation network in the parish of Cabanelas | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Vila Verde | Braga | 3 | 30 | 14-12-2017 | 09-08-2019 | 603 | 365 | 921642.58 | 737314.07 | 2 | 709113.75 | 28200.32 | 103.9768 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical value of the proposal - 30% [considering: Descriptive memory and justification of the mode of execution of the contract (50%) and the Work Program (50%) (as better explained in point 17 of the Tender Program)] | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2888 | 3984255 | The object of this contract consists of carrying out the work defined, in terms of its type, quantity and technical conditions of execution, in the project and in the Specifications and comprises | 45213112-1 | Shop units construction work | FALSE | 2017 | 2018 | Portugal | Amadora | Lisboa | 11 | N/A | 04-12-2017 | 05-11-2018 | 336 | 365 | 329726.27 | 263800 | 2 | 263800 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | early receipt of the project
2889 | 3980609 | Construction of a transport interface - road interface of vimioso | 45213311-6 | Bus station construction work | FALSE | 2017 | 2020 | Portugal | Vimioso | Bragança | 4 | 24 | 07-12-2017 | 25-10-2020 | 1053 | 180 | 349200 | 317002.98 | 2 | 315679.94 | 1323.04 | 100.4191 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | free extensions | articles 4.11, 4.15.10 and 7.3 have not been implemented because they are not justified
2890 | 3976788 | The object of this contract is the execution of the sanitation network in the parish of Turiz | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Vila Verde | Braga | 3 | 30 | 07-12-2017 | 02-04-2019 | 481 | 365 | 808496.54 | 646797.24 | 2 | 646787.34 | 9.9 | 100.0015 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical Valuation - 30% [considering: Descriptive memory and justification of the mode of execution of the contract (50%) and the Program of Jobs (50%)] (as better explained in point 17 of the Tender Program) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2891 | 3976654 | The object of this contract is the execution of the sanitation network in the parish of Cervães | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Vila Verde | Braga | 3 | 30 | 07-12-2017 | 11-12-2019 | 734 | 365 | 873653.46 | 664000 | 2 | 660551.24 | 3448.76 | 100.5221 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical Valuation - 30% [considering: Descriptive memory and justification of the mode of execution of the contract (50%) and the Program of Jobs (50%)] (as better explained in point 17 of the Tender Program) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
2892 | 3976438 | Torrão WWTP Refurbishment Contract | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2019 | Portugal | Guarda | Guarda | 9 | 30 | 09-11-2017 | 27-11-2019 | 748 | 540 | 1500000 | 1269780.03 | 3 | 1300981.17 | -31201.14 | 97.6017 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of 60 days for the execution of additional works. | changes in the value of the project resulting from more, underwork and the price review carried out.
2893 | 3975639 | SAMBADE AA SUBSYSTEM, ALFÂNDEGA DA FÉ MUNICIPALITY (2016) – Supply to the southern area of ​​the municipality (Gouveia, Cabreira, Picões and Vilarelhos) | 45231110-9 | Pipelaying construction work | FALSE | 2017 | 2018 | Portugal | Alfandega da Fé | Bragança | 4 | N/A | 27-09-2017 | 09-11-2018 | 408 | 365 | 655693.24 | 598751.3 | 2 | 598751.16 | 0.14 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | nothing to register
2894 | 3971959 | Public tender for the contract for the remodeling of wastewater networks in the municipality of Amadora, for the years 2017 and 2018 | 45232410-9 | Sewerage work | FALSE | 2017 | 2020 | Portugal | Amadora | Lisboa | 11 | N/A | 30-11-2017 | 17-03-2020 | 838 | 365 | 368737 | 278067.85 | 2 | 278067.85 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to clause 28 of the procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline ended 1 day before.
2895 | 3970311 | Extension of street25 de Abril, Lomar - 1st phase | 45233140-2 | Roadworks | FALSE | 2017 | 2018 | Portugal | Braga | Braga | 3 | 30 | 04-12-2017 | 20-06-2018 | 198 | 120 | 239930.03 | 207008.49 | 1 | 200430.36 | 6578.13 | 103.282 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed on 05/29/2018. | underwork
2896 | 3970254 | The contract comprises the construction of networks of domestic wastewater drainage collectors and repaving, in Penalva in the parish of St.º António da Charneca | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Barreiro | Setúbal | 17 | 20 | 17-11-2017 | 19-02-2020 | 824 | 240 | 867000 | 725251.67 | 2 | 813888.07 | -88636.4 | 89.1095 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in opening trenches due to other existing infrastructure/existence of water table | more works detected during the project
2897 | 3968228 | Rehabilitation of the old barn building in Vila do Bispo - Public equipment for cultural action - EPAC "O Celeiro da História" according to the specifications described in the Tender Program | 45210000-2 | Building construction work | FALSE | 2017 | 2020 | Portugal | Vila do Bispo | Faro | 8 | 21 | 29-11-2017 | 18-02-2020 | 811 | 365 | 1404505.59 | 1326903.05 | 3 | 186589.51 | 1140313.54 | 711.1349 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract termination | contract termination
2898 | 3968041 | Expansion contract for Pousada Castelo de Óbidos - Estalagem do Lidador Annex, Óbidos | 45212400-0 | Accommodation and restaurant buildings | FALSE | 2017 | 2020 | Portugal | Óbidos | Leiria | 10 | N/A | 20-11-2017 | 31-07-2020 | 984 | 270 | 700000 | 548500 | 2 | 535036.41 | 13463.59 | 102.5164 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay in the execution period was due to the licensing process and the enormous difficulties faced by the contractor to ensure the means of production necessary to comply with the project schedule; supply of materials and, mainly, to specialized labor. | replacement of some of the initially planned elements, either for reasons of adequacy to the existing spaces or for aesthetic and durability reasons.
2899 | 3967289 | The object of the contract is the execution of the sanitation network in the parish of Loureira | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Vila Verde | Braga | 3 | 30 | 06-12-2017 | 11-01-2019 | 401 | 365 | 363014.5 | 290411.61 | 2 | 277355.32 | 13056.29 | 104.7074 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical value of the proposal - 30% [considering: Descriptive memory and justification of the mode of execution of the contract (50%) and the Work Program (50%)] (as better explained in point 17 of the Tender Program) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2900 | 3961670 | Installation of fenders at the Fisherman's Dock Protection Jetty, in the Port of Setúbal | 45243500-7 | Sea defences construction work | FALSE | 2017 | 2018 | Portugal | Setúbal | Setúbal | 17 | 20 | 24-10-2017 | 10-07-2018 | 259 | 120 | 250000 | 187500.01 | 1 | 187500.01 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Factor A - Price 50%; b) Factor B - Delivery and installation time 20%; c) Factor C - Warranty period 15%. d) Factor D - Technical Quality and Work Methodology 15% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2901 | 3960449 | Paintings on the Pavement and Paving in the Expansion Area Downstream of the Ro-Ro Terminal – Coelho da Mota, in the Port of Setúbal | 45213342-2 | Ro-Ro terminal construction work | FALSE | 2017 | 2018 | Portugal | Setúbal | Setúbal | 17 | 20 | 04-10-2017 | 15-03-2018 | 162 | 120 | 200000 | 173627.62 | 1 | 173627.62 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor A - Price, 55% Factor B - Technical Quality and Work Methodology, 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2902 | 3959240 | EGA-AA0327 - Contract to change the Sordo Water Supply System. Interventions in the Ribeira d'Elos and Fontes Reservoirs (Municipality of Santa Marta de Penaguião) | 45232152-2 | Pumping station construction work | FALSE | 2017 | 2021 | Portugal | Sta Marta de Penaguião | Vila Real | 19 | 20 | 08-11-2017 | 01-02-2021 | 1181 | 90 | 450000 | 439998.21 | 2 | 460142.74 | -20144.53 | 95.6221 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the project; exploitation constraints for interruption of water supply; delay in the supply of energy to the transformer station. fall of trees in the enclosure of the ribeira d´elos reservoir. | errors and omissions work resulting from the alteration of the automation system; more works resulting from the alteration of the protection system against hydraulic shock
2903 | 3959216 | Requalification of streetDuque D'Ávila e Bolama and creation of a multifunctional space in Vila Pouca de Aguiar | 45211350-7 | Multi-functional buildings construction work | FALSE | 2017 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 24 | 02-11-2017 | 21-01-2021 | 1176 | 360 | 285582.29 | 271200 | 2 | 299834.34 | -28634.34 | 90.4499 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions and delay in the delivery of materials by suppliers. | revision of prices, over and underwork.
2904 | 3956782 | Requalification of the outdoor playgrounds of several elementary schools | 45453100-8 | Refurbishment work | FALSE | 2017 | 2018 | Portugal | Braga | Braga | 3 | 30 | 27-11-2017 | 11-10-2018 | 318 | 60 | 281686 | 272562.33 | 2 | 215839.64 | 56722.69 | 126.28 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork and compensation paid
2905 | 3956330 | Rehabilitation of Quinta do Espírito Santo, in Odivelas | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2016 | 2021 | Portugal | Odivelas | Lisboa | 11 | 20 | 29-11-2017 | 05-02-2021 | 1164 | 270 | 840000 | 803543.57 | 2 | 810215.17 | -6671.6 | 99.1766 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: In accordance with point 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work subject to 4 deadline extension, due to more work, delays in the supply of requested materials, difficulties in the execution of ceilings on floors 0 and 1, execution of underground crossing for ited infrastructure and reconstruction of elements due to flooding | performing over and underwork
2906 | 3955910 | Landscape Enhancement of the Dolmen at Sítio das Pedras Grandes | 45112700-2 | Landscaping work | FALSE | 2016 | 2019 | Portugal | Odivelas | Lisboa | 11 | 20 | 28-11-2017 | 21-03-2019 | 478 | 120 | 257851.72 | 247885.79 | 1 | 306856.81 | -58971.02 | 80.7822 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Item 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were changes in the execution period of the project. reason: weather conditions and archeology. | there was Extra work, errors and omissions and underwork
2907 | 3952366 | Rehabilitation of Mealhada High school | 45214220-8 | Secondary school construction work | FALSE | 2017 | 2019 | Portugal | Mealhada | Aveiro | 1 | 30 | 21-11-2017 | 22-07-2019 | 608 | 180 | 772500 | 570364.94 | 2 | 110777.68 | 459587.26 | 514.8735 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the execution period due to the execution of additional work and work to correct errors and omissions. | the change in the value of the project resulted from the existence of work to supply errors and omissions, underwork, more work and price revisions.
2908 | 3944676 | The object of this contract is the execution of the contract referring to the "Extension of the Sanitation Network of the Subsystem of Veiros - Estremoz". The intervention is due to the fact that the existing network does not provide coverage | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Estremoz | Évora | 7 | 20 | 06-11-2017 | 17-01-2020 | 802 | 240 | 502142.8 | 301285.68 | 2 | 301285.68 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price = 50% Sub factors: | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2909 | 3934880 | Public drainage and wastewater treatment in Vila Franca da Serra | 45222100-0 | Waste-treatment plant construction work | FALSE | 2016 | 2020 | Portugal | Gouveia | Guarda | 9 | N/A | 25-04-2017 | 26-03-2020 | 1066 | 210 | 321903.75 | 293671.56 | 2 | 352869.69 | -59198.13 | 83.2238 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | approval of the supply of errors and omissions and competent authorization of the infrastructures of portugal | supply of errors and omissions
2910 | 3933824 | Bike path - Phase 1 - Works related to the change of ownership | 45223000-6 | Structures construction work | FALSE | 2017 | 2018 | Portugal | Guimarães | Braga | 3 | 9 | 20-11-2017 | 03-07-2018 | 225 | 90 | 192496.89 | 186084.81 | 1 | 183834.81 | 2250 | 101.2239 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | following the inspection notice for provisional acceptance (12/03/2018), the contractor had to correct defects in the project, so he was granted a period of 60 days. | existence of underwork due to the foreseen quantities not being used up.
2911 | 3930471 | 5010030949 - En3 - km 57+490 to km 58+750 - walks on legs | 45233140-2 | Roadworks | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 30 | 17-11-2017 | 29-07-2020 | 985 | 90 | 256500 | 236858.48 | 1 | 258096.99 | -21238.51 | 91.7711 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need to carry out unforeseen work not contemplated in the contract, namely the execution of a collector in the ditch and adjacent paving, as well as work resulting from the relocation of the sidewalk to be carried out around km 58+145, for reasons of road safety. | alteration of drainage, lining of sidewalks with concrete slabs in the continuity of sidewalks covered in glass sidewalk, and adjustments in the amount of paving
2912 | 3926677 | Construction of new school building | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2021 | Portugal | Odemira | Beja | 2 | 45 | 07-11-2017 | 20-07-2021 | 1351 | 270 | 1676160.46 | 1666311.34 | 3 | 1663614.19 | 2697.15 | 100.1621 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The criterion on which the award is based is the the most economically advantageous proposal, taking into account the Price factor; a) In case of a tie, the proposals will be evaluated taking into account the following factors, with the indicated weighting: a.1) Descriptive memory and justification...................................0 to 50 Points a.2) Work plan ............................................. ................0 to 50 Points The award being made to the proposal that adds the most points according to the subfactors of analysis contained in the Program of the contest. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of unforeseen complementary work in the execution of the contract, requests for extension of deadlines made by the successful tenderer based on various exhibitions made where extensions were granted on a free basis, as well as delays in the responses made during the course of the project to the team of designers, within the scope of doubts that arose.
2913 | 3921293 | Refurbishment of Machico elementary and High school - Work under guarantee | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Machico | Região Autónoma da Madeira | 14 | 21 | 21-11-2017 | 05-04-2019 | 500 | 180 | 249000 | 223172.42 | 1 | 220384.04 | 2788.38 | 101.2652 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | underwork
2914 | 3920332 | Geão Urban Park - Santo Tirso | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2021 | Portugal | Santo Tirso | Porto | 13 | 20 | 06-11-2017 | 29-11-2021 | 1484 | 365 | 1997541.48 | 1842997.62 | 3 | 1726794.94 | 116202.68 | 106.7294 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: - A - Price - with a weighting of 60% in the overall assessment; - B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: - B1 - Work Schedule - with a weighting of 25% in the overall classification; - B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; - B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the existence of more works, originating study and design of the same and not contemplated in the initial project. | more work and underwork.
2915 | 3919456 | Contract for the Protection, Rehabilitation and Reinforcement of the Dune Cord between Camarido and Moledo | 45243000-2 | Coastal-defence works | FALSE | 2016 | 2019 | Portugal | Caminha | Viana do Castelo | 18 | 30 | 17-10-2017 | 25-02-2019 | 496 | 150 | 366000 | 293850 | 2 | 297924.17 | -4074.17 | 98.6325 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2916 | 3915074 | Connecting road from Vilarinho cemetery to Paradela - 2nd Phase | 45233120-6 | Road construction works | FALSE | 2017 | 2021 | Portugal | N/A | N/A | N/A | 20 | 06-11-2017 | 09-02-2021 | 1191 | 150 | 636021.21 | 547121.37 | 2 | 639968.76 | -92847.39 | 85.4919 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: A - Price - with a weighting of 60% in the overall evaluation; B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: B1 - Work Schedule - with a weighting of 25% in the overall classification; B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the project, adverse weather conditions, execution of other works by other external entities at the project site. | the execution of complementary works and the non-execution of other projected works.
2917 | 3914579 | Expansion and requalification of the elementary school of quinta - fajozes | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2019 | Portugal | Vila do Conde | Porto | 13 | 22 | 06-11-2017 | 30-09-2019 | 693 | 360 | 695000 | 643494.68 | 2 | 672008.56 | -28513.88 | 95.7569 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: PRICE 60%; TECHNICAL QUALITY OF PROPOSAL 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2918 | 3912698 | S.e.c. - Proc no. 69/A1/17 - Public Tender for the award of the contract for "Construction of Buildings E3 - Restaurants and Beverages and E7B - Sports Support Equipment - North Beach" | 45210000-2 | Building construction work | FALSE | 2017 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 17-11-2017 | 30-11-2020 | 1109 | 240 | 1200000 | 1111578.4 | 3 | 1109181.29 | 2397.11 | 100.2161 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value of the Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | covid-19 measures | works not performed.
2919 | 3909859 | Elevated walkway at Monte Gordo beach | 45246510-1 | Boardwalk construction work | FALSE | 2016 | 2019 | Portugal | Vila Real Sto Antonio | Faro | 8 | 20 | 14-02-2017 | 04-02-2019 | 720 | 60 | 1155137.12 | 782527.06 | 2 | 778148.18 | 4378.88 | 100.5627 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | works
2920 | 3903624 | Requalification works of the Leiria Municipal Swimming Pool Complex | 45261900-3 | Roof repair and maintenance work | FALSE | 2017 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 15-11-2017 | 02-01-2019 | 413 | 395 | 297186.83 | 287398.03 | 2 | 272167.57 | 15230.46 | 105.596 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes | underwork worth €15,230.46
2921 | 3900370 | Rehabilitation of public space in the historic center - 2nd Phase - streetde São Bento and surrounding areas | 45233200-1 | Various surface works | FALSE | 2017 | 2020 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 10-11-2017 | 10-07-2020 | 973 | 240 | 524750 | 501102.34 | 2 | 510781.22 | -9678.88 | 98.1051 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
2922 | 3892082 | Rehabilitation of the Gomes Eanes de Azurara School and Pavilion | 45454000-4 | Restructuring work | FALSE | 2016 | 2019 | Portugal | Mangualde | Viseu | 20 | 25 | 15-11-2017 | 18-07-2019 | 610 | 180 | 306908.19 | 276217.38 | 2 | 282539.53 | -6322.15 | 97.7624 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | book of work | price revisions
2923 | 3881195 | Contract work for the São Martinho do Porto system - Alfeizerao sub-system - Vale Maceira sewage and water supply network | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Alcobaça | Leiria | 10 | N/A | 10-11-2017 | 04-11-2019 | 724 | 365 | 1030922.66 | 824738.14 | 2 | 824738.14 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions
2924 | 3873844 | Repair and Refurbishment of Municipal Swimming Pools - Caranguejeira Municipal Swimming Pool (Lot 1) and Maceira Municipal Swimming Pool (Lot 2) | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 10-11-2017 | 20-07-2018 | 252 | 90 | 369523 | 189017.3 | 1 | 189017.3 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline change | there was no change
2925 | 3871919 | Cavalinha Multisports Recovery | 45236119-7 | Repair work on sports fields | FALSE | 2017 | 2018 | Portugal | Olhão | Faro | 8 | 20 | 21-09-2017 | 29-08-2018 | 342 | 90 | 170000 | 167617.35 | 1 | 167617.35 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions were granted due to the lack of weather conditions for carrying out the project
2926 | 3869157 | 5010030222/Drf-coms/2017 - contract called "new sales line - replacement of rnp fixings for nabla type fixings and defective rails - 2nd and 3rd phases" | 45234100-7 | Railway construction works | FALSE | 2017 | 2019 | Portugal | Salvaterra de Magos | Santarém | 16 | 25 | 27-10-2017 | 09-09-2019 | 682 | 150 | 660051.6 | 556443.51 | 2 | 596195.9 | -39752.39 | 93.3323 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2927 | 3868816 | PRC_0144/2017 - EGA-EB0303 - Contract to close sewage networks in Campelo, Gôve, Sta. Cruz do Douro, Loivos da Ribeira and Tresouras (Baião) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Baião | Porto | 13 | 12 | 25-10-2017 | 26-06-2020 | 975 | 105 | 249500 | 212685.9 | 1 | 202098.16 | 10587.74 | 105.2389 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the execution of the power branch to the campelo pumping station by an entity external to the project, namely edp; delay in the dup process for a plot of land in tresouras and there were also delays in the execution of works under the responsibility of the contractor | due to the optimization of the route, there was no need to carry out all the contractual works, which meant underwork.
2928 | 3868740 | Rehabilitation of the "envelope" of Blocks 1 to 6 and 8 to 9 of the Bom Pastor Municipal Public Housing complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 40 | 07-11-2017 | 06-11-2019 | 729 | 510 | 4350000 | 4199008.71 | 3 | 4128709.73 | 70298.98 | 101.7027 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | TRUE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | work not carried out in the amount of €138,029.21 and eo in the amount of €67,730.23
2929 | 3867100 | EGA-AR0302 - Contract for the Execution of Interceptor Systems for the Plate and Screens (Amarante) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Amarante | Porto | 13 | 47 | 25-10-2017 | 20-10-2019 | 725 | 252 | 990000 | 885753.45 | 2 | 876574.84 | 9178.61 | 101.0471 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in freeing parcels, especially in the plate gravity interceptor, with notable impacts on the project deadline. | nothing to point out, except for less quantities resulting from adjustments to the interceptor route, consequences of negotiations with the clients of the plots.
2930 | 3866740 | Requalification of Rainwater Discharge - Vale Faro Water Line | 45232454-9 | Rain-water basin construction work | FALSE | 2017 | 2020 | Portugal | Albufeira | Faro | 8 | 20 | 30-10-2017 | 22-05-2020 | 935 | 153 | 711400 | 590147.11 | 2 | 584439.82 | 5707.29 | 100.9765 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension due to pending approval of the court of accounts and due to the high season and festivities. | €5707.29 remained to be invoiced
2931 | 3863882 | Water Distribution Projects - Burn Subsystems | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Fafe | Braga | 3 | 30 | 31-10-2017 | 20-05-2019 | 566 | 210 | 811076.96 | 688534.85 | 2 | 683731.75 | 4803.1 | 100.7025 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60.00%; Technical Valuation and Warranty Proposal - 40.00%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | the quantities provided for some items were not carried out
2932 | 3858643 | Expansion of the water supply network between Besteiro and Rabaçal | 45000000-7 | Construction work | FALSE | 2017 | 2019 | Portugal | Penela | Coimbra | 6 | 20 | 27-10-2017 | 23-05-2019 | 573 | 180 | 407621.5 | 346902.22 | 2 | 343987.06 | 2915.16 | 100.8475 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | errors and omissions | underwork.
2933 | 3856325 | Emergency Discharges in the Southern Interceptor | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Mira | Aveiro | 1 | 11 | 25-09-2017 | 27-03-2019 | 548 | 150 | 199000 | 198814.06 | 1 | 118506.1 | 80307.96 | 167.7669 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suppression of ees4 works due to lack of licensing. | suppression of ees4 works due to lack of licensing.
2934 | 3854473 | Public Tender for awarding the contract for "Viana do Castelo Urban Cycle Path Network - Cais Novo/Cabedelo Section"- Proc. 78/A1/17. | 45233200-1 | Various surface works | FALSE | 2017 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 06-11-2017 | 29-10-2018 | 357 | 120 | 495000 | 467281.08 | 2 | 446466.09 | 20814.99 | 104.6622 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value of the Proposal - 60%. The subfactors are those contained in article 18 of the tender program | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
2935 | 3853321 | Requalification of the EN 270 in Santa Catarina da Fonte do Bispo | 45233252-0 | Surface work for streets | FALSE | 2017 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 27-10-2017 | 25-10-2019 | 728 | 270 | 681134.99 | 627396.87 | 2 | 702291.78 | -74894.91 | 89.3356 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions relating to pss approval, additional work, and work to address errors and omissions | additional work and work to correct errors and omissions, in the amount of €60,008.72; underwork, worth -2,987.39€ and definitive price revision, worth €17,873.58
2936 | 3851229 | Hospital Dr. Nélio Mendonça - Rehabilitation of the Obstetrics and Medicinal Gases Block | 45215140-0 | Hospital facilities construction work | FALSE | 2017 | 2020 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 40 | 27-10-2017 | 28-05-2020 | 944 | 150 | 1250000 | 1000000.01 | 3 | 994833.67 | 5166.34 | 100.5193 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension - alteration to the hvac project | price review
2937 | 3848706 | Lots 10 and 11 - Requalification of Avenida General Ribeiro de Carvalho (PAMUS 1.8), streetNadir Afonso, Travessa Nuno Álvares and streetMário dos Santos Delgado (PAMUS 1.9) and streetArtur Maria Afonso and streetArtur Maria Afonso | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Chaves | Vila Real | 19 | 30 | 02-11-2017 | 04-02-2020 | 824 | 150 | 722000 | 678999.44 | 2 | 782402.18 | -103402.74 | 86.7839 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension for 41 days, additional work for 15 days and correction of errors and omissions for 8 days | more work, errors and omissions supply, underwork and price revision.
2938 | 3848322 | Contract 6/GEBALIS/2017 - Public tender for Maintenance and Repair of Fires and Common Areas in Neighborhoods in the South Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 20 | 31-10-2017 | 18-11-2019 | 748 | 730 | 599999.46 | 559370.3 | 2 | 559370.3 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | ends by value and duration.
2939 | 3848125 | Lot 2: Requalification of Avenida Nuno Álvares (PAMUS 1.4) | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 02-11-2017 | 11-09-2019 | 678 | 180 | 840963 | 749527.95 | 2 | 769638.16 | -20110.21 | 97.3871 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work extensions and suspensions | errors and omissions supply work worth €25,359.00 and underwork worth €30,976.10 and price review worth €25,727.31
2940 | 3847369 | Improvement of pavements and construction of sidewalks in Nevogilde and Casais | 45233140-2 | Roadworks | FALSE | 2017 | 2018 | Portugal | Lousada | Porto | 13 | N/A | 26-10-2017 | 23-11-2018 | 393 | 120 | 248486.5 | 243017.75 | 1 | 243017.75 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | water supply works carried out by external teams and delays in the availability of plots of land for enlargements
2941 | 3841629 | Procedure No. 76/DSUMC/2016-Renovation of barracks for GIPS of the Republican National Guard-Pontinha Barracks | 45454000-4 | Restructuring work | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | 3 | 27-07-2017 | 19-03-2018 | 235 | 120 | 349000 | 318500 | 2 | 318500 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | waiting time that existed to receive the approval of the request for the occupation of a public road by the lisbon city council. delay of some materials and equipment for the project. | nothing to say.
2942 | 3839591 | Restoration of Municipal Roads in the Union of the parishes of Areias and Pias, Águas Belas Parish and Nossa Senhora do Pranto Parish | 45233142-6 | Road-repair works | FALSE | 2017 | 2021 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 16-10-2017 | 06-08-2021 | 1390 | 120 | 503200 | 447874.3 | 2 | 537526.59 | -89652.29 | 83.3213 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to overwork and the suspension of work | due to overwork, underwork and price revisions
2943 | 3838613 | Rehabilitation works of blocks G, H and J to O of Bairro do Carvalhido | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 24-10-2017 | 26-09-2018 | 337 | 240 | 800000 | 764083.75 | 2 | 763828.82 | 254.93 | 100.0334 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | eo in the amount of €7,076.34 and work not carried out in the amount of €7,331.27
2944 | 3834672 | ic5 node arrangement | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 25-07-2017 | 31-01-2019 | 555 | 450 | 599844 | 517053.88 | 2 | 462436.91 | 54616.97 | 111.8107 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in signal supply | works less
2945 | 3828905 | Rehabilitation of the Melo palace - installation of a youth hostel | 45000000-7 | Construction work | FALSE | 2016 | 2020 | Portugal | Vila do Conde | Porto | 13 | 22 | 06-02-2017 | 26-11-2020 | 1389 | 480 | 990000 | 792000.01 | 2 | 1010305.36 | -218305.35 | 78.3921 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: TECHNICAL QUALITY OF THE PROPOSAL- 50% PRICE-50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2946 | 3828510 | Construction of kennels at the Guarda School, in Queluz | 45223600-2 | Dog kennels construction work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 28-02-2017 | 09-03-2018 | 374 | 180 | 348500 | 301040 | 2 | 301040 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to the factors in Annex IV of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the approval of extracontractual works. atmosphere conditions. | nothing to say
2947 | 3826144 | Expansion and Refurbishment of the Baltar Barracks | 45262800-9 | Building extension work | FALSE | 2017 | 2018 | Portugal | Paredes | Porto | 13 | 20 | 30-08-2017 | 30-06-2018 | 304 | 88 | 601764.34 | 579840.65 | 2 | 610723.9 | -30883.25 | 94.9432 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The relative weight of the factors will be as follows distributed: Pa = 33% (Good performance guarantee) Pb = 32% (Technical quality of the proposal) Pc = 30% (Price) Pd = 5% (Execution time) (See Annex IV of the Program of Procedures) | 1 | 30 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | avoid disruptions to the proper functioning of the barracks | extra work
2948 | 3813761 | Sanitation and Paving in Alcaria longa | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Mértola | Beja | 2 | 30 | 13-10-2017 | 27-05-2020 | 957 | 270 | 1210083 | 878874.19 | 2 | 872824.72 | 6049.47 | 100.6931 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in hiring labor and delay in the supply of materials. | underwork
2949 | 3810846 | Expansion of the sanitation network in Vila Fonche (Tourim/Outeiro/Church) and Paçô (Paço Velho) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 20-10-2017 | 04-02-2019 | 472 | 210 | 244000 | 207400.01 | 1 | 207399.99 | 0.02 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 50% - Lowest overall price; 50% Worth proposal technique These criteria are decomposed into sub-criteria, in accordance with article 12 of the Procedure Program | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended for 120 days, for small section terminus and pavement replacement
2950 | 3810116 | 5010019932 - Stabilization contract for the excavation slopes between km 236+710 and km 236+937, between km 237+230 and km 237+800, between km 239+000 and km 239+250, between the km 241+200 and km 241 | 45111230-9 | Ground-stabilisation work | FALSE | 2016 | 2020 | Portugal | N/A | N/A | N/A | 37 | 06-09-2017 | 16-12-2020 | 1197 | 420 | 3250000 | 1950000.01 | 3 | 1163257 | 786743.01 | 167.6328 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical value 15% - Security Management System 15% - Quality Management System 5% - Environmental Management System 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 25 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2951 | 3806516 | Execution of the 1st section of the channel connecting Av. Fernão de Magalhães (Loja do Cidadão) to street of Sofia (Paços do Concelho), in order to ensure the circulation | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 08-06-2017 | 25-10-2019 | 869 | 270 | 733330 | 591561.44 | 2 | 496110.18 | 95451.26 | 119.2399 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of term | work not performed and price revision
2952 | 3805141 | Rehabilitation contract for the Carmo neighborhood in Moura | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2019 | Portugal | Moura | Beja | 2 | 30 | 19-10-2017 | 20-11-2019 | 762 | 240 | 497035.51 | 450170.66 | 2 | 421047.73 | 29122.93 | 106.9168 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the installation of electrical infrastructure and supply of materials | extra work
2953 | 3799940 | Consists of carrying out demolition work on construction and adjacent structures by the Special Rehousing Program (Decree-Law No. 163/93 of May 7th and Decree-Law No. 271/03 of October 28th) | 45111100-9 | Demolition work | FALSE | 2017 | 2020 | Portugal | Amadora | Lisboa | 11 | 10 | 09-10-2017 | 23-03-2020 | 896 | 300 | 227000 | 181601.68 | 1 | 181601.68 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: CF= 0.75xP+0.25xV P is the score assigned to the "Price" Factor V is the score assigned to the "Technical Value" Factor The factors and subfactors will be evaluated according to the model in Annex III of the Tender Programme. In the event of a tie, a drawing will be made between the equivalent proposals. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | early compliance
2954 | 3791564 | Requalification contract for the elementary and High school of Mêda | 45331000-6, 45261213-0 | Heating, ventilation and air-conditioning installation work, Metal roof-covering work | FALSE | 2017 | 2018 | Portugal | Meda | Guarda | 9 | 10 | 28-09-2017 | 04-06-2018 | 249 | 90 | 282488 | 227755.5 | 1 | 231194.82 | -3439.32 | 98.5124 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | impossibility to remove fiber cement boards during class time. these works were carried out during school holidays and weekends. | due to overwork, underwork, and errors and omissions supply work.
2955 | 3788318 | The purpose of the contract is to carry out the contract, called "Requalification of the public space surrounding the Torres da Bela vista, in Santo António dos Cavaleiros" | 45233222-1 | Paving and asphalting works | FALSE | 2017 | 2018 | Portugal | Loures | Lisboa | 11 | 12 | 14-09-2017 | 29-10-2018 | 410 | 35 | 215000 | 168940.85 | 1 | 168940.85 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 19 of the Tender Programme. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2956 | 3786678 | PRC_0051_2017 - EGA-EB0323 - Construction contract for the execution of the Drainage Networks of Água Longa SAR (Santo Tirso) | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Santo Tirso | Porto | 13 | 12 | 11-10-2017 | 06-07-2020 | 999 | 308 | 2600000 | 1929507.62 | 3 | 1857049 | 72458.62 | 103.9018 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the above | there was no need to perform all contract work.
2957 | 3778517 | Domestic wastewater drainage networks and gândara water supply | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Coimbra | Coimbra | 6 | 24 | 11-09-2017 | 19-11-2020 | 1165 | 240 | 560000 | 498488.97 | 2 | 479490.61 | 18998.36 | 103.9622 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: Those indicated in point 15 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | alteration of the pipeline route due to problems with owners | underwork has taken place
2958 | 3778099 | Occasional repairs to the wastewater drainage system in the municipality of Coimbra - Phase 3 | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Coimbra | Coimbra | 6 | 22 | 16-10-2017 | 13-08-2019 | 666 | 180 | 180000 | 175737.94 | 1 | 171177.06 | 4560.88 | 102.6644 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Those indicated in point 15 of the Program of Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was dependent on external entities to give authorization | underwork has taken place
2959 | 3777915 | Contract for Execution of Water Supply Pipelines to Pessegueiro | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Alcoutim | Faro | 8 | 20 | 12-09-2017 | 26-02-2019 | 532 | 180 | 610060.57 | 498718.96 | 2 | 498718.96 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and subfactors are in accordance with the stipulated in number 12.3 of the tender program - 100.00%. | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to provisional acceptance
2960 | 3775397 | Requalification of Azinhaga do Moinho de Vento and Largo de Santa Catarina in Alter do Chão. | 45211360-0 | Urban development construction work | FALSE | 2017 | 2019 | Portugal | Alter do Chão | Portalegre | 12 | 16 | 29-09-2017 | 28-10-2019 | 759 | 240 | 226686.38 | 199547.27 | 1 | 223934.42 | -24387.15 | 89.1097 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the deadline due to the execution of complementary work and due to the economic and financial situation that the country went through in the provision of raw material. | change in the value of the project due to the execution of complementary works and price revision.
2961 | 3772685 | Execution of the Sewer Network in Roqueiro | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Oleiros | Castelo Branco | 5 | 15 | 08-09-2017 | 21-10-2019 | 773 | 180 | 384778.48 | 349400.6 | 2 | 349400.6 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions. lack of labour.
2962 | 3768379 | Remodeling of the water supply network on streets anta Isabel, street of Salgueiro and streetD. João Pereira Venâncio | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Marinha Grande | Leiria | 10 | 20 | 28-08-2017 | 12-07-2019 | 683 | 90 | 246762 | 185050.6 | 1 | 191046.3 | -5995.7 | 96.8617 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for reasons attributable to the owner of the project | due to job suppression
2963 | 3767780 | Contract for the Rehabilitation and Expansion of a warehouse on streetde Mértola de Castro Verde | 45262800-9 | Building extension work | FALSE | 2016 | 2019 | Portugal | Castro Verde | Beja | 2 | 21 | 29-03-2017 | 02-09-2019 | 887 | 180 | 200000 | 193900 | 1 | 193000 | 900 | 100.4663 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term contract | contract value
2964 | 3766383 | Paving and Roads in the Municipality of Alijó - Requalification and Expansion (Repaving Cleaning and Arrangement of Berms and Trenches in the Access of Povoação de Carvalho to the Cemetery), Access | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2017 | 2018 | Portugal | Alijó | Vila Real | 19 | 20 | 20-09-2017 | 19-10-2018 | 394 | 120 | 245923.1 | 227989.07 | 1 | 236675.67 | -8686.6 | 96.3297 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions that occur during this period, namely rainfall and low temperatures, which do not allow for the technical conditions to carry out the paving | a) são mamede de ribatua - demolition of the existing wall after carrying out the project corresponding to the execution of the paving base or the agricultural path called access – slopes / lama do lagar in são mamede de ribatua – paving (paving of the agricultural path between the parish of castedo and s. mamede de ribatua) check -if there is a need in a certain area of ​​the road to widen it, given that most of the traffic that the path will have will be agricultural machinery, this widening will facilitate its manoeuvrability. the widening of the road will be for a private land, being agreed with the client the transfer of it for public use. the projects to be carried out are the demolition of the existing shale wall and façade - value: €761.60, plus vat at the legal rate in force. b) vale de agodim – laying of water and wastewater pipes during the contract, there is a need to carry out these works that are not included in the measurement map, given that these works will complement the intended work. wastewater piping: the municipality intends to remodel the sanitation and wastewater treatment network in the village of vale de agodim, it is not technically advantageous to place the wastewater piping after paving, so it is necessary to leave the pipe on “waiting” for the time of the contract described above to be placed in part of the section that connects vale de agodim to the en 323. the projects to be carried out are the supply and placement of a 200 mm diameter corrugated pipe, opening and closing of the trench and execution of manholes – amount: €3,375.00, plus vat at the legal rate in force. the projects mentioned above need to be carried out in this contract, since after the paving of this street, carrying out these works a posteriori will imply opening and replacing the laid pavement, jeopardizing the guarantee of the project as well as the quality of the projects to be carried out. accomplish. c) são mamede de ribatua – execution of wall after signing the contract, a part of the slope that supports the agricultural path called the access – slopes / lama do lagar in são mamede de ribatua – paving (paving of the agricultural path between the parish of castedo and s. mamede de ribatua) collapsed due to the weather conditions that occurred in the last months of the current year, thus making this area of ​​the path in question fragile, and the road in question could collapse after being paved, thus making it necessary and urgent to build a shale wall ( typical of the region) – 35 m2 to support the road slope, for subsequent paving as provided for in the execution project. the non-construction of this shale wall jeopardizes the stability of the path. the projects to be carried out are the execution of a shale wall, including excavation and implantation of the wall - value: € 4,550.00, plus vat at the legal rate.
2965 | 3763859 | Requalification of elementary school No. 1 in Reguengos de Monsaraz-Surrounding Area and Exterior Arrangements | 45233226-9 | Access road construction work | FALSE | 2017 | 2018 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 10-08-2017 | 06-08-2018 | 361 | 150 | 245955.27 | 237000 | 1 | 237000 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1-PRICE(70%) Subfactors: a) Overall Price (90%) b) Proposed Price Justification Note (10%) 2-TECHNICAL VALUE (30%) Subfactors: a) Work Program (50%) a.1) Work Plan (50%) a.2) Labor plan (25%) a.3) Equipment Plan (25%) b) Descriptive and Justification Memory (40%) c) Payment Plan (10%) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to suspend the term
2966 | 3762092 | Construction of the wastewater interceptor system I das Galveias | 45232410-9 | Sewerage work | FALSE | 2017 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 30 | 10-10-2017 | 21-02-2019 | 499 | 180 | 250000 | 217413.72 | 1 | 219577.82 | -2164.1 | 99.0144 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A) Price - 70% B) Technical Valuation - 30% B1) Work execution methodology - 20% B2) Detail and consistency of the Work Plan - 10% B2.1) Work Schedule - 5% B2.2) Means Plan -5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | slight delay in scheduling the inspection for the purposes of provisional acceptance. | the effective total price considers the amount of €5,622.87 relating to the price revision
2967 | 3759758 | Contract for public works to carry out road markings in various locations in the Municipality of Cascais | 45233221-4 | Road-surface painting work | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 20 | 29-09-2017 | 31-07-2019 | 670 | 365 | 599964.5 | 395973.45 | 2 | 395973.45 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work interrupted due to lack of safety conditions (rain and bad weather)
2968 | 3759243 | 201/143 - DGEPIM - Requalification of streetPedro Nunes, Oeiras | 45233251-3, 45316110-9, 45233294-6 | Resurfacing works, Installation of road lighting equipment, Installation of road signals | FALSE | 2017 | 2019 | Portugal | Oeiras | Lisboa | 11 | 24 | 04-10-2017 | 19-02-2019 | 503 | 75 | 192279.84 | 169925.51 | 1 | 148818.43 | 21107.08 | 114.1831 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2969 | 3756366 | Rehabilitation of the Clock Tower, in Amareleja | 45453100-8 | Refurbishment work | FALSE | 2017 | 2021 | Portugal | Moura | Beja | 2 | 30 | 06-09-2017 | 17-11-2021 | 1533 | 240 | 467951.5 | 459329.59 | 2 | 463392.99 | -4063.4 | 99.1231 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | request for 2 extensions | no change
2970 | 3754070 | Construction contract "Rehabilitation and equipping of pre-school and elementary education buildings" | 45259000-7 | Repair and maintenance of plant | FALSE | 2017 | 2018 | Portugal | Figueiró dos Vinhos | Leiria | 10 | 21 | 11-07-2017 | 28-02-2018 | 232 | 180 | 211625.09 | 199898.36 | 1 | 199867.1 | 31.26 | 100.0156 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
2971 | 3750256 | Execution of horizontal signage in the municipality - Loures | 45233221-4 | Road-surface painting work | FALSE | 2017 | 2018 | Portugal | Loures | Lisboa | 11 | N/A | 24-07-2017 | 08-03-2018 | 227 | 120 | 471698.11 | 180000 | 1 | 179917.8 | 82.2 | 100.0457 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with Point 18 of the Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
2972 | 3749674 | Execution of horizontal signage in the municipality of Loures | 45233221-4 | Road-surface painting work | FALSE | 2017 | 2018 | Portugal | Loures | Lisboa | 11 | N/A | 30-05-2017 | 13-08-2018 | 440 | 365 | 471698.11 | 291698.11 | 2 | 291502.4 | 195.71 | 100.0671 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with Point 18 of the Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
2973 | 3748542 | Requalification of Largo 1.º de Maio in Abrantes | 45454000-4 | Restructuring work | FALSE | 2016 | 2020 | Portugal | Abrantes | Santarém | 16 | 36 | 02-10-2017 | 09-06-2020 | 981 | 240 | 425149.05 | 372534.07 | 2 | 374506.24 | -1972.17 | 99.4734 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two extensions of time were granted for a total of 139 days. | underwork and the ordinary revision of prices were considered.
2974 | 3747880 | Contract for the Conservation and Rehabilitation of the Synagogue of Tomar | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Tomar | Santarém | 16 | 24 | 21-09-2017 | 09-12-2019 | 809 | 180 | 230200 | 227520.64 | 1 | 247270.27 | -19749.63 | 92.0129 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project suffered some delays due to the carrying out of archaeological excavation work at the site, imposed by the dgpc | duplication of the intrusion detection and video surveillance chapter
2975 | 3746916 | 2016.107.01.C1 - SE Caldas da Rainha - Replacement of the HVAC, Lighting and Safety Conditions system | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2017 | 2018 | Portugal | Caldas da Rainha | Leiria | 10 | 23 | 21-07-2017 | 23-02-2018 | 217 | 120 | 230000 | 188924.7 | 1 | 188924.7 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | concluded
2976 | 3746685 | 2015.524.02.C1 - Employment Center of Ourique - Replacement of HVAC, lighting and telecommunications system | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2017 | 2018 | Portugal | Ourique | Beja | 2 | 24 | 04-08-2017 | 12-02-2018 | 192 | 90 | 195000 | 173668.87 | 1 | 166567.21 | 7101.66 | 104.2635 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there is no process | underwork
2977 | 3746564 | Rehabilitation of street of Maritona and streetConselheiro Arnaldo Vidal, in Oliveirinha | 45233120-6 | Road construction works | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | 23 | 18-09-2017 | 20-01-2020 | 854 | 180 | 348000 | 268763.53 | 2 | 241384.8 | 27378.73 | 111.3424 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | underwork
2978 | 3744392 | Rehabilitation of the Public Space of the IHRU Neighborhood | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Barcelos | Braga | 3 | 12 | 21-09-2017 | 24-06-2019 | 641 | 120 | 357350.82 | 303748.21 | 2 | 294226.21 | 9522 | 103.2363 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in carrying out the projects is not attributable to the contractor, since the project intervention area was partially occupied by scaffolding from another firm, which was carrying out an intervention on the buildings in the neighbourhood. this undertaking was the responsibility of the housing and urban rehabilitation institute. and this, too, exceeded the expected execution time, conditioning for this reason, even more, the execution of the project of the municipality. | there was underwork to be registered in the amount of €9,522.00.
2979 | 3744064 | Requalification of the Lavoeira neighborhood and streets in Mesquitela | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Mangualde | Viseu | 20 | 15 | 04-10-2017 | 01-03-2019 | 513 | 90 | 165000 | 158660.45 | 1 | 155843.74 | 2816.71 | 101.8074 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | specifications | underwork
2980 | 3743229 | Construction of the Ramalde Health Unit (EM.004.2017.124) | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 02-10-2017 | 31-10-2018 | 394 | 240 | 750000 | 745067.14 | 2 | 727862.91 | 17204.23 | 102.3637 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Proposal 20%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of term from 06/27/2018 to 08/01/2018 | work not carried out in the amount of €70,858.50 and eo in the amount of €50,652.13
2981 | 3743087 | Urban Requalification to the East - streetAntónio da Silva Brinco | 45233142-6 | Road-repair works | FALSE | 2016 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 03-07-2017 | 04-06-2020 | 1067 | 180 | 248277.75 | 222985.25 | 1 | 239680.3 | -16695.05 | 93.0345 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for execution of the project was changed due to the carrying out of more work and due to non-compliance with the project plan | the final value of the project has changed due to the approval of more works
2982 | 3735036 | Bonjardim Island Rehabilitation/Renovation (EM.004.2017.099) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 20 | 25-09-2017 | 07-03-2019 | 528 | 180 | 410000 | 390335 | 2 | 399590.05 | -9255.05 | 97.6839 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension | additional work worth €9,631.41, eo worth €839.47 and unfinished work worth €1,215.85
2983 | 3731654 | Urban Requalification of the central area of ​​Fiães - Phases 1, 2 and 3, in the parish of Fiães, municipality of Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 26-09-2017 | 19-11-2020 | 1150 | 360 | 683973.53 | 537067.71 | 2 | 580225.74 | -43158.03 | 92.5619 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 40 days of legal extension of the term and 110 days of graceful extension. 366 days of delay under the responsibility of the contractor and 77 days between the 1st inspection and the provisional reception of the project in the correction of deficiencies | more work and underwork
2984 | 3730543 | Expansion contract for Guia municipal market | 45213141-3 | Covered market construction work | FALSE | 2017 | 2019 | Portugal | Albufeira | Faro | 8 | 20 | 28-09-2017 | 04-12-2019 | 797 | 120 | 199947.4 | 169177.52 | 1 | 168977.52 | 200 | 100.1184 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | reasons not attributable to the contractor | job suppression
2985 | 3730480 | Paving construction contract in the municipality of cascais 2016/2017 | 45316110-9, 45232410-9, 45233200-1, 45233294-6, 45100000-8, 45111100-9 | Installation of road lighting equipment, Sewerage work, Various surface works, Installation of road signals, Site preparation work, Demolition work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | N/A | 14-06-2017 | 28-06-2018 | 379 | 380 | 1744660 | 226266.01 | 1 | 226266.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
2986 | 3730362 | Paving construction contract in the municipality of cascais 2016/2017 | 45316110-9, 45233200-1, 45100000-8, 45232410-9, 45233294-6, 45111100-9 | Installation of road lighting equipment, Various surface works, Site preparation work, Sewerage work, Installation of road signals, Demolition work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | N/A | 12-06-2017 | 28-02-2018 | 261 | 380 | 1744660 | 325410.01 | 2 | 325410.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A
2987 | 3730227 | Paving construction contract in the municipality of cascais 2016-2017 | 45233294-6, 45111100-9, 45233200-1, 45316110-9, 45100000-8, 45232410-9 | Installation of road signals, Demolition work, Various surface works, Installation of road lighting equipment, Site preparation work, Sewerage work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | N/A | 14-06-2017 | 05-03-2018 | 264 | 380 | 1744660 | 325258.51 | 2 | 325258.51 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
2988 | 3730054 | Paving construction contract in the municipality of cascais 2016/2017 | 45232410-9, 45233294-6, 45233200-1, 45100000-8, 45111100-9, 45316110-9 | Sewerage work, Installation of road signals, Various surface works, Site preparation work, Demolition work, Installation of road lighting equipment | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | N/A | 14-06-2017 | 10-05-2018 | 330 | 380 | 1744660 | 196656.5 | 1 | 196656.5 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
2989 | 3729165 | The purpose of the contract is the expansion of the São Miguel do Mato Wastewater System. | 45232460-4 | Sanitary works | FALSE | 2017 | 2021 | Portugal | Vouzela | Viseu | 20 | 30 | 25-09-2017 | 08-11-2021 | 1505 | 540 | 786800 | 777824.21 | 2 | 757838.73 | 19985.48 | 102.6372 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline change resulted from two partial suspensions. | the change in the value of the project resulted from underwork.
2990 | 3725959 | Execution of the infrastructures for the alteration of the ZICOFA allotment and construction of the variant connecting ZICOFA to the EM 533-2 (Pinheiros) | 45233120-6 | Road construction works | FALSE | 2017 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 28-09-2017 | 27-02-2019 | 517 | 365 | 2344472.83 | 1829996 | 3 | 1820533.51 | 9462.49 | 100.5198 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes | underwork
2991 | 3724671 | EGA-AR0254 - Execution contract for Barrimau II, Figueiras I, S. Mamede I and II, Salgueirinhos, Cernadelo and Ribeira Branca Interceptors | 45232423-3, 45232411-6 | Sewage pumping stations construction work, Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Lousada | Porto | 13 | 47 | 20-09-2017 | 16-12-2019 | 817 | 168 | 600000 | 472771.58 | 2 | 423625.62 | 49145.96 | 111.6013 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | phased availability of land needed for the contract and delays in the execution of works by the contractor. | it was possible to optimize some layouts of the implantation of some interceptors which implied some underwork, namely the elimination of a horizontal drilling in the interceptor of s. mamede i
2992 | 3722981 | Requalification and improvement of streets of the municipal road network - 2017 | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 14-06-2017 | 29-08-2018 | 441 | 240 | 4373377.84 | 3787350.23 | 3 | 3583869.78 | 203480.45 | 105.6777 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50%; Technical value - 40%; Lead time - 10%. | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | total suspension of work: 132 days, pursuant to art. a) of article 297 of the pcc. | existence of underwork due to the foreseen quantities not being used up.
2993 | 3719066 | EGA-O0271 - Technical room (Datacenter) at Águas do Douro e Paiva, S.A. And simdouro, s.a. on the stage | 45310000-3 | Electrical installation work | FALSE | 2017 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 25 | 17-07-2017 | 29-12-2018 | 530 | 485 | 180000 | 151987.09 | 1 | 147685.99 | 4301.1 | 102.9123 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | work not done
2994 | 3718765 | EGA-AA0082 - Contract for Executing the Connection to S. Gens, Rabies and Lomba | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Gondomar | Aveiro | 1 | 30 | 23-06-2017 | 31-07-2018 | 403 | 120 | 450000 | 384829.46 | 2 | 384829.46 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A. PRICE - 50% B. TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change to the layout of s.gens due to difficulty in obtaining land. adverse meteorological conditions for carrying out paving in the winter period.
2995 | 3715696 | Construction of the Lousada Health Center - Lustosa Health Unit | 45215140-0 | Hospital facilities construction work | FALSE | 2017 | 2019 | Portugal | Lousada | Porto | 13 | 21 | 22-09-2017 | 17-01-2019 | 482 | 180 | 252228.78 | 239953.75 | 1 | 239953.75 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension by 171 days
2996 | 3714077 | Contract 21/Gebalis/2016 - Rehabilitation and conservation works in the Marquês de Abrantes Neighborhood, lots 28 to 34 - CP 398/CM/2015, Action nº 18, Sub-action nº 18.3 | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Lisboa | Lisboa | 11 | 11 | 26-09-2017 | 27-11-2020 | 1158 | 270 | 495988 | 434357.26 | 2 | 517164.78 | -82807.52 | 83.9882 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | complexity in the execution of the projects and adverse weather conditions during the course of the projects / suspension of the projects due to lack of definition of the project
2997 | 3713842 | Improvement of the EM 509 from Seixas to Pinheiro Novo - Section (Contim - Pinheiro Velho) | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Vinhais | Bragança | 4 | 30 | 22-09-2017 | 06-11-2019 | 775 | 270 | 349800 | 282069.5 | 2 | 304130.71 | -22061.21 | 92.7461 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (Weighting 80%) Technical Value of the Proposal (Weighting 20%) | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change in the execution period
2998 | 3712950 | Rehabilitation of streetManuel Teixeira Gomes - Silves | 45211360-0 | Urban development construction work | FALSE | 2017 | 2019 | Portugal | Silves | Faro | 8 | 30 | 15-09-2017 | 04-12-2019 | 810 | 120 | 221487 | 176072.68 | 1 | 187671.42 | -11598.74 | 93.8197 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the execution of the project and deadline extension | supply of errors and omissions, short work and price revisions
2999 | 3711632 | Requalification of Praça da Republica - 1st Phase. General requalification of the Square, renovating floors, infrastructures, garden areas and general requalification of accessibility in the surrounding walkways. | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2018 | Portugal | Monção | Viana do Castelo | 18 | N/A | 02-06-2017 | 17-01-2018 | 229 | 365 | 581000 | 580995.18 | 2 | 14436.08 | 566559.1 | 4024.6049 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Guarantee/Exceptional conditions given to the work and its equipment - 20% Maintenance deadline Green Spaces - 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this undertaking, following the entry of the new executive, had an agreement for the revocation by mutual agreement of contract no. 44/2017 approved at the executive meeting on 12/18/2017. | this undertaking, following the entry of the new executive, had an agreement for the revocation by mutual agreement of contract no. 44/2017 approved at the executive meeting on 12/18/2017.
3000 | 3711020 | Repaving of E.M. 520-4 E Urbanização de Mata Lobos | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | Faro | Faro | 8 | 12 | 22-09-2017 | 06-02-2019 | 502 | 60 | 277019 | 179677.9 | 1 | 179677.9 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3001 | 3711007 | Hayward City Avenue Repaving | 45233142-6 | Road-repair works | FALSE | 2017 | 2018 | Portugal | Faro | Faro | 8 | 12 | 21-09-2017 | 18-10-2018 | 392 | 90 | 265640.58 | 178466.86 | 1 | 167134.22 | 11332.64 | 106.7806 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3002 | 3710436 | 5010030811 - IC19 Nó do Cacém, Via Coletora do Branch B | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 32 | 11-09-2017 | 26-09-2019 | 745 | 120 | 375000 | 335331.6 | 2 | 324925.58 | 10406.02 | 103.2026 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | bill of quantities results
3003 | 3706150 | Execution of the public works contract "EXTERIOR ARRANGEMENTS OF streetINFANTE D. Henrique (zone 4) and exterior repairs of the area surrounding the church of s. Sebastião (zone 5)" | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Alandroal | Évora | 7 | 21 | 13-09-2017 | 11-09-2019 | 728 | 120 | 580113.18 | 349300 | 2 | 271112.96 | 78187.04 | 128.8393 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Proposed price - 60%; Technical value of proposal - 40%. The subfactors are those contained in point 17.3 of the Tender Program | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays fully attributable to the contractor. | due to the existence of underwork in the amount of €80,373.75 and ordinary revision of prices in the amount of €2,186.71.
3004 | 3704798 | Refurbishment of the Playground with grass on synthetic floor - Vila Boa de Quires | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2017 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 11 | 12-09-2017 | 03-05-2019 | 598 | 60 | 228097.85 | 225246.49 | 1 | 224846.49 | 400 | 100.1779 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was suspended | underwork worth €400.00
3005 | 3704677 | Requalification of the municipal sludge pool | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Braga | Braga | 3 | 15 | 14-09-2017 | 01-06-2020 | 991 | 50 | 210833 | 195789.13 | 1 | 197715.98 | -1926.85 | 99.0254 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions, uncertainty in the location of the elevator and others. | underwork and price review.
3006 | 3703858 | Requalification of the Penamacor Health Center | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2020 | Portugal | Penamacor | Castelo Branco | 5 | 57 | 22-09-2017 | 02-04-2020 | 923 | 300 | 431895.66 | 418728.61 | 2 | 485816.26 | -67087.65 | 86.1907 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions: additional work: 36 days; errors and omissions: 14 days; other extensions: 316 days. total 366 days. | additional work: €49,173.32; errors and omissions: €19,884.70; underwork: €7,111.85; price revision: €8,929.64.
3007 | 3702396 | Contract for "Vale Torto wastewater subsystem" | 45232420-2 | Sewage work | FALSE | 2017 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | N/A | 21-09-2017 | 24-09-2018 | 368 | 150 | 215000 | 204748.29 | 1 | 154478.11 | 50270.18 | 132.5419 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspension | more work and underwork
3008 | 3701900 | EGA-EB0119 - Water Supply Infrastructure in Covelas and Gove (Pedreda) and Sanitation Infrastructure in Gôve (Baião) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2020 | Portugal | Baião | Porto | 13 | 50 | 05-09-2017 | 17-02-2020 | 895 | 300 | 940000 | 770798.09 | 2 | 645778.11 | 125019.98 | 119.3596 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in the execution of works by the contractor and unavailability of land included in the contract | there was no need to carry out all the contractual work, fundamentally the foreseen quantities
3009 | 3701356 | Construction of a road linking the Industrial Zone in Rebordosa to the A41 in Gandra | 45233121-3 | Main road construction works | FALSE | 2017 | 2020 | Portugal | Paredes | Porto | 13 | 20 | 14-09-2017 | 28-12-2020 | 1201 | 270 | 328750.9 | 297886 | 2 | 297886 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | indications of mr. mayor
3010 | 3701251 | Construction of the wastewater drainage system for Espadanal, Lageosa and Vila Seca | 45232400-6 | Sewer construction work | FALSE | 2017 | 2020 | Portugal | Tábua | Coimbra | 6 | 24 | 21-09-2017 | 23-07-2020 | 1036 | 515 | 709700.77 | 629321.45 | 2 | 582727.41 | 46594.04 | 107.9959 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | rocky nature of the terrain. simultaneous execution of the water network. conduct corrections. | underwork
3011 | 3698953 | Moinhos da Póvoa Riverside Park and Tagus Bike Path | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2020 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 31-07-2017 | 02-12-2020 | 1220 | 150 | 2295000 | 2143154.13 | 3 | 2053203.88 | 89950.25 | 104.381 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two graceful extensions of the 64 + 28 day lead time, for a total of 92 days of extension (150+92 days = 242 run days) | - decrease due to underwork; - addition of the final value of the contract due to the positive value of the price revision (definitive).
3012 | 3697518 | P064/2017 - EN 356 - Intervention to safeguard human life - law 27/2006 of July 3 | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | Ourém | Santarém | 16 | 24 | 01-09-2017 | 06-11-2019 | 796 | 60 | 408586.37 | 272218.24 | 2 | 275563.84 | -3345.6 | 98.7859 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the project | value of additional works; underwork and price revision
3013 | 3696012 | Road alteration of the roundabout at Praia da Barra (refurbishment) | 45233125-1 | Road junction construction work | FALSE | 2017 | 2019 | Portugal | Ílhavo | Aveiro | 1 | 13 | 28-07-2017 | 16-09-2019 | 780 | 300 | 1743250 | 1729610 | 3 | 1757193.13 | -27583.13 | 98.4303 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions; delays in the supply of materials; delays in changing underground infrastructure. | underwork (not performed); pricing review.
3014 | 3695848 | Refurbishment of the sewage and rainwater drainage network and the water supply network. Improvement of the sidewalk pavement. | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2018 | Portugal | Oleiros | Castelo Branco | 5 | 14 | 08-05-2017 | 26-02-2018 | 294 | 180 | 300000 | 249500.72 | 1 | 249500.72 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the causes of the deadline changes were due to unfavorable weather conditions
3015 | 3695154 | Widening of the Caminho do Ribeiro da Ponte das Laranjeiras for agricultural purposes - São Martinho | 45233123-7 | Secondary road construction work | FALSE | 2017 | 2018 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 19-09-2017 | 10-10-2018 | 386 | 270 | 311754 | 255142.9 | 2 | 255142.9 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions
3016 | 3695018 | Requalification and improvement of several streets in the União das Parishes of Colmeias and Memória, municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 18-09-2017 | 09-05-2019 | 598 | 180 | 321877.7 | 303719.23 | 2 | 303719.23 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of work carried out by other entities at the site where the contract is being carried out | price revision calculation
3017 | 3693092 | Requalification and modernization of the premises of the Latino Coelho High school | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2020 | Portugal | Lamego | Viseu | 20 | 15 | 19-07-2017 | 31-07-2020 | 1108 | 365 | 4685445.08 | 3748356.08 | 3 | 3785321.16 | -36965.08 | 99.0235 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value - 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was not possible to intervene on the roof due to bad weather, which caused delays in the course of the project. | price review
3018 | 3692731 | Renovation of the drinking water network in Caminho do Lombo - Incendios 2016 | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2018 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 14-09-2017 | 08-06-2018 | 267 | 150 | 395442 | 344541 | 2 | 344541 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions that led to successive suspensions of the project
3019 | 3692559 | EMP-R/4/2017 - Contract for the Rehabilitation and Removal of Fiber Cement from Blocks 1 to 9 - Bairro do Hospital | 45442110-1, 45261213-0, 45453100-8 | Painting work of buildings, Metal roof-covering work, Refurbishment work | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 20 | 11-09-2017 | 13-02-2019 | 520 | 210 | 585000 | 497137.39 | 2 | 497137.39 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project were carried out within the deadline
3020 | 3692388 | conservation and improvement of the road network in the municipality of tavira – Repaving of streets in Santa Catarina da Fonte do Bispo | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 18-09-2017 | 20-02-2019 | 520 | 90 | 328896.28 | 262395.81 | 2 | 262720.15 | -324.34 | 99.8765 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delivery of the technical compilation. | definitive price review worth €324.34 (positive)
3021 | 3689762 | Requalification of the carriageway, gutter and pavements of the North Terminal of the Port of Aveiro - 2nd Phase | 45234120-3 | Urban railway works | FALSE | 2017 | 2018 | Portugal | Ílhavo | Aveiro | 1 | 30 | 18-09-2017 | 04-05-2018 | 228 | 90 | 320000 | 259768 | 2 | 259768 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 0.70 Technical Valuation of the Proposal: 0.30 | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ended within the contractual period of 90 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective receipt.
3022 | 3687337 | Maintenance of closing devices for manholes in the sanitation network of the municipality of Lisbon | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 18-08-2017 | 20-12-2019 | 854 | 730 | 1626348.92 | 949572.7 | 2 | 1015836.33 | -66263.63 | 93.4769 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Refer to point 14. of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3023 | 3686810 | Paving, in bituminous concrete, of the municipality's streets - 6th Phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 20 | 15-09-2017 | 17-03-2021 | 1279 | 150 | 1094415 | 1017383.65 | 3 | 877665.1 | 139718.55 | 115.9193 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% and b) Technical Quality of the Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 794 days of non-compliance by the contractor in completing some works and 141 days in correcting physical and documental defects | underwork
3024 | 3686753 | Construction of a wastewater treatment plant (WWTP) in Reguengo | 45232420-2 | Sewage work | FALSE | 2017 | 2018 | Portugal | Portalegre | Portalegre | 12 | 20 | 05-09-2017 | 31-10-2018 | 421 | 270 | 248913.81 | 174880.71 | 1 | 176802.88 | -1922.17 | 98.9128 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the fact that the 30 potted and planted trees foreseen in the contract dried up due to lack of irrigation, this anomaly having happened before the provisional reception of the project
3025 | 3684389 | Rehabilitation of the "envelope" and installation of an energy system (solar) in blocks 3, 4, 6 and 8 and Requalification of the Cultural and Sports Association of the Municipal Public Housing Complex of Falcão | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2019 | Portugal | Porto | Porto | 13 | 20 | 06-09-2017 | 30-01-2019 | 511 | 420 | 2478000 | 1988000 | 3 | 1956060.28 | 31939.72 | 101.6329 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the project went ahead as planned | eo in the amount of 36,203.73, deletions in the amount of 2,809.08€ and work not carried out in the amount of 65,334.37€
3026 | 3683702 | Improvement and repair of streets in the Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 12-09-2017 | 06-09-2018 | 359 | 120 | 1893100 | 346328.25 | 2 | 346328.25 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3027 | 3683606 | The object of the contract is the expansion of the wastewater system in Paços de . | 45232460-4 | Sanitary works | FALSE | 2017 | 2021 | Portugal | Vouzela | Viseu | 20 | 30 | 01-09-2017 | 29-07-2021 | 1427 | 540 | 472000 | 445514.06 | 2 | 431178.11 | 14335.95 | 103.3248 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were two partial suspensions of the period under the terms of subparagraph b) of article 365.º in conjunction with subparagraph a) of article 297.º, both of the public contracts code, approved by decree-law no. 18/2008, of 29 of january, with the wording prior to decree-law no. 111-b/2017, of august 31, | the change in the value of the project was due to underwork.
3028 | 3683448 | Improvement and repair of streets in the Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 12-09-2017 | 21-11-2018 | 435 | 120 | 1893100 | 360000 | 2 | 360000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
3029 | 3682916 | Improvement of streetde Leiria, construction of a roundabout at the intersection with en.356-1, repaving of street of Alquebe and construction of a sidewalk on em.540 in the town of Vale da Gunha - Maceira | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 12-09-2017 | 02-12-2019 | 811 | 240 | 624000 | 549713.31 | 2 | 573281.42 | -23568.11 | 95.8889 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work | price review
3030 | 3680363 | Rehabilitation of eb 1 in Grândola | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2021 | Portugal | Grandola | Setúbal | 17 | 60 | 11-09-2017 | 13-05-2021 | 1340 | 450 | 3057179.47 | 2445700 | 3 | 2639663.88 | -193963.88 | 92.6519 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the term of the project has been extended due to unforeseen incidents that arise during the projects | it was a complex work. given their nature and unprevisibility of some works, it was necessary to perform more works
3031 | 3679662 | Contract for the Requalification of Water and Sewage Infrastructures in Bairro Operário | 45232400-6, 45233251-3, 45232151-5 | Sewer construction work, Resurfacing works, Water-main refurbishment construction work | FALSE | 2017 | 2019 | Portugal | Lagos | Faro | 8 | N/A | 30-08-2017 | 28-08-2019 | 728 | 150 | 699000 | 624884.75 | 2 | 659648.29 | -34763.54 | 94.73 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | constraints due to the nature of the project and lack of labor | approval of work to correct errors and omissions in the amount of €16,611.87, plus vat by order of mrs. chairman of 09/07/2018 and calculated the final price revision amounting to €18,151.67
3032 | 3677487 | Process No. CP/AU 169/DOPM - Requalification of streetIrmã S. Romão | 45211360-0 | Urban development construction work | FALSE | 2017 | 2018 | Portugal | Barcelos | Braga | 3 | 9 | 08-09-2017 | 20-03-2018 | 193 | 150 | 325351.49 | 309324.65 | 2 | 291202.62 | 18122.03 | 106.2232 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the reason for the change in the deadline for the project was due to adverse weather conditions that made it impossible to carry out finishing work.
3033 | 3677174 | Carpet Paving Contract in Various Locations in the county | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Arouca | Aveiro | 1 | 21 | 14-09-2017 | 11-03-2019 | 543 | 60 | 349092.2 | 239864.53 | 1 | 172953.96 | 66910.57 | 138.6869 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | withdrawal of work due to the need for other interventions by other entities.
3034 | 3670732 | 5010031884/Drf-comn/2017 - Execution of the contract called "Northern Line - Renovation of the superstructure of the track between Valadares and Gaia | 50225000-8 | Railway-track maintenance services | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 32 | 28-08-2017 | 17-08-2020 | 1085 | 240 | 4703484 | 4135096.8 | 3 | 4206125.32 | -71028.52 | 98.3113 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical Valuation 20% Safety Management System 10% Quality Management System 5% Environmental Management System 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | nothing to register
3035 | 3669562 | The object of this contract is the construction of a domestic wastewater drainage system with around 11.7 km of gravity network and 6 pumping stations, with 1.5 km of conduits. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2020 | Portugal | Murtosa | Aveiro | 1 | N/A | 08-09-2017 | 16-03-2020 | 920 | 365 | 1500000 | 1273526.9 | 3 | 1273476.84 | 50.06 | 100.0039 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment and materials - 10%) | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3036 | 3669217 | Remodeling and Expansion of the António Matos Fortuna Primary School - partial remodeling of the school building and existing outdoor spaces and their expansion | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2020 | Portugal | Palmela | Setúbal | 17 | 20 | 18-08-2017 | 17-06-2020 | 1034 | 395 | 780000 | 763695.01 | 2 | 836165.25 | -72470.24 | 91.333 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to carry out unforeseen work, following the need to change the project and the need to extend the deadline due to the approval of project errors and omissions | need to carry out unforeseen work, following the need to change the project and pay for errors and omissions approved by the developer
3037 | 3668087 | Execution of underground water catchment hole in corroios | 45120000-4 | Test drilling and boring work | FALSE | 2017 | 2019 | Portugal | Seixal | Setúbal | 17 | N/A | 17-08-2017 | 07-02-2019 | 539 | 60 | 270000 | 258230 | 2 | 270310 | -12080 | 95.5311 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: according to point 23 program procedures | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work stoppages due to lack of safety conditions due to adverse weather conditions and the need to change the project/excess work | more works inherent to the records verified during the course of the project, mentioned above.
3038 | 3664410 | The object of the contract is the execution of a set of small works for the requalification of outdoor spaces/green areas, scattered throughout the southern area of ​​the municipality of Amdaora | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 06-09-2017 | 05-08-2020 | 1064 | 355 | 281943 | 239651.56 | 1 | 243348.1 | -3696.54 | 98.481 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out MDi = 100; - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform MDi = 65; - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of MDi detail = 30; - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest MDi = 0. b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between PTi activities = 100; - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities PTi = 65; - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out PTi = 30; - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out PTi = 0. The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 7 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay of children's equipment requested by suppliers, as well as delay in delivery of the "plan for the prevention and management of construction and demolition waste" by the successful bidder. | definitive price revision worth €3,696.54
3039 | 3663903 | Basic Sanitation of Adão | 45232410-9 | Sewerage work | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 07-09-2017 | 30-04-2019 | 600 | 180 | 388120 | 346345.85 | 2 | 346345.85 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3040 | 3663804 | Paving Repair Contract in the Municipality of Cascais | 45100000-8 | Site preparation work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | 47 | 07-07-2017 | 21-02-2018 | 229 | 432 | 5421862.5 | 707340.01 | 2 | 707340.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3041 | 3663753 | Paving Repair Contract in the Municipality of Cascais | 45100000-8 | Site preparation work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | 47 | 30-06-2017 | 26-11-2018 | 514 | 432 | 5421862.5 | 990399.01 | 2 | 990399.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3042 | 3663690 | Paving Repair Contract in the Municipality of Cascais | 45100000-8 | Site preparation work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | 47 | 07-07-2017 | 26-11-2018 | 507 | 432 | 5421862.5 | 989454.01 | 2 | 989454.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3043 | 3663609 | Paving Repair Contract in the Municipality of Cascais | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | 47 | 07-07-2017 | 28-02-2018 | 236 | 432 | 5421862.5 | 565924.51 | 2 | 565924.51 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3044 | 3663597 | Other Urban Arrangements - (Bairro João Paulo II - Phase 1 - Exterior and landscaping arrangements) | 45112700-2 | Landscaping work | FALSE | 2017 | 2018 | Portugal | Felgueiras | Porto | 13 | 24 | 07-09-2017 | 13-08-2018 | 340 | 270 | 231587.25 | 188339.41 | 1 | 188339.41 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | some adverse situations during the execution of the project | the value entered refers to the ordinary price revision, under the terms of article 382 of the "public procurement code"
3045 | 3662022 | Contract for "Seixas wastewater subsystem" | 45232420-2 | Sewage work | FALSE | 2017 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | N/A | 07-09-2017 | 14-09-2018 | 372 | 150 | 198000 | 182998.52 | 1 | 144722.72 | 38275.8 | 126.4477 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspension | more work and underwork
3046 | 3661846 | The object of the contract consists of carrying out work defined in terms of its type, quantity and technical conditions of execution, in the Project and in the Specifications | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 01-09-2017 | 05-07-2019 | 672 | 355 | 281975 | 254875.32 | 2 | 254875.32 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 65 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi = 65 - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out: PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delays in the project were due to: - outdated records of the area - diversity of work required; - the geographic variability in this type of work implies different mobilizations of means and resources; - multiplicity of interactions with the various services affected in each specific work.
3047 | 3660965 | 5010029394/RR-COSUL/2017 Contract called "marcação rodoviária 2017 - lot vi" | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 20 | 04-08-2017 | 10-12-2019 | 858 | 175 | 4500000 | 596739.3 | 2 | 587781.13 | 8958.17 | 101.5241 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the change in the value of the project corresponds to the determination of more works in the amount of €175,062.00, underwork in the amount of €188,036.50 and the final price revision in the amount of €4,016.32
3048 | 3659987 | 5010028957 - Er342, km 9+834, bridge over the river pranto - rehabilitation | 45221119-9 | Bridge renewal construction work | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 30 | 29-08-2017 | 28-04-2020 | 973 | 120 | 215000 | 178334.88 | 1 | 180562.12 | -2227.24 | 98.7665 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need for adaptations to the execution project. in fact, after the assignment of the project, the contractor made contacts with specialized companies, for the supply of prefabricated beams with the geometry foreseen in the execution project, however none of the companies supplied these materials, proposing, as an alternative, the supply of t70 beams. in these terms, there is room for the compatibility of the execution project with the current offer of the specialized market. impossibility of assembling the necessary work platforms to replace the deck of the bridge, in safe conditions, due to the meteorological conditions of intense rainfall that led to a rise in the water level of the pranto river. | compatibility of the execution project with the current offer of the specialized market.
3049 | 3658740 | Conservation of the municipal road network - Repaving of the C.M. 1054 Salsas-Vila Boa and C.M. 1032 Access Cova de Lua | 45233142-6 | Road-repair works | FALSE | 2017 | 2018 | Portugal | Bragança | Bragança | 4 | 20 | 05-09-2017 | 22-05-2018 | 259 | 120 | 345000 | 273587 | 2 | 273587 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical quality of the proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay due to adverse weather conditions and in accordance with technical clauses, the horizontal signaling work was only possible to carry out later.
3050 | 3652459 | EGA-AA0006 - Contract for the Rehabilitation of the Ribeirão Reservoir (Vila Nova de Famalicão) | 45247270-3 | Reservoir construction works | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 42 | 25-08-2017 | 30-11-2018 | 462 | 84 | 210000 | 158863.8 | 1 | 142922.21 | 15941.59 | 111.154 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price, 50%; b) Technical value of the proposal, 50%. | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | exploitation constraints on water supply to the population. adverse weather conditions. | optimization of the design solution led to the removal of some equipment considered unnecessary.
3051 | 3652220 | Conservation and Improvement of the Municipal Road Network - City of Tavira | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 14-07-2017 | 02-10-2019 | 810 | 150 | 251600 | 185902.96 | 1 | 185016.17 | 886.79 | 100.4793 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for carrying out the project began when the executing entity was notified of the approval of the health and safety plan (09/08/2017). | negative price review
3052 | 3650749 | Requalification and Expansion of Fafe High school | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2021 | Portugal | Fafe | Braga | 3 | 30 | 30-08-2017 | 24-02-2021 | 1274 | 540 | 3960756.38 | 3955000 | 3 | 3955000 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical Valuation and Warranty Proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was an extension of the term of the contract due to a substantial reduction in the programmed profitability of the project. | there was more work
3053 | 3650171 | EGA-AA0192 - Construction work for the Vilarinho Reservoir - Santo Tirso | 45247270-3, 45231300-8 | Reservoir construction works, Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Santo Tirso | Porto | 13 | 47 | 20-07-2017 | 18-09-2018 | 425 | 112 | 240000 | 184410.14 | 1 | 184410.14 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price, 50%; b) Technical value of the proposal, 50%. | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | as one of the consortium members is in the per phase, this also had repercussions on the development of the project, namely with regard to the possibility of reinforcing work teams.
3054 | 3650016 | Contract for the survey and replacement/construction and repair of sidewalks in specific areas of the Municipality of Albufeira. | 45233253-7 | Surface work for footpaths | FALSE | 2017 | 2018 | Portugal | Albufeira | Faro | 8 | 20 | 29-08-2017 | 04-12-2018 | 462 | 450 | 280000 | 252410.5 | 2 | 252410.5 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without changes
3055 | 3647051 | Basic Sanitation in Póvoa de Bodiosa | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Viseu | Viseu | 20 | 30 | 28-08-2017 | 26-07-2019 | 697 | 292 | 640000 | 598364.97 | 2 | 596011.29 | 2353.68 | 100.3949 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 21.00%; Price - 75.00%; Lead time - 4.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the owner of work was slow to make available the land necessary for the conclusion of the project. | the forecast quantities of work were forecast in excess.
3056 | 3646915 | Public Tender No. CP/EMP-01/16 - Contract for the Cleaning Station in Beato | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | 30 | 10-07-2017 | 23-07-2019 | 743 | 180 | 349745.39 | 335834.9 | 2 | 355064.9 | -19230 | 94.5841 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | supply of errors and omissions | supply of errors and omissions and price review
3057 | 3645720 | This contract is intended for the supply of water and the drainage of domestic wastewater in several streets in the parish of Ribafeita | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Viseu | Viseu | 20 | 30 | 28-08-2017 | 29-07-2019 | 700 | 292 | 1171501.6 | 877246.2 | 2 | 863795.11 | 13451.09 | 101.5572 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 21.00%; Price - 75.00%; Lead time - 4.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were lands to be unlocked. | there were quantities predicted in the measurement map that were not executed.
3058 | 3640864 | Rehabilitation of the Turf of the Velas Municipal Football Field, São Jorge Island | 45113000-2 | Siteworks | FALSE | 2017 | 2018 | Portugal | Velas | Região Autónoma dos Açores | 15 | 35 | 31-08-2017 | 12-01-2018 | 134 | 60 | 230101.68 | 200000 | 1 | 200000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the first provisional receipt notice dated 11/30/2017 had attached a list of deficiencies to be corrected by 12/30/2017 approved by the city council of velas on 11/11/2017, which were corrected and a new provisional reception dated 01/12/2018, in this case the second approved by the city council of velas on 01/19/2018.
3059 | 3640758 | Paving of the EM 553 connection to Frutuoso | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Valpaços | Vila Real | 19 | 24 | 31-08-2017 | 17-08-2018 | 351 | 180 | 256842.9 | 247217.58 | 1 | 247217.58 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price - 75% and Technical Valuation 25%, for this purpose, clause 17 of the procedural program must be consulted. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3060 | 3640722 | Chaves Business Park Adductor - Cando Adductor - Soutelo and Soutelo Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 30-08-2017 | 23-12-2019 | 845 | 270 | 456966 | 456442.73 | 2 | 446840.1 | 9602.63 | 102.149 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 2 term extensions | underwork and revision prices 90 days + 45 days)
3061 | 3640669 | Chaves Business Park Adductor - Urzeira and Remodeling of the Urzeira Reservoir | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 30-08-2017 | 30-04-2019 | 608 | 75 | 287876 | 287817.32 | 2 | 282554.99 | 5262.33 | 101.8624 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 2 term extensions of 78 days (44 + 34). | underwork worth €5,262.33
3062 | 3639976 | Adaptation of Existing Industrial Buildings to a Business Nest / Business Center in Mação | 45262700-8 | Building alteration work | FALSE | 2016 | 2021 | Portugal | Mação | Santarém | 16 | 11 | 10-10-2016 | 24-02-2021 | 1598 | 180 | 669349.32 | 601146.02 | 2 | 744552.55 | -143406.53 | 80.7392 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
3063 | 3639427 | execution of parque verde da ribeira de aljezur - Urban Requalification of street25 de Abril in Aljezur | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2018 | Portugal | Aljezur | Faro | 8 | 30 | 30-08-2017 | 31-10-2018 | 427 | 120 | 272000 | 270901.34 | 2 | 31402.11 | 239499.23 | 862.6852 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension request | the project was not completed due to abandonment by the contracting company
3064 | 3637627 | Expansion of the 1st Cycle of the Primary school in São Bernardo | 45214210-5 | Primary school construction work | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | 27 | 30-08-2017 | 20-11-2020 | 1178 | 365 | 1010656 | 708339.77 | 2 | 756232.7 | -47892.93 | 93.6669 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions and the need to carry out a latticework of foundation beams at ground level, delay in the delivery of materials, suppliers’ vacation period, difficulties in hiring subcontractors, accident with the locksmith subcontractor that prevented the continuation of the manufacture of parts already in progress , forcing the company to have new consultations and a new adjudication | miscellaneous unforeseen work
3065 | 3637110 | Contract for the coastal rehabilitation of the north coast of São Miguel, Rabo de Peixe, São Miguel Island | 45243100-3 | Cliff-protection works | FALSE | 2016 | 2019 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 34 | 29-08-2017 | 21-01-2019 | 510 | 300 | 3300000 | 2805000.01 | 3 | 2805000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work (366th "public procurement code"). extension of the execution period (n.º 2 of the 298th "public procurement code").
3066 | 3633485 | The contract includes the execution of paving work on municipal roads, in several parishes in the municipality of Santiago do Cacém. | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Santiago do Cacém | Setúbal | 17 | 22 | 17-08-2017 | 21-05-2018 | 277 | 60 | 630000 | 467727.16 | 2 | 306135.71 | 161591.45 | 152.7843 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in execution by the contractor. | breach of contract by the contractor
3067 | 3632682 | Urban requalification of Bairro das Barreiras | 45453100-8 | Refurbishment work | FALSE | 2017 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 22 | 25-08-2017 | 07-06-2021 | 1382 | 410 | 415934.36 | 331911.9 | 2 | 332622.49 | -710.59 | 99.7864 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | impediment of works for reasons beyond the control of the contractor and the owner of the project (execution of the natural gas network, changeover from the "overhead" to "underground" electrical network), delay in the delivery of materials by suppliers and adverse weather conditions. | job suppression and price revision.
3068 | 3630661 | Requalification of Largo Inácio Monteiro - Souto - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2018 | Portugal | Santa Maria da Feira | Aveiro | 1 | 20 | 24-08-2017 | 28-11-2018 | 461 | 120 | 226100 | 167680 | 1 | 132064.98 | 35615.02 | 126.9678 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | reasons attributable to the contractor | underwork
3069 | 3629856 | Recovery and enhancement of an urban green park and construction of a kiosk | 45212420-6, 45112710-5 | Construction work for restaurants and similar facilities, Landscaping work for green areas | FALSE | 2017 | 2019 | Portugal | Cadaval | Lisboa | 11 | 20 | 28-08-2017 | 09-09-2019 | 742 | 120 | 221260.14 | 220785.95 | 1 | 225105.1 | -4319.15 | 98.0813 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: proposed price - 60.00%; deadline - 40.00% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | taking into account that there was a delay in the completion of the project, and that this delay was largely due to vicissitudes, namely the carrying out of other works in the same space. | extra work
3070 | 3628689 | It consists of carrying out the defined works, in terms of their type, quantity and technical conditions of execution, in the project and in the Instruction Manual for this procedure | 45233221-4 | Road-surface painting work | FALSE | 2017 | 2018 | Portugal | Amadora | Lisboa | 11 | 30 | 17-08-2017 | 16-02-2018 | 183 | 365 | 183750 | 183000 | 1 | 183000 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: 1st - Price (P) - 45%; 2nd - Quality of Work and Material (Q) - 40%; 3rd - Response Time (PR) - 15%. Price Factor The score will be from 0 to 10, and the values ​​will be calculated according to the following formula: a) If the price offered by competitor i is within the range: 0.8 x Base Price < Competitor price i <= Base Price The formula will apply Pi = 8x [(Base Price - Competitor Price i) / (Base Price - 0.8 x Base Price)] b) If the price presented by competitor i is: Competitor price i <= 0.8 x Base Price and if the justification for the abnormally low price is accepted, pursuant to paragraph 4 of article 71 of the CCP: The formula will apply Pi = 10 - 2 x [ Competitor Price i / (0.8 x Base Price) ] Where Pi corresponds to the score assigned to the price presented by competitor i. Work and Material Quality Factor The Quality of work and material (Q) will be evaluated according to the following subfactors, evaluated during the execution of the tests and 15 days after its application: a) Drying time (TS) Evaluation of the drying time of each material upon application, in minutes, classifying it according to the intervals of time indicated below; TS (min) - Score >= 50 1 [45;50[ 2 [40;45[3 [35;40[4 [30;35[5 [25;30[6 [20;25[7 [15;20[8 [10;15[9 <10 10 b) Color (C) Changed 1 Unchanged 10 c) Pigment (PG) Inadequate 1 Adequate 10 d) Grip to the floor (A) Bad 1 good 10 e) Degradation (D) With traces 1 no trace 10 f) Finishing level (NA) bad 1 Reasonable 5 good 10 The value of zero will be assigned to the competitor who does not demonstrate the quality of work and material. The formula to be applied to evaluate each subfactor will be: - Drying Time TS = 0.25x TS White Thermoplastic + 0.25 x TS white plastic spray + 0.25 x TS yellow plastic spray + 0.25 x white aqueous TS - Color C = 0.25x C White Thermoplastic + 0.25x C white plastic spray + 0.25x C yellow plastic spray + 0.25 C white aqueous - Pigment PG = 1 x PG yellow plastic spray - Grip to the Floor A = 0.25x A White Thermoplastic + 0.25 x A white plastic spray + 0.25 x A yellow plastic spray + 0.25 A white aqueous - Degradation D = 0.25x D White Thermoplastic + 0.25 x D white plastic spray + 0.25 x D yellow plastic spray + 0.25 x D white aqueous - Finishing Level NA = 0.25x NA Thermoplastic White + 0.25 x NA white plastic spray + 0.25 x NA yellow plastic spray + 0.25 x aqueous NA white The formula to be applied to each competitor i will be: Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi Response Time Factor PR (days) - Score ]3;4] 1 ]2;3] 4 ]1;2] 7 [0;1] 10 The maximum response time allowed is 4 days. A value of zero will be assigned to the competitor who submits a response deadline greater than 4 days. The adjudication of this tender to be carried out between the Municipality of Amadora and the competitor with the highest classification will be performed after evaluating and scoring the results, obtained according to the mathematical expression described below: Final Score (PFi): PFi= 0.45xPi + 0.40xQi + 0.15xPRi where Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi applied to each competitor (i). The tiebreaker will be based on the following criteria, rounded to the second decimal place: - In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be given to the proposal with the highest score in the Work and Material Quality factor; - Thirdly, the proposal that obtained the lowest value in paragraph 3.1 of chapter 3 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 45 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was an urgent need to carry out work to mark parking lots and other pavement markings, to ensure good legibility of the existing spaces, as well as several cases that required urgent intervention were identified, it being convenient that the aforementioned works were carried out before the time the rains.
3071 | 3625998 | Rehabilitation and adaptation of a building for new premises of the Commission for the Protection of Children and Young People (CPCJ) of the Municipality of Porto (EM.004.2017.110) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 18-08-2017 | 24-01-2018 | 159 | 90 | 190000 | 179011.73 | 1 | 184577.71 | -5565.98 | 96.9845 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractually foreseen | eo in the amount of €7,894.98 and work not carried out in the amount of €2,329.00
3072 | 3623607 | Expansion of the Industrial Zone of Arrifana - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2021 | Portugal | Santa Maria da Feira | Aveiro | 1 | 20 | 24-08-2017 | 30-07-2021 | 1436 | 240 | 434326 | 316058.01 | 2 | 330283.43 | -14225.42 | 95.693 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 40% and b) Technical Quality of the Proposal - 40%. | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of the project, for reasons beyond the control of the owner and contractor related to the medium voltage branch | overwork due to unforeseen circumstances and measurement errors, as well as underwork
3073 | 3623432 | Requalification of streetArmando Pinto Assunção - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 20 | 24-08-2017 | 23-11-2020 | 1187 | 60 | 269461.1 | 222810 | 1 | 202220.2 | 20589.8 | 110.1819 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of Proposal - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 373 days for delay in completing the project, and 688 days for correcting physical and documental defects between the 1st inspection and provisional acceptance | underwork
3074 | 3621350 | Construction of the new bridge at Cabreira and requalification of accesses, Union of Parishes of Marrazes and Barosa | 45221110-6 | Bridge construction work | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 21-07-2017 | 27-06-2018 | 341 | 210 | 309580 | 282354.03 | 2 | 275635.15 | 6718.88 | 102.4376 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change | underwork
3075 | 3620920 | Rehabilitation of Municipal Road Infrastructures - North Zone | 45233252-0 | Surface work for streets | FALSE | 2017 | 2021 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 23 | 18-08-2017 | 07-04-2021 | 1328 | 120 | 580000 | 534000 | 2 | 527004.91 | 6995.09 | 101.3273 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | complexity of works | more work, underwork, price revision
3076 | 3618183 | Replacement of the current synthetic floor in Campo Marquês Jácome Correia, Parish of São Pedro, Ponta Delgada | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2017 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 28 | 12-07-2017 | 22-10-2019 | 832 | 75 | 288000 | 267445.29 | 2 | 275991.18 | -8545.89 | 96.9036 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | price review
3077 | 3617890 | Refurbishment of the Ernesto do Canto Public Library Building, Parish of São Pedro, Ponta Delgada | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2017 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 46 | 31-07-2017 | 31-05-2019 | 669 | 240 | 255000 | 235458.1 | 1 | 234567.9 | 890.2 | 100.3795 | PRESIDENCY OF THE REGIONAL GOVERNMENT OF THE AZORES EDITION OFFICE OF THE OFFICIAL JOURNAL HTTP://JO.AZORES.GOV.PT GEJO@AZORES.GOV.PTII SERIES Nº 65 FRIDAY, APRIL 7, 2017 If the criterion is the most economically advantageous proposal, indicate the factors and any subfactors accompanied by the respective weighting coefficients (*) They are those listed in article 18 of the tender program | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were 5 requests for extension of the contract period, resulting in an increase of 241 days. | need for more work.
3078 | 3615187 | Contract for "Chão Sobral wastewater subsystem" | 45232420-2 | Sewage work | FALSE | 2017 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | 20 | 22-08-2017 | 14-09-2018 | 388 | 150 | 162000 | 158900 | 1 | 134326.16 | 24573.84 | 118.2942 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspension | more work and underwork
3079 | 3610208 | Requalification of elementary school No. 1 in Chaves - elementary school in Santo Amaro | 45262400-5 | Structural steel erection work | FALSE | 2017 | 2018 | Portugal | Chaves | Vila Real | 19 | 30 | 17-08-2017 | 20-03-2018 | 215 | 60 | 267979.29 | 249900 | 1 | 249044.6 | 855.4 | 100.3435 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension approved at the board meeting on 11/02/2017, for a period of 24 days. | underwork worth €855.40
3080 | 3609736 | The purpose of the contract is to expand the Ventosa Wastewater System. | 45232460-4 | Sanitary works | FALSE | 2017 | 2021 | Portugal | Vouzela | Viseu | 20 | 24 | 16-08-2017 | 19-04-2021 | 1342 | 540 | 230000 | 221796.71 | 1 | 175102.21 | 46694.5 | 126.667 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline resulted from the suspension of the deadline for the project.
3081 | 3609634 | The purpose of the contract is to expand the Water Supply System in Cambra. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2020 | Portugal | Vouzela | Viseu | 20 | 24 | 14-08-2017 | 20-01-2020 | 889 | 540 | 270677.55 | 249400 | 1 | 249400 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the value of the project has not changed.
3082 | 3603266 | Reconstruction of the road, providing it with sidewalks, rearranging and expanding the parking area, as well as carrying out complementary work. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 19-04-2017 | 11-10-2019 | 905 | 150 | 195900 | 168802.94 | 1 | 175535.94 | -6733 | 96.1643 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension of the term | carrying out additional work and reviewing prices
3083 | 3601886 | 5010023510 - North Line - Válega / Gaia - Urgent actions to mitigate the risk of degradation of infrastructure performance | 45234100-7 | Railway construction works | FALSE | 2016 | 2018 | Portugal | N/A | N/A | N/A | 30 | 20-02-2017 | 24-05-2018 | 458 | 180 | 1190000 | 940235.53 | 2 | 955639.53 | -15404 | 98.3881 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1- Price 60% 2- Technical Valuation 20% 3 - Security Management System 10% 4-Quality Management System 5% 5- Environmental Monitoring System 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | additional work (art. 373º "public procurement code") (€) 46,996.00 € underwork (article 379 nº 2 "public procurement code") (€) -46,998.50 € ordinary price revision (art. 382º "public procurement code") (€) 15,406.50
3084 | 3601725 | 5010026390/Rr-cogl/2017 - execution of the contract called “en247 - km 54+700 to km 55+200, slope stabilization, excavation wall and slope” | 45233142-6 | Road-repair works | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 24 | 17-04-2017 | 05-12-2019 | 962 | 120 | 800000 | 480000.01 | 2 | 477378.51 | 2621.5 | 100.5491 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | resultant of bill of quantities
3085 | 3600456 | Sewage drainage network to Lamas/Serém (PAR 028) and water supply to Beco (Serém) (PAA 030) | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Águeda | Aveiro | 1 | N/A | 26-07-2017 | 28-02-2019 | 582 | 365 | 2200000 | 1943556.35 | 3 | 1788521.4 | 155034.95 | 108.6683 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: - PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with the contracting company's responsibility | nothing to report
3086 | 3598292 | Expansion of the Water Supply Network - Parish of Miranda (High Zone) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 22 | 09-08-2017 | 06-02-2019 | 546 | 270 | 555450 | 495406.12 | 2 | 495406.12 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Lowest global price - 50%; technical value of the proposal - 50% These criteria are decomposed into sub-criteria, in accordance with article 12 of the Tender Program | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended for 120 days, to complete the installation of equipment
3087 | 3597688 | The object of the contract is the execution of a set of small works for the requalification of outdoor spaces/green areas, scattered across the northern part of the municipality of Amadora | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 09-08-2017 | 13-11-2019 | 826 | 355 | 281943 | 239251.56 | 1 | 243438 | -4186.44 | 98.2803 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100; - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 65; - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi = 30; - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi = 0. b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi = 100; - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi = 65; - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi = 30; - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out -- PTi = 0. The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 7 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was due to the delay in the delivery, by the contractor, of the final "plan for the prevention and management of construction and demolition waste". | price review
3088 | 3597671 | 0329 - 683 - Contract to improve the WWTP in Oliveira do Hospital | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2019 | Portugal | Oliveira do Hospital | Coimbra | 6 | N/A | 11-05-2017 | 13-11-2019 | 916 | 285 | 800000 | 658594.8 | 2 | 694348.95 | -35754.15 | 94.8507 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extended by 34 days. | there was extra and underwork on errors and omissions and price revisions.
3089 | 3595489 | Requalification of Avenida D. Afonso Henriques and adjacent streets in Santarém – Phase 1 | 45233140-2 | Roadworks | FALSE | 2017 | 2019 | Portugal | Santarém | Santarém | 16 | 20 | 02-08-2017 | 07-07-2019 | 704 | 100 | 240819.21 | 218870.86 | 1 | 212925.15 | 5945.71 | 102.7924 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | conditions for the normal development of works due to user safety, accessibility and road and pedestrian mobility in the streets targeted for intervention. | works not performed
3090 | 3595454 | The object of this contract is the execution of water and sanitation networks and respective home extensions in a section of the EN 231 and street ofs Quintelas in Rebordinho in the municipality of Viseu. | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Viseu | Viseu | 20 | 42 | 20-07-2017 | 25-03-2019 | 613 | 216 | 217878 | 198217.89 | 1 | 184977.19 | 13240.7 | 107.158 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Technical value of the proposal - 21.00%; two - Price - 75.00%; 3 - Period of execution - 4.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of availability of land for the execution of the collector in some private land. | the value of the project carried out was below the value of the award of the contract.
3091 | 3595425 | Requalification of pavements and rainwater systems | 45233140-2 | Roadworks | FALSE | 2017 | 2018 | Portugal | Vizela | Braga | 3 | 11 | 11-08-2017 | 06-04-2018 | 238 | 60 | 342439.34 | 298602.3 | 2 | 297684.26 | 918.04 | 100.3084 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to some unforeseen circumstances at work. | underwork
3092 | 3595118 | Expansion of the sanitation network to Prozelo (Sucães/Lagoa) and Aguiã (Vila Nova/Bairro Novo) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 08-08-2017 | 06-02-2019 | 547 | 240 | 250000 | 197361.4 | 1 | 197361.4 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: 50% - Lowest global price 50% - Technical value of the proposal These criteria are decomposed into sub-criteria, in accordance with article 12 of the Procedure Program | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended for 89 days, for the purpose of replacing pavements
3093 | 3594332 | Requalification of the 1st cycle school - elementary school do Cruzeiro | 45453100-8 | Refurbishment work | FALSE | 2017 | 2018 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 17-07-2017 | 08-01-2018 | 175 | 90 | 289978 | 205440 | 1 | 197941.88 | 7498.12 | 103.788 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project finished within the deadline. | underwork worth 7,498.12
3094 | 3593814 | Demolition of pavements and repaving of approximately 2.8 km of road with bituminous masses, after installation of pipelines through Águas do Norte | 45233142-6 | Road-repair works | FALSE | 2017 | 2020 | Portugal | Amarante | Porto | 13 | 30 | 24-07-2017 | 13-03-2020 | 963 | 240 | 728019.32 | 399855.42 | 2 | 362166.19 | 37689.23 | 110.4066 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspensions due to adverse weather conditions | underwork and positive price revision
3095 | 3593690 | Demolition of pavements and repaving of approximately 2.2 km of road with bituminous masses, after installation of pipelines through Águas do Norte | 45233142-6 | Road-repair works | FALSE | 2017 | 2020 | Portugal | Amarante | Porto | 13 | 30 | 24-07-2017 | 13-03-2020 | 963 | 240 | 537168.02 | 363535.45 | 2 | 360447.64 | 3087.81 | 100.8567 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspensions due to adverse weather conditions | underwork and positive price revision
3096 | 3591605 | Completion of wastewater drainage networks in the Mezio Basin | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2019 | Portugal | Lousada | Porto | 13 | 21 | 04-08-2017 | 02-07-2019 | 697 | 365 | 961270.8 | 784070.95 | 2 | 642653.14 | 141417.81 | 122.0053 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in the provision of land | underwork
3097 | 3591566 | "Requalification of the Surroundings to the Municipal Sports Park" | 45236290-9 | Repair work on recreational areas | FALSE | 2017 | 2018 | Portugal | Figueiró dos Vinhos | Leiria | 10 | 21 | 21-06-2017 | 14-11-2018 | 511 | 180 | 738153.38 | 714215.48 | 2 | 712044.1 | 2171.38 | 100.305 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | underwork
3098 | 3590622 | All the works necessary for the requalification of the classroom blocks, offices, laboratories and arrangements and accessibility outside the teaching establishment in reference | 45214220-8 | Secondary school construction work | FALSE | 2017 | 2019 | Portugal | Valongo | Porto | 13 | 24 | 09-08-2017 | 09-05-2019 | 638 | 395 | 3400000 | 3111232.39 | 3 | 3280900.4 | -169668.01 | 94.8286 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions of time due to the execution of additional work and the correction of errors and omissions, as well as extensions of terms for free | changes to the value of works stemmed from approval of more work and supply of errors and omissions and less and from price revisions including the definitive price review (4th situation) approved on 20.11.2019, in the amount of €8,342.30 + vat.
3099 | 3590363 | Expansion of the D. Miguel da Silva Library | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2017 | 2019 | Portugal | Viseu | Viseu | 20 | 18 | 27-06-2017 | 31-05-2019 | 703 | 112 | 313000 | 264481.78 | 2 | 274138.71 | -9656.93 | 96.4774 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
3100 | 3590321 | Rehabilitation of the Primary school Grão Vasco - Viseu | 45113000-2 | Siteworks | FALSE | 2016 | 2021 | Portugal | Viseu | Viseu | 20 | 25 | 15-02-2017 | 30-06-2021 | 1596 | 266 | 1245000 | 1227104.63 | 3 | 1455466.4 | -228361.77 | 84.3101 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | by reviewing the protection/contracting of complementary work | complementary works
3101 | 3589644 | The contract consists of carrying out the work defined as to its type, quantity and technical conditions of execution, in the project and in the specifications governing the procedure | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 21 | 24-07-2017 | 16-01-2019 | 541 | 490 | 673474.13 | 575003.02 | 2 | 576475.78 | -1472.76 | 99.7445 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.45 * Pi + 0.55 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / (Base Price)) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the work to be perform - QAi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the work to be carried out - QAi = 60 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail - QAi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest - QAi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities - PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities - PTi = 60 - Presents a poorly detailed Work Plan, making it difficult to analyze the development of the work to be carried out - PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out - PTi = 0 The formula to be applied will be: VTi = QAi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; QAi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: - In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; - Thirdly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | provisional price revision in the amount of €1,472.76
3102 | 3587644 | Requalification of street ofmingos Torcato Ribeiro and Praceta Lions Internacional - Costa | 45233160-8 | Paths and other metalled surfaces | FALSE | 2017 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 07-08-2017 | 09-03-2018 | 214 | 120 | 469188 | 388001 | 2 | 385771.34 | 2229.66 | 100.578 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | following the inspection notice for provisional acceptance (07/12/2017), the contractor had to correct defects in the project, so he was granted a period of 45 days. | underwork due to the anticipated quantities not being used up.
3103 | 3584571 | Refurbishment of the Family Health Unit in Aradas | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | 23 | 14-07-2017 | 31-08-2020 | 1144 | 180 | 209430.2 | 193882.1 | 1 | 199139.83 | -5257.73 | 97.3598 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | procedure for renting containers to accommodate the services during the execution of the contract, adverse weather conditions and delay in supplies | extra work
3104 | 3584007 | Contract for the Expansion and Rehabilitation of the Milagres Elementary School, Parish of Arrifes, Ponta Delgada | 45214210-5 | Primary school construction work | FALSE | 2017 | 2020 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 46 | 01-08-2017 | 21-01-2020 | 903 | 360 | 1700000 | 1275001 | 3 | 1275001 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were two extension requests and one suspension, resulting in an increase of 219 days. | there were no changes to the value of the project
3105 | 3577914 | school rehabilitation | 45214220-8 | Secondary school construction work | FALSE | 2017 | 2019 | Portugal | Almeida | Guarda | 9 | 18 | 07-08-2017 | 01-04-2019 | 602 | 75 | 188600 | 155542.2 | 1 | 172029.83 | -16487.63 | 90.4158 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the fact that the projects take place inside a school establishment and given the need to carry out more work | more work; underwork and price revision.
3106 | 3577405 | The object of this contract is the remodeling of a pumping station, which includes civil works, equipment, electrical installations and instrumentation | 45232452-5 | Drainage works | FALSE | 2017 | 2018 | Portugal | Águeda | Aveiro | 1 | N/A | 19-07-2017 | 16-04-2018 | 271 | 90 | 160000 | 154000 | 1 | 142340.79 | 11659.21 | 108.1911 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no breaches of contractual deadlines. pss approved and communicated on 11/03/2017 | contracted work that was not necessary to perform
3107 | 3576188 | The object of the contract is the repair and upgrading of the streets and respective surroundings located in the northern part of the county, covering the parish of Mina de Água. | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 04-08-2017 | 16-01-2019 | 530 | 355 | 281975 | 239678.76 | 1 | 244211.98 | -4533.22 | 98.1437 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 65 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi = 65 - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out: PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - diversity/deployment of work required in various locations; - multiplicity of interactions with the affected services; - adverse weather conditions. | definitive price revision in the amount of €4,533.22.
3108 | 3576095 | Construction of the Moreira WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2017 | 2020 | Portugal | Nelas | Viseu | 20 | 22 | 01-08-2017 | 23-09-2020 | 1149 | 365 | 270000 | 267646.79 | 2 | 248518.27 | 19128.52 | 107.697 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspensions and extensions | more work, underwork and price revisions
3109 | 3576048 | Requalification of Public Space for the Creation of an Intergenerational Park in the Neighborhood of Vale de Rãs - Abrantes | 45454000-4 | Restructuring work | FALSE | 2017 | 2019 | Portugal | Abrantes | Santarém | 16 | 36 | 04-08-2017 | 02-05-2019 | 636 | 180 | 325750.6 | 297954.83 | 2 | 299200.35 | -1245.52 | 99.5837 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork and the ordinary revision of prices were considered.
3110 | 3573875 | Supply and installation of ladders and quay fenders - Portimão, Sagres and Lagos Fishing Ports | 45000000-7 | Construction work | FALSE | 2017 | 2018 | Portugal | Lagos | Faro | 8 | 30 | 17-07-2017 | 11-09-2018 | 421 | 105 | 315000 | 260659.83 | 2 | 263943.95 | -3284.12 | 98.7558 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 40%; deadline 10%; Technical quality of proposal 50% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | project omissions | errors and omissions
3111 | 3573085 | Contract for the creation of a large courtroom and reorganization of the sentence execution court - lisbon | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 19-07-2017 | 22-11-2018 | 491 | 120 | 290500 | 258588.81 | 2 | 220594.85 | 37993.96 | 117.2234 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was delayed due to the difficulty of carrying out work during the projecting hours of the court and delivery of the utan after the deadline. | there were shortcomings and fines.
3112 | 3571384 | Preventive maintenance of the buildings of the Viso Housing Group - Blocks 9 to 16 and Towers 1 to 4 (EM.004.2017.083) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 28-07-2017 | 22-10-2018 | 451 | 240 | 840000 | 763562.22 | 2 | 720922.4 | 42639.82 | 105.9146 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 113 day extension | eo in the amount of €3,793.60 and work not carried out in the amount of €46,433.42
3113 | 3571087 | Home of the Five Parishes - S. Miguel do Pinheiro - Mértola | 45215212-6 | Retirement home construction work | FALSE | 2017 | 2020 | Portugal | Mértola | Beja | 2 | 30 | 26-07-2017 | 07-04-2020 | 986 | 450 | 3031879.65 | 2869999.29 | 3 | 823538.32 | 2046460.97 | 348.4961 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Revocation of the Contract) | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | inability to comply with the pace of execution of works by the contractor, with the yields foreseen in the proposal phase not being achieved on the project. inability to mobilize labor and equipment. | more works. underwork
3114 | 3568737 | Extension of the Requalification of street of Maina to the Sports venue - Urgezes | 45233252-0 | Surface work for streets | FALSE | 2017 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 25-07-2017 | 16-04-2018 | 265 | 150 | 531209.86 | 498042.93 | 2 | 496309.26 | 1733.67 | 100.3493 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | following the inspection notice for provisional acceptance (22/12/2017), the contractor had to correct defects in the project, so he was granted a period of 30 days. and following the inspection notice for provisional acceptance (22/01/2018), the contractor had to correct defects in the project, so he was granted a period of another 30 days. | existence of underwork due to not carrying out the quantities of work foreseen in the bill of quantities.
3115 | 3568584 | LED lighting on the IP network | 45316110-9 | Installation of road lighting equipment | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | N/A | 26-07-2017 | 20-04-2018 | 268 | 90 | 2714000 | 1830628 | 3 | 1830628 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was communicated on 11/22/2017.
3116 | 3567601 | Interface of São João da Pesqueira and the Requalification of the Place of the Convent in the village of S. João da Pesqueira | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2018 | Portugal | São João da Pesqueira | Viseu | 20 | 20 | 05-06-2017 | 27-12-2018 | 570 | 320 | 882136.72 | 603161.49 | 2 | 603161.49 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Elementary factors and elementary subfactors, as foreseen in the tender program: Price 70%, Planning 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project had an extension of time requested by the contractor, for reasons related to the cleaning work and final finishing touches for closing the project, it was convenient to carry out the provisional reception after the end date of the project plan and with the delivery of the waste management plan. | the project had a provisional price review and a final price review.
3117 | 3566790 | Requalification of elementary school No. 1 - Chaves - Cino-Chaves Kindergarten | 45454100-5 | Restoration work | FALSE | 2017 | 2018 | Portugal | Chaves | Vila Real | 19 | 30 | 02-08-2017 | 03-05-2018 | 274 | 90 | 416447 | 384990 | 2 | 384990 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension, for a period of 24 days, approved at the board meeting on 11/16/2017.
3118 | 3566195 | Construction of the sports headquarters of Parede Futebol Clube | 45212200-8 | Construction work for sports facilities | FALSE | 2016 | 2019 | Portugal | Cascais | Lisboa | 11 | N/A | 23-02-2017 | 28-08-2019 | 916 | 384 | 1273584.91 | 1134000 | 3 | 1172661.15 | -38661.15 | 96.7031 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline: 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | study changes to introduce to the landscape project, execution of missing works. | pricing review.
3119 | 3565737 | 73/EOP/DCOP/2016 - Contract for the rehabilitation and reconstruction of the Vitória Cine Building (Ludance) Carcavelos | 45453100-8 | Refurbishment work | FALSE | 2016 | 2019 | Portugal | Cascais | Lisboa | 11 | 30 | 18-05-2017 | 09-07-2019 | 782 | 336 | 1179245.28 | 853576.26 | 2 | 853576.26 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline for correcting deficiencies.
3120 | 3564543 | The purpose of the contract is to expand the Fataunços Wastewater System. | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Vouzela | Viseu | 20 | 24 | 24-07-2017 | 25-05-2020 | 1036 | 540 | 205000 | 199954.64 | 1 | 128687.03 | 71267.61 | 155.3806 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the amendment results from the partial suspension of the deadline. | due to underwork.
3121 | 3564462 | Bravães Wastewater Sanitation | 45232400-6 | Sewer construction work | FALSE | 2017 | 2019 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 30 | 31-07-2017 | 02-09-2019 | 763 | 365 | 367834.94 | 289406.64 | 2 | 286981.65 | 2424.99 | 100.845 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | underwork
3122 | 3564055 | "AR-001.2 - Arda Crossing - E.N 222" | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2018 | Portugal | Castelo de Paiva | Aveiro | 1 | N/A | 31-07-2017 | 21-05-2018 | 294 | 150 | 392000 | 363504.74 | 2 | 353517.2 | 9987.54 | 102.8252 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | an extension of 33 calendar days was granted for the following reasons: (1) impossibility of supplying the piping provided for in the contract due to the impossibility of contacting its supplier (steel tse pn40); (2) difficulty in supplying due to the pressure class and reduced length of the ffd pn40 piping; (3) time for analysis, review and approval by the design team of the project adapted in view of constraints (1) and (2); (4) adverse weather conditions | underwork - demolitions not carried out
3123 | 3564035 | Refurbishment of the Municipal Market | 45454000-4 | Restructuring work | FALSE | 2017 | 2019 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 21-07-2017 | 08-02-2019 | 567 | 365 | 365292 | 319387.75 | 2 | 319387.75 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the existence of two monthly fairs, preventing the performance of any task on those dates. the constraint in the fishmonger area, which is permanently in operation, implied interventions. carrying out the entire contract with the market in operation with successive adaptations of the project fronts to the convenience of sellers and users. the fish market space was only vacated by the sellers on 11.14.2018, which made it impossible for the project to progress. | during the course of the project, it was necessary to carry out some complementary work due to unforeseen circumstances, which economically cannot be separated from the project to be built. with regard to underwork, the existing floor must be in good condition.
3124 | 3563655 | Contract for the rehabilitation of streetAntónio Saúde/Largo General Sousa Brandão. | 45233200-1 | Various surface works | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 07-07-2017 | 12-03-2018 | 248 | 90 | 310000 | 273901.99 | 2 | 276676.24 | -2774.25 | 98.9973 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | constraints due to incompatibilities with lisboagás and epal, as well as with the public lighting network. | additional work
3125 | 3563259 | Execution of the contract for "Dune Reconstitution North of Praia do Furadouro and South of Furadouro - Torrão do Lameiro" | 45243000-2 | Coastal-defence works | FALSE | 2017 | 2020 | Portugal | Ovar | Aveiro | 1 | 24 | 27-07-2017 | 07-01-2020 | 894 | 150 | 722154.47 | 587207 | 2 | 589256.35 | -2049.35 | 99.6522 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | change in labor, material or equipment costs during the execution of the project
3126 | 3561674 | OSM-CEB-0088 Execution of branch lines in the water supply and wastewater drainage networks in downtown, within the scope of the Water System of the Northwest Region. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2021 | Portugal | Baião | Viseu | 20 | 20 | 22-06-2017 | 24-11-2021 | 1616 | 730 | 3120000 | 210000.01 | 1 | 274607.85 | -64607.84 | 76.4727 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: A. PRICE - 60%; B. TECHNICAL VALUES - 40% B.1 Work execution methodology - 25%; B.2 Detail and consistency of the Work Plan - 15%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract with 1 renewal | according to renovations and underwork
3127 | 3561476 | 5010027751 - For the execution of the contract called “en109 – km163+550 to km164+430 - requalification” | 45233128-2 | Roundabout construction work | FALSE | 2014 | 2020 | Portugal | Évora | Évora | 7 | 26 | 10-07-2017 | 02-03-2020 | 966 | 150 | 700000 | 652849.37 | 2 | 593114.83 | 59734.54 | 110.0713 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | analysis and adaptation of the execution project taking into account the identified pathologies | adjustments resulting from the intervention solution on the pavement, in the need to demolish a wall and those resulting from the ripping of the guideline for the restoration of access to the industrial zone at roundabout 1
3128 | 3560863 | EMP-R/2/2017 - Contract for the Rehabilitation of Blocks III - Bairro da Nazaré | 45453100-8, 45442110-1, 45313100-5 | Refurbishment work, Painting work of buildings, Lift installation work | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 20 | 07-07-2017 | 28-10-2019 | 843 | 270 | 950000 | 760000.01 | 2 | 759328.31 | 671.7 | 100.0885 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | labor shortage. | capital losses on some paint works.
3129 | 3558600 | Water supply to Coruche (Aguiar da Beira) and Vela (Guarda) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Aguiar da Beira | Guarda | 9 | 48 | 14-07-2017 | 11-07-2018 | 362 | 180 | 300000 | 261553.23 | 2 | 261553.23 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A) Price - 60% B) Technical Value - 40% b.1. Work Execution Methodology - 20% b.2. Detail and consistency of the Work Plan - 10% b.2.1. Work Schedule - 5% b.2.2. Means Plan - 5% b.3. Characterization and quality of equipment and materials - 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3130 | 3558410 | S.e.c. - Procº nº 224/a1/16 - international public tender for the contract award of "requalification, modernization and expansion of the facilities of the frei bartolomeu dos mártires elementary school | 45262800-9 | Building extension work | FALSE | 2017 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 47 | 20-07-2017 | 06-12-2019 | 869 | 540 | 5893000 | 5310990 | 3 | 5304610.77 | 6379.23 | 100.1203 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork.
3131 | 3553258 | 42/Eop/dcop/2016 - contract for completion of the Police building in cascais | 45216111-5 | Police station construction work | FALSE | 2016 | 2020 | Portugal | Cascais | Lisboa | 11 | N/A | 05-04-2017 | 31-08-2020 | 1244 | 480 | 2512616.8 | 1633476.8 | 3 | 2230400.47 | -596923.67 | 73.2369 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 90% Execution time - 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions and suspensions | errors and omissions and price revision
3132 | 3552302 | Repaving and improvement of national road 16, in the section crossing Castelo Mendo / Ponte de S.Roque. | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Almeida | Guarda | 9 | 20 | 25-07-2017 | 06-08-2019 | 742 | 120 | 657728.68 | 498000.01 | 2 | 487885.44 | 10114.57 | 102.0731 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of unforeseen works as well as delays under the responsibility of the contracting firm | underwork, more work and price revisions
3133 | 3551955 | Connection road between streetD. Afonso and streets . Marta, in Arcozelo. | 45232451-8 | Drainage and surface works | FALSE | 2015 | 2019 | Portugal | Barcelos | Braga | 3 | 20 | 24-07-2017 | 04-01-2019 | 529 | 210 | 395460.9 | 355914.82 | 2 | 378478.41 | -22563.59 | 94.0383 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (50%); b) Technical Valuation of the Proposal (50%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Interconnection/compatibility between Work Plans, Manpower Plan, "IC" Equipment Plan (25%). | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of more works in quantity and of different kind carried out on site, climatic reasons - high rainfall, contributed to the alteration of the deadline of the project. start of work: 08/22/2017. end of work: 11/23/2018. | - additional work: referring to work that was carried out in excess of quantity on site, namely, lifting a blue granite cube with an 11cm edge, lifting granite boundary curbs, applying extensive granulometry, applying a layer of sand and blue granite cube paving with an 11 cm edge, in the parking lot, application of a granite kerb to delimit the parking lot and border the landfill, execution of home water supply branches, dn 1 1/2'' and dn 2", opening ditch, stone dust to protect the pipes, final filling of the ditch and transport of leftover products and reinforced concrete pipes to the dump, dn 600mm and dn 700mm of the rainwater drainage network, application of forks in pp sn8, execution of home branches and complete intercepting boxes of the wastewater drainage network. - work of a different kind: referring to work that was not contractually agreed on site, namely demolition of the existing concrete collector, dn 600mm and dn 70mm, civil construction work in the manholes, backfilling the ditch with granular material or gravel and cost of shipyard. - underwork: referring to work that was not carried out on site, namely, the application of litter bins, bicycle storage, pvc meter boxes and cable connection in the transformer station switchboard, and work that was carried out in smaller quantities such as the application of grooves in polymer concrete.
3134 | 3551636 | Construction of the Barbacena and S. Vicente WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2016 | 2019 | Portugal | Elvas | Portalegre | 12 | 48 | 07-07-2017 | 13-03-2019 | 614 | 360 | 800000 | 752160 | 2 | 739493.16 | 12666.84 | 101.7129 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension requested by the contractor to complete the project. | changes in the value of the project result from works that are less indicated and from the provisional price revision.
3135 | 3551377 | 5010028890 - En 255, km 121+173, bridge over ravine of almond / at 265, km 016+239, bridge over ravine of retort rehabilitation and reinforcement of works of art | 45221119-9 | Bridge renewal construction work | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 26 | 25-07-2017 | 13-11-2019 | 841 | 135 | 240000 | 169995.26 | 1 | 162164.17 | 7831.09 | 104.8291 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% - Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | works to supply negative errors and omissions in the amount of €7,831.09 were determined
3136 | 3549499 | Contract No. 24/2017 - Contract "Expansion of the Calvão Sanitation and WWTP Network" | 45232410-9 | Sewerage work | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 14-07-2017 | 17-09-2019 | 795 | 180 | 457400 | 398152.5 | 2 | 335584.36 | 62568.14 | 118.6445 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 2 term extension for a period of 180 days (90 + 90) | underwork worth €64,500.00
3137 | 3548850 | 1-Emp/17 - Contract for the conservation and improvement of the county's road network - Ponte dos Descobrimentos, Atalaia and Vale Caranguejo, Tavira | 45233220-7 | Surface work for roads | FALSE | 2017 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 12-07-2017 | 24-10-2019 | 834 | 150 | 344500 | 294331.6 | 2 | 294023.79 | 307.81 | 100.1047 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions and delay in delivering the technical compilation. | negative price review.
3138 | 3547148 | Infrastructure contract for enhancing and visiting the Neiva River estuary - pedestrian and cycle bridge | 45221113-7 | Footbridge construction work | FALSE | 2016 | 2020 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 48 | 22-06-2017 | 16-03-2020 | 998 | 180 | 435000 | 409993.32 | 2 | 395524.44 | 14468.88 | 103.6582 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price: 30% b) Technical Quality of the Proposal: 70% b.1) Descriptive and Justification: 35% b.2) Work Plan: 20% b.3) Occupational Health and Safety Management: 15% | 1 | 30 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | causes of changes to the term of execution of the project there was a significant delay due to the difficulty in subcontracting the task of carrying out molded piles, due to an abnormal volume of requests to this type of company, very specific and with a very small market, which did not allow finding a company available to carry out this task. work on the dates set out in the project plan. the last months of 2017 and the first 4 months of 2018 (especially) were subject to very adverse weather conditions, which caused several floods on the banks of the river and destroyed work already carried out within the scope of the project, in addition to making access to the project impassable, which resulted in sub-income due to both the specificity and the complexity of the project. the execution of the project coincided with a phase of exponential growth in the number of works in the country, which implied great difficulty in hiring labour, equipment and the delivery of materials by suppliers, even considering the specificity and complexity of the project.
3139 | 3546436 | Contract for "Galizes wastewater subsystem" | 45232420-2 | Sewage work | FALSE | 2017 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | N/A | 25-07-2017 | 28-12-2018 | 521 | 150 | 300000 | 230148.87 | 1 | 200200.79 | 29948.08 | 114.959 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspensions | underwork
3140 | 3543406 | Requalification of the area that integrates the Main Church, theelementary school2,3 School of Souselo and the Commercial Space | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | Cinfães | Viseu | 20 | 20 | 21-07-2017 | 04-10-2019 | 805 | 120 | 501540.39 | 396548.01 | 2 | 386814.33 | 9733.68 | 102.5164 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climacteric | over and underwork
3141 | 3543088 | Conservation and improvement works on the municipality's road network - streetf. Sá Carneiro, street25 de Abril, Urb. Asseca and EM 508 | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Tavira | Faro | 8 | 24 | 12-07-2017 | 21-01-2020 | 923 | 150 | 282000 | 239232.89 | 1 | 238871.92 | 360.97 | 100.1511 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in provisional reception due to non-delivery of the technical compilation. | price review
3142 | 3541436 | Complementary Wastewater Networks - Sector II | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2020 | Portugal | Lousada | Porto | 13 | 20 | 19-07-2017 | 06-04-2020 | 992 | 360 | 537000 | 455834.68 | 2 | 415567.64 | 40267.04 | 109.6896 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions. | underwork.
3143 | 3541367 | CP02/2016/GIE - Contract for the refurbishment of the Feira Nova Health Unit_x000D_ | 45454000-4 | Restructuring work | FALSE | 2017 | 2018 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 14-07-2017 | 19-02-2018 | 220 | 150 | 584284.3 | 537100.88 | 2 | 537100.88 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70% B - Technical value of the proposal 30%: B1 - Descriptive memory 10% B2 - Work, labor, equipment and payment plans 10% B3 - Safety to be implemented in the work (technical note) 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3144 | 3537651 | Construction of pedestrian pathways, with replacement of the water network, execution of a storm sewerage network and laying of granite pavement. | 45233161-5 | Footpath construction work | FALSE | 2017 | 2019 | Portugal | Nisa | Portalegre | 12 | 30 | 14-07-2017 | 13-05-2019 | 668 | 365 | 213483.5 | 193451.84 | 1 | 195557.44 | -2105.6 | 98.9233 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the project deadline. | definitive price review worth €2105.60
3145 | 3537581 | Contract 2/GEBALIS/2017 - Public tender Maintenance and Repair of Fires and Common Areas in Neighborhoods of the West Zone, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Lisboa | Lisboa | 11 | 20 | 19-07-2017 | 20-12-2019 | 884 | 730 | 600000 | 565800 | 2 | 565800 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | TRUE | N/A | work went smoothly/on schedule
3146 | 3533516 | Water distribution projects - rabagão subsystem | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Fafe | Braga | 3 | 30 | 14-07-2017 | 20-05-2019 | 675 | 180 | 608632.08 | 409301.55 | 2 | 403398.44 | 5903.11 | 101.4633 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical Valuation and Warranty Proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | the quantities provided for some items were not carried out
3147 | 3533347 | Requalification and improvement of the municipal swimming pools building. | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2017 | 2018 | Portugal | Barcelos | Braga | 3 | 9 | 18-07-2017 | 13-03-2018 | 238 | 90 | 564608.45 | 563605.8 | 2 | 554949.2 | 8656.6 | 101.5599 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | at the tenderer's request. | due to the existence of underwork.
3148 | 3532546 | Rehabilitation of Tondela High school 1st Phase | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2021 | Portugal | Tondela | Viseu | 20 | 20 | 12-07-2017 | 29-03-2021 | 1356 | 488 | 1076000 | 885058.37 | 2 | 982566.37 | -97508 | 90.0762 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | derived from suspensions and extensions. | more work, underwork and price revision.
3149 | 3532429 | Urban Requalification of the Center of Salvador | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Penamacor | Castelo Branco | 5 | 11 | 20-07-2017 | 10-07-2019 | 720 | 210 | 180546.88 | 168790.11 | 1 | 193776.6 | -24986.49 | 87.1055 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed on may 4, 2018. delay on the part of the contractor. | additional works at contract prices amounting to €24,405.04; additional work at prices to be agreed in the amount of €11,047.02; underwork in the amount of €11,314.26; price revision in the amount of €848.69.
3150 | 3530951 | The intervention concerns the execution of the Requalification of the EN 329-2, in the section between the towns of Póvoa de Cervães (Km 0+000) and Abrunhosa-a-Velha (Km 4+200). | 45233140-2 | Roadworks | FALSE | 2017 | 2020 | Portugal | Mangualde | Viseu | 20 | 21 | 19-07-2017 | 09-01-2020 | 904 | 270 | 831440 | 748296.01 | 2 | 719404.36 | 28891.65 | 104.0161 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | as per information in the process. | underwork according to information in the process.
3151 | 3528760 | Restoration of pavements, sidewalks and sanitation. | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Cartaxo | Santarém | 16 | N/A | 18-07-2017 | 28-09-2020 | 1168 | 90 | 349967.65 | 279974.13 | 2 | 314494.21 | -34520.08 | 89.0236 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | price revision amount
3152 | 3525839 | The object of the present procedure consists of the rehabilitation of the accessibility of Municipal and Rural roads in several roads of the municipality, comprising the replacement of the initial circulation solutions… | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 36 | 04-07-2017 | 08-03-2018 | 247 | 183 | 430494.9 | 349954.9 | 2 | 349954.9 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no extension of the deadline.
3153 | 3524532 | Improvement of Municipal Road n.º 1016 from Vinhais to Armoniz | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Vinhais | Bragança | 4 | 30 | 07-07-2017 | 18-01-2019 | 560 | 270 | 426000 | 318515 | 2 | 319055.23 | -540.23 | 99.8307 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (Weighting 80%) Technical value of the proposal (Weighting 20%) | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the lead time has not changed | price review
3154 | 3522822 | Rehabilitation of the exterior surroundings, including walls, and common spaces in Bairro de S. Gonçalo, guimarães | 45453100-8 | Refurbishment work | FALSE | 2016 | 2020 | Portugal | Guimarães | Braga | 3 | 30 | 27-06-2017 | 23-09-2020 | 1184 | 210 | 500000 | 397093.79 | 2 | 419965.04 | -22871.25 | 94.554 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The most economically advantageous proposal having into account the following factors with the following weighting: Price..................................................80% Technical value of the proposal.....20% a) Price factor: evaluated according to the application of the following formula: Cprice i = 20 - 10 x (Pi/Vb) On what: Cprice i- Score value of the competitor's proposal Vb-Base value of the tender Pi- Competitor's bid price b) Technical value factor of the proposal, evaluated with the following subfactors: Planning (Pli) -50% Proposal evaluation criteria: Schedule of activities not very explicit and without definition of precedence of activities.................................................. ...... 10 Very explicit schedule of activities and with definition of precedence of activities.................................................. .............15 Very explicit and detailed schedule of activities with definition of precedence of activities and accompanied by Memory Descriptive and well-founded justification.........20 Construction processes (Pci) -50% Proposal evaluation criteria: Descriptive Memory and Justification of the Mode of Execution of the Work incoherent and with little or no adherence to the constructions................................................. .......10 Descriptive Memory and Justification of the Mode of Execution of the Work generic, but compatible with the notebook of charges .....................................................................15 Descriptive Memory and Justification of the Mode of Execution of the Work well structured in function of the specificity of the work..................................20 | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions; need to adapt the project to stocks taking into account the long gap since the survey of the pathologies (execution project) and the start of the project on the contract; difficulties in articulating with tenants to carry out work within the units; need to perform more work. | redefinition of the quantification of the project to be carried out taking into account the time lag between the preparation of the project and the execution of the contract (worsening of the pathologies initially identified).
3155 | 3522721 | CB 1109 Rehabilitation of the exterior surroundings, including walls, roof and common spaces in the Quinta da Marinha neighborhood – Espinho | 45453100-8 | Refurbishment work | FALSE | 2016 | 2020 | Portugal | Espinho | Aveiro | 1 | 30 | 20-06-2017 | 30-01-2020 | 954 | 210 | 590000 | 499290.96 | 2 | 542634.46 | -43343.5 | 92.0124 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The most economically advantageous proposal having into account the following factors with the following weighting - Price..................................................80% Technical value of the proposal.....20% a) Price factor: evaluated according to the application of the following formula: Cprice i = 20 - 10 x (Pi/Vb) On what: Cprice i- Score value of the competitor's proposal Vb-Base value of the tender Pi- Competitor's bid price b) Technical value factor of the proposal, evaluated with the following sub-factors: Planning (Pli) -50% Proposal evaluation criteria: Schedule of activities not very explicit and without definition of precedence of activities.................................................. .............10 Very explicit schedule of activities and with definition of precedence of activities.................................................. ......15 Very explicit and detailed schedule of activities with definition of precedence of activities and accompanied by Memory Descriptive and well-founded justification ...................20 Construction processes (Pci) -50% Proposal evaluation criteria: Descriptive Memory and Justification of the Mode of Execution of the Work incoherent and with little or no adherence to the constructions................................................. ...... 10 Descriptive Memory and Justification of the Mode of Execution of the Work generic, but compatible with the notebook of charges................................................. ...15 Descriptive Memory and Justification of the Work Execution Mode well structured according to the specificity of the work...................20 | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the alteration to the execution period of the contract was due to the 2 dispatches issued by the cd, authorizing the extension by 180 days of the period for the execution of the contract, | the alterations to the value of the contract were due to the need to redefine the quantification of the project to be carried out, taking into account the time lag between the preparation of the project and the execution of the contract. underwork, more work, and price revisions.
3156 | 3522048 | Rehabilitation of the "envelope" and installation of an energy system (solar) in Blocks 1 and 2 of the Falcão Municipal Public Housing Complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 17-07-2017 | 28-02-2018 | 226 | 210 | 950000 | 908012.07 | 2 | 888852.7 | 19159.37 | 102.1555 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractually foreseen. | eo in the amount of €1,635.50 and underwork in the amount of €20,794.87
3157 | 3517278 | 5010032423/R.r - c.o.s/2017 - contract called "placement of road retention systems 2015 - batch vi" | 45233292-2 | Installation of safety equipment | FALSE | 2015 | 2019 | Portugal | N/A | N/A | N/A | 56 | 03-07-2017 | 07-12-2019 | 887 | 180 | 3000000 | 297495.06 | 2 | 306594.71 | -9099.65 | 97.032 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor informed of the difficulties he was experiencing vis-à-vis the suppliers, since the supplying factories had closed during the month of august, so that only in october would they be able to supply the material to start the related works. the drama of the fires that hit the center of the country, both that summer and in october, contributed to the fact that it was only on october 24 that the contractor, specialized in road safety, had the conditions to enter the land, since he was an active part in the recovery of the affected area. | the change in the value of the project was due to the calculation of more work in the amount of €46,648.80, work to correct errors and positive omissions in the amount of €14,860.00, underwork in the amount of €59,671.18 € and final price revision in the amount of €7,262.03
3158 | 3514776 | Rehabilitation of the "envelope" of Block 7 and telecommunications infrastructure (ITUR) in the Bom Pastor Municipal Public Housing complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 06-07-2017 | 07-05-2018 | 305 | 210 | 750000 | 593377.09 | 2 | 582129.18 | 11247.91 | 101.9322 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 80% and Technical Valuation of the Proposal 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | eo in the amount of €8,234.02, work not carried out in the amount of €19,481.93
3159 | 3513981 | EGA-EB0016 - Gondar Wastewater Drainage Network - 2nd and 3rd Phase (Amarante) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Amarante | Porto | 13 | 50 | 28-06-2017 | 08-10-2018 | 467 | 270 | 700000 | 648803.65 | 2 | 533971.52 | 114832.13 | 121.5053 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the above | there was no need to perform all contract project
3160 | 3513909 | This contract comprises the works of: Demolitions; preparatory work; pedestrian and cycle pavements; placement of curbs; fences; horizontal signage; plantations; irrigation network | 45112700-2 | Landscaping work | FALSE | 2017 | 2018 | Portugal | Barreiro | Setúbal | 17 | 20 | 28-04-2017 | 12-06-2018 | 410 | 90 | 200000 | 180009.72 | 1 | 212476.59 | -32466.87 | 84.7198 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | continuity of work on connections to the pluvial network, until obtaining the proper authorization from infraestruturas de portugal
3161 | 3513824 | The work includes the following works: - Demolitions and preparatory work; - Pedestrian and cyclable pavements; - Supply and placement of curbs; - Execution of concrete walls - Supply | 45112700-2 | Landscaping work | FALSE | 2017 | 2018 | Portugal | Barreiro | Setúbal | 17 | 20 | 11-07-2017 | 29-10-2018 | 475 | 90 | 190000 | 169958.86 | 1 | 169958.86 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractor default
3162 | 3513417 | EGA-EB0118 - Water Supply Infrastructure in Gestaçô and Tresouras and Sanitation in Gestaçô and Frende (Baião)". | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Baião | Porto | 13 | 50 | 11-07-2017 | 21-12-2018 | 528 | 270 | 620000 | 496000 | 2 | 425619.01 | 70380.99 | 116.5361 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50% Technical Valuation of the Proposal: 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in issuing a license to carry out work on the en108 and difficulties during the project (equipment breakdowns, adverse weather conditions and the appearance of rock that is difficult to dismantle). | there was no need to carry out all the contractual work, namely work to replace the bituminous pavement.
3163 | 3512574 | Rehabilitation of the "envelope" of Block 10 of the Bom Pastor Municipal Public Housing complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 06-07-2017 | 09-10-2018 | 460 | 180 | 800000 | 779985 | 2 | 769383.84 | 10601.16 | 101.3779 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 80% and Technical Valuation of the Proposal 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
3164 | 3511972 | EGA-AA0141 - Replacement of the Pipeline between CPC 3 and the Cumieira Reservoir (SAA Sordo) - Municipalities of Vila Real and Santa Marta de Penaguião | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2018 | Portugal | Sta Marta de Penaguião | Vila Real | 19 | 20 | 21-06-2017 | 11-05-2018 | 324 | 60 | 400000 | 377632.91 | 2 | 371793.27 | 5839.64 | 101.5707 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | wrong registration led to more surveys being carried out than expected, which caused a decrease in the expected income. alteration of accessories foreseen in the connection of profile i. | underwork resulting from the reduction of curves necessary for the installation of the pipeline
3165 | 3511355 | This contract is intended to supply water to the villages of Quintas and Silvares in the parish of Cota. | 45232460-4 | Sanitary works | FALSE | 2016 | 2018 | Portugal | Viseu | Viseu | 20 | 42 | 03-07-2017 | 28-11-2018 | 513 | 292 | 326495.38 | 287136.14 | 2 | 282159.07 | 4977.07 | 101.7639 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 21.00%; Price - 75.00%; Lead time - 4.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the contractual period. | the final value of the project was below the award value.
3166 | 3511116 | Ribeirada Urban Park - Odivelas | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2019 | Portugal | Odivelas | Lisboa | 11 | 20 | 06-07-2017 | 09-07-2019 | 733 | 120 | 260000 | 222794.71 | 1 | 221358.31 | 1436.4 | 100.6489 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Item 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project. | the project had underwork worth €1,436.40, referring to work not carried out.
3167 | 3509915 | EGA-EB0105 - Water Supply and Wastewater Drainage Networks in the Parish of Espadanedo - Municipality of Cinfães | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2020 | Portugal | Cinfães | Viseu | 20 | 47 | 28-06-2017 | 05-11-2020 | 1226 | 420 | 1900000 | 1416921.63 | 3 | 937205.39 | 479716.24 | 151.1858 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a protocol entered into with the municipality of cinfães regarding the paving of the intervened roads seriously conditioned the progress of the project, causing delays in the completion of the contract. | protocol entered into with the municipality of cinfães resulted in underwork related to paving in the contract, as well as the suppression of part of the network to be executed.
3168 | 3509548 | EGA-EB0106 - Water Supply and Wastewater Drainage Networks in the Parish of Tarouquela - Municipality of Cinfães | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2020 | Portugal | Cinfães | Viseu | 20 | 47 | 28-06-2017 | 01-09-2020 | 1161 | 420 | 2350000 | 1826032.62 | 3 | 1394600.61 | 431432.01 | 130.9359 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to reverse the projects foreseen in the initial contract in order to increase the extensions of the water and sanitation networks, starting to serve a greater number of inhabitants with the extension of the water and sanitation networks initially foreseen; as a way of not increasing projected costs, some paving work on municipal streets was removed from the contract and became the responsibility of the municipality. circumstances elapsed from the prolotolo entered into on july 21, 2017 between the municipality of cinfães and adnorte. in a first approach, the possibility had been considered of not building two pumping stations; however, there was a later need to maintain the construction of the three pumping stations initially planned, without which the wastewater system would not be able to function. the alterations introduced in the object of the contract caused constraints on the development of the projects of the contract, making it necessary to wait for the city council to proceed with the opening of the procedure for the paving works, as well as to wait for the teams hired by the city council to carry out the survey prior to the sidewalks, thus making it impossible to carry out work on opening ditches, installing conduits and closing ditches. | as explained in the previous point, underwork resulted in the amount of €535,529.05. there was a need to carry out complementary work in the final phase of the project, namely to carry out reconstruction work on a mine that appeared at a depth of about 10.00 meters, in the area where the sanitation collector is located, as a way of guaranteeing conditions of security, or for the infrastructure built for users, in general, amounting to a total of €23,445.61
3169 | 3508789 | Construction contract for the Marginal Road connecting Santa Clara to Relva - 2nd Phase | 45233120-6 | Road construction works | FALSE | 2016 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 36 | 30-06-2017 | 22-11-2019 | 875 | 240 | 2120000 | 1604040.06 | 3 | 1718156.88 | -114116.82 | 93.3582 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: These are those listed in article 18 of the program of competition | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspensions and term extensions. | underwork and price revision.
3170 | 3507652 | The object of the contract is to carry out the work defined as to its type, quantity and technical conditions of execution, in the project and in the specifications | 45453100-8 | Refurbishment work | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 21 | 03-07-2017 | 07-01-2019 | 553 | 490 | 673578.67 | 572542.08 | 2 | 576067.01 | -3524.93 | 99.3881 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.45 * Pi + 0.55 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / (Base Price)) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the work to be perform - QAi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the work to be carried out - QAi = 60 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail - QAi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest - QAi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities - PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities - PTi = 60 - Presents a poorly detailed Work Plan, making it difficult to analyze the development of the work to be carried out - PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out - PTi = 0 The formula to be applied will be: VTi = QAi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; QAi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: - In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; - Thirdly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | provisional price revision worth €3,524.93
3171 | 3505679 | Improvement of EM from street of Igreja (Cernadelo) to EM 564-2 (Macieira) | 45233140-2 | Roadworks | FALSE | 2017 | 2019 | Portugal | Lousada | Porto | 13 | 21 | 28-06-2017 | 01-04-2019 | 642 | 120 | 464290.04 | 439403.51 | 2 | 433715.02 | 5688.49 | 101.3116 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions that made it impossible to carry out paving work; delays in the transfer of land; lack of definition of work related to the sanitation network | underwork / price review
3172 | 3505294 | Rehabilitation of the "envelope" and installation of an energy system (solar) in Blocks 7 and 9 of the Municipal Public Housing Complex of Falcão (EM.004.2017.058) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 06-07-2017 | 23-05-2018 | 321 | 210 | 850000 | 732549.87 | 2 | 698984.74 | 33565.13 | 104.802 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in accordance with the contractual provisions | work not carried out worth €33,565.13
3173 | 3505001 | Refurbishment of the facade of the municipal stadium of Alpendorada - Sports Complex of Alpendorada | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2017 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 20 | 30-06-2017 | 17-01-2019 | 566 | 150 | 528300.54 | 517503.61 | 2 | 79987.02 | 437516.59 | 646.9845 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract revocation agreement pursuant to the provisions of articles 330.º, paragraph b) and 331.º of the "public procurement code" | contract revocation agreement pursuant to the provisions of articles 330.º, paragraph b) and 331.º of the "public procurement code"
3174 | 3504026 | Improvement, rehabilitation of the municipal road network and reinforcement of bituminous pavements with the execution of a cold bituminous surface layer and ancillary works, municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 06-07-2017 | 11-07-2018 | 370 | 90 | 368320 | 293309.05 | 2 | 293309.05 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was suspended
3175 | 3503054 | OSM-CEB-0088 Execution of branches in the water supply and wastewater drainage networks in Baixa - Municipalities of Amarante and Celorico de Basto - Lot 1 | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2021 | Portugal | Celorico de Basto | Porto | 13 | 20 | 22-06-2017 | 24-11-2021 | 1616 | 730 | 3120000 | 600000.01 | 2 | 467405.71 | 132594.3 | 128.3681 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: A. PRICE - 60%; B. TECHNICAL VALUES - 40% B.1 Work execution methodology - 25%; B.2 Detail and consistency of the Work Plan - 15%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract signed with 1 renewal | according to renovations and underwork
3176 | 3501230 | Maintenance Dredging of the Port of Aveiro | 45252124-3 | Dredging and pumping works | FALSE | 2017 | 2020 | Portugal | Ílhavo | Aveiro | 1 | 21 | 06-07-2017 | 08-01-2020 | 916 | 913 | 1645000 | 1463000 | 3 | 1501851.36 | -38851.36 | 97.4131 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 0.65; Performance Quality Assurance: 0.35. | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the maximum amount of dredgers foreseen was extinguished before the end of the contractual term. | the above mentioned
3177 | 3495941 | Repaving of streetNossa Senhora da Graça, Parish of Covoada and Paving of Canada and crossstreet of Abelheira, Parish of Capelas, Ponta Delgada | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 23 | 05-07-2017 | 02-11-2018 | 485 | 60 | 205000 | 204000 | 1 | 204000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project.
3178 | 3495382 | Extension of Basic Sanitation in the Parish of Silgueiros | 45232460-4 | Sanitary works | FALSE | 2017 | 2019 | Portugal | Viseu | Viseu | 20 | 42 | 23-06-2017 | 25-03-2019 | 640 | 292 | 315445.36 | 291731.24 | 2 | 263828.23 | 27903.01 | 110.5762 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 21.00%; Price - 75.00%; Lead time - 4.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of land availability, bad weather conditions and contractor delay. | the value of the project carried out was below the value of the award.
3179 | 3495221 | Construction of the Torrão WWTP | 45232421-9 | Sewage treatment works | FALSE | 2017 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 28-06-2017 | 29-11-2019 | 884 | 150 | 348193.8 | 298016.49 | 2 | 310781.82 | -12765.33 | 95.8925 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work, paragraph b) of article 365 of the "public procurement code". | more work worth 14,891.33 and underwork worth 2,126.00.
3180 | 3494759 | Requalification of the Praça elementary school - Macieira de Cambra | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 19-04-2017 | 15-02-2018 | 302 | 180 | 427754.04 | 384954.89 | 2 | 379544.35 | 5410.54 | 101.4255 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there is not. | there is not.
3181 | 3494618 | Improvement of the municipal road network - Estrada Alfandanga - Moncarapacho - [EM 516-2] | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Olhão | Faro | 8 | 30 | 12-04-2017 | 24-07-2018 | 468 | 120 | 500000 | 430065.2 | 2 | 430065.2 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays by the contractor
3182 | 3494585 | Contract for the Rehabilitation and Structural Reinforcement of the section of the Pegões Aqueduct in Tomar | 45454000-4 | Restructuring work | FALSE | 2017 | 2019 | Portugal | Tomar | Santarém | 16 | 30 | 04-07-2017 | 18-02-2019 | 594 | 180 | 402000 | 308860.71 | 2 | 333752.8 | -24892.09 | 92.5418 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractual execution period, with the provisional acceptance being scheduled after its completion, given the availability of the representative of the dgpc | reinforcement of the resistant capacity of the pillar shoes and their stabilization.
3183 | 3492732 | Hotel Construction Contract | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2016 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 47 | 30-06-2017 | 16-09-2019 | 808 | 610 | 20715000 | 15536250.01 | 3 | 15928573.37 | -392323.36 | 97.537 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (60% weighting) b) Technical value (40% weighting) | 1 | 60 | N/A | TRUE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A | readjustments to the contract projects. | readjustments to the contract projects, which resulted in more associated works.
3184 | 3488358 | The object of this contract is the execution of the sanitation network in the Parish of Vila Verde | 45232460-4 | Sanitary works | FALSE | 2017 | 2018 | Portugal | Vila Verde | Braga | 3 | 24 | 05-07-2017 | 22-10-2018 | 474 | 365 | 310342.41 | 253960.06 | 2 | 253285.04 | 675.02 | 100.2665 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to study changes to the development of the contract, namely the unavailability of repaving the section of estrada nacional 308 | underwork
3185 | 3488032 | Earthmoving, Drainage and Accessories and Paving | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2018 | Portugal | Mogadouro | Bragança | 4 | 14 | 29-06-2017 | 26-02-2018 | 242 | 120 | 301310 | 271025.25 | 2 | 271025.25 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: refer to point 16 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of signaling
3186 | 3487374 | The object of this contract is the completion of the urban requalification of S. Sebastião square in Prado | 45233200-1 | Various surface works | FALSE | 2017 | 2018 | Portugal | Vila Verde | Braga | 3 | 24 | 05-07-2017 | 21-11-2018 | 504 | 120 | 212418.14 | 175000.01 | 1 | 169054.96 | 5945.05 | 103.5166 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | non-execution of work on some articles
3187 | 3484360 | The intervention is due to the fact that the existing network does not cover the entire population of São Bento do Cortiço, as well as the implementation of a Domestic Wastewater Treatment Plant | 45232460-4 | Sanitary works | FALSE | 2017 | 2020 | Portugal | Estremoz | Évora | 7 | 20 | 26-06-2017 | 17-01-2020 | 935 | 365 | 764272.55 | 697000 | 2 | 697000 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price = 50% Sub factors: | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3188 | 3484149 | Repairs to social housing properties owned by the municipality of Portalegre | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2018 | Portugal | Portalegre | Portalegre | 12 | 30 | 30-06-2017 | 18-10-2018 | 475 | 90 | 361945 | 313750 | 2 | 310075 | 3675 | 101.1852 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the difficulty of availability of residents and adverse weather conditions
3189 | 3484025 | Conservation Works at the Municipal Library | 45453100-8 | Refurbishment work | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 05-06-2017 | 04-06-2019 | 729 | 180 | 237298.5 | 230989.27 | 1 | 240618.49 | -9629.22 | 95.9981 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | pss approval, additional contract and due to keep space in use. | additional contract, underwork and price revision.
3190 | 3480242 | The object of this contract is the construction of a reservoir supported by À-dos-Ferreiros with a capacity of 800 m3, a chlorination water treatment plant, a pumping station | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2018 | Portugal | Águeda | Aveiro | 1 | N/A | 27-06-2017 | 18-10-2018 | 478 | 365 | 1500000 | 974386.96 | 2 | 974386.96 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: A- PRICE: 55% B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3191 | 3480019 | The object of this contract is the construction of a water supply network in an extension of about 6,000.00 meters and 80 home branches | 45232100-3 | Ancillary works for water pipelines | FALSE | 2017 | 2018 | Portugal | Águeda | Aveiro | 1 | N/A | 22-06-2017 | 17-07-2018 | 390 | 120 | 245000 | 236916.52 | 1 | 216637.34 | 20279.18 | 109.3609 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3192 | 3479030 | It consists of repairing and upgrading the streets and respective surroundings located in the southern part of the municipality, covering the parishes of Alfragide, Águas Livres and Venteira. | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 29-06-2017 | 16-01-2019 | 566 | 355 | 281975 | 247631.76 | 1 | 250818.47 | -3186.71 | 98.7295 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100; - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 65; - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi = 30; - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi = 0. b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi = 100; - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi = 65; - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi = 30; - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out: PTi = 0; The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - diversity/deployment of work required in various locations; - multiplicity of interactions with the affected services; - adverse weather conditions. | definitive price revision worth €3,186.71
3193 | 3478003 | Repaving of B.º das Maroitas in São João da Talha and B.º das Courelas in Santa Iria de Azóia | 45233222-1 | Paving and asphalting works | FALSE | 2017 | 2018 | Portugal | Loures | Lisboa | 11 | 15 | 14-06-2017 | 08-11-2018 | 512 | 35 | 344185.55 | 223642.1 | 1 | 223642.1 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made according to the criterion of most economically advantageous proposal, as defined in point 19 of the Tender Programme. In case of a tie, it will be used as a tiebreaker the proposal with the lowest price. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3194 | 3475405 | It consists of the execution of a set of small works for the requalification of outdoor spaces/green areas, scattered throughout the central zone of the municipality of Amadora | 45112710-5 | Landscaping work for green areas | FALSE | 2017 | 2020 | Portugal | Amadora | Lisboa | 11 | 30 | 23-06-2017 | 09-07-2020 | 1112 | 355 | 281943 | 239651.56 | 1 | 242374.67 | -2723.11 | 98.8765 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 65 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi = 65 - Presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out: PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the tiebreaker will be based on the following criteria, rounding to the second place decimal: - Firstly, the proposal that obtained the lowest value in chapter 7 of the Unit Price List will be considered; - Secondly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deviation/delay was due to adverse weather conditions. | definitive price revision worth €2,723.11
3195 | 3473175 | Design-construction of the Sever do Vouga urban wastewater treatment plant, including: a) The provision of the execution project and the construction of the corresponding treatment stages | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2021 | Portugal | Sever do Vouga | Aveiro | 1 | N/A | 26-09-2016 | 22-03-2021 | 1638 | 730 | 2950000 | 2488926.05 | 3 | 2474103.23 | 14822.82 | 100.5991 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Technical value of the proposal - 60% 2) Price - 40% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3196 | 3473072 | It consists of the complete removal of the existing asbestos cement ribs and their replacement with sandwich panels, the complete removal of the existing window frames and their replacement and the complete painting of the buildings. | 45453100-8 | Refurbishment work | FALSE | 2017 | 2018 | Portugal | Amadora | Lisboa | 11 | 21 | 22-06-2017 | 24-08-2018 | 428 | 490 | 326602 | 277612.6 | 2 | 277612.6 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.45 * Pi + 0.55 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / (Base Price)) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the work to be perform - QAi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the work to be carried out - QAi = 60 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail - QAi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest - QAi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities - PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities - PTi = 60 - Presents a poorly detailed Work Plan, making it difficult to analyze the development of the work to be carried out - PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out - PTi = 0 The formula to be applied will be: VTi = QAi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; QAi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: - In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; - Thirdly, the proposal that obtained the lowest value in chapter 1 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was possible to strengthen teams, minimizing impacts on school functioning.
3197 | 3472761 | The purpose of the contract is to carry out work defined in terms of its type, quantity and technical conditions of execution, in the Project and in the Specifications | 45453100-8 | Refurbishment work | FALSE | 2017 | 2018 | Portugal | Amadora | Lisboa | 11 | 21 | 26-06-2017 | 10-09-2018 | 441 | 490 | 434161.57 | 369037.36 | 2 | 369037.36 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.45 * Pi + 0.55 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / (Base Price)) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the work to be perform - QAi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the work to be carried out - QAi = 60 - Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail - QAi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest - QAi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities - PTi = 100 - Presents a Work Plan with a correct sequence, with some detail of the work to be carried out, allowing thus an interpretation of the interconnection between activities - PTi = 60 - Presents a poorly detailed Work Plan, making it difficult to analyze the development of the work to be carried out - PTi = 30 - It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out - PTi = 0 The formula to be applied will be: VTi = QAi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; QAi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: - In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; - Thirdly, the proposal that obtained the lowest value in chapter 2 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the compatibility and articulation with the use of the different school spaces targeted by the intervention, made it possible for the project not only to be carried out during holiday periods, which allowed the incorporation of the necessary teams by the contractor to minimize the project time.
3198 | 3471781 | Execution of the Sanitation Network in Mosca | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Bragança | Bragança | 4 | 30 | 08-06-2017 | 28-05-2018 | 354 | 180 | 465000 | 279077 | 2 | 265958.73 | 13118.27 | 104.9324 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60.00%; Technical quality of the proposal - 40.00%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work due to edp intervention. | underwork.
3199 | 3470051 | Cycling corridor aljustrel - vale d`´oca/algares/plano neighborhoods | 45233162-2 | Cycle path construction work | FALSE | 2017 | 2018 | Portugal | Aljustrel | Beja | 2 | 30 | 26-06-2017 | 06-11-2018 | 498 | 180 | 444000 | 389860.1 | 2 | 359023.94 | 30836.16 | 108.5889 | Lowest priceDiary of the Republic, 2nd series - N.º 13 - January 18, 2017 - Announcement rectification statement n.º 15/2017 - Page n.º 3 | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor requested an extension of the term for another 60 days, which, by decision of 01/17/2018, was not granted. by order of 02/15/2018 by mr. president of the chamber, ratified at a meeting on 02/28/2018, was dispatched to apply clause 11 of the general clauses of the terms of reference - fines for breach of contractual deadlines, a sanction that was subsequently annulled by resolution of 10/ 10/2018, given the reasons invoked by the contractor. | existence of underwork and provisional calculation of the price revision.
3200 | 3466481 | Expansion and remodeling of the E. B. 1 Conde s. Cosme (Sede nº 1) - Union of the parishes of V. N. De Famalicão and Calendar | 45214210-5 | Primary school construction work | FALSE | 2017 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 26-06-2017 | 29-03-2019 | 641 | 365 | 870000 | 760639.09 | 2 | 701361.23 | 59277.86 | 108.4518 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price: 60% and Technical Valuation of the Proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two graceful extensions of 39 and 43 days respectively. | there were underwork and price revisions, according to values ​​already described.
3201 | 3463633 | Construction of a continuous pedestrian corridor between Km 3,200 and Km 6,900 (right side) of the EN 15, partly as a sidewalk and partly delimited by traffic deterrents. | 45233161-5 | Footpath construction work | FALSE | 2017 | 2021 | Portugal | Valongo | Porto | 13 | 24 | 14-06-2017 | 08-04-2021 | 1394 | 150 | 223520 | 195579.23 | 1 | 216053.47 | -20474.24 | 90.5235 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional contract - assignment of 5 days to carry out the project extension of the execution period - 48 days | additional contract worth €15,949.18 final price review calculation approval - €4,525.06
3202 | 3462809 | Improvement of Urban Mobility and Road Safety in the Municipality of Reguengos de Monsaraz - Requalification of Pedestrian Routes in São Pedro do Corval | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 06-06-2017 | 18-04-2018 | 316 | 180 | 298861.94 | 289918.92 | 2 | 289918.92 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price (70%) Subfactors: - Overall Price (90%); - Note justifying the Proposed Price (10%). | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution period
3203 | 3462353 | Construction/Expansion- Park- ZIM do Lagedo | 45236250-7 | Flatwork for parks | FALSE | 2017 | 2020 | Portugal | Tondela | Viseu | 20 | 20 | 21-06-2017 | 17-12-2020 | 1275 | 180 | 1113309 | 868808.61 | 2 | 838840.86 | 29967.75 | 103.5725 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Those contained in article 12 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of suspensions and extensions. | existence of underworks.
3204 | 3455726 | Requalification of the public and living spaces of the Fonte da Cruz social neighborhoods | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Penafiel | Porto | 13 | 13 | 17-01-2017 | 01-10-2018 | 622 | 180 | 977982.43 | 658913.3 | 2 | 658913.3 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions involving other entities
3205 | 3452527 | 17Ep00002707 - contract for provisional installation of stj - lisbon - escadinhas s. Crispin | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 21-06-2017 | 12-02-2018 | 236 | 75 | 235165 | 226622 | 1 | 226472 | 150 | 100.0662 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline | there was underwork
3206 | 3450299 | 5010026784/Drr/2017 - for the execution of the contract called "en4 - intersection with en118 prox. de montijo (km 18.750) and intersection with en10 pegões (km 44.257) rehabilitation". | 45233142-6 | Road-repair works | FALSE | 2017 | 2020 | Portugal | N/A | N/A | N/A | 32 | 26-05-2017 | 17-02-2020 | 997 | 332 | 4500000 | 3647000 | 3 | 3714285.22 | -67285.22 | 98.1885 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% - Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | resulting from the elaboration of bill of quantities
3207 | 3447520 | Urban regeneration - Area surrounding the Church and streetGonçalo Ériz | 45233252-0 | Surface work for streets | FALSE | 2016 | 2020 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 22 | 08-05-2017 | 07-10-2020 | 1248 | 150 | 697000 | 603992.06 | 2 | 728774.37 | -124782.31 | 82.8778 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of extra work and the complexity of the project | extra work
3208 | 3447345 | Requalification and improvement of several streets in the Parish of Coimbrão, Union of the Parishes of Monte Redondo and Carreira and Monte Real and Carvide | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 20-06-2017 | 20-07-2018 | 395 | 120 | 291560 | 270935.83 | 2 | 270935.83 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3209 | 3447063 | Sanjoanenses champions academy - resorts | 45210000-2 | Building construction work | FALSE | 2017 | 2018 | Portugal | São João da Madeira | Aveiro | 1 | 24 | 06-06-2017 | 26-11-2018 | 538 | 120 | 230000 | 212970 | 1 | 212970 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 70% Technical value of the proposal 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | dependent on carrying out other work
3210 | 3446570 | AA 2422 - Construction contract for the execution of the junction of the EN103, km 29+000, with access to the ETA of Areias de Vilar | 45233128-2 | Roundabout construction work | FALSE | 2015 | 2018 | Portugal | Barcelos | Braga | 3 | 25 | 14-06-2017 | 06-06-2018 | 357 | 60 | 240000 | 168480.83 | 1 | 167563.84 | 916.99 | 100.5472 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Overall price 50% 2) Technical value of the proposal 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was verified in the initial phase of the project that there was a lack of availability of part of the land necessary for the execution of the project. as the object of the contract was carried out under a management agreement also with infraestruturas de portugal, sa and the municipality of barcelos, there was a considerable delay on the part of the municipality of barcelos in unblocking the process of electric lighting.
3211 | 3445454 | The object of the contract is to carry out the contract for paving in bituminous concrete for streets in the municipality - 5th Phase in Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2017 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 16-06-2017 | 11-05-2020 | 1060 | 120 | 890000 | 723716.07 | 2 | 673750.82 | 49965.25 | 107.416 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) - Price: 60%; and b) - Technical quality of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 240 days extension of the deadline based on adverse weather conditions, 298 days due to delay for which the contractor is responsible, 362 days elapsed between the 1st and the last inspection for provisional acceptance purposes | underwork resulting from the supply of streets that did not need to be intervened
3212 | 3443765 | Contract for the Reorganization and Enhancement of the Lagoon Fishing Centers at Cais da Tijosa and Cais do Torrão (Ovar) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Ovar | Aveiro | 1 | 42 | 16-06-2017 | 24-08-2018 | 434 | 180 | 231000 | 208629.14 | 1 | 206015.04 | 2614.1 | 101.2689 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no conditioning factor for the start of the project to justify the delay verified in the project. during the course of the projects, there were some constraints due to local conditions, namely due to the action of the tides (which caused multiple bursting of the cofferdams), as well as the characteristics of the waterbed soils, the excess of completely saturated mud (caused instability of the excavations causing daily changes in the excavations carried out in terms of alignments and excavation dimensions). there were 2 accidents at work: - the first in january 2018 (perforation of the hand with a nail), caused by "impact with an object", with no permanent or temporary disability; - the second in february 2018 (poor foot support), caused by a "fall from a height", with no permanent or temporary disability.
3213 | 3443668 | Requalification of the EM 520 Between Gravulha and the County Limit (Portela do Brás) and Occasional Works on Other Roads | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 02-06-2017 | 22-08-2019 | 811 | 90 | 746160 | 684235.29 | 2 | 731437.25 | -47201.96 | 93.5467 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | over work, deadline extension | over and underwork, price revision
3214 | 3443466 | Carrying out work related to the “Requalification and Expansion of the elementary school of Vimeiro” | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2018 | Portugal | Lourinhã | Lisboa | 11 | 20 | 14-06-2017 | 27-08-2018 | 439 | 144 | 303377.72 | 300000 | 2 | 311900.01 | -11900.01 | 96.1847 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (PR) - 60.00%; deadline (PZ) - 40.00%; two. In case of equality of points, for tie-breaking, the proposal that obtains the best classification will be considered, in the order indicated, in the Price and Time factors. - 0.00%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | errors and omissions detected during the execution of the contract accepted by the owner, which jeopardized the normal development of the approved work plans - proc.n.º1 inf.n.º7554/2018 of 10/30/2017 extension of 54 days and proc. no. 2 inf. no. 1394 of 02/12/2018 47-day extension | errors and omissions detected during the execution of the contract accepted by the client, quantities of work not foreseen in the initial contract - proc.n.º1 inf.n.º7554/2018 of 10/30/2017 and proc.n.º2 inf. no. 1394 of 02/12/2018
3215 | 3443428 | Conservation of Local Access | 45233251-3 | Resurfacing works | FALSE | 2017 | 2020 | Portugal | Aveiro | Aveiro | 1 | 21 | 13-06-2017 | 04-02-2020 | 966 | 120 | 340247.63 | 311961.59 | 2 | 309761.78 | 2199.81 | 100.7102 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need for intervention by external entities.
3216 | 3442765 | “Improvement of en 396 – section between the industrial zone of loulé and the franchised zone – 2nd phase” – om 08/2017 | 45233251-3 | Resurfacing works | FALSE | 2017 | 2020 | Portugal | Loulé | Faro | 8 | 30 | 06-06-2017 | 21-09-2020 | 1203 | 180 | 265000 | 181884.68 | 1 | 181323.68 | 561 | 100.3094 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a time lag between the completion of the contract and its provisional acceptance. the contractor completed the project within the stipulated time frame. | underwork.
3217 | 3441581 | Strategic Urban Development Plan - Public Space Requalification | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Rio Maior | Santarém | 16 | 21 | 09-06-2017 | 15-11-2018 | 524 | 150 | 544940.58 | 226942.77 | 1 | 203595.83 | 23346.94 | 111.4673 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | more work, underwork and price revision.
3218 | 3441177 | Contract for Requalification of the Municipal Road Network - Year 2017 | 45233100-0 | Construction work for highways, roads | FALSE | 2017 | 2018 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 21 | 29-05-2017 | 31-10-2018 | 520 | 300 | 310982.5 | 248000 | 1 | 248000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed sooner
3219 | 3440705 | Public Contest No. 5-A1/2017 - The purpose of the procedure in question is the milling and replacement of bituminous pavements within the scope of interventions for the execution of collectors and pipelines | 45233222-1 | Paving and asphalting works | FALSE | 2017 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 12-06-2017 | 13-03-2019 | 639 | 365 | 310000 | 186000.01 | 1 | 185950.88 | 49.13 | 100.0264 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the quantities of work foreseen in the contract had not yet been reached | the estimated quantities were higher than the necessary quantities
3220 | 3440652 | Expansion of the Sanitation Network to Guilhadeses (Mó da Lomba/Fontão Covo) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 16-06-2017 | 06-02-2019 | 600 | 240 | 244000 | 204762.44 | 1 | 204762.44 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 50% - Lowest overall price; 50% - Worth proposal technique These criteria are broken down into sub-criteria, in accordance with article 12 of the Tender Program | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended for 30 days, for the purpose of replacing pavements
3221 | 3440637 | “Paving of the Connection from Fonte Filipe to Estrada do Almarjão” – (REPAVING FROM CM 1196 FROM EM 523 TO THE COUNCIL LIMIT) – OM 21/2017 | 45233251-3 | Resurfacing works | FALSE | 2017 | 2018 | Portugal | Loulé | Faro | 8 | 24 | 14-06-2017 | 02-03-2018 | 261 | 150 | 210000 | 167025.61 | 1 | 165256.73 | 1768.88 | 101.0704 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the deadline for execution of the contract, there were administrative delays in scheduling the provisional acceptance. | works initially foreseen and which were not necessary to carry out (underwork).
3222 | 3440387 | Opening and filling of ditches for laying pipes | 45232411-6 | Foul-water piping construction work | FALSE | 2017 | 2018 | Portugal | Portalegre | Portalegre | 12 | 20 | 16-06-2017 | 07-05-2018 | 325 | 180 | 306103 | 183661.81 | 1 | 183661.81 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline due to the morphology of the terrain with rocky soils that hindered the normal operation of the machines
3223 | 3439531 | 5010024200 - Contract to migrate wooden sleepers to concrete -LL-Pk 191.5/194.5 - East Line for 2017 | 45234100-7 | Railway construction works | FALSE | 2017 | 2018 | Portugal | N/A | N/A | N/A | 21 | 07-06-2017 | 28-11-2018 | 539 | 120 | 319336 | 274942.2 | 2 | 275418.33 | -476.13 | 99.8271 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (65% weighting) - FPRECIO b) Technical value (weighting of 15%) - FVT c) Safety Management System (10% weighting) - FSGS d) Quality Management System (5% weighting) - FSQ e) Environmental Monitoring System (5% weighting) - FNTA | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3224 | 3438083 | Requalification and improvement of several streets in the Union of Parishes of Leiria, Pousos, Barreira e Cortes and Parish of Arrabal - Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2017 | 2020 | Portugal | Leiria | Leiria | 10 | 20 | 09-06-2017 | 13-11-2020 | 1253 | 120 | 381470 | 372996 | 2 | 372996 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension (by the owner of the project) due to the need to study changes to the project (art. 365.º, paragraph b) of the "public procurement code")
3225 | 3434297 | Requalification and improvement of several streets in the Parishes of Amor, Bidoeira, Milagres, Regueira de Pontes and União das Parishes of Souto da Carpalhosa and Ortigosa | 45233220-7 | Surface work for roads | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 14-06-2017 | 13-07-2018 | 394 | 120 | 320924.65 | 309700 | 2 | 304869.47 | 4830.53 | 101.5845 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work | underwork
3226 | 3434157 | Conservation and Maintenance Contract for Municipal Roads in the Municipality of Leiria | 45233141-9 | Road-maintenance works | FALSE | 2017 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 09-06-2017 | 06-09-2018 | 454 | 365 | 283950 | 257498.23 | 2 | 257498.23 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3227 | 3431616 | Restoration of the Pedestrian Routes of the Ecological Park of Funchal | 45233260-9 | Pedestrian ways construction work | FALSE | 2017 | 2018 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 26-05-2017 | 28-12-2018 | 581 | 270 | 602788 | 361672.81 | 2 | 392560.67 | -30887.86 | 92.1317 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A | abnormal weather conditions | abnormal weather conditions with damage to work already carried out
3228 | 3429030 | Housing and Social Ecopark of Sernancelhe | 45211360-0 | Urban development construction work | FALSE | 2017 | 2018 | Portugal | Sernancelhe | Viseu | 20 | 30 | 12-06-2017 | 08-06-2018 | 361 | 150 | 329689.68 | 280236.24 | 2 | 263777.6 | 16458.64 | 106.2396 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price --------------40% Technical value of the proposal ---------60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to weather conditions | underwork
3229 | 3427866 | Requalification of the South Access to Mação | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Mação | Santarém | 16 | 11 | 23-09-2016 | 30-04-2018 | 584 | 180 | 1130974.75 | 891221.29 | 2 | 1178786.92 | -287565.63 | 75.605 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | additional work and price revision
3230 | 3427400 | Urban Requalification of the Central Axis of Guarda-Park of the City of Guarda - 2nd Phase | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2018 | Portugal | Guarda | Guarda | 9 | 20 | 09-06-2017 | 17-09-2018 | 465 | 120 | 581000 | 348600.01 | 2 | 348600.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical value of the proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | inspection carried out for the purposes of provisional acceptance on 10/11/2017, with anomalies being found in the project carried out. granted 30 days to repair them.
3231 | 3427084 | Rehabilitation of streets in the Silgarmar Urbanization - phase 1 (EN 124-1) | 45211360-0 | Urban development construction work | FALSE | 2017 | 2020 | Portugal | Silves | Faro | 8 | 30 | 25-05-2017 | 03-11-2020 | 1258 | 240 | 628515.71 | 488317.68 | 2 | 513495.84 | -25178.16 | 95.0967 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work deadline extension of 135 days | underwork, errors and omissions and price revisions
3232 | 3426186 | Requalification and Expansion of the Prof. carlos teixeira | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2021 | Portugal | Fafe | Braga | 3 | 30 | 09-06-2017 | 24-02-2021 | 1356 | 547 | 3985657.38 | 3980000 | 3 | 4079106.78 | -99106.78 | 97.5704 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical Valuation and Warranty Proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were 3 extensions of the contract term, and a partial suspension of the contract | there were more works
3233 | 3425460 | Contract for a cycle path as a way of experiencing the Ria: Section Estarreja-Albergaria-Aveiro and Section Vagos-Mira | 45233200-1 | Various surface works | FALSE | 2014 | 2020 | Portugal | Vagos | Aveiro | 1 | 45 | 14-02-2017 | 10-02-2020 | 1091 | 275 | 1042600 | 909862.07 | 2 | 915493.81 | -5631.74 | 99.3848 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | nothing relevant to point out. | adjustments/alterations to the execution project due to the fact that in some areas the conditions of the sites where the project will be implemented are very different from those existing when the tender was launched
3234 | 3418590 | Contract work to repave streets in the county - 2017 - repair and renew the wear layer of pavements in the county. | 45233223-8 | Carriageway resurfacing works | FALSE | 2017 | 2018 | Portugal | Barreiro | Setúbal | 17 | 20 | 22-05-2017 | 16-08-2018 | 451 | 150 | 550000 | 510558.31 | 2 | 510558.31 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to non-compliance with work | existence of underworks
3235 | 3415589 | 2nd Phase of Construction of the Pias Leisure Park - Cinfães | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2019 | Portugal | Cinfães | Viseu | 20 | 20 | 07-06-2017 | 01-02-2019 | 604 | 90 | 204727.42 | 203745 | 1 | 177805.8 | 25939.2 | 114.5885 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of more works | existence of overwork and underwork
3236 | 3413494 | Contract for: Construction of the WWTP in Vila Fernando and Emissários. | 45232421-9 | Sewage treatment works | FALSE | 2017 | 2018 | Portugal | Elvas | Portalegre | 12 | 24 | 07-06-2017 | 17-05-2018 | 344 | 180 | 597200 | 358324.8 | 2 | 324713.63 | 33611.17 | 110.351 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to make repairs in order to be able to carry out the provisional acceptance | there were works whose project quantities exceeded the actual executed quantities.
3237 | 3411402 | Construction of the Health Unit, in Odivelas | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2020 | Portugal | Odivelas | Lisboa | 11 | 20 | 06-06-2017 | 18-02-2020 | 987 | 180 | 1567000 | 1398800 | 3 | 1441231.98 | -42431.98 | 97.0559 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: In accordance with point 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the execution period is due to extensions of time due to adverse weather conditions and lack of definition of the project. | the increase in the value of the project results from a price review.
3238 | 3410493 | Refurbishment of the "Theatro Oliveira Zina" building in the regueifa and biscuit promotion workshop, located at streetJosé Seara and Largo do centenary, in the parish of Valongo | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2017 | 2021 | Portugal | Valongo | Porto | 13 | 24 | 05-06-2017 | 11-11-2021 | 1620 | 365 | 1900000 | 1898803.61 | 3 | 1953846.25 | -55042.64 | 97.1829 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two extensions to the initial execution period (120 days + 77 days) execution deadlines assigned to the 4 additional contracts signed (67+25+86+30 days) note: the last measurement report dates from 10.31.2019. the 1st inspection for the purposes of provisional acceptance took place on 04.11.2019, but due to successive regularizations of works it only took place in the 5th inspection on 15.04.2020. | underwork ↔ €134,544.84 more works ↔ €76,768.26 errors and omissions supply work ↔ €79,308.51 price review ↔ €33,510.71
3239 | 3409903 | EGA-EB0038 - Water Supply and Sanitation Infrastructure - Left Bank - Phase 2 (Amarante) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2019 | Portugal | Amarante | Porto | 13 | 50 | 12-04-2017 | 15-02-2019 | 674 | 365 | 2640000 | 1920655.81 | 3 | 789696.52 | 1130959.29 | 243.2144 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change due to deadline extension | underwork
3240 | 3409544 | Lot 3: Requalification of Avenida Irmãos Rui and Garcia Lopes | 45233200-1 | Various surface works | FALSE | 2017 | 2019 | Portugal | Chaves | Vila Real | 19 | 30 | 05-06-2017 | 30-04-2019 | 694 | 150 | 384900 | 319940 | 2 | 335126.84 | -15186.84 | 95.4683 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 2 deadline extensions of 90 days (55 + 35) and additional work with a deadline of 10 days | more works - €22,500.00, underwork - €7,500.00 and price review €186.84
3241 | 3409525 | EGA-AR0143 - Execution contract for the Rio Este Pumping System (FD10) - 1st Phase (Part 2) - Vila do Conde | 45232423-3, 45232411-6 | Sewage pumping stations construction work, Foul-water piping construction work | FALSE | 2016 | 2019 | Portugal | Vila do Conde | Porto | 13 | 47 | 12-04-2017 | 02-09-2019 | 873 | 196 | 620000 | 481268.23 | 2 | 567446.2 | -86177.97 | 84.813 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL EVALUATION - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of the contract and execution of errors and omissions and additional work | errors in the measurement of earthmoving quantities in the carvalhal interceptor; amendment of ascendi's prior opinion on the conditions for crossing under the a7 motorway,
3242 | 3409394 | Requalification of Vidago Primary School - Kindergarten | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2018 | Portugal | Chaves | Vila Real | 19 | 30 | 22-05-2017 | 16-02-2018 | 270 | 60 | 186627 | 164122.76 | 1 | 168432.76 | -4310 | 97.4411 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | errors and omissions supply 8 days | supply of errors and omissions and underwork
3243 | 3406352 | Land support wall on Estrada da Tesoureira, EM530-1, in Bucelas - Obra do Loan | 45262310-7 | Reinforced-concrete work | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | 30 | 12-01-2017 | 26-11-2018 | 683 | 144 | 495000 | 444241.51 | 2 | 574370.97 | -130129.46 | 77.344 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: ai) Factor (PP) - Bid Price - 50% aii) Factor (PE) - Execution Time - 20% aiii) Factor (QT) - Technical Quality of the Proposal - 30% aiii-1) Subfactor (PT) - Work Plan compatible with the proposed deadline and adequate to the proposed phasing - 15% aiii-2) Subfactor (PME) - Equipment Mobilization Plan adapted to conditions of the site and execution of the work - 15% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work for safety reasons. | additional work
3244 | 3404171 | Rehabilitation of the Municipal Garden | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2018 | Portugal | Resende | Viseu | 20 | 20 | 09-05-2017 | 14-08-2018 | 462 | 90 | 248655.15 | 243793.22 | 1 | 243793.22 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the existing water and electricity supply networks did not correspond to what was mentioned in the projects provided by the owner of work, as well as the need for compatibility between the project quotas and the existing quotas of trees and other contiguous elements.
3245 | 3396196 | Improvement of streets in Povoação de Chão de Codes | 45233222-1 | Paving and asphalting works | FALSE | 2017 | 2018 | Portugal | Mação | Santarém | 16 | 11 | 15-05-2017 | 18-04-2018 | 338 | 30 | 175765 | 168296 | 1 | 168296 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension.
3246 | 3395311 | Rectification of Av. Gen. Pimentel | 45233140-2 | Roadworks | FALSE | 2017 | 2019 | Portugal | Felgueiras | Porto | 13 | 24 | 02-06-2017 | 17-06-2019 | 745 | 300 | 897000 | 648265.27 | 2 | 503998.47 | 144266.8 | 128.6245 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | some adverse situations during the execution of the project. | smaller quantities executed
3247 | 3390877 | Equip the surrounding area of ​​PER de Sampaio with new coatings on the circulation floors, namely, on pedestrian paths and sidewalks, garden areas, living and permanence areas | 45233228-3 | Surface coating construction work | FALSE | 2017 | 2018 | Portugal | Valongo | Porto | 13 | 24 | 25-05-2017 | 17-05-2018 | 357 | 120 | 220000 | 207073.98 | 1 | 203731.34 | 3342.64 | 101.6407 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | approval of a 42-day extension to the period for carrying out the project, on a free basis. (addendum to the contract dated 11/10/2017) | approval of the provisional calculation of the price revision, dated 11/05/2018, in the amount of - €11,624.97 (credit in favor of the city council) approval of the final calculation of the price revision dated 27.02.2019, which amounted to -1,987.64€ (credit in favor of the city council), whereby the balance to be added to the previously approved final bill is €9,637.33 for settlement of the same. approval of the proposal for underwork by order of 05/17/2018, in the amount of €1,355.00
3248 | 3388598 | Expansion and remodeling of the Esmeriz primary school (Largo de S. Marçal) | 45214210-5 | Primary school construction work | FALSE | 2017 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 30-05-2017 | 03-07-2019 | 764 | 365 | 550000 | 463121.55 | 2 | 469928.08 | -6806.53 | 98.5516 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price: 60% and Technical Valuation of the Proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the value of the project was changed due to underwork and price revisions.
3249 | 3388404 | Sanitation of domestic wastewater from small settlements and small expansions of the domestic wastewater drainage network | 45232460-4 | Sanitary works | FALSE | 2016 | 2021 | Portugal | Cantanhede | Coimbra | 6 | 30 | 17-03-2017 | 19-07-2021 | 1585 | 360 | 1050000 | 1049492.27 | 3 | 1071174.81 | -21682.54 | 97.9758 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork and price revision
3250 | 3386646 | The contract includes the expansion and renovation of the Ermidas-Sado Primary School, in Ermidas-Sado, in the municipality of Santiago do Cacém. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Santiago do Cacém | Setúbal | 17 | 31 | 18-05-2017 | 19-07-2018 | 427 | 150 | 353400 | 352143.87 | 2 | 361922.94 | -9779.07 | 97.298 | lowest price | 2 | 100 | N/A | FALSE | N/A | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the characteristics of the existing building, being made of stone, and due to bad weather conditions. | additional work
3251 | 3383401 | 5010025189 - Ic17 (cril), km 15+700 to km 16+450 (ld), stabilization of excavation slopes | 45233142-6 | Road-repair works | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 36 | 29-05-2017 | 21-02-2020 | 998 | 83 | 350000 | 249388.87 | 1 | 260368.49 | -10979.62 | 95.783 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | resulting from the elaboration of bill of quantities
3252 | 3383158 | Sanitation and Paving in Montes Altos | 45232460-4 | Sanitary works | FALSE | 2016 | 2019 | Portugal | Mértola | Beja | 2 | 30 | 19-04-2017 | 09-04-2019 | 720 | 210 | 672500 | 593995.34 | 2 | 569765.88 | 24229.46 | 104.2525 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | works to supply errors and pace of work development on site | underwork and errors and omissions supply work
3253 | 3380885 | Replacement of the water and paving network - Liberdade and Amoreiras neighborhoods | 45232151-5 | Water-main refurbishment construction work | FALSE | 2017 | 2018 | Portugal | Grandola | Setúbal | 17 | 20 | 11-05-2017 | 13-11-2018 | 551 | 150 | 188276.82 | 141207.63 | 1 | 170792.1 | -29584.47 | 82.6781 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work | more works and price revisions
3254 | 3380345 | Contract 20 - Closing of the Wastewater Sanitation System in Saudel | 45232460-4 | Sanitary works | FALSE | 2017 | 2018 | Portugal | Sabrosa | Vila Real | 19 | 15 | 30-05-2017 | 26-06-2018 | 392 | 180 | 219910.78 | 209811.67 | 1 | 182584.19 | 27227.48 | 114.9123 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
3255 | 3375748 | Water supply contract for Parceiro, Covão and Alentejo | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | 24 | 24-05-2017 | 30-05-2018 | 371 | 150 | 215000 | 157343.07 | 1 | 154637.45 | 2705.62 | 101.7497 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | fires in october 2017 affected the project already carried out and consequently the provisional reception. | existence of home extensions, such as more work and existence of underwork in the projects of the contract.
3256 | 3374799 | 5010027818 - En1, km 24+627 to km 25+035, black point 2012. Complementary works | 45233142-6 | Road-repair works | FALSE | 2017 | 2019 | Portugal | N/A | N/A | N/A | 30 | 24-05-2017 | 04-11-2019 | 894 | 60 | 250000 | 234575.21 | 1 | 340494.37 | -105919.16 | 68.8925 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | associated with bill of quantities | associated with bill of quantities
3257 | 3372537 | Church of São Vicente, Abrantes – Exterior Improvement | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2019 | Portugal | Abrantes | Santarém | 16 | 36 | 24-05-2017 | 23-05-2019 | 729 | 240 | 381206.63 | 264151.75 | 2 | 269493.67 | -5341.92 | 98.0178 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | an extension of 60 days to the execution period of the project was authorized | underwork and the ordinary revision of prices were considered.
3258 | 3372503 | Rehabilitation of the Tennis Courts of the Tavira Sports Complex | 45236119-7 | Repair work on sports fields | FALSE | 2017 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 24-05-2017 | 22-01-2019 | 608 | 120 | 195730.75 | 176447.14 | 1 | 176447.14 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
3259 | 3372130 | Qualification of the São João Bridge | 45221111-3 | Road bridge construction work | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | 15 | 25-05-2017 | 10-09-2019 | 838 | 150 | 603000 | 602186.59 | 2 | 662178.57 | -59991.98 | 90.9402 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions and extensions | more work and underwork
3260 | 3371825 | Execution of water supply pipeline | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2017 | 2019 | Portugal | Sertã | Castelo Branco | 5 | 20 | 24-05-2017 | 29-11-2019 | 919 | 180 | 400147 | 278704.69 | 2 | 276267.66 | 2437.03 | 100.8821 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension | underwork and price revision
3261 | 3371774 | Requalification of the 1st of December Park and Complementary streets . | 45233251-3 | Resurfacing works | FALSE | 2017 | 2019 | Portugal | Fafe | Braga | 3 | 30 | 25-05-2017 | 15-10-2019 | 873 | 120 | 311912 | 299976.35 | 2 | 299976.35 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical value and guarantee of proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were changes to the project, the need to introduce new infrastructure and additional work | extra work
3262 | 3371719 | Requalification of E.M. 556, Between S. Facundo and Vale das Mós – Abrantes | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Abrantes | Santarém | 16 | 37 | 22-05-2017 | 24-07-2018 | 428 | 120 | 437369.92 | 332640.87 | 2 | 333420.56 | -779.69 | 99.7662 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the deadline for carrying out the project. | the change in the value of the project came about following the price revision calculation, in accordance with the legislation.
3263 | 3371482 | EGA-EB0015 - Wastewater Drainage Network (1st Phase) and Water Supply Network of Aboim (Amarante) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Amarante | Porto | 13 | 50 | 11-04-2017 | 10-10-2018 | 547 | 210 | 750000 | 554840 | 2 | 480006.29 | 74833.71 | 115.5902 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A. PRICE - 50% B. TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the existence of numerous private water supply pipes, mines and aqueducts prevented the implementation of infrastructures from being carried out with the expected yields. the private infrastructures were not registered, so with the occurrence of ruptures, it resulted in the need to restore the existing supply conditions, succeeding in some cases, the need to adjust the layout and depth of the infrastructures to be built. delay in issuing ip license to intervene on en10. | underwork resulting from adjusting the layout and depth of the sanitation network.
3264 | 3366964 | Improvement from streetde Santana in Boim to EN 320 in Meinedo | 45233140-2 | Roadworks | FALSE | 2017 | 2018 | Portugal | Lousada | Porto | 13 | 21 | 16-05-2017 | 03-12-2018 | 566 | 90 | 215286.9 | 197964 | 1 | 197964 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions: lack of definitions regarding the planned extensions; replacement of the water supply pipe and shut-off valves; definition of limits for the execution of tours. suspension of work: the low temperatures did not allow paving the wearing course in bituminous, as well as the subsequent horizontal signage.
3265 | 3366858 | Demolitions, Exterior Work, Roofing, Facades, Signage and Window Frames-Interior Flooring, Interior Walls, Interior Ceilings, Carpentry, Electricity, Water Supply Network | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Mogadouro | Bragança | 4 | N/A | 03-05-2017 | 20-02-2020 | 1023 | 365 | 198832.23 | 198794.77 | 1 | 240988.97 | -42194.2 | 82.4912 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Refer to point 16 of the Program of procedure. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in supplies of materials and equipment | unforeseen work initially
3266 | 3362835 | Ponta da Piedade Requalification Contract - 1st Phase | 45233161-5 | Footpath construction work | FALSE | 2017 | 2018 | Portugal | Lagos | Faro | 8 | N/A | 22-05-2017 | 18-04-2018 | 331 | 90 | 235000 | 193000 | 1 | 170488.19 | 22511.81 | 113.2043 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was extended for another 141 days, as a grace | more work was calculated in the amount of €42,454.84 and underwork in the amount of €64,966.65
3267 | 3361966 | Execution of the Canteen of elementary school nº 2 of Cova da Piedade - Nª Srª da Piedade neighborhood | 45214200-2 | Construction work for school buildings | FALSE | 2017 | 2018 | Portugal | Almada | Setúbal | 17 | 24 | 17-05-2017 | 12-12-2018 | 574 | 150 | 172469.56 | 161160.97 | 1 | 161160.97 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 "Technical Value of the Proposal" - (40%) with the subfactors "Work execution plan" - 30 points and "Equipment and labor means" - 10 points Factor 2 - "Proposal Price" - (60%). | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work.
3268 | 3360182 | Via creation for smooth modes - 1st phase - | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Penafiel | Porto | 13 | 15 | 16-02-2017 | 03-01-2018 | 321 | 180 | 1850350.46 | 1220902.58 | 3 | 1220902.58 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension
3269 | 3359728 | Rehabilitation of the Argemil Housing Complex and Requalification of Exterior Spaces | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2020 | Portugal | Santo Tirso | Porto | 13 | 20 | 18-05-2017 | 13-01-2020 | 970 | 365 | 990797.85 | 986240.39 | 2 | 1111071.79 | -124831.4 | 88.7648 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The proposal evaluation model will be centered on the assessment of the following factors: - A - Price - with a weighting of 60% in the overall assessment; - B - Technical Value of the Proposal - with a weighting of 40% in the overall classification. The Technical Value of the Proposal will be broken down into the following sub-factors: - B1 - Work Schedule - with a weighting of 25% in the overall classification; - B2 - Means Affected to the Work - with a weighting of 10% in the overall classification; - B3 - Occupational Health and Safety Risk Management - with a weighting of 5% in the overall classification. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the existence of more work (contractual extension) and adverse weather conditions (graceful extension) | the existence of more works.
3270 | 3358790 | Construction of the Ecological Park and Intermodal Park - Venda do Pinheiro. | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | Mafra | Lisboa | 11 | 24 | 05-05-2017 | 19-12-2019 | 958 | 210 | 2322406.95 | 2279495.05 | 3 | 2627494.16 | -347999.11 | 86.7555 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Overall price of the proposal (47.5%); b) Technical quality of the proposal (52.5%), divided by the following subfactors: b.1) Descriptive memory and justification of the mode of execution of the contract, including description of the execution planning of the works, according to the specifications (45%); b.2) Work Plan (25%); b.3) Labor Plan (15%); b.4) Equipment Plan (15%). | 1 | 47.5 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work and deadline extension | additional work and price revision
3271 | 3357747 | Contract for the conservation and maintenance of rainwater drainage and water lines in the Municipality of Cascais | 45233200-1, 45232151-5, 45112000-5, 45232130-2, 45100000-8 | Various surface works, Water-main refurbishment construction work, Excavating and earthmoving work, Storm-water piping construction work, Site preparation work | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | 30 | 21-03-2017 | 26-03-2018 | 370 | 288 | 2214439.3 | 1695464.25 | 3 | 1695464.25 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3272 | 3356878 | Refurbishment of the Pedrógão Grande Health Center | 45215100-8 | Construction work for buildings relating to health | FALSE | 2017 | 2019 | Portugal | Pedrogão Grande | Leiria | 10 | 30 | 22-05-2017 | 05-12-2019 | 927 | 365 | 347561.65 | 312599.86 | 2 | 349145.72 | -36545.86 | 89.5328 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the execution of more works and delays in the execution of the electricity works. | due to more work detected during the course of the contract.
3273 | 3353500 | 2014.152.01.C1 - SFP Beja - Remodeling of the Center's facilities | 45259000-7 | Repair and maintenance of plant | FALSE | 2015 | 2018 | Portugal | Beja | Beja | 2 | 22 | 23-09-2015 | 19-12-2018 | 1183 | 240 | 685500 | 498603.97 | 2 | 463047.98 | 35555.99 | 107.6787 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | job suppression
3274 | 3350748 | The object of this contract is the construction of a water distribution network, with 1.9 km, and a domestic wastewater drainage system, with about 1.5 km | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2019 | Portugal | Murtosa | Aveiro | 1 | N/A | 15-05-2017 | 11-11-2019 | 910 | 90 | 300000 | 232603 | 1 | 232603 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment and materials - 10%) | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3275 | 3348389 | The purpose of the contract is to carry out the protection contract of the right margin of the ribeira dos flamengos near street of cantinho, flamengos, horta, faial. | 45246000-3 | River regulation and flood control works | FALSE | 2016 | 2018 | Portugal | Horta | Região Autónoma dos Açores | 15 | 28 | 10-04-2017 | 07-02-2018 | 303 | 180 | 220000 | 187000.01 | 1 | 181996.63 | 5003.38 | 102.7492 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for the project ended on time, that is, 11/05/2017, and the partial provisional acceptance notice was issued on 12/05/2017. | underwork
3276 | 3346463 | Rehabilitation of the restaurant and beverage establishment at Jardim Luis de Camões | 45212421-3 | Restaurant construction work | FALSE | 2017 | 2021 | Portugal | Marinha Grande | Leiria | 10 | 20 | 02-05-2017 | 25-11-2021 | 1668 | 180 | 219921.73 | 197916.09 | 1 | 207646.15 | -9730.06 | 95.3141 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for reasons attributable to the owner of the project | for the purposes of price revisions, errors and omissions supply works and suppression of works
3277 | 3338967 | Regularization and Canalization of Ribeiro do Corujeira - Monte, 2nd Phase | 45246000-3 | River regulation and flood control works | FALSE | 2016 | 2020 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 12-05-2017 | 17-09-2020 | 1224 | 420 | 1500000 | 1275000.01 | 3 | 1305181.46 | -30181.45 | 97.6876 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the need to study changes to be introduced to the project in the part referring to the execution of the water line channeling between pk 230 and pk 280 | difference between forecast quantities and executed quantities.
3278 | 3331773 | Execution of sidewalks, paving and repaving; remodeling of the water supply network; execution of the domestic sewage network and rainwater drainage network. | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2018 | Portugal | Nisa | Portalegre | 12 | 30 | 10-05-2017 | 03-10-2018 | 511 | 120 | 237110 | 159568.94 | 1 | 159568.94 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | appearance of rocky outcrops on the projectsite, calamity of the fires that broke out in the area of ​​the company's headquarters. works that were conditioned by the replacement of electricity pylons at the construction site by another company. | contract price revisions
3279 | 3331246 | Rehabilitation of the Municipal Market of Pampilhosa | 45213141-3 | Covered market construction work | FALSE | 2016 | 2021 | Portugal | Mealhada | Aveiro | 1 | 30 | 08-05-2017 | 05-01-2021 | 1338 | 365 | 1152000 | 897904.84 | 2 | 897904.84 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | revision of prices, fines, errors and omissions supply works, more works and underwork
3280 | 3331131 | Preliminary work, drainage, lancing, paving, horizontal signage, vertical signage | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Figueira da Foz | Coimbra | 6 | N/A | 16-02-2017 | 26-01-2018 | 344 | 90 | 349887 | 344000.02 | 2 | 304042.73 | 39957.29 | 113.142 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline for completion of the project | due to the value of underwork
3281 | 3330094 | Paving of the Section between the Parish Council and Jardim do Algoz. | 45211360-0, 45232460-4 | Urban development construction work, Sanitary works | FALSE | 2017 | 2019 | Portugal | Silves | Faro | 8 | 30 | 04-05-2017 | 12-07-2019 | 799 | 210 | 304640 | 217832.54 | 1 | 230954.87 | -13122.33 | 94.3182 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work subject to deadline extension | review of prices and correction of errors and omissions.
3282 | 3328111 | AA 2374 - Construction contract for the execution of the connection to the Lara/Pinheiros Reservoir (Monção) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2020 | Portugal | Monção | Viana do Castelo | 18 | 41 | 21-04-2017 | 06-05-2020 | 1111 | 420 | 3400000 | 2040000.01 | 3 | 2040000.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price 50% 2) Technical Value of the Proposal 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the process of connecting the electricity by the entity responsible for the execution of the branches | no change
3283 | 3327843 | Rehabilitation of Chalet Ribeiro Telles - Cova da Piedade | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 30 | 27-04-2017 | 19-12-2018 | 601 | 240 | 622467.15 | 598582.1 | 2 | 615575 | -16992.9 | 97.2395 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 - "Technical Value of the Proposal" - (40%), with the subfactors "Work plan" - 30 points and "Descriptive memory and justification" - 10 points. Factor 2 - "Proposal Price" - 60% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to extend the deadline due to unpredictable work. | the value was changed in relation to the award due to the need for unpredictable works, giving rise to an additional contract.
3284 | 3325468 | Requalification contract for the banks of the River Gondim between Vila Boa and Alhavaite - 1st phase | 45212110-0 | Leisure centre construction work | FALSE | 2017 | 2018 | Portugal | Arouca | Aveiro | 1 | 15 | 12-05-2017 | 19-10-2018 | 525 | 180 | 503773.58 | 448302.15 | 2 | 431884 | 16418.15 | 103.8015 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | delays attributable to the contractor. | existence of errors and omissions and deleted works.
3285 | 3325016 | Stabilization of ER 102 | 45111230-9 | Ground-stabilisation work | FALSE | 2016 | 2019 | Portugal | Machico | Região Autónoma da Madeira | 14 | 20 | 28-04-2017 | 03-04-2019 | 705 | 180 | 505000 | 414000 | 2 | 394823.14 | 19176.86 | 104.8571 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project. | in the procedure carried out to carry out the measurements, pursuant to paragraph 2 of article 388 of the "public procurement code", it was found that the calculation of some quantities of work did not reach the forecast.
3286 | 3322141 | Alteration of the Quarteira Fire Brigade to a National Guard Territorial Post | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2016 | 2019 | Portugal | Loulé | Faro | 8 | 48 | 23-03-2017 | 01-08-2019 | 861 | 365 | 896000 | 873284.14 | 2 | 859697.71 | 13586.43 | 101.5804 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in carrying out work | underwork
3287 | 3321635 | Requalification of the Castle/Fortress of Penamacor | 45453100-8 | Refurbishment work | FALSE | 2017 | 2020 | Portugal | Penamacor | Castelo Branco | 5 | 44 | 03-05-2017 | 06-01-2020 | 978 | 365 | 975535.68 | 589183.1 | 2 | 30260.78 | 558922.32 | 1947.0189 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of Contract (Object of refusal of approval by the Court of Auditors) | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | termination of the contract. underwork worth: €558,922.32.
3288 | 3318148 | The object of this work contract is the execution, by the second party to the first party, of the work « Health of Proximity - Rehabilitation of the Extension of the Health Center of Caban | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2019 | Portugal | Carregal do Sal | Viseu | 20 | 21 | 13-04-2017 | 18-01-2019 | 645 | 180 | 224000 | 169300.7 | 1 | 168978.06 | 322.64 | 100.1909 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the execution of more work and the need for changes to the project. | the execution of Extra work and the existence of underwork
3289 | 3315961 | Construction of the fairgrounds and markets of S. Bartolomeu de Messines | 45213142-0 | Open-air market construction work | FALSE | 2016 | 2021 | Portugal | Silves | Faro | 8 | 30 | 04-04-2017 | 08-01-2021 | 1375 | 270 | 950000 | 925562.88 | 2 | 935389.16 | -9826.28 | 98.9495 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension - 111 days | revision of prices and work to be done
3290 | 3315924 | Street Paving 2017 | 45000000-7 | Construction work | FALSE | 2017 | 2018 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 09-05-2017 | 30-11-2018 | 570 | 240 | 307114.59 | 279000 | 2 | 279000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | indefinitions in the project and bad weather
3291 | 3315476 | Improvement of street of Igreja, including hydraulic infrastructure | 45000000-7 | Construction work | FALSE | 2017 | 2019 | Portugal | Esposende | Braga | 3 | 30 | 04-05-2017 | 24-01-2019 | 630 | 135 | 361000 | 333579.84 | 2 | 333578.95 | 0.89 | 100.0003 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40% Technical quality of the proposal - 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay verified occurred with the entry of esposende ambiente to carry out the rehabilitation of ribeira da fonte | there was no change to the execution period of the project
3292 | 3315445 | The object of this contract is the renovation of the water supply networks in Ílhavo. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2019 | Portugal | Ílhavo | Aveiro | 1 | N/A | 26-04-2017 | 10-10-2019 | 897 | 365 | 249000 | 176519.56 | 1 | 176519.56 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3293 | 3313574 | Construction of the pedrouços sports hall, to be carried out at the pedrouços sports complex, including the preparation of the necessary projects, in the parish of pedrouços | 45212220-4 | Multi-purpose sports facilities construction work | FALSE | 2016 | 2019 | Portugal | Maia | Porto | 13 | 39 | 05-05-2017 | 26-06-2019 | 782 | 300 | 1492891.57 | 1399556.49 | 3 | 1343612.73 | 55943.76 | 104.1637 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | there was a 60-day extension of the deadline, difficulties in the delivery of materials by suppliers and long periods of rain, which delayed the normal development of the project. | the alteration of the structural project which implied a reduction in the amount of work in this undertaking.
3294 | 3307783 | Refurbishment and Expansion of the Transit School Building for the Headquarters of ARPIFAFE-Association of Retired, Pensioners and Senior Citizens of Fafe. | 45262700-8 | Building alteration work | FALSE | 2017 | 2019 | Portugal | Fafe | Braga | 3 | 30 | 08-05-2017 | 07-05-2019 | 729 | 180 | 167770.06 | 155817.99 | 1 | 155816.92 | 1.07 | 100.0007 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 70.00%; Technical Valuation and Warranty Proposal - 30.00%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a new procedure and also due to adverse weather conditions | there were no changes to the value of the project
3295 | 3295756 | Contract for the execution of the Alcorochel sanitation subsystem | 45232421-9 | Sewage treatment works | FALSE | 2016 | 2021 | Portugal | Torres Novas | Santarém | 16 | 48 | 21-04-2017 | 02-04-2021 | 1442 | 360 | 900000 | 646134.18 | 2 | 655129.15 | -8994.97 | 98.627 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements.
3296 | 3295604 | Contract for the execution of the Fungalvaz sanitation subsystem | 45232421-9 | Sewage treatment works | FALSE | 2016 | 2020 | Portugal | Torres Novas | Santarém | 16 | 48 | 21-04-2017 | 21-10-2020 | 1279 | 450 | 700000 | 689070 | 2 | 653131.53 | 35938.47 | 105.5025 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements | the objective of the project was fully achieved, not requiring the invoicing of all items
3297 | 3295113 | Requalification of the Urban Park of Santiago | 45112723-9 | Landscaping work for playgrounds | FALSE | 2017 | 2019 | Portugal | Aveiro | Aveiro | 1 | 26 | 02-05-2017 | 06-12-2019 | 948 | 120 | 285193.58 | 284852.67 | 2 | 284882.5 | -29.83 | 99.9895 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions and suspension | errors and omissions and suppressed work supplies
3298 | 3289703 | Improvement of the elementary school of Ferreiró, in Santa Maria de Avioso, parish of Castelo da Maia | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2018 | Portugal | Maia | Porto | 13 | 45 | 21-04-2017 | 29-06-2018 | 434 | 365 | 391560 | 369459.84 | 2 | 380346.09 | -10886.25 | 97.1378 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | verification of the projects for the execution of this contract.. | it is due to the price revision.
3299 | 3286239 | Requalification of Dr. Jaime Magalhães Lima | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2019 | Portugal | Aveiro | Aveiro | 1 | 27 | 12-04-2017 | 12-11-2019 | 944 | 365 | 1516653.37 | 1474538.64 | 3 | 1546744.99 | -72206.35 | 95.3317 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | more work, underwork and price revisions
3300 | 3285902 | Contract for the Rehabilitation, Conservation and Restoration of the Igreja da Misericórdia de Penafiel | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2016 | 2018 | Portugal | Penafiel | Porto | 13 | 21 | 05-04-2017 | 14-09-2018 | 527 | 485 | 648268.49 | 551028.53 | 2 | 551028.53 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical quality of the proposal - 40% - (70% for descriptive and justification and 30% for work planning) | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the weather conditions allowed a good development of the contract. | because it is the rehabilitation of a classified building and there are always unpredictable works.
3301 | 3285060 | EGA-AA0057 - Execution contract for the Fornelo Reservoir and Pipeline (Vila do Conde) | 45247270-3, 45231300-8 | Reservoir construction works, Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Vila do Conde | Porto | 13 | 47 | 31-03-2017 | 26-10-2018 | 574 | 168 | 460000 | 343524.25 | 2 | 331957.53 | 11566.72 | 103.4844 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price 50%; b) Technical value of the proposal, 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of additional work and correction/repair of work performed | execution of extra and underwork and price revision
3302 | 3284377 | Contract for the maintenance of water supply networks | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2019 | Portugal | Coruche | Santarém | 16 | 24 | 16-02-2017 | 01-03-2019 | 743 | 730 | 150000 | 150000 | 1 | 139126.46 | 10873.54 | 107.8156 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the deadline. the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
3303 | 3284263 | Rehabilitation works for the "envelope" and installation of an energy system (solar) in block 5 of the Falcão Municipal Public Housing Complex | 45453000-7 | Overhaul and refurbishment work | FALSE | 2017 | 2018 | Portugal | Porto | Porto | 13 | 20 | 28-04-2017 | 23-02-2018 | 301 | 180 | 500000 | 425525.33 | 2 | 425525.33 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractually foreseen
3304 | 3284251 | Requalification of streetMarquês de Pombal, in the City of Cantanhede, by Contract - CP-CCP-EMP n.º 02/2017 | 45113000-2 | Siteworks | FALSE | 2017 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 20 | 03-05-2017 | 31-01-2019 | 638 | 180 | 473225.71 | 434997.89 | 2 | 431582.18 | 3415.71 | 100.7914 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it took more days to complete the normal works and the extra ones. | existence of over and underwork
3305 | 3282287 | Recovery from E.M. 632 Section Muna - Carvalhal da Mulher | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Tondela | Viseu | 20 | 20 | 14-02-2017 | 04-12-2018 | 658 | 240 | 424000 | 344285.28 | 2 | 321551.84 | 22733.44 | 107.0699 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Those contained in article 12 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the undertaking began with the communication from the pss | existence of underworks
3306 | 3281768 | Refurbishment of the water supply network to Valverde and execution of the sewerage network to Naia and Valverde | 45232400-6 | Sewer construction work | FALSE | 2016 | 2021 | Portugal | Tondela | Viseu | 20 | 20 | 28-04-2017 | 13-12-2021 | 1690 | 390 | 478544.97 | 401943.44 | 2 | 462997.46 | -61054.02 | 86.8133 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | derived from suspensions and extensions | existence of underworks
3307 | 3281194 | Execution of the road marking of pavements of the municipal road network - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-04-2017 | 03-05-2019 | 735 | 180 | 665347 | 322937.42 | 2 | 313779.37 | 9158.05 | 102.9186 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% b) Technical quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension due to issues associated with making certain streets available for signage (60 days) graceful extension due to the occurrence of unfavorable weather conditions (250 days) 118 days to carry out inspections and correct deficiencies | underwork due to differences between the tender quantities and those actually carried out
3308 | 3279950 | DPES-CP-03-2016 - Rehabilitation of reservoirs and water pumping stations in Alcarraques, Quinta da Zombaria and Trouxemil | 50000000-5 | Repair and maintenance services | FALSE | 2016 | 2019 | Portugal | Coimbra | Coimbra | 6 | 30 | 20-04-2017 | 11-03-2019 | 690 | 210 | 240000 | 228019.21 | 1 | 224157.84 | 3861.37 | 101.7226 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: Those indicated in point 15 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | barriers created by other entities for the progress of works | there were works that were not performed
3309 | 3279368 | DPES-CP-04-2016 -Wastewater drainage networks and remodeling of the water supply network in Lagoas (2nd Phase), Tapada and Eira Velha | 45232440-8 | Construction work for sewage pipes | FALSE | 2017 | 2020 | Portugal | Coimbra | Coimbra | 6 | 24 | 31-03-2017 | 25-09-2020 | 1274 | 420 | 970000 | 937999.68 | 2 | 912811.83 | 25187.85 | 102.7594 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: Those indicated in point 15 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to being dependent due to being dependent on other entities | underwork has taken place
3310 | 3272646 | Contract for the recovery of ARM irrigation systems in the parishes of Gaula, Santa Cruz and Campanário | 45232120-9 | Irrigation works | FALSE | 2017 | 2018 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 48 | 28-04-2017 | 10-10-2018 | 530 | 120 | 450000 | 379492.5 | 2 | 379492.5 | 0 | 100 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 1 -operational issues, unavailability of infrastructure for the project as they are in the operating period (irrigation) 2- adverse atmospheric conditions.
3311 | 3271632 | Improvement of the quality of the public space with the construction of a circumscribed car park and a vast pedestrian square, including the creation of electrical, water and sewage infrastructure | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 27-12-2016 | 25-09-2018 | 637 | 210 | 458485 | 397353.66 | 2 | 372542.22 | 24811.44 | 106.66 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | correction of deficiencies detected in inspection | value of underwork and price revision
3312 | 3269658 | Improvement of the EN 101 pavement between Km 45+700 and Km 50+450 | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2019 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 24-04-2017 | 06-02-2019 | 653 | 60 | 257447.1 | 204268.65 | 1 | 204268.65 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | not applicable
3313 | 3267898 | Workers' Pavilion - Funchal - Rehabilitation Works | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2017 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 21 | 17-04-2017 | 09-01-2019 | 632 | 150 | 433000 | 376807.25 | 2 | 379163.67 | -2356.42 | 99.3785 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | underwork and price revision.
3314 | 3267081 | Connection from Bairro do Modorno to Almeidinha | 45000000-7 | Construction work | FALSE | 2017 | 2019 | Portugal | Mangualde | Viseu | 20 | 20 | 26-04-2017 | 27-02-2019 | 672 | 365 | 280000 | 252000.01 | 2 | 247004.57 | 4995.44 | 102.0224 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | according to process | according to final account
3315 | 3267045 | Contract for the Recovery of Ferreira da Silva Laboratory | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Porto | Porto | 13 | 36 | 06-04-2017 | 06-12-2018 | 609 | 270 | 398354.74 | 393977.63 | 2 | 393534.2 | 443.43 | 100.1127 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Overall price of the proposal 40%; b) Technical value of the proposal 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | said deadline extensions. | referral increases/decreases.
3316 | 3266898 | Conservation of the municipal road network - Repaving of the E.M. 518 Formil - alimonde | 45233142-6 | Road-repair works | FALSE | 2017 | 2018 | Portugal | Bragança | Bragança | 4 | N/A | 24-04-2017 | 14-02-2018 | 296 | 120 | 345000 | 249975 | 1 | 249975 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price (weighting) of 70%) Technical quality of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in providing horizontal and vertical signaling by the company to the contractor.
3317 | 3266709 | Improvement of the access, tank and gazebo, as well as the space related to the exhibition of blankets, sanitary facilities and construction of an amphitheater, parking lots and north pedestrian access | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2021 | Portugal | Amarante | Porto | 13 | 30 | 11-04-2017 | 26-01-2021 | 1386 | 180 | 259450 | 216321.94 | 1 | 207794.49 | 8527.45 | 104.1038 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspensions | over and underwork and positive price revision
3318 | 3264084 | Year 2017_Contract for the Rehabilitation of the Convent of São Pedro de Alcântara, located at streetde São Pedro de Alcântara 85, in Lisbon – 1st Phase | 45454100-5 | Restoration work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 12-04-2017 | 23-09-2019 | 894 | 180 | 410000 | 323899.93 | 2 | 442199.52 | -118299.59 | 73.2475 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need to carry out additional work resulted in an extension of the period for carrying out the project. | the need to carry out additional work resulted in an increase in the cost of the project.
3319 | 3261255 | Metropolitan Ecological Network for the Valorization of Nature, Biodiversity, Recreation and Leisure - Urban Park of the Colinas do Cruzeiro urbanization, in Odivelas | 45112711-2 | Landscaping work for parks | FALSE | 2016 | 2018 | Portugal | Odivelas | Lisboa | 11 | 20 | 21-04-2017 | 13-07-2018 | 448 | 120 | 465790.87 | 309871.63 | 2 | 336066.73 | -26195.1 | 92.2054 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: As established in point 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the execution period was 120 days and there was an extension of 45 days. | there were additional works worth €26,195.10.
3320 | 3260975 | Requalification of Green Spaces | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2018 | Portugal | Entroncamento | Santarém | 16 | 20 | 24-04-2017 | 08-06-2018 | 410 | 240 | 461428.47 | 410971.04 | 2 | 412008.26 | -1037.22 | 99.7483 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | reformulation of the electrical installations project; adverse weather conditions that conditioned the completion of some floors and delay in the intervention of external entities, namely edp | reformulation of the electrical installations project
3321 | 3260945 | Contract for Completion of the Installations of the Elementary School of the Parish of Santa Bárbara | 45000000-7 | Construction work | FALSE | 2017 | 2019 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 21 | 24-04-2017 | 20-02-2019 | 667 | 90 | 800000 | 680000.01 | 2 | 673039.56 | 6960.45 | 101.0342 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to clause 24 of the Procedure. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | request for graceful extension of the deadline by the contractor. | deletion of works.
3322 | 3259032 | 19/Eop/dcop/2016 - rehabilitation of the Bicesse road to Livramento | 45100000-8, 45112700-2, 45262310-7, 45232332-8, 45233000-9, 45232411-6, 45232452-5, 45112000-5, 45232130-2, 45232200-4, 45232151-5, 45233294-6, 45223000-6 | Site preparation work, Landscaping work, Reinforced-concrete work, Ancillary works for telecommunications, Construction, foundation and surface works for highways, roads, Foul-water piping construction work, Drainage works, Excavating and earthmoving work, Storm-water piping construction work, Ancillary works for electricity power lines, Water-main refurbishment construction work, Installation of road signals, Structures construction work | FALSE | 2016 | 2019 | Portugal | Cascais | Lisboa | 11 | N/A | 17-02-2017 | 25-11-2019 | 1011 | 240 | 1300104.83 | 905829.03 | 2 | 815833.65 | 89995.38 | 111.0311 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 90% Execution time - 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changes to the respective infrastructure project | works not performed.
3323 | 3257319 | Conservation of sports facilities - refurbishment of the playground of the Águas Santas sports group, in the parish of Águas Santas | 45236119-7 | Repair work on sports fields | FALSE | 2016 | 2018 | Portugal | Maia | Porto | 13 | 46 | 19-04-2017 | 28-02-2018 | 315 | 150 | 285271.45 | 228217.17 | 1 | 225450.56 | 2766.61 | 101.2271 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this contract had a deadline extension of 31 days at the request of the contracting company, due to the fact that it was carried out in the summer months, june, july and august, the vacation period for many companies, which implies a lack of labour. work, delays in the supply of some materials necessary for carrying out the project. the awarded company also refers to the lack of licensing for the borehole, despite the fact that they are making every effort in this direction to be able to finish the project on this contract, and even though the provisional reception was drawn up on the initiative of this city council. | the value of the contract is the result of the project carried out, with the exception of the execution of the water catchment hole.
3324 | 3256814 | Repaving and Requalification of the Road from Estádio to Sampaio - Cinfães; Repaving and Requalification of the Municipal Road of E.N. 321 To Marcelim - Tendais; Municipal path to the WWTP in the Zona Alta | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Cinfães | Viseu | 20 | 20 | 14-10-2016 | 07-03-2018 | 509 | 180 | 236292 | 167935 | 1 | 191990.58 | -24055.58 | 87.4704 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work and existence of overwork. | extra work
3325 | 3255120 | Contract for pavement reinforcement and ancillary works in the municipality of cascais | 45111100-9, 45111000-8, 45232410-9, 45233200-1, 45233294-6 | Demolition work, Demolition, site preparation and clearance work, Sewerage work, Various surface works, Installation of road signals | FALSE | 2016 | 2018 | Portugal | Cascais | Lisboa | 11 | N/A | 09-02-2017 | 21-02-2018 | 377 | 304 | 668285.4 | 400971.24 | 2 | 431016.9 | -30045.66 | 93.0291 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline: 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3326 | 3254531 | Km 10 river park, including accesses | 45212110-0 | Leisure centre construction work | FALSE | 2017 | 2019 | Portugal | Cinfães | Viseu | 20 | 20 | 19-04-2017 | 01-02-2019 | 653 | 120 | 315053.05 | 282000.02 | 2 | 293176.07 | -11176.05 | 96.1879 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of more works. | existence of more works and underwork.
3327 | 3250303 | Sanitation Network and Water Supply Network of the village of Milreu | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 05-04-2017 | 04-04-2019 | 729 | 90 | 340000 | 297562.67 | 2 | 282196.96 | 15365.71 | 105.445 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions for various reasons | complementary work and less
3328 | 3247639 | Construction of Wastewater Drainage Networks at Forte da Barra and Coastal Fishing Port of Aveiro | 45232400-6 | Sewer construction work | FALSE | 2016 | 2018 | Portugal | Ílhavo | Aveiro | 1 | 45 | 27-03-2017 | 06-02-2018 | 316 | 75 | 592000 | 521883.39 | 2 | 521850.29 | 33.1 | 100.0063 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in supplying equipment. | less quantity of works.
3329 | 3247469 | This procedure aims at signing a contract for the dredging of the main channel of the Mira River near its mouth and the transfer of sediments to Praia da Franquia | 45243400-6 | Beach-consolidation works | FALSE | 2016 | 2018 | Portugal | Odemira | Beja | 2 | 24 | 17-03-2017 | 10-08-2018 | 511 | 150 | 1177625 | 706575.01 | 2 | 923478.06 | -216903.05 | 76.5124 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of works and adaptation of the project to the restrictions imposed by the season | underwork
3330 | 3246577 | Demolition of existing pavements and repaving with 2 layers of bituminous mass with a total thickness of 10 cm | 45432110-8 | Floor-laying work | FALSE | 2016 | 2021 | Portugal | Amarante | Porto | 13 | 30 | 23-03-2017 | 26-01-2021 | 1405 | 180 | 410500 | 326228.02 | 2 | 333255.97 | -7027.95 | 97.8911 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in inspection for provisional acceptance | underwork and positive price revision
3331 | 3241560 | Construction of the Gym at Primary School António Gedeão | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2018 | Portugal | Odivelas | Lisboa | 11 | 20 | 05-04-2017 | 09-05-2018 | 399 | 180 | 489720.8 | 391776.64 | 2 | 391776.64 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with the provisions of point 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the supply and assembly of material related to the execution of the metal roof | failure to install electric water heaters
3332 | 3241331 | Requalification of the Arroja Fair in Odivelas | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Odivelas | Lisboa | 11 | 20 | 11-04-2017 | 26-02-2018 | 321 | 120 | 660000 | 514954.36 | 2 | 514954.36 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Item 14 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | burst of a water supply pipe. rocky composition of the soil found, conditioned the initial yields. | there were no changes to the value of the project
3333 | 3241271 | The object of this contract is the repair of ruptures in the wastewater drainage networks, in the water system of the Region of Aveiro. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2017 | 2019 | Portugal | Albergaria-a-Velha | Aveiro | 1 | N/A | 17-04-2017 | 25-01-2019 | 648 | 730 | 249000 | 198596.19 | 1 | 198596.19 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3334 | 3238378 | Construction of a building for a health center | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2019 | Portugal | Cadaval | Lisboa | 11 | 20 | 10-02-2017 | 27-05-2019 | 836 | 250 | 703280.91 | 657144.15 | 2 | 715417.81 | -58273.66 | 91.8546 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: In accordance with Annex V of the procedure; Bid price - 60.00%; Execution time - 40.00% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to term extensions totaling 225 days | more works worth 54,105.75. underwork worth 7,194.50. price revision in the amount of 11,362.41.
3335 | 3237306 | Rehabilitation in terms of public drainage systems for domestic wastewater and rainwater, roads, paving, as well as the public water distribution system | 45232460-4 | Sanitary works | FALSE | 2016 | 2019 | Portugal | Sesimbra | Setúbal | 17 | 30 | 24-02-2017 | 13-03-2019 | 747 | 210 | 622000 | 373200.01 | 2 | 433906.01 | -60706 | 86.0094 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | art. 312.º paragraph a9 of the "public procurement code" | paragraph a) and b) paragraph 1 of article 370 of the "public procurement code"
3336 | 3229798 | S.e.c. - PROCº nº 18/A1/17 - Public Tender for the contract award of "Requalification of the Public Area of ​​Areia - Darque". | 45233200-1 | Various surface works | FALSE | 2017 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 10-04-2017 | 01-03-2018 | 325 | 150 | 525000 | 445016.52 | 2 | 445016.52 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the Proposal - 60%; Price - 40%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3337 | 3228343 | Closure of the Water Network - Parish Casal Comba | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2019 | Portugal | Mealhada | Aveiro | 1 | 30 | 10-04-2017 | 25-11-2019 | 959 | 365 | 747950 | 668432.54 | 2 | 634837.18 | 33595.36 | 105.292 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of additional contracts (extra work and supply of errors and omissions). | existence of additional contracts (extra work and supply of errors and omissions).
3338 | 3224837 | Contract for "Beira Baixa Line - Pk 3,530/6,200 - Migration of wooden sleepers by biblock concrete" (contracts No. 5010023828). | 45234100-7 | Railway construction works | FALSE | 2016 | 2018 | Portugal | N/A | N/A | N/A | 35 | 03-04-2017 | 03-09-2018 | 518 | 90 | 342997 | 336551.98 | 2 | 310496.37 | 26055.61 | 108.3916 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | over and underwork
3339 | 3219405 | Work to improve Municipal Road 1025 | 45233220-7, 45232452-5 | Surface work for roads, Drainage works | FALSE | 2016 | 2018 | Portugal | Silves | Faro | 8 | 30 | 28-03-2017 | 17-07-2018 | 476 | 210 | 356072.7 | 316514.88 | 2 | 343657.35 | -27142.47 | 92.1019 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without changes | supply of errors and omissions in the amount of € 14,863.89 and price revision in the amount of € 12,278.58 and refund of the amount of the previous price revision.
3340 | 3215580 | Revitalization of the Urban Center of Moscavide | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | 30 | 17-10-2016 | 16-11-2018 | 760 | 144 | 783018.87 | 687599.44 | 2 | 674230.46 | 13368.98 | 101.9829 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) The award will be made according to the criterion of the most economically advantageous proposal, according to the factors and subfactors indicated below: ai) Factor (PP) - Proposal Price - 40% aii) Factor (PE) - Execution Time - 30% aiii) Factor (QT) - Technical Quality of the Proposal - 30% aiii-1) Subfactor (PT) - Work Plan compatible with the proposed deadline and adequate to the proposed phasing - 15% aiii-2) Subfactor (PME) - Equipment Mobilization Plan adapted to the conditions of the site and execution of the work - 15% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays arising from delays in work carried out by external entities, as well as the difficulty in defining and implementing cuts and alternative transit diversions for public transport. | ordinary review of prices based on definitive indexes and correction of measurements of work performed.
3341 | 3210802 | 0133/DOM/DGEPIM/16 - Requalification of the Comandante Joaquim Matias neighborhood, in Paço de Arcos | 45316000-5, 45233251-3 | Installation work of illumination and signalling systems, Resurfacing works | FALSE | 2016 | 2018 | Portugal | Oeiras | Lisboa | 11 | 30 | 29-03-2017 | 24-10-2018 | 574 | 180 | 415179.2 | 290625.45 | 2 | 264180.73 | 26444.72 | 110.0101 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3342 | 3208165 | Restructuring and rehabilitation of Largo 25 de Abril, Alameda and Surrounding Area | 45112700-2 | Landscaping work | FALSE | 2017 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 25 | 04-04-2017 | 02-07-2019 | 819 | 150 | 274450.5 | 271487.86 | 2 | 265331.76 | 6156.1 | 102.3202 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | existence of underworks
3343 | 3207986 | 0144/DOM/DGEPIM/16 - Construction of roundabout in Lage, Oeiras | 45316100-6, 45233128-2, 45232452-5, 45233294-6 | Installation of outdoor illumination equipment, Roundabout construction work, Drainage works, Installation of road signals | FALSE | 2016 | 2020 | Portugal | Oeiras | Lisboa | 11 | 42 | 29-03-2017 | 24-01-2020 | 1031 | 120 | 274270.08 | 236563.81 | 1 | 235317.51 | 1246.3 | 100.5296 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3344 | 3207586 | Regularization and Clearing of Ribeiras do Concelho | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 35 | 03-04-2017 | 31-01-2018 | 303 | 300 | 271959.7 | 205905.72 | 1 | 205905.72 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the stipulated timeframes.
3345 | 3207575 | This contract has a project for the execution of the defined works, regarding their type, quantity and technical conditions of execution, in the Project and in the Specifications | 45233221-4 | Road-surface painting work | FALSE | 2016 | 2018 | Portugal | Amadora | Lisboa | 11 | 30 | 24-03-2017 | 17-12-2018 | 633 | 550 | 264000 | 238000.5 | 1 | 254584.14 | -16583.64 | 93.486 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: 1st - Price (P) - 45%; 2nd - Quality of Work and Material (Q) - 40%; 3rd - Response Time (PR) - 15%. Price Factor The score will be from 0 to 10, and the values ​​will be calculated according to the following formula: a) If the price offered by competitor i is within the range: 0.8 x Base Price < Competitor price i <= Base Price The formula will apply Pi = 8x [(Base Price - Competitor Price i) / (Base Price - 0.8 x Base Price)] b) If the price presented by competitor i is: Competitor price i <= 0.8 x Base Price and if the abnormally low price justification is accepted, under the deadlines of number 4 of article 71 of the D.L. 18/2008, of January 29: The formula will apply Pi = 10 - 2 x [ Competitor Price i / (0.8 x Base Price) ] Where Pi corresponds to the score assigned to the price presented by competitor i. Work and Material Quality Factor All bidders whose bids are accepted must be available to demonstrate the quality of the work. and material, and in a period that does not exceed 15 working days, from the 1st scheduled date, in a place to be defined later, namely: - Execution of a treadmill in white thermoplastic; - Execution of a longitudinal line in white plastic spray (extension of 25 meters); - Execution of a longitudinal line in yellow plastic spray (25 meters long); - Marking of parking spaces in white aqueous paint (extension of 25 meters); The locations will be defined by the Traffic and Urban Furniture Division. After the demonstration and verification of the good quality, the jury of the tender will continue with the analysis of proposals. The Quality of work and material (Q) will be evaluated according to the following subfactors, evaluated during the execution of the tests and 15 days after its application: a) Drying time (TS) >= 50 1 [45;50[ 2 [40;45[3 [35;40[4 [30;35[5 [25;30[6 [20;25[7 [15;20[8 [10;15[9 <10 10 b) Color (C) Changed 1 Unchanged 10 c) Pigment (PG) Inadequate 1 Adequate 10 d) Grip to the floor (A) Bad 1 good 10 e) Degradation (D) With traces 1 no trace 10 f) Finishing level (NA) Bad 1 Reasonable 5 good 10 The value of zero will be assigned to the competitor who does not demonstrate the quality of work and material. The formula to be applied to evaluate each subfactor will be: - Drying Time TS = 0.25x TS White Thermoplastic + 0.25 x TS white plastic spray + 0.25 x TS yellow plastic spray + 0.25 x white aqueous TS - Color C = 0.25x C White Thermoplastic + 0.25x C white plastic spray + 0.25x C yellow plastic spray + 0.25 C white aqueous - Pigment PG = 1 x PG yellow plastic spray - Grip to the Floor A = 0.25x A White Thermoplastic + 0.25 x A white plastic spray + 0.25 x A yellow plastic spray + 0.25 A white aqueous - Degradation D = 0.25x D White Thermoplastic + 0.25 x D white plastic spray + 0.25 x D yellow plastic spray + 0.25 x D white aqueous - Finishing Level NA = 0.25x NA Thermoplastic White + 0.25 x NA white plastic spray + 0.25 x NA yellow plastic spray + 0.25 x aqueous NA white The formula to be applied to each competitor i will be: Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi Response Time Factor PR (days) - Score ]3;4] 1 ]2;3] 4 ]1;2] 7 [0;1] 10 The maximum response time allowed is 4 days. A value of zero will be assigned to the competitor who submits a response deadline greater than 4 days. The adjudication of this tender to be carried out between the Municipality of Amadora and the competitor with the highest classification will be performed after evaluating and scoring the results, obtained according to the mathematical expression described below: Final Score (PFi): PFi= 0.45xPi + 0.40xQi+ 0.15xPRi where Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi applied to each competitor (i). The tiebreaker will be based on the following criteria, rounding to the second decimal place: - In first place, an advantage will be attributed to the proposal with the best classification in the Price factor; - Secondly, an advantage will be given to the proposal with the highest score in the Work and Material Quality factor; - Thirdly, the proposal that obtained the lowest value in paragraph 3.1 of chapter 3 of the Unit Price List will be considered; - Fourthly, by drawing lots to be carried out with the presence of the legal representatives of each competitor whose proposals are in situation of a tie, and conducted by the Jury of the competition. | 1 | 45 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was planned and completed on schedule. | definitive price revision worth €16,583.64
3346 | 3204462 | Urban Requalification Contract for Largo Padre António Vieira, Vila de Rabo de Peixe | 45000000-7 | Construction work | FALSE | 2017 | 2018 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 28 | 03-04-2017 | 15-01-2018 | 287 | 240 | 318658.98 | 299951.53 | 2 | 299951.53 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
3347 | 3203769 | Construction of the Junqueira Roundabout, Intersection with Ex-EN109, in Cacia | 45233128-2 | Roundabout construction work | FALSE | 2016 | 2018 | Portugal | Aveiro | Aveiro | 1 | 22 | 20-02-2017 | 17-04-2018 | 421 | 90 | 218607.61 | 179731.34 | 1 | 191201.36 | -11470.02 | 94.0011 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions and extra work | extra work and work to supply errors and omissions
3348 | 3200362 | Intervention to protect the coastline in an area at risk on the island of Santa Maria, specifically the retention to the north of the coastal protection of the section north of the fishing port of Maia. | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | 32 | 01-09-2016 | 27-11-2018 | 817 | 120 | 410000 | 388000 | 2 | 388000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of the project (366.º "public procurement code"). extension of execution period.
3349 | 3194618 | Urbanization works at UGT 15 (AUGI) - Portela de Azóia neighborhood, Santa Iria de Azóia | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | 20 | 20-03-2017 | 29-10-2018 | 588 | 40 | 305994.71 | 207264.01 | 1 | 207264.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% deadline - 30% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3350 | 3193771 | Contract for the stabilization/consolidation contract for the cliffs at Praia da Zambujeira do Mar | 45243000-2 | Coastal-defence works | FALSE | 2016 | 2019 | Portugal | Odemira | Beja | 2 | 24 | 14-12-2016 | 15-03-2019 | 821 | 180 | 1089806.28 | 653883.77 | 2 | 621309.5 | 32574.27 | 105.2428 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of works and adaptation of the project to the restrictions imposed by the season | existence of underwork and price revision
3351 | 3188603 | 5010016079 - Work to stabilize the slopes between km 59+920 and km 82+950, ​​on the Beira Alta Line. | 45111230-9 | Ground-stabilisation work | FALSE | 2014 | 2020 | Portugal | N/A | N/A | N/A | N/A | 20-04-2016 | 10-03-2020 | 1420 | 393 | 2226000 | 1965206.45 | 3 | 2003623.12 | -38416.67 | 98.0826 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 50% 2. Technical Valuation - 30% 3. Safety Management System - 10% 4. Quality Management System - 5% 5. Environmental Management System - 5% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | miscellaneous | need to carry out more work
3352 | 3187447 | Refurbishment of street of Cutileiros - Creixomil | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 30-01-2017 | 08-02-2018 | 374 | 180 | 1393503 | 1228212.84 | 3 | 1244884.23 | -16671.39 | 98.6608 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60%; Technical value - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - suspension for 60 days (partial work suspension notice 1 of 10/4/2017) - work to be carried out by vimagua, namely the technical need to replace the water supply pipe; - notice of restart of works 1 - 4/12/2017; - suspension for 15 days (partial work suspension notice 2 - i of 10/10/2017) - work to be carried out by the edp company, namely, the need to replace the overhead electrical network with an underground network; - suspension 20 days (notice of partial suspension of works 2 - ii of 10/10/2017) - edp was unable to complete the project to replace the overhead electrical network with an underground network, maintaining the need for partial suspension of the contract; - notice of restart of works 2 - 11/14/2017. | underwork corresponding to the non-exhaustion of the quantities of work foreseen in the bill of quantities. interim pricing review.
3353 | 3186221 | Current conservation of the pavement of roads in the municipality of Guimarães - 2017 | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 24-03-2017 | 15-06-2018 | 448 | 365 | 368530.86 | 348714.23 | 2 | 348714.23 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was communicated on 04/20/2017.
3354 | 3183748 | Replacement of Exterior Frames, Air Conditioning, Lighting in Odemira elementary school | 45262800-9 | Building extension work | FALSE | 2016 | 2018 | Portugal | Odemira | Beja | 2 | 30 | 23-03-2017 | 22-11-2018 | 609 | 60 | 208741.26 | 203500 | 1 | 203500 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in equipment delivery
3355 | 3164307 | Rehabilitation of Avenida Afonso Costa and street of Ferrinho | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2016 | 2019 | Portugal | Guarda | Guarda | 9 | N/A | 20-03-2017 | 13-02-2019 | 695 | 120 | 355000 | 253000 | 2 | 257147.86 | -4147.86 | 98.387 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical value of the proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of term was approved for another 147 days, ending on 12/12/2017. on that day, the projects were inspected for the purpose of provisional acceptance, and it was found that they were not in accordance with the project and needed to be rectified and repaired, with a period of 60 days given to resolve the anomalies detected. | existence of price revision
3356 | 3162464 | Urban Arrangement Contract for Entroncamento at Largo da Feira - Improvement of ER 225 - 3rd phase | 45233120-6 | Road construction works | FALSE | 2016 | 2018 | Portugal | Arouca | Aveiro | 1 | 30 | 24-03-2017 | 21-09-2018 | 546 | 150 | 287978.73 | 249337.09 | 1 | 241808.35 | 7528.74 | 103.1135 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | existence of works in unnecessary quantities for the completion of the project.
3357 | 3162014 | Pontével School Center - Elementary School | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2021 | Portugal | Cartaxo | Santarém | 16 | N/A | 22-03-2017 | 01-02-2021 | 1412 | 365 | 1273455.29 | 1063017.61 | 3 | 1060628.27 | 2389.34 | 100.2253 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work on behalf of the developer and graceful extension requests, granted by the developer | underwork
3358 | 3158592 | For the execution of the contract called “Beira Alta line – replacement of bi-block concrete sleepers with mono-block concrete between kms 158,250/167,490” | 45234100-7 | Railway construction works | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 20 | 01-03-2017 | 09-05-2019 | 799 | 150 | 1130000 | 960087.45 | 2 | 960087.45 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (60% weighting) - FPREÇO Technical value (20% weighting) - FVT Safety Management System (10% weighting) - FSGS Quality Control System (5% weighting) - FSQ Environmental Monitoring System (5% weighting) - FSGA | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register
3359 | 3155370 | 5010023708 - Supply and assembly of 4 new mechanical ladders, with removal of existing ones that are at the end of their life cycle, at Queluz Belas Station | 45313200-6 | Escalator installation work | FALSE | 2016 | 2018 | Portugal | N/A | N/A | N/A | 32 | 10-03-2017 | 18-06-2018 | 465 | 90 | 321588 | 292050 | 2 | 298555.45 | -6505.45 | 97.821 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price (50% weighting) - FPRECIO b) Execution period (10% weighting) - Fdeadline c) Technical value (20% weighting) - FVT d) Safety Management System (10% weighting) - FSGS e) Quality Control System for the provision of services (5% weighting) - FSGQ f) Technical Note on Environmental Monitoring (5% weighting) - FNTAA | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3360 | 3152698 | For the execution of the contract called “anticorrosive protection of metallic bridges on the Minho line, phase 1” | 45221112-0 | Railway bridge construction work | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 25 | 10-03-2017 | 18-10-2019 | 952 | 210 | 900000 | 892342.13 | 2 | 886756.91 | 5585.22 | 100.6298 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award is made according to the criterion the most economically advantageous tender. 1- Price 55% 2- Technical Valuation 25% 3 - Security Management System 10% 4-Quality Control System 5% 5- Environmental Monitoring System 5% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the object of the contract consists of stripping and applying a new anticorrosive protection scheme. the painting work requires specific rules that, with high humidity, make it impossible to carry out the same. production and even redoing work already carried out, as a result of the above, the granting of a graceful extension of the deadline was inevitable.
3361 | 3151849 | Reformulation of the junction of EN 106 and EN 106-3 - Rotunda da Ribeira | 45233128-2 | Roundabout construction work | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 24 | 21-03-2017 | 15-07-2020 | 1212 | 140 | 400000 | 240000.01 | 1 | 208298.9 | 31701.11 | 115.219 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | some additional work essentially related to drainage and paving, as well as underwork resulting from the failure to build a gabion wall planned in the project.
3362 | 3147553 | Contract for requalification of typified paths. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Albufeira | Faro | 8 | 21 | 14-03-2017 | 20-03-2018 | 371 | 365 | 750000 | 618534.47 | 2 | 618534.47 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | awaiting decision of the court of auditors within the scope of the prior inspection of the process.
3363 | 3141728 | 100% Quality - Recovery of the 25 de Abril Park | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Matosinhos | Porto | 13 | 36 | 16-03-2017 | 12-11-2019 | 971 | 180 | 316042 | 189625.2 | 1 | 227974.2 | -38349 | 83.1784 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension notice from 04/03/2017 until restart notice 07/30/2017; notice of suspension 03/16/2018 for one month until 04/16/2018
3364 | 3141149 | 100% Quality - Superelevation of intersections and widening of sidewalks on streets ousa Aroso | 45233252-0 | Surface work for streets | FALSE | 2016 | 2019 | Portugal | Matosinhos | Porto | 13 | 10 | 16-03-2017 | 23-08-2019 | 890 | 60 | 149500 | 126877.8 | 1 | 175107.8 | -48230 | 72.457 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The most economically advantageous proposal having into account the following criteria: a) Price (60% weighting) b) Technical value (40% weighting) The final classification will result from the application of the following equation weighting the classifications obtained in each of the factors: Cf = 0.6 Pi + 0.4Vt Being: Cf = Final classification resulting from the weighted average Pi = Score of each Price proposal Vt = Technical value score | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
3365 | 3135952 | Contract for the Horta Corporate Reception Center | 45211350-7 | Multi-functional buildings construction work | FALSE | 2016 | 2019 | Portugal | Horta | Região Autónoma dos Açores | 15 | 36 | 03-02-2017 | 14-05-2019 | 830 | 300 | 1132765.64 | 1129545 | 3 | 1165249.31 | -35704.31 | 96.9359 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1- Price -60% K2 - Technical Quality of the Proposal - 40%, subdivided into two sub-factors: K2.1 - Work Plan: 70%; K2.2 - Descriptive and Justification of the Work Execution Mode: 30%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the term of the contract | extension of the term of the contract
3366 | 3132969 | WWTP West of Mangualde and Emissary | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2021 | Portugal | Mangualde | Viseu | 20 | 60 | 15-03-2017 | 16-09-2021 | 1646 | 913 | 3262029.41 | 2965500.01 | 3 | 3217314.5 | -251814.49 | 92.1731 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | according to information in the process | according to information in the process
3367 | 3129594 | Floor Repair 2016 | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Vagos | Aveiro | 1 | 30 | 10-03-2017 | 24-07-2018 | 501 | 180 | 348867.13 | 348118.94 | 2 | 329585.33 | 18533.61 | 105.6233 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension based on the occurrence of the devastating fires on 10/15/2017, which strongly affected the awarded company, preventing it from immediately continuing with the execution of the contract. extensions based on the occurrence of technical malfunctions of the equipment used on site. | resulting from measurements of the quantities of work actually carried out during the course of the project and, also, calculation of price revisions.
3368 | 3128279 | Contract for the execution of the HVAC installations at nos. 83 a and b and no. 85 a and b of av. Defensores de Chaves and n.º 45 of Av. Barbosa du bocage in lisbon | 45300000-0 | Building installation work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | 20 | 17-11-2016 | 12-12-2019 | 1120 | 59 | 299000 | 239256.64 | 1 | 253236.56 | -13979.92 | 94.4795 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | additional expenses
3369 | 3127461 | The object of this contract is the renovation of water supply networks, with approximately 1.8 km, in diameters of 110 and 400 mm, including 27 home branches. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2018 | Portugal | Aveiro | Aveiro | 1 | N/A | 10-03-2017 | 24-08-2018 | 532 | 60 | 188000 | 168149.52 | 1 | 163412.23 | 4737.29 | 102.899 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3370 | 3120379 | Construction of a building from scratch and rehabilitation of buildings. | 45262800-9 | Building extension work | FALSE | 2016 | 2019 | Portugal | Barreiro | Setúbal | 17 | 30 | 03-03-2017 | 06-02-2019 | 705 | 300 | 1589700 | 1583238.22 | 3 | 532096.02 | 1051142.2 | 297.5475 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Non-fulfilment of the contract (Revocation of the Contract) | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | design issue | contract revocation
3371 | 3119796 | EGA-AA0029 - S. Jorge Water Supply Subsystem. Pousadas Reservoir and Respective Supply Connection (Viana do Castelo) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 47 | 14-02-2017 | 22-01-2019 | 707 | 420 | 1450000 | 870000.01 | 2 | 826491.45 | 43508.56 | 105.2642 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price 50%; b) Technical value of the proposal, 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to point out | nothing to point out
3372 | 3119355 | EGA-EB0117 - Water Supply and Sanitation Infrastructure in Sta. Marinha do Zêzere - North (Baião) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2019 | Portugal | Baião | Porto | 13 | 50 | 14-02-2017 | 20-03-2019 | 764 | 300 | 900000 | 706561.69 | 2 | 681553.06 | 25008.63 | 103.6694 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: PRICE - 50% TECHNICAL VALUE OF THE PROPOSAL - 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | high number of unregistered infrastructures | alterations to the project that configured the cancellation of a lift, starting to work gravity.
3373 | 3116470 | The object of this contract is the construction of a gravity network in an extension of 7,788.20 meters of wastewater collectors, 410 home extensions, including the construction of 3 stations | 45232460-4 | Sanitary works | FALSE | 2016 | 2018 | Portugal | Águeda | Aveiro | 1 | N/A | 10-03-2017 | 15-10-2018 | 584 | 365 | 1050000 | 630000.01 | 2 | 571563.28 | 58436.73 | 110.224 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: A- PRICE: 55EUR B - TECHNICAL VALUES: 45% B.1 Work execution methodology: 20% B.2 Detail and consistency of the Work Plan: 15% B.2.1 Work Schedule: 10% B.2.2 Means Plan: 5% B.3 Characterization and quality of equipment and materials: 10% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | the construction of 1 pumping station was eliminated
3374 | 3112255 | S.e.c. - Proc no. 181/a1/16 - public tender for the award of the contract for "installation of a contact center - lot 61 - concession park at praia norte" | 45210000-2 | Building construction work | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 09-03-2017 | 16-04-2018 | 403 | 120 | 748500 | 697100.55 | 2 | 697100.55 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3375 | 3112171 | Masonry work, plastering and laying stonework, stucco, painting and other coatings, carpentry, work on non-structural profiles, plumbing and ducts in buildings | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | Barreiro | Setúbal | 17 | 25 | 20-02-2017 | 04-10-2019 | 956 | 180 | 323500 | 279801.92 | 2 | 309394.18 | -29592.26 | 90.4354 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | security conditions | works and more and less
3376 | 3109668 | Public Space Rehabilitation - Downtown - Phase I | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Alfandega da Fé | Bragança | 4 | 30 | 12-01-2017 | 15-03-2018 | 427 | 210 | 727168.2 | 559835.33 | 2 | 559835.33 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register | nothing to register
3377 | 3107025 | Consolidation of escarpments at Lugar de Lavadouro - S. Cristóvão de Nogueira | 45111230-9 | Ground-stabilisation work | FALSE | 2016 | 2019 | Portugal | Cinfães | Viseu | 20 | 20 | 17-01-2017 | 28-03-2019 | 800 | 180 | 292250 | 265325.33 | 2 | 241726.33 | 23599 | 109.7627 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climacteric | existence of over and underwork
3378 | 3103708 | The object of this contract is the execution of various works, in order to comply with EASA (European Aviation Safety Agency) regulations | 45235110-7 | Construction work for airfields | FALSE | 2016 | 2018 | Portugal | São Roque do Pico | Região Autónoma dos Açores | 15 | 25 | 30-01-2017 | 28-09-2018 | 606 | 180 | 194085 | 189940 | 1 | 189940 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | there were no changes to the value of the project
3379 | 3100782 | 5010024311 - Contract for "Supply and Assembly of a Debris Containment Structure on the Santana Bridge, at Pk 2+369 of the Belt Line" | 45221119-9 | Bridge renewal construction work | FALSE | 2016 | 2018 | Portugal | N/A | N/A | N/A | 40 | 06-03-2017 | 22-02-2018 | 353 | 110 | 350000 | 210000.01 | 1 | 211774.87 | -1774.86 | 99.1619 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price (60% weighting) - FPRECIO b) Technical value (20% weighting) - FVT c) Safety Management System (10% weighting) - FSGS d) Quality Control System (5% weighting) - FSQ e) Technical Note on Environmental Monitoring (5% weighting) - FNTAA | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3380 | 3097951 | Revitalization of the urban center of Camarate | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | 30 | 17-10-2016 | 28-11-2018 | 772 | 120 | 672669.07 | 538546.6 | 2 | 509875.59 | 28671.01 | 105.6231 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) The award will be made according to the criterion of the most economically advantageous proposal, according to the factors and subfactors indicated below: ai) Factor (PP) - Proposal Price - 40% aii) Factor (PE) - Execution Time - 30% aiii) Factor (QT) - Technical Quality of the Proposal - 30% aiii-1) Subfactor (PT) - Work Plan compatible with the proposed deadline and adequate to the proposed phasing - 15% aiii-2) Subfactor (PME) - Equipment Mobilization Plan adapted to the conditions of the site and execution of the work - 15% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays arising from delays in work performed by external entities. | corrections in the measurement of work performed and regular revision of prices based on definitive indexes
3381 | 3094386 | Refurbishment of sendim outdoor swimming pools | 45212212-5 | Construction work for swimming pool | FALSE | 2016 | 2018 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 10-02-2017 | 28-09-2018 | 595 | 180 | 309100 | 268950 | 2 | 242023.03 | 26926.97 | 111.1258 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension notice | underwork
3382 | 3093873 | It contemplates the improvement of the public space and the modernization of the infrastructures, the creation of parking and cycle-pedestrian routes along the entire river front of Areínho | 45233200-1 | Various surface works | FALSE | 2016 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 24-02-2017 | 15-03-2021 | 1480 | 270 | 1672797 | 1573880 | 3 | 1759012.73 | -185132.73 | 89.4752 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (Cp) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contracted period, however, the provisional acceptance notice was only drawn up on the date indicated, given the need for the contractor to correct anomalies in the project carried out. | the completion of the project resulted in: - additional work worth €87,529.96; - works to correct errors and omissions in the amount of €65,219.38; - underwork worth €76,223.44 and - price review
3383 | 3092820 | Replacement of the coverage of the pavilions at the Grândola fair | 45223100-7 | Assembly of metal structures | FALSE | 2016 | 2018 | Portugal | Grandola | Setúbal | 17 | 20 | 02-03-2017 | 24-05-2018 | 448 | 120 | 225000 | 198838.48 | 1 | 242045.72 | -43207.24 | 82.1491 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | over and underworks | over and underworks
3384 | 3088597 | Refurbishment of the water network and streets in Batão | 45231110-9, 45233252-0 | Pipelaying construction work, Surface work for streets | FALSE | 2016 | 2018 | Portugal | Alcácer do Sal | Setúbal | 17 | 31 | 09-02-2017 | 25-01-2018 | 350 | 240 | 231500 | 202935.38 | 1 | 176028.47 | 26906.91 | 115.2855 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with the provisions of no. 12 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the effective completion of the project was on 11/03/2017, as recorded in the project book, with the inspection for the purposes of «provisional receipt» having been scheduled for 11/13/2017. | underwork and price revision (provisional) - approved by resolution of the board of 01.25.2018
3385 | 3088223 | Remodeling of the municipal road e.m. 01 - Hostel / huts | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Alcácer do Sal | Setúbal | 17 | 30 | 20-02-2017 | 14-02-2018 | 359 | 210 | 423000 | 260538.01 | 2 | 275410.58 | -14872.57 | 94.5999 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied by the respective weighting coefficients: - In accordance with paragraph 12 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of the projects within the established period, with the inspection carried out for the purposes of provisional acceptance of the projects on 12.14.2017, due to the large volume of work of the services. | reason: final calculation of the price revision, which resulted in a plus (+) €14,872.82.
3386 | 3086470 | Requalification of Avenida Dr. Godinho Moreira | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Faro | Faro | 8 | 12 | 02-03-2017 | 26-09-2018 | 573 | 120 | 498902.5 | 480954.59 | 2 | 476284.37 | 4670.22 | 100.9806 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the project deadline | price review
3387 | 3086246 | Penalva do Castelo Road - Lisei | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Penalva do Castelo | Viseu | 20 | 21 | 02-03-2017 | 11-10-2018 | 588 | 365 | 521244.24 | 388775.69 | 2 | 37589.35 | 351186.34 | 1034.2709 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 75% Technical Value 25% (Justification and descriptive memory 40% Human resources and technical services to be allocated to the work 30% Medium and equipment to be allocated to the work 30%) | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork and supply of errors and omissions
3388 | 3082258 | 5010026498 - En230, km160+400. Embankment and road platform stabilization | 45233142-6 | Road-repair works | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 24 | 24-02-2017 | 22-11-2019 | 1001 | 120 | 500000 | 300000.01 | 2 | 316899.09 | -16899.08 | 94.6674 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% - Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | changes to the patented design for tender by the design team, due to the conditions of the foundation ground and due to the need to create accesses in the ph area for safe handling of the gate.
3389 | 3080831 | Contract for the Construction of Infrastructures for the Enhancement and Visitation of Classified Areas in the Municipality of Caminha | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Caminha | Viana do Castelo | 18 | 31 | 01-02-2017 | 15-11-2019 | 1017 | 180 | 255000 | 204000.01 | 1 | 194341.64 | 9658.37 | 104.9698 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was suspended for 155 days, since the project owner was contacted during the term of the contract by the company sociedade lisbonense de metalição, s.a., as a contractor contractor for an infrastructures of portugal (ip) construction on the railway bridge over the rio âncora, alerting that it would occupy the land where the pedoneral and cyclable bridge provided for in the project referred to in this report would be carried out, what type of works to be carried out there by ip and the type of equipment to use carried on high safety risks for the simultaneous process of the two contracts; as to the term extensions, they were granted in accordance with the following facts: the execution of the project coincid with a phase of exponential growth in the number of works in the country, which implicated a lot of difficulty in hiring labor, equipment and the delivery of materials by suppliers, meeting the specificity and complexity of the project; the above-mentioned suspension means that the bridge could only be started in the mid of autumn 2017 and the last months of that year and the first 4 months of 2018 (especially) were subject to very adverse weather conditions, which caused several floods on the river banks and making access to the project impassable.
3390 | 3080063 | Lot 1: Requalification of Avenida do Estádio (PAMUS 1.2 and PAMUS 2.1) | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Chaves | Vila Real | 19 | 30 | 23-02-2017 | 09-01-2018 | 320 | 150 | 641000 | 544199 | 2 | 532169 | 12030 | 102.2606 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 1st extension for a period of 44 days approved at a city council meeting on 08/18/2017. 2nd extension for a period of 46 days approved at a city council meeting on 11/02/2017. | underwork worth €12,030.00
3391 | 3077003 | Intervention in the public space of the São Mateus 2016 fair - civil construction | 45211310-5 | Bathrooms construction work | FALSE | 2016 | 2019 | Portugal | Viseu | Viseu | 20 | 20 | 25-04-2016 | 22-08-2019 | 1214 | 91 | 243600 | 208509.97 | 1 | 219440.15 | -10930.18 | 95.0191 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
3392 | 3065696 | Contract for the Requalification of Pavements and Water and Sewage Infrastructures in the Historic Center of Lagos - 2nd Phase | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Lagos | Faro | 8 | N/A | 17-02-2017 | 12-04-2018 | 419 | 150 | 315000 | 237715.92 | 1 | 252760.48 | -15044.56 | 94.0479 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the period of execution of the project was extended for another 78 days, as a grace | calculated the provisional value of price revision in the amount of € 15044.56
3393 | 3049218 | Contract 17/Gebalis/2016 - Public Tender for the maintenance and repair of fires and common areas in neighborhoods in the North East Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 17-02-2017 | 31-10-2018 | 621 | 730 | 600000 | 471681.88 | 2 | 471681.88 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | TRUE | N/A | the end of the contract will occur, as well and alternatively, when 24 months have elapsed since the beginning of the projects included in it or when the global amount of the projects carried out within its scope reaches the value for which the contract was awarded, regardless of the time elapsed since its inception
3394 | 3043781 | Improvement of CM 1150 from EN 207-2 to Largo da Feira | 45233140-2 | Roadworks | FALSE | 2016 | 2020 | Portugal | Lousada | Porto | 13 | 21 | 10-02-2017 | 21-12-2020 | 1410 | 120 | 360168 | 354763.2 | 2 | 354769.91 | -6.71 | 99.9981 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the execution of work by direct administration; process of expropriation of real estate and negotiation of land. | underwork/ price revision
3395 | 3042344 | Ecovia de Guimarães - 1st phase | 45233162-2 | Cycle path construction work | FALSE | 2016 | 2018 | Portugal | Guimarães | Braga | 3 | 20 | 30-01-2017 | 29-08-2018 | 576 | 180 | 3787385.08 | 2361921.28 | 3 | 2323514.65 | 38406.63 | 101.653 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60%; Technical value - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was only communicated on 05/08/2017. zone 2 section 10: - notice of partial work suspension: 08/01/2017 (90 days); - notice of partial suspension of work 2: 10/30/2017 (60 days); - work restart notice: 12/22/2017; zone 1 section 3: - notice of partial work suspension: 08/10/2017 (30 days); - notice of restart of works: 09/08/2017; zone 5 section 4: - notice of partial work suspension: 08/11/2017 (90 days); - notice of partial suspension of work 2: 11/09/2017 (90 days); - work restart notice: 02/05/2018; zone 1 section 1: - notice of partial work suspension: 08/16/2017 (120 days); - notice of partial suspension of work 2: 12/14/2017 (45 days); - notice of restart of works: 01/15/2018; zone 5 section 9: - notice of partial work suspension: 09/03/2017 (90 days); - notice of partial suspension of work 2: 11/30/2017 (45 days); - notice of restart of works: 01/11/2018; zone 5 section 7: - notice of partial work suspension: 09/11/2017 (90 days); - notice of partial suspension of work 2: 12/07/2017 (60 days); - notice of restart of works: 01/15/2018; | existence of underwork due to the foreseen quantities not being used up.
3396 | 3041779 | Refurbishment of School Buildings and Spaces - elementary school with Kindergarten in Ferreira do Alentejo. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2019 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 14-12-2016 | 28-02-2019 | 806 | 365 | 349000 | 332430.29 | 2 | 334425.65 | -1995.36 | 99.4033 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The criterion for evaluating the proposals will be that of economically most advantageous proposal, based on the following evaluation criteria:PF = 0.70xP + 0.30xVT, where:P - Price; VT - Technical Valuation; The Price Factor is calculated by the following formula: P = 100 - 50 x (Pp/Pb), where: P- price factor score;Pp - Price of the proposal under analysis; Pb - Base price of the tender (base value of the tender which, under the deadlines of the law, is the maximum price of the proposals). The technical value factor of the proposal will be the result of 3 factors: A - Work Program (40%); B - Descriptive Memory of the mode of execution of work (40%); C - Occupational Health and Safety Management (20%). Which results in the following expression mathematics: VT = 0.4 *A + 0.4*B + 0.2*C. The Work Program subfactor (A) is divided into 3 subfactors: A1- Work Plan (40%); A2 - Labor Plan (30%); A3 - Equipment Plan (30%) Which results in the following mathematical expression A = (0.4x(A1/4) + 0.3x(A2/4) + 0.3x(A3/4)) x 100. These criteria are broken down into sub-criteria, in accordance with point no. 19 of the Tender Programme. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | assignment of the contractual position of the co-contractor and harmonization of the project with the school calendar. | more works and errors and omissions supplies works
3397 | 3038138 | Requalification of the Montargil and Jardim das Afonsas entrances | 45112700-2 | Landscaping work | FALSE | 2016 | 2020 | Portugal | Ponte de Sor | Portalegre | 12 | 26 | 14-02-2017 | 06-10-2020 | 1330 | 120 | 169796.33 | 169449.44 | 1 | 168624.1 | 825.34 | 100.4895 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | existence of underworks
3398 | 3038123 | Public tender for awarding the contract for "remodeling the surroundings of the darque cemetery" - proc. 163/A1/16. | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 16-02-2017 | 19-07-2018 | 518 | 150 | 860000 | 583544.82 | 2 | 582476.41 | 1068.41 | 100.1834 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
3399 | 3032361 | Requalification of the banks of the River Caia next to the Municipal Swimming Pool | 45246200-5 | Riverbank protection works | FALSE | 2016 | 2018 | Portugal | Arronches | Portalegre | 12 | N/A | 19-01-2017 | 23-03-2018 | 428 | 270 | 623549.3 | 518891.92 | 2 | 504774.27 | 14117.65 | 102.7968 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a1) Price: 60 % a2) Descriptive and Justification of the Work Execution Method: 10% a3) Work Plan: 10% a4) Labor Plan: 10% a5) Equipment Plan: 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | doubts in work | on-site measurements resulted in underwork
3400 | 3030215 | Completion of the wastewater drainage subsystems - Lot No. 2 | 45232460-4 | Sanitary works | FALSE | 2016 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 18 | 13-02-2017 | 17-02-2021 | 1465 | 180 | 1889385.63 | 199548.5 | 1 | 202962.55 | -3414.05 | 98.3179 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the delivery of materials by suppliers and adverse weather conditions. | pricing review.
3401 | 3029240 | Contract for reconverting the old school building into a School of Traditions and Flavors and requalification of the public space Largo João Lopes Namorado and Largo das Escolas | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Alter do Chão | Portalegre | 12 | 18 | 08-02-2017 | 06-11-2018 | 636 | 244 | 335653.37 | 331975.03 | 2 | 362680.21 | -30705.18 | 91.5338 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Those provided for in point 14 of the program of the procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need to perform more work. alterations to the project during the course of the project in order to better serve the residents of the cluster, which led to limitations in the execution of the projects. during the contract there were still constraints caused by the replacement of the electricity distribution network.
3402 | 3029067 | Requalification of the Surrounding Area to the Fire Station | 45453100-8 | Refurbishment work | FALSE | 2016 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 20 | 14-02-2017 | 27-07-2021 | 1624 | 240 | 362783.2 | 277258.77 | 2 | 213949.66 | 63309.11 | 129.5907 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | degree of difficulty/slowness in carrying out the project higher than expected, adverse weather conditions, delay in the contract for the construction of the new cattle market and pandemic associated with covid 19. | deletion of works.
3403 | 3026857 | The object of this contract is the renovation of the water supply networks in Aveiro. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2018 | Portugal | Aveiro | Aveiro | 1 | N/A | 24-01-2017 | 14-05-2018 | 475 | 365 | 249000 | 175097.82 | 1 | 175097.82 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3404 | 3022900 | Construction of urbanization works in the Sernancelhe business district - phase 2 | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Sernancelhe | Viseu | 20 | 30 | 10-02-2017 | 13-04-2018 | 427 | 150 | 807226.49 | 686142.53 | 2 | 638376.35 | 47766.18 | 107.4824 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The criteria are those set out in point 12 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to suspension of the term | underwork
3405 | 3020900 | Execution of a traffic regulation roundabout at the Arnado intersection, in order to improve road fluidity and safety, execution of renovation and conservation work on pavements on the highway | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 02-11-2016 | 26-11-2018 | 754 | 180 | 483153.13 | 443865.33 | 2 | 342397.6 | 101467.73 | 129.6345 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | for safety reasons, to eliminate the inconvenience and inconvenience that the execution of the projects causes to passers-by, traders and residents and to traffic in general. that is, given the nature of the project, not confined, open to the public road and coexisting with high car traffic and passers-by, with the subsoil overfilled with existing infrastructure, which makes digging ditches and progressing with the projects of new infrastructure. once the project had started, the revocation of the contract would have caused serious difficulties on the roads that were the object of the project (public space), with serious consequences in terms of safety, accessibility and mobility of people, goods and vehicles, serious inconvenience and constraints due to the suspension of works, until the contractual resolution and new public contracting for its conclusion. | the amounts of work not carried out are due to over-measuring in view of the dimensions resulting from the drawn and written parts of the execution project, in most items of types of contractual work of the specialties aggregated in chapter, namely: preparatory work (chap. 1.), civil construction (chap. 2.), paving (chap. 3.), telecommunications infrastructure (chap. 4.), low voltage infrastructure (chapter 5.), public lighting infrastructure (chapter 6.) .), feeding directional arrows (chap. 7.), landscape integration (chap. 10.), urban solid waste (chap. 11.) and drainage networks (chap. 12.). there is a measurement deviation towards what is represented and detailed in the drawn parts, and what is detailed and described in the written parts of the execution project. the types of work in items 11.1, 11.2, 11.3 and 11.4, installation of buried containers for the collection of urban solid waste and ecopoint (cardboard, packaging and glass), were suppressed due to the existence of infrastructures in the implantation site (given the depth quotas in question, overlapping and detouring not being possible), which prevented it, as well as, it was also not possible in the other places studied and tested together with the employees of the environment division, in these, from the point of view exploration and obstacle/disruption for transit in the collection.
3406 | 3019070 | Contract work for "Tank for Receiving and Regularizing Leachate and Septic Tanks at the WWTP of Ribeira dos Moinhos" | 45247270-3 | Reservoir construction works | FALSE | 2015 | 2018 | Portugal | Sines | Setúbal | 17 | 26 | 22-12-2016 | 27-06-2018 | 552 | 180 | 500000 | 334665.12 | 2 | 343581.06 | -8915.94 | 97.405 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension note: the first inspection took place on 29-09-2017 | complementary works
3407 | 3017176 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Aveiro | Aveiro | 1 | N/A | 19-12-2016 | 22-05-2018 | 519 | 365 | 249000 | 189470.44 | 1 | 189470.44 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3408 | 3011291 | The work essentially consists of the execution of a bridge in metallic structure for bicycle lane and pedestrian crossing, execution of paved accesses in bituminous concrete and sidewalk | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 28-11-2016 | 10-12-2018 | 742 | 210 | 693596 | 610289.54 | 2 | 533447.87 | 76841.67 | 114.4047 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extensions or extensions | value of underwork and price revision
3409 | 3009928 | It consists of redefining the road platform in the pedestrian circulation area and parking spaces in order to facilitate and organize existing road traffic | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Amadora | Lisboa | 11 | 30 | 27-01-2017 | 20-09-2018 | 601 | 90 | 179520.4 | 152592.35 | 1 | 159198.91 | -6606.56 | 95.8501 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.35 * Pi + 0.65 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i Assessment of Factors and Subfactors: "Price" Factor The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out MDi = 100 Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform MDi = 65 Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of MDi detail = 30 Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest MDi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Presents a Work Plan with a correct sequence, with detailed detail and interconnection between PTi activities = 100 It presents a Work Plan with a correct sequence, with some details of the work to be carried out, allowing thus an interpretation of the interconnection between PTi activities = 65 It presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out PTi = 30 It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; Thirdly, the proposal that obtained the lowest value in chapter 3 of the Unit Price List will be considered; Fourthly, by drawing lots to be carried out in the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay in the execution of the project was essentially due to an intervention by simas, total replacement of the existing water network on that avenue, starting in august 2016 and ending in may 2017, which led to several stoppages of the project due to interventions simultaneously in several sections. | definitive price revision worth €6,606.56
3410 | 3008216 | Requalification of the West Access to S. Bartolomeu de Messines | 45233222-1 | Paving and asphalting works | FALSE | 2016 | 2019 | Portugal | Silves | Faro | 8 | 30 | 03-02-2017 | 28-05-2019 | 844 | 240 | 678839.49 | 595061.34 | 2 | 585247.98 | 9813.36 | 101.6768 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | underwork worth €19,550.78 and price revisions worth €9,737.42
3411 | 3004075 | The object of the contract is the repaving and road management in streets in the parish of Lourosa | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2018 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 08-02-2017 | 22-05-2018 | 468 | 120 | 250912 | 150547.21 | 1 | 151958.27 | -1411.06 | 99.0714 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% b) Technical quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance by the contractor, despite written requests. extension of the period between the 1st provisional reception (11/13/2017) and the final one (04/23/2018) for correction of defects of a physical and documentary nature. | work to supply errors (measurement) and omissions related to the leveling of existing infrastructures. additional work arising from having identified in loco the need to carry out a rainwater collection box and the respective connection to the existing rainwater network. underwork resulting from lags between project measurements and those of the project.
3412 | 3002673 | Application of a synthetic turf for competition in national championships | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2016 | 2018 | Portugal | São João da Madeira | Aveiro | 1 | 30 | 15-12-2016 | 22-10-2018 | 676 | 180 | 526400 | 463400 | 2 | 463400 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting) Technical value of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | land acquisition
3413 | 2993619 | Requalification of the Porcalho Zone. Supply and execution of Portuguese pavement pavement and execution of water supply infrastructure, rainwater drainage network and drainage network. | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Monção | Viana do Castelo | 18 | N/A | 17-01-2017 | 26-09-2018 | 617 | 365 | 276500 | 218242.01 | 1 | 236180.54 | -17938.53 | 92.4047 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the provisional acceptance notice was pending certification by certiel | need to carry out additional work.
3414 | 2991685 | Rehabilitation of City Waterbury Avenue and surrounding area | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2016 | 2020 | Portugal | Guarda | Guarda | 9 | N/A | 06-02-2017 | 04-02-2020 | 1093 | 90 | 340000 | 321817.94 | 2 | 325878.73 | -4060.79 | 98.7539 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulty in carrying out underground infrastructure, due to the lack of reliable records of existing infrastructure. | existence of price revision
3415 | 2990683 | Pavement Conservation | 45233200-1 | Various surface works | FALSE | 2016 | 2021 | Portugal | Guarda | Guarda | 9 | N/A | 06-02-2017 | 25-02-2021 | 1480 | 120 | 347555 | 337200 | 2 | 344708.05 | -7508.05 | 97.8219 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | inspections were carried out for the purposes of provisional acceptance, where anomalies were detected, and the contractor was notified to repair them. | existence of price revision
3416 | 2989620 | Recovery of Municipal Roads | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 01-02-2017 | 22-10-2018 | 628 | 60 | 285000 | 232982.25 | 1 | 373535.86 | -140553.61 | 62.3721 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension granted | due to overwork, underwork, and price revisions
3417 | 2987306 | Restoration and expansion of Escola do Bárrio, in Roriz. | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2018 | Portugal | Barcelos | Braga | 3 | 30 | 02-02-2017 | 28-08-2018 | 572 | 270 | 460321.63 | 417036.01 | 2 | 408531.48 | 8504.53 | 102.0817 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive memory and justification, of the way of execution of the work "MDJ" (25%); | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions. | predicted quantification errors.
3418 | 2985550 | Contract for the work "REQUALIFICATION OF C.M. 1208-1 Between C.M. 1208 AND house water | 45233141-9 | Road-maintenance works | FALSE | 2016 | 2018 | Portugal | Abrantes | Santarém | 16 | 36 | 01-02-2017 | 21-08-2018 | 566 | 90 | 254141.7 | 168309.55 | 1 | 182401.2 | -14091.65 | 92.2744 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project. | the change in the value of the project came after calculating the price revision, in accordance with the legislation and underwork.
3419 | 2983636 | Contract for EM Requalification Work. 546-1 Between Carvalhal and Souto and the E.N. 358 to Carvalhal | 45233141-9 | Road-maintenance works | FALSE | 2016 | 2018 | Portugal | Abrantes | Santarém | 16 | 36 | 01-02-2017 | 21-08-2018 | 566 | 60 | 314155.21 | 220964.41 | 1 | 239127.33 | -18162.92 | 92.4045 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project | there were no changes to the value of the project
3420 | 2980845 | Rehabilitation of Access and Recovery of Ribeiras - 1st. Stage - Casa da Ribeira | 45246000-3 | River regulation and flood control works | FALSE | 2016 | 2018 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 35 | 03-02-2017 | 31-07-2018 | 543 | 270 | 338959.79 | 302735.75 | 2 | 302735.75 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions
3421 | 2979237 | Contract 15/Gebalis/2016 - Public Tender for the maintenance and repair of fires and common areas in neighborhoods in the North West Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 24-01-2017 | 03-09-2018 | 587 | 730 | 600000 | 505000 | 2 | 505000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | TRUE | N/A | in accordance
3422 | 2978336 | Expansion of the Aljustrel Urban Cycle Path | 45233162-2 | Cycle path construction work | FALSE | 2016 | 2018 | Portugal | Aljustrel | Beja | 2 | 31 | 11-01-2017 | 30-04-2018 | 474 | 180 | 303000 | 264476.17 | 2 | 265982.62 | -1506.45 | 99.4336 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was extended by 116 days, due to the destruction, by summer fires, of the subcontractor's facilities on which the supply of wood for the walkway depended. | the effective total price indicated includes underwork worth €1602.00 and price revision - provisional calculation - worth €3108.45.
3423 | 2975820 | Alto da Eira Primary School - Refurbishment of the building | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | N/A | 29-06-2016 | 13-11-2018 | 867 | 75 | 677836.69 | 663090.01 | 2 | 712586.79 | -49496.78 | 93.0539 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price - 40% Work plan - 30% Execution Time - 30% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | citation of the administrative court of circle of lisbon, for the proc. 1512/16.obelsb – pre-contractual litigation process filed by famaconcret, lda and extension of 35 days takes into account the proportion between the estimated settlement of overwork, errors and omissions, and difficulties attributable to the contractor | work of an unpredictable nature such as demolition of walls and unloading of products to the dump and construction of masonry, finding errors and omissions detected during the construction phase with division of responsibility between the client and the contractor and others of the full responsibility of the client and adjustment of quantities on site and shipyard costs due to the extension of the term and damages suffered with the suspension of the project.
3424 | 2974708 | Execution contract for Electrical Installations and Equipment at nos. 83 A and 83 B and no. 85 A and B of Av. Defensores de Chaves and n.º 45 of Av. Barbosa du Bocage in Lisbon | 45310000-3 | Electrical installation work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 30-11-2016 | 19-11-2018 | 719 | 60 | 250000 | 202267.35 | 1 | 202267.35 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without description
3425 | 2973778 | Urban Rehabilitation of the Seat of the Municipality of Velas, São Jorge Island | 45113000-2 | Siteworks | FALSE | 2016 | 2018 | Portugal | Velas | Região Autónoma dos Açores | 15 | 35 | 26-01-2017 | 11-05-2018 | 470 | 240 | 1171965.88 | 1169150 | 3 | 1169150 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: 40% Price and 60% Technical Value of the Proposal | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | council resolution dated 01/19/2018, approved a period of 60 days from 12/29/2017, to correct the anomalies found in the 1st provisional acceptance notice (with reservations) dated 12/29/ 2017. | price revision pursuant to art. 382 of the "public procurement code".
3426 | 2973076 | Urban rehabilitation, phase I - in the parish of Paços de Brandão, municipality of Santa Maria da Feira. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 31-01-2017 | 10-07-2020 | 1256 | 180 | 466453 | 313830 | 2 | 310114.26 | 3715.74 | 101.1982 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% b) Technical quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 449 days of delay for which the contractor is responsible, 503 days between the 1st and the last inspection for the purposes of provisional acceptance in the correction of deficiencies | underwork
3427 | 2972004 | Restoration of the Sports Pavilion | 45212225-9 | Sports hall construction work | FALSE | 2016 | 2018 | Portugal | Entroncamento | Santarém | 16 | 30 | 25-01-2017 | 25-09-2018 | 608 | 240 | 576000 | 473631.71 | 2 | 478876.08 | -5244.37 | 98.9049 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | project errors and omissions
3428 | 2964862 | Renovation of training and teaching infrastructure in the municipality of Vila Pouca de Aguiar | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 21 | 27-01-2017 | 24-10-2018 | 635 | 270 | 887005.95 | 698998 | 2 | 713848.34 | -14850.34 | 97.9197 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in starting work (school activity). | pricing review.
3429 | 2946094 | This contract concerns the rehabilitation of C. M. 1464, Between E.N. 329 (Entroncamento next to Torre de Tavares) and the urban center of Vila Cova de Tavares | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Mangualde | Viseu | 20 | N/A | 20-01-2017 | 02-09-2019 | 955 | 180 | 183000 | 164700.01 | 1 | 122537.46 | 42162.55 | 134.4079 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | according to information in the process | less work in terms of information in the process.
3430 | 2942661 | Contract for the Chemical and Radiological Decontamination Works and Environmental Requalification in the Area of ​​the Former Chemical Treatment Workshops and Buildings of the Former Mining Perimeter | 45453100-8 | Refurbishment work | FALSE | 2016 | 2020 | Portugal | Nelas | Viseu | 20 | 31 | 11-01-2017 | 14-12-2020 | 1433 | 540 | 4000000 | 2693979.74 | 3 | 2816881.75 | -122902.01 | 95.6369 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60%; 2. Technical Value of the Proposal - 40%. (As indicated in the Contest Schedule). | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | financial complications of the consortium, difficulties in subcontracting, difficulties in the supply of materials | need to carry out additional work and to cancel contractual work as a result of unforeseen circumstances
3431 | 2940880 | Requalification of the fairgrounds and surrounding area | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Tábua | Coimbra | 6 | 20 | 16-01-2017 | 30-01-2019 | 744 | 180 | 345000 | 329108.7 | 2 | 339288.91 | -10180.21 | 96.9995 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 64 days - work to correct errors and omissions, 125 days - changes to infrastructure and delay in providing essential clarifications for carrying out the project, as well as the consequences arising from the fire of october 15, 120 days - adverse weather conditions, changes introduced to the initial project and the execution of unforeseen works and the fires of october 15 | errors and omissions supply works and work less
3432 | 2937590 | S.e.c. - Procº nº 205/A1/16 - Public Tender for the contract award of "Requalification of the Public Space of the Historic Center of Darque - streetManuel Espregueira, streets acadura Cabral | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 23-01-2017 | 01-03-2019 | 767 | 180 | 950000 | 938428.97 | 2 | 916464.15 | 21964.82 | 102.3967 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
3433 | 2925262 | Continuous bituminous paving contract - year 2015 | 45233200-1 | Various surface works | FALSE | 2015 | 2019 | Portugal | Viseu | Viseu | 20 | 24 | 12-10-2015 | 04-04-2019 | 1270 | 665 | 1000000 | 689000 | 2 | 627372.4 | 61627.6 | 109.8231 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork
3434 | 2915221 | Access to Minho Park - South Entrance. Construction of a diversion from an existing itinerary at E.M. 507 In the new industrial zone located in the Union of Parishes of Lapela and Troporiz. Earthworks are planned | 45432110-8 | Floor-laying work | FALSE | 2016 | 2018 | Portugal | Monção | Viana do Castelo | 18 | 30 | 18-08-2016 | 08-08-2018 | 720 | 365 | 435000 | 299335.67 | 2 | 259003.2 | 40332.47 | 115.5722 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work to be carried out for the installation of a water supply pipeline | as part of the management of the project, with the respective follow-up and inspection by the services, it was possible to make some works avoidable, without, however, affecting the good quality of the project.
3435 | 2904862 | En6-7, km 3+150; ic19, km 1+850. Pedestrian overpasses. Replacement of works of art" (under design/construction regime) with disposal of the material removed (steel/iron) | 45233144-0 | Overpass construction work | FALSE | 2015 | 2019 | Portugal | Lisboa | Lisboa | 11 | 26 | 14-12-2015 | 17-05-2019 | 1250 | 105 | 600000 | 514372.94 | 2 | 514372.94 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 15% - Technical value of the Preliminary Study: 5% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in the supply of materials.
3436 | 2898143 | FEM - Improvement of Roads - Weather | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 21 | 07-12-2016 | 05-06-2019 | 910 | 90 | 206600 | 197720 | 1 | 213357.26 | -15637.26 | 92.6709 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of the project | underwork and price revision
3437 | 2897041 | Circular desp. And Improvement of the Branca Sports Zone | 45233161-5 | Footpath construction work | FALSE | 2016 | 2019 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 21 | 07-12-2016 | 06-03-2019 | 819 | 120 | 199500 | 196077.42 | 1 | 247448.2 | -51370.78 | 79.2398 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of the project | additional work and price revision
3438 | 2892640 | International Public Tender no. 5-A1/2015 - The purpose of the procedure in question is the construction of the building – “Praça – Municipal Assistance”. | 45210000-2 | Building construction work | FALSE | 2015 | 2019 | Portugal | Vila Nova de Gaia | Porto | 13 | 47 | 21-12-2016 | 23-12-2019 | 1097 | 300 | 2500000 | 2125000 | 3 | 2355598.07 | -230598.07 | 90.2106 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award criterion is the proposal economically most advantageous, taking into account the following factors with the following weighting: a) Technical Quality of the Proposal - 55% b) Price - 45% These factors are, in turn, divided into different sub-factors duly weighted, as follows: a) Technical Quality of the Proposal (QTP) The Technical Quality of the Proposal will be carried out by evaluating the proposed methodology for the execution of the work, namely: a1) Work Program (Work plan, descriptive memory and justification of the work plan, Human resources plan to be to allocate to the work, Plan of technical means/equipment to be allocated to the work, payment plan) (PT) - 25% a2) Human resources to be allocated to the work (MH) - 25% a3) Technical means / equipment to be allocated to the work (MTE) - 25%; a4) Work Execution Methodology (MEO) - 25% For the evaluation of this factor, the documents to be presented by the bidders regarding items b3), (items i), ii), iii), iv) and v)), b4), b5), b6) and b7), of point 16.1 of this Tender Programme. Subfactors a1 to a4 will be evaluated in accordance with the stipulations in point 22.3 of the Tender Programme. QTP = 25% x PT + 25% x MH + 25% x MTE + 25% x MEO b) Price (P) The price evaluation factor will be assigned a score equal to or less than 10. The classification, in this factor, is attributed by application of the following expression: - If Bid Value Vi > EUR2,125,000 Score (Proposal i) = 9 x (2,500,000 - Vi) / (2,500,000 - 2,125,000) - If Bid Value Vi <= EUR2,125,000 - Score (Proposal i) = 10 - (Vi / 2,125,000) On what: Score (Proposal i) - score to be assigned to the Price factor, with a maximum value of 10 points Vi - proposal value i The final classification will be given by the following formula: CF = 55% x QTP + 45% x P The proposals are sorted in descending order according to the classification obtained. | 1 | 45 | N/A | TRUE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of extra work, supply of errors and omissions, and completion of overdue work. | the effective price of the contract includes additional work, price revision and correction of errors and omissions.
3439 | 2885928 | Completion of the wastewater drainage subsystems - Lot No. 5 | 45232460-4 | Sanitary works | FALSE | 2016 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 18 | 27-12-2016 | 18-02-2021 | 1514 | 180 | 1889385.63 | 294259.86 | 2 | 300060.89 | -5801.03 | 98.0667 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the delivery of materials by suppliers and adverse weather conditions. | pricing review.
3440 | 2884703 | The object of this contract is the construction of a domestic wastewater drainage system of approximately 6.9 km and a rainwater drainage system of approximately 1.0 km. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Estarreja | Aveiro | 1 | N/A | 11-01-2017 | 28-02-2018 | 413 | 240 | 950000 | 570000.01 | 2 | 555804.04 | 14195.97 | 102.5541 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment and materials - 10%) | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not carried out
3441 | 2882797 | Contract for the Rehabilitation of the Castelhana Outfall downstream of the A5 | 45232410-9 | Sewerage work | FALSE | 2015 | 2021 | Portugal | Cascais | Lisboa | 11 | 30 | 14-12-2016 | 21-04-2021 | 1589 | 330 | 1370000 | 878926.41 | 2 | 878926.41 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Global Price - 60% Technical value of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor was in a special revitalization plan (per); adverse weather conditions; occasional adjustments to construction processes. | occasional changes to construction processes.
3442 | 2879274 | Qualification of the Surrounding Zone to Malacate Vipasca | 45112700-2 | Landscaping work | FALSE | 2016 | 2018 | Portugal | Aljustrel | Beja | 2 | 31 | 04-01-2017 | 09-05-2018 | 490 | 180 | 208000 | 167963.72 | 1 | 169853.53 | -1889.81 | 98.8874 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | the value of the project includes provisional calculation of the price revision in the amount of €2218.43 and underwork in the amount of €793.98.
3443 | 2876607 | Assembly and disassembly of the support site for the work in general, earthmoving; indirect foundations; reinforced concrete and metallic structure; masonry, waterproofing and insulation, stonework; | 45212225-9 | Sports hall construction work | FALSE | 2016 | 2020 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 22-12-2016 | 13-11-2020 | 1422 | 365 | 1430000 | 987000 | 2 | 1011966.74 | -24966.74 | 97.5328 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (P) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the foreseen period, however, it was necessary for the contractor to correct defects in the project, which is why the provisional acceptance notice was only prepared on the date indicated. | with the completion of the project, underwork was carried out in the amount of €1,612.00 and a price review was carried out with definitive indices in the amount of €26,578.74.
3444 | 2875400 | Requalification of EN 338/EN16 - Maçainhas - Guard | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2016 | 2021 | Portugal | Guarda | Guarda | 9 | N/A | 06-01-2017 | 01-03-2021 | 1515 | 120 | 208819.6 | 208000 | 1 | 216341.34 | -8341.34 | 96.1444 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of extension of term | existence of price revision
3445 | 2874920 | Rehabilitation of the Cassapo and Raposo Reservoirs | 45259000-7 | Repair and maintenance of plant | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 20 | 03-01-2017 | 25-09-2018 | 630 | 129 | 208500 | 208470.86 | 1 | 274896.35 | -66425.49 | 75.8362 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) P - Price b) T - Technical Value The most economically advantageous proposal will result from the application of the factors with the following mathematical expression: c) K = 0.4xP + 0.6xT The criterion score (P) results from the following expression: If Vpc<=0.6xVpb => P = 100 If Vpc >0.6xVpb => P = [100 - (Vpcx100/Vpb)] x2.5 On what: Vpc - Competitor bid value Vpb - Base value of the tender The technical value of the proposal will be the result of 2 main factors, which in turn break down into sub-factors that are evaluated as stipulated in point 23 of the Program of Procedures. A - Work program (55%) B - Descriptive memory (45%) These factors will be weighted according to the following expression: T = 0.55xA + 0.45xB | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | as the execution of the project inside the pressure towers meant that they were out of service, which collided with the need to guarantee the public water supply to the populations, it was necessary (together with the contractor) to articulate in order to suspend the projects. added to this is the fact that, after unloading the reservoirs, additional work has been carried out. | in the reservoirs, there was an increase in complementary work, namely in terms of conservation and extension.
3446 | 2874270 | Rehabilitation of the Municipal Market and Arrangements of the Surrounding Area | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2019 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 13-12-2016 | 15-03-2019 | 822 | 365 | 526000 | 525900 | 2 | 531549.19 | -5649.19 | 98.9372 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The criterion for evaluating the proposals will be that of economically most advantageous proposal, based on the following evaluation criteria:PF = 0.70xP + 0.30xVT, where:P - Price; VT - Technical Value; The Price Factor is calculated by the following formula: P = 100 - 50 x (Pp/Pb), where: P- factor score price; Pp - Price of the proposal under analysis; Pb - Base price of the tender (base value of the tender which, under the deadlines of the law, is the maximum price of the proposals). The technical value factor of the proposal will be the result of 3 factors: A - Work Program (40%); B - Descriptive Memory the way in which the work is carried out (40%); C - Occupational Health and Safety Management (20%). Which results in the following expression math:VT = 0.4 *A + 0.4*B + 0.2*C The Work Program subfactor (A) is divided into 3 subfactors:A1- Work Plan (40%);A2 - Labor Plan (30%);A3 - Equipment Plan (30%). Which results in the following mathematical expression A = (0.4x(A1/4) + 0.3x(A2/4) + 0.3x(A3/4)) x 100. These criteria are decomposed into sub-criteria, in accordance with point no. 19 of the Tender Program | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | reformulation of the electrical installation project and delay in the execution of the electricity branch line and ited by the respective suppliers. | unforeseen work and work due to design errors and omissions.
3447 | 2874018 | Contract for the Logistic Interface of the Escariz Business Park | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Arouca | Aveiro | 1 | 30 | 09-01-2017 | 23-03-2018 | 438 | 240 | 542905.69 | 397650 | 2 | 366948.93 | 30701.07 | 108.3666 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | existence of underworks.
3448 | 2868231 | Construction of Day Center in Amoreira - A.S.I.A. | 45223100-7, 45220000-5, 45262522-6, 45233292-2, 45421000-4, 45231600-1, 45332400-7, 45432111-5, 45231300-8, 45313100-5, 45112700-2, 45421152-4, 45331000-6, 45112000-5, 45231221-0, 45231400-9, 45232130-2, 45100000-8 | Assembly of metal structures, Engineering works and construction works, Masonry work, Installation of safety equipment, Joinery work, Construction work for communication lines, Sanitary fixture installation work, Laying work of flexible floor coverings, Construction work for water and sewage pipelines, Lift installation work, Landscaping work, Installation of partition walls, Heating, ventilation and air-conditioning installation work, Excavating and earthmoving work, Gas supply mains construction work, Construction work for electricity power lines, Storm-water piping construction work, Site preparation work | FALSE | 2016 | 2020 | Portugal | Cascais | Lisboa | 11 | 30 | 03-01-2017 | 23-03-2020 | 1175 | 216 | 805141.11 | 681710.43 | 2 | 681710.43 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 90%; deadline: 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | changing works and correcting deficiencies
3449 | 2868141 | Completion of the Construction of a Nest of Companies | 45213250-0 | Construction work for industrial buildings | FALSE | 2016 | 2018 | Portugal | Arronches | Portalegre | 12 | 30 | 08-12-2016 | 20-04-2018 | 498 | 270 | 358900.24 | 354371.02 | 2 | 351202 | 3169.02 | 100.9023 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a1) Price: 60 % a2) Descriptive and Justification of the Work Execution Method: 10% a3) Work Plan: 10% a4) Labor Plan: 10% a5) Equipment Plan: 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | heavy rains caused land subsidence. | quantities measured on site that were too
3450 | 2859120 | Conservation and Improvement of streets in the Municipality of Almada - 2nd Action of 2016 | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 21 | 29-12-2016 | 29-01-2018 | 396 | 120 | 299720 | 229807.25 | 1 | 227917.25 | 1890 | 100.8292 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | underwork.
3451 | 2848797 | Completion of the wastewater drainage subsystems - Lot No. 8 | 45232460-4 | Sanitary works | FALSE | 2016 | 2021 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 18 | 19-12-2016 | 17-02-2021 | 1521 | 270 | 1889385.63 | 425102.99 | 2 | 433172.63 | -8069.64 | 98.1371 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the delivery of materials by suppliers and adverse weather conditions. | pricing review.
3452 | 2845708 | Refurbishment of the WWTP at Quinta do Seixo | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2016 | 2018 | Portugal | Trancoso | Guarda | 9 | 30 | 23-12-2016 | 03-10-2018 | 649 | 180 | 564983.99 | 383108.96 | 2 | 383108.96 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: In accordance with article 14 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | earthmoving delay by soil type (100% - rock) | there was no change in the value of the project
3453 | 2845312 | It consists of the execution of horizontal road signs, covering the northern geographical area of ​​the Municipality of Amadora, in places where there is a need to replace the existing signs | 45233221-4 | Road-surface painting work | FALSE | 2016 | 2018 | Portugal | Amadora | Lisboa | 11 | 30 | 29-12-2016 | 17-09-2018 | 627 | 550 | 264000 | 238000.05 | 1 | 253410.73 | -15410.68 | 93.9187 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: 1st - Price (P) - 45%; 2nd - Quality of Work and Material (Q) - 40%; 3rd - Response Time (PR) - 15%. Price Factor The score will be from 0 to 10, and the values ​​will be calculated according to the following formula: a) If the price offered by competitor i is within the range: 0.8 x Base Price < Competitor price i <= Base Price The formula will apply Pi = 8x [(Base Price - Competitor Price i) / (Base Price - 0.8 x Base Price)] b) If the price presented by competitor i is: Competitor price i <= 0.8 x Base Price and if the abnormally low price justification is accepted, under the deadlines of number 4 of article 71 of the D.L. 18/2008, of January 29: The formula will apply Pi = 10 - 2 x [ Competitor Price i / (0.8 x Base Price) ] Where Pi corresponds to the score assigned to the price presented by competitor i. Work and Material Quality Factor All bidders whose bids are accepted must be available to demonstrate the quality of the work. and material, and in a period that does not exceed 15 working days, from the 1st scheduled date, in a place to be defined later, namely: Execution of a treadmill in white thermoplastic; Execution of a longitudinal line in white plastic spray (extension of 25 meters); Execution of a longitudinal line in yellow plastic spray (extension of 25 meters); Marking of parking spaces in white aqueous paint (25 meters long); The Quality of work and material (Q) will be evaluated according to the following subfactors, evaluated during the execution of the tests and 15 days after its application: a) Drying time (TS) >= 50 1 [45;50[ 2 [40;45[3 [35;40[4 [30;35[5 [25;30[6 [20;25[7 [15;20[8 [10;15[9 <10 10 b) Color (C) Changed 1 Unchanged 10 c) Pigment (PG) Inadequate 1 Adequate 10 d) Grip to the floor (A) Bad 1 good 10 e) Degradation (D) With traces 1 no trace 10 f) Finishing level (NA) Bad 1 Reasonable 5 good 10 The value of zero will be assigned to the competitor who does not demonstrate the quality of work and material. The formula to be applied to evaluate each subfactor will be: Drying Time TS = 0.25x TS White Thermoplastic + 0.25 x TS white plastic spray + 0.25 x TS yellow plastic spray + 0.25 x white aqueous TS Color C = 0.25x C White Thermoplastic + 0.25x C white plastic spray + 0.25x C yellow plastic spray + 0.25 C white aqueous Pigment PG = 1 x PG yellow plastic spray Floor Adherence A = 0.25x A White Thermoplastic + 0.25 x A white plastic spray + 0.25 x A yellow plastic spray + 0.25 A white aqueous Degradation D = 0.25x D White Thermoplastic + 0.25 x D white plastic spray + 0.25 x D yellow plastic spray + 0.25 x D white aqueous Finish Level NA = 0.25x NA Thermoplastic White + 0.25 x NA white plastic spray + 0.25 x NA yellow plastic spray + 0.25 x aqueous NA white The formula to be applied to each competitor i will be: Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi Response Time Factor "Deadline for Response" means the period of time that elapses between the request for intervention made by the CMA to the contractor, and carrying out the work on site, referring to work that has not been previously planned and which, due to its relevance, if you want a quick intervention. ]3;4] 1 ]2;3] 4 ]1;2] 7 [0;1] 10 The maximum response time allowed is 4 days. A value of zero will be assigned to the competitor who submits a response deadline greater than 4 days. The adjudication of this tender to be carried out between the Municipality of Amadora and the competitor with the highest classification will be performed after evaluating and scoring the results, obtained according to the mathematical expression described below: Final Score (PFi): PFi= 0.45xPi + 0.40xQi+ 0.15xPRi where Qi = 0.175 x TSi + 0.175 x Ci + 0.125 x PGi + 0.175 x Ai + 0.175 x Di + 0.175 x NAi applied to each competitor (i). The tiebreaker will be based on the following criteria, rounding to the second decimal place: In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; Second, an advantage will be given to the proposal with the highest score in the Work and Material Quality factor; Thirdly, the proposal that obtained the lowest value in paragraph 3.1 of chapter 3 of the Unit Price List will be considered; Fourthly, by drawing lots to be carried out in the presence of the legal representatives of each competitor whose proposals are in situation of a tie, and conducted by the Jury of the competition. | 1 | 45 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the completion of the project was brought forward by two days because the scheduled end date would be on a sunday (july 22, 2018) and provisional reception was carried out on july 20 (friday) | the contractual price due to lapse was introduced incorrectly (238,000.05€) in the communication of the hiring report, it should be equal to the effective total price (238,000.50€). definitive price revision in the amount of €15,410.23.
3454 | 2844932 | Rehabilitation of streetNova de Santa Cruz - S. victor - braga | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Braga | Braga | 3 | 30 | 28-12-2016 | 05-02-2019 | 769 | 250 | 544780.18 | 373861.05 | 2 | 373861 | 0.05 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | rounding
3455 | 2844703 | 5010022653 - Construction and adaptation of the existing telecommunications infrastructure on the Alfarelos-Pampilhosa section to be carried out within the scope of the RIV. | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | N/A | N/A | N/A | 45 | 29-09-2016 | 19-02-2019 | 873 | 609 | 674500 | 612262.17 | 2 | 588054.47 | 24207.7 | 104.1166 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 50% - Technical value 30% - Security Management System 10% - Quality Management System 5% - Environmental Management System 5% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork (art. 379, no. 2 of the "public procurement code")
3456 | 2843320 | Contract 5/GEBALIS/2016 - Public tender Maintenance and Repair of Fires and Common Areas in Neighborhoods of the East Zone, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | N/A | 29-12-2016 | 15-10-2019 | 1020 | 720 | 599743.61 | 413927.88 | 2 | 413927.88 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | in accordance
3457 | 2835546 | Rehabilitation of the Viriato High school, Abraveses - Viseu | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2019 | Portugal | Viseu | Viseu | 20 | 12 | 17-11-2016 | 02-07-2019 | 957 | 238 | 505000 | 446613.43 | 2 | 459213.77 | -12600.34 | 97.2561 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work and carrying out additional work | more work and underwork
3458 | 2835242 | S.e.c. - PROC No. 154/A1/16 - Public Tender for the award of the contract for "Reformulation of the Canteen at Escola das Oliveiras" | 45454000-4 | Restructuring work | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 28-12-2016 | 27-02-2018 | 426 | 120 | 422368.75 | 401283.24 | 2 | 401283.24 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Bid Price - 40%, Technical Valuation of Proposal - 60%. The subfactors are those contained in article 18 of the tender program | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions
3459 | 2830353 | Execution of all the works necessary for the qualification of the buildings of the municipal social housing development, located at street ofs Valmarinhas, in the parish of Alfena - Municipality of Valongo | 45321000-3 | Thermal insulation work | FALSE | 2016 | 2018 | Portugal | Valongo | Porto | 13 | 12 | 28-12-2016 | 01-02-2018 | 400 | 120 | 330000 | 307748.99 | 2 | 312638.98 | -4889.99 | 98.4359 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | approval of a graceful 41-day extension of time (city council resolution of 06.08.2017) | approval by order of 07.04.2020 of the definitive price revision in the amount of €4,889.99 + vat.
3460 | 2828802 | Construction of the Alvalade Health Extension | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2018 | Portugal | Santiago do Cacém | Setúbal | 17 | N/A | 24-11-2016 | 01-08-2018 | 615 | 242 | 160000 | 154053 | 1 | 155687.61 | -1634.61 | 98.9501 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1 - Price - 70% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in carrying out the project for reasons due to the contractor | underwork and price revision
3461 | 2827498 | 5010020392 - Contract for the Anticorrosive Protection of Metallic Bridges on the North Line - Phase 3 | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2015 | 2018 | Portugal | N/A | N/A | N/A | 34 | 07-06-2016 | 03-05-2018 | 695 | 180 | 700000 | 670589.95 | 2 | 672970.72 | -2380.77 | 99.6462 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 55% - Technical value 25% - Security Management System 10% - Quality Management System 5% - Environmental Monitoring System 5% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | additional hours of services provided by inspection: - €1,549.59
3462 | 2826521 | Paving and infrastructure on Avenida da Igreja - São João de Vêr - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2018 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 27-12-2016 | 14-02-2018 | 414 | 120 | 370448 | 291662.71 | 2 | 271029 | 20633.71 | 107.6131 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60%; Technical quality of the proposal 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in execution under the responsibility of the contractor (147 days). | underwork and more work.
3463 | 2814795 | Requalification of the «pedro nunes» municipal museum | 45212313-3 | Museum construction work | FALSE | 2016 | 2019 | Portugal | Alcácer do Sal | Setúbal | 17 | 30 | 15-12-2016 | 17-10-2019 | 1036 | 300 | 440100 | 309200.01 | 2 | 302953.81 | 6246.2 | 102.0618 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: - In accordance with paragraph 12 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to extensions of the execution period granted to the contractor during the course of the project, due to some unforeseen circumstances and the complexity of the same, and non-compliance by the contractor. | errors and omissions supply - additional contract 1 (extra and underwork)
3464 | 2810011 | Rehabilitation of the Dorna and Surrounding Area | 45233252-0 | Surface work for streets | FALSE | 2016 | 2019 | Portugal | Guarda | Guarda | 9 | N/A | 07-12-2016 | 13-02-2019 | 798 | 180 | 357719.15 | 323000 | 2 | 348636.88 | -25636.88 | 92.6465 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of term was approved for another 190 days, ending on 12/12/2017. on that day, the projects were inspected for the purposes of provisional acceptance of the project, and it was found that they were not in compliance, with a period of 60 days being granted to resolve the anomalies detected. | existence of underwork and price revision
3465 | 2809441 | Enhancement of the sameeiro garden | 45112712-9 | Landscaping work for gardens | FALSE | 2016 | 2018 | Portugal | Penafiel | Porto | 13 | 12 | 12-12-2016 | 22-10-2018 | 679 | 90 | 360176.54 | 244808.29 | 1 | 244808.29 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension and suspension
3466 | 2805701 | It consists of carrying out the work defined as to its type, quantity and technical conditions of execution, in the Project and in the Tender Documents instructing the procedure | 45112711-2 | Landscaping work for parks | FALSE | 2016 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 22-12-2016 | 08-04-2019 | 837 | 120 | 366216.66 | 311284.17 | 2 | 323952.67 | -12668.5 | 96.0894 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i Assessment of Factors and Subfactors: "Price" Factor The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out MDi = 100; Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform MDi = 65; Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of MDi detail = 30; Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest MDi = 0. b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities PTi = 100; It presents a Work Plan with a correct sequence, with some details of the work to be carried out, allowing thus an interpretation of the interconnection between activities PTi = 65; It presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out PTi = 30; It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out PTi = 0. The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; Thirdly, the proposal that obtained the lowest value in chapter 3 of the Unit Price List will be considered; Fourthly, by drawing lots to be carried out in the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay was due to adverse weather conditions, which led to long periods of work stoppage, taking into account the specificity of the project, with large slopes of the sidewalks/paths (in some cases, greater than 20%/25%) and with the pavement of the aforementioned on gravel (soil/cement). the remaining time was due to the delivery of the elements to carry out the aforementioned, namely the "plan for the prevention and management of construction and demolition waste" and scheduling of inspection and carrying out the same. | provisional price review in the amount of €12,668.50.
3467 | 2804714 | Contract for the Protection, Consolidation and Enhancement of Fanal Bay - 1st Phase | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 21 | 19-12-2016 | 09-11-2018 | 690 | 365 | 844000 | 780000 | 2 | 775587.47 | 4412.53 | 100.5689 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
3468 | 2804254 | Paving streets in S. João dos Caldeireiros | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Mértola | Beja | 2 | 30 | 13-12-2016 | 28-02-2018 | 442 | 300 | 843255.39 | 636861.79 | 2 | 609550.69 | 27311.1 | 104.4805 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project. | underwork.
3469 | 2803893 | Requalification / Refurbishment of the elementary school of Cantanhede Sul, by Contract - CP-CCP-EMP n.º 11/2016 | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2016 | 2019 | Portugal | Cantanhede | Coimbra | 6 | 31 | 23-12-2016 | 15-11-2019 | 1057 | 180 | 800137.76 | 675999.97 | 2 | 705543.43 | -29543.46 | 95.8127 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of work | existence of extra work, underwork and revision of prices
3470 | 2796880 | Year 2016_Rehabilitation contract for the building located at Calçada do Patriarcal, 24-28 in Lisbon | 45200000-9, 45000000-7 | Works for complete or part construction and civil engineering work, Construction work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 06-12-2016 | 20-09-2018 | 653 | 365 | 720000 | 595000 | 2 | 661657.26 | -66657.26 | 89.9257 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to make adjustments to the project and to carry out additional work. | there was a need to make adjustments to the project and to carry out additional work.
3471 | 2796778 | S.e.c. - PROCº nº 162/A1/16 - Public Tender for the contract award of "Execution of the Pavilhão do Atlântico" | 45212200-8 | Construction work for sports facilities | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 21-12-2016 | 30-05-2018 | 525 | 180 | 1490000 | 1345777.63 | 3 | 1345777.63 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions
3472 | 2796073 | The object of the contract is the introduction of a central divider with green spaces (a continuation of the existing one), redefinition of the pedestrian circulation zone and parking spaces | 45233200-1 | Various surface works | FALSE | 2016 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 15-12-2016 | 23-01-2019 | 769 | 120 | 200726.2 | 170617.28 | 1 | 170617.28 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: The evaluation model is as follows: PF=0.35 * Pi + 0.65 * VTi On what: PF- Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i Assessment of Factors and Subfactors: "Price" Factor The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out MDi = 100 Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform MDi = 65 Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of MDi detail = 30 Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest MDi = 0 b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Presents a Work Plan with a correct sequence, with detailed detail and interconnection between PTi activities = 100 It presents a Work Plan with a correct sequence, with some details of the work to be carried out, allowing thus an interpretation of the interconnection between PTi activities = 65 It presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out PTi = 30 It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. The tiebreaker will be based on the following criteria, rounded to the second decimal place: In the first place, an advantage will be attributed to the proposal with the best classification in the Price factor; Secondly, an advantage will be attributed to the proposal with the highest score in the Descriptive Memory sub-factor; Thirdly, the proposal that obtained the lowest value in chapter 3 of the Unit Price List will be considered; Fourthly, by drawing lots to be carried out in the presence of the legal representatives of each competitor whose proposals are in tie situation, and conducted by the competition jury. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the increase in execution time had to do with: - maintenance of green spaces for 12 months; - the execution of the provisional acceptance was waiting for the contractor to delivery of elements, namely, the "plan for the prevention and management of construction and demolition waste" and the respective signature of the provisional acceptance document.
3473 | 2784099 | Contract for the Refurbishment of the Administrative Building of the Choupal WWTP | 45454000-4 | Restructuring work | FALSE | 2016 | 2018 | Portugal | Coimbra | Coimbra | 6 | 40 | 07-11-2016 | 26-01-2018 | 445 | 180 | 490000 | 427892.52 | 2 | 463081.08 | -35188.56 | 92.4012 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical Valuation 40% | 1 | 60 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this deadline change was a consequence of project changes that had repercussions on critical activities, conditions for meeting the deadlines. | due to underwork worth €22,582.69 and more work worth €57,771.25.
3474 | 2783007 | Restoration of the Old Town Hall Building | 45262800-9 | Building extension work | FALSE | 2016 | 2018 | Portugal | Penalva do Castelo | Viseu | 20 | 22 | 13-12-2016 | 29-10-2018 | 685 | 365 | 779582.56 | 639896.84 | 2 | 646843.61 | -6946.77 | 98.9261 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 75.00%; Technical Value of the Proposal - 25.00%. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork
3475 | 2781600 | Rehabilitation of the Old Fire Hall Building | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2016 | 2018 | Portugal | Rio Maior | Santarém | 16 | 20 | 25-11-2016 | 13-07-2018 | 595 | 120 | 399049.24 | 171922.08 | 1 | 165717.13 | 6204.95 | 103.7443 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the contractual period | underwork and positive price revision
3476 | 2778928 | The Second Contracting Party undertakes to carry out the contract for “Implementation of buried containers for the collection of urban solid waste – phase 2” | 45222110-3 | Waste disposal site construction work | FALSE | 2016 | 2018 | Portugal | Porto Santo | Região Autónoma da Madeira | 14 | 25 | 19-12-2016 | 16-07-2018 | 574 | 90 | 208000 | 177500 | 1 | 177500 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the supply of equipment, need to study changes to the project and relevant recommendations from the competent administrative authority._x000d_
3477 | 2778819 | "Reconversion of the old c+s school and Rehabilitation of the Fair Park" | 45112710-5 | Landscaping work for green areas | FALSE | 2016 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 12-12-2016 | 20-02-2019 | 800 | 150 | 254000 | 253634.12 | 2 | 250619.09 | 3015.03 | 101.203 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work for a total of 52 days | underwork worth €3015.04
3478 | 2775602 | Improvement of the EM 514-2 (A22/Quatro Estradas Viaduct) | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 16-12-2016 | 22-01-2019 | 767 | 90 | 212831.75 | 156873.51 | 1 | 175399.35 | -18525.84 | 89.4379 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful 15-day deadline extension and technical compilation delivery. | price revision in the amount of €18,525.84.
3479 | 2775333 | Year 2016_Rehabilitation contract for the building located at street of Diário de Notícias, n.º 11-13, in Lisbon | 45000000-7, 45200000-9 | Construction work, Works for complete or part construction and civil engineering work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 05-12-2016 | 24-09-2019 | 1023 | 270 | 220000 | 173384.93 | 1 | 206399.32 | -33014.39 | 84.0046 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need to carry out additional work resulted in an extension of the period for carrying out the project. | the need to carry out additional work resulted in an increase in the cost of the project.
3480 | 2761045 | Conservation works at E.M. 504, Between Cachopo and Mealha | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 13-12-2016 | 12-02-2019 | 791 | 90 | 481465.4 | 396488.71 | 2 | 443180.72 | -46692.01 | 89.4643 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delivery of the technical compilation. | definitive price revision in the amount of €46,692.01 (positive).
3481 | 2756179 | Construction of Caravanning Park in Almodôvar | 45212410-3 | Construction work for lodging buildings | FALSE | 2016 | 2021 | Portugal | Almodovar | Beja | 2 | 30 | 12-12-2016 | 27-05-2021 | 1627 | 240 | 475000 | 398449.29 | 2 | 370323.76 | 28125.53 | 107.5948 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional contracts, project changes, lack of labour, and suspension due to covid 19 | errors and omissions supply work €19,669.28, work less €53,020.47, and price revision €5,225.61
3482 | 2753270 | Urban Requalification of Penamacor - Phase 1: Urban Requalification of the Access to Cimo de Vila | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Penamacor | Castelo Branco | 5 | 14 | 06-12-2016 | 08-08-2018 | 610 | 180 | 329395.25 | 176540.99 | 1 | 225819.8 | -49278.81 | 78.1778 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline for 72 days approved at the board meeting of june 2, 2017. | additional work worth €50,046.81; errors and omissions in the amount of: €8,152.86; revision of prices in the amount of: €6,375.73; underwork in the amount of €13,316.35; responsibility of the performing entity for errors and omissions in the amount of: €1,980.24.
3483 | 2749686 | Construction contract for the Intergenerational Center of Vila Franca do Campo - Ponta Garça - Creche and ATL, with the characteristics defined in the technical clauses described in the specifications | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | Vila Franca do Campo | Região Autónoma dos Açores | 15 | 24 | 29-07-2016 | 30-05-2019 | 1035 | 420 | 1510000 | 1428503.4 | 3 | 1494894.17 | -66390.77 | 95.5588 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1 - Price - 40% K2 - Quality - 60% K2.1 - Work plan - 70% K2.2 - Descriptive memory and justification of how the work was carried out - 30% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | errors or omissions supply work not included in the initial contract and delay in the execution of the projects due to the projectload below the contractually foreseen, consubstantiated in the lack of general labour verified in the autonomous region of the azores | errors or omissions supply work not included in the initial contract and underwork
3484 | 2742883 | Aljustrel Cycling Corridor/Bairro de S. João do Deserto | 45233162-2 | Cycle path construction work | FALSE | 2016 | 2018 | Portugal | Aljustrel | Beja | 2 | 36 | 30-11-2016 | 15-01-2018 | 411 | 180 | 226000 | 199524.61 | 1 | 208052.97 | -8528.36 | 95.9009 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | final calculation of the price revision
3485 | 2741325 | Thermal Power Station for DHW Production and Remodeling of the Water Supply Network at Pavilhão Dr. eduardo tame | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 05-12-2016 | 06-02-2019 | 793 | 120 | 293554.68 | 238015.37 | 1 | 240752.3 | -2736.93 | 98.8632 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of deadline and delivery of documents.
3486 | 2739850 | Works for the Conservation and Improvement of the Road Network of the Municipality - Union of Parishes of Conceição – Cabanas and Santa Luzia | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 25-11-2016 | 21-01-2019 | 787 | 150 | 280500 | 216574.82 | 1 | 241374.14 | -24799.32 | 89.7258 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of the contract before the deadline. | price review
3487 | 2738039 | Conservation Works in Social Housing Buildings – Av. doctor Eduardo Mansinho n.º 1, R. Dr. Morais Simão n.º 1, R. De Santo António n.ºs 4, 6, 8, 10, 12 and 16, crossstreet of Santo António n.ºs 1, 2, 3 | 45262650-2 | Cladding works | FALSE | 2016 | 2020 | Portugal | Tavira | Faro | 8 | 24 | 02-12-2016 | 18-12-2020 | 1477 | 180 | 284534 | 244000 | 1 | 245323.14 | -1323.14 | 99.4607 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension. | underwork and price revision.
3488 | 2728171 | Construction/Expansion of the Lajedo ZIM - Terrain Modeling | 45112000-5 | Excavating and earthmoving work | FALSE | 2016 | 2018 | Portugal | Tondela | Viseu | 20 | 11 | 22-08-2016 | 28-05-2018 | 644 | 40 | 575968.87 | 552715.34 | 2 | 549217.34 | 3498 | 100.6369 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Those contained in article 12 of the program of procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the expected execution time.
3489 | 2723482 | Implementation of metallic structure, construction of sidewalks, bituminous paving, water, electricity and telecommunications networks. | 45233251-3 | Resurfacing works | FALSE | 2016 | 2019 | Portugal | Sertã | Castelo Branco | 5 | 20 | 05-12-2016 | 25-10-2019 | 1054 | 150 | 430000 | 386345.1 | 2 | 386345.1 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension and graceful extension | there were no changes to the value of the project
3490 | 2723323 | Year 2016_Contract for External Arrangements and Electrical Infrastructures of QGBT and QE of Hospital de Sant`Ana, in Parede | 45315000-8, 45315600-4 | Electrical installation work of heating and other electrical building-equipment, Low-voltage installation work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 30-11-2016 | 22-08-2018 | 630 | 90 | 950000 | 570000.01 | 2 | 655877.83 | -85877.82 | 86.9064 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the fact that the contract was developed next to a space assigned to another contract in progress, forced the realization of partial assignments and led to an increase in the execution period of the project. | performing Extra work, underworking and correcting errors and omissions.
3491 | 2722895 | CP01/2016/GIE - Construction contract for the Field Health Unit | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2018 | Portugal | Valongo | Porto | 13 | 30 | 28-11-2016 | 30-11-2018 | 732 | 365 | 859676.8 | 687741.45 | 2 | 706434.97 | -18693.52 | 97.3538 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70% B - Technical value of the proposal 30%: B1 - Descriptive memory 10% B2 - Work, labor, equipment and payment plans 10% B3 - Safety to be implemented in the work (technical note) 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions | overwork + underwork + omissions
3492 | 2722220 | The proposal foresees, throughout the area in question, the leveling of the area reserved for pedestrian circulation with the area reserved for car circulation (shared solution) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 15-07-2016 | 09-10-2018 | 816 | 300 | 469190 | 456865.84 | 2 | 463908.06 | -7042.22 | 98.482 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work without deadline extension | value of work less and value of price revision
3493 | 2721368 | Remodeling of networks dependent on the Brielas reservoir. Av. gen. Humberto Delgado and R. Eng.º Henrique Mendia in Costa da Caparica | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2019 | Portugal | Almada | Setúbal | 17 | 20 | 24-11-2016 | 08-01-2019 | 775 | 120 | 278008.73 | 189304.07 | 1 | 253915.07 | -64611 | 74.5541 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to point 23 of the procedures | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were some setbacks due to the need to cut water at a time of high consumption, as it is located in a bathing area. execution of the following additional works: existing infrastructure not identified in the project, sidewalk settlement conditions different from those expected, removal of rcd's found in excavation. changing accessories. delay in the delivery of the technical compilation that led to the acceptance of the contract occurs long after its physical conclusion. | there was too extra and underwork and errors and omissions already identified. there was also a financial rebalancing of the contract following night shifts.
3494 | 2719817 | Contract for the Execution of HVAC Installations destined for the New Installations in the Port of OTOC - Order of Official Accounting Technicians | 45300000-0 | Building installation work | FALSE | 2015 | 2018 | Portugal | Porto | Porto | 13 | 20 | 11-08-2015 | 23-03-2018 | 955 | 88 | 530000 | 353120 | 2 | 353120 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 23 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3495 | 2713563 | E.M repair 1123 Between Beliche de Baixo and Portela da Corcha | 45233142-6 | Road-repair works | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 08-07-2016 | 22-01-2019 | 928 | 90 | 329676 | 218879.07 | 1 | 230131.5 | -11252.43 | 95.1104 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension for 1 day due to the communication of the approval of the pss on 08/04/2016, graceful extension of 45 days and delivery of the technical compilation. | definitive price revision in the amount of €11,252.43.
3496 | 2712155 | Refurbishment of the WWTP in Vila Nova de Paiva | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2016 | 2019 | Portugal | Vila Nova de Paiva | Viseu | 20 | 24 | 11-11-2016 | 21-03-2019 | 860 | 240 | 700000 | 599916.5 | 2 | 646575.31 | -46658.81 | 92.7837 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | atmospheric conditions and execution of additional works | execution of additional work
3497 | 2709353 | Expansion of the sanitation network in Giela (Secas / Rochina) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 30 | 29-11-2016 | 20-08-2018 | 629 | 270 | 252500 | 212310.99 | 1 | 212310.97 | 0.02 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 50% - Lowest overall price; 50% - Technical value of the proposal. These criteria are decomposed into sub-criteria, in accordance with article 12 of the program of procedures | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3498 | 2708871 | The object of the contract is the requalification of the northern area of ​​the town of Vouzela. | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Vouzela | Viseu | 20 | 12 | 21-11-2016 | 03-08-2018 | 620 | 180 | 310000 | 277114.29 | 2 | 260155.54 | 16958.75 | 106.5187 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline for the project was due to a partial suspension determined by the owner of the project, for a period of 51 days, and that, after the circumstances that led to the suspension ended, the deadline was extended for an equal period, under the terms of the n.º 2 of article 298.º of the "public procurement code", in the wording prior to decree-law n.º 111-b/2017, of 31 august. | the value of the project was changed due to one less set of works.
3499 | 2706912 | Improvement of Game Parks | 45236119-7 | Repair work on sports fields | FALSE | 2016 | 2018 | Portugal | Lousada | Porto | 13 | 21 | 18-11-2016 | 03-04-2018 | 501 | 90 | 362368.36 | 362258.3 | 2 | 333610.93 | 28647.37 | 108.5871 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: For the purposes of calculating the final score of the proposal (PF), it will be obtained by applying the following mathematical formula, namely: PF=0.80A+0.20B Being that: PF=Final score of the proposal; A=Price (EUR); B=Guarantee for synthetic turf. The classifications of each of the factors mentioned above will be obtained through the following valuation methods: A) Price (EUR) - (80%) - to assess this factor, the score of each proposal will be calculated on a scale from 0 (zero) to 100 (one hundred) points, with a score of 0 (zero) points being assigned to the proposal corresponding to the established base price, to the remaining proposals will be scored with the normalization of the respective price presented at that price, according to the application of the following formula: A=[(PB-PP)/PB]x100 Being that: A= bid price score; PB= base price of the procedure; PP= price of the proposal under analysis. B) Synthetic grass guarantee - (20%) - to assess this factor, each proposal will be assigned the score obtained in accordance with the Following: - For the evaluation of this factor, the guarantee must be presented by the competitors. - The presentation of a guarantee period of less than 5 years for the synthetic grass implies the exclusion of the proposal (see point b) of number 1 of art. 37th) Synthetic grass warranty period: Warranty period equal to or greater than 10 (ten) years - 20 points Warranty period equal to or greater than 9 (nine) years and less than 10 (ten) years - 16 points Warranty period equal to or greater than 8 (eight) years and less than 9 (nine) years - 12 points Warranty period equal to or greater than 7 (seven) years and less than 8 (eight) years - 8 points Warranty period equal to or greater than 6 (six) years and less than 7 (seven) years - 4 points Warranty period equal to or greater than 5 (five) years and less than 6 (six) years - 0 points | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions prevented certain works from being carried out and caused damage to the synthetic turf, making it impossible to carry out other complementary works. | underwork
3500 | 2704510 | 5010027821 - En17, km9+200, stabilization of the embankment support wall | 45233142-6 | Road-repair works | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 24 | 14-11-2016 | 16-04-2020 | 1249 | 150 | 385000 | 306289.53 | 2 | 305933.01 | 356.52 | 100.1165 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | it was not necessary to carry out excavation using explosives
3501 | 2703264 | The object of this contract is the renovation of the water supply networks in Ovar. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2018 | Portugal | Aveiro | Aveiro | 1 | N/A | 21-11-2016 | 28-09-2018 | 676 | 365 | 249000 | 165194.94 | 1 | 165194.91 | 0.03 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3502 | 2693616 | Sanitation Network in the Municipality - Industrial Zone of Alijó | 45231000-5 | Construction work for pipelines, communication and power lines | FALSE | 2016 | 2020 | Portugal | Alijó | Vila Real | 19 | 15 | 14-10-2016 | 24-04-2020 | 1288 | 180 | 335881.49 | 239838.12 | 1 | 239838.12 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were delays in the project due to the licensing of the same with infraestruturas de portugal
3503 | 2686460 | Rehabilitation of the old prison for the installation of the Center for Cultural Development and Social Innovation - Rehabilitation of the surrounding public space | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2019 | Portugal | São Pedro do Sul | Viseu | 20 | 11 | 22-11-2016 | 19-12-2019 | 1122 | 180 | 182957 | 174906.73 | 1 | 181585.98 | -6679.25 | 96.3217 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the suspension of 43 days referred to above due to bad weather | the aforementioned price revision
3504 | 2675546 | Renovation of water distribution networks, of the Águas da Região de Aveiro system. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2019 | Portugal | Ílhavo | Aveiro | 1 | N/A | 18-11-2016 | 27-02-2019 | 831 | 1095 | 249000 | 175168.5 | 1 | 175168.5 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3505 | 2675064 | Improvement of C.M. 1480 - Parish of Gavião | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 26-10-2016 | 06-05-2019 | 922 | 300 | 590585.11 | 423886.47 | 2 | 475133.22 | -51246.75 | 89.2142 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical value of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | total suspension of work for 120 days. | price revision - addition of €25,813.54.
3506 | 2673474 | EGA-EB0071 - Improvement of the EM 615-2, between the EN 207 (Km 48.70) and Lugar da Telha (Antime, Silvares S. Clemente and Silvares S. Martinho) | 45232410-9 | Sewerage work | FALSE | 2016 | 2018 | Portugal | Fafe | Braga | 3 | 30 | 18-10-2016 | 06-12-2018 | 779 | 270 | 1002015.7 | 151040.95 | 1 | 152739.19 | -1698.24 | 98.8881 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a1) Factor - Price: 60% a2) Factor - Technical Valuation and guarantee of the proposal: 40% a2.1) Sub Factor - Descriptive and Justification: 50% a2.2) Sub Factor - Work Program: 50% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | since the contract was governed by an agreement between the contracting authorities, the projects of águas do norte were conditioned by the unavailability of private plots, planned to be intervened by the project of the municipal council of fafe | fewer branch boxes were made and the route on site was optimized.
3507 | 2672543 | Contract for the 2nd phase of requalification of the Santo Espírito sports center, Santa Maria | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | 35 | 01-09-2016 | 16-03-2018 | 561 | 150 | 170000 | 154082.54 | 1 | 154082.54 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension granted to contractor.
3508 | 2653948 | Contract for the Rehabilitation of the Dr. Francisco Sá Carneiro - Pedu | 45211360-0 | Urban development construction work | FALSE | 2016 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 11-11-2016 | 02-01-2019 | 782 | 180 | 834684.3 | 789000 | 2 | 783226 | 5774 | 100.7372 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was suspended. | underwork worth €5,774.00
3509 | 2636612 | The object of this contract is the execution of measurement and control points, of pressures and flows in the water supply network, in Ílhavo and Albergaria-a-Velha. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2018 | Portugal | Ílhavo | Aveiro | 1 | N/A | 20-10-2016 | 11-04-2018 | 538 | 120 | 210000 | 179053.25 | 1 | 172436.65 | 6616.6 | 103.8371 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contractual deadlines due to lack of municipal licensing | contracted works not performed
3510 | 2635125 | Improvement of E.M. 509/1 - Union of the parishes of Esmeriz and Cabeçudos | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 08-11-2016 | 10-04-2019 | 883 | 300 | 965864.23 | 648023.89 | 2 | 703013.6 | -54989.71 | 92.178 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60%; Technical value of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time. however, as the deadline corresponded to a non-working day, the project was received on the following working day. | underwork in the amount of €5,928.46 and review of prices to be paid in the amount of €60,918.17
3511 | 2633328 | Rehabilitation of blocks 53 to 56, 62 to 65 and 72 to 75 of Bairro de Santa Luzia (EM.004.2016.148) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2018 | Portugal | Porto | Porto | 13 | 20 | 24-10-2016 | 29-01-2018 | 462 | 300 | 1030000 | 992810 | 2 | 966412.96 | 26397.04 | 102.7314 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract work proceeds normally, with the contractor proceeding with the partial delivery of the blocks within the contractually foreseen completion deadlines. | errors and omissions worth €2,926.80 and work not performed worth €29,323.84
3512 | 2630696 | Contract for the Coastal Defense and Protection of People and Assets on the Praia Norte Maritime Front, and for the Requalification of the Praia Norte Maritime Front | 45243000-2 | Coastal-defence works | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 29 | 06-07-2016 | 21-09-2018 | 807 | 210 | 3050000 | 2421686.19 | 3 | 2420731.92 | 954.27 | 100.0394 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | performance of errors and omissions supply works, with extension of the period of execution of the work in 16 days; deadline extension of execution of the contract, sustained in convenience for the public interest, due to conditions that involve users of praia norte, namely, the elevated percentage of children's presence at that time. | underwork and carrying out work to supply errors and omissions
3513 | 2624431 | Social and Cultural Community Center - Finishing | 45215220-5 | Construction work for social facilities other than subsidised residential accommodation | FALSE | 2016 | 2020 | Portugal | Loures | Lisboa | 11 | 30 | 22-07-2016 | 18-11-2020 | 1580 | 230 | 2383060.71 | 1719630.74 | 3 | 1747507.03 | -27876.29 | 98.4048 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Proposal price: 40% Work plan: 50% Execution time: 10% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | considering the request for an extension of the deadline for completion of the project until 30.06.2017, requested by the company tps-teixeira pinto & soares, s.a. and taking into account the evolution of the projects with some constraints that occurred during the same. | contract no. 100/2016 was drawn up - consignment on 10.03.2016 - execution period of 230 days (completion scheduled for 05.21.2017) on 08.24.2017, by contract no. 143/2017, the second clause of initial contract no. 100/2016 was modified, referring to the execution period, which increased to 271 days (with completion scheduled for 07.01.2017)
3514 | 2620471 | The object of this contract is the execution, by the second party to the first party, of the contract «Remodeling of the future premises of the Loja do Cidadão de Carregal do Sal». | 45262700-8 | Building alteration work | FALSE | 2016 | 2018 | Portugal | Carregal do Sal | Viseu | 20 | 20 | 28-10-2016 | 28-03-2018 | 516 | 300 | 442000 | 348488.41 | 2 | 335865.2 | 12623.21 | 103.7584 | lowest price | 2 | 100 | N/A | FALSE | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline changes are due to deadline extensions granted by the developer. | changes in the value of the project are due to the fact that some quantities estimated in the project were not fully executed, which led to a value of underwork, as shown in the final account.
3515 | 2617882 | Repaving of EM 513-1 and CM 1217, parish of Santa Catarina da Fonte do Bispo | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 02-11-2016 | 24-01-2019 | 813 | 180 | 966039.62 | 623446.47 | 2 | 732605.68 | -109159.21 | 85.0999 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor completed the project ahead of schedule. | underwork worth -1,561.98€ and definitive price revision worth €110,721.19 (positive).
3516 | 2616204 | Urban Requalification of the Mineiro District of S. João do Deserto | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Aljustrel | Beja | 2 | 42 | 13-10-2016 | 15-01-2018 | 459 | 180 | 183500 | 162228.78 | 1 | 168189.85 | -5961.07 | 96.4557 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | final calculation of the price revision
3517 | 2594163 | Various tours in the city - Group I/2016 | 45233253-7 | Surface work for footpaths | FALSE | 2016 | 2018 | Portugal | Bragança | Bragança | 4 | 20 | 27-10-2016 | 14-02-2018 | 475 | 180 | 349000 | 226889.75 | 1 | 170113.82 | 56775.93 | 133.3753 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting) Technical quality of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | breakage of essential materials for the proper execution of the missing works. | underwork
3518 | 2591480 | Refurbishment contract for the Ervedal da Beira Health Unit | 45215100-8 | Construction work for buildings relating to health | FALSE | 2016 | 2018 | Portugal | Oliveira do Hospital | Coimbra | 6 | 21 | 26-10-2016 | 08-03-2018 | 498 | 210 | 340000 | 277572.06 | 2 | 288124.49 | -10552.43 | 96.3375 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of work monitoring/approval of inspection materials and equipment by arsc technicians. - suspension | over and underwork.
3519 | 2587276 | Execution of Sidewalks on the Main Road of Tocha (EN109), by Contract: Section between KM97+334 and KM98+221 - CP-CCP-EMP No. 10/2016 | 45113000-2 | Siteworks | FALSE | 2016 | 2020 | Portugal | Cantanhede | Coimbra | 6 | 20 | 27-10-2016 | 20-04-2020 | 1271 | 180 | 377000 | 336760.42 | 2 | 325088.33 | 11672.09 | 103.5904 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completion of works, some of them were readjusted | existence of extra and underwork and errors and omissions
3520 | 2585410 | The object of this contract is the construction of a gravity network in an extension of 11,654 m of wastewater collectors, in PP of DN 200mm (10,195 m) and DN 250mm (1,459 m), 724 domicile branches | 45232460-4 | Sanitary works | FALSE | 2015 | 2018 | Portugal | Vagos | Aveiro | 1 | N/A | 21-10-2016 | 16-03-2018 | 511 | 365 | 1500000 | 1113275.29 | 3 | 1039673.79 | 73601.5 | 107.0793 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - price: 55% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3521 | 2580086 | Demolitions, floor and wall coverings, false ceilings and electrical, ITED and security infrastructure work. | 45453100-8 | Refurbishment work | FALSE | 2016 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 22-10-2016 | 04-01-2018 | 439 | 120 | 670000 | 550000 | 2 | 549840.01 | 159.99 | 100.0291 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (P) 50%; Technical quality of the proposal (QTP) 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | three deadline extension notices were drawn up, duly authorized. | the completion of the project resulted in underwork.
3522 | 2579452 | The object of this contract is the construction of the wastewater drainage network with a total length of 34 653 meters and 1 554 home branches with the respective manholes | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Ovar | Aveiro | 1 | N/A | 18-10-2016 | 18-10-2018 | 730 | 365 | 3500000 | 2100000.01 | 3 | 2028436.29 | 71563.72 | 103.528 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractual deadlines not met by the winning company | work not done
3523 | 2576780 | Improvement of C.M. 1527 - Parish of Delães, Oliveira S. Mateus and Oliveira Sta. Maria | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 20-10-2016 | 11-06-2019 | 964 | 300 | 1016000 | 689250.19 | 2 | 750555.24 | -61305.05 | 91.832 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical value of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule (300+270 days). | addition due to price review.
3524 | 2576660 | Improvement of C. M. 1500/1 - Parish of Mogege | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 20-10-2016 | 11-06-2019 | 964 | 300 | 480000 | 320231.74 | 2 | 350957.09 | -30725.35 | 91.2453 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical value of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work for a period of 60 days. | addition of price revision value.
3525 | 2576556 | Improvement of Avenida Rio Veirão - Ribeirão | 45233140-2 | Roadworks | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 20-10-2016 | 10-04-2019 | 902 | 300 | 1100000 | 729922.87 | 2 | 800635.52 | -70712.65 | 91.1679 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical value of the proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of the project for a period of 120 days. | price revision, amount payable to the contractor: €70,712.65
3526 | 2576075 | Contract for "Rehabilitation of Elementary School n.º 3 in Lagos" | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2018 | Portugal | Lagos | Faro | 8 | N/A | 11-10-2016 | 31-01-2018 | 477 | 150 | 940000 | 888501.47 | 2 | 888501.47 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | design constraints, delayed delivery of materials, and changes to anticipated source work | the value of the project has not changed
3527 | 2563241 | The contract includes the expansion and renovation of elementary school No. 3, in Vila Nova de Santo André. | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2018 | Portugal | Santiago do Cacém | Setúbal | 17 | 31 | 06-10-2016 | 28-11-2018 | 783 | 270 | 650000 | 596029.71 | 2 | 596029.71 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the supply of materials from suppliers to the contractor, due to the vacation period. | more unforeseen works.
3528 | 2560552 | Refurbishment of Facades and Roofing of the Old Celtex Factory and Refurbishment of the Machine Park | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Marvão | Portalegre | 12 | 32 | 19-10-2016 | 10-10-2018 | 721 | 150 | 732326.05 | 687376.42 | 2 | 676944.98 | 10431.44 | 101.541 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the end of the projects was on the date of 03-04-2017 | underwork worth €10,431.44, approved by decision of the city council on 30-03-2017
3529 | 2550389 | Infrastructures of the Laranjal Allotment, in Montargil | 45111290-7 | Primary works for services | FALSE | 2016 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 18-10-2016 | 03-07-2019 | 988 | 120 | 346507.15 | 284800.7 | 2 | 284800.7 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension granted
3530 | 2542997 | Paving in bituminous concrete, of streets in the county - 3rd Phase - Santa Maria da Feira. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 18-10-2016 | 08-04-2020 | 1268 | 120 | 945750 | 611428.18 | 2 | 630478.88 | -19050.7 | 96.9784 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 5 days due to additional work, 599 days due to delays for which the contractor is responsible, 473 days elapsed between the 1st inspection and the date of provisional acceptance | over and underwork
3531 | 2542840 | Contract for the Environmental Recovery Works of the Former Mining Areas of Castelejo, Formiga, Vale de Videira, Vales and Póvoa de Cervães | 45112500-0 | Earthmoving work | FALSE | 2015 | 2018 | Portugal | Fornos de Algodres | Viseu | 20 | 29 | 12-10-2016 | 19-02-2018 | 495 | 365 | 4000000 | 2400000.01 | 3 | 2479454.55 | -79454.54 | 96.7955 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 25 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the contractual period | the change in the value of the project was due to the revision of prices
3532 | 2542522 | 0097/DOM/DGEPIM/16 - Landscaping requalification of streetAlmirante Sousa Dias, Oeiras | 45232452-5, 45112700-2, 45233252-0, 45316100-6 | Drainage works, Landscaping work, Surface work for streets, Installation of outdoor illumination equipment | FALSE | 2016 | 2020 | Portugal | Oeiras | Lisboa | 11 | 30 | 10-10-2016 | 06-07-2020 | 1365 | 90 | 287654.85 | 227079.96 | 1 | 246711.25 | -19631.29 | 92.0428 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension | over and underwork
3533 | 2538496 | US Baguim do Monte - Construction contract_x000D_ | 45215100-8 | Construction work for buildings relating to health | FALSE | 2015 | 2018 | Portugal | Gondomar | Porto | 13 | 30 | 19-09-2016 | 30-05-2018 | 618 | 630 | 796785.78 | 610000 | 2 | 578477.88 | 31522.12 | 105.4491 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70%; B - Technical value of the proposal 30%: B1 - Descriptive memory 10%; B2 - Work, labor, equipment and payment plans 10%; B3 - Security a implement in the work (technical note) 10%. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | initially, the contractual term was reduced and, later, the need was verified due to adverse weather conditions and was extended. | less approved works
3534 | 2536453 | Construction of the Santa Luzia Neighborhood Community Center | 45212422-0 | Canteen construction work | FALSE | 2016 | 2018 | Portugal | Elvas | Portalegre | 12 | 24 | 07-10-2016 | 16-04-2018 | 556 | 300 | 432000 | 409600.03 | 2 | 404546.06 | 5053.97 | 101.2493 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The basic criteria for assessing proposals are those established in paragraph b) of paragraph 1 of article 74 of the Public Procurement Code, namely the economically most advantageous, for the contracting entity, based on the factors and sub-factors, designated in article 5 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to make several corrections in order to be able to receive the project. | existence of excessive amounts in the bill of quantities and works that were not performed because they were not necessary.
3535 | 2530607 | Multimodal Toll Plaza - Exterior Arrangements | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Marvão | Portalegre | 12 | 32 | 07-10-2016 | 07-02-2018 | 488 | 150 | 279935.28 | 245750.7 | 1 | 275438.21 | -29687.51 | 89.2217 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the end of the projects was on the date of 10-04-2017
3536 | 2525424 | Domestic wastewater sanitation system in place of Souto Côvo | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | Lamego | Viseu | 20 | 15 | 13-10-2016 | 20-03-2019 | 888 | 450 | 726501.25 | 526880.61 | 2 | 526880.61 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a suspension auto
3537 | 2519889 | Requalification of the CM 1218, which connects the EM 532 of the Union of Parishes of Colmeias and Memory to the EN 350, Parish of Caranguejeira | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Leiria | Leiria | 10 | 20 | 11-10-2016 | 15-02-2018 | 492 | 300 | 940623.15 | 763489.94 | 2 | 763498.94 | -9 | 99.9988 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change | there were no value changes
3538 | 2501846 | The object of this contract is the construction of a gravity network over a length of 9,920 m of wastewater collectors, in PP of DN 250mm (313 m) and DN 200mm (9,607 m), 469 home branches | 45232460-4 | Sanitary works | FALSE | 2016 | 2018 | Portugal | Vagos | Aveiro | 1 | N/A | 06-09-2016 | 23-02-2018 | 535 | 365 | 1500000 | 1079154.31 | 3 | 877647.76 | 201506.55 | 122.9598 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: 1 - price: 55% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
3539 | 2497441 | Repaving and Requalification of the E.M. From Vila Nova to Ramires | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Cinfães | Viseu | 20 | 20 | 03-08-2016 | 07-03-2018 | 581 | 120 | 339586.55 | 184218 | 1 | 225150.02 | -40932.02 | 81.8201 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term suspension. | the presentation of more works, underwork and price revision.
3540 | 2496748 | Asphaltic and non-asphalt repairs on municipal roads (Repaving of E.M. De Cosconhe a Vilarinho - Piães; Repaving of E.M. Da e.n. 222 A Pousada - Espadanedo; E.M. Da Gralheira | 45233140-2 | Roadworks | FALSE | 2016 | 2018 | Portugal | Cinfães | Viseu | 20 | 20 | 12-07-2016 | 07-03-2018 | 603 | 180 | 314544.89 | 198695 | 1 | 233095.22 | -34400.22 | 85.242 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of term and the existence of more work | the existence of additional work and price revision.
3541 | 2496542 | Repaving of Municipal Road 526-1 (Algoz/Guia) | 45232452-5, 45233200-1 | Drainage works, Various surface works | FALSE | 2016 | 2018 | Portugal | Silves | Faro | 8 | 30 | 29-09-2016 | 07-03-2018 | 524 | 150 | 280819.15 | 222939.83 | 1 | 258659.68 | -35719.85 | 86.1904 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register. | nothing to register.
3542 | 2496076 | Public Contest No. 3-A1/2016 - The purpose of the procedure in question is the installation of rainwater drainage networks in various streets of the municipality. | 45232460-4 | Sanitary works | FALSE | 2016 | 2021 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 23-09-2016 | 28-06-2021 | 1739 | 365 | 415000 | 247492.59 | 1 | 247492.59 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Technical Quality of the Proposal - 60%; B) Price - 40%. These factors are, in turn, divided into different duly weighted sub-factors, according to the following: a) Technical Quality of the Proposal (QTP): a1) Work Plan (PT) - 25%; a2) Plan of human resources to be allocated to the work (PMH) - 25%; a3) Plan of technical means / equipment to be allocated to the work (PMTE) - 25%; a4) Justification and descriptive memory of the mode of execution of the work (MJD) - 25%. QTP = 25% x PT + 25% x PMH + 25% x PMTE + 25% x MJD. b) Price (P). P = Pb / VP, in that: Pb- Base Price and PV- Proposal Value. Subfactors a1 to a4 will be evaluated according to a scoring scale from 0.00 to 1.00, where: 0.00 - Bad; 0.25 - Insufficient; 0.50 - Enough; 0.75 - Good; 1.00 - Very Good. The final classification will be given by the following formula: CF= 60% x QTP + 40% x P. Proposals are sorted in descending order according to the classification obtained | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ended on the scheduled date, however, for reasons of force majeure on the part of the intervening parties, the inspection could only be carried out on the mentioned date.
3543 | 2495937 | Rehabilitation of C. M. 1458 (street of Rio Ave - Largo de S. Bento) - fradelos | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 9 | 28-09-2016 | 05-12-2018 | 798 | 210 | 329025 | 201743.65 | 1 | 201743.65 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value of the Proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule. | price revision worth €13,008.38.
3544 | 2494062 | S.e.c. - PROC- No. 61/A1/16 - Public Tender for the award of the contract for "Requalification of the public space surrounding the Social Neighborhood of the Technical School and Requalification of the Public space | 45233251-3 | Resurfacing works | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 04-10-2016 | 31-01-2018 | 484 | 180 | 575000 | 455725.84 | 2 | 455725.84 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of proposal - 60%. The subfactors are those set out in article 18 of the Tender Programme. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3545 | 2492859 | Installation of the Municipal Gym | 45212222-8 | Gymnasium construction work | FALSE | 2016 | 2018 | Portugal | Avis | Portalegre | 12 | 30 | 01-09-2016 | 28-03-2018 | 573 | 150 | 230000 | 189915.02 | 1 | 193464.55 | -3549.53 | 98.1653 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | additional work
3546 | 2488746 | 5010024445 - EN258 - Bridge over Ribeira da Totalga / EM 386 - Pontoon at Km 13+374 - Rehabilitation/Replacement of works of art | 45221119-9 | Bridge renewal construction work | FALSE | 2015 | 2019 | Portugal | N/A | N/A | N/A | 36 | 27-09-2016 | 26-12-2019 | 1185 | 148 | 430000 | 258000.01 | 2 | 243908.06 | 14091.95 | 105.7776 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the change in the value of the project results from the determination of more works in the amount of €12,935.50, of works to supply errors and omissions in the amount of €3,537.00, and of underwork in the amount of €30,791.00.
3547 | 2488579 | Recovery of Municipal Roads | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 08-09-2016 | 22-10-2018 | 774 | 90 | 415547 | 306902.24 | 2 | 271154.2 | 35748.04 | 113.1837 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension granted. | it is due to the existence of over and underwork and price revisions
3548 | 2484996 | Refurbishment and Expansion of the School Building | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2016 | 2018 | Portugal | Loures | Lisboa | 11 | 20 | 22-06-2016 | 09-05-2018 | 686 | 75 | 512822.64 | 469938.36 | 2 | 458861.64 | 11076.72 | 102.414 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: ai) Bid Price (PP) - 40%; aii) Plan of Jobs (PT) - 30%; aiii) Period of Execution (PE) - 30% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork. the contractor changed the materials to be applied and did not comply with the technical standards for the application of materials with the consent of the client of the project, resulting in lower quality in the project.
3549 | 2483914 | S.e.c. - Proc. No. 75/A1/16 - Public Tender for the award of the contract for "Renovation of streets port Clube Vianense". | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 28-09-2016 | 26-07-2018 | 666 | 180 | 675000 | 580317.38 | 2 | 527831.51 | 52485.87 | 109.9437 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price - 40%; Technical value of Proposal - 60%. The subfactors are those set out in article 18 of the Tender Programme. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork.
3550 | 2483795 | Conservation and improvement works of the road network in the municipality of Tavira, union of the parishes of Luz de Tavira and Santo Estêvão and Santa Catarina da Fonte do Bispo | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 13-09-2016 | 21-01-2019 | 860 | 150 | 280500 | 205741.31 | 1 | 228053.79 | -22312.48 | 90.2161 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed before the deadline. | price review
3551 | 2482802 | Urban regeneration – r. Infantry 28, r. Outeiro, R. Central de Sargentos, Praça Conde de Águeda, including mechanical solution – Reinforcement of the high/low city connection | 45233142-6 | Road-repair works | FALSE | 2015 | 2019 | Portugal | Águeda | Aveiro | 1 | 30 | 24-06-2016 | 29-04-2019 | 1039 | 365 | 786109.75 | 620300.99 | 2 | 559878.44 | 60422.55 | 110.7921 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the course of the project, there were some delays due to negotiations between the contractor and subcontractors and non-compliance with the project plan. | more work needed during the course of the project.
3552 | 2480142 | The object of this contract is the construction of the Mozelos Sports Pavilion in Santa Maria da Feira | 45220000-5 | Engineering works and construction works | FALSE | 2016 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 28-09-2016 | 17-06-2019 | 992 | 400 | 1278680 | 1100000 | 3 | 1105042.06 | -5042.06 | 99.5437 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price 60% b) Technical Quality of the Proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 27 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 198 days of graceful extension, 307 days of inspections and defect corrections until provisional acceptance of the project | errors & omissions supply work, and work cut short by difference between predicted and actual measurements
3553 | 2475424 | Rehabilitation of the Dorna Fountain and surrounding area | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Guarda | Guarda | 9 | 15 | 17-08-2016 | 08-10-2018 | 782 | 120 | 214993.3 | 214700 | 1 | 231122.55 | -16422.55 | 92.8944 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical Valuation of the Proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract subject to archaeological monitoring, with delay in archaeological diagnostic surveys
3554 | 2474907 | Qualification of the Public Space of Bairro do Modorno | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Mangualde | Viseu | 20 | 20 | 19-09-2016 | 19-10-2018 | 760 | 365 | 388000 | 349200.01 | 2 | 361488.05 | -12288.04 | 96.6007 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | book of work | underwork
3555 | 2457491 | Construction of a protective pier at the Porto de Abrigo da Torreira consisting of a rockfill with approximately 220 m of development | 45243000-2 | Coastal-defence works | FALSE | 2016 | 2018 | Portugal | Murtosa | Aveiro | 1 | 30 | 21-09-2016 | 12-07-2018 | 659 | 180 | 505176.05 | 394534.98 | 2 | 381052.77 | 13482.21 | 103.5381 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions, the investigation of the need for more work (€3,077.00 + vat) and the detection of underwork (€16,559.20 + vat), led to the municipality of murtosa not meeting the scheduled date of the end | more work (€3,077.00 + vat) and underwork (€16,559.20 + vat)
3556 | 2456243 | 5010023464 - Beira Alta Line - Stabilization of the excavation slope between kms 59+670 and 59+830, on the left side. | 45220000-5 | Engineering works and construction works | FALSE | 2016 | 2018 | Portugal | N/A | N/A | N/A | 38 | 22-07-2016 | 16-04-2018 | 633 | 90 | 260000 | 156000.01 | 1 | 156000.01 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 65% - Technical value 15% - Security Management System 10% - Quality Control System 5% - Environmental Monitoring System 5% | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3557 | 2443867 | Urban arrangements in Miranda, New Village, Eagle Valley, Palancar, White Pena, Malhadas, Genisio and Especiosa | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 08-09-2016 | 23-02-2018 | 533 | 450 | 349747 | 344879.54 | 2 | 344879.54 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unfavorable weather conditions
3558 | 2443550 | Urban Intervention providing the Parish of Monte, Municipality of Murtosa, with a Leisure Park in which it will be implemented: Cafeteria, WC, covered multipurpose space, reorganization of areas and streets | 45112700-2 | Landscaping work | FALSE | 2016 | 2019 | Portugal | Murtosa | Aveiro | 1 | 30 | 16-09-2016 | 24-06-2019 | 1011 | 365 | 1020731.53 | 673500 | 2 | 735991.11 | -62491.11 | 91.5093 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | request for extension by the contractor; suspension of work. | complementary works.
3559 | 2434408 | Refurbishment of the garden on the slope of Cerro do Malpique, in Albufeira. | 45112710-5 | Landscaping work for green areas | FALSE | 2016 | 2020 | Portugal | Albufeira | Faro | 8 | 20 | 23-08-2016 | 14-02-2020 | 1270 | 90 | 264150 | 255522.66 | 2 | 281699.63 | -26176.97 | 90.7075 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | more works. adverse weather conditions | over and underwork.
3560 | 2432621 | Urban Rehabilitation of Lameira | 45432112-2 | Laying of paving | FALSE | 2016 | 2018 | Portugal | Penalva do Castelo | Viseu | 20 | 21 | 13-09-2016 | 12-02-2018 | 517 | 120 | 349952.87 | 326404.08 | 2 | 391657.05 | -65252.97 | 83.3393 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 75%; Technical Valuation of the Proposal - 25%: MJD - Justification and Descriptive Memory, MHT - Human resources and technical services to be allocated to the work, MEQ - Means and equipment to be allocated to the work. | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | more work and underwork
3561 | 2431236 | Conception Contract Construction of the Improvement in the treatment process of the Roxo WTP | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2018 | Portugal | Aljustrel | Beja | 2 | 20 | 15-09-2016 | 29-06-2018 | 652 | 180 | 1470000 | 1120713.19 | 3 | 1164678.59 | -43965.4 | 96.2251 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: 1. Price 50% 2. Technical value 50% 2.1 Work execution methodology 25% 2.2 Detail and consistency of the work plan 15% 2.2.1 Work schedule 10% 2.2.2. Means plan 5% 2.3 Characterization and quality of equipment and materials 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | job adjustment
3562 | 2431173 | Construction of the urbanization works of the Sernancelhe Business Zone - phase 1 | 45211360-0 | Urban development construction work | FALSE | 2016 | 2018 | Portugal | Sernancelhe | Viseu | 20 | 20 | 16-09-2016 | 23-03-2018 | 553 | 150 | 598000 | 508300.01 | 2 | 480689.3 | 27610.71 | 105.744 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The criteria are those set out in point 12 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | underwork
3563 | 2422284 | The contract refers to the expansion of the existing equipment, including the execution of works in the scope of demolitions, earthworks, concrete, masonry, roofing, stonework, insulation | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2018 | Portugal | Benavente | Santarém | 16 | 30 | 09-09-2016 | 06-02-2018 | 515 | 240 | 375000 | 354938.15 | 2 | 354938.15 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of work due to weather conditions that did not allow the screeds to dry for laying the floor.
3564 | 2420457 | 5010021693 - Contract for the Rehabilitation of 9 Hydraulic Passages, 7 on the Neves Corvo Branch and 2 on the South Line | 45453100-8 | Refurbishment work | FALSE | 2015 | 2021 | Portugal | N/A | N/A | N/A | 36 | 29-07-2016 | 06-07-2021 | 1803 | 150 | 450000 | 413843.88 | 2 | 329300.88 | 84543 | 125.6735 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical value 20% - Security Management System 10% - Quality Control System 5% - Environmental Management System 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3565 | 2416678 | Paving of VNC 94 | 45000000-7 | Construction work | FALSE | 2016 | 2019 | Portugal | Loulé | Faro | 8 | 30 | 21-07-2016 | 11-01-2019 | 904 | 120 | 250000 | 197957.74 | 1 | 183601.96 | 14355.78 | 107.819 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the stipulated time frame. | some of the anticipated amounts of work have not been exhausted.
3566 | 2404149 | Construction of the Boa-Fé Neighborhood Community Center | 45212422-0 | Canteen construction work | FALSE | 2016 | 2018 | Portugal | Elvas | Portalegre | 12 | 24 | 06-09-2016 | 16-04-2018 | 587 | 300 | 432000 | 388383.04 | 2 | 382793.96 | 5589.08 | 101.4601 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The basic criteria for assessing proposals are those established in paragraph b) of paragraph 1 of article 74 of the Public Procurement Code, namely the economically most advantageous, for the contracting entity, based on the factors and sub-factors, designated in article 5 of the procedure program. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to correct work on site | checked whether the existence and excessive quantities in the map of quantities and works that were not necessary were performed.
3567 | 2402461 | Public Contest No. 2-A1/2016 - The purpose of the contract is to raise and replace floors, open and close trenches, supply and lay about 2,250 m of Ø 250 mm piping | 45232400-6 | Sewer construction work | FALSE | 2016 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 29-08-2016 | 13-06-2018 | 653 | 270 | 250000 | 150000.01 | 1 | 149981.91 | 18.1 | 100.0121 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Technical Quality of the Proposal - 55%; B) Price - 45% These factors are, in turn, divided into different duly weighted sub-factors, as follows: a) Technical Quality of the Proposal (QTP): a1) Work Plan (PT) - 35%; a2) Plan of human resources to be allocated to the work (PMH) - 35%; a3) Plan of technical means / equipment to be allocated to the work (PMTE) - 15%; a4) Justification and descriptive memory of the mode of execution of the work (MJD) - 15%. QTP = 35% x PT + 35% x PMH + 15% x PMTE + 15% x MJD. b) Price (P). The price valuation factor will be A score equal to or less than 10 is assigned. The classification, in this factor, is assigned by applying the following expression: - If Bid Value Vi > EUR200,000 Score (Proposal i) = 9 x (250,000 - Vi) / (250,000 - 200,000) - If Bid Value Vi <= EUR200,000 - Score (Proposal i) = 10 - (Vi / 200,000) Where: Score (Proposal i) - score to be attributed to the Price factor, with a maximum value of 10 points. Vi - proposal value i. You subfactors a1) to a4) will be evaluated in accordance with what is described in point 22.3 of the Tender Programme. The final ranking will be given by the following formula: CF= 55% x QTP + 45% x P. Proposals are sorted in descending order according to classification obtained. | 1 | 45 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract ended on the scheduled date, however due to the impossibility of the interveners, the reception was only carried out on the mentioned date | during the execution of the project, it was verified that it was not necessary to carry out all the projects initially foreseen.
3568 | 2401308 | Extension and rectification of the Pindelo dos Milagres connection to the A24 | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2019 | Portugal | São Pedro do Sul | Viseu | 20 | 12 | 18-08-2016 | 13-03-2019 | 937 | 365 | 207547 | 159763.75 | 1 | 175036.99 | -15273.24 | 91.2743 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the aforementioned suspension. | the price revision amounting to €15,273.24.
3569 | 2400527 | S.e.c. - Proc. nº 40/A1/16 - Public Tender for the award of the contract for "Requalification of streetCidade de Riom - Urban Arrangement" | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 28 | 30-08-2016 | 26-07-2018 | 695 | 180 | 1125000 | 875028.45 | 2 | 846281.84 | 28746.61 | 103.3968 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Bid price - 40%, Technical Valuation of Proposal - 60%. The subfactors are those set out in article 18 of the procedural program. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
3570 | 2400499 | The contract refers to the expansion of the existing School Centre, including work in the scope of demolitions, earthworks, concrete, masonry, roofing, stonework, insulation and waterproofing. | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2019 | Portugal | Benavente | Santarém | 16 | 30 | 02-09-2016 | 19-03-2019 | 928 | 120 | 188000 | 168450 | 1 | 168542.65 | -92.65 | 99.945 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the deadline, however the provisional acceptance was carried out later, after carrying out several inspections of the project. | the amount of the price review of €92.65 is added to the value of the award.
3571 | 2399967 | The object of this contract is the execution of works in Parque da Boba, in the parish of Mina de Água, with defined works, as to their type, quantity and technical conditions of execution. | 45112711-2 | Landscaping work for parks | FALSE | 2016 | 2019 | Portugal | Amadora | Lisboa | 11 | 30 | 10-08-2016 | 23-01-2019 | 896 | 240 | 796167.41 | 676742.31 | 2 | 676742.31 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, with interspersed intervals of 20 by 20, and the values ​​assigned according to the following scale: - Descriptive Memorandum prepared in good detail, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 80 - Descriptive Memory prepared with satisfactory detail of the work to be carried out, focusing on important constructive aspects, making possible, the interpretation of the work to be carried out: MDi = 60 - Descriptive Memory with acceptable detail, focusing on constructive aspects of a general nature. Some constructive aspects are focused, without high degree of detail: MDi = 40 - Descriptive Memory with little detail and little suited to the work in question, limited only to a summary description. No introduces or focuses on any constructive aspect of great interest: MDi = 20 - The Descriptive Memory does not present a description of the work to be carried out: MDi = 0 b) Work Plan: The classification will be from 0 to 100, with interspersed intervals of 20 by 20, and the values ​​assigned according to the following scale: - It presents a Work Plan that is very suitable for the work in question, with very good justification for the dimensioning of the teams and expected yields: PTi = 100 - Presents a Work Plan that is well suited to the work in question, with good justification of the sizing of teams and income expected: PTi = 80 - Presents a Work Plan suitable for the work in question, with satisfactory justification of the sizing of the teams and expected yields: PTi = 60 It presents a Work Plan reasonably adequate to the work in question, with poor justification of the sizing of the teams and expected income: PTi = 40 - Presents a Work Plan that is not suitable for the work and without justification for the sizing of the teams and expected yields: PTi = 20 - The Work Plan does not present development regarding the work in question, as well as the dimensioning of the teams and also the expected yield: PTi = 0 The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the proposal submitted first will win. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this increase in the “execution period” had to do with the specificity of the project, which with large movements/modeling of the land, when it rained and after the period of rain, it was necessary a long period of time until the land dried and the machines were able to continue the project, so that, taking into account the adverse weather conditions, it was not possible to verify the normal development of the projects.
3572 | 2398613 | AA 2387 - Connection of the S.Jorge Water Supply Subsystem to the Southwest System (Arcos de Valdevez) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2020 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 43 | 12-08-2016 | 15-10-2020 | 1525 | 420 | 2100000 | 1260000.01 | 3 | 1260000.01 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the contract extensions were granted gracefully so that there were no additional costs to be borne by the owner of work, largely due to the financial difficulties of the contractor soares da costa, s.a., which initially triggered a transfer approval process credits to subcontractors sensiaqua, lda. and boaventura & boaventura, ltd. and later a contractual position was transferred to boaventura & boaventura, lda., resulting in a total of 381 days of extension. finally, when the project was completed, edp had not yet guaranteed the supply of energy to the built installations, namely the hydropressor station and intermediate station. | assignment of contractual position
3573 | 2397710 | AA 2388 – São Jorge Water Supply Subsystem. Milhões, Vila Franca and Barroselas Reservoirs and the Respective Supply Connections (Viana do Castelo) | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2018 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 41 | 12-08-2016 | 05-12-2018 | 845 | 540 | 6500000 | 3900000.01 | 3 | 4059008.61 | -159008.6 | 96.0826 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to indicate | nothing to indicate
3574 | 2387303 | The contract essentially concerns the execution of milling next to the sidewalks, cuts and removal of the bituminous pavement in the sanitation areas, application of tout-venant and smoothing layers | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Benavente | Santarém | 16 | 30 | 30-08-2016 | 26-02-2018 | 545 | 90 | 266500 | 179000 | 1 | 197358.63 | -18358.63 | 90.6978 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the set deadline. the inspection for the purposes of provisional acceptance, by agreement between the parties, took place after the execution period. | the change in the value of the project was due to the price review
3575 | 2385882 | The purpose of the contract is the requalification and expansion of the Elementary school in Chão do Rio - Fiães | 45210000-2 | Building construction work | FALSE | 2016 | 2019 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 31-08-2016 | 14-10-2019 | 1139 | 180 | 240000 | 187665.11 | 1 | 187289.18 | 375.93 | 100.2007 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60% b) Technical Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 135 days due to work on additional contracts and the need to revise the project to eliminate architectural barriers 25 days elapsed between the expected completion date and the carrying out of the inspection for the purposes of provisional acceptance 703 days elapsed between the date of the 1st inspection and the final one to correct physical and documental defects | additional work resulting from the revision of the project to eliminate architectural barriers; errors and omissions and underwork resulting from the mismatch of project and actual measurements; replacement of the financial rebalancing resulting from the extension of the deadline resulting from the review of the project.
3576 | 2377325 | Connection node to IPCA by E.N. 204 (Barcelos Ring Road), in Vila Frescaínha S. Martinho. | 45233125-1 | Road junction construction work | FALSE | 2015 | 2018 | Portugal | Barcelos | Braga | 3 | 42 | 16-08-2016 | 30-04-2018 | 622 | 180 | 442625.35 | 415345.45 | 2 | 384624.56 | 30720.89 | 107.9872 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (50%); b) Technical Valuation of the Proposal (50%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Interconnection/compatibility between Work Plans, Manpower Plan, "IC" Equipment Plan (25%). | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the present contract had the 1st partial consignment on september 15, 2016, given that only part of the land necessary for the execution of the project was available, however the beginning of the projects in this area of ​​the project, only started after the communication of the approval of the project plan safety and health that took place on february 8, 2017. the total consignment of the contract took place on march 1, 2017, the date on which all the land necessary for the execution of the project became available. however, the execution of the contract was partially suspended on june 30, 2017 in the area of ​​the project partially consigned on september 15, 2016, due to the need for the owner to study changes to be introduced to the project, as better described in the register gimb 31.819/17. the execution of works in this area was resumed on october 31, 2017, the date on which the final version of the project execution project was delivered, a project which included the alterations carried out by the owner-of-work, having drawn up a auto restart works. taking into account what is described in paragraphs 2 and 3 of article 298 of decree-law no. 18/2008, of january 29, the deadline for completion of the project was december 29, 2017. simultaneously, for the projects consigned on march 1, 2017, the contractor requested the following contract term extensions: 1. registration 52.149/17 the contractor justified the need to extend the completion date of the project for another 60 (sixty) days, with the change in the start date of work on the bypass having only started in august 2017 and not in may 2017 as initially foreseen. the change in the date of completion of the part of the contract assigned on march 1, 2017, was accepted by the mayor of barcelos on september 1, 2017, leaving october 27, 2017 as the completion date of this part of the project. 2. registration 64.070/17 the contractor justified the need to extend the date of completion of the project by 30 (thirty) days, with the backlog of works that were awarded and above the physical capacity of execution of the company. the change in the date of completion of the part of the contract assigned on march 1, 2017, was approved at a meeting of the city council of barcelos on november 17, 2017, thus leaving november 26, 2017 as the completion date of this part of the project. | "justification of the underwork: art.º 02.02.01.02 - ""slope crest ditches: lined with concrete, of semi-circular section with a diameter equal to 0.30 m."" - according to the project specifications, this item was quantified at 229.00 m, however, after measuring this item, it was found that only 31.00 m had to be executed by the contractor, resulting in a shortfall of €3,613.50. art. 02.03.05.01 - "embankment or excavation slope descents lined with concrete: semi-circular section with diameter equal to 0.30 m. - according to the project specifications, this article was quantified in 3.00 m, however, after measuring this article, it was verified that there was no need to execute this article, resulting in a less value of €57.36. art. 02.03.05.02 - "embankment or excavation slope descent lined with concrete: semi-circular section with diameter equal to 0.40 m. - according to the project specifications, this article was quantified in 15.80 m, however, after measuring this article, it was found that the contractor only needed to execute the quantity of 10.00 m, resulting in a value less than €125.11. article 03.01.02.01.02 - ''crushed aggregate of large grain size: 0.20 m thick. - according to the specifications of the project and specifications, this article was quantified in 568.37 m2, however, after measuring this article, it was found that it was only necessary to execute by the contractor the quantity of 292.50 m2, resulting in a less value of €925.17. article 03.01.02.02.01 - ''recycled aggregate: 0.25 m thick. - according to the specifications of the project and specifications, this article was quantified in 1660.00 m2, however, after measuring this article, it was found that it was only necessary to execute by the contractor the quantity of 1508.00 m2, resulting in a value less than €547.20. art. 03.02.01.01.01 - ""layers of hot mix asphalt: binding layer: ac20 bin 35/50 (m8): 0.08 m thick."" - according to the project specifications, this item was quantified at 1613.30 m2, however, after measuring this item, it was found that only 1407.36 m2 had to be carried out by the contractor, resulting in a value less than €1668.11. art. 03.02.01.01.02 - ""layers of hot mix asphalt: binding layer: ac20 bin 35/50 (m8): 0.09 m thick."" - according to the project specifications, this item was quantified at 2473.51 m2, however, after measuring this item, it was found that the contractor only needed to carry out the quantity of 2245.00 m2, resulting in a value less than €2056.59. art. no. 03.02.02.01.02 - ""layers of hot bituminous mixtures: wearing course: ac14 surf 35/50 (88): 0.05 m thick."" - according to the specifications of the project and specifications, this article was quantified in 1300.00 m2, however, after measuring this article, it was found that it was only necessary to execute by the contractor the quantity of 1130.00 m2, resulting in a value less than €1071.00. art. no. 03.02.02.01.03 - ""layers of hot mix asphalt: wearing course: ac14 surf 35/50 (88): 0.06 m thick."" - according to the specifications of the project and specifications, this article was quantified in 2900.00 m2, however, after measuring this article, it was found that it was only necessary to execute by the contractor the quantity of 2676.00 m2, resulting in a less value of €1612.80. art. 03.04.01.01 - "bituminous impregnation watering: with bituminous emulsion or f/uidified bitumen. - according to the specifications of the project and specifications, this article was quantified in 4086.81 m2, however after measuring this article, it was found that it was only necessary to perform by the contractor the amount of 3652.36 m2, resulting in a value of less than €330.18. art. 03.04.02.01 - ""irrigation of bonding: with bituminous emulsion. - according to the project specifications and specifications, this article was quantified in 10166.81 m2, however after measuring this article, it was found that it was only necessary to execute by the contractor the amount of 9827.50 m2, resulting in a value less than €122.15.art.no. 04.01.01.01 - "" laying of topsoil, reusing stripping products previously stored (01.01.05) and/or coming from borrowing (04.01.01.01), including all the necessary work, namely loading, transport and spreading: in embankment coating (thickness 0.10 m). - according to the specifications of the project and specifications, this article was quantified in 1898.30 m2, however, after measuring this article, it was found that only 1350.50 m2 had to be executed by the contractor, resulting in a value less than €1,479.06. art. no. 04.01.01.02 - "" laying of topsoil, reusing stripping products previously stored (01.01.05) and/or borrowed (04.01.01.01), including all necessary work, namely loading, transport and spreading: in separators and directional islands (thickness 0.15 m). - according to the project specifications and specifications, this article was quantified at 16.00 m2, however it was found that the execution of this article was not necessary, thus resulting in a value of less than €50.40. art.no. 04.01.01.03 - "laying of topsoil, reusing the products of previously stored blasting (01.01.05) and/or borrowing (04.01.01.01), including all necessary works, namely loading, transport and spreading: in the areas inside the knot branches (thickness 0.15 m over ground) modelled. - according to the specifications of the project and specifications, this article was quantified at 43.00 m2, however it was found that the execution of this article was not necessary, thus resulting in a value of less than €135.45. article 04.04.01 - "supply and laying of kerbs, islets and separators: kerbstone, including foundations. - according to the specifications of the project and specifications, this article was quantified in 695.91 m, however, after measuring this article, it was verified that it was only necessary to execute by the contractor the quantity of 486.00 m2, resulting in a less value of €1.908.08. art.º 04.04.03 - "supply and laying of kerbs, islets and separators: kerbs at the end of kerbs with garden areas, including foundations. - in accordance with the specifications of the project and specifications, this article was quantified in 502.57 m, however, after measuring this article, it was verified that it was only necessary to execute by the contractor the quantity of 279.00 m2, resulting in a less value of €1.636.53. art.º 04.05.03.04 - "paving with concrete slabs of the "marmocim" type or equivalent, 1.8 cm thick, in grey colour, on mortar regularization with 2 cm thickness. - according to the project specifications, this article was quantified in 18.00 m2, however it was verified that the execution of this article was not necessary, resulting in a value less than €340.20. article 04.05.07 - "" works for change of gas network signalling marks, including alteration of inscriptions. - according to the project specifications, this item was quantified in 2.0 units, however, after measuring this item, it was found that the contractor only needed to execute the quantity of 1.0 unit, resulting in a value less than €45.00. article 05.07.06 - "supply and application of skirts to protect motorcyclists on the existing guardrails, according to detail. - the justification for not carrying out the works listed in this article is as follows: during the course of the present contract, the contractor informed the construction supervision of the impossibility of applying the motorcyclist protection skirts to the existing railings as foreseen in the project. specifically, it was verified that the available height - measured between the top of the existing kerb and the bottom of the longitudinal profile of the existing semi-flexible safety guardrail - is insufficient for placing the metallic skirt type protection device. it was also verified that the semi-flexible safety guardrail is, in general terms, in a poor state of conservation. we also inform that the present project did not contemplate the substitution of the existing semi-flexible safety guarding or even the execution of any adaptation to it. in order to avoid this additional expense, the infraestruturas de portugal, s.a. representative on site, mr. elísio melo, was questioned by e-mail (attached), so that he could give his opinion about the legal need to apply the metal skirt type protection device, given that these devices are planned to be placed on the central part of the bypass, and therefore, in a part of the work that is under infraestruturas de portugal, s.a.'s jurisdiction (l.p., s.a.). the response from infraestruturas de portugal, s.a, official letter ref. 241brg140113, was received by barcelos city council on 28 february 2018 (gimb record: 12.614/18), which stated the following: "it is further noted that the project must be complied with regarding the application of protection devices for motorcyclists, by raising the props of the existing safety barriers ensuring a minimum height of 0.55m from the horizontal axis of the beam to the ground". this response comes more than 2 months after the last measurement report was drawn up and after the project was put into operation. in addition, in information provided by the project designer (information ref. 06-18-dopm-af), it was proposed that the entire guardrail be replaced, as it was in a poor state of repair. as a result of the above, the present contract works result in a underwork amounting to €33,321.89 (thirty-three thousand, three hundred and twenty-one euros and eighty-nine cents).
3577 | 2372514 | Contract for the rehabilitation of the municipality's road network. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Alcobaça | Leiria | 10 | 15 | 26-08-2016 | 13-03-2018 | 564 | 120 | 390000 | 312000 | 2 | 312000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | although the provisional acceptance date was later than the execution deadline, the project was completed within the deadline. | there was no change in value.
3578 | 2370805 | Flooring, Urban Equipment/Furniture, Water Supply Network, smiths, Electricity and Signaling. | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Nisa | Portalegre | 12 | 30 | 25-08-2016 | 16-05-2018 | 629 | 240 | 188679 | 167604 | 1 | 171773.07 | -4169.07 | 97.5729 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-existence of definitive price revision indices. | files no. 01 and 02 of price revision.
3579 | 2363396 | Replacement of fiber cement roofs with asbestos in five school buildings: EB Cacilhas, EB Fontre Santa, EB Costa de Caparica, EB nº 2 do Alfeite and JI de Marco Cabaço | 45261900-3 | Roof repair and maintenance work | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 24 | 18-08-2016 | 20-04-2018 | 610 | 90 | 298388.14 | 232234.06 | 1 | 206859.68 | 25374.38 | 112.2665 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climacteric factors and the supplier of the type of material to be applied in schools being only one in portugal, which led to delays. however, it did not affect the functioning of schools. | underwork.
3580 | 2354205 | Urban Requalification of the Central Axis of Guarda - Guarda City Park | 45112712-9 | Landscaping work for gardens | FALSE | 2016 | 2018 | Portugal | Guarda | Guarda | 9 | 15 | 19-08-2016 | 17-09-2018 | 759 | 270 | 436133.3 | 274421.24 | 2 | 284513.44 | -10092.2 | 96.4528 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Proposal Price -60% Technical Value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | filing of precautionary measure | existence of price revision
3581 | 2350940 | Urban Requalification of the Central Axis of Guarda - Jardim José de Lemos | 45112712-9 | Landscaping work for gardens | FALSE | 2016 | 2018 | Portugal | Guarda | Guarda | 9 | 15 | 19-08-2016 | 19-10-2018 | 791 | 270 | 434132.83 | 292414.75 | 2 | 266873.11 | 25541.64 | 109.5707 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical value of the Proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the counting of the period of execution of the project started with the date of approval of the pss. | existence of underwork and price revision
3582 | 2344228 | Conservation and remodeling contract for Building A of the Institute for Interdisciplinary Research at the University of Lisbon | 45262700-8 | Building alteration work | FALSE | 2016 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 26-07-2016 | 15-11-2019 | 1207 | 240 | 955000 | 759923.43 | 2 | 808693.23 | -48769.8 | 93.9693 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A |  | errors and omissions and extra work
3583 | 2338801 | Montargil Cultural Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2016 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 11-08-2016 | 18-02-2019 | 921 | 250 | 698788 | 698461.76 | 2 | 698461.76 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | price review
3584 | 2335329 | Construction of municipal and bal facilities in Quarteira | 45211350-7 | Multi-functional buildings construction work | FALSE | 2013 | 2020 | Portugal | Loulé | Faro | 8 | 30 | 28-07-2016 | 28-10-2020 | 1553 | 540 | 1840000 | 1563298.14 | 3 | 1563298.14 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension of the deadline.
3585 | 2333261 | Construction of the Social and Sports Development Center of Nespereira | 45212200-8 | Construction work for sports facilities | FALSE | 2016 | 2018 | Portugal | Cinfães | Viseu | 20 | 20 | 08-08-2016 | 18-05-2018 | 648 | 240 | 799992.96 | 696576.33 | 2 | 689419.26 | 7157.07 | 101.0381 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | metrological situations that jeopardized the normal development of the project. | existence of underwork.
3586 | 2322272 | Execution of extensions of the water, sewage and rainwater networks, and execution of water and home sewage branches in various locations in the Council of Viseu | 45232460-4 | Sanitary works | FALSE | 2016 | 2018 | Portugal | Viseu | Viseu | 20 | 36 | 19-07-2016 | 04-07-2018 | 715 | 365 | 338932.05 | 264019.99 | 2 | 251122.06 | 12897.93 | 105.1361 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: 1) Technical value of the proposal 24% 2) Price 76% | 1 | 76 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline for carrying out the project. | the final value of the project was below the value of the award.
3587 | 2322240 | AA 2362 - Construction contract for the execution of the reservoirs and pipelines of Junqueira, Bagunte and Touguinhó (Vila do Conde) | 45231300-8, 45247270-3 | Construction work for water and sewage pipelines, Reservoir construction works | FALSE | 2015 | 2018 | Portugal | Vila do Conde | Porto | 13 | 42 | 14-06-2016 | 22-03-2018 | 646 | 301 | 1600000 | 1175330.8 | 3 | 925934.74 | 249396.06 | 126.9345 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | insufficient labour. the delays were the responsibility of the contractor and attributed to the same | the execution of the touguinho reservoir was suppressed due to the unavailability of the land within the contractual period. this situation implied underwork
3588 | 2318789 | Conservation and improvement works of the municipality's road network – union of parishes of Tavira | 45233220-7 | Surface work for roads | FALSE | 2016 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 19-07-2016 | 21-01-2019 | 916 | 150 | 322000 | 244196.31 | 1 | 242919.27 | 1277.04 | 100.5257 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the procedure program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | documents delivery | underwork and price revision
3589 | 2318610 | Animal Welfare Center | 45223600-2 | Dog kennels construction work | FALSE | 2016 | 2019 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 27-07-2016 | 29-11-2019 | 1220 | 180 | 211955.25 | 168324.7 | 1 | 171824.7 | -3500 | 97.963 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension works | extra work
3590 | 2316003 | Repaving of CM 520-1 and Avenida da Venezuela | 45233142-6 | Road-repair works | FALSE | 2016 | 2018 | Portugal | Faro | Faro | 8 | 11 | 29-07-2016 | 20-04-2018 | 630 | 60 | 193355 | 168909.1 | 1 | 168909.1 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change to the project deadline
3591 | 2314044 | Paving sidewalks and streets , partition walls, replacement of the water supply network and execution of sections of the domestic sewage network. | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Nisa | Portalegre | 12 | 30 | 28-07-2016 | 11-05-2018 | 652 | 180 | 227055 | 168402.33 | 1 | 169933.73 | -1531.4 | 99.0988 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | ordinary price review.
3592 | 2310743 | Citizen's Shop - Valpaços | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Valpaços | Vila Real | 19 | 24 | 26-07-2016 | 24-01-2018 | 547 | 365 | 525240.25 | 495000 | 2 | 494550 | 450 | 100.091 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price - 70% and Technical Valuation - 30%, for this purpose, point 14 of the procedural program should be consulted. | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of 60 plus 60 days | underwork worth €450.00
3593 | 2308283 | Maintenance Dredging of the Port of Figueira da Foz | 45252124-3 | Dredging and pumping works | FALSE | 2016 | 2019 | Portugal | Figueira da Foz | Coimbra | 6 | 20 | 14-07-2016 | 26-02-2019 | 957 | 910 | 2208150 | 1428800 | 3 | 1428800 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: "Price" factor: 0.65; "Execution Quality Assurance" factor: 0.35. | 1 | 65 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this contract ended before the end of the execution period, as the maximum amount of dredged items was reached.
3594 | 2306975 | It consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution in the project and in the specifications for the procedure | 45112711-2 | Landscaping work for parks | FALSE | 2015 | 2018 | Portugal | Amadora | Lisboa | 11 | 30 | 21-07-2016 | 15-11-2018 | 847 | 240 | 1408902.36 | 1197567.02 | 3 | 1229525.62 | -31958.6 | 97.4007 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: - The final score, assigned to each competitor, is given by the formula: PF = 0.35 * Pi + 0.65 * VTi On what : PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valuation is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, with interspersed intervals of 20 by 20, and the values ​​assigned according to the following scale: - Descriptive Memorandum prepared in good detail, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi = 100; - Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi = 80; - Descriptive Memory prepared with satisfactory detail of the work to be carried out, focusing on important constructive aspects, making possible, the interpretation of the work to be carried out: MDi = 60; - Descriptive Memory with acceptable detail, focusing on constructive aspects of a general nature. Some constructive aspects are focused, without high degree of detail: MDi = 40; - Descriptive Memory with little detail and little suited to the work in question, limited only to a summary description. No introduces or focuses on any constructive aspect of great interest: MDi = 20; - Non-presentation of the Descriptive Memory: MDi = 0. b) Work Plan: The classification will be from 0 to 100, with interspersed intervals of 20 by 20, and the values ​​assigned according to the following scale: - It presents a Work Plan that is very suitable for the work in question, with very good justification for the dimensioning of the teams and expected yields: PTi = 100; - Presents a Work Plan that is well suited to the work in question, with good justification of the sizing of teams and income expected: PTi = 80; - Presents a Work Plan suitable for the work in question, with satisfactory justification of the sizing of the teams and expected yields: PTi = 60; - Presents a Work Plan reasonably adequate to the work in question, with poor justification of the sizing of the teams and expected income: PTi = 40; - Presents a Work Plan that is not suitable for the work and without justification for the sizing of the teams and expected yields: PTi = 20; - Does not show the Work Plan: PTi = 0. The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the proposal submitted first will win. | 1 | 35 | N/A | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | upon partial provisional acceptance, a number of anomalies were detected which were only later corrected, giving rise to provisional acceptance. therefore, between the consignment and the partial provisional reception, 293 days elapsed, giving rise to a deviation of 53 days, due to the specificity of the project, which with a large volume of earth moving and the bad weather conditions verified during the execution of the project, it was not possible to proceed with the normal development of the projects. the remaining 181 days (making up the 234 days of deviation) was due to the time elapsed for the contractor to correct the anomalies detected during the partial acceptance. | definitive price revision in the amount of €31,958.60.
3595 | 2306474 | Refurbishment and expansion of the Lovares school - Union of the parishes of Vale S. Cosme, Telhado and Portela | 45214210-5 | Primary school construction work | FALSE | 2016 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 20-07-2016 | 28-12-2018 | 891 | 360 | 390000 | 348901.71 | 2 | 355599.41 | -6697.7 | 98.1165 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value of the Proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork in the amount of 1,542.78 and revision of prices to be received by the contractor in the amount of 8,240.48.
3596 | 2305152 | Repaving of City Neighborhoods - Group I | 45233252-0 | Surface work for streets | FALSE | 2016 | 2019 | Portugal | Bragança | Bragança | 4 | 20 | 12-07-2016 | 20-03-2019 | 981 | 120 | 240000 | 172587.64 | 1 | 136769.2 | 35818.44 | 126.189 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1-Price (weighting) of 70%) 2-Technical quality of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract was completed on 2017/05/21, with the opening of all infrastructures to the municipalities, the closure of accounts was only possible on 20/03/2019 date of provisional reception. | there was underwork resulting from the determination of the quantification of work carried out at the construction site, which did not reach the values ​​foreseen in the project quantity map.
3597 | 2302782 | Replacement of Drainage and Water Distribution Networks on streetLuís de Queiroz and Av.Rainha D.Leonor (East). | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2018 | Portugal | Almada | Setúbal | 17 | 20 | 19-07-2016 | 22-10-2018 | 825 | 120 | 731000 | 606016.96 | 2 | 660064.5 | -54047.54 | 91.8118 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: P - Price T - Technical Value The most economically advantageous proposal results from the application of the factors according to the mathematical expression that is explained below: K =0.4xP +0.6xT | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | incorrect records, removal of asbestos, contaminated land and other circumstances that prevented the normal development of the projects. | removal and replacement of existing infrastructure, video inspection, increase in the class of concrete shackles, lifting and replacement of pavement and alteration of connection nodes in the supply network.
3598 | 2301988 | Construction of 5,905.20 m of piping; 34.50m of FFd DN 200 piping, 2,929.58m of PPc piping; 345 home sanitation extensions; 240 wastewater manholes. | 45232460-4 | Sanitary works | FALSE | 2015 | 2020 | Portugal | Fafe | Braga | 3 | 42 | 22-06-2016 | 26-06-2020 | 1465 | 300 | 1050000 | 712515.84 | 2 | 607665.46 | 104850.38 | 117.2546 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Overall price 50% 2) Technical value of the proposal 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in the execution of works by the contractor, unavailability of private land included in the contract and delays due to compatibility with works by cm fafe. | it was not possible to carry out all the projects foreseen in parcel 02 due to a dispute with the client. there was no need to carry out all the contractual work foreseen.
3599 | 2300985 | Contract to carry out the sealing of the dump on the island of Faial | 90000000-7 | Sewage-, refuse-, cleaning-, and environmental services | FALSE | 2016 | 2018 | Portugal | Horta | Região Autónoma dos Açores | 15 | 42 | 18-07-2016 | 15-02-2018 | 577 | 210 | 660000 | 597000 | 2 | 587673 | 9327 | 101.5871 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40% Technical quality of the proposal: 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension for security reasons | underwork
3600 | 2295036 | This contract aims to repair and renew the wear layer of the pavements in the following streets in the county: Lavradio - Praceta Lusíadas + street6 de Janeiro + streetAlmirante Reis | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2018 | Portugal | Barreiro | Setúbal | 17 | 20 | 01-07-2016 | 01-10-2018 | 822 | 90 | 400000 | 344687.01 | 2 | 291686.99 | 53000.02 | 118.1702 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: a) Bid price - 60% b) Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of security
3601 | 2292724 | Execution of the Bus Terminal of S. B. De messines | 45213311-6 | Bus station construction work | FALSE | 2016 | 2019 | Portugal | Silves | Faro | 8 | 30 | 07-07-2016 | 30-04-2019 | 1027 | 210 | 293091.56 | 258056.81 | 2 | 302117.2 | -44060.39 | 85.4161 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | granting extensions for the execution of the project | revision of prices and work to supply errors and omissions in the amount of 12,886.25
3602 | 2288942 | Rehabilitation of the Municipal Market of Estarreja | 45212310-2 | Construction work for buildings relating to exhibitions | FALSE | 2016 | 2018 | Portugal | Estarreja | Aveiro | 1 | 31 | 04-07-2016 | 14-09-2018 | 802 | 365 | 2000000 | 1788271.63 | 3 | 1782695.65 | 5575.98 | 100.3128 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension | underwork and price revision
3603 | 2287097 | Construction contract for the square/park of fairs and markets in Alcantarilha | 45233160-8 | Paths and other metalled surfaces | FALSE | 2016 | 2019 | Portugal | Silves | Faro | 8 | 30 | 30-06-2016 | 14-08-2019 | 1140 | 150 | 195316 | 190912.33 | 1 | 198615.22 | -7702.89 | 96.1217 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
3604 | 2285891 | "Rehabilitation of the Campo de Ourique Reservoir" | 45220000-5 | Engineering works and construction works | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | 65 | 01-06-2016 | 18-04-2018 | 686 | 460 | 2200000 | 1485716.04 | 3 | 1485716.04 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: See tender program: price (50%), value technique (40%) and deadline compliance guarantee (10%) | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3605 | 2285357 | Intervention in the Pardelhas primary school building with the aim of transforming it into an arts workshop | 45210000-2 | Building construction work | FALSE | 2016 | 2019 | Portugal | Murtosa | Aveiro | 1 | 30 | 11-07-2016 | 24-05-2019 | 1047 | 274 | 396732.18 | 347793.41 | 2 | 364472.26 | -16678.85 | 95.4238 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of additional work, need to adjust the exterior arrangements and relocation of labor to another work that the company was doing in the municipality of murtosa (health centre). | existence of underwork, more work and price revision
3606 | 2283779 | Design/Construction contract for the remodeling/expansion of the treatment level of the Proença-a-Nova WWTP - Work 301A | 45232420-2 | Sewage work | FALSE | 2015 | 2018 | Portugal | Proença-a-Nova | Castelo Branco | 5 | 24 | 18-05-2016 | 19-12-2018 | 945 | 270 | 500000 | 495782.5 | 2 | 514210.85 | -18428.35 | 96.4162 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Technical Value of the Proposal 60% 2) Price 40% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of a period of 37 days and a period of 30 days for correction of defects in the project detected in the inspection for the purposes of provisional acceptance. | changes in the value of the project result from more work, underwork, the supply of errors and omissions and the price revision carried out.
3607 | 2282990 | Execution of infrastructures for the creation of social housing in Outeiro da Maceda, Municipality of Murtosa | 45111000-8 | Demolition, site preparation and clearance work | FALSE | 2016 | 2019 | Portugal | Murtosa | Aveiro | 1 | 30 | 07-07-2016 | 08-03-2019 | 974 | 365 | 726726.19 | 562916.62 | 2 | 584240.52 | -21323.9 | 96.3502 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a deadline | the project was completed in its entirety, with €562,916.62 being invoiced for normal work and €21,323.90 for price revisions (vat at the legal rate in force is added to both values)
3608 | 2279413 | Refurbishment/Expansion of the Basic and High school of Central Portugal | 45000000-7 | Construction work | FALSE | 2015 | 2019 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 04-07-2016 | 18-12-2019 | 1262 | 240 | 700000 | 553226.67 | 2 | 530383.57 | 22843.1 | 104.3069 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of deadline for completion of works and finishes | over and underwork. additional works: waterproofing screens, shale screen, omega gutters.
3609 | 2276261 | Memorial to refugees and consul Aristides de Sousa Mendes, in Vilar Formoso | 45212313-3 | Museum construction work | FALSE | 2016 | 2019 | Portugal | Almeida | Guarda | 9 | 20 | 01-07-2016 | 08-07-2019 | 1102 | 270 | 765368.02 | 537000 | 2 | 681950.52 | -144950.52 | 78.7447 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful and legal extensions | extra and underwork, errors and omissions supply and price review
3610 | 2270887 | Reinforcement of sectorization of the water supply system - Construction of 24 new measurement points and modifications to the distribution network | 45000000-7 | Construction work | FALSE | 2016 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 20-06-2016 | 15-10-2018 | 847 | 150 | 210000 | 162103.6 | 1 | 160829.63 | 1273.97 | 100.7921 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Those indicated in point 15 of the Program of Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | waiting for authorizations from other entities | underwork has occurred
3611 | 2265302 | 09/2016/EMP/DGR _ EN256 Variant to the Albardão bridge, including a new bridge over the Degébe river | 45233142-6 | Road-repair works | FALSE | 2010 | 2019 | Portugal | N/A | N/A | N/A | 48 | 31-05-2016 | 27-11-2019 | 1275 | 300 | 3000000 | 2605654.08 | 3 | 2568062.57 | 37591.51 | 101.4638 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractor difficulty in initial mobilization, affected services, felling of protected trees, expropriations and unfavorable weather conditions | works in which it was found that the estimated amount of the project was not adequate in view of the real situation verified and adjustments within the scope of the affected services.
3612 | 2260675 | Business Nest - Phase 2 - Building Expansion | 45213000-3 | Construction work for commercial buildings, warehouses and industrial buildings, buildings relating to transport | FALSE | 2016 | 2019 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 24-06-2016 | 10-09-2019 | 1173 | 270 | 613207.55 | 519807.94 | 2 | 519807.94 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension
3613 | 2256803 | "Expansion of the wastewater drainage network in Barroselas - quarry and feijo" | 45232452-5 | Drainage works | FALSE | 2016 | 2019 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 24-06-2016 | 08-01-2019 | 928 | 240 | 372588 | 318779.87 | 2 | 318779.87 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the Proposal - 60%; price of Proposal - 40%. The subfactors are those contained in article 18 of the procedure program | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3614 | 2254003 | Parish of Louriçal / Path between Moita do Boi and Castelhanas - Proc. No. 24/2015 | 45233220-7 | Surface work for roads | FALSE | 2015 | 2018 | Portugal | Pombal | Leiria | 10 | 24 | 16-07-2015 | 03-01-2018 | 902 | 240 | 338283.96 | 276899.98 | 2 | 265271.1 | 11628.88 | 104.3838 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay in the contract is due to the verification of all the projects carried out by the contractor, recorded in the measurement report after the end of the project period, march 2016, with the measurements being determined between the inspection department and the project director after verification of the good execution, namely tests of some materials applied on site and without which it is impossible to assess conformity. | existence of underwork, more work and negative price revision value.
3615 | 2253429 | Pe_15076_cie - international public tender for the conclusion of the contract for the modernization works of the High school of Padrão da Légua, in Matosinhos | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2018 | Portugal | Matosinhos | Porto | 13 | 41 | 21-06-2016 | 27-11-2018 | 889 | 364 | 12018498.21 | 9439272.77 | 3 | 9298629 | 140643.77 | 101.5125 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 26 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the 65-day period granted due to the unforeseen existence of unregistered infrastructure in the retaining wall deployment zone and the need to change the construction method of said wall, for safety reasons. | - errors and omissions with 50% responsibility of the client - errors and omissions with 100% responsibility of the client - measurement balances
3616 | 2251931 | Requalification of EM 590 - streetDr. Joao Mendes Correia da Rocha | 45233142-6 | Road-repair works | FALSE | 2016 | 2019 | Portugal | Vagos | Aveiro | 1 | 30 | 17-06-2016 | 12-09-2019 | 1182 | 120 | 322326.1 | 298320.24 | 2 | 256777.23 | 41543.01 | 116.1786 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension: 30 days until 12/25/2016 - cmv decision dated 12/15/2016; term extension: 30 days until 01/25/2017 - cmv deliberation, dated 01/19/2017. | underwork: €52,819.57 and provisional price revision: €11,276.56
3617 | 2250066 | Improvement and conservation of roads - execution of support walls and storm drains | 45233252-0 | Surface work for streets | FALSE | 2016 | 2018 | Portugal | Guarda | Guarda | 9 | 9 | 08-06-2016 | 04-10-2018 | 848 | 240 | 275872 | 219199.94 | 1 | 219199.94 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions experienced during the project
3618 | 2247003 | Installation of the Escola do Mar: Civil Construction contract to adapt the facilities of the former Naval Radio, and Acquisition of Basic Equipment | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2016 | 2019 | Portugal | Horta | Região Autónoma dos Açores | 15 | 48 | 18-06-2016 | 22-05-2019 | 1068 | 365 | 3450000 | 3445400 | 3 | 3670338.29 | -224938.29 | 93.8715 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K = (0.4 x K1) + (0.6 X K2) K1) Price (40%) K2) Technical quality of the proposal (60%) assessed by: - Work Plan (70%); -Descriptive and Justification of the mode of execution of the work (30%). | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of work to supply errors and omissions and additional work. | execution of work, work to supply errors and omissions and extra work.
3619 | 2237032 | Rehabilitation of the New Music Building | 45212170-8, 45212321-2 | Entertainment building construction work, Auditorium construction work | FALSE | 2015 | 2019 | Portugal | Loulé | Faro | 8 | 40 | 17-05-2016 | 22-05-2019 | 1100 | 540 | 3065523.16 | 2329999.04 | 3 | 2313961.98 | 16037.06 | 100.6931 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work execution delay | underwork
3620 | 2236425 | Cycle path-1st phase | 45233260-9 | Pedestrian ways construction work | FALSE | 2016 | 2018 | Portugal | São Pedro do Sul | Viseu | 20 | 20 | 07-06-2016 | 22-05-2018 | 714 | 360 | 371602.03 | 297281.63 | 2 | 308534.6 | -11252.97 | 96.3528 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | more work, underwork and price revisions
3621 | 2234940 | Improvement of bituminous pavements on different roads | 45233142-6 | Road-repair works | FALSE | 2015 | 2018 | Portugal | Maia | Porto | 13 | 32 | 07-06-2016 | 13-04-2018 | 675 | 420 | 2555997.36 | 2044797.9 | 3 | 2016883.93 | 27913.97 | 101.384 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60%; Technical value - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | after the completion of the project deadline, there were two inspection notices - to correct anomalies, the 1st on october 2, 2017 extending the deadline to 60 days and the 2nd on december 27 2017, to extend the deadline for another 90 days. | this contract had a contract no. 58/2016 of 06/7/2016 with an initial value of 2,044,797.90, a 2nd compensation contract for underwork for more work with no. 107/2017 of 03/08/2017, replacing the initial value by 2,044,627.97, and also a reduction of works, with the total value of the project being 2,016,863.93 €.
3622 | 2234719 | Contract for the Repair and Improvement of Municipal Social Housing | 45453100-8 | Refurbishment work | FALSE | 2016 | 2019 | Portugal | Lagos | Faro | 8 | N/A | 09-06-2016 | 15-07-2019 | 1131 | 365 | 287500 | 224872.61 | 1 | 226252.13 | -1379.52 | 99.3903 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the project execution period, pursuant to paragraph 7.8 of the tender specifications, until the contractual price is exhausted | determined the final value of the price revision, in the amount of €1,379.52
3623 | 2233386 | Conservation of the municipal road network - Repaving of the EM 521 from S. Sebastião to the IP4 overpass | 45233220-7 | Surface work for roads | FALSE | 2016 | 2018 | Portugal | Bragança | Bragança | 4 | 20 | 03-06-2016 | 08-02-2018 | 615 | 180 | 298565.08 | 229184 | 1 | 221133.95 | 8050.05 | 103.6404 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting) Technical quality of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unforeseen difficulties in drilling the windows of the pedestrian shelter at the entrance to the miguel torga secondary school. | underwork
3624 | 2232231 | Improvement of cube pavements on different roads | 45233142-6 | Road-repair works | FALSE | 2015 | 2018 | Portugal | Maia | Porto | 13 | 30 | 07-06-2016 | 05-01-2018 | 577 | 420 | 1771778.29 | 1417422.65 | 3 | 1417422.65 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 60% Price; 40% Technical value | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract had 14 work inspection and measurement reports, the last of which was dated september 26, 2017.
3625 | 2230782 | Building rehabilitation on streetAdriano Pinto Basto | 45262700-8 | Building alteration work | FALSE | 2016 | 2019 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 30-05-2016 | 07-02-2019 | 983 | 365 | 200000 | 154790.1 | 1 | 145451.26 | 9338.84 | 106.4206 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value of the Proposal: 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work and deadline extension. | underwork and price revision.
3626 | 2227723 | Paving in the parish of Cachopo | 45112700-2, 45233220-7 | Landscaping work, Surface work for roads | FALSE | 2015 | 2019 | Portugal | Tavira | Faro | 8 | 31 | 07-06-2016 | 24-01-2019 | 961 | 180 | 680364.42 | 366721.48 | 2 | 355429.1 | 11292.38 | 103.1771 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension due to pss approval and delivery of the technical compilation. | underwork worth -63.78€ and definitive price revision worth -11,228.60€ (negative).
3627 | 2224105 | "Improvement and Repaving of Av.ª Sá Carneiro, in Valpaços". | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Valpaços | Vila Real | 19 | 24 | 06-06-2016 | 31-08-2018 | 816 | 270 | 557278.56 | 390095 | 2 | 382811.44 | 7283.56 | 101.9026 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: In accordance with paragraph 17 of the Program of Procedure: a) The most economically advantageous proposal for the City Council, densified by the factors and sub-factors defined in Annex VI of the Procedure Program; b) The analysis and evaluation of the proposals will be carried out by the expressly appointed jury; c) If there are two or more proposals with the same score, the following tiebreaker is established: 1st - The proposal with the lowest price. If the tie still exists: 2nd - The proposal that obtains the best score in the "technical value" factor. If the tie still exists: 3.º - Proposals will be ordered by the order of entry on the platform. Annex VI of the Procedure Program: 1st - The award will be made to the most economically advantageous proposal, this being dedeadlineined by assessing two factors: Proposal (PP) and Technical Value of the Proposal (VTP). 2nd - The weighting coefficients for the two factors are, respectively, 75% and 25%. 3.º - The classification of proposals is carried out by applying the following formula: CP = PP x 75% + VTP x 25% 4th - Definition of concepts: a) Price of the Proposal under analysis (PPa) - is the algebraic addition of the value contained in the Main Form of the Proposal under analysis with the value assigned to supply the List of Errors and Omissions approved by the competent Body for the decision to hire, if applicable, and, occurring with the correction of account errors; b) Base Price (PB) - is the maximum price that the contracting authority is willing to pay for the execution of all the services that constitute the object of the contract to be signed, article 47 of the Public Contracts Code (CCP); c) Abnormally Low Price (PAB) - is the value set in the tender program, by reference to the base price set in the charges, from which the total price resulting from a proposal is considered abnormally low, article 132 of the CCP. d) Documents with Justification Clarifications - are the documents to be presented by the bidder with a proposal with price abnormally low, either accompanying the proposal or after notification, in writing, to provide clarifications within a suitable period justifications relating to the constituent elements of the proposal that it deems relevant for this purpose, paragraph d) of number 1 of article 57 and number 3 of article 71 of the CCP, respectively; e) Approximation of the score - the score to be assigned to each subfactor and factor is approximated to four decimal places. 5.º - Scoring of the Proposal Price, is carried out by applying the following formulas and the following rules: a) Formula 1, for proposals with prices within the following limits: less than or equal to the base price and greater than or equal to seventy percent (70%) of the base price: PP = 30 + (PB-PPa)/(0.30xPB) x 70 b) Proposals with an abnormally low total price, whose justifications have been considered under the deadlines of article 71 of the CCP, are punctuated by the application of Formula 2: PP = 100 + (PB-PPa)/(0.70xPB) x 5 c) Being: i) PP - score of the price of the proposal under consideration; ii) PB - base price; iii) PPa - price of the proposal under analysis; d) The scoring scale varies between thirty (30) and one hundred and five (105) points; e) Proposals that present a price are excluded: i) contract higher than the base price, under the deadlines of paragraph d) of number 2 of article 70 and paragraph o) of number 2 of article 146 of the CCP; ii) an abnormally low total, under the deadlines of subparagraph e) of number 2 of article 70 and of subparagraph d) and o) of number 2 of article 146 of the CCP, after verification pursuant to the provisions of article 71 of the CCP. 6 - The Technical Valuation of the Proposal is scored based on the analysis of the following three sub-factors: Work Plan (PT), Memory Justification and Description of the Work (MO) and Payment Plan (PG), with the respective weighting coefficients of 50%, 30% and 20%, using the following formula: VT = PT x 50% + MO x 30% + PG x 20% 7.º - The score for the Work Plan subfactor is obtained by analyzing the following three elementary subfactors: Work Map (MdT), Manpower Map (MMO) and Equipment Map (MEq), with the following weighting coefficients of 50%, 25% and 25%, using the following formula: PT=MdT x 50%+ MMO x 25%+MEq x 25% 8.º - The scoring scale for these elementary factors and subfactors varies between zero (0) and one hundred (100) points, according to the set order of different attributes likely to be proposed that allows the attribution of partial scores (descriptors- predicted 9th to 13th of Annex VI of the Program of Procedure). | 1 | 75 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two graceful extensions:90+45 days | underwork worth €7,283.56
3628 | 2223126 | 5010021635 - Belt Line - Implementation of the RCT+TP system and remote control of disconnectors | 50220000-3 | Repair, maintenance and associated services related to railways and other equipment | FALSE | 2015 | 2018 | Portugal | N/A | N/A | N/A | 20 | 16-05-2016 | 10-10-2018 | 877 | 270 | 260000 | 257984.69 | 2 | 257686.34 | 298.35 | 100.1158 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 70% 2. Technical value - 10% 3. Safety Management System - 10% 4. Quality Control System - 5% 5. Environmental Monitoring System - 5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3629 | 2221467 | Year 2016_Contract for the Rehabilitation/Expansion of the Building located at street of Vinha, 21-23, in Lisbon | 45000000-7, 45210000-2, 45260000-7, 45200000-9 | Construction work, Building construction work, Roof works and other special trade construction works, Works for complete or part construction and civil engineering work | FALSE | 2015 | 2019 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-05-2016 | 01-08-2019 | 1168 | 365 | 420000 | 329032.29 | 2 | 465440.91 | -136408.62 | 70.6926 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 31 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to carry out additional works and to proceed with the extension of the execution period of the project. | there was a need to carry out additional works and to proceed with the extension of the execution period of the project.
3630 | 2215109 | The purpose of the contract is to carry out all the work defined, as to their type, quantity and technical conditions, in the execution projects and in the specifications. | 45212313-3 | Museum construction work | FALSE | 2015 | 2018 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | 21 | 24-05-2016 | 14-09-2018 | 843 | 365 | 1600000 | 1360000.01 | 3 | 1388544.94 | -28544.93 | 97.9443 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factor 1 - Technical Quality of the Proposal - 60% subfactor 1.1 - Work Plan - 70% subfactor 1.2 - Descriptive and Justification - 30% Factor 2 - Price - 40% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays in crane assembly; labor shortage; constraints on the supply of aggregates; difficulties in resolving orders for materials. | there was no change
3631 | 2206451 | 5010020489 - Minho Line Contract - Stabilization of Slopes Pk 64+610 - 64+990 (LE) and 64+660 - 64+915 (LD) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2018 | Portugal | N/A | N/A | N/A | 20 | 16-05-2016 | 13-04-2018 | 697 | 150 | 501356 | 321340.44 | 2 | 317552.39 | 3788.05 | 101.1929 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price 60% 2. Technical Valuation 20% 3. Occupational Health and Safety Management System 10% 4. Work Quality Control System 5% 5. Environmental Monitoring System 5% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | ordinary price review (article 382 of the "public procurement code")
3632 | 2203934 | Repaving and Improvement of E.N.16-Alto do Leomil section / Mendo castle crossing | 45233200-1 | Various surface works | FALSE | 2016 | 2018 | Portugal | Almeida | Guarda | 9 | 24 | 09-05-2016 | 08-01-2018 | 609 | 120 | 396299.78 | 266800 | 2 | 276435.14 | -9635.14 | 96.5145 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions and the responsibility of the contractor | price review
3633 | 2200841 | All works related to the contract for the construction of the Science and Technology Park on Terceira Island. | 45220000-5 | Engineering works and construction works | FALSE | 2015 | 2018 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 48 | 19-05-2016 | 03-07-2018 | 775 | 545 | 7600000 | 6999523.17 | 3 | 7077289.48 | -77766.31 | 98.9012 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The factors and subfactors that densify the award criteria, as well as the respective descriptors, evaluation methods and calculation formulas, are those contained in clause 21 of the Procedure Program. | 0 | 0 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | project change | demolition of unforeseen walls
3634 | 2196759 | Enlargement of the pedestrian and cycle network in Conceição - Cabanas | 45112700-2 | Landscaping work | FALSE | 2015 | 2019 | Portugal | Tavira | Faro | 8 | 25 | 16-05-2016 | 04-02-2019 | 994 | 180 | 192321.21 | 159687.57 | 1 | 154246.69 | 5440.88 | 103.5274 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions and delivery of the technical compilation. | underwork worth -5,394.99€ and definitive price revision worth -45.89€ (negative).
3635 | 2190368 | Requalification and improvement of several streets in the parishes of Amor, Bidoeira de Cima, Milagres and União de Freguesias de Souto da Carpalhosa and Ortigosa - Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2015 | 2019 | Portugal | Leiria | Leiria | 10 | 20 | 18-03-2016 | 08-05-2019 | 1146 | 180 | 472348.5 | 364000 | 2 | 341696.88 | 22303.12 | 106.5272 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to define underwork | underwork
3636 | 2183442 | Sanitation and water supply in Rompecilha | 45232460-4 | Sanitary works | FALSE | 2016 | 2019 | Portugal | São Pedro do Sul | Viseu | 20 | 20 | 11-05-2016 | 05-09-2019 | 1212 | 365 | 227264 | 163995.74 | 1 | 142130.54 | 21865.2 | 115.3839 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work | more work, underwork and price revision.
3637 | 2177537 | Road infrastructures of the Detailed Plan of Part of the Industrial Zone of Cacia | 45233120-6 | Road construction works | FALSE | 2016 | 2019 | Portugal | Aveiro | Aveiro | 1 | 21 | 04-05-2016 | 20-11-2019 | 1295 | 180 | 849056.02 | 749003.8 | 2 | 898146.53 | -149142.73 | 83.3944 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | more works -
3638 | 2173888 | Paving in hot bituminous coating of several roads in the Municipality, including in the city of Coimbra, which are very degraded, including the replacement of horizontal signage | 45233252-0 | Surface work for streets | FALSE | 2015 | 2019 | Portugal | Coimbra | Coimbra | 6 | 24 | 20-11-2015 | 26-11-2019 | 1467 | 330 | 1472000 | 883200.01 | 2 | 819980.17 | 63219.84 | 107.7099 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | gracious term extension | amount of price revision and work not performed.
3639 | 2169991 | Repaving of Povos do Alto and Saneamento road | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2018 | Portugal | São Pedro do Sul | Viseu | 20 | 12 | 04-05-2016 | 04-05-2018 | 730 | 120 | 188679 | 163747.68 | 1 | 165475.35 | -1727.67 | 98.9559 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | there was underwork. there was a final price revision in the amount of €2,280.16.
3640 | 2152546 | Construction contract for new facilities for Primary school in Canto da Maia - São Miguel | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2019 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 60 | 15-04-2016 | 07-01-2019 | 997 | 730 | 17000000 | 14450000.01 | 3 | 14739094.9 | -289094.89 | 98.0386 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1: Price - 40% Factor 2: Technical quality of the proposal - 60% Subfactor 2.1: Work plan Subfactor 2.2: Descriptive memory and justification of the mode of execution of the work | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | free term extension | order of non-execution of work
3641 | 2140727 | The purpose of the contract is the execution of the water supply and drainage networks and the treatment of domestic wastewater and rainwater in the village of João Serra. | 45232460-4 | Sanitary works | FALSE | 2015 | 2018 | Portugal | Mértola | Beja | 2 | 30 | 04-04-2016 | 06-06-2018 | 793 | 270 | 869874.08 | 645509.37 | 2 | 636986.35 | 8523.02 | 101.338 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | underwork
3642 | 2115360 | Year 2016_Rehabilitation contract for the new entrance to the S. Roque complex | 45262000-1, 45260000-7, 45262700-8 | Special trade construction works other than roof works, Roof works and other special trade construction works, Building alteration work | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 31-03-2016 | 08-02-2018 | 679 | 275 | 750000 | 547477.15 | 2 | 636688.72 | -89211.57 | 85.9882 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 26 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to carry out additional works and to proceed with the extension of the execution period of the project. | there was a need to carry out additional works and to proceed with the extension of the execution period of the project.
3643 | 2110081 | Construction contract for the Doze Ribeiras Day Center, Terceira Island. | 45215221-2 | Daycare centre construction work | FALSE | 2015 | 2018 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 15-03-2016 | 09-11-2018 | 969 | 365 | 799000 | 798000 | 2 | 801013.65 | -3013.65 | 99.6238 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price factor (K1) with a weight of 40% 2. Factor technical quality of the proposal (K2) with a weight of 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | article 13, decree-law no. 6/2004, of 6 january.
3644 | 2085614 | Public Contest No. 4-A1/2015 - The purpose of the contract is the milling and replacement of pavements in interventions in the water supply and domestic wastewater and rainwater drainage networks | 45233222-1 | Paving and asphalting works | FALSE | 2015 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 15-03-2016 | 16-08-2018 | 884 | 365 | 320000 | 240130 | 1 | 240130 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award criterion is the proposal economically most advantageous, taking into account the following factors with the following weighting: a) Technical Quality of the Proposal - 60% and b) Price - 40%. These factors are, in turn, divided into different duly weighted sub-factors, according to with the following: a) Technical Quality of the Proposal (QTP): a1) Number of personnel assigned to carry out the tasks per work front (QP) - 20%; a2) Quantity of equipment to be assigned to the work per work front (QE) - 35%; a3) Number of work fronts in simultaneous (FT) - 45%. QTP = 20% x QP + 35% x QE + 45% x FT. b) Price (P)- P = (Pb - Vp) / Pb, where: Pb - Base Price; Vp - Proposal Value; P = 0.4 - if 0 < Vp < Pab, where: Pab - Abnormally low price (<40% Pbase). The subfactors a1) to a3) will be evaluated in accordance with what is described in point 22.3 of the Tender Programme. The final classification will be given by the following formula: CF= 60% x QTP + 40% x P. Proposals are sorted in descending order according to the classification obtained. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in less time than initially planned because the company's needs required it.
3645 | 2085582 | Remodeling and rehabilitation of reservoirs | 45453100-8 | Refurbishment work | FALSE | 2015 | 2018 | Portugal | Cantanhede | Coimbra | 6 | 30 | 11-03-2016 | 05-11-2018 | 969 | 355 | 370000 | 337639.22 | 2 | 318731.91 | 18907.31 | 105.932 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | underwork
3646 | 2076678 | Construction contract for the new Carril Bridge over the Lousã stream | 45221111-3 | Road bridge construction work | FALSE | 2015 | 2019 | Portugal | Tomar | Santarém | 16 | 20 | 03-03-2016 | 04-02-2019 | 1068 | 180 | 220000 | 197883 | 1 | 195550.8 | 2332.2 | 101.1926 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay in carrying out the project was due to changes made to the structure of the bridge, and adverse weather conditions that prevented some works from being carried out on the scheduled dates. | price revision: -2 332.18€
3647 | 2067621 | Repair of the Transport Coordinating Center - Union of the parishes of Antas and Abade de Vermoim | 45453100-8 | Refurbishment work | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 03-03-2016 | 28-06-2018 | 847 | 210 | 212000 | 157690.64 | 1 | 154097.48 | 3593.16 | 102.3317 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60% Technical Valuation of the Proposal: 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of work (60 days). | underwork worth €3,593.16.
3648 | 2065988 | 10-Emp/15 - Repair of CM 1231 between Fuseta and Cintados (up to the Municipality Limit) | 45233220-7 | Surface work for roads | FALSE | 2015 | 2019 | Portugal | Tavira | Faro | 8 | 24 | 07-03-2016 | 22-01-2019 | 1051 | 150 | 779086.2 | 485651.49 | 2 | 456349.02 | 29302.47 | 106.4211 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension for 1 day due to communication of pss approval on 02/06/2016 and delivery of the technical compilation. | price revision in the amount of -29,302.47€ (negative).
3649 | 2011344 | The object of this contract is the general renovation of the water supply networks throughout the period of the contract. These renovations will be requested by the owner of the work according to their needs. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2015 | 2018 | Portugal | Estarreja | Aveiro | 1 | N/A | 04-02-2016 | 02-04-2018 | 788 | 1095 | 249000 | 225697.04 | 1 | 225697.04 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractual deadlines have been met
3650 | 2009673 | EN234 Pontes Criz I and Criz II, EN234-6 Ponte São João das Areias. Intervention of structural reinforcement in pillars and foundations | 45221119-9 | Bridge renewal construction work | FALSE | 2015 | 2020 | Portugal | Mortágua | Viseu | 20 | 48 | 16-10-2015 | 15-04-2020 | 1643 | 600 | 9000000 | 6992031.33 | 3 | 7142989.86 | -150958.53 | 97.8866 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 70% - Technical value 30% | 1 | 70 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline was based on 2 factors, the abnormally low water level in the aguieira dam reservoir and the fire that occurred on october 15th. | drilling and execution of micropiles. increase in the amount of pipe for piles on the criz bridges and removal of injection along the axis of the piles. increased amount of pipe for piles on s.j. de areias and the removal of the number of piles on the criz ii bridge. execution of the thickening of the p6 pillar of the criz ii bridge and also the removal of unfulfilled quantities of work
3651 | 1990243 | Construction of the neighborhood of S.Sebastião | 45211100-0 | Construction work for houses | FALSE | 2015 | 2019 | Portugal | Cinfães | Viseu | 20 | 20 | 02-02-2016 | 08-11-2019 | 1375 | 545 | 999992.42 | 918918 | 2 | 961863.42 | -42945.42 | 95.5352 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | existence of work to supply errors and omissions. | existence of work to supply errors and omissions, underwork and price revision.
3652 | 1951380 | The object of the contract is the execution of the contract for the construction of the building to support artisanal fishing in Burgau, in accordance with the specifications described in the terms of reference and in the contract. | 45210000-2 | Building construction work | FALSE | 2015 | 2019 | Portugal | Vila do Bispo | Faro | 8 | 15 | 30-10-2015 | 13-08-2019 | 1383 | 90 | 250000 | 214608.35 | 1 | 214226.76 | 381.59 | 100.1781 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of works | underwork
3653 | 1938752 | By this contract, the Second Party undertakes to carry out all the works related to the CONTRACT FOR CONSTRUCTION OF THE FAMILY THERAPY CENTER | 45215200-9 | Construction work for social services buildings | FALSE | 2015 | 2018 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 30 | 30-11-2015 | 05-06-2018 | 918 | 366 | 508559.55 | 413269.16 | 2 | 403218 | 10051.16 | 102.4927 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: K1 - Price 40% K2 - Technical Quality of the Proposal - 60% K2.1 - Work plan - 70% K2.2 - Descriptive memory and justification of how the work was carried out - 30% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | article 379.º, "public procurement code"
3654 | 1935798 | Execution of the Flood Control contract in Águeda – Interventions in the Flow Sections of Ponte do Campo, Ponte de Óis da Ribeira and in the Secondary Channel of the River Águeda “By-Pass” in Águeda | 45221111-3 | Road bridge construction work | FALSE | 2015 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 06-01-2016 | 11-02-2020 | 1497 | 210 | 881627.85 | 723277.59 | 2 | 661346.49 | 61931.1 | 109.3644 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the fact that it was awaited for edp to indicate the location of public lighting connection for the completion of the contract. and also because of the extra work. | the change in the value of the project is due to the fact that there is underwork, namely the detour signaling that was not applied, and the removal of the electricity poles that were carried out by edp
3655 | 1922743 | “Improvement of the street layout between the municipal stadium and streetQuinta de Betunes” | 45233251-3 | Resurfacing works | FALSE | 2015 | 2018 | Portugal | Loulé | Faro | 8 | 36 | 21-10-2015 | 22-11-2018 | 1128 | 210 | 782984.54 | 544750.16 | 2 | 493635.16 | 51115 | 110.3548 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | basically, there were two basic reasons for changing the project's execution deadline, the unavailability of land between pk 0+400.00 and pk 0+460.00 (which were initially negotiated) and the need, on the part of the edp, distribuição, s.a., to build a new medium voltage network between pk 0+400.00 and pk 0+660.00. | contract work not performed.
3656 | 1911651 | Design and Construction of a new sorting station, on the island of São Miguel, and respective Supply and Assembly of all equipment | 45222100-0 | Waste-treatment plant construction work | FALSE | 2015 | 2018 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 47 | 25-11-2015 | 30-10-2018 | 1070 | 365 | 2800000 | 2799602.3 | 3 | 2799602.3 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Technical value of the proposal: 75% b) Price: 25% | 1 | 25 | N/A | TRUE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 1st extension of the deadline due to the failure of the compressor in the projectshop that supplies the compressed air and the 2nd extension of the term of the contract to carry out tests of acceptance and technical compilation / final screens. | causes of changes in the value of the project
3657 | 1901354 | Creation of infrastructures in urban space in an area of ​​1.5 hectares, serving 26 lots, 3 of which are already occupied/under construction. | 45211360-0 | Urban development construction work | FALSE | 2015 | 2018 | Portugal | Sesimbra | Setúbal | 17 | 24 | 13-10-2015 | 21-11-2018 | 1135 | 180 | 269369.72 | 183101.99 | 1 | 200481.49 | -17379.5 | 91.3311 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension following the execution of additional works. | works not contemplated
3658 | 1890665 | The object of the contract is the paving in bituminous concrete of streets in the municipality - 2nd phase | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2015 | 2020 | Portugal | Santa Maria da Feira | Aveiro | 1 | 24 | 09-12-2015 | 07-05-2020 | 1611 | 120 | 1125900 | 675540.01 | 2 | 642081.71 | 33458.3 | 105.2109 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 851 days of delay in the definitive conclusion of the project, 535 days of delay between the 1st inspection and the final one to correct defects | underwork
3659 | 1884887 | Pe_15048_cie - international public tender for the completion of the contract for the modernization of the Ponte Lima High school | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2018 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 42 | 04-12-2015 | 06-03-2018 | 823 | 455 | 13276694.01 | 9948068.08 | 3 | 9699476.63 | 248591.45 | 102.5629 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the facts that led to the extension of the term of the contract derived from work to supply errors and omissions not attributable to the contractor, which led to the extension of the contractual term for the conclusion of the contract by 17 days. | existence of work to supply errors and omissions identified in the execution phase of the contract.
3660 | 1879551 | Contract 5/GEBALIS/2015 - Public tender Maintenance and Repair of Fires and Common Areas in Neighborhoods of the South Zone, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 01-12-2015 | 28-02-2018 | 820 | 730 | 599816.6 | 575780.91 | 2 | 575780.91 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | TRUE | N/A
3661 | 1879267 | Contract 4/GEBALIS/2015 - Public tender Maintenance and Repair of Fires and Common Areas in Neighborhoods of the West Zone, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | N/A | 01-12-2015 | 09-04-2018 | 860 | 730 | 600000 | 460311.5 | 2 | 452558.99 | 7752.51 | 101.713 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | TRUE | N/A | i close the contract. | i close the contract.
3662 | 1872505 | US Vilar de Andorinho - Construction contract_x000D_ | 45215100-8 | Construction work for buildings relating to health | FALSE | 2015 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 11-09-2015 | 22-06-2018 | 1015 | 480 | 1475363.41 | 1032754.39 | 3 | 1021644.99 | 11109.4 | 101.0874 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: A - Price 70% B - Technical value of the proposal 30%: B1 - Descriptive memory 10% B2 - Work, labor, equipment and payment plans 10% B3 - Safety to be implemented in the work (technical note) 10% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3663 | 1850466 | Football Field Synthetic Grass | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2015 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 20-11-2015 | 15-04-2019 | 1242 | 120 | 287001.05 | 259206.24 | 2 | 259041.08 | 165.16 | 100.0638 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 1 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract was completed within the contractual period | underwork
3664 | 1849321 | Execution of contract en115 - improvement between km 77+025 and km 77+075. Rematerialization of the transverse profile | 45233142-6 | Road-repair works | FALSE | 2015 | 2020 | Portugal | N/A | N/A | N/A | 26 | 25-09-2015 | 20-02-2020 | 1609 | 178 | 198000 | 155671.62 | 1 | 142284.81 | 13386.81 | 109.4085 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | resulting from the elaboration of bill of quantities | resulting from the elaboration of bill of quantities, adjustment of executed quantities and underwork.
3665 | 1823801 | Water supply to Brejinho d'Agua - 2nd phase | 45232152-2 | Pumping station construction work | FALSE | 2015 | 2018 | Portugal | Grandola | Setúbal | 17 | 45 | 12-11-2015 | 21-02-2018 | 832 | 120 | 171579.05 | 158748.58 | 1 | 169437.73 | -10689.15 | 93.6914 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | appearance of greater levels during the implementation of the contract, which leaded to its delay, and delay in the delivery of the electromechanical equipment because they were decided and approved late. | during the construction, small adjustments were made in the quantities executed in relation to the quantities contracted.
3666 | 1752781 | Refurbishment of the sanitation network in Corticeiro de Cima and Vilamar | 45233252-0, 45112000-5, 45232460-4 | Surface work for streets, Excavating and earthmoving work, Sanitary works | FALSE | 2015 | 2018 | Portugal | Cantanhede | Coimbra | 6 | N/A | 30-10-2015 | 21-02-2018 | 845 | 270 | 300000 | 215848.39 | 1 | 210042.85 | 5805.54 | 102.764 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climate change | underwork
3667 | 1742245 | Bituminous concrete paving of streets in the municipality - 1st Phase - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2015 | 2018 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 27-10-2015 | 17-07-2018 | 994 | 120 | 1221935 | 854337.47 | 2 | 848963.76 | 5373.71 | 100.633 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (P) - 60%; and b) Technical Quality of the Proposal (QTP) - 40%. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension granted as a grace (74 days). delay in execution attributable to the contractor (665 days). period elapsed between the 1st and the last inspection for the purposes of provisional acceptance, to correct deficiencies (42 days). | underwork.
3668 | 1690154 | Carrying out the work defined as to its type, quantity and technical conditions of execution, in the submitted proposal and in the specifications | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2018 | Portugal | Calheta | Região Autónoma dos Açores | 15 | 75 | 14-10-2015 | 15-12-2018 | 1158 | 730 | 16000000 | 14989999.99 | 3 | 15083896.68 | -93896.69 | 99.3775 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1: Price - 40%; Factor 2: Quality proposal technique - 60%; Subfactor 2.1: Work plan; Subfactor 2.2: Descriptive memory and justification of the execution mode of the constructions. | 1 | 40 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions | less and more work
3669 | 1682966 | Road Sezures - Boco - Quinta da Ponte - House (Municipal Road 1429, Sezures - Boco) | 45233142-6 | Road-repair works | FALSE | 2015 | 2018 | Portugal | Penalva do Castelo | Viseu | 20 | 21 | 19-10-2015 | 20-03-2018 | 883 | 120 | 335836.18 | 269472.31 | 2 | 253653.9 | 15818.41 | 106.2362 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | over and underwork
3670 | 1665457 | Intervention in Terceira's Terrestrial Logistic Circuits - rehabilitation and improvement of Regional Road n.º5 - 2.ª, in São Brás and Lajes - Terceira Island - Azores | 45232451-8 | Drainage and surface works | FALSE | 2015 | 2018 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 24 | 09-10-2015 | 13-08-2018 | 1039 | 180 | 590000 | 501500.01 | 2 | 463135.61 | 38364.4 | 108.2836 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Bid price - 40% b) Technical quality of the proposal - 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions | price review
3671 | 1657542 | 0070/DOM/DGEPIM/14 - Maritime Promenade - Section between Baia dos Golfinhos and Praia da Cruz Quebrada | 45233200-1, 45262300-4, 45246500-8, 45315600-4, 45112000-5, 45232452-5 | Various surface works, Concrete work, Promenade construction work, Low-voltage installation work, Excavating and earthmoving work, Drainage works | FALSE | 2015 | 2019 | Portugal | Oeiras | Lisboa | 11 | 60 | 11-08-2015 | 14-01-2019 | 1252 | 365 | 4121841.02 | 2535088.03 | 3 | 2503278.12 | 31809.91 | 101.2707 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: F1 - Price (60%); F2 - Value and feasibility proposal technique (30%); F3 - Execution time (10%) | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
3672 | 1653462 | Execution of a new street layout and widening of existing street layout platforms | 45000000-7 | Construction work | FALSE | 2015 | 2018 | Portugal | Murtosa | Aveiro | 1 | 30 | 08-10-2015 | 17-12-2018 | 1166 | 150 | 219903.5 | 176843.8 | 1 | 174247.29 | 2596.51 | 101.4901 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was physically completed in the last quarter of 2016, however works worth €26,227.05 were not measured on that date, having been measured in december 2018 | works worth €2,596.50 + vat were not carried out
3673 | 1643205 | Benefit from E.M. 397 E slope stabilization | 45262310-7, 45112700-2, 45233142-6 | Reinforced-concrete work, Landscaping work, Road-repair works | FALSE | 2015 | 2021 | Portugal | Tavira | Faro | 8 | 24 | 15-09-2015 | 07-05-2021 | 2061 | 210 | 475684.87 | 289366.07 | 2 | 232141.01 | 57225.06 | 124.651 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the term, suspension of the term, replacement of plantations and delivery of the technical compilation. | underwork and price revision
3674 | 1633608 | Improvement of Energy Efficiency in Bairro Social da Coxa | 45321000-3 | Thermal insulation work | FALSE | 2015 | 2018 | Portugal | Bragança | Bragança | 4 | 20 | 30-09-2015 | 08-05-2018 | 951 | 365 | 1310795.5 | 980748.93 | 2 | 971458.26 | 9290.67 | 100.9564 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty associated with marking to access the interior of several units. | underwork.
3675 | 1580792 | Improvement of E. M. 571-1 (1st phase) - Union of the parishes of Lemenhe, Mouquim and Jesufrei | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 15-09-2015 | 06-12-2018 | 1178 | 365 | 744480.13 | 644093.83 | 2 | 635237.24 | 8856.59 | 101.3942 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended for a period of 300 days. | review of prices payable by the successful tenderer in the amount of €8,856.59.
3676 | 1580749 | Improvement of C.M. 1521 - Union of the parishes of Ruivães and Novais and parish of Landim | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 15-09-2015 | 18-10-2018 | 1129 | 540 | 936246.1 | 876672.15 | 2 | 866647.56 | 10024.59 | 101.1567 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule. | decrease in the cost of the project due to price revisions.
3677 | 1575526 | The object of this work contract is the execution, by the second party to the first party, of the work of the «Estrada Oliveirinha a Travanca de São Tomé | 45233142-6 | Road-repair works | FALSE | 2015 | 2018 | Portugal | Carregal do Sal | Viseu | 20 | 20 | 08-09-2015 | 05-01-2018 | 850 | 240 | 208000 | 185500 | 1 | 189108.55 | -3608.55 | 98.0918 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline is due to the completion of more work | the execution of additional works was the widening of the road next to the building of the old primary school of travanca de são tomé, allowing the execution of sidewalks, parking area and road profile with 5.5 meters.
3678 | 1567128 | Improvement of E.M. 573-2 - Union of the parishes of Antas and Abade de Vermoim and union of the parishes of Avidos and Lagoa | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 11-09-2015 | 25-10-2018 | 1140 | 365 | 640074.88 | 512043.95 | 2 | 503398.89 | 8645.06 | 101.7173 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended for 93 days. | decrease in the value of the project due to the price review.
3679 | 1566178 | Revitalization of public spaces - Churchyard - Union of the parishes of Antas and Abade de Vermoim | 45233160-8 | Paths and other metalled surfaces | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 10-09-2015 | 18-10-2018 | 1134 | 365 | 568589.5 | 523657.84 | 2 | 518167.48 | 5490.36 | 101.0596 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended for a period of 120 days. | revision of prices to be paid by the contractor in the amount of €5,307.75.
3680 | 1565981 | Improvement of the Municipal Council 1490 / 1490-1 - Union of the parishes of Vale S. Cosme, Telhado and Portela and the parish of Vale S. Martinho | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 10-09-2015 | 30-10-2018 | 1146 | 730 | 1871367.32 | 1417301.15 | 3 | 1408080.7 | 9220.45 | 100.6548 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule. | amount payable by the contractor regarding the price review: €9,920.43
3681 | 1534098 | Reconstruction of a student residence building at streetConselho Abílio Beça n.º 4-6-8 within the scope of the strategic plan for urban rehabilitation | 45214700-7 | Construction work for halls of residence | FALSE | 2015 | 2018 | Portugal | Bragança | Bragança | 4 | 20 | 18-08-2015 | 20-12-2018 | 1220 | 300 | 345000 | 299746.44 | 2 | 299746.44 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (70% weighting) b) Technical quality of the proposal (30% weighting) | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | project uncertainties and archeology works.
3682 | 1522246 | construction work number 12/dmpo/dcmivp/ds/2014 - "conservation and maintenance of the public sanitation network in the western and north areas" (process no. 17/cp/deps/n.d./2015) | 45232460-4 | Sanitary works | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 10-08-2015 | 12-11-2018 | 1190 | 365 | 729589.49 | 507711.03 | 2 | 507711.02 | 0.01 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Refer to point 14 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3683 | 1521421 | construction work number 13/dmpo/dcmivp/ds/2014 - "conservation and maintenance of the public sanitation network in the center and historical center areas" (process no. 16/cp/deps/n.d./2015) | 45232460-4 | Sanitary works | FALSE | 2015 | 2018 | Portugal | Lisboa | Lisboa | 11 | 20 | 10-08-2015 | 21-09-2018 | 1138 | 365 | 747999.95 | 523611.73 | 2 | 513630.72 | 9981.01 | 101.9432 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Refer to point 14 of the Program of Contest | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3684 | 1513881 | Barrosas Water Network | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2018 | Portugal | Loulé | Faro | 8 | 24 | 26-03-2015 | 12-12-2018 | 1357 | 90 | 365484.57 | 206878.06 | 1 | 206875.3 | 2.76 | 100.0013 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | executed the necessary for the functioning of the final object of the project
3685 | 1510804 | Municipal Rehabilitation Contract for the External Surroundings and Common Parts of the Buildings of Lots 24 and 25 of Quinta da Mina - Cidade Sol | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2015 | 2021 | Portugal | Barreiro | Setúbal | 17 | 20 | 15-07-2015 | 01-03-2021 | 2056 | 120 | 236000 | 168050 | 1 | 170941.26 | -2891.26 | 98.3086 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a)-Price of the proposal - 60% b)-Quality of the proposal - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extensions | over and underwork
3686 | 1508135 | Improvement of C. M. 1464 / 1464-1 - Ribeirão | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 24-07-2015 | 18-10-2018 | 1182 | 365 | 417001.2 | 389634.4 | 2 | 367823.95 | 21810.45 | 105.9296 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork in the amount of €9,824.02 and a decrease in the final value due to the price revision in the amount of €11,986.13.
3687 | 1507517 | Improvement of E. M. 571 - 2nd phase - Union of parishes of Arnoso Sta. Maria, arnoso sta. Eulália and Sezures and parish of Nine | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 22-07-2015 | 29-10-2018 | 1195 | 540 | 1189883.03 | 950491.99 | 2 | 938330.56 | 12161.43 | 101.2961 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work for a period of 30 days. | decrease in the cost of the project due to the price review.
3688 | 1507505 | Improvement of E.M. 573-1 - Requião | 45233140-2 | Roadworks | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 23-07-2015 | 18-10-2018 | 1183 | 365 | 699537.99 | 649969.77 | 2 | 638508.85 | 11460.92 | 101.795 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical boo of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended for a period of 120 days. | decrease in the value of the project due to the price revision.
3689 | 1507497 | Connection of E. N. 14 to E. M. 508-1 - Union of the parishes of V. N. De Famalicão and Calendar | 45233120-6 | Road construction works | FALSE | 2015 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 23-07-2015 | 29-10-2018 | 1194 | 365 | 594170.24 | 456080.31 | 2 | 448283.9 | 7796.41 | 101.7392 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical value of the proposal: 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspended for a period of 120 days. | decrease in the total value of the project due to price revisions.
3690 | 1499072 | Enlargement and Improvement of streetOuteiro da Bandeira, in the parish of Avanca, in the municipality of Estarreja | 45233142-6 | Road-repair works | FALSE | 2014 | 2018 | Portugal | Estarreja | Aveiro | 1 | 66 | 10-07-2015 | 20-11-2018 | 1229 | 365 | 401992.7 | 238740 | 1 | 231747.97 | 6992.03 | 103.0171 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Global Proposal Price - 80% Quality and Technical Merit of the Proposal - 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | price review
3691 | 1495844 | Edgar Cardoso Bridge in Figueira da Foz - rehabilitation and structural reinforcement of the base of the towers | 45221119-9 | Bridge renewal construction work | FALSE | 2015 | 2019 | Portugal | Coimbra | Coimbra | 6 | 36 | 24-06-2015 | 18-07-2019 | 1485 | 180 | 500000 | 336489.22 | 2 | 321844.49 | 14644.73 | 104.5503 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | relevant extension of the execution period, due to delay by the administration of the port of figueira da foz in issuing the approval of the maritime signaling, due to difficulties in obtaining the concrete composition to be used in reinforcing the cylinders and due to yields much lower than those initially estimated, in view of the specificity of the project and very demanding execution conditions | failure to carry out 1 of the 2 planned mappings; reduction of gap sealing amounts and opening of holes for anchoring reinforcements
3692 | 1495068 | Connection of the en234 to the en16 - complementary works | 45233142-6 | Road-repair works | FALSE | 2015 | 2019 | Portugal | Mangualde | Viseu | 20 | 27 | 24-06-2015 | 19-07-2019 | 1486 | 60 | 300000 | 194324.81 | 1 | 180326.08 | 13998.73 | 107.763 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the contract only had an additional negative value, quantities determined after completion of the project.
3693 | 1494268 | CONSTRUCTION CONTRACT NUMBER 1/DMPO/DCMIVP/DS/15 – “REHABILITATION OF streets AND SANITATION INFRASTRUCTURES - SOUTH ZONE OF LISBON” (Process No. 13/CP/DEPS/N.D./2015) | 45232451-8 | Drainage and surface works | FALSE | 2015 | 2019 | Portugal | Lisboa | Lisboa | 11 | 20 | 02-07-2015 | 24-07-2019 | 1483 | 730 | 4000000 | 2800000.01 | 3 | 2799666.54 | 333.47 | 100.0119 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Refer to point 14 of the Program of Procedure | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3694 | 1493397 | It consists of the demolition of PER buildings and other annexed structures, as well as the execution of cleaning and demolitions in municipal spaces, in the municipality of Amadora | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2015 | 2018 | Portugal | Amadora | Lisboa | 11 | 21 | 29-06-2015 | 13-03-2018 | 988 | 120 | 204250 | 163401 | 1 | 163401 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The evaluation model is the one indicated in the follow: PF = 0.50 * Pi + 0.50 * VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i - Evaluation of Factors and Subfactors: - Factor "Price" The score will be from 0 to 100, and the values ​​will be calculated as follows: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. - Factor "Technical Value" Technical Valuation is evaluated according to the following subfactor: - Descriptive Memory Detail: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: - Very well-prepared Descriptive Memory, with a detailed description of the work to be carried out, focusing on important aspects, making possible a great ease of interpretation. The Descriptive Memory reveals a careful and profound analysis of the work to be perform - MDi = 100 - Descriptive Memory prepared with details of the work to be carried out, focusing on important aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the work to be carried out - MDi = 65 - Descriptive Memory with reference to the work carried out, focusing on general aspects, referring to some human resources and equipment affections although without great detail. The Descriptive Memory reveals little care in the analysis of the work to be carried out - MDi = 30 - Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any aspect of great interest - MDi = 0 The formula to be applied will be: VTi = MDi On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the detail in the Descriptive Memory of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: - An advantage will be given to the proposal with the best classification in the Price factor. - In the event of a tie, the proposal submitted first will win. | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unforeseen delay in vacating buildings to be demolished
3695 | 1491862 | En4, km 20+000, embankment stabilization | 45233142-6 | Road-repair works | FALSE | 2015 | 2018 | Portugal | Alcochete | Setúbal | 17 | 26 | 24-06-2015 | 09-01-2018 | 930 | 180 | 475000 | 348073.86 | 2 | 337124.49 | 10949.37 | 103.2479 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | resulting from the preparation of bill of quantities
3696 | 1487558 | EN6 - seaside road reinforcement of the maritime protection of the section adjacent to the santana hospital, on the wall | 45233140-2 | Roadworks | FALSE | 2015 | 2019 | Portugal | Cascais | Lisboa | 11 | 25 | 22-06-2015 | 04-11-2019 | 1596 | 120 | 850000 | 808499.05 | 2 | 664901.57 | 143597.48 | 121.5968 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | associated with bill of quantities
3697 | 1481503 | Resurfacing of EM 605-1 - street of Casarão, Portela do Sol, Cova da Areia and Flores - Parish of Aguada de Cima and Union of Parishes of Águeda and Borralha; Belazaima do Chão, Castanheira do Vouga | 45233141-9 | Road-maintenance works | FALSE | 2015 | 2020 | Portugal | Águeda | Aveiro | 1 | 30 | 08-06-2015 | 11-02-2020 | 1709 | 60 | 348081 | 259892.5 | 2 | 304537.56 | -44645.06 | 85.34 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to work suspensions. | due to more work
3698 | 1476181 | Vertical signage 2015 – lot iii | 45233294-6 | Installation of road signals | FALSE | 2014 | 2019 | Portugal | Guarda | Coimbra | 6 | 49 | 29-05-2015 | 27-11-2019 | 1643 | 365 | 6000000 | 967277.85 | 2 | 935562.35 | 31715.5 | 103.39 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | the area of ​​the side panels was increased at the expense of another vertical code signaling, namely in the ip3 and ic6
3699 | 1475779 | Vertical Signage 2015 – Lot IV | 45233294-6 | Installation of road signals | FALSE | 2014 | 2019 | Portugal | Leiria | Santarém | 16 | 49 | 29-05-2015 | 29-03-2019 | 1400 | 365 | 6000000 | 924247.41 | 2 | 897595.47 | 26651.94 | 102.9693 | lowest price | 2 | 100 | N/A | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adaptation of the execution project | adaptation of the execution project
3700 | 1455841 | BAIXA WATER SUPPLY NETWORK - 3rd PHASE - (Airães System - Various Parishes) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2014 | 2018 | Portugal | Felgueiras | Porto | 13 | 24 | 15-05-2015 | 12-10-2018 | 1246 | 180 | 450874.44 | 313594.43 | 2 | 283897.13 | 29697.3 | 110.4606 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value - 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were some deadline extensions. | smaller quantities executed.
3701 | 1451194 | Occasional rehabilitation of pipelines in various locations in Coimbra and the supply pipeline to the HUC | 45000000-7 | Construction work | FALSE | 2014 | 2018 | Portugal | Coimbra | Coimbra | 6 | 24 | 29-04-2015 | 28-06-2018 | 1156 | 240 | 420000 | 390190.87 | 2 | 347825.27 | 42365.6 | 112.1801 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | suspension and deadline extension | underwork has taken place
3702 | 1450726 | Baixa Water Supply Network - 3rd Phase - (Margaride System (Lagares, Margaride, Pombeiro, Varziela, Refontoura)) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2014 | 2019 | Portugal | Felgueiras | Porto | 13 | 24 | 07-05-2015 | 24-07-2019 | 1539 | 180 | 337433.11 | 210730.58 | 1 | 207755.58 | 2975 | 101.432 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Value - 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | some adverse situations during the execution of the project | smaller quantities executed
3703 | 1442525 | Conservation of the Municipal Road Network | 45233200-1 | Various surface works | FALSE | 2015 | 2018 | Portugal | Mangualde | Viseu | 20 | 12 | 27-04-2015 | 22-06-2018 | 1152 | 90 | 189503.5 | 170553.16 | 1 | 155848.96 | 14704.2 | 109.4349 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | according to process | according to final account
3704 | 1442246 | Requalification of streetDr. José pires padinha – tavira | 45112700-2, 45315600-4 | Landscaping work, Low-voltage installation work | FALSE | 2014 | 2019 | Portugal | Tavira | Faro | 8 | 36 | 27-04-2015 | 23-01-2019 | 1367 | 180 | 587602.99 | 417580.3 | 2 | 397742.02 | 19838.28 | 104.9877 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | - extension of 42 days due to the approval of the pss on 21/09/2015 and communication of the approval of the pss to the contractor on 22/09/2015; - extension of 87 days due to bad weather; rise in the water table; excess of existing infrastructures, many of which are not registered and the need to adapt the project to existing conditions; approved by order of mr. chairman of 02/04/2016, setting the completion of the projects for 15/06/2016; - extension of 30 days due to the excess of existing infrastructures, many of which are not registered and the need to adapt the project to existing conditions; approved by order of mr. chairman of 06/16/2016, setting the completion of the projects for 07/15/2016; - delivery of the technical compilation. | underwork in the amount of -17,773.10€ and definitive price revision in the amount of -2,065.18€ (negative).
3705 | 1435987 | Carrying out the “Construction of the Águeda Arts Center” contract, as described in the Tender Specifications | 45212320-5 | Construction work for buildings relating to artistic performances | FALSE | 2014 | 2021 | Portugal | Águeda | Aveiro | 1 | 48 | 16-04-2015 | 12-08-2021 | 2310 | 730 | 5293784.73 | 3980432.54 | 3 | 4542040.52 | -561607.98 | 87.6353 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the contractual term | changes in the value of the project were caused by the need to perform some more work and work to supply errors and omissions
3706 | 1419039 | construction work number 4/dmpo/dcmivp/ds/2013 – “conservation and maintenance of the public sanitation network in the eastern area of the city of lisbon” (process no. 38/cp/deps/n.d./2013) | 45232460-4 | Sanitary works | FALSE | 2013 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 24-03-2015 | 06-04-2018 | 1109 | 365 | 744965.17 | 414208.2 | 2 | 412187.96 | 2020.24 | 100.4901 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
3707 | 1407521 | En114-2, km 0+325, bridge over Ribeira de Freiria. Replacement | 45221100-3 | Construction work for bridges | FALSE | 2014 | 2019 | Portugal | Santarém | Santarém | 16 | 32 | 09-03-2015 | 29-03-2019 | 1481 | 270 | 750000 | 642852.56 | 2 | 604335.85 | 38516.71 | 106.3734 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | the reasons were fundamentally the time elapsed, necessary for the approval of the project of the prefabricated parts and their manufacturing process. | less unnecessary work to perform in the contract to complete the project.
3708 | 1399815 | Tondela Ring Road - Access E.R. 230- High tassel- ip3- 3rd phase | 45233122-0 | Ring road construction work | FALSE | 2014 | 2021 | Portugal | Tondela | Viseu | 20 | 11 | 05-03-2015 | 28-01-2021 | 2156 | 150 | 1202830.19 | 949800 | 2 | 910806.59 | 38993.41 | 104.2812 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the stipulated time frame. | existence of underworks
3709 | 1374520 | Execution of the primary network, execution of mosaics of fuel management plots, improvement of the road network, improvement of two water points and the construction of two water points. | 90000000-7 | Sewage-, refuse-, cleaning-, and environmental services | FALSE | 2014 | 2021 | Portugal | Moimenta da Beira | Viseu | 20 | 20 | 05-02-2015 | 02-11-2021 | 2462 | 150 | 870332.66 | 737874 | 2 | 584862.5 | 153011.5 | 126.162 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the deadline for the execution of the project is due to the fact of better quality in the execution/completion of the project.
3710 | 1358443 | Synthetic grassing of Campo Municipal Dr. Camilo Sobrinho, Construction of Changing Rooms and Covering the Bench | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2020 | Portugal | Torre de Moncorvo | Bragança | 4 | 11 | 05-01-2015 | 08-06-2020 | 1981 | 180 | 409000 | 312006.72 | 2 | 312006.72 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project ended earlier than expected.
3711 | 1343681 | Expansion and Reinforcement of the Municipality's Water Supply - Remodeling of the Water Supply Network to Vila da Marmeleria | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2018 | Portugal | Rio Maior | Santarém | 16 | 9 | 26-12-2014 | 12-01-2018 | 1113 | 120 | 369344.83 | 321842.45 | 2 | 311230.78 | 10611.67 | 103.4096 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in starting work | negative price revision and underwork
3712 | 1338823 | Contract to Improve the Road Access to the New Basic Education School in the Parish of Santa Bárbara | 45233200-1 | Various surface works | FALSE | 2014 | 2019 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 17-12-2014 | 19-02-2019 | 1525 | 150 | 444127 | 403700 | 2 | 316523.87 | 87176.13 | 127.5417 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | undefined exact location of existing electrical networks. | job suppression
3713 | 1333810 | Refurbishment of the water and sewage network | 45232460-4 | Sanitary works | FALSE | 2014 | 2018 | Portugal | Tondela | Viseu | 20 | 11 | 29-12-2014 | 09-11-2018 | 1411 | 180 | 1179245.28 | 943396.23 | 2 | 84350.7 | 859045.53 | 1118.4213 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the constants in the resolution of the board meeting in minutes no. 23 of october 13, 2015 | the constants in the resolution of the board meeting in minutes no. 23 of october 13, 2015
3714 | 1316401 | execution of the public works contract named aa 2231 – contract for implementing the emergency capture of rabagão – equipment, within the scope of the multimunicipal system of water supply | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2020 | Portugal | Vieira do Minho | Braga | 3 | 68 | 05-06-2014 | 08-07-2020 | 2225 | 90 | 249000 | 218942.61 | 1 | 187072.89 | 31869.72 | 117.036 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | no indication | underwork
3715 | 1316381 | execution of the public works contract named aa 2230 – contract for execution of the emergency capturing in rabagão – civil construction, within the scope of the multimunicipal water supply system | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2020 | Portugal | Vieira do Minho | Braga | 3 | 68 | 04-06-2014 | 08-07-2020 | 2226 | 90 | 238000 | 198291.97 | 1 | 194727.71 | 3564.26 | 101.8304 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | no indication
3716 | 1310782 | Conservation of the Hermitage of S. Roque | 45112700-2, 45453100-8 | Landscaping work, Refurbishment work | FALSE | 2014 | 2019 | Portugal | Tavira | Faro | 8 | 30 | 21-11-2014 | 12-02-2019 | 1544 | 360 | 231558.91 | 223511.39 | 1 | 235345.33 | -11833.94 | 94.9717 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | extensions associated with additional work and suspension of work | additional work and price revision
3717 | 1285555 | Center for Traditional Arts and Crafts/Casa do Risco - Construction/ Improvement | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2014 | 2018 | Portugal | Felgueiras | Porto | 13 | 24 | 29-10-2014 | 08-10-2018 | 1440 | 300 | 456610.6 | 416931.46 | 2 | 416931.46 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | had a deadline extension
3718 | 1282212 | Rehabilitation of the Feijó Reservoirs | 45247270-3 | Reservoir construction works | FALSE | 2013 | 2019 | Portugal | Almada | Setúbal | 17 | 60 | 20-10-2014 | 04-11-2019 | 1841 | 120 | 400000 | 259936.12 | 2 | 335618.43 | -75682.31 | 77.4499 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | the present contract presented several situations that strongly conditioned the progress of the project. we highlight the need to change the project inherent to the characteristics of the slabs covering the supported reservoirs, which are quite different from what was recommended in the project and which led to a stoppage of work for a substantial period. differences were also found between the designer and the contractor with regard to the execution of interior lining work on the supported reservoirs, which led to a decision being taken by the owner of the project. there were work stoppages associated with the need to guarantee the water supply to the populations. | the need to change the project inherent to the characteristics of the slabs covering the supported reservoirs, quite different from what was recommended in the project and which led to a stoppage of work for a substantial period. work was also carried out to repair the concrete walls of the elevated reservoir that presented pathologies associated with corrosion of reinforcements. the extension of the term led to the payment of financial rebalancing in compensation for the extension of the shipyard. a claim was filed against the project account duly validated by the client of the project.
3719 | 1245633 | Contract for the requalification of the section of Ribeira de Santana | 45112700-2 | Landscaping work | FALSE | 2012 | 2019 | Portugal | Ourique | Beja | 2 | 30 | 26-06-2012 | 26-07-2019 | 2586 | 180 | 202000 | 198162.63 | 1 | 208613.33 | -10450.7 | 94.9904 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | grounds for the 1st extension - necessary alterations in the project due to doubts in the implementation of the project derived from errors in the topographical survey, only detected with the implementation of the project on site. reasons for the 2nd extension - adverse weather conditions that conditioned the normal development of the project. | price review
3720 | 1228763 | Current conservation by contract 2013 - 2016 - district of évora | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2019 | Portugal | Évora | Évora | 7 | 47 | 08-09-2014 | 26-12-2019 | 1935 | 1095 | 7200000 | 5625833.18 | 3 | 5659316.06 | -33482.88 | 99.4084 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the reasons were the continuity of road conservation activities in the time gap between the end of the contracts in force and the beginning of future contracts for the three-year period 2017-2020, based on the public interest, pursuant to paragraph a) of art. 312.º of the "public procurement code", from the date of expiry of the initial contract that occurred on 2017-09-30, transferring the expiry date of the contractual term to 2017-11-30 (legal extension of the period of 61 days), verifying the assumptions allowed by article 313 of the "public procurement code" for these objective modifications of the contract are followed, namely the provisions of paragraph 2 of that article. | the alteration in the value of the project was due to the calculation of additional works in the amount of €314,214.10, works to correct errors and omissions in the amount of €170,290.55, other objective modifications to the contract in the amount of €29,941.40, underwork in the amount of €371,346.77 and the final price revision in the amount of €-109,66.39.
3721 | 1190543 | 2013.157.01.C1 - SFP Portalegre - Renovation of the kitchen, dining room and bar | 45212500-1 | Kitchen or restaurant conversion | FALSE | 2013 | 2020 | Portugal | Portalegre | Portalegre | 12 | 21 | 27-11-2013 | 07-07-2020 | 2414 | 120 | 600000 | 580000 | 2 | 580000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | no data
3722 | 1175651 | Refurbishment of Casa Rural do Adro - Construction | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2014 | 2018 | Portugal | Felgueiras | Porto | 13 | 24 | 29-08-2014 | 03-10-2018 | 1496 | 120 | 203162.22 | 201549.83 | 1 | 201549.81 | 0.02 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some extensions of the deadline for execution of the project. | rounding
3723 | 1165376 | IP4 (A4) - MARÃO TUNNEL (Under design/construction regime) | 45221241-3 | Road tunnel construction work | FALSE | 2014 | 2018 | Portugal | Amarante | Vila Real | 19 | 75 | 14-08-2014 | 06-08-2018 | 1453 | 518 | 110000000 | 88099873.47 | 3 | 88099873.47 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A
3724 | 1144226 | Current conservation by contract 2013 - 2016 - district of faro | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2020 | Portugal | Faro | Faro | 8 | 48 | 01-04-2014 | 18-01-2020 | 2118 | 1095 | 5100000 | 4254342.38 | 3 | 4167713.44 | 86628.94 | 102.0786 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | the reason for extending the 133-day period was the continuation of the pursuit of the public interest underlying the contract, namely maintaining, without interruption, current conservation activities on the network covered by this contract. | calculation of €551,004.00 in additional work, €98,473.44 in other objective modifications to the contract, work to correct errors and negative omissions in the amount of €478,804.16 and underwork in the amount of €193,215.24
3725 | 1142223 | "Current conservation by contract 2013 - 2016 - district of setúbal". | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2019 | Portugal | Setúbal | Setúbal | 17 | 47 | 30-04-2014 | 21-06-2019 | 1878 | 1095 | 8650000 | 6443963.55 | 3 | 7583709.1 | -1139745.55 | 84.9711 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | bill of quantities results | bill of quantities results
3726 | 1142090 | Current conservation by contract 2013/2016 - district of lisbon | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2019 | Portugal | Lisboa | Lisboa | 11 | 46 | 30-04-2014 | 21-06-2019 | 1878 | 1095 | 7700000 | 5840000 | 3 | 6794750.27 | -954750.27 | 85.9487 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | bill of quantities results | bill of quantities results
3727 | 1124119 | Continuing contract for sidewalk paving - year 2013/2014 | 45233200-1 | Various surface works | FALSE | 2014 | 2019 | Portugal | Viseu | Viseu | 20 | 24 | 10-07-2014 | 03-07-2019 | 1819 | 735 | 450000 | 331300 | 2 | 128262.27 | 203037.73 | 258.2989 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | no change | underwork
3728 | 1112978 | construction work number 3/dmpo/dcmivp/ds/13– “conservation and maintenance of the public sanitation network in the center and historical center areas of the city of lisbon” (process no. 36/cp/deps/n.d./2013) | 45232460-4 | Sanitary works | FALSE | 2013 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-06-2014 | 12-06-2018 | 1453 | 365 | 745004.8 | 431605.7 | 2 | 431605.7 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A
3729 | 1101105 | Construction of the connection between Avenida Sá Carneiro and E.N. 227 | 45233120-6 | Road construction works | FALSE | 2013 | 2018 | Portugal | São Pedro do Sul | Viseu | 20 | 24 | 20-06-2014 | 23-11-2018 | 1617 | 180 | 470000 | 339875.98 | 2 | 320019.52 | 19856.46 | 106.2048 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | in addition to the suspensions referred to above, there were two inspection notices for provisional acceptance with defects and one partial provisional acceptance. | underwork referred to above as well as price revision in favor of the municipality.
3730 | 1074495 | En10 - Sacavém bridge over the trancão river - replacement of the bridge | 45221100-3 | Construction work for bridges | FALSE | 2012 | 2019 | Portugal | Loures | Lisboa | 11 | 90 | 24-04-2014 | 21-06-2019 | 1884 | 365 | 3400000 | 2549067 | 3 | 2826729.79 | -277662.79 | 90.1772 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bill of quantities results | bill of quantities results
3731 | 1058783 | Current conservation by contract 2013 - 2016 beja district | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2019 | Portugal | Beja | Beja | 2 | 48 | 24-04-2014 | 30-12-2019 | 2076 | 1095 | 10650000 | 8305648.49 | 3 | 9490489.03 | -1184840.54 | 87.5155 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the reason for extending the 122-day period was the continuation of the pursuit of the public interest underlying the contract, namely to maintain without interruption the current conservation activities on the network covered by this contract | the change in the value of the project was due to the determination of more works in the amount of €826,910.79, of omoc (art. errors and omissions correction in the amount of €484,550.69, underwork in the amount of €109,864.78 and negative errors and omissions in the amount of €223,749.75
3732 | 1044760 | Contract number 1/dmau/dhu/2013 – “refurbishment of building a and construction of infrastructure in the municipal complex of marvila - financing of piparu” process n.º30/cp/deps/n.d./2013) | 50000000-5, 71000000-8, 45200000-9, 71500000-3, 45310000-3, 45442000-7 | Repair and maintenance services, Architectural, construction, engineering and inspection services, Works for complete or part construction and civil engineering work, Construction-related services, Electrical installation work, Application work of protective coatings | FALSE | 2013 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 15-04-2014 | 22-11-2018 | 1682 | 270 | 802830.19 | 698564.04 | 2 | 831647.83 | -133083.79 | 83.9976 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A
3733 | 980400 | Rehabilitation of the Luso Municipal Football Field | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2013 | 2018 | Portugal | Mealhada | Aveiro | 1 | 30 | 12-02-2014 | 14-02-2018 | 1463 | 90 | 375000 | 297000 | 2 | 313294.66 | -16294.66 | 94.7989 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | modifications introduced to the project | modifications introduced to the project
3734 | 956127 | montelongo educational center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2021 | Portugal | Fafe | Braga | 3 | 30 | 27-12-2013 | 18-05-2021 | 2699 | 420 | 2912116.89 | 2460356.52 | 3 | 2457077.75 | 3278.77 | 100.1334 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | there were three extensions of the contract term | not all quantities were executed for some items
3735 | 906336 | En16, km 39+614 to km 56+900 - weathering improvement 2012-2013 | 45233142-6 | Road-repair works | FALSE | 2013 | 2019 | Portugal | Oliveira de Frades | Viseu | 20 | 24 | 30-09-2013 | 12-07-2019 | 2111 | 60 | 895000 | 639454.27 | 2 | 643907.97 | -4453.7 | 99.3083 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | extension due to adverse weather conditions | over and underwork
3736 | 886459 | Improvement and rectification of the connection path of CM1680-2 (place of Sangidos) passing through place of Azenha, including streetand crossstreet of Azenha - 1st Phase | 45233120-6 | Road construction works | FALSE | 2012 | 2019 | Portugal | Fafe | Braga | 3 | N/A | 01-11-2013 | 24-10-2019 | 2183 | 300 | 600977.05 | 477686.72 | 2 | 457320.98 | 20365.74 | 104.4533 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | not all the planned works were carried out.
3737 | 854651 | En3-2 reguengo bridge over the azambuja ditch at km4+260. Replacement of the artwork | 45221100-3 | Construction work for bridges | FALSE | 2013 | 2018 | Portugal | Cartaxo | Santarém | 16 | 31 | 16-09-2013 | 05-02-2018 | 1603 | 365 | 1300000 | 1024140.85 | 3 | 982815.32 | 41325.53 | 104.2048 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work for 167 days as a result of the flooding of the project area and the change in the medium voltage line. | execution of unforeseen access, complementary tests and adjustments of final quantities unnecessary for the completion of the project.
3738 | 835105 | 2013.158.02.C1 - SFP Évora - Drainage and water supply and paving networks - 2nd phase | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2019 | Portugal | Évora | Évora | 7 | 20 | 04-09-2013 | 18-11-2019 | 2266 | 80 | 295000 | 197966.13 | 1 | 134793.35 | 63172.78 | 146.8664 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | works not performed
3739 | 817543 | A21 mafra/malveira subsection - dismantling of the pine tree sale toll plaza | 45111100-9 | Demolition work | FALSE | 2013 | 2019 | Portugal | Mafra | Lisboa | 11 | 20 | 18-07-2013 | 01-07-2019 | 2174 | 45 | 398000 | 394544.92 | 2 | 466258.19 | -71713.27 | 84.6194 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bill of quantities results | bill of quantities results
3740 | 803356 | Execution of infrastructures for the urbanization of an area in Torreira, where Social Housing will later be built | 45111290-7 | Primary works for services | FALSE | 2012 | 2019 | Portugal | Murtosa | Aveiro | 1 | 30 | 30-07-2013 | 06-02-2019 | 2017 | 540 | 744593.41 | 441268.22 | 2 | 393169.17 | 48099.05 | 112.2337 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a deadline extension | there were works not done
3741 | 788279 | Roundabout connecting E. N. 14 to E. M. 508/1 | 45233128-2 | Roundabout construction work | FALSE | 2013 | 2018 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 04-07-2013 | 21-11-2018 | 1966 | 365 | 515000 | 462452.53 | 2 | 459613.54 | 2838.99 | 100.6177 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | work suspended for a period of 420 days. | underwork amounting to €2,838.99 and the price review revealed a decrease of €9,363.17.
3742 | 784318 | construction contract number 41/dmpo/dcme/dpe/2012 - "improvement works for the kitchen at school 29 + ji de são josé - financing of piparu" (process no. 51/cp/deps/n.d./2012) | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 25-06-2013 | 22-11-2018 | 1976 | 180 | 324837 | 158092.98 | 1 | 158092.98 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
3743 | 781968 | execution of the public work contract "rehabilitation and expansion of a building for security forces", which consists of the interior remodeling of an existing building and the expansion of the built area | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2013 | 2017 | Portugal | Alandroal | Évora | 7 | 21 | 17-06-2013 | 29-11-2017 | 1626 | 365 | 719477.09 | 489526.39 | 2 | 500921.85 | -11395.46 | 97.7251 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 20 | N/A | N/A | N/A | N/A | N/A | N/A | delays fully attributable to the contractor. | due to the existence of: more work worth €41,382.38; errors and omissions works worth €5,746.48; underwork ordered by the developer in the amount of €32,176.80; and, work not carried out by the contractor in the amount of €3,556.60.
3744 | 768070 | Construction of the New G.N.R. | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2012 | 2018 | Portugal | Mangualde | Viseu | 20 | 24 | 28-05-2013 | 27-03-2018 | 1764 | 720 | 2076930 | 1628811.71 | 3 | 1474411.36 | 154400.35 | 110.472 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
3745 | 759772 | En374-2, km 1+500 - landfill rehabilitation | 45233142-6 | Road-repair works | FALSE | 2012 | 2019 | Portugal | Loures | Lisboa | 11 | 23 | 08-05-2013 | 03-12-2019 | 2400 | 150 | 225000 | 150522.08 | 1 | 149532.62 | 989.46 | 100.6617 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | bill of quantities results
3746 | 742798 | Requalification of the streets of Portela -Arões S.Romão | 45233252-0 | Surface work for streets | FALSE | 2012 | 2020 | Portugal | Fafe | Braga | 3 | 30 | 26-03-2013 | 05-03-2020 | 2536 | 180 | 511206.66 | 413754.34 | 2 | 411464.28 | 2290.06 | 100.5566 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | not all work has been carried out
3747 | 738017 | Requalification of Praça das Comunidades (Weekly Fair) | 45211360-0 | Urban development construction work | FALSE | 2012 | 2018 | Portugal | Fafe | Braga | 3 | 20 | 26-03-2013 | 06-02-2018 | 1778 | 180 | 1270425.57 | 954895.12 | 2 | 946806.03 | 8089.09 | 100.8544 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a suspension of work | all the projects were not carried out
3748 | 737743 | Reconversion and expansion of a building for the future installations of the territorial detachment of the National Guard of Fafe | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2012 | 2018 | Portugal | Fafe | Braga | 3 | 30 | 15-03-2013 | 12-04-2018 | 1854 | 365 | 2063191.69 | 1741457.9 | 3 | 1738110.06 | 3347.84 | 100.1926 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a suspension of work | there were no changes to the value of the project
3749 | 922458 | The green park includes a maintenance circuit, pedestrian routes, meeting and accommodation points, a bike path, parking lots and planted areas. | 45112711-2 | Landscaping work for parks | FALSE | 2011 | 2019 | Portugal | Tavira | Faro | 8 | 90 | 13-03-2013 | 18-02-2019 | 2168 | 270 | 804660.46 | 544526.22 | 2 | 540051.97 | 4474.25 | 100.8285 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delivery of documents and correction of pathologies. | underwork and price revision.
3750 | 661207 | Remodeling of the Cleaning Station on Av. general mowing | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2012 | 2018 | Portugal | Lisboa | Lisboa | 11 | 21 | 27-12-2012 | 16-11-2018 | 2150 | 180 | 375487 | 320000 | 2 | 333979.59 | -13979.59 | 95.8142 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
3751 | 602049 | Ribeiro da Quinta das Freiras Detour - Caniço | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2018 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 22 | 26-09-2011 | 13-12-2018 | 2635 | 90 | 1020776 | 646440 | 2 | 646314.81 | 125.19 | 100.0194 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes | there were no changes
3752 | 396006 | Regularization and Canalization of Ribeiro da Capela - Curral das Freiras | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2019 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 21 | 31-08-2012 | 27-02-2019 | 2371 | 540 | 1200000 | 845039.9 | 2 | 740211.65 | 104828.25 | 114.1619 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3753 | 372239 | Reconstruction of PH and Channeling Walls in Ribeiro Arriving at Vereda das Lajes - Imaculado Coração de Maria. | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2018 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 22 | 31-08-2012 | 20-04-2018 | 2058 | 120 | 227500 | 159250.01 | 1 | 159147.87 | 102.14 | 100.0642 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3754 | 325698 | Rehabilitation and Regularization of the Ribeira de João Gomes - Construction of the A1 to A4 dams. | 45247220-8 | Weir construction work | FALSE | 2011 | 2019 | Portugal | Machico | Região Autónoma da Madeira | 14 | 43 | 26-06-2012 | 28-01-2019 | 2407 | 540 | 3350000 | 2747146.09 | 3 | 2737925.41 | 9220.68 | 100.3368 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3755 | 344472 | Regularization and Canalization of Ribeiro da Carne Azeda downstream of streetDr. Angelo Augusto da Silva - Funchal | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2019 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 27 | 20-06-2012 | 11-11-2019 | 2700 | 360 | 600100 | 360060.5 | 2 | 357219.06 | 2841.44 | 100.7954 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3756 | 328859 | Detour from Ribeiro de São Filipe to Ribeiro da Nora - Funchal | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2018 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 22 | 17-10-2011 | 10-03-2018 | 2336 | 90 | 299750 | 205500 | 1 | 202027.52 | 3472.48 | 101.7188 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | difference between planned and executed quantities
3757 | 330839 | Reconstruction of the bridge and access to Fajã da Ribeira in Ribeira Brava | 45221110-6 | Bridge construction work | FALSE | 2011 | 2021 | Portugal | Ribeira Brava | Região Autónoma da Madeira | 14 | 23 | 17-10-2011 | 16-02-2021 | 3410 | 240 | 720000 | 648000.01 | 2 | 649593.37 | -1593.36 | 99.7547 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities and the ordinary revision of prices.
3758 | 275700 | Contract No. 128/2011, of July 27, 2011 | 45111230-9 | Ground-stabilisation work | FALSE | 2011 | 2018 | Portugal | Loulé | Faro | 8 | 30 | 27-07-2011 | 14-06-2018 | 2514 | 180 | 357617.5 | 229486.88 | 1 | 228917.54 | 569.34 | 100.2487 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the successful tenderer claimed the restructuring of the company and the actual income from the project. | underwork.
3759 | 297819 | Bypass to the Center of Caniço - Complementary Works | 45243510-0 | Embankment works | FALSE | 2011 | 2018 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 42 | 02-08-2011 | 28-11-2018 | 2675 | 120 | 1575000 | 1497650 | 3 | 862513.64 | 635136.36 | 173.6378 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | suspension | agreement for the completion of the project
3760 | 287780 | slope stabilization | 45220000-5 | Engineering works and construction works | FALSE | 2011 | 2019 | Portugal | Ribeira Brava | Região Autónoma da Madeira | 14 | 21 | 28-07-2011 | 03-10-2019 | 2989 | 150 | 700000 | 515000 | 2 | 514688.3 | 311.7 | 100.0606 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3761 | 265337 | Reconstruction of the Bridge next to the Church of Ribeira Brava | 45221110-6 | Bridge construction work | FALSE | 2011 | 2021 | Portugal | Ribeira Brava | Região Autónoma da Madeira | 14 | 21 | 16-06-2011 | 26-11-2021 | 3816 | 180 | 380000 | 248999.99 | 1 | 248947.61 | 52.38 | 100.021 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
3762 | 191865 | Construction of a building for the Police police station, as well as the execution of the respective exterior arrangements. | 45216111-5 | Police station construction work | FALSE | 2010 | 2018 | Portugal | Vila Nova de Gaia | Porto | 13 | 42 | 26-05-2011 | 23-01-2018 | 2434 | 365 | 987426.77 | 834720.77 | 2 | 856322.74 | -21601.97 | 97.4774 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions to the deadline for carrying out the project were duly approved. | two additions to the contract were duly approved, the existence of underwork and a final price review.
3763 | 246456 | Execution of the Interpretation Route Along the Left Bank of the Sabugal Reservoir | 45112000-5 | Excavating and earthmoving work | FALSE | 2010 | 2020 | Portugal | Sabugal | Guarda | 9 | 15 | 08-04-2011 | 22-07-2020 | 3393 | 365 | 323603.65 | 137201.32 | 1 | 171718.76 | -34517.44 | 79.8989 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension and suspension of the deadline. | contract modifications: supply of errors and omissions and underwork
3764 | 134910 | Current conservation by contract - 2010/2013. Centro Sul Operational Center - District of Santarém. | 45233140-2 | Roadworks | FALSE | 2010 | 2018 | Portugal | Santarém | Santarém | 16 | 48 | 04-08-2010 | 02-07-2018 | 2889 | 1092 | 18500000 | 11953291.43 | 3 | 12166791.83 | -213500.4 | 98.2452 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the need for continuity from this current conservation contract to the next one, which was delayed at tender level, led to the deadline changes. | changes to the final value of the project were due to: a) work not carried out due to the verification of its unnecessaryness during the term of the contract; b) the projects that resulted from an objective modification of the contract, namely the legal extension of the contract; c) works that resulted from activities foreseen in the project, but that it was not required that they had been detected in the contract formation phase, because due to the nature of this contract, the quantities are estimated,
3765 | 79194 | Maintenance of municipal accessibility | 45233251-3 | Resurfacing works | FALSE | N/A | 2020 | Portugal | Alenquer | Lisboa | 11 | N/A | 23-07-2009 | 30-04-2020 | 3934 | 540 | N/A | 4198954.54 | 3 | 4174220.03 | 24734.51 | 100.5926 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the arguments for the change in the execution period are: lower yields caused by infrastructure, not covered. | vat increased from 5% to 6% but there were no changes in the value of the project.
3766 | 6580000 | Cp 20/2016 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Vizela | Braga | 3 | 20 | 12-08-2016 | 26-05-2017 | 287 | 540 | 260000 | 203914.66 | 1 | 203888.53 | 26.13 | 100.0128 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | underwork | underwork
3767 | 4866293 | EB 2322 - Construction of wastewater drainage networks for the parishes of Canedo and Corgo - Celorico de Basto | 45232460-4 | Sanitary works | FALSE | 2014 | 2017 | Portugal | Celorico de Basto | Braga | 3 | 41 | 03-06-2015 | 02-10-2017 | 852 | 180 | 1700000 | 1032116.44 | 3 | 1031858.78 | 257.66 | 100.025 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | underwork
3768 | 4846460 | Contract for the Refurbishment of Building 18 at Parque da Saúde in Lisbon | 45453000-7 | Overhaul and refurbishment work | FALSE | 2014 | 2017 | Portugal | Lisboa | Lisboa | 11 | 20 | 11-09-2015 | 02-02-2017 | 510 | 233 | 825000 | 586089.67 | 2 | 583501.08 | 2588.59 | 100.4436 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Those indicated in the parts of the procedure | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | derived from the suppression of some planned works
3769 | 4696675 | Development of teaching infrastructure - setúbal (eb1/ji dos arcos; eb1/ji monte belo; eb1 Fonte do Lavra; eb1 pinheirinhos and eb1/ji s. Gabriel | 45453100-8 | Refurbishment work | FALSE | 2016 | 2017 | Portugal | Setúbal | Setúbal | 17 | 30 | 18-11-2016 | 25-09-2017 | 311 | 180 | 262202.45 | 251659.36 | 2 | 251659.36 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline changes | no value change
3770 | 4288690 | Execution of the contract for the construction of a water main between Poejo and Roseira, to reinforce the water supply system for Reservoirs 7R1; 5R1 and 5R2, located in the parish of Ribeirinha, municipality of Angra do Heroímo | 45000000-7 | Construction work | FALSE | 2016 | 2017 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 22 | 18-07-2016 | 19-12-2017 | 519 | 90 | 470000 | 456730.05 | 2 | 455548.04 | 1182.01 | 100.2595 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - the project was suspended on 27-10-2016 and resumed on 17-05-2017, at the request of the owner of the project, due to the refusal of approved by the court of auditors. - the execution period was extended by another 60 days (from 90 days to 150 days); - there were 2 graceful extensions of the lead time: 21 days + 28 days. | underwork worth €1,182.01.
3771 | 4239799 | Contract for the Construction of Road Access to the New Hospital in Vila Franca de Xira | 45221121-6 | Road viaduct construction work | FALSE | 2011 | 2017 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 24-02-2012 | 10-01-2017 | 1782 | 270 | 3400000 | 2993313.73 | 3 | 2952412.93 | 40900.8 | 101.3853 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | approval of deviations from the project plan, extensions. | approval of underwork and approval of price review
3772 | 4188001 | Environmental Requalification of Amoreira da Gândara Park | 45112711-2 | Landscaping work for parks | FALSE | 2016 | 2017 | Portugal | Anadia | Aveiro | 1 | 20 | 11-05-2016 | 03-05-2017 | 357 | 120 | 204481.71 | 188866.17 | 1 | 187919.85 | 946.32 | 100.5036 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | it was considered adequate not to carry out the pavements foreseen in r. 24 de abril, as that street needs more repairs
3773 | 4182569 | Urban Requalification of the Area Surrounding the Municipal Library of Anadia | 45112700-2 | Landscaping work | FALSE | 2016 | 2017 | Portugal | Anadia | Aveiro | 1 | 20 | 30-11-2016 | 28-12-2017 | 393 | 150 | 396702.6 | 338000.26 | 2 | 338000.26 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a suspension and an extension of the period of execution of the project
3774 | 3950225 | Public works contract for the execution of Branches of the SBPP Stations (Shared Public Bicycle System) | 45311000-0 | Electrical wiring and fitting work | FALSE | 2017 | 2017 | Portugal | Lisboa | Lisboa | 11 | 26 | 30-03-2017 | 23-05-2017 | 54 | 730 | 450000 | 450000 | 2 | 58168.17 | 391831.83 | 773.619 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | change in the execution period of the project is due to works not carried out | balance refers to work not performed
3775 | 3869481 | 2017.123.01.C1 - "SFP Seixal - New Welding Workshop Facilities | 45310000-3 | Electrical installation work | FALSE | 2017 | 2017 | Portugal | Seixal | Setúbal | 17 | 21 | 07-08-2017 | 22-12-2017 | 137 | 90 | 190000 | 154873.12 | 1 | 154873.12 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unknown
3776 | 3822296 | Improvement and conservation of roads in the municipality of Azambuja | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2017 | 2017 | Portugal | Azambuja | Lisboa | 11 | N/A | 25-10-2017 | 19-12-2017 | 55 | 90 | 301850 | 256572.51 | 2 | 256572.51 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor carried out the project within the timeframe given for its execution
3777 | 3790964 | Contract for the replacement of wooden sleepers by concrete sleepers and rails and construction of welded long bars at the Vila Nova da Baronia and Cuba stations (contract no. 5010017759) | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 02-10-2015 | 31-07-2017 | 668 | 90 | 400000 | 389432.3 | 2 | 388818.24 | 614.06 | 100.1579 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 65% 2. Technical Valuation - 15% 3. Safety Management System - 10% 4. Work Quality Control System - 5% 5. Environmental Management System - 5% | 1 | 65 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | errors and omissions supply work not included in the initial contract: €614.06
3778 | 3789941 | Contract to Replace Wooden Sleepers with Concrete Sleepers, Replacement of Defective Rails and Constitution of Long Welded Bars - Alcantarilha, Silves, Estômbar | 50225000-8 | Railway-track maintenance services | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 30-06-2015 | 05-06-2017 | 706 | 90 | 600000 | 549436.25 | 2 | 536019.99 | 13416.26 | 102.5029 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | errors and omissions supply work not included in the initial contract (art. 377 nº 1 "public procurement code"): -13,416.26 €
3779 | 3681349 | Procedure No. 133/DSUMC/2015 - Replacement of Roofs in the Building of the Territorial Command of the Republican National Guard in Aveiro | 45261200-6 | Roof-covering and roof-painting work | FALSE | 2016 | 2017 | Portugal | Aveiro | Aveiro | 1 | 6 | 02-01-2017 | 25-10-2017 | 296 | 120 | 291500 | 241353.22 | 1 | 241353.22 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there was a request for a deadline extension, requested on september 4, 2017, until september 29, 2017. the request was due to a delay in delivery to the site, by the supplier, of accessories for the water pipe with a diameter of 75mm. this diameter is not a normally used diameter, so there were several delays from placing your order to delivery to the site.
3780 | 3609969 | 5010014584 - Contract for "Linha do Sul - km 218,300 to 242,500 - Replacement of RNP-type fixings by NABLA-type fixings and Adjustment of Long Welded Bars". | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 15-01-2015 | 30-03-2017 | 805 | 120 | 300000 | 215072.43 | 1 | 210962.08 | 4110.35 | 101.9484 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A |  | errors and omissions supply work (art. 377 nº 1 "public procurement code"): - €4,110.35
3781 | 3588478 | Improvement of Roads in Various Locations Through Platform Adjustment and Bituminous Application | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Mogadouro | Bragança | 4 | 15 | 03-07-2017 | 04-11-2017 | 124 | 120 | 382265.9 | 278533.36 | 2 | 347533.46 | -69000.1 | 80.1458 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Refer to point 16 of the Program of Procedure. | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | quantities not provided for in the contract and necessary for the proper execution of the project
3782 | 3581293 | Exterior restoration of the Town Hall building in Póvoa de Lanhoso, essentially in terms of cleaning and general waterproofing of the façade and roof. | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2017 | 2017 | Portugal | Póvoa de Lanhoso | Braga | 3 | 24 | 08-08-2017 | 29-12-2017 | 143 | 120 | 330000 | 297000.01 | 2 | 285399.65 | 11600.36 | 104.0646 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical Quality - 50% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-existent. | non-execution of work foreseen in the project.
3783 | 3528171 | Repair and repaving work on the municipal road | 45233142-6 | Road-repair works | FALSE | 2017 | 2017 | Portugal | Portalegre | Portalegre | 12 | 20 | 07-07-2017 | 27-11-2017 | 143 | 60 | 324445 | 238422.3 | 1 | 238422.3 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension due to weather conditions
3784 | 3523014 | Refurbishment Works on the 2nd Floor of the ESEP HEADQUARTERS - Phase 3, 5B and 7 | 45262700-8 | Building alteration work | FALSE | 2017 | 2017 | Portugal | Porto | Porto | 13 | 25 | 21-06-2017 | 30-11-2017 | 162 | 90 | 175000 | 164647.75 | 1 | 187694.74 | -23046.99 | 87.721 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | as per amendments to the contract. | as per amendments to the contract.
3785 | 3521009 | Rehabilitation of the property located in the Urbanização do Parque Desportivo, Lot 38 for the installation of the Municipal Sports Complex. | 45212225-9 | Sports hall construction work | FALSE | 2017 | 2017 | Portugal | Lourinhã | Lisboa | 11 | 20 | 17-07-2017 | 11-12-2017 | 147 | 145 | 540392.94 | 486353.63 | 2 | 478482.47 | 7871.16 | 101.645 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price (PR) obeys the following formula: PR = 10+ [(Pb-Ppa)/(0.10 x Pb)] x 90 Where: PR = Price factor classification Pb = Tender base price Ppa = Proposal price in analysis - 60.00%; Deadline (PZ) obeys the following formula: PZ = 20+[(180-Ppz)/(0.20 x 180)] x 80 Where: PZ = Factor classification deadline 180 days = Deadline indicated in the Specifications Ppz = Deadline of the proposal under analysis - 40.00%; In case of equality of score, for tiebreakers, the proposal that obtains the best classification, cumulatively, in the factors Price and Deadline. - 0.00%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | according to technical information of registration no. 5389/2017, the projects referring to article 10.4 of the contract “rehabilitation of the property located in the urbanização do parque desportivo, lot 38 for the installation of the municipal sports complex” namely: art.10.4 (supply and installation of coverage equal to the existing one, in the damaged areas, including fixing work, and materials necessary for a good final finish) are not to be executed and will be removed from the contract.
3786 | 3490275 | Requalification of the Pavement in the Translar neighborhood | 45233252-0 | Surface work for streets | FALSE | 2017 | 2017 | Portugal | Chaves | Vila Real | 19 | 30 | 30-06-2017 | 16-10-2017 | 108 | 60 | 157000 | 152990 | 1 | 152990 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3787 | 3470770 | 5010017189 - Reinforcement and rehabilitation of the Infrastructures from the Zêzere 1st Bridge to PK 157.701 of the Beira Baixa Line | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 20-04-2015 | 20-04-2017 | 731 | 180 | 950000 | 849331.91 | 2 | 891559.02 | -42227.11 | 95.2637 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 55% 2. Technical Value - 25% 3. Safety Management System - 10% 4. Work Quality Management System - 5% 5. Environmental Management System - 5% | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the execution of the preparatory work to reinforce the p1 pillar, two reconnaissance wells were made, next to the pillar, to measure its foundation level. from this preparatory work, discrepancies were found between the foundation elevation of pillar p1 and that defined in the project, as well as the nature of the geological formations above this layer. from the above, it was necessary to suspend the project front for 46 days, due to the need to study changes to the project (days), pursuant to article 365, paragraph b) "public procurement code". as the activity is on the critical path, a legal extension was granted for the same duration as the suspension (46 d). | over and underwork, resulting from: discrepancies detected in the foundation extracts of pillar p1; quantities of grout in masonry. decrease in the cost of work: -6790.84€ referring to inspection hours.
3788 | 3466266 | Requalification of the elementary school of the 1st Cycle of Pinhel. | 45454100-5 | Restoration work | FALSE | 2017 | 2017 | Portugal | Pinhel | Guarda | 9 | N/A | 08-06-2017 | 11-12-2017 | 186 | 120 | 351951 | 268872.79 | 2 | 268872.79 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension
3789 | 3459889 | Construction of the provisional street layout and reformulation of the Alexandre Herculano square | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Barreiro | Setúbal | 17 | 20 | 07-04-2016 | 31-05-2017 | 419 | 120 | 450000 | 399462 | 2 | 436562.83 | -37100.83 | 91.5016 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Proposal price - 60% b) Quality of the proposal - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the removal of concrete poles from the lighting columns of the old barreirense stadium | existence of works with non-contractual price
3790 | 3447554 | Requalification and improvement of several streets in the Union of Parishes of Santa Catarina da Serra and Chaínça and Santa Eufémia and Boa Vista | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 20-06-2017 | 17-11-2017 | 150 | 120 | 187590 | 185453.5 | 1 | 181341 | 4112.5 | 102.2678 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork.
3791 | 3446979 | Taipas leisure park | 45112711-2 | Landscaping work for parks | FALSE | 2017 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 14-06-2017 | 21-12-2017 | 190 | 90 | 216926.28 | 179267.98 | 1 | 175876.28 | 3391.7 | 101.9285 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was only communicated on 06/26/2017. following the inspection notice for provisional acceptance (25/09/2017), the contractor had to correct defects in the project, so he was granted a period of 30 days. | existence of underwork due to the foreseen quantities not being used up.
3792 | 3440440 | Reprofiling of the road section between the EN 101 and the central area of ​​Vila de Ponte - Phase 2 | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 26-05-2017 | 24-11-2017 | 182 | 120 | 481842.01 | 359900 | 2 | 348289.88 | 11610.12 | 103.3335 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork due to the anticipated quantities not being used up.
3793 | 3434383 | Requalification of cm 1219, section that goes from the ic2, place of mount in hives, to the collective of the couple of the farm inmilagres | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 14-06-2017 | 30-10-2017 | 138 | 90 | 208875.2 | 194750 | 1 | 190086.2 | 4663.8 | 102.4535 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | underwork.
3794 | 3429344 | Refurbishment of street of Paz in Vale do Horto, Azoia | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 09-06-2017 | 04-10-2017 | 117 | 90 | 240257 | 200091.5 | 1 | 200091.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline.
3795 | 3428550 | Refurbishment of the Elementary School Building in Salto | 45453100-8 | Refurbishment work | FALSE | 2017 | 2017 | Portugal | Montalegre | Vila Real | 19 | 5 | 12-06-2017 | 17-07-2017 | 35 | 180 | 260733.08 | 234659.77 | 1 | 5760 | 228899.77 | 4073.9543 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Non-fulfilment of contract (Cancelled or declared void) | 5 | N/A | N/A | N/A | N/A | N/A | N/A |  | contract annulment
3796 | 3428045 | Rehabilitation of pavements on the municipal road of Porto da Areia - Castanheira do Ribatejo | 45233220-7 | Surface work for roads | FALSE | 2012 | 2017 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 20-02-2013 | 10-05-2017 | 1540 | 135 | 478300 | 369232 | 2 | 363087.39 | 6144.61 | 101.6923 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | diversion of deadlines to the date of completion of the project | approval of price revision in the amount of - €6,144.61
3797 | 3421683 | Requalification and improvement of several streets in the União das Freguesias de Marrazes e Barosa and Parceiros e Azoia | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 09-06-2017 | 02-11-2017 | 146 | 120 | 280456.85 | 274978.85 | 2 | 274978.85 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
3798 | 3417873 | Requalification of streetDr. Egas moniz, in cuba, through the execution of all the works detailed in the execution project and bill of quantities | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2017 | 2017 | Portugal | Cuba | Beja | 2 | 20 | 26-05-2017 | 06-11-2017 | 164 | 90 | 200000 | 194992.08 | 1 | 197419.31 | -2427.23 | 98.7705 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
3799 | 3415657 | Conservation and Improvement of streets in the Municipality of Almada - 5th Action 2016 | 45233142-6 | Road-repair works | FALSE | 2017 | 2017 | Portugal | Almada | Setúbal | 17 | 21 | 01-06-2017 | 16-10-2017 | 137 | 90 | 419905 | 314416.67 | 2 | 314376.67 | 40 | 100.0127 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3800 | 3414363 | Public Tender No. 1-SC/IPS/2017 - Contract for the Remodeling of Roofs at the Higher School of Education of the Polytechnic Institute of Setúbal | 45260000-7 | Roof works and other special trade construction works | FALSE | 2017 | 2017 | Portugal | Setúbal | Setúbal | 17 | 9 | 01-06-2017 | 19-12-2017 | 201 | 75 | 309000 | 182289.74 | 1 | 230096.49 | -47806.75 | 79.2232 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting) Technical value (30% weighting) Technical Valuable Subfactors Descriptive Memory (Md) - Weighting = 0.40 Work Plan (Pt) - Weighting = 0.30 Work Warranty Period (Pgo) - Weighting = 0.30 | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the modification resulting from the additional work will be, pursuant to paragraph 1 of article 315 of the "public procurement code", published on the basegov portal. | the additional works are awarded for the value of 47,806.78 euros, the modification resulting from the additional works will be, under the terms of paragraph 1 of article 315 of the "public procurement code", published on the basegov portal.
3801 | 3405105 | Requalification of streetFrei Joaquim das Neves, section between the chapel of Souto do Meio and the EN350, Parish of Caranguejeira | 45232451-8 | Drainage and surface works | FALSE | 2017 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 05-06-2017 | 06-10-2017 | 123 | 90 | 259765 | 259525.3 | 2 | 259525.3 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | auto de vitoria for issuing the provisional acceptance.
3802 | 3398663 | Refurbishment of the C.M.P. Employee Spas, at the Carvalhido Workshops (EM.004.2017.021) | 45453100-8 | Refurbishment work | FALSE | 2017 | 2017 | Portugal | Porto | Porto | 13 | 20 | 29-05-2017 | 20-12-2017 | 205 | 90 | 213000 | 178522.21 | 1 | 184516.14 | -5993.93 | 96.7515 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 80% and Technical Valuation of Offer 20%. Subfactors (Technical value): Methodology 50%, Work program 40%, Safety 10% | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractually foreseen | eo worth €5,993.93
3803 | 3395549 | Repaving contract in the urbanizations of Vale do Lobo, Aldeia das Ferrarias and Quinta Jacintina | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Loulé | Faro | 8 | 11 | 06-04-2017 | 01-06-2017 | 56 | 60 | 210389.05 | 164606.75 | 1 | 144492.93 | 20113.82 | 113.9203 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Refer to the Procedure Program. | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | underwork has been done. | underwork has been performed.
3804 | 3394224 | 5010021100 - Contract work for the "Alfarelos Branch/Verride Agreement - Transformation of BC/BLS and TM/TBB (1st Phase) | 50225000-8 | Railway-track maintenance services | FALSE | 2015 | 2017 | Portugal | N/A | N/A | 13 | N/A | 21-10-2015 | 16-02-2017 | 484 | 60 | 336000 | 330676.3 | 2 | 330676.3 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 55% 2. Technical Value - 25% 3. Safety Management System - 10% 4. Quality Control System - 5% 5. Technical Note on Environmental Monitoring - 5% | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3805 | 3378239 | Contract for the Refurbishment of Infrastructures in the Urbanização das Mimosas | 45232400-6 | Sewer construction work | FALSE | 2015 | 2017 | Portugal | Loulé | Faro | 8 | 20 | 10-02-2016 | 27-04-2017 | 442 | 150 | 349000 | 209400.01 | 1 | 194947.79 | 14452.22 | 107.4134 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | underground infrastructures that had to remain in operation throughout the contract, which limited the development of the projects. the construction site, due to its constraints, required the removal of land after opening a trench and subsequent transfer of land from deposit to landfill, which reduced the income from the project.
3806 | 3372432 | Urban and functional rehabilitation of peripheral neighborhoods of Elvas - Bairro do Revoltilho and surroundings of Can-cão | 45233200-1 | Various surface works | FALSE | 2017 | 2017 | Portugal | Elvas | Portalegre | 12 | 24 | 23-05-2017 | 16-11-2017 | 177 | 120 | 300000 | 271585.05 | 2 | 271585.05 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was necessary to make some corrections in the project
3807 | 3362732 | Contract for Municipal Road Structure - Paving of Various streets - 1st Phase | 45233223-8 | Carriageway resurfacing works | FALSE | 2017 | 2017 | Portugal | Lagos | Faro | 8 | N/A | 22-05-2017 | 21-12-2017 | 213 | 120 | 345000 | 287917.3 | 2 | 302266.8 | -14349.5 | 95.2527 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | signed an additional contract on 10/19/2017 in the amount of €14,349.50
3808 | 3346394 | Improvement of the Municipal road network EM 514 (Between the Underpass under the A22) | 45233140-2 | Roadworks | FALSE | 2016 | 2017 | Portugal | Olhão | Faro | 8 | 20 | 10-02-2017 | 25-05-2017 | 104 | 60 | 265000 | 197005.72 | 1 | 197005.72 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor requested a deadline extension due to a subcontractor being late
3809 | 3346155 | Improvement of the municipal road network in sections of roads in Bias do Sul and Qutrim in the south and north | 45233140-2 | Roadworks | FALSE | 2017 | 2017 | Portugal | Olhão | Faro | 8 | 20 | 05-04-2017 | 15-12-2017 | 254 | 90 | 260000 | 218889.81 | 1 | 200208.17 | 18681.64 | 109.3311 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the development of the project was delayed because there were strata of hard rock in the area where the collector was to be installed and because work was being carried out by entities external to the municipality of olhão. | existence of underworks
3810 | 3341258 | 5010015647 - Contract for the Vouga Line - Sernada/Águeda - Improvement of the Track Superstructure | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 29-04-2015 | 20-03-2017 | 691 | 120 | 2467475 | 1968750.32 | 3 | 1938222.09 | 30528.23 | 101.5751 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A
3811 | 3328891 | The contract includes the execution of paving work on municipal roads, in several parishes in the municipality of Santiago do Cacém. | 45233220-7 | Surface work for roads | FALSE | 2017 | 2017 | Portugal | Santiago do Cacém | Setúbal | 17 | 22 | 03-05-2017 | 21-09-2017 | 141 | 60 | 516000 | 369642.3 | 2 | 369642.3 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed on 28-07-2017, according to the description in the project book. given that the technician in charge (construction owner) was attested, the provisional acceptance report was not drawn up at the end of the project.
3812 | 3328314 | Execution of Covered Playgrounds and Exterior Paintings at EB nº 1 of Cova da Piedade, EB nº 2 of Laranjeiro and Marco Cabaço Kindergarten | 45236290-9 | Repair work on recreational areas | FALSE | 2016 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 28-04-2017 | 29-12-2017 | 245 | 150 | 405544.21 | 298700 | 2 | 293804.95 | 4895.05 | 101.6661 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 "Technical Value of the Proposal" - (40%), with the subfactors "Work execution plan" - 30 points and "Equipment and labor resources" - 10 points. Factor 2 - Proposal price (60%). | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | anticipation in work. | underwork.
3813 | 3327525 | Paving and Roads in the Municipality of Alijó – Requalification and Expansion (Access to the Cemetery of Vilar de Maçada, street of Sobreira and street of Fontainha in Vilar de Maçada, street of Cruzeiro | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2016 | 2017 | Portugal | Alijó | Vila Real | 19 | 20 | 27-04-2017 | 27-11-2017 | 214 | 138 | 222674.02 | 152942.41 | 1 | 152942.41 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3814 | 3293901 | Repairs to Bituminous Paving Lot 1 - contract no. 154/2014 | 45233251-3 | Resurfacing works | FALSE | 2014 | 2017 | Portugal | Matosinhos | Porto | 13 | 9 | 30-12-2014 | 18-04-2017 | 840 | 183 | 1970000 | 654000.01 | 2 | 653121.26 | 878.75 | 100.1345 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | underwork
3815 | 3291393 | Requalification contract for the Urban Center of Bicesse | 45232300-5, 45316110-9, 45100000-8, 45112700-2, 45231223-4, 45233200-1, 45111100-9, 45232130-2, 45232151-5, 45232411-6, 45233294-6 | Construction and ancillary works for telephone and communication lines, Installation of road lighting equipment, Site preparation work, Landscaping work, Gas distribution ancillary work, Various surface works, Demolition work, Storm-water piping construction work, Water-main refurbishment construction work, Foul-water piping construction work, Installation of road signals | FALSE | 2016 | 2017 | Portugal | Cascais | Lisboa | 11 | N/A | 10-02-2017 | 08-09-2017 | 210 | 216 | 984893.9 | 590936.34 | 2 | 590936.34 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% deadline 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3816 | 3288957 | Deepening Dredging Contract for the Access Channel to the Fishing Area of ​​Angeiras | 45243000-2 | Coastal-defence works | FALSE | 2017 | 2017 | Portugal | Matosinhos | Porto | 13 | N/A | 27-03-2017 | 14-12-2017 | 262 | 92 | 315000 | 243839.79 | 1 | 285269.8 | -41430.01 | 85.4769 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 55% Technical Valuation of the Proposal 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | complementary works | complementary works
3817 | 3279442 | Execution of the Contract for Repaving the Path of Poço das Canas and Adjacent streets . | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 24-04-2017 | 23-11-2017 | 213 | 90 | 340000 | 255094.2 | 2 | 255094.2 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to delays by the contractor. | no change
3818 | 3274388 | URGENT REPAIRS OF BITUMINOUS FLOORING 2015 – Union of Parishes of Sª da Hora S. Mamede de Infesta - EDOC 2014/78157 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2017 | Portugal | Matosinhos | Porto | 13 | 36 | 30-09-2015 | 18-04-2017 | 566 | 183 | 850000 | 692143.14 | 2 | 692143.14 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
3819 | 3274211 | 100% Quality - Urgent Repairs for Bituminous Paving 2016-EDC/2014/78188 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2017 | Portugal | Matosinhos | Porto | 13 | 36 | 12-10-2015 | 18-04-2017 | 554 | 183 | 943395.23 | 566037.14 | 2 | 564387.52 | 1649.62 | 100.2923 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | works not required
3820 | 3256897 | Improvement of the Gymnodesportivo "Armando Costa" | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2016 | 2017 | Portugal | Cinfães | Viseu | 20 | 20 | 28-10-2016 | 12-07-2017 | 257 | 180 | 367207.22 | 298000 | 2 | 317393.52 | -19393.52 | 93.8898 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | approval of more works | performing over and underwork.
3821 | 3247179 | Execution of Rainwater Infrastructures | 45232130-2 | Storm-water piping construction work | FALSE | 2016 | 2017 | Portugal | Aveiro | Aveiro | 1 | 26 | 01-03-2017 | 11-11-2017 | 255 | 120 | 217000 | 195000 | 1 | 193111.1 | 1888.9 | 100.9781 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were two extensions and one suspension. | underwork - non-execution of the planned horizontal and vertical signage
3822 | 3227007 | Improvement of Municipal Roads - E.M. 548 (Section cross. E.n. 244 - street of Lagar, Aboboreira) E E.M. 551 (Section cross. E.n. 241-1, Maxieira - new sale) | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Mação | Santarém | 16 | 11 | 29-04-2016 | 01-03-2017 | 306 | 90 | 418309.7 | 250985.83 | 2 | 243013.96 | 7971.87 | 103.2804 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension.
3823 | 3219695 | Works to adapt and rehabilitate the Kindergarten at Santa Casa da Misericordia de S. Bento de arnoia - celorico de basto | 45453100-8 | Refurbishment work | FALSE | 2016 | 2017 | Portugal | Celorico de Basto | Braga | 3 | 20 | 16-05-2016 | 24-03-2017 | 312 | 120 | 297718.72 | 239278.36 | 1 | 236375.61 | 2902.75 | 101.228 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PF = 0.50xPr+0.50xVt Price Factor (Pr): Pr = 100 - 25*Pra/Prb, where, Pr - Price of the proposal under analysis; Prb - Price of the base proposal; Technical value of the proposal (Vt): Vt = 0.10xNj+0.50xMd+0.20xPt+0.10xPSS+0.10xPpr, where, Nj - Price Justification Note, Md - Description and justification, Pt - Work plan, PSS - Health and safety plan, Ppr - Environmental protection and safety plan waste treatment | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with deadlines for carrying out the project due to a fact attributable to the contractor | changes of the execution project.
3824 | 3214311 | Repaving of Several streets | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Lisboa | Lisboa | 11 | 25 | 29-03-2017 | 27-07-2017 | 120 | 90 | 330000 | 205408.17 | 1 | 207284.59 | -1876.42 | 99.0948 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the change in the value of the contract is due to the additional works
3825 | 3202446 | Urgent Repairs for Cube Flooring 2016 - EDOC/2014/78180 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2017 | Portugal | Matosinhos | Porto | 13 | 36 | 16-10-2015 | 22-03-2017 | 523 | 183 | 566036.74 | 279734.5 | 2 | 279734.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
3826 | 3195915 | The objective of this contract is the rehabilitation of a public space, integrated in an area with a high rate of construction and intended for the creation of green spaces and equipment. | 45112712-9 | Landscaping work for gardens | FALSE | 2017 | 2017 | Portugal | Covilhã | Castelo Branco | 5 | 21 | 23-03-2017 | 27-10-2017 | 218 | 130 | 852007.2 | 608020.74 | 2 | 608020.74 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | equipment supply
3827 | 3183223 | Conservation and Improvement of streets in the Municipality of Almada - 4th Action 2016 | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Almada | Setúbal | 17 | 21 | 09-03-2017 | 17-10-2017 | 222 | 90 | 508946 | 414771.33 | 2 | 410312.59 | 4458.74 | 101.0867 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the projects were completed within the contract term, however the provisional receipt was only made on this date due to delivery of the final screens and technical compilation | underwork
3828 | 3155376 | 5010018083 - Contract for the Rehabilitation of the Track between km 226.570 and 230.880 - Linha do Leste | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 21-08-2015 | 21-02-2017 | 550 | 120 | 902929 | 789967 | 2 | 781267 | 8700 | 101.1136 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 50% 2. Technical Valuation - 30% 3. Safety Management System - 10% 4. Quality Control System - 5% 5. Environmental Monitoring System - 5% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3829 | 3153593 | Conservation and Improvement of streets in the Municipality of Almada - 3rd Action 2016 | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Almada | Setúbal | 17 | 21 | 06-02-2017 | 27-09-2017 | 233 | 90 | 504161 | 369767.13 | 2 | 363922.47 | 5844.66 | 101.606 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the contract period, however the provisional reception was only made on this date due to the delivery of the final screens and technical compilation | underwork
3830 | 3150433 | Work to repave the Amendoal path. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 14-03-2017 | 04-08-2017 | 143 | 90 | 335000 | 236959.05 | 1 | 236959.05 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline is due to delays on the part of the contractor
3831 | 3130161 | Repaving of the Caminho do Roque | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 10-03-2017 | 16-11-2017 | 251 | 60 | 250000 | 197879.35 | 1 | 197879.35 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | due to delays by the contractor.
3832 | 3120978 | Repair and Improvement of the APSS Railway Track in the Port of Setúbal | 45234120-3 | Urban railway works | FALSE | 2016 | 2017 | Portugal | Setúbal | Setúbal | 17 | N/A | 23-02-2017 | 22-11-2017 | 272 | 120 | 400000 | 325691.86 | 2 | 308622.9 | 17068.96 | 105.5307 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Overall Price 40% 2) Technical Quality and Work Methodology 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the conditions of use of the railway | no need to perform some work
3833 | 3108357 | Contract to repave the path to Barnabas and the path to Vine. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 06-03-2017 | 22-06-2017 | 108 | 60 | 205000 | 157449.4 | 1 | 157449.4 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor completed the project before the deadline.
3834 | 3107430 | Requalification of the School of Valbom - S. Cristóvão | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2017 | Portugal | Cinfães | Viseu | 20 | 20 | 15-02-2017 | 27-09-2017 | 224 | 120 | 193702.8 | 166514.6 | 1 | 175579.4 | -9064.8 | 94.8372 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | performing more work. | more work and underwork.
3835 | 3093145 | Contract to repave the path to the Ataboeira well. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 03-03-2017 | 16-11-2017 | 258 | 90 | 420000 | 256706.76 | 2 | 256706.76 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to delays by the contractor. | no change
3836 | 3084743 | 5010016732 - Complete rehabilitation of the track - Migration of wooden sleepers to biblock concrete sleepers - Phase 1 - Beira Baixa Line - Entroncamento / Rodão Section | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | N/A | 22-05-2015 | 31-01-2017 | 620 | 60 | 1730142.03 | 1375554.12 | 3 | 1371607.95 | 3946.17 | 100.2877 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
3837 | 3082654 | Contract to improve the road linking Abóboda - Conceição da Abóboda | 45232332-8, 45112700-2, 45112100-6, 45233294-6, 45232410-9, 45232151-5, 45316110-9, 45100000-8, 45233200-1 | Ancillary works for telecommunications, Landscaping work, Trench-digging work, Installation of road signals, Sewerage work, Water-main refurbishment construction work, Installation of road lighting equipment, Site preparation work, Various surface works | FALSE | 2016 | 2017 | Portugal | Cascais | Lisboa | 11 | N/A | 25-10-2016 | 07-08-2017 | 286 | 216 | 1441542.46 | 864925.48 | 2 | 947118.74 | -82193.26 | 91.3218 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price 90% Execution time 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3838 | 3082480 | Moscavide -Portela - Sacavém cycling net | 45233162-2 | Cycle path construction work | FALSE | 2016 | 2017 | Portugal | Loures | Lisboa | 11 | 20 | 06-01-2017 | 06-07-2017 | 181 | 60 | 221500 | 203587.71 | 1 | 203587.71 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made according to the criterion of most economically advantageous proposal. According to the following factors and respective weighting: Price - 70%. deadline - 30% PF=(Base Price)/(Proposed Price)×5 Deadline=(Maximum Deadline)/(Proposal Deadline)×5 CF=0.7×PF+0.3×Pr CF - Final Classification PF - Final Price attributed to the proposal Pr - Deadline Deadlines less than or equal to 60 consecutive days will be classified as 7.5 in the deadline criterion. In the event of a tie, the percentage discount to be applied to the bid price will be used as a tiebreaker. | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3839 | 3064939 | Reformulation of false ceilings, electrical installations and fire safety in the DMOPATDE building | 45310000-3 | Electrical installation work | FALSE | 2016 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 19-12-2016 | 04-10-2017 | 289 | 150 | 424000 | 412692.37 | 2 | 403062.85 | 9629.52 | 102.3891 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 - "Technical Value of the Proposal" - (40%), with the subfactors "Work execution plan" - 30 points and "Equipment and labor resources" - 10 points Factor 2 - "Proposal Price" - (60%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | there was a suppression of works.
3840 | 3057561 | 5010020210 - Anticorrosive protection of metal bridges, on the West Line. | 45221112-0 | Railway bridge construction work | FALSE | 2015 | 2017 | Portugal | N/A | N/A | 13 | 27 | 07-06-2016 | 06-07-2017 | 394 | 180 | 650000 | 636143.41 | 2 | 629620.6 | 6522.81 | 101.036 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: - Price 55% - Technical value 25% - Security Management System 10% - Quality Management System 5% - Environmental Monitoring System 5% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | additional hours of service provided by inspection: - €6,522.81
3841 | 3048174 | S.e.c. - PROC No. 180/A1/16 - Public Tender for the award of the contract for "Construction of the Supports of Beach E1 and E2 - Praia Norte" | 45212600-2 | Pavilion construction work | FALSE | 2016 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 21-02-2017 | 29-12-2017 | 311 | 120 | 976747.1 | 929930.08 | 2 | 929930.08 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3842 | 3020236 | Requalification of streetMouzinho de Albuquerque, Cartaxo. | 45233252-0 | Surface work for streets | FALSE | 2016 | 2017 | Portugal | Cartaxo | Santarém | 16 | N/A | 08-02-2017 | 28-11-2017 | 293 | 120 | 192592.83 | 168320.76 | 1 | 164993.75 | 3327.01 | 102.0164 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to point out | works not performed, as there is no need
3843 | 3010707 | Repaving of Roads in Cerro Grande. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 02-02-2017 | 04-08-2017 | 183 | 60 | 460000 | 331742.6 | 2 | 331742.6 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline for the project is due to delays on the part of the contractor.
3844 | 3010097 | Execution of the Sol Building, in the parish of Rosais, municipality of Velas, island of São Jorge | 45113000-2 | Siteworks | FALSE | 2016 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 35 | 10-02-2017 | 15-09-2017 | 217 | 180 | 321690.7 | 319607.66 | 2 | 319607.66 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: 50% Price and 50% Technical Value of the Proposal | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract was completed 1 day before the deadline, which was 180 days
3845 | 3009823 | Rehabilitation of Largo do Viteleiro/Leisure Area of ​​Fajã do Ouvidor, in the Parish of Norte Grande, Municipality of Velas, island of São Jorge | 45113000-2 | Siteworks | FALSE | 2016 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 35 | 10-02-2017 | 20-10-2017 | 252 | 180 | 240000 | 239503.99 | 1 | 239503.99 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 50% Price and 50% Technical value of the Proposal | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | more 47 days - atmospheric conditions that have been verified, which are a cause of delays, as well as the delay in the delivery of the material by some suppliers, since some articles have to be directly manufactured, not existing in stock.
3846 | 3009144 | Repaving of streets in the Municipality of Loures | 45233222-1 | Paving and asphalting works | FALSE | 2016 | 2017 | Portugal | Loures | Lisboa | 11 | 30 | 28-11-2016 | 21-08-2017 | 266 | 60 | 443396.23 | 319720.43 | 2 | 319720.43 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | impossibility of carrying out part of the project on the contract, as work on another contract was ongoing in the surrounding area, which made it impossible to restrict the traffic of the two contracts simultaneously. | ordinary price review based on definitive indices
3847 | 2998581 | Contract for Requalification of the Road Infrastructure of Estrada do Ancão - Phase 2 | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Loulé | Faro | 8 | 21 | 12-12-2016 | 16-05-2017 | 155 | 63 | 205000 | 174881.18 | 1 | 174881.18 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension and suspension indicated above, by mutual agreement between the owner and the contractor.
3848 | 2988325 | Execution of streets next to the Pinhel Football Field. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Pinhel | Guarda | 9 | N/A | 01-02-2017 | 06-06-2017 | 125 | 60 | 349800 | 314000 | 2 | 301484.3 | 12515.7 | 104.1514 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extensions due to work not contemplated
3849 | 2980071 | Process RD21A - Construction of the schools sports pavilion in Fragoso | 45000000-7 | Construction work | FALSE | 2016 | 2017 | Portugal | Barcelos | Braga | 3 | 30 | 27-01-2017 | 19-12-2017 | 326 | 225 | 790000 | 748974.36 | 2 | 731438.71 | 17535.65 | 102.3974 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40%); b) Technical Value of the Proposal (60%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Descriptive and Justification of the mode of execution of the work "MDJ" (25%). | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in carrying out the project. | a) difference in the quantities foreseen and necessary to execute. b) in chapters chapter vi - wastewater drainage network and chapter vii - rainwater drainage network, it was verified on site that the land already had networks of these infrastructures in good condition, which led to the non-execution of the new infrastructures.
3850 | 2976722 | Requalification of the Central street in Pala | 45211360-0 | Urban development construction work | FALSE | 2016 | 2017 | Portugal | Pinhel | Guarda | 9 | N/A | 17-01-2017 | 30-10-2017 | 286 | 90 | 270000 | 187000 | 1 | 165028.54 | 21971.46 | 113.3137 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of the deadline due to the fault of the contractor. | underwork
3851 | 2974343 | Enhancementb of the Entrance to Castelo de Vide, Martinho/São José - Pedestrian Corridors | 45233260-9 | Pedestrian ways construction work | FALSE | 2016 | 2017 | Portugal | Castelo de Vide | Portalegre | 12 | 22 | 11-01-2017 | 10-10-2017 | 272 | 210 | 385687 | 296598.89 | 2 | 319998.45 | -23399.56 | 92.6876 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Proposed Price, (60%); b) Technical value of Proposal, (40%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of additional works | execution of additional work and price revision
3852 | 2955176 | Requalification of E.N.242 - Between Ponte das Mestras and Barosa | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 16-01-2017 | 22-11-2017 | 310 | 120 | 169811.32 | 164808 | 1 | 164808 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension.
3853 | 2908720 | For the execution of the contract called “en120 - bridge over the torgal stream / er267 - bridge over the oeiras river. Rehabilitation and reinforcement of works of art” | 45221119-9 | Bridge renewal construction work | FALSE | 2013 | 2017 | Portugal | Beja | Beja | 2 | 60 | 28-08-2015 | 08-03-2017 | 558 | 180 | 600000 | 463563 | 2 | 461370.41 | 2192.59 | 100.4752 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension of 7 days under the contractor's responsibility for reasons related to the weather condition | the alteration resulted from the determination in the final measurement of the project of work to supply negative errors and omissions in the amount of €1,150.19 and of work to be done in the amount of €1,042.40
3854 | 2904930 | Urban rehabilitation of the central area of ​​Cortes, Union of Parishes of Leiria, Pousos, Barreira and Cortes | 45211360-0 | Urban development construction work | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 12-01-2017 | 11-08-2017 | 211 | 180 | 355005.72 | 265442.14 | 2 | 265442.14 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
3855 | 2902624 | Requalification of Several streets in Cruz Da Areia - Leiria | 45233253-7 | Surface work for footpaths | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 10-01-2017 | 08-05-2017 | 118 | 90 | 254250 | 231340.5 | 1 | 231340.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3856 | 2901974 | Requalification of the Municipal Road Network - Supply and application of cold microagglomerate in several places in the Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 16-01-2017 | 11-05-2017 | 115 | 90 | 345000 | 254475.56 | 2 | 254475.56 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline.
3857 | 2877371 | S.e.c. - Proc. nº 206/a1/16 - public tender for the contract award of "execution of reinforcement of the forest defense network against fires" | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 10-01-2017 | 06-06-2017 | 147 | 90 | 237482.03 | 231926.12 | 1 | 231926.12 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Bid price - 40%, Technical Valuation of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3858 | 2862651 | Year 2016_Contract for the Rehabilitation of the Central Laundry and Auditorium in the São Roque complex | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2018 | Portugal | Lisboa | Lisboa | 11 | 30 | 15-12-2016 | 07-06-2018 | 539 | 365 | 2800000 | 2207957.21 | 3 | 5596.8 | 2202360.41 | 39450.3504 | lowest price | 2 | 100 | Yes (no values) | FALSE | Non-fulfilment of the contract (Contract Termination) | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project suffered some constraints related to the identification of buried installations that were not duly registered, as well as the identification of the need to carry out additional work that derived from design errors and Extra work. the fact that the contractor did not complete the contract within the deadline, which, together with other situations, led to the contract being terminated, with the respective penalties for the contractor. | the project suffered some constraints related to the identification of buried installations that were not duly registered, as well as the identification of the need to carry out additional work that derived from design errors and Extra work. the fact that the contractor did not complete the contract within the deadline, which, together with other situations, led to the contract being terminated, with the respective penalties for the contractor.
3859 | 2830954 | 21/Eop/dcop/2016 - contract for en 247-5 widening in Manique | 45112100-6, 45223000-6, 45232410-9, 45112700-2, 45316110-9, 45232100-3, 45232151-5, 45233294-6, 45232332-8, 45100000-8, 45233200-1 | Trench-digging work, Structures construction work, Sewerage work, Landscaping work, Installation of road lighting equipment, Ancillary works for water pipelines, Water-main refurbishment construction work, Installation of road signals, Ancillary works for telecommunications, Site preparation work, Various surface works | FALSE | 2016 | 2017 | Portugal | Cascais | Lisboa | 11 | N/A | 19-10-2016 | 07-08-2017 | 292 | 216 | 740648 | 566990 | 2 | 613242.73 | -46252.73 | 92.4577 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Deadline - 10%; Price 90% | 1 | 90 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3860 | 2819516 | Reformulation of false ceilings, electrical installations and fire safety in the DMOPATDE building | 45310000-3 | Electrical installation work | FALSE | 2015 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 19-12-2016 | 04-10-2017 | 289 | 150 | 446817.81 | 412692.37 | 2 | 403062.85 | 9629.52 | 102.3891 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 - "Technical Value of the Proposal" - (40%), with subfactors "Work execution plan" - 30 points and "Equipment means and labor" - 10 points. Factor 2 - "Proposal Price" - (60%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | there was a deletion of works
3861 | 2805679 | Rehabilitation and Reinforcement of the Support Wall of the CED NSC | 45223500-1 | Reinforced-concrete structures | FALSE | 2016 | 2017 | Portugal | Lisboa | Lisboa | 11 | N/A | 14-11-2016 | 26-07-2017 | 254 | 70 | 199500 | 158033.3 | 1 | 157863.02 | 170.28 | 100.1079 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (40%); technical gains (60%) | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractor's request for extension of time | existence of overwork and underwork
3862 | 2805445 | Rehabilitation of the Library Building - CED PM | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Lisboa | Lisboa | 11 | N/A | 24-10-2016 | 04-01-2017 | 72 | 65 | 190835 | 181236.55 | 1 | 181236.55 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (60%) and Technical Valuations (40%) | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline changes | no value changes
3863 | 2804981 | Refurbishment of electrical installations, HVAC and telecommunications systems in the municipal library of Alverca do Ribatejo | 45310000-3 | Electrical installation work | FALSE | 2016 | 2017 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 21-12-2016 | 26-07-2017 | 217 | 150 | 198000 | 196408.2 | 1 | 196408.2 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report
3864 | 2804048 | Rehabilitation of the Social Neighborhood of Almoinhas - PEDU | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 12-12-2016 | 30-06-2017 | 200 | 180 | 264000 | 249696.95 | 1 | 246139.8 | 3557.15 | 101.4452 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | underwork.
3865 | 2802903 | Rehabilitation of street of Curado and streetJoaquim Pedro Monteiro - Vila Franca de Xira | 45233251-3 | Resurfacing works | FALSE | 2016 | 2017 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 12-10-2016 | 30-06-2017 | 261 | 150 | 414000 | 405619.9 | 2 | 369576.33 | 36043.57 | 109.7527 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | approval of underwork at the board meeting of 04/26/2017 in the amount of 36,043.37
3866 | 2797733 | S.e.c. - PROCº nº 202/A1/16 - Public Tender for the award of the contract for "Pedestrianization of the Historic Center of Viana do Castelo - Requalification of streetde Olivença and Largo Mestre César" | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 22-12-2016 | 24-11-2017 | 337 | 120 | 545000 | 537003.89 | 2 | 463954.77 | 73049.12 | 115.7449 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the procedure program | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions | not as much work was needed as originally planned.
3867 | 2778995 | 5/EOP/DCOP/2016 - Contract for conservation and maintenance of streets in the municipality of Cascais | 45232452-5, 45111100-9, 45100000-8, 45233221-4, 45233200-1 | Drainage works, Demolition work, Site preparation work, Road-surface painting work, Various surface works | FALSE | 2016 | 2017 | Portugal | Cascais | Lisboa | 11 | N/A | 18-08-2016 | 18-05-2017 | 273 | 144 | 999495 | 599697.01 | 2 | 641106.92 | -41409.91 | 93.5409 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 90% Execution time 10% | 1 | 90 | N/A | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | price review
3868 | 2758917 | Construction contract and supply of the Improvement of the Mechanical Pre-treatment Line of the Organic Valorization Center | 45222100-0 | Waste-treatment plant construction work | FALSE | 2015 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 42 | 24-11-2016 | 16-08-2017 | 265 | 155 | 476821 | 390668.03 | 2 | 393788.03 | -3120 | 99.2077 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | performing more work. | performing more work.
3869 | 2749371 | Requalification of the carriageway, gutter and pavements of the North Terminal of the Port of Aveiro - 1st Phase | 45234120-3 | Urban railway works | FALSE | 2016 | 2017 | Portugal | Ílhavo | Aveiro | 1 | 24 | 07-12-2016 | 04-10-2017 | 301 | 120 | 350000 | 210000.01 | 1 | 210000.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 0.70 Technical Valuation of the Proposal: 0.30 | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ended within the contractual period of 120 days. the days after the deadline were used for internal administrative procedures, as well as to notify the successful tenderer in writing, to carry out the inspection and sign the respective receipt.
3870 | 2723950 | Finishing, furniture, audio and video contract for the otoc auditorium in lisbon | 45212321-2 | Auditorium construction work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | 12 | 15-07-2016 | 28-12-2017 | 531 | 60 | 630000 | 572889.16 | 2 | 567973.1 | 4916.06 | 100.8655 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without description | purchasing cheaper materials
3871 | 2719755 | Construction of Pinhel Discovery Swimming Pools | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2016 | 2017 | Portugal | Pinhel | Guarda | 9 | N/A | 19-11-2016 | 05-12-2017 | 381 | 150 | 489000 | 438714.79 | 2 | 414801.32 | 23913.47 | 105.765 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extensions | underwork
3872 | 2714696 | Execution contract for Basic Sanitation Infrastructure and Pavement Rehabilitation in street of Outeiro - Lomba da Maia | 45233120-6 | Road construction works | FALSE | 2015 | 2017 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 45 | 09-08-2016 | 20-10-2017 | 437 | 270 | 596380.46 | 485960 | 2 | 482397.72 | 3562.28 | 100.7385 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price: 60%; 2. Work Execution Quality: 40%; The. Descriptive memory and justification of the execution of the work: 30%; B. Work plan: 25%; ç. Labor Plan: 25% d. Equipment Plan: 20% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project only started after the contract was approved by the court of auditors | in the undertaking there were underwork.
3873 | 2710728 | EGA-EB0011 - Mancelos (Amarante) Wastewater Drainage Network | 45232440-8 | Construction work for sewage pipes | FALSE | 2015 | 2017 | Portugal | Amarante | Porto | 13 | 42 | 09-11-2016 | 28-06-2017 | 231 | 120 | 245000 | 154756.51 | 1 | 125763.91 | 28992.6 | 123.0532 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork - some sections were not carried out because it was verified in the project that they were private streets (about 400m)
3874 | 2700548 | Contract for remodeling the roof of a building in the parish of Ponte and remodeling the head office building in Guimaraes | 45261910-6 | Roof repair | FALSE | 2016 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 24-11-2016 | 18-07-2017 | 236 | 120 | 260000 | 208001.03 | 1 | 208001.03 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting); Technical value (30% weighting) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | pre-contractual litigation process 2236/16.3bebrg which forced the interruption of the project from 12/13/2016 to 3/23/2017 (100 days).
3875 | 2694718 | The purpose of this contract is to carry out work on window frames, window frames, kitchen furniture, kitchen and bathroom faucets, interior and exterior doors | 45453100-8 | Refurbishment work | FALSE | 2016 | 2017 | Portugal | Amadora | Lisboa | 11 | 20 | 16-11-2016 | 09-08-2017 | 266 | 45 | 188623.06 | 168373.49 | 1 | 168373.49 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | abnormal and unpredictable change in circumstances (art 312 a) of the "public procurement code"
3876 | 2693296 | Sanitation network in the Municipality - Location of Cheires | 45231000-5 | Construction work for pipelines, communication and power lines | FALSE | 2016 | 2017 | Portugal | Alijó | Vila Real | 19 | 15 | 17-10-2016 | 30-08-2017 | 317 | 180 | 253860.88 | 176600 | 1 | 176600 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a) delay verified in the excavations, since there was a need to use explosives, so they had to resort to licenses and authorizations, for their use, which was only possible in january of the current year; b) delay in the delivery of the two fiberglass tanks to the site, which only took place in april 201, which are large, also causing a delay in the construction of the gabion wall.
3877 | 2691137 | Preventive Maintenance Works for the Social Housing Buildings of the Housing Park of Porto Chamber - Bairro das Campinas, Blocks 1 to 7 (EM.004.2016.210) | 45443000-4 | Facade work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 18-11-2016 | 19-04-2017 | 152 | 100 | 280000 | 241815.7 | 1 | 248004.72 | -6189.02 | 97.5045 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%, Technical Valuation of Proposal 20% and Deadline 10%; Subfactors (of technical value): Work program 50%, Methodology 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project took place within the contractually foreseen. | errors and omissions worth €6,189.02
3878 | 2689432 | Preventive Maintenance Works in the Outeiro District - Blocks A to N (EM.004.2016.201) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 10-11-2016 | 21-07-2017 | 253 | 150 | 585000 | 559325.47 | 2 | 533348.28 | 25977.19 | 104.8706 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%; Technical value of Proposal 20% and Deadline 10%; Subfactors (Technical value): Work program 50%, Methodology 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | eo in the amount of €2,047.86 and work not carried out in the amount of €28,025.05
3879 | 2689364 | Improvement of streets in the Union of Parishes of Briteiros S. Salvador and Briteiros Sta Leocádia | 45233251-3 | Resurfacing works | FALSE | 2016 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 21-11-2016 | 15-05-2017 | 175 | 90 | 472083.27 | 348842.75 | 2 | 338062.86 | 10779.89 | 103.1887 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60%; Technical value - 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | works were suspended (partial work suspension notice dated 01/26/2017) for a probable period of 30 days under the terms set forth in paragraph a) of art. 297 of the public contracts code, since the unfavorable weather conditions made it impossible, even temporarily, to apply bituminous pavements and the respective subsequent activities. work restart notice: 02/20/2017. | underwork due to the anticipated quantities not being used up.
3880 | 2687836 | Requalification of the municipal road network - Repair of Pavements affected by tree roots in several places in the municipality of Leiria | 45233140-2 | Roadworks | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 23-11-2016 | 24-07-2017 | 243 | 90 | 200000 | 175350 | 1 | 175350 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline.
3881 | 2685620 | Preventive maintenance works in the neighborhood of Mouteira - Block 10 (EM.004.2016.209) | 45443000-4 | Facade work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 18-11-2016 | 27-10-2017 | 343 | 119 | 400000 | 369790.55 | 2 | 365203.33 | 4587.22 | 101.2561 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%, Technical Valuation of Proposal 20% and Deadline 10%; Subfactors (of technical value): Work program 50%, Methodology 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractually stipulated period was not met. the undertaking had a contractual sanction. | errors and omissions in the amount of €3,854.28 and work not carried out in the amount of €7,025.40.
3882 | 2681989 | Contract for Boavista School Center, Santa Eulália | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2017 | Portugal | Arouca | Aveiro | 1 | 30 | 21-11-2016 | 21-11-2017 | 365 | 270 | 547988.68 | 440000 | 2 | 403129 | 36871 | 109.1462 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | underwork
3883 | 2676261 | Recovery of the municipal road network 2016/2020 - 1st phase | 45233251-3 | Resurfacing works | FALSE | 2016 | 2017 | Portugal | Cartaxo | Santarém | 16 | 20 | 21-11-2016 | 02-05-2017 | 162 | 90 | 348492.56 | 278794.06 | 2 | 270923.05 | 7871.01 | 102.9053 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; b) Technical value of the proposal - 40%; | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline changes | no deadline changes
3884 | 2674997 | Landscaping on the left bank of Porto Manes – Landscape Pavilion | 45112723-9 | Landscaping work for playgrounds | FALSE | 2016 | 2017 | Portugal | Arronches | Portalegre | 12 | 30 | 02-11-2016 | 18-10-2017 | 350 | 270 | 599847.11 | 598999 | 2 | 590464.78 | 8534.22 | 101.4453 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60 % Descriptive Memory and Justification of the Mode of Execution of the Work: 10% a3) Work Plan: 10% a4) Labor Plan: 10% Equipment Plan: 10% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension of more work | additional work
3885 | 2664452 | Requalification of Largo de S. Sebastião | 45233262-3 | Pedestrian zone construction work | FALSE | 2016 | 2017 | Portugal | São Brás de Alportel | Faro | 8 | 30 | 08-11-2016 | 24-05-2017 | 197 | 180 | 377000 | 297595.23 | 2 | 297595.23 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 - Proposal value (PV) 60% Factor 2 - Technical value of the proposal (TV) 40% Subfactor 2.1-Work plan (PT) 80% Sub-sub-factor 2.1.1 - Bar chart (GB) 50% Sub-subfactor 2.1.2 - Descriptive memory and justification (MD) 30% Sub-sub-factor 2.1.3 - Labor Plan (PMO) 10% Sub-sub-factor 2.1.4 - Equipment plan (PEQ) 10% Subfactor 2.2 - Payment plan (PP) 20% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3886 | 2663432 | Contract for repaving streets in Canals. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 16-11-2016 | 14-07-2017 | 240 | 90 | 370000 | 275747.42 | 2 | 275747.42 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the alteration to the execution period of the project is due to delays on the part of the contractor.
3887 | 2660288 | Repaving of the Municipal Road EM 506 | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2017 | Portugal | Mértola | Beja | 2 | 30 | 07-11-2016 | 23-10-2017 | 350 | 150 | 950000 | 776747.98 | 2 | 776747.98 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project.
3888 | 2648372 | The contract includes the execution of earthworks, wastewater and rainwater drainage networks, water supply networks, electrical infrastructure, circulation areas and sidewalks | 45211360-0 | Urban development construction work | FALSE | 2016 | 2017 | Portugal | Oleiros | Castelo Branco | 5 | 15 | 27-10-2016 | 27-06-2017 | 243 | 150 | 348720 | 277300 | 2 | 288349.63 | -11049.63 | 96.168 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the reasons invoked by the contractor, referring to the impossibility of completing the projects of the contract mentioned above, within the established period, due to adverse weather conditions that conditioned the execution of the projects and delays in the reception of the specific material
3889 | 2648190 | Contract to repave a section of the Sesmarias path, including access to the JI in Vale Rabelho. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 14-11-2016 | 04-08-2017 | 263 | 90 | 240000 | 154510.17 | 1 | 154510.17 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays by the contractor
3890 | 2644158 | Preventive maintenance works for the Viso Housing Group - Blocks 1 to 8 - crossstreet ofs Cruzes (EM.004.2016.192) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 08-11-2016 | 09-05-2017 | 182 | 140 | 385000 | 359601.6 | 2 | 343846.88 | 15754.72 | 104.5819 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 70%; deadline 10% and Technical Valuation of Proposal 20%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | work not carried out worth €15,745.72
3891 | 2640221 | Replacement of Water Supply Pipelines and Repaving-Valhascos-North Zone | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2017 | Portugal | Sardoal | Santarém | 16 | 20 | 10-11-2016 | 07-08-2017 | 270 | 150 | 166000 | 153983 | 1 | 153983 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3892 | 2633810 | Preventive Maintenance Works for Social Housing Buildings in the Oporto City Council Housing Park - Bairro Vale Formoso, Blocks 1, 2, 3 and 4 (EM.004.2016.211) | 45443000-4 | Facade work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 02-11-2016 | 08-05-2017 | 187 | 99 | 200000 | 199937.33 | 1 | 204123.92 | -4186.59 | 97.949 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%, Technical Valuation of Proposal 20% and Deadline 10%; Subfactors (of technical value): Work program 50%, Methodology 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | more work worth €4,517.99, errors and omissions worth €5,055.24 and work not performed worth €5,386.64.
3893 | 2625916 | The object of this contract is the renovation of a 2.5 km water distribution network, including the remodeling of the reserve system, and a domestic wastewater drainage system | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Murtosa | Aveiro | 1 | N/A | 02-11-2016 | 07-09-2017 | 309 | 90 | 500000 | 378250.7 | 2 | 377800.72 | 449.98 | 100.1191 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment and materials - 10%) | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | contracted works, not performed
3894 | 2624992 | Business Park Adductor - Vilela Seca and Remodeling of the Vilela Seca Reservoir | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Chaves | Vila Real | 19 | 30 | 04-11-2016 | 24-10-2017 | 354 | 150 | 254332 | 226315 | 1 | 217100.56 | 9214.44 | 104.2443 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork worth €9,214.44
3895 | 2619679 | Reprofiling of the road section between the EN 101 and the central area of ​​Vila de Ponte - 1st Phase | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 02-11-2016 | 26-04-2017 | 175 | 120 | 361630.76 | 310000.01 | 2 | 309062.43 | 937.58 | 100.3034 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60%; Technical Value - 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork due to the anticipated quantities not being used up.
3896 | 2615527 | Requalification of Squares and streets in the Historic Center of Arouca - Alameda D. Domingos de Pinho Brandão | 45233160-8 | Paths and other metalled surfaces | FALSE | 2016 | 2017 | Portugal | Arouca | Aveiro | 1 | 30 | 31-10-2016 | 21-08-2017 | 294 | 270 | 243641.64 | 229279.98 | 1 | 217533.99 | 11745.99 | 105.3996 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay attributable to the contractor. | deletion of works.
3897 | 2599453 | Preventive Maintenance Works in the Duque de Saldanha District (EM.004.2016.207) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 20-10-2016 | 07-03-2017 | 138 | 90 | 200000 | 159120.91 | 1 | 157158.84 | 1962.07 | 101.2485 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%, Technical Valuation of Proposal 20% and Deadline 10%; Subfactors (of technical value): Work program 50%, Methodology 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | work not carried out worth €1962.07
3898 | 2591649 | Requalification and Improvement of Avenida Dr Carlos Campos | 45233251-3 | Resurfacing works | FALSE | 2016 | 2017 | Portugal | Oliveira do Hospital | Coimbra | 6 | 21 | 26-10-2016 | 18-12-2017 | 418 | 210 | 510000 | 345427.77 | 2 | 334552.78 | 10874.99 | 103.2506 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project.
3899 | 2585873 | Public works contract Preventive Maintenance Works in the Agra do Amial neighborhood (EM.004.2016.196) | 45443000-4 | Facade work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 25-10-2016 | 19-04-2017 | 176 | 120 | 300000 | 273426.12 | 2 | 278709.77 | -5283.65 | 98.1042 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 70%; deadline 10% and Technical Valuation of Proposal 20%; Subfactors (Technical value): Methodology 50%, Work program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the contractually stipulated period | errors and omissions worth €5,283.65
3900 | 2585450 | The object of this contract is the construction of a gravity network over a length of 2,820 meters of wastewater collectors, in PP and DN 200mm, 210 home branches | 45232460-4 | Sanitary works | FALSE | 2015 | 2017 | Portugal | Oliveira do Bairro | Aveiro | 1 | N/A | 21-10-2016 | 10-11-2017 | 385 | 180 | 470000 | 363464.45 | 2 | 345753.58 | 17710.87 | 105.1224 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1- Price: 55% | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | work contracted and not performed
3901 | 2577789 | Execution of the Contract for "Dredging maintenance of the bar, the access channel and the port basin of the port of Póvoa de Varzim" | 45252124-3 | Dredging and pumping works | FALSE | 2016 | 2017 | Portugal | Póvoa de Varzim | Porto | 13 | 11 | 25-10-2016 | 14-12-2017 | 415 | 60 | 430000 | 375000 | 2 | 370872 | 4128 | 101.1131 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award is carried out according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors and respective weighting coefficients: a) Price (50%) scored using the value function represented in Annex 4 to the tender program; b) Technical value (50%) assessed using the methodology set out in Annex 4 to the tender program. The subfactors and respective qualitative analysis descriptors and respective weightings and scores, to be considered for the evaluation of the factor "Technical value of the proposal" are the following: a) Descriptive memory and justification of how the work was carried out - 30%; b) Work plan - 10%; c) Labor plan - 10%; d) Equipment plan - 50%. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work due to lack of safety conditions for the dredgers to operate, due to adverse sea turmoil (significant swell and strong wind). | deduction corresponding to the dredging equipment foreseen in the contractor's proposal and which was not mobilized.
3902 | 2576752 | Requalification of street ofs Minas, street of Cooperativa, streetN.ª Sr.ª de Fátima and street ofs Flores in the Union of Parishes of Leiria, Pousos, Barreira and Cortes and section between Azambujo and Soutocico of E.M.544 | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 24-10-2016 | 06-02-2017 | 105 | 90 | 206800 | 192745.75 | 1 | 192745.75 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3903 | 2568149 | Rehabilitation of blocks 57 to 61 and 70 to 71 of Bairro de Santa Luzia (EM.004.2016.153) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 14-10-2016 | 24-10-2017 | 375 | 240 | 630000 | 441000.01 | 2 | 434138.98 | 6861.03 | 101.5804 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project did not proceed according to contractually foreseen only due to the failure of deadlines by the executing entity. | eo in the amount of €2,499.98 and work not carried out in the amount of €9,361.01
3904 | 2567755 | Expansion of the support building of the Municipal Stadium | 45212200-8 | Construction work for sports facilities | FALSE | 2016 | 2017 | Portugal | Almeirim | Santarém | 16 | 24 | 13-10-2016 | 18-11-2017 | 401 | 180 | 294976.19 | 180102.09 | 1 | 166573.85 | 13528.24 | 108.1215 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the previous contract | underwork - plastering has been removed from the project plan
3905 | 2557905 | Remodeling of Largo General Silveira | 45233160-8 | Paths and other metalled surfaces | FALSE | 2016 | 2017 | Portugal | Chaves | Vila Real | 19 | 30 | 19-10-2016 | 07-12-2017 | 414 | 90 | 315000 | 245699 | 1 | 269455.48 | -23756.48 | 91.1835 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | errors and omissions supply information no. 71/2017 approved at a city council meeting on march 3, 2017. | supply of errors and omissions in the amount of 17,925.80 euros, underwork in the amount of 2,084.75 euros and provisional price revision in the amount of 7,915.43 euros.
3906 | 2536528 | 5010017459 - Contract for Reinforcement and anti-corrosive Treatments Cascais Line | 45442200-9 | Application work of anti-corrosive coatings | FALSE | 2015 | 2017 | Portugal | N/A | N/A | 13 | N/A | 23-03-2016 | 12-09-2017 | 538 | 212 | 610000 | 366000.01 | 2 | 362396.86 | 3603.15 | 100.9943 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 50% 2. Technical Valuation - 30% 3. Safety Management System - 10% 4. Quality Control System - 5% 5. Environmental Monitoring System - 5% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3907 | 2527137 | Rehabilitation and correction of anomalies in blocks 41 to 45 and 66 to 69 of Bairro de Santa Luzia (EM.004.2016.137) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Porto | Porto | 13 | 20 | 12-10-2016 | 24-10-2017 | 377 | 240 | 740000 | 560929.45 | 2 | 539066.08 | 21863.37 | 104.0558 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project did not proceed according to the contractually foreseen only due to the non-compliance with deadlines by the executing entity. | eo in the amount of €1,400.04 and work not carried out in the amount of €23,263.41
3908 | 2515928 | SEC - PROC No. 99/A1/16 - Public Tender for the award of the contract for "Requalification of the Surroundings of Campo da Agonia". | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 28 | 10-10-2016 | 26-06-2017 | 259 | 120 | 220000 | 175955.15 | 1 | 175955.15 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the Tender Program | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3909 | 2515890 | Contract for repaving streets in Olhos de Água. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 26-09-2016 | 31-03-2017 | 186 | 60 | 330000 | 229000.32 | 1 | 229000.32 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline is due to delays on the part of the contractor.
3910 | 2514630 | Rehabilitation of the elementary school of Macinhata | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2017 | Portugal | Vale de Cambra | Aveiro | 1 | 30 | 16-08-2016 | 29-11-2017 | 470 | 180 | 274052.64 | 267938.93 | 2 | 269516.93 | -1578 | 99.4145 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | did not have.
3911 | 2507726 | SEC - PROC No. 100/A1/16 - Public Tender for the award of the contract for "Requalification of the Surroundings of the Nó do Náutico". | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 28 | 07-10-2016 | 29-11-2017 | 418 | 120 | 545000 | 490168.75 | 2 | 490168.75 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid Price: 40%; Technical value of Proposal: 60%. The subfactors are those set out in article 18 of the Tender Programme. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
3912 | 2504679 | Construction contract for the completion of the construction of the boat workshop at the Praia da Vitória fishing port, namely work on the roof, spans, telecommunications and voice power network | 45213252-4 | Workshops construction work | FALSE | 2015 | 2017 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 06-10-2016 | 25-05-2017 | 231 | 120 | 250000 | 212500.71 | 1 | 209126.67 | 3374.04 | 101.6134 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical Quality of the proposal - 60% (Work plan - 70% and Descriptive memory and justification for the execution of the work - 30%) | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline has been met | underwork
3913 | 2499785 | Requalification of the C.M. 1221 - Ponte da Pedra a Milagres | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 04-10-2016 | 13-01-2017 | 101 | 90 | 207547 | 199632.5 | 1 | 199632.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the deadline.
3914 | 2496197 | Public Contest No. 1-A1/2016 - The purpose of the contract is to replace the main distribution pipe in ductile cast iron (FFD), with a DN 400 mm diameter, of Reservoir R4, at streetNorton de Matos | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 02-09-2016 | 30-08-2017 | 362 | 180 | 304000 | 238112.68 | 1 | 238112.68 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Technical Quality of the Proposal - 55% and b) Price - 45%. These factors are, in turn, divided into different duly weighted sub-factors, according to the following: a) Technical Quality of the Proposal (QTP): a1) Work Plan (PT) - 35%; a2) Plan of human resources to be allocated to the work (PMH) - 35%; a3) Plan of technical means / equipment to be allocated to the work (PMTE) - 15%; a4) Justification and descriptive memory of the mode of execution of the work (MJD) - 15%. QTP = 35% x PT + 35% x PMH + 15% x PMTE + 15% x MJD. b) Price (P). to the factor of price assessment will be assigned a score equal to or less than 10. The classification, in this factor, is assigned by applying the following expression: If Proposal Value Vi > EUR375,000 Score (Proposal i) = 9 x (460,000 - Vi) / (460,000 - 375,000). If Value of Proposal Vi <= EUR375,000 Score (Proposal i) = 10 - (Vi / 375,000). Where: Score (Proposal i) - score to be assigned to the Price factor, with a maximum value of 10 points. Vi - proposal value i. Subfactors a1 to a4 will be evaluated according to the detailed in point 22.3 of the Tender Programme. The final classification will be given by the following formula: CF= 55% x QTP + 45% x P. Proceeding in descending order of proposals according to the classification obtained. | 1 | 45 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline set for the execution of the contract was exceeded due to the adverse weather conditions that occurred for long periods, which, associated with the great depth of the ditch and the high number of existing infrastructures in the artery, forced the contractor, for reasons of safety and precaution, to have a slower pace of work than anticipated in the project plan.
3915 | 2490867 | Conservation and Improvement of streets in the Municipality of Almada | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Almada | Setúbal | 17 | 12 | 30-08-2016 | 03-04-2017 | 216 | 90 | 228470 | 187975.68 | 1 | 187975.68 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work.
3916 | 2483924 | Contract to repave streets in Galé. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 27-09-2016 | 04-08-2017 | 311 | 60 | 338500 | 234857 | 1 | 234857 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it is due to delays on the part of the contractor. | no change
3917 | 2483325 | Repaving contract on Avenida Infante D. Henrique. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 28-09-2016 | 31-03-2017 | 184 | 60 | 195000 | 159499.6 | 1 | 159499.6 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the execution period is due to delay on the part of the contractor
3918 | 2465727 | Urban arrangements in Sendim, Atenor, Teixeira, Prado Gatão, Palaçoulo, Picote and Douro Barrocal | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 21-09-2016 | 15-11-2017 | 420 | 450 | 349860 | 328684.25 | 2 | 328684.25 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | favorable conditions for carrying out the project
3919 | 2462474 | Urban arrangements in Ifanes, Paradela, Constantim, Cicouro, São Martinho and Povoa | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 21-09-2016 | 25-10-2017 | 399 | 450 | 349994 | 330349.7 | 2 | 330349.7 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | favorable climate conditions for carrying out the projects
3920 | 2459888 | Urban developments in Vila Chã, Fonte de Aldeia, Freixiosa, Duas Aldeias, Cércio, Vale de Mira, São Pedro, Granja, Fonte Leão and Águas Vivas | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 21-09-2016 | 13-09-2017 | 357 | 450 | 349996 | 338700.5 | 2 | 338700.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | favorable weather conditions
3921 | 2454127 | CP4/2016 - Roads and Paving in the Municipality of Sabrosa: lot 1 in Ferrão a Donelo; Lot 2 1258 Gouvinhas on the edge of the municipality; Plot 3 IN 1267 - Celeirós to Paradelinha. | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Sabrosa | Vila Real | 19 | 10 | 22-09-2016 | 03-02-2017 | 134 | 60 | 387435 | 289550.76 | 2 | 289410.76 | 140 | 100.0484 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | time | underwork
3922 | 2444201 | Urban arrangements in different parts of the municipality of miranda do douro | 45233200-1 | Various surface works | FALSE | 2016 | 2017 | Portugal | Miranda do Douro | Bragança | 4 | 34 | 06-09-2016 | 25-09-2017 | 384 | 240 | 235000 | 227302.95 | 1 | 227302.95 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions not favorable to the project in question
3923 | 2442132 | Repair of Vessel Hauling Platform - Vila do Conde Naval Shipyards | 50246000-1 | Harbour equipment maintenance services | FALSE | 2016 | 2017 | Portugal | Vila do Conde | Porto | 13 | 3 | 05-09-2016 | 12-01-2017 | 129 | 90 | 220000 | 210313 | 1 | 271918.42 | -61605.42 | 77.3442 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | unspecified contingencies | unspecified contingencies
3924 | 2442049 | Repaving of the Patroves road. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 19-09-2016 | 23-11-2017 | 430 | 60 | 285000 | 199999.99 | 1 | 199999.99 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays by the contractor
3925 | 2441286 | Requalification of E.M. 532 E streetNossa Senhora de Fátima | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 04-08-2016 | 31-10-2017 | 453 | 180 | 456212.14 | 352678 | 2 | 352678 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension
3926 | 2425477 | Expansion and renovation of the building | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2016 | 2017 | Portugal | Loures | Lisboa | 11 | N/A | 21-06-2016 | 14-07-2017 | 388 | 75 | 386678.3 | 385986 | 2 | 385986 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Proposal price 40% Work plan 30% Execution time 30% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | nothing to report
3927 | 2416018 | Enhancement and promotion of a central space in Outeiro da Maceda, parish and municipality of Murtosa, which includes the construction of a playground, a playground, parking lots and a green area | 45112700-2 | Landscaping work | FALSE | 2016 | 2017 | Portugal | Murtosa | Aveiro | 1 | 24 | 13-09-2016 | 12-01-2017 | 121 | 120 | 202505.2 | 165986.5 | 1 | 165986.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ran smoothly
3928 | 2408522 | Execution of the urban garden of Aljezur | 45112712-9 | Landscaping work for gardens | FALSE | 2016 | 2017 | Portugal | Aljezur | Faro | 8 | 30 | 05-09-2016 | 14-07-2017 | 312 | 120 | 179001.6 | 166126.17 | 1 | 170698.26 | -4572.09 | 97.3215 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | during the project, there were two extensions of the project execution period - 60 days + 30 days. | there were more works worth €4,572.10
3929 | 2403900 | Year 2016_Contract for Rehabilitation of the Coverage of Services IV, Paintings of the Facade of the Northwest Wing and of the Exterior Wall of the Orthopedic Hospital of Sant`Ana, located at streetde Benguela | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2016 | 2017 | Portugal | Lisboa | Lisboa | 11 | 21 | 30-08-2016 | 13-04-2017 | 226 | 180 | 400000 | 290030.48 | 2 | 290030.48 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 27 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the availability of the space where the project was carried out delayed its assignment.
3930 | 2401803 | 2013.607.01.C1 - SE Porto - Refurbishment/expansion of the service area | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 22 | 01-04-2016 | 07-06-2017 | 432 | 120 | 330000 | 269639.98 | 2 | 280949.56 | -11309.58 | 95.9745 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional | additional
3931 | 2397620 | AA 2389 - S. Jorge Water Supply Subsystem. Subportela and Mujães reservoirs and respective supply connections (V. Castelo)". | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 41 | 12-08-2016 | 09-11-2017 | 454 | 420 | 2150000 | 1290000.01 | 3 | 1274747.45 | 15252.56 | 101.1965 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price 50% 2) Technical Value of the Proposal 50% | 1 | 50 | N/A | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | overwork and errors and omissions supply works.
3932 | 2394484 | Expansion of the primary school in Eiró | 45262700-8 | Building alteration work | FALSE | 2016 | 2017 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 11-08-2016 | 14-12-2017 | 490 | 360 | 587933.41 | 520000 | 2 | 516011.82 | 3988.18 | 100.7729 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project finished within the deadline. | underwork and price review .
3933 | 2389721 | Conservation of the Municipal Road Network - Paving of Estrada Donai to Vila Nova | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Bragança | Bragança | 4 | 20 | 31-08-2016 | 06-04-2017 | 218 | 120 | 281000 | 208596.5 | 1 | 207260.44 | 1336.06 | 100.6446 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (70% weighting) Technical quality of the proposal (30% weighting) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of deadline due to adverse weather conditions for the execution of horizontal signage. | underwork
3934 | 2385837 | Contract for improvements and repairs in a municipal building located in Lagoas - Ferreiras. | 45421130-4, 45442110-1 | Installation of doors and windows, Painting work of buildings | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 30-08-2016 | 13-06-2017 | 287 | 75 | 188127.47 | 150317.74 | 1 | 150317.74 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | part of the project was not available in time for the contractor to carry out the project
3935 | 2385773 | Pavement rehabilitation on Estrada do Casal Novo, street of Malta, crossstreet ofCasal Novo, street of Casal Novo, street of Casal do Quinta and streetBertolo Bastos, execution of the Domestic Wastewater Network | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2016 | 2017 | Portugal | Batalha | Leiria | 10 | N/A | 25-07-2016 | 25-05-2017 | 304 | 45 | 340000 | 266664.4 | 2 | 262119.72 | 4544.68 | 101.7338 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 3 extensions: 1st: 15 days. 2nd: 10 days: 3rd 88 days | additional work: €5,255.75 works less: -5,824.09 + -3,976.34€
3936 | 2385431 | The object of this contract is the construction of a domestic wastewater drainage system with about 2.6 km of gravity collectors, 100 home extensions, 3 pumping stations | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Murtosa | Aveiro | 1 | N/A | 16-08-2016 | 20-10-2017 | 430 | 180 | 950000 | 667317.82 | 2 | 667317.82 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 10%; Means Plan - 5%; Characterization and quality of equipment and materials - 10%) | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | there are no changes in the contracted and effective price
3937 | 2385189 | The object of this contract is the construction of a wastewater drainage system Households of about 6.8 km and a rainwater drainage system of approximately 1.00 m | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Estarreja | Aveiro | 1 | N/A | 01-08-2016 | 19-10-2017 | 444 | 180 | 950000 | 570000.01 | 2 | 553006.83 | 16993.18 | 103.0729 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 55%; Technical Value - 45% (Work execution methodology - 20%; Work Schedule - 7.5%; Means Plan - 7.5%; Characterization and quality of equipment and materials - 10%). | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
3938 | 2356011 | Street layouts in the parish of Vilarandelo" - (streetProfessora Amélia Castelo - section from km 0 of the M 213-1 to Largo do Toural) | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2017 | Portugal | Valpaços | Vila Real | 19 | 24 | 11-08-2016 | 11-09-2017 | 396 | 180 | 225129 | 170359.12 | 1 | 170359.12 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Provided for in point 17 of the program of procedure and in Annex VI: 1st - The award will be made to the most economically advantageous proposal, this being dedeadlineined by assessing two factors: Proposal (PP) and Technical Value of the Proposal (VTP). 2nd - The weighting coefficients for the two factors are, respectively, 75% and 25%. 3.º - The classification of proposals is carried out by applying the following formula: CP = PP x 75% + VTP x 25% 4th - Definition of concepts: a) Price of the Proposal under analysis (PPa) - is the algebraic addition of the value contained in the Main Form of the Proposal under analysis with the value assigned to supply the List of Errors and Omissions approved by the competent Body for the decision to hire, if applicable, and, occurring with the correction of account errors; b) Base Price (PB) - is the maximum price that the contracting authority is willing to pay for the execution of all the services that constitute the object of the contract to be signed, article 47 of the Public Contracts Code (CCP); c) Abnormally Low Price (PAB) - is the value set in the tender program, by reference to the base price set in the charges, from which the total price resulting from a proposal is considered abnormally low, article 132 of the CCP. d) Documents with Justification Clarifications - are the documents to be presented by the bidder with a proposal with price abnormally low, either accompanying the proposal or after notification, in writing, to provide clarifications within a suitable period justifications relating to the constituent elements of the proposal that it deems relevant for this purpose, paragraph d) of number 1 of article 57 and number 3 of article 71 of the CCP, respectively; e) Approximation of the score - the score to be assigned to each subfactor and factor is approximated to four decimal places. 5.º - Scoring of the Proposal Price, is carried out by applying the following formulas and the following rules: a) Formula 1, for proposals with prices within the following limits: less than or equal to the base price and greater than or equal to seventy percent (70%) of the base price: PP = 30 + (PB-PPa)/(0.30xPB) x 70 b) Proposals with an abnormally low total price, whose justifications have been considered under the deadlines of article 71 of the CCP, are punctuated by the application of Formula 2: PP = 100 + (PB-PPa)/(0.70xPB) x 5 c) Being: i) PP - score of the price of the proposal under consideration; ii) PB - base price; iii) PPa - price of the proposal under analysis; d) The scoring scale varies between thirty (30) and one hundred and five (105) points; e) Proposals that present a price are excluded: i) contract higher than the base price, under the deadlines of paragraph d) of number 2 of article 70 and paragraph o) of number 2 of article 146 of the CCP; ii) an abnormally low total, under the deadlines of paragraph e) of number 2 of article 70 and of paragraph d) and o) of number 2 of article 146 of the CCP, after verification pursuant to the provisions of article 71 of the CCP. 6 - The Technical Valuation of the Proposal is scored based on the analysis of the following three sub-factors: Work Plan (PT), Memory Justification and Description of the Work (MO) and Payment Plan (PG), with the respective weighting coefficients of 50%, 30% and 20%, using the following formula: VT = PT x 50% + MO x 30% + PG x 20% 7.º - The score for the Work Plan subfactor is obtained by analyzing the following three elementary subfactors: Work Map (MdT), Manpower Map (MMO) and Equipment Map (MEq), with the following weighting coefficients of 50%, 25% and 25%, using the following formula: PT=MdT x 50%+ MMO x 25%+MEq x 25% 8.º - The scoring scale for these elementary subfactors and subfactors varies between zero (0) and one hundred (100) points, according to the ordered set of different attributes likely to be proposed that allow the attribution of partial scores (descriptors - provided for in 9th to 13th of Annex VI of the procedural program). | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension - 90+30 days
3939 | 2355867 | Improvement of Av.ª dos Bombeiros, in Carrazedo de Montenegro | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2017 | Portugal | Valpaços | Vila Real | 19 | 24 | 18-08-2016 | 07-11-2017 | 446 | 180 | 362552.34 | 268288 | 2 | 268288 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Provided for in point 17 of the Program of Procedure and Annex VI: 1st - The award will be made to the most economically advantageous proposal, this being dedeadlineined by assessing two factors: Proposal (PP) and Technical Value of the Proposal (VTP). 2nd - The weighting coefficients for the two factors are, respectively, 75% and 25%. 3.º - The classification of proposals is carried out by applying the following formula: CP = PP x 75% + VTP x 25% 4th - Definition of concepts: a) Price of the Proposal under analysis (PPa) - is the algebraic addition of the value contained in the Main Form of the Proposal under analysis with the value assigned to supply the List of Errors and Omissions approved by the competent Body for the decision to hire, if applicable, and, occurring with the correction of account errors; b) Base Price (PB) - is the maximum price that the contracting authority is willing to pay for the execution of all the services that constitute the object of the contract to be signed, article 47 of the Public Contracts Code (CCP); c) Abnormally Low Price (PAB) - is the value set in the tender program, by reference to the base price set in the charges, from which the total price resulting from a proposal is considered abnormally low, article 132 of the CCP. d) Documents with Justification Clarifications - are the documents to be presented by the bidder with a proposal with price abnormally low, either accompanying the proposal or after notification, in writing, to provide clarifications within a suitable period justifications relating to the constituent elements of the proposal that it deems relevant for this purpose, paragraph d) of number 1 of article 57 and number 3 of article 71 of the CCP, respectively; e) Approximation of the score - the score to be assigned to each subfactor and factor is approximated to four decimal places. 5.º - Scoring of the Proposal Price, is carried out by applying the following formulas and the following rules: a) Formula 1, for proposals with prices within the following limits: less than or equal to the base price and greater than or equal to seventy percent (70%) of the base price: PP = 30 + (PB-PPa)/(0.30xPB) x 70 b) Proposals with an abnormally low total price, whose justifications have been considered under the deadlines of article 71 of the CCP, are punctuated by the application of Formula 2: PP = 100 + (PB-PPa)/(0.70xPB) x 5 c) Being: i) PP - score of the price of the proposal under consideration; ii) PB - base price; iii) PPa - price of the proposal under analysis; d) The scoring scale varies between thirty (30) and one hundred and five (105) points; e) Proposals that present a price are excluded: i) contract higher than the base price, under the deadlines of paragraph d) of number 2 of article 70 and paragraph o) of number 2 of article 146 of the CCP; ii) an abnormally low total, under the deadlines of paragraph e) of number 2 of article 70 and of paragraph d) and o) of number 2 of article 146 of the CCP, after verification pursuant to the provisions of article 71 of the CCP. 6 - The Technical Valuation of the Proposal is scored based on the analysis of the following three sub-factors: Work Plan (PT), Memory Justification and Description of the Work (MO) and Payment Plan (PG), with the respective weighting coefficients of 50%, 30% and 20%, using the following formula: VT = PT x 50% + MO x 30% + PG x 20% 7.º - The score for the Work Plan subfactor is obtained by analyzing the following three elementary subfactors: Work Map (MdT), Manpower Map (MMO) and Equipment Map (MEq), with the following weighting coefficients of 50%, 25% and 25%, using the following formula: PT=MdT x 50%+ MMO x 25%+MEq x 25% 8.º - The scoring scale for these elementary subfactors and subfactors varies between zero (0) and one hundred (100) points, according to the ordered set of different attributes likely to be proposed that allow the attribution of partial scores (descriptors - 9th to 13th of Annex VI of the Procedure Programme). | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the execution period (90+60+40 days)
3940 | 2347501 | Contract for Execution of Elevator Conduct for Water Supply to Torres Novas | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2016 | 2017 | Portugal | Torres Novas | Santarém | 16 | 24 | 15-07-2016 | 06-10-2017 | 448 | 120 | 320000 | 241112.68 | 1 | 232883.3 | 8229.38 | 103.5337 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | correction of execution defects detected during the inspection phase for provisional acceptance. | it was verified during the execution of the project that some of the projects foreseen in the initial contract were not necessary.
3941 | 2346797 | This contract includes landfilling and land modeling so that, at a later stage, the street layout for this section of the avenue can be built. | 45262310-7 | Reinforced-concrete work | FALSE | 2016 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 04-08-2016 | 10-11-2017 | 463 | 270 | 295836.13 | 257978.31 | 2 | 293765.48 | -35787.17 | 87.8178 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 60% Technical Quality of the proposal 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project had a work suspension notice, due to the temporary impossibility of fulfilling the contract, duly authorized. | a price review was carried out with definitive indices worth €782.57.
3942 | 2346694 | Sports Gym Academy - Costa | 45212225-9 | Sports hall construction work | FALSE | 2016 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 16-08-2016 | 21-08-2017 | 370 | 240 | 3884348.26 | 3588126.15 | 3 | 3579227.01 | 8899.14 | 100.2486 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50%; Technical value - 40%; Lead time - 10%. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the safety and health plan for the project was only communicated on 10/03/2017 and following the inspection notice for provisional acceptance on 06/01/2017, the contractor had to correct defects in the project, so was granted a period of 25 days. | existence of underwork due to the foreseen quantities not being used up.
3943 | 2340947 | Contract for the execution of wastewater drainage systems in the area surrounding Consul Dabney | 45232460-4 | Sanitary works | FALSE | 2016 | 2017 | Portugal | Horta | Região Autónoma dos Açores | 15 | 48 | 21-06-2016 | 29-09-2017 | 465 | 300 | 1392847.23 | 1298000 | 3 | 1179812.61 | 118187.39 | 110.0175 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: k1 - Price - 80% k2 - Technical value of the proposal - 10% k3 - Ecological value of the proposal - 10% | 1 | 80 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change in the execution period of the project | underwork
3944 | 2340093 | Contract No. 20/2016 - streets and Pavements in the Municipality - EM 1268 - Donelo a Vilela | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Sabrosa | Vila Real | 19 | 15 | 11-08-2016 | 10-01-2017 | 152 | 60 | 280312.5 | 186955.7 | 1 | 186430.7 | 525 | 100.2816 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this is in accordance with the consignment note.
3945 | 2335316 | Requalification of Schools that are part of the Afonso de Albuquerque Grouping of Schools and the Sé School Grouping | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2017 | Portugal | Guarda | Guarda | 9 | 9 | 05-08-2016 | 27-06-2017 | 326 | 60 | 358856.99 | 344000 | 2 | 344000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
3946 | 2310046 | Construction of a parking lot at Largo Piramide in Linda a Velha and rehabilitation of the surrounding streets . | 45233140-2 | Roadworks | FALSE | 2016 | 2017 | Portugal | Oeiras | Lisboa | 11 | N/A | 25-05-2016 | 23-01-2017 | 243 | 180 | 521000 | 364700.01 | 2 | 364700.01 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Cf = (Cp x 0.60 + Cvt x 0.40) x 10 and Cvt = Cpt x 0.60 + Cmeo x 0.40 On what Cf - Final classification of the proposal Cp - Price factor classification of the proposal Cvt - Classification of the technical value factor and technical feasibility of the proposal Cpt - Classification of the subfactor adequacy of the work plan to the planning and phasing of the work Cmeo - Classification of the work execution mode subfactor | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed on time.
3947 | 2309054 | Paving of Roads and streets | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Avis | Portalegre | 12 | 20 | 26-07-2016 | 30-01-2017 | 188 | 60 | 260000 | 180585.12 | 1 | 180585.12 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame.
3948 | 2303146 | The contract includes demolition work and preparatory work; pedestrian and road paving; supply and placement of street furniture; rainwater drainage network; distribution network. | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Barreiro | Setúbal | 17 | 20 | 07-04-2016 | 03-04-2017 | 361 | 120 | 700000 | 420002.13 | 2 | 282680.24 | 137321.89 | 148.5785 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Proposal price - 60% b) Quality of the proposal - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of definition of the public lighting project and delay by the owner of the project in cutting the water network for the execution of connections to the network | underwork
3949 | 2296236 | Requalification and Improvement of streets of the municipal road network | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2017 | Portugal | Guimarães | Braga | 3 | 20 | 15-07-2016 | 28-07-2017 | 378 | 180 | 2155579.18 | 2054959.65 | 3 | 2028468.68 | 26490.97 | 101.306 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | auto partial suspension of work 01: 1/26/2017; work restart notice 01: 02/20/2017 (25 days) auto partial suspension of work 02: 01/26/2017; auto reset works 02: 04/26/2017 (90 days). | existence of underwork due to the foreseen quantities not being used up.
3950 | 2295851 | Rehabilitation and requalification of the Leiria municipal housing station | 45216121-8 | Fire station construction work | FALSE | 2015 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 05-07-2016 | 27-07-2017 | 387 | 270 | 414530 | 344700 | 2 | 344700 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension.
3951 | 2288451 | Refurbishment of floors in the Municipal Swimming Pools Car Park - Silves | 45233251-3 | Resurfacing works | FALSE | 2016 | 2017 | Portugal | Silves | Faro | 8 | 30 | 29-06-2016 | 05-09-2017 | 433 | 120 | 292718 | 174464.35 | 1 | 170733.83 | 3730.52 | 102.185 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report | underwork
3952 | 2279643 | Refurbishment contract for the Almeirim / Alpiarça WWTP (inlet work and maturation pond) | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2016 | 2017 | Portugal | Alpiarça | Santarém | 16 | 24 | 24-06-2016 | 03-10-2017 | 466 | 120 | 300000 | 240000.01 | 1 | 232714.55 | 7285.46 | 103.1306 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the objective of the project was carried out in its entirety, not requiring the invoicing of all items.
3953 | 2279481 | Restoration contract for the rainwater drainage system on streetde Birre | 45262300-4, 45111000-8, 45112700-2, 45233200-1, 45111100-9, 45232410-9, 45262522-6 | Concrete work, Demolition, site preparation and clearance work, Landscaping work, Various surface works, Demolition work, Sewerage work, Masonry work | FALSE | 2016 | 2017 | Portugal | Cascais | Lisboa | 11 | 30 | 09-06-2016 | 06-06-2017 | 362 | 144 | 298799.85 | 196632.3 | 1 | 197191.61 | -559.31 | 99.7164 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PG = 0.9 x K1 + 0.1 x K2 (1) On what: K1 - Densification of the Price Factor and respective partial score, according to the following expressions: K1 = 175 - 125 x (VP/PB) (2) K1 = 50 x VP / (0.6xPB) (3) K2 - Densification of the Execution Time Factor and respective partial score, according to the following expressions: K2 = 300 - 250 x (PP/PM) (4) K2 = 50 x [PP / (0.8 x PM)] (5) Where: VP- Value of the proposal under consideration PB- Base price of the tender PP- Deadline for execution of the proposal under consideration PM- Maximum period established for the execution of the work | 1 | 90 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the conditions necessary for the intervention of the object of the contract are not met. | price review
3954 | 2274828 | Requalification of streetN.º Senhor dos Aflitos, Soutocico, Arrabal | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 20-06-2016 | 23-03-2017 | 276 | 180 | 223320 | 171999.38 | 1 | 146354.08 | 25645.3 | 117.5228 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of works | underwork
3955 | 2273028 | Maintenance dredging in Portinho de São Martinho do Porto | 45252124-3 | Dredging and pumping works | FALSE | 2016 | 2017 | Portugal | Alcobaça | Leiria | 10 | 14 | 01-07-2016 | 24-01-2017 | 207 | 69 | 610000 | 449000 | 2 | 408260 | 40740 | 109.9789 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Price (50%) scored using the function value represented in annex 4 to the tender program; b) Technical value (50%) assessed using the methodology set out in annex 4 to the tender program. The subfactors and respective qualitative analysis descriptors and respective weightings and scores, to be considered for the evaluation of the factor "Technical value of the proposal" are the following: a) Descriptive memory and justification of the execution of the work - 30%; b) Work plan - 5%; c) Labor plan - 5%; d) Equipment plan - 60%. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse maritime conditions that made navigability in safe conditions impossible. | quantities not dredged above the quotas defined by the project and which correspond to rocky outcrops, whose dismantling was not the object of this contract.
3956 | 2261556 | The contract includes the construction of the WWTP in Vale da Eira and Relvas Verdes. | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2016 | 2017 | Portugal | Santiago do Cacém | Setúbal | 17 | 21 | 14-06-2016 | 30-05-2017 | 350 | 150 | 175000 | 153518.76 | 1 | 149514.76 | 4004 | 102.678 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climatic conditions. | due to underwork, as it was verified that it was not necessary to carry out the amount foreseen in the design of the walls of gabião.
3957 | 2258754 | The object of this contract is the construction of a gravity network over a length of 1131m in PP DN200, 24 home extensions with the respective manholes and branch | 45232460-4 | Sanitary works | FALSE | 2015 | 2017 | Portugal | Águeda | Aveiro | 1 | N/A | 27-06-2016 | 14-11-2017 | 505 | 120 | 350000 | 229598.6 | 1 | 223351.58 | 6247.02 | 102.7969 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Price 55% 2) Technical Valuation of the Proposal 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
3958 | 2257889 | Execution of public works contract, with installation and supply of LEDs, to reduce the energy bill in the public lighting network | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2015 | 2017 | Portugal | Paredes | Porto | 13 | 20 | 20-06-2016 | 04-01-2017 | 198 | 30 | 342000 | 339873.73 | 2 | 339873.73 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unavailability to work
3959 | 2256828 | "Improvement and Repaving of CM 1103 from São João de Corveira to Junqueira and CM 1104 and CM 1103 to Vilarinho do Monte". | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Valpaços | Vila Real | 19 | 24 | 24-06-2016 | 26-07-2017 | 397 | 120 | 222251.88 | 168019.45 | 1 | 168019.45 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: In accordance with paragraph 17 of the Program of Procedure: a) The most economically advantageous proposal for the City Council, densified by the factors and sub-factors defined in Annex VI of the Procedure Program; b) The analysis and evaluation of the proposals will be carried out by the expressly appointed jury; c) If there are two or more proposals with the same score, the following tiebreaker is established: 1st - The proposal with the lowest price. If the tie still exists: 2nd - The proposal that obtains the best score in the "technical value" factor. If the tie still exists: 3.º - Proposals will be ordered by the order of entry on the platform. Annex VI of the Procedure Program: 1st - The award will be made to the most economically advantageous proposal, this being dedeadlineined by assessing two factors: Proposal (PP) and Technical Value of the Proposal (VTP). 2nd - The weighting coefficients for the two factors are, respectively, 75% and 25%. 3.º - The classification of proposals is carried out by applying the following formula: CP = PP x 75% + VTP x 25% 4th - Definition of concepts: a) Price of the Proposal under analysis (PPa) - is the algebraic addition of the value contained in the Main Form of the Proposal under analysis with the value assigned to supply the List of Errors and Omissions approved by the competent Body for the decision to hire, if applicable, and, occurring with the correction of account errors; b) Base Price (PB) - is the maximum price that the contracting authority is willing to pay for the execution of all the services that constitute the object of the contract to be signed, article 47 of the Public Contracts Code (CCP); c) Abnormally Low Price (PAB) - is the value set in the tender program, by reference to the base price set in the charges, from which the total price resulting from a proposal is considered abnormally low, article 132 of the CCP. d) Documents with Justification Clarifications - are the documents to be presented by the bidder with a proposal with price abnormally low, either accompanying the proposal or after notification, in writing, to provide clarifications within a suitable period justifications relating to the constituent elements of the proposal that it deems relevant for this purpose, paragraph d) of number 1 of article 57 and number 3 of article 71 of the CCP, respectively; e) Approximation of the score - the score to be assigned to each subfactor and factor is approximated to four decimal places. 5.º - Scoring of the Proposal Price, is carried out by applying the following formulas and the following rules: a) Formula 1, for proposals with prices within the following limits: less than or equal to the base price and greater than or equal to seventy percent (70%) of the base price: PP = 30 + (PB-PPa)/(0.30xPB) x 70 b) Proposals with an abnormally low total price, whose justifications have been considered under the deadlines of article 71 of the CCP, are punctuated by the application of Formula 2: PP = 100 + (PB-PPa)/(0.70xPB) x 5 c) Being: i) PP - score of the price of the proposal under consideration; ii) PB - base price; iii) PPa - price of the proposal under analysis; d) The scoring scale varies between thirty (30) and one hundred and five (105) points; e) Proposals that present a price are excluded: i) contract higher than the base price, under the deadlines of paragraph d) of number 2 of article 70 and paragraph o) of number 2 of article 146 of the CCP; ii) an abnormally low total, under the deadlines of paragraph e) of number 2 of article 70 and of paragraph d) and o) of number 2 of article 146 of the CCP, after verification pursuant to the provisions of article 71 of the CCP. 6 - The Technical Valuation of the Proposal is scored based on the analysis of the following three sub-factors: Work Plan (PT), Memory Justification and Description of the Work (MO) and Payment Plan (PG), with the respective weighting coefficients of 50%, 30% and 20%, using the following formula: VT = PT x 50% + MO x 30% + PG x 20% 7.º - The score for the Work Plan subfactor is obtained by analyzing the following three elementary subfactors: Work Map (MdT), Manpower Map (MMO) and Equipment Map (MEq), with the following weighting coefficients of 50%, 25% and 25%, using the following formula: PT=MdT x 50%+ MMO x 25%+MEq x 25% 8.º - The scoring scale for these elementary subfactors and subfactors varies between zero (0) and one hundred (100) points, according to the ordered set of different attributes likely to be proposed that allow the attribution of partial scores (descriptors - 9th to 13th of Annex VI of the Procedure Program). | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension of the deadline by 60 days. suspension of the project in 130 days. | there have been no changes to the price.
3960 | 2254355 | Improvement of the C.M. 1115, Between Milhazes and Faria. | 45233140-2 | Roadworks | FALSE | 2015 | 2017 | Portugal | Barcelos | Braga | 3 | 48 | 22-06-2016 | 29-12-2017 | 555 | 300 | 1714930 | 1543437.01 | 3 | 1539187.01 | 4250 | 100.2761 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (50%); b) Technical Valuation of the Proposal (50%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Interconnection/compatibility between Work Plans, Manpower Plan, "IC" Equipment Plan (25%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | june 16, 2017, july 17, 2017 and august 22, 2017. information as of june 16, 2017: in the part of the present work that takes place in rua dos artesãos, the owner of the project does not own a plot of land where a sidewalk is planned. on the other hand, there were complaints from residents, raising objections to the design of the project. it was necessary to stop the project to negotiate the ownership of the plot of land and decide on the claims. following the facts set out above, the contractor interrupted the project by order of the owner, as of june 16, 2017. it is proposed to approve a work suspension notice, for a period likely to be one month, as provided for in paragraph 2 of article 298 of the and paragraph b) of article 365 of the d.l. 18/2008. information as of july 17, 2017: in the part of the present work that takes place in rua dos artesãos, the conditions that determined the suspension of works since june 16, 2017 are maintained. - the owner of the project does not own a plot of land where a sidewalk is planned. - there were complaints from residents, raising objections to the design of the project. it is proposed to approve the maintenance of the situation of suspension of works, for an additional and probable period of one month, as provided for in paragraph 2 of article 298 of the and paragraph b) of article 365 of the d.l. 18/2008. information on the 22nd of august 2017: in the part of the present work that takes place in rua dos artesãos, the conditions that determined the suspension of works since june 16, 2017 are maintained. - the owner of the project does not own a plot of land where a sidewalk is planned. - there is still no definition of the changes to be introduced to the project. it is proposed to approve the maintenance of the situation of suspension of works, for an additional period and probably sixty days, as provided for in paragraph 2 of article 298 of the and paragraph b) of article 365 of the d.l. 18/2008. | they resulted from an impediment beyond the control of the municipality, thus, the demolition works of the existing pt and dismantling of the existing transformation station, provided for in articles 02.01.01 and article 09.21 were not carried out because the equipment had not been removed, a task that was incumbent on the edp.
3961 | 2248503 | Nursing home remodeling - farmhouse | 45215212-6 | Retirement home construction work | FALSE | 2016 | 2017 | Portugal | São Pedro do Sul | Viseu | 20 | N/A | 17-06-2016 | 15-11-2017 | 516 | 250 | 650000 | 500000.01 | 2 | 500000.01 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract was signed on 17/06/2016, however the consignment was suspended and, consequently, the start of the project, due to a pre-contractual litigation action brought by a competitor. the judicial procedures ran until february 2017, when a judicial decision was issued that considered the action totally unfounded, thus allowing the signing of the consignment notice on 02/21/2017.
3962 | 2245549 | 2014.117.01.C1 - Professional Training Services Tomar - Cover replacement | 45261213-0 | Metal roof-covering work | FALSE | 2015 | 2017 | Portugal | Tomar | Santarém | 16 | 21 | 15-07-2015 | 24-07-2017 | 740 | 150 | 505000 | 380918.1 | 2 | 380918.1 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | assignment of contractual position/assignment of contractual position
3963 | 2235298 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2016 | 2017 | Portugal | Aveiro | Aveiro | 1 | N/A | 12-05-2016 | 22-11-2017 | 559 | 365 | 249000 | 178750.84 | 1 | 178750.56 | 0.28 | 100.0002 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work completed before the contractual deadline | rounding
3964 | 2227519 | Requalification and improvement of several streets in the Parish of Caranguejeira, Union of Parishes of Santa Catarina da Serra and Chaínça and Union of Parishes of Santa Eufémia and Boa Vista | 45233220-7 | Surface work for roads | FALSE | 2015 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 17-05-2016 | 31-01-2017 | 259 | 180 | 421474 | 320511.72 | 2 | 310341.72 | 10170 | 103.277 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension | underwork
3965 | 2223624 | Contract for the adaptation work for the Munícipe store | 45259900-6 | Plant upgrade work | FALSE | 2016 | 2017 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 24 | 17-05-2016 | 29-03-2017 | 316 | 180 | 303000 | 181800.01 | 1 | 181800.01 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a delay of about 30 days in the beginning of the project, necessary for the execution of a structural reinforcement of the pillars and central beams of the slab of the upper floor adjoining the space of the municipality store. in addition to this delay in the project, there was also a delay of 60 days between the last situation of works and the provisional reception motivated by the deficiency found in the painting of the pavement
3966 | 2223058 | Construction of the Elementary School No. 1 in Camarate. | 45000000-7 | Construction work | FALSE | 2015 | 2017 | Portugal | Loures | Lisboa | 11 | 30 | 03-02-2016 | 14-07-2017 | 527 | 330 | 2600000 | 2079000 | 3 | 2079000 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: ai) Bid Price (PP) - 40% aii) Work Plan (PT) - 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to report
3967 | 2221599 | Year 2016_Contract work for the conservation and restoration of the Palace of the Marquês do Alegrete and Romantic Garden, for the installation of a Social Unit, in Quinta Alegre - Phase I | 45200000-9, 45000000-7 | Works for complete or part construction and civil engineering work, Construction work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | 21 | 31-05-2016 | 03-07-2017 | 398 | 365 | 1400000 | 927078.76 | 2 | 984694.96 | -57616.2 | 94.1488 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the period of execution of the project was 12 months. | the need to carry out additional work resulted in an increase in the cost of the project. underwork was also authorized under this procedure.
3968 | 2221360 | Execution of Nucleus 22 - Exterior Arrangements - Charneca de Caparica | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 19-05-2016 | 31-01-2017 | 257 | 150 | 357000 | 212111.18 | 1 | 193588.79 | 18522.39 | 109.5679 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 - "Technical Value of the Proposal" - (40%), with subfactors "Work Execution Plan" - 30 points and "Equipment and Manpower Means to be assigned to the Work" - 10 points; Factor 2 - "Proposal Price" - (60%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 29 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | underwork.
3969 | 2212814 | EGA-AR0007 - Contract to Execution of the Nutrient Removal Stage of the Mesão Frio WWTP | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2017 | Portugal | Peso da Régua | Vila Real | 19 | 49 | 18-05-2016 | 27-10-2017 | 527 | 420 | 240000 | 239485.12 | 1 | 239485.12 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the proposal, 60%; Price, 40% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | there were no changes to the value of the project
3970 | 2212420 | Construction of the São Jorge Judo pavilion | 45000000-7 | Construction work | FALSE | 2015 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 34 | 30-05-2016 | 27-03-2017 | 301 | 210 | 784906.96 | 783000 | 2 | 783000 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1: Price-40% Factor 2: Technical quality of the proposal-60% Subfactor 2.1: Work plan Subfactor 2.2: Descriptive memory and justification of the mode of execution of the work | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project only started after communication by the owner of the project of the approval of the development of the safety and health plan of the project.
3971 | 2210643 | Public Tender n.º 1/DRP/2016 Consolidation contract for the port of Santa Cruz da Graciosa - works to improve the operability and safety of the port | 45241100-9 | Quay construction work | FALSE | 2016 | 2017 | Portugal | Santa Cruz da Graciosa | Região Autónoma dos Açores | 15 | 36 | 27-05-2016 | 31-08-2017 | 461 | 240 | 500000 | 425000.01 | 2 | 372688.24 | 52311.77 | 114.0363 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40%; Technical quality of the proposal - 60% (Work plan 70% and Descriptive memory and justification for the execution of the work - 30%) | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work by order of 12/21/2016, for a period of 60 days, and by order of 03/30/2017, for a period of 30 days, resulting from sea conditions, which resulted in lack of safety conditions. | more work resulting from the amount needed to fill spaces and underwork resulting from restructuring the lighting network.
3972 | 2207754 | Year 2016_Remodeling and improvement contract for the reinstallation of home support services at Penha de França, n.º 193, D, E, F, in Lisbon | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-05-2016 | 30-01-2017 | 255 | 180 | 210000 | 177230.64 | 1 | 177230.64 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no extension of the execution period.
3973 | 2205260 | Contract for the Refurbishment and Adaptation of a House to the Headquarters Building of the Start Up of Angra do Heroísmo | 45210000-2 | Building construction work | FALSE | 2016 | 2017 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 20-05-2016 | 12-06-2017 | 388 | 180 | 208901.97 | 199100 | 1 | 185900.12 | 13199.88 | 107.1005 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Pursuant to clause 24 of the Procedure | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extensions | approval of errors and omissions and suppression of work
3974 | 2199253 | Requalification of José Estevão Street / Agostinho Pinheiro Street / Conselheiro Luís Magalhães Street | 45432110-8 | Floor-laying work | FALSE | 2016 | 2017 | Portugal | Aveiro | Aveiro | 1 | 22 | 16-05-2016 | 26-12-2017 | 589 | 120 | 294410.75 | 189662.88 | 1 | 193681.11 | -4018.23 | 97.9253 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | notice of suspension, notice of restart, term extensions (limitations/constraints during the course of the project and excessive delivery time practiced by the street furniture supplier provided for in the specifications of the project) | more work and underwork
3975 | 2188487 | Contract for the Requalification of the Exterior Surroundings of the FAUP Buildings | 45454000-4 | Restructuring work | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 48 | 04-05-2016 | 05-06-2017 | 397 | 224 | 460000 | 395062.95 | 2 | 340489.99 | 54572.96 | 116.0278 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Contract - score represented by VP, 40%; b) Technical value of the proposal - score represented by VT, 60%. | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | insufficient human resources, lack of timely supply of materials and preparation of the project. | due to the errors and omissions found and the impossibility of carrying them out in full due to exceeding the limits provided for in the "public procurement code".
3976 | 2184593 | Repaving, Cleaning and Arrangement of Berms and Gutters at CM 1285 from Pegarinhos to the limit of the Municipality of Alijó/ Murça | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2015 | 2017 | Portugal | Alijó | Vila Real | 19 | 20 | 06-05-2016 | 12-01-2017 | 251 | 180 | 299671.27 | 205546.89 | 1 | 194471.89 | 11075 | 105.6949 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was due to the fact that there was more work | more work worth €69,695.18
3977 | 2171609 | Requalification of Urban Space and remodeling of infrastructures, in a place that currently serves essentially as a car park. | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Coimbra | Coimbra | 6 | 30 | 14-10-2015 | 09-10-2017 | 726 | 240 | 613602.17 | 490463.58 | 2 | 472849.39 | 17614.19 | 103.7251 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline extensions | amount of price revision and work not performed
3978 | 2162180 | The present contract refers to the construction and/or reconstruction of retaining walls to protect slopes and/or municipal roads | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2017 | Portugal | Coimbra | Coimbra | 6 | 24 | 15-04-2016 | 14-11-2017 | 578 | 180 | 191228.3 | 174933.23 | 1 | 171543.23 | 3390 | 101.9762 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the project deadline | underwork and price revision
3979 | 2162143 | Contract work for paving streets in the Montechoro area. | 45233220-7 | Surface work for roads | FALSE | 2016 | 2017 | Portugal | Albufeira | Faro | 8 | 20 | 27-04-2016 | 31-03-2017 | 338 | 90 | 574400 | 344640.01 | 2 | 344640.01 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the deadline is due to delays on the part of the contractor
3980 | 2158756 | Requalification and Improvement of Several streets in the Union of Parishes of Leiria, Pousos, Barreira and Cortes - Municipality of Leiria | 45233220-7 | Surface work for roads | FALSE | 2015 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 30-03-2016 | 03-07-2017 | 460 | 180 | 395151 | 339793.57 | 2 | 250057.61 | 89735.96 | 135.8861 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspended. | underwork.
3981 | 2146127 | Requalification of streets in the Parishes of Torreira, Bunheiro and Monte | 45233142-6 | Road-repair works | FALSE | 2016 | 2017 | Portugal | Murtosa | Aveiro | 1 | 30 | 19-04-2016 | 04-01-2017 | 260 | 120 | 286028.6 | 197754.05 | 1 | 197754.05 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ran smoothly
3982 | 2140318 | The purpose of this contract is to carry out the contract for the remodeling of the water supply network in Bairro da Cavalinha, in the city of Olhão, under the terms and conditions established in the booklet | 45232151-5 | Water-main refurbishment construction work | FALSE | 2015 | 2017 | Portugal | Olhão | Faro | 8 | 30 | 28-03-2016 | 01-06-2017 | 430 | 240 | 349000 | 209400.01 | 1 | 202286.01 | 7114 | 103.5168 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The factors and subfactors accompanied by the respective weighting coefficients are indicated in the Procedure Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the causes were mainly due to the reduced number of workers on site | the project less in this contract was due to the identification of accessories foreseen in the project and not necessary in the project (ex: watering mouths)
3983 | 2129909 | The object of this contract is the construction of a gravity network over a length of 1670m in PP DN200, 82 home extensions with the respective manholes and branch | 45232460-4 | Sanitary works | FALSE | 2015 | 2017 | Portugal | Águeda | Aveiro | 1 | N/A | 29-03-2016 | 08-11-2017 | 589 | 120 | 245000 | 159722.22 | 1 | 154742.8 | 4979.42 | 103.2179 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price: 55% Technical Value: 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contractual deadlines by the contractor's responsibility | contracted works, not performed
3984 | 2127424 | Construction of Controlled Cost Housing in São João de Deus (EM.004.2015.136) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 30 | 01-04-2016 | 11-05-2017 | 405 | 240 | 585000 | 529937.76 | 2 | 523573.99 | 6363.77 | 101.2154 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical value of the proposal 30%; Subfactors (technical value of the proposal): Methodology 50%, work program 40% and safety 10%. | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in accordance with the contractually stipulated | additional work worth €11,599.90, errors and omissions worth €16,493.39 and unfinished work worth €34,457.06
3985 | 2126920 | Rehabilitation of the "Island" of Bela Vista - 2nd Phase (EM.004.2015.176) | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 30 | 01-04-2016 | 24-08-2017 | 510 | 270 | 810000 | 804980.34 | 2 | 762085.42 | 42894.92 | 105.6286 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 19 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension for 30 days. | work not carried out worth €27,127.71
3986 | 2115885 | Paving by E.M. 304 - Troviscous - merufe. Execution of floors in bituminous carpet. | 45432110-8 | Floor-laying work | FALSE | 2015 | 2017 | Portugal | Monção | Viana do Castelo | 18 | N/A | 14-03-2016 | 07-03-2017 | 358 | 210 | 297500 | 178500.01 | 1 | 195239.2 | -16739.19 | 91.4263 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no deadline change | additional work and price revision
3987 | 2112210 | 15Ep00001894 - Works contract for remodeling the electrical installation in the Palace of Justice of Oliveira de Azeméis | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2017 | Portugal | Oliveira de Azemeis | Aveiro | 1 | 12 | 18-03-2016 | 04-12-2017 | 626 | 90 | 230000 | 184450.86 | 1 | 191987.09 | -7536.23 | 96.0746 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes | project errors and omissions
3988 | 2085550 | Requalification of Largo Marquês de Pombal | 45223300-9 | Parking lot construction work | FALSE | 2015 | 2017 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 15-03-2016 | 13-03-2017 | 363 | 180 | 410465.01 | 336590.15 | 2 | 328298.1 | 8292.05 | 102.5258 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 60% - Technical Quality of the Proposed Solution 40% Descriptive memory and justification ............. 50% Work plan ...................................................... 40% Note justifying the proposed price .......... 10% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension | existence of underworks
3989 | 2085407 | Requalification of streetPadre Alfredo da Rocha Martins, Campo 25 de Abril and streetDr. Francisco Torres. | 45232451-8 | Drainage and surface works | FALSE | 2015 | 2017 | Portugal | Barcelos | Braga | 3 | 42 | 09-03-2016 | 21-04-2017 | 408 | 365 | 502165.89 | 466863.85 | 2 | 405500.03 | 61363.82 | 115.1329 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (50%); b) Technical Valuation of the Proposal (50%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Interconnection/compatibility between Work Plans, Manpower Plan, "IC" Equipment Plan (25%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | difference in the amounts foreseen and necessary to execute in the water supply chapter, the non-execution of node 5 - because it is outside the intervention area; adjustment to the layout of the project in the 25 de abril field.
3990 | 2081176 | Year 2015_ Contract to carry out rehabilitation works on the refectory, cafeteria and kitchen of the Casa do Pessoal of SCML | 45210000-2, 45200000-9, 45000000-7 | Building construction work, Works for complete or part construction and civil engineering work, Construction work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | 20 | 08-10-2015 | 07-03-2017 | 516 | 120 | 300000 | 298590.78 | 2 | 364399.95 | -65809.17 | 81.9404 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the need to perform additional work. | the need to perform additional work.
3991 | 2077150 | public work contract agreement casal vistoso municipal allotment i – 1st phase (streets armento beires and projected road b “to pt”) (public procurement procedure no. 1/2015/cp/jfa) | 45111290-7 | Primary works for services | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | 20 | 16-03-2016 | 09-08-2017 | 511 | 90 | 452979.44 | 315747.26 | 2 | 315747.26 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of the project contained in the files.
3992 | 2076398 | Commissioning contract for the fourth decantation line at the Guia WWTP Liquid Phase Treatment Station | 45232421-9 | Sewage treatment works | FALSE | 2014 | 2017 | Portugal | Cascais | Lisboa | 11 | 30 | 28-01-2016 | 15-11-2017 | 657 | 180 | 1150000 | 768105 | 2 | 762667.44 | 5437.56 | 100.713 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension associated with the delay in the supply of equipment.
3993 | 2076364 | Contract for the Improvement of the Entry Work of the WWTP in Guia - Replacement of Harrowing Equipment | 45232421-9 | Sewage treatment works | FALSE | 2014 | 2017 | Portugal | Cascais | Lisboa | 11 | 30 | 26-01-2016 | 15-11-2017 | 659 | 180 | 748000 | 448800.01 | 2 | 445778.15 | 3021.86 | 100.6779 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension associated with the delay in the supply of equipment.
3994 | 2057552 | Restoration and Rehabilitation of the Misericórdia Church in Leiria | 45454100-5 | Restoration work | FALSE | 2015 | 2017 | Portugal | Leiria | Leiria | 10 | N/A | 02-03-2016 | 02-01-2017 | 306 | 300 | 553246.79 | 436766.15 | 2 | 436766.15 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 23 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
3995 | 2054071 | campel mortuary | 45212360-7 | Religious buildings construction work | FALSE | 2015 | 2017 | Portugal | Baião | Porto | 13 | 31 | 15-01-2016 | 01-02-2017 | 383 | 365 | 258770.89 | 260360.43 | 2 | 260360.43 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Those contained in no. 14 of the Contest. | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there are no changes to the time for completion of the project. | there were no changes to the value of the project
3996 | 2045302 | Refurbishment of the Old Railway Station Building. The work consists of recovering and adapting the existing building, which has two floors, on the ground floor and 1st floor. | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2015 | 2017 | Portugal | Monção | Viana do Castelo | 18 | N/A | 04-01-2016 | 25-09-2017 | 630 | 365 | 370000 | 322656 | 2 | 328457.98 | -5801.98 | 98.2336 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 80% Guarantee/Exceptional Conditions for the work and its equipment - 20% | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to replace materials that were discontinued as well as safeguarding the supply of electricity to the building, and certification of the installation by certiel, necessary for the definitive energy connection. | as the project progressed, it was verified that some works were foreseen that were understood as unnecessary, as well as, for a good finish of the project, it was necessary to carry out some works that were initially not foreseen and were essential.
3997 | 2044721 | The contract comprises the execution of a wastewater drainage network in the Union of Parishes of Trofa, Segadães and Lamas do Vouga, with the objective of building a gravity network | 45232400-6 | Sewer construction work | FALSE | 2015 | 2017 | Portugal | Águeda | Aveiro | 1 | 40 | 29-02-2016 | 02-10-2017 | 581 | 365 | 1200000 | 720000.01 | 2 | 683039.82 | 36960.19 | 105.4111 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 55% Technical value: 45% | 1 | 55 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
3998 | 2037538 | Expansion of the basic sanitation network - arcos de valdevez (s. Paio) - section 4 and 5 | 45232411-6 | Foul-water piping construction work | FALSE | 2015 | 2017 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 24-02-2016 | 13-11-2017 | 628 | 180 | 382000 | 277306.05 | 2 | 277306.05 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: 50% - Lowest global price 50% - Technical value of the proposal These criteria are decomposed into sub-criteria, in accordance with article 12 of the procedural program | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline was extended by 180 days due to the delay in issuing the license to carry out work on the en 101 viaduct, by infraestruturas de portugal, s.a.
3999 | 2018056 | Rehabilitation of the Water Network in the Municipality of Velas/Borehole/Reservoirs/ Pumping Stations/Springs on the island of São Jorge | 45232460-4 | Sanitary works | FALSE | 2015 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 20 | 18-02-2016 | 30-11-2017 | 651 | 275 | 1299950.71 | 1250000 | 3 | 1250000 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 60% Price and 40% Technical Value of the Proposal. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | four requests for extension of the contract execution period.
4000 | 2013396 | Contract for the execution of the retention project to the south of the coastal protection of the section to the north of the fishing port of Maia | 45000000-7 | Construction work | FALSE | 2015 | 2017 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | N/A | 02-02-2016 | 02-03-2017 | 394 | 150 | 425000 | 419900 | 2 | 418858.55 | 1041.45 | 100.2486 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: (PF) Final Score = K = (0.4 x K1) + (0.6 X K2) On what: K1 = Score obtained in the bid price factor; K2 = Score obtained in the technical quality factor of the proposal. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions. | underwork.
4001 | 2009197 | 0044/DOM/DGEPIM/15 - Reformulation and reorganization of Av. Carolina Michaelis and Largo da Lagoa, in Linda-a-Velha | 45232460-4, 45432110-8, 45317300-5 | Sanitary works, Floor-laying work, Electrical installation work of electrical distribution apparatus | FALSE | 2015 | 2017 | Portugal | Oeiras | Lisboa | 11 | 61 | 01-02-2016 | 18-12-2017 | 686 | 180 | 226497.91 | 199222.46 | 1 | 199222.46 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Refer to article 27 of the Program of Procedure: CF= (0.60*F1+0.30*F2+0.10*F3)+10 | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4002 | 2005625 | Work related to the construction of Creche A Joaninha | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2015 | 2017 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 42 | 30-12-2015 | 05-09-2017 | 615 | 300 | 656700 | 613435.7 | 2 | 612583.02 | 852.68 | 100.1392 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1 - Price - 40%; K2 - Technical Quality of the Proposal - 60%. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | decree-law no. 6/2004, of january 6
4003 | 2005463 | Rehabilitation contract for eighteen vacant municipal buildings located in the municipality of Odivelas | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Odivelas | Lisboa | 11 | 30 | 15-01-2016 | 09-06-2017 | 511 | 90 | 370000 | 305000 | 2 | 301722.84 | 3277.16 | 101.0861 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Item 12 Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to inadequate planning by the construction contractor, the contractual period of 90 days was not complied with. | additional work worth €8,019.78. underwork worth €1740.03. errors and omissions amounting to €1423.09. contractual penalty in the amount of €10,980.00, for non-compliance with the contractual term.
4004 | 1997607 | Rehabilitation and adaptation of the building for the future National Guard facilities in Ericeira | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Mafra | Lisboa | 11 | 24 | 03-02-2016 | 27-11-2017 | 663 | 240 | 748129.46 | 649727.76 | 2 | 738554.88 | -88827.12 | 87.9728 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Overall price of the proposal (50%); b) Technical quality of the proposal (50%), divided by the following sub-factors: b.1) Descriptive memory and justification of the mode of execution of the contract, including description of the execution planning of the works, according to specifications (45%); b.2) Work Plan (20%); b.3) Labor Plan (17.5%); b.4) Equipment Plan (17.5%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the delay in signing the contract for the additional works | demolitions, constructions in reinforced concrete, reformulation of sidewalks
4005 | 1994651 | Construction of the Fontambom WWTP | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2017 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 27-01-2016 | 24-02-2017 | 394 | 180 | 391870.33 | 278953.79 | 2 | 284808.29 | -5854.5 | 97.9444 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
4006 | 1971835 | The object of this contract is the construction of the wastewater drainage network with a total length of 23,949 meters and 1,408 home branches with the respective manholes and outlets. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2015 | 2017 | Portugal | Ovar | Aveiro | 1 | N/A | 11-01-2016 | 19-09-2017 | 617 | 365 | 3100000 | 1962597.32 | 3 | 1953017.25 | 9580.07 | 100.4905 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value of the proposal - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
4007 | 1961023 | public works contract no. 48/dra/2015 for the "construction contract for reprofiling the ribeira da beira and construction of three hydraulic passages, on são jorge island" | 45220000-5 | Engineering works and construction works | FALSE | 2015 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 24 | 11-12-2015 | 30-01-2017 | 416 | 180 | 230000 | 199400 | 1 | 186080.37 | 13319.63 | 107.158 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made to the most advantageous whose criteria, factors, subfactors and weighting coefficients are those contained in the Procedure Program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the main cause that influenced the execution time of the project were the adverse weather conditions, which due to the rain, water flowed in the ribeira bed and prevented the continuation of the projects. it should also be noted that most of the project took place in the winter season. | underwork
4008 | 1951014 | streets of Fish Packing and Packing Units - Matosinhos Fishing Port | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Matosinhos | Porto | 13 | N/A | 31-12-2015 | 10-02-2017 | 407 | 150 | 350000 | 248287.5 | 1 | 285822.8 | -37535.3 | 86.8676 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% deadline 5% Descriptive Memory 20% Work Plan 15% Labor Plan 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4009 | 1943538 | Refurbishment and rehabilitation of the feijó municipal market | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 17-12-2015 | 13-06-2017 | 544 | 180 | 533497 | 529857.3 | 2 | 524123.31 | 5733.99 | 101.094 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1 "Technical value of the Proposal" - (40%), with the subfactors "Work execution plan" - 30 points and "Equipment and manpower to be assigned to the work" - 10 points.' Factor 2 - "Proposal Price" - (60%). | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | underwork.
4010 | 1930039 | Refurbishment of interior spaces and public areas at elementary school nº 3 in laranjeiro and elementary school nº 1 in monte de caparica | 45236290-9 | Repair work on recreational areas | FALSE | 2015 | 2017 | Portugal | Almada | Setúbal | 17 | 24 | 03-12-2015 | 31-10-2017 | 698 | 150 | 335000 | 287267.06 | 2 | 277856.94 | 9410.12 | 103.3867 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | underwork.
4011 | 1917232 | Conservation and Maintenance Contract for Municipal Roads in the Municipality of Leiria | 45233141-9 | Road-maintenance works | FALSE | 2015 | 2017 | Portugal | Leiria | Leiria | 10 | 20 | 22-12-2015 | 20-01-2017 | 395 | 365 | 200000 | 154789.66 | 1 | 151988.91 | 2800.75 | 101.8427 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
4012 | 1914959 | Contract for paving streets in the Municipality of Tavira | 45233220-7 | Surface work for roads | FALSE | 2015 | 2017 | Portugal | Tavira | Faro | 8 | 30 | 18-12-2015 | 17-11-2017 | 700 | 210 | 308747.57 | 213343.04 | 1 | 198307.53 | 15035.51 | 107.5819 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: In accordance with the provisions of article 9 of the Procedure Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extension for 3 days due to the communication of the approval of the pss on 02/04/2016 and delivery of the technical compilation. | underwork worth -420.00€ and price revision worth (-) 14,615.51€.
4013 | 1902127 | Work contract for the installations of the Lar do Reconhecimento de Jesus Maria José | 45215200-9 | Construction work for social services buildings | FALSE | 2015 | 2017 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 27-11-2015 | 24-04-2017 | 514 | 450 | 1724775.3 | 1466059.02 | 3 | 1466059.02 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1 - Price - 40% K1 = (Pb - Pp) x 20 /Pb On what: Pb = base price and Pp = price of the proposal under evaluation K2 - Technical quality of the proposal - 60% K2 = (0.70xK2.1) + (0.3xK2.2) On what: K2.1 = score assigned to the sub-factor "Work plan" K.2.2 = score assigned to the subfactor "Descriptive memory and justification of the way the work was carried out" | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4014 | 1885058 | Enlargement and improvement in the cemetery of loulé - retaining wall to stabilize the slope and reinforce surface drainage | 45232460-4, 45111230-9 | Sanitary works, Ground-stabilisation work | FALSE | 2015 | 2017 | Portugal | Loulé | Faro | 8 | 30 | 09-12-2015 | 06-01-2017 | 394 | 150 | 216000 | 187081.04 | 1 | 187081.04 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4015 | 1873037 | The object of the contract is to carry out work defined as to its type, quantity and technical conditions of execution, in the project and in the specifications | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Amadora | Lisboa | 11 | 30 | 30-11-2015 | 18-05-2017 | 535 | 120 | 304173.97 | 299230.93 | 2 | 299230.93 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The final score, assigned to each competitor, is given by the formula: PF=0.35*Pi+0.65*VTi On what: PF - Final score Pi - Score corresponding to the price of competitor i VTi - Score corresponding to the Technical Valia of competitor i Assessment of Factors and Subfactors: "Price" Factor The score will be from 0 to 100, and the values ​​will be calculated according to the following formula: Pi = ((Base Price - Competitor Price i) / Base Price) * 100 Where Pi corresponds to the score assigned to the price presented by competitor i. Factor "Technical Value" Technical Valia is evaluated according to the following subfactors: a) Quality and Adequacy of the Descriptive Memory: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: Very well-crafted descriptive memory, with a detailed description of the work to be carried out, focusing on constructive aspects important, making possible a great ease of interpretation. The Descriptive Memory reveals a deep analysis of the project and of the work to be carried out: MDi=100; Descriptive Memory prepared with details of the work to be carried out, focusing on important constructive aspects, making it possible, with some ease, the interpretation of the work to be carried out. The Descriptive Memory reveals some care in the analysis of the project and the work to be perform: MDi=65; Descriptive Memory with reference to the work carried out, focusing on constructive aspects of a general nature, referring to some means human and equipment affections although without great detail. Some constructive aspects are focused, without a great degree of detail: MDi=30; Descriptive Memory without any detail or detail, limited only to a summary description. Does not introduce or focus any constructive aspect of great interest: MDi=0. b) Work Plan: The classification will be from 0 to 100, and the values ​​assigned according to the following scale: It presents a Work Plan with a correct sequence, with detailed detail and interconnection between activities: PTi=100; It presents a Work Plan with a correct sequence, with some details of the work to be carried out, allowing thus an interpretation of the interconnection between activities: PTi=65; It presents a Work Plan that is not very detailed, making it difficult to analyze the development of the work to be carried out: PTi=30; It presents a Work Plan without details, not allowing the analysis of the development of the works to be carried out: PTi=0. The formula to be applied will be: VTi = MDi * 0.70 + PTi * 0.30 On what: VTi is the score corresponding to the Technical Valia of competitor i; MDi is the score corresponding to the quality and suitability of the Descriptive Memory of competitor i; PTi is the score corresponding to the Work Plan of competitor i. In the event of equal punctual classification of competitors, the tiebreaker will be made by the following method: An advantage will be attributed to the proposal with the best classification in the Price factor. In the event of a tie, the proposal submitted first will win. | 1 | 35 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline initially foreseen in the contract was exceeded for several reasons, which i will now list: rainfall conditions conditioned the progress of the projects, having interrupted the projects on several occasions, namely in the following works: opening of box; execution of the foundation and placement of border curbs to the existing pavement; placement and compaction of the support layer (tout-venant); colored bituminous layer. since the path of the runway is in an urban area with a lot of pedestrian and road traffic, which made the progress of the project very difficult and forced a more careful execution in certain more sensitive sections, reducing the predicted pace. this is a particularly sensitive situation as it makes it impossible to access the buildings - the runway was developed, mostly next to them, forcing the execution of sections of reduced length. need to change the location of urban furniture and public lighting poles. detail geometric alterations due to non-existent or inaccurate registration. intervention next to a classified monument and need for careful removal of constructions attached to it - águas livres aqueduct.
4016 | 1857222 | UP Museum Contract - Partial Intervention I | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 36 | 16-11-2015 | 06-09-2017 | 660 | 240 | 592475.02 | 525000 | 2 | 568488.25 | -43488.25 | 92.3502 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Contract - score represented by VP -- 40%; b) Technical value of the proposal - score represented by VT -- 60%. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | request for graceful extension of term. | additions and decreases mentioned.
4017 | 1855756 | Construction of the House of Memory of Sephardic Medicine António Ribeiro Sanches | 45210000-2 | Building construction work | FALSE | 2015 | 2017 | Portugal | Penamacor | Castelo Branco | 5 | 39 | 24-11-2015 | 21-06-2017 | 575 | 330 | 284066.11 | 273001.97 | 2 | 275111.22 | -2109.25 | 99.2333 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | work completed on november 18, 2016, due to overwork. | value of normal work: €261,206.09; underwork: €11,795.28; additional work: €4,594.35; errors and/or omissions: €9,310.78.
4018 | 1848551 | Contract for Requalification of Building for Day and Night Center in Cinco Ribeiras | 45215200-9 | Construction work for social services buildings | FALSE | 2015 | 2017 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 28-10-2015 | 31-07-2017 | 642 | 420 | 1350000 | 1147500 | 3 | 1213531.71 | -66031.71 | 94.5587 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 40% Technical Quality of the Proposal - 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | article 13, decree-law no. 6/2004, of 6 january. | articles 376.º and 379.º, "public procurement code".
4019 | 1848330 | Contract for Road Layouts to be Intervened in the Municipality of Aveiro - Phase 2 | 45233142-6 | Road-repair works | FALSE | 2015 | 2017 | Portugal | Aveiro | Aveiro | 1 | 22 | 17-11-2015 | 06-12-2017 | 750 | 120 | 271355.67 | 189585.73 | 1 | 174216.87 | 15368.86 | 108.8217 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | objective modification of the contract at praceta dr. alberto souto - alteration of the flooring to be applied | new consideration of the existing circumstances - replacement of the permeable pavement with an impermeable pavement layer.
4020 | 1847604 | Work Contract for the Construction of a Building for a Day Center for the Elderly/Playroom | 45215221-2 | Daycare centre construction work | FALSE | 2014 | 2017 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 48 | 11-09-2015 | 05-07-2017 | 663 | 400 | 1165830 | 847984.44 | 2 | 850747.9 | -2763.46 | 99.6752 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1 - Price - 40% K1 = (Pb - Pp) x 20 / Pb Where: Pb = base price and Pp = price of the proposal under evaluation K2 - Technical quality of the proposal - 60% K2 = (0.70xK2.1) + (0.30xK2.2) Where:: K2.1 = score assigned to the sub-factor "Work plan" K2.2 = score assigned to the subfactor "Descriptive memory and justification of the way the work was carried out" | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4021 | 1841792 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2015 | 2017 | Portugal | Aveiro | Aveiro | 1 | N/A | 19-10-2015 | 13-09-2017 | 695 | 730 | 248000 | 229023.58 | 1 | 229023.58 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work was completed ahead of schedule. there is nothing to report.
4022 | 1829174 | The contract works essentially consist of the following: a) Construction site assembly and disassembly; b) Civil construction work, supply and assembly of electromechanical equipment | 45247270-3 | Reservoir construction works | FALSE | 2015 | 2017 | Portugal | Bragança | Bragança | 4 | 20 | 03-11-2015 | 12-01-2017 | 436 | 150 | 200000 | 168900.03 | 1 | 173690.34 | -4790.31 | 97.242 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical value of the proposal - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | adjustment of quantities of work planned due to the characteristics of the foundation soils. it forced changes to the amount of work carried out on the foundations of the reservoir and the maneuvering chamber in freixeda.
4023 | 1814111 | Requalification of the municipal road in about 2.6 km with installation of a rainwater network, paving with bituminous masses and signaling | 45233200-1 | Various surface works | FALSE | 2015 | 2017 | Portugal | Amarante | Porto | 13 | 30 | 06-11-2015 | 04-12-2017 | 759 | 150 | 382000 | 293766.07 | 2 | 272366.65 | 21399.42 | 107.8568 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | rectification of the project and intervention by other entities | negative price review
4024 | 1769639 | Exterior Improvement of the Machado Vaz Neighborhood (Blocks 24 to 36) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2017 | Portugal | Porto | Porto | 13 | 21 | 06-11-2015 | 29-10-2017 | 723 | 365 | 3450000 | 3163586.05 | 3 | 3093496.81 | 70089.24 | 102.2657 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in accordance with the contractually stipulated | eo in the amount of €93,324.98, works deleted in the amount of €16,324.80 and underwork in the amount of €147,089.42
4025 | 1737735 | Maintenance Dredging of the Port of Aveiro | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2017 | Portugal | Ílhavo | Aveiro | 1 | 28 | 26-10-2015 | 10-04-2017 | 532 | 730 | 1995000 | 1855350 | 3 | 1806623.75 | 48726.25 | 102.6971 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 0.65; Execution Quality Assurance: 0.35. | 1 | 65 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the maximum amount of dredged material to be removed, provided for in the contract, was met. | pricing review.
4026 | 1737304 | Construction of the Maureles WWTP | 45232421-9 | Sewage treatment works | FALSE | 2015 | 2017 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 23-10-2015 | 24-01-2017 | 459 | 150 | 287915.4 | 229428.17 | 1 | 229428.17 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nº1 of article 359 of the "public procurement code" - administrative possession of the land for the implementation of the wwtp. | negative interim price revision
4027 | 1693378 | The object of the contract is the requalification of the Vouzela campsite | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2015 | 2017 | Portugal | Vouzela | Viseu | 20 | 12 | 13-10-2015 | 29-11-2017 | 778 | 210 | 380000 | 368171.83 | 2 | 324388.91 | 43782.92 | 113.497 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the contractually established period. | the change in the value of the project is due to the fact that underwork has taken place, in terms of the information that was the basis for the deliberation of the municipality of vouzela.
4028 | 1673438 | Work contract for the requalification and expansion of the Senhora da Piedade Home for the Elderly | 45215212-6 | Retirement home construction work | FALSE | 2014 | 2017 | Portugal | Lajes do Pico | Região Autónoma dos Açores | 15 | 48 | 14-04-2015 | 06-10-2017 | 906 | 360 | 590000 | 585132.18 | 2 | 576000.11 | 9132.07 | 101.5854 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | article 379, "public procurement code".
4029 | 1666896 | Construction of a multi-functional building | 45211350-7 | Multi-functional buildings construction work | FALSE | 2015 | 2017 | Portugal | Fafe | Braga | 3 | 21 | 13-10-2015 | 17-01-2017 | 462 | 90 | 747622.3 | 697523.77 | 2 | 697522.05 | 1.72 | 100.0002 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was partial suspension of work | the value of €1.72 is due to rounding
4030 | 1654930 | Maintenance Dredging of the Port of Figueira da Foz | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2017 | Portugal | Figueira da Foz | Coimbra | 6 | 31 | 08-10-2015 | 11-11-2017 | 765 | 730 | 1165600 | 1103700 | 3 | 1062433.02 | 41266.98 | 103.8842 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 0.65; Execution Quality Assurance: 0.35. | 1 | 65 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the contractual period. | price review
4031 | 1650535 | Ar 2337 - contract for the requalification of wastewater pumping stations in viana do Castelo - 1st phase | 45232431-2 | Wastewater pumping station | FALSE | 2014 | 2017 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 40 | 04-09-2015 | 06-12-2017 | 824 | 120 | 249000 | 235388.64 | 1 | 202983.8 | 32404.84 | 115.9642 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Overall price 50% 2) Technical value of the proposal 50% | 1 | 50 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without changes | over and underwork
4032 | 1592160 | Contract for: "Execution of bituminous concrete carpet on streets in the municipality of Benavente" | 45233252-0 | Surface work for streets | FALSE | 2015 | 2017 | Portugal | Benavente | Santarém | 16 | 30 | 18-09-2015 | 17-05-2017 | 607 | 75 | 228400 | 160903.6 | 1 | 160903.6 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the deadline, however the provisional reception was scheduled later.
4033 | 1585432 | Public Contest No. 2-A1/2015 - The purpose of the contract is the milling and replacement of pavements in interventions on the Water Supply Network | 45233222-1 | Paving and asphalting works | FALSE | 2015 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 18-09-2015 | 12-01-2017 | 482 | 365 | 204000 | 178750 | 1 | 178750 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Technical Quality of the Proposal - 60%; B) Price - 40% These factors are, in turn, divided into different duly weighted sub-factors, according to the following: a) Technical Quality of the Proposal (QTP): a1) Number of staff assigned to carry out the tasks per work front (QP) - 20%;a2) Quantity of equipment to be assigned to the work per work front (QE) - 35%;a3) Number of work fronts in simultaneous (FT) - 45%. QTP = 20% x QP + 35% x QE + 45% x FT. b) Price (P). P = (Pb - Vp) / Pb, where: Pb - Base Price; Vp - Proposal Value. P = 0.4 - if 0 < Vp < Pab, where:Pab - Abnormally low price (<40% Pbase). The subfactors a1) to a3) will be evaluated in accordance with what is described in point 22.3 of the Tender Programme. The final classification will be given by the following formula: CF= 60% x QTP + 40% x P. Proposals are sorted in descending order according to the classification obtained. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a greater number of unexpected breakdowns according to their history, so there was a need for more frequent interventions to solve problems on the pavements in the municipality's arteries.
4034 | 1566681 | Contract 3/GEBALIS/2015 - Public Tender Contract for the Maintenance and Repair of Houses and Common Areas in Neighborhoods in the North West Zone, in Lisbon | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | N/A | 28-07-2015 | 07-06-2017 | 680 | 730 | 600000 | 479220.74 | 2 | 536682.95 | -57462.21 | 89.2931 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | TRUE | N/A
4035 | 1561945 | eb1 construction - n.º 2 of vialonga | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2017 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 30-06-2015 | 24-07-2017 | 755 | 330 | 2670000 | 1981994.9 | 3 | 1948060.02 | 33934.88 | 101.742 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1 - The Bid Price - 65% | 1 | 65 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change of completion date of the project to 9/5/2016 | approval of work proposals
4036 | 1560936 | Construction of the Agricultural Path of Beira do Massapez | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2017 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 21 | 28-08-2015 | 08-03-2017 | 558 | 270 | 2580268.72 | 417348.34 | 2 | 401028.5 | 16319.84 | 104.0695 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4037 | 1560928 | Construction of the East Section Agricultural Path | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2017 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 21 | 28-08-2015 | 08-03-2017 | 558 | 210 | 2580268.72 | 418387.61 | 2 | 379219.12 | 39168.49 | 110.3287 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4038 | 1560913 | Construction of agricultural path | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2017 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 21 | 28-08-2015 | 08-03-2017 | 558 | 365 | 2580268.72 | 900447.69 | 2 | 789725.85 | 110721.84 | 114.0203 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4039 | 1560876 | Construction of agricultural path | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2017 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 21 | 28-08-2015 | 08-03-2017 | 558 | 360 | 2580268.72 | 457044.79 | 2 | 442273.19 | 14771.6 | 103.3399 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4040 | 1559051 | Requalification of the streets of CERCIAG, Carmeleiras de Cima, Pinhal das Cabanas and street of Poalho_x000D_ _x000D_ | 45233252-0 | Surface work for streets | FALSE | 2015 | 2017 | Portugal | Águeda | Aveiro | 1 | 30 | 10-09-2015 | 01-02-2017 | 510 | 100 | 201658.75 | 168474.35 | 1 | 161832.76 | 6641.59 | 104.104 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for the contract has changed due to the extension of the deadline due to more work and suspension of the project. | more work, underwork and price revision
4041 | 1520403 | Loreto School Center (Eiras) - Expansion | 45210000-2 | Building construction work | FALSE | 2012 | 2017 | Portugal | Coimbra | Coimbra | 6 | 18 | 04-03-2015 | 04-10-2017 | 945 | 360 | 1688473.99 | 1358343.33 | 3 | 1255866.1 | 102477.23 | 108.1599 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed on schedule, with the exception of tests on special installations and technical training for building users. | approval of underwork and correction of errors and omissions
4042 | 1515728 | Contract 01/GEBALIS/2015 - Public tender for Maintenance and Repair of Fires and Common Areas in Neighborhoods in the North East Zone of Lisbon | 45453100-8 | Refurbishment work | FALSE | 2015 | 2017 | Portugal | Lisboa | Lisboa | 11 | N/A | 22-07-2015 | 19-04-2017 | 637 | 730 | 600000 | 419735.26 | 2 | 440718.03 | -20982.77 | 95.239 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | TRUE | N/A | it went on normally
4043 | 1512308 | Miscellaneous demolition work, namely coatings, sewage and electricity installations, benches, spans, reinforced concrete slab for the implementation of a vertical connection | 45213141-3 | Covered market construction work | FALSE | 2015 | 2017 | Portugal | Sesimbra | Setúbal | 17 | 24 | 20-05-2015 | 06-01-2017 | 597 | 180 | 467423.98 | 464815.19 | 2 | 484502.45 | -19687.26 | 95.9366 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: See point 16 of the Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contract modification | work more to less and supply of errors and omissions
4044 | 1499597 | Structural renovation of the roof, conservation and restoration of the coffers and other decorative elements on the ceiling and walls of the Church of Santa Bárbara, parish of Manadas | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2014 | 2017 | Portugal | Velas | Região Autónoma dos Açores | 15 | 21 | 08-07-2015 | 02-06-2017 | 695 | 365 | 450000 | 399700 | 2 | 460889.27 | -61189.27 | 86.7237 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor 1: Technical Quality of the Proposal - 60%; Subfactor 1.1: Work Plan - 70%; Subfactor 1.2: Descriptive and Justification Memory - 30%. Factor 2: Price - 40% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the dismantling of the chancel's ceiling uncovered another, similar to the nave's ceiling, in carved cedar wood, in the mudéjar style, and with some very interesting curiosities, namely the representation of the church's patron saint, santa bárbara, in one of the coffers. the set was in poor condition, with many elements missing and at risk of falling. it was decided to carry out the intervention at the level of the structure and due documentation for the future, with the original roof remaining covered by the current roof; | the amount refers to the restoration work on the ceiling in the 'mudéjar' style found in the chancel and intervention in the lines of the central nave and chancel.
4045 | 1489520 | Execution of the contract for "Requalification of the streets Dr. Cândido Pinho, António Martins Soares Leite and Olival, and avenues 5 de Outubro and Monumento - Santa Maria da Feira | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2015 | 2017 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 26-06-2015 | 05-05-2017 | 679 | 150 | 354740 | 212844.02 | 1 | 238131.08 | -25287.06 | 89.381 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (P) - 60%; and b) Technical Quality of the Proposal (QTP) - 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance by the contractor, despite various requests. extension of the period between the 1st provisional reception (10/10/2016) and the final (05/03/2017) for correction of defects of a physical and documentary nature. | additional work relating to situations whose details could not have been foreseen or marked out, namely the adaptation of the threshold levels of the houses/parking bays and the reinforcement of paving in some parts of the project. ununderwork resulted from lags in measurements (surplus) or which, for various reasons, became expendable.
4046 | 1475754 | Vertical Signage 2015 – Lot V | 45233294-6 | Installation of road signals | FALSE | 2014 | 2017 | Portugal | Setúbal | Lisboa | 11 | 49 | 29-05-2015 | 26-07-2017 | 789 | 365 | 6000000 | 999691.97 | 2 | 973185.62 | 26506.35 | 102.7237 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | resulting from the elaboration of bill of quantities | resulting from the elaboration of bill of quantities
4047 | 1470067 | Road marking 2015 - lot 6 | 45233142-6 | Road-repair works | FALSE | 2015 | 2017 | Portugal | Beja | Faro | 8 | 48 | 18-05-2015 | 26-05-2017 | 739 | 180 | 6000000 | 637662.78 | 2 | 615760.8 | 21901.98 | 103.5569 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the graceful extension of the contract's execution period for 95 days was requested due to the constant difficulties in maintaining the subcontracted teams and due to adverse weather conditions, more precisely precipitation, high levels of humidity and low temperatures that contradicted a quick drying of the pavement in order to allow the normal progress of the projects, with quality and in compliance with the appropriate safety conditions. | the change in the value of the project resulted from the determination of positive errors and omissions correction work in the amount of €117,362.02 and negative errors and omissions correction work in the amount of €139,264.01
4048 | 1466423 | Reformulation of the exterior spaces of eb1 nº 111 - são joão de brito | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2017 | Portugal | Lisboa | Lisboa | 11 | 21 | 27-05-2015 | 28-07-2017 | 793 | 210 | 360915.25 | 289000.03 | 2 | 292268.68 | -3268.65 | 98.8816 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Refer to point 14 of the Program of Procedure | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4049 | 1446693 | Paving of section of CM 1079 and section of CM 1080 - Vale Fuzeiros | 45233222-1 | Paving and asphalting works | FALSE | 2014 | 2017 | Portugal | Silves | Faro | 8 | N/A | 19-03-2015 | 05-05-2017 | 778 | 90 | 395700 | 276989.1 | 2 | 276989.1 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | free extension granted | value of the project unchanged. price revision with negative value.
4050 | 1442442 | “Refurbishment of the Old Mafra Volunteer Firefighters Building”. | 45454000-4 | Restructuring work | FALSE | 2015 | 2017 | Portugal | Mafra | Lisboa | 11 | N/A | 28-04-2015 | 23-03-2017 | 695 | 150 | 1100399.58 | 1100000 | 3 | 1100000 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Overall price of the proposal (50%); b) Technical quality of the proposal (50%) | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | resolution of structural solutions. | does not exist.
4051 | 1437115 | Repaving of a rural path | 45233220-7 | Surface work for roads | FALSE | 2015 | 2017 | Portugal | Almeida | Guarda | 9 | 20 | 13-04-2015 | 30-08-2017 | 870 | 90 | 333529.82 | 200117.9 | 1 | 208174.52 | -8056.62 | 96.1299 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | overwork and work to supply errors and omissions
4052 | 1422921 | Execution of the Rodo Business Allotment | 45233120-6 | Road construction works | FALSE | 2015 | 2017 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 24 | 02-04-2015 | 06-11-2017 | 949 | 120 | 321337.34 | 224991.79 | 1 | 224991.79 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | there was no change in the value of the project
4053 | 1420829 | The purpose of this contract is to repair ruptures in the wastewater drainage networks throughout the period of the contract. These repairs will be requested by the client | 45232460-4 | Sanitary works | FALSE | 2014 | 2017 | Portugal | Aveiro | Aveiro | 1 | N/A | 05-03-2015 | 27-09-2017 | 937 | 730 | 249000 | 230442.61 | 1 | 227985.1 | 2457.51 | 101.0779 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value of the proposal - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work was completed within the contractual period | contracted work that was not necessary to perform
4054 | 1410621 | En1, km 113+444, roundabout connecting to en356 (ic2 - variant of the battle) | 45233128-2 | Roundabout construction work | FALSE | 2014 | 2017 | Portugal | Batalha | Leiria | 10 | 26 | 16-03-2015 | 23-06-2017 | 830 | 83 | 430000 | 416253.93 | 2 | 386160.79 | 30093.14 | 107.7929 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 80% Technical Valuation 20% | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it resulted from a delay in the approval of the lighting project by the future operator. | adaptations made to the project, including public lighting.
4055 | 1394592 | The purpose of this contract is to carry out the contract for the construction of cell 1 of the Ecoparque on the island of São Miguel, which includes, in addition to what is defined in other clauses on the matter | 45000000-7 | Construction work | FALSE | 2014 | 2017 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 30 | 20-02-2015 | 31-05-2017 | 831 | 240 | 1800000 | 1758734.21 | 3 | 1645779.07 | 112955.14 | 106.8633 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the contract's deadline resulted essentially from the excavation work in rock | it was found that the amount of excavation and transport to the dump was greater than expected
4056 | 1386477 | It consists of the execution of a longitudinal and transverse drainage system on the access road to Fajãzinha and the adjacent slope, with discharge of the drained flows in the water line affluent to Ribeira Grande | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2017 | Portugal | Lajes das Flores | Região Autónoma dos Açores | 15 | 24 | 17-12-2014 | 28-02-2017 | 804 | 365 | 1430058.67 | 1215549.88 | 3 | 1192901.4 | 22648.48 | 101.8986 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the extension of the execution period of the project for 90 days, due to the extra work. | the value of the project has changed due to underwork and more work.
4057 | 1382104 | Construction contract for reinforcement of the rail interfaces of the liquid and solid bulk terminals in the port of aveiro. | 45234100-7 | Railway construction works | FALSE | 2014 | 2017 | Portugal | Ílhavo | Aveiro | 1 | 21 | 12-02-2015 | 14-06-2017 | 853 | 150 | 1100000 | 1099455.99 | 3 | 1099455.99 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the supply of equipment components of the project
4058 | 1380044 | building construction | 45210000-2 | Building construction work | FALSE | 2014 | 2017 | Portugal | Murtosa | Aveiro | 1 | 30 | 10-02-2015 | 12-09-2017 | 945 | 305 | 287989.6 | 172793.77 | 1 | 172970.06 | -176.29 | 99.8981 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 22 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to some technical solutions that had to be adopted, the project ended up being delayed | there was over and underwork due to some work solutions, different from those planned, that had to be adopted.
4059 | 1359645 | Fresh fish storage, ice manufacturing and storage - Lota de Póvoa de Varzim | 45351000-2 | Mechanical engineering installation works | FALSE | 2014 | 2017 | Portugal | Póvoa de Varzim | Porto | 13 | 11 | 05-12-2014 | 05-01-2017 | 762 | 120 | 320000 | 289693.67 | 2 | 295082.9 | -5389.23 | 98.1737 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 40% Technical Quality Proposal 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work suspensions and extensions. | work extensions.
4060 | 1358627 | Urban Requalification of the North Center of Penamacor | 45453100-8 | Refurbishment work | FALSE | 2014 | 2017 | Portugal | Penamacor | Castelo Branco | 5 | 9 | 21-01-2015 | 17-11-2017 | 1031 | 120 | 270519.2 | 139818.97 | 1 | 195039.74 | -55220.77 | 71.6874 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in carrying out the project. | additional work worth €55,220.77.
4061 | 1351965 | BASIC SANITATION IN THE PARISH OF ALMALAGUÊS – 4th PHASE - Rio de Galinhas and Monforte | 45000000-7 | Construction work | FALSE | 2014 | 2017 | Portugal | Coimbra | Coimbra | 6 | 32 | 09-01-2015 | 04-08-2017 | 938 | 420 | 1200000 | 849000 | 2 | 782318.06 | 66681.94 | 108.5236 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | the project ended before the deadline | there were works that weren't done
4062 | 1343656 | Execution of the Domestic Sanitation Network in the Municipality - Execution of the Sewerage Network in the Municipality of Rio Maior | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2014 | 2017 | Portugal | Rio Maior | Santarém | 16 | 9 | 29-12-2014 | 10-02-2017 | 774 | 60 | 322482.66 | 168732.78 | 1 | 128407.09 | 40325.69 | 131.4046 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the execution deadline for the contract (60 days) was met, given that the approval of the pss was communicated to the contractor on 11/02/2015, under the terms and for the purposes set out in paragraph 1 of article 362 of the "public procurement code". | negative price revision and underwork
4063 | 1331719 | Ic1-stabilization and reinforcement of excavation slopes between santana da serra (nearby) and s.marcos da serra (nearby) | 45233142-6 | Road-repair works | FALSE | 2014 | 2017 | Portugal | Odemira | Faro | 8 | 24 | 05-12-2014 | 16-03-2017 | 832 | 90 | 270000 | 224000 | 1 | 208520.64 | 15479.36 | 107.4234 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | a graceful extension of the 18-day period was granted by the owner of work, with the successful tenderer claiming difficulties due to the existing circumstances in the national market in this sector, namely on the part of the companies and suppliers on whom they depend. | the change in the value of the project is related to the clearance of negative errors and omissions supply work in the amount of €15,479.36
4064 | 1324426 | Construction contract for the Purple Hydraulic Circuit - Sado of the Alqueva Multipurpose Development | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2017 | Portugal | Santiago do Cacém | Beja | 2 | 46 | 09-12-2014 | 21-09-2017 | 1017 | 455 | 17000000 | 16294193.92 | 3 | 15829130.04 | 465063.88 | 102.938 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | a 31-day extension was granted due to constraints on the normal development of the project, consequences of archaeological finds that forced the interruption of a work front. | underwork.
4065 | 1306037 | Infrastructure construction in Casaldaça/Gândara - Guisande | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2013 | 2017 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 19-11-2014 | 19-01-2017 | 792 | 90 | 210754 | 188450 | 1 | 170978.29 | 17471.71 | 110.2187 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | focused and previously described causes. | delay between project measurements and those carried out on site.
4066 | 1271308 | The object of this contract is the execution of the construction contract for the sports pavilion of São João de Vêr | 45210000-2 | Building construction work | FALSE | 2014 | 2017 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 15-10-2014 | 10-01-2017 | 818 | 500 | 1332122 | 1127329.77 | 3 | 1098947.45 | 28382.32 | 102.5827 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 36 | N/A | N/A | N/A | N/A | N/A | N/A | delay in execution attributable to the contractor (183 days). a graceful extension of 82 days was also made, due to the need to remove the medium voltage line that crossed the site where the project was to be implemented, which was not done in good time, as well as the execution of a contract in the same place that conditioned the progress of the projects. | changes arising from the interconnection with another contract carried out in the same location, resulting in a decrease in costs (adaptation to the project).
4067 | 1247043 | Improvement of safety conditions in water supply and wastewater drainage installations – 2nd phase | 90000000-7 | Sewage-, refuse-, cleaning-, and environmental services | FALSE | 2014 | 2017 | Portugal | Coimbra | Coimbra | 6 | 24 | 11-09-2014 | 03-03-2017 | 904 | 210 | 250000 | 225940.18 | 1 | 218890.82 | 7049.36 | 103.2205 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | authorization was lacking from official entities to start work | there was underwork
4068 | 1245667 | En110, km 2+500 to km 13+185. En17, km 11+386 to km 19+200. Protection on excavation slopes. Weather 2012-2013 | 45233142-6 | Road-repair works | FALSE | 2014 | 2017 | Portugal | Coimbra | Coimbra | 6 | 24 | 15-09-2014 | 11-05-2017 | 969 | 120 | 630000 | 378000.01 | 2 | 378743.21 | -743.2 | 99.8038 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline changes were motivated by the approval of the 1st additional map, by the new zoning implemented by the projects owner and the high road traffic on the en17, which did not allow the implementation of the signaling scheme with alternating circulation during the foreseen period, between 8.00 am and 6:00 pm. | after the clearing and cleaning of the slopes, it was verified the need to extend the height of the nets in view of the existence of loose stones that could jeopardize the safety of road users. with the completion of the project, it was verified that there was a balance, so the quantities were adjusted in order to proceed with the administrative closure of the contract
4069 | 1186637 | Road marking 2014 - Lot 4 | 45233142-6 | Road-repair works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | 24 | 01-09-2014 | 23-06-2017 | 1026 | 180 | 1637500 | 186994.44 | 1 | 178790.65 | 8203.79 | 104.5885 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | delay of 90 days due to unfavorable weather conditions and low yields on manual brands in ic2.
4070 | 1186509 | Road marking 2014 - lot 3 | 45233142-6 | Road-repair works | FALSE | 2014 | 2017 | Portugal | N/A | N/A | 13 | 24 | 01-09-2014 | 17-04-2017 | 959 | 180 | 1637500 | 187516.41 | 1 | 181521.84 | 5994.57 | 103.3024 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions that did not allow the project to be carried out safely, forcing the project to be suspended. | with the completion of the project, it was verified that there was a balance, so the quantities were adjusted in order to proceed with the administrative closure of the contract
4071 | 1141130 | Requalification of the riverfront next to streetDr. José Pires Padinha – Section Lota / Ponte dos Descobrimentos | 45223000-6, 45112700-2, 45315600-4 | Structures construction work, Landscaping work, Low-voltage installation work | FALSE | 2013 | 2017 | Portugal | Tavira | Faro | 8 | 30 | 01-08-2014 | 17-11-2017 | 1204 | 120 | 175408.07 | 153493.38 | 1 | 142252.7 | 11240.68 | 107.9019 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | extension for 55 days due to the approval and communication of the approval of the pss and 90 days due to the existence, in the intervention area, of boxes with utensils belonging to the fishermen, 464 days of suspension of the term due to the execution of another contract at the project site and delivery of the technical compilation. | underwork worth -11,157.77 and price revision worth (-) €82.91.
4072 | 1122721 | Quad Space - Innovation and Creativity (Burito Brito Capelo) | 45453100-8 | Refurbishment work | FALSE | 2013 | 2017 | Portugal | Matosinhos | Porto | 13 | 20 | 04-06-2014 | 17-01-2017 | 958 | 330 | 950000 | 690000 | 2 | 679086.76 | 10913.24 | 101.607 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | no change
4073 | 1112272 | Contract for the Sanitation System in the Municipality of Portel - Rehabilitation/Construction of the Portel, Amieira and Alqueva WWTPs and the respective Pumping Stations and Interceptor Systems. | 45232420-2 | Sewage work | FALSE | 2013 | 2017 | Portugal | Portel | Évora | 7 | 75 | 23-04-2014 | 31-03-2017 | 1073 | 365 | 1250000 | 1012549.44 | 3 | 1003988.5 | 8560.94 | 100.8527 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | during the project, planning slipped due to the difficulty expressed by the contractor in finding labor in the area. added to this information is the low performance shown by subcontractors. | the contractor waived the amount of €8,560.96, as this value will eliminate the problems that remain at the level of the discharge channel of the amieira wwtp, a situation that should have been carried out by the contractor during the start-up phase
4074 | 1100216 | Construction contract for the irrigation, road and drainage infrastructure for the Block of Pias. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2017 | Portugal | Beja | Beja | 2 | 53 | 13-06-2014 | 02-05-2017 | 1054 | 547 | 27800000 | 21947209.32 | 3 | 21946448.03 | 761.29 | 100.0035 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A | period of inspections for provisional acceptance purposes. | the executed quantities differed in some works from the initially estimated quantities
4075 | 1099463 | Sousa Rural Heritage Interpretive Center - Construção_x000D_ | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2014 | 2017 | Portugal | Felgueiras | Porto | 13 | 24 | 18-06-2014 | 27-06-2017 | 1105 | 300 | 477066.4 | 436004.8 | 2 | 409326.62 | 26678.18 | 106.5176 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there are several deadline extensions. | smaller quantities executed.
4076 | 1097971 | Improvement of the Caparide-Tires link road | 45316110-9, 45232130-2, 45233000-9, 45112000-5, 45232300-5 | Installation of road lighting equipment, Storm-water piping construction work, Construction, foundation and surface works for highways, roads, Excavating and earthmoving work, Construction and ancillary works for telephone and communication lines | FALSE | 2013 | 2017 | Portugal | Cascais | Lisboa | 11 | 47 | 21-04-2014 | 08-02-2017 | 1024 | 216 | 1596444.02 | 1087114.02 | 3 | 1087114.02 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of work
4077 | 1047393 | Environmental rehabilitation of the ecological corridor of Ribeira da Lavandeira - Rebordosa | 45112700-2 | Landscaping work | FALSE | 2013 | 2017 | Portugal | Paredes | Porto | 13 | 20 | 10-04-2014 | 14-09-2017 | 1253 | 365 | 346000 | 207600.01 | 1 | 207600.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | unavailability of land
4078 | 1044177 | Mealhada School Center | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2017 | Portugal | Mealhada | Aveiro | 1 | 30 | 16-04-2014 | 25-01-2017 | 1015 | 450 | 3110000 | 2774000 | 3 | 2651647.07 | 122352.93 | 104.6142 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the execution period due to the delay in the beginning of the 2nd phase, due to the need to approve the shipyard plan for the 2nd phase and extension of the execution period of the contract for the execution of works to correct errors and omissions, whose responsibility for its execution cannot be attributed to the contractor (platbands of the kindergarten building) | the change in the value of the project resulted from the existence of work to supply errors and omissions, underwork and price revisions.
4079 | 987111 | Rehabilitation of pavements on municipal roads 202-2, 518, 530 and 530-2 | 45233223-8 | Carriageway resurfacing works | FALSE | 2013 | 2017 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 9 | 20-02-2014 | 02-03-2017 | 1106 | 90 | 349300 | 292614.72 | 2 | 292571.79 | 42.93 | 100.0147 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project suffered successive delays, due to the company's lack of financial capacity, as well as technical shortcomings of the project carried out that required repairs.
4080 | 978185 | "EN VN 366, Bridge over Ribeira do Judeu at km 13+010 - Rehabilitation of the Work of Art and Rectification, Regularization and Protection of the Riverbed". | 45221119-9 | Bridge renewal construction work | FALSE | 2013 | 2017 | Portugal | Azambuja | Lisboa | 11 | 42 | 04-02-2014 | 23-05-2017 | 1204 | 120 | 215000 | 171334.49 | 1 | 155944.5 | 15389.99 | 109.8689 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions led to an increase in the flow of the stream, with repercussions on work income | suppression of some unnecessary amounts performed for the completion of the project.
4081 | 945670 | Public tender no. 3-A1/2013 - The purpose of the procedure in question is to carry out the drainage networks for domestic wastewater and rainwater from Travessa Particular João Félix | 45232460-4 | Sanitary works | FALSE | 2013 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 08-01-2014 | 30-01-2017 | 1118 | 180 | 280000 | 219937.51 | 1 | 217334.22 | 2603.29 | 101.1978 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | an inspection notice was issued for the purposes of provisional acceptance on 10/13/2014, in which the contract was not accepted, and the contractor was given a deadline to carry out the necessary repairs and deliver the missing documents | the total effective price of the contract includes the value of €-2,603.25, related to the price revision, in accordance with no. 1 of art. 382nd. of the "public procurement code"
4082 | 936457 | En 3 (ex-ip2) - slope stabilization between kms 130+800 and 133+100 | 45233142-6 | Road-repair works | FALSE | 2012 | 2017 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 26 | 20-12-2013 | 17-04-2017 | 1214 | 180 | 360000 | 288891.82 | 2 | 280233.52 | 8658.3 | 103.0897 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions that did not allow the project to be carried out safely, forcing the project to be suspended. | with the completion of the project, it was verified that there was a balance, so the quantities were adjusted in order to proceed with the administrative closure of the contract
4083 | 902270 | Er247, km 13+750, bridge over the couple new stream - access | 45233120-6 | Road construction works | FALSE | 2013 | 2017 | Portugal | Lourinhã | Lisboa | 11 | 48 | 25-11-2013 | 24-07-2017 | 1337 | 150 | 320000 | 319231.04 | 2 | 284332.37 | 34898.67 | 112.2739 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 1 | N/A | N/A | N/A | N/A | N/A | N/A | the contract was suspended due to lack of safety conditions, caused by weather conditions, namely heavy rainfall and strong winds
4084 | 835851 | General improvement of the school eb1, nº 183 and ji nº 5 - sarah afonso - santa maria dos olivais | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2013 | 2017 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-09-2013 | 06-02-2017 | 1235 | 365 | 4000000 | 3105113.07 | 3 | 3136361.34 | -31248.27 | 99.0037 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4085 | 817571 | Er 266 – Luzianes-gare (km 0+550) and intersection towards savoy (km13+380). Improvement | 45233142-6 | Road-repair works | FALSE | 2013 | 2014 | Portugal | Beja | Beja | 2 | 38 | 22-07-2013 | 24-06-2014 | 337 | 150 | 2450000 | 2140146.46 | 3 | 238468.44 | 1901678.02 | 897.4548 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Revocation of the Contract) | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | initial contract in the amount of €2,140,146.46, amount of work carried out calculated €238,468.44, amount of work not carried out €1,901,678.02
4086 | 817519 | Er244 - slope stabilization and protection at km 109+000 at km 111+000 | 45233142-6 | Road-repair works | FALSE | 2012 | 2017 | Portugal | Avis | Portalegre | 12 | 30 | 16-07-2013 | 02-06-2017 | 1417 | 120 | 550000 | 539931.56 | 2 | 411521.63 | 128409.93 | 131.2037 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register. | it was found that the amounts of excavation using explosives were inflated.
4087 | 801015 | Vertical signage - renovation and adaptation of equipment - south center - lot 4 | 45316200-7 | Installation of signalling equipment | FALSE | 2011 | 2017 | Portugal | N/A | N/A | 13 | 48 | 28-01-2013 | 15-11-2017 | 1752 | 365 | 6728500 | 444766.41 | 2 | 442972.27 | 1794.14 | 100.405 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adaptation of signage to the needs of the three districts, and recurrent supply difficulties on the part of suppliers. | adjustment of the final quantities in view of the adaptation of signage to the needs of the three districts.
4088 | 348306 | The purpose of the contract is the milling and replacement of pavements in interventions by Águas e Parque Biológico de Gaia, EEM, including the supply of the necessary materials and the removal of leftovers | 45233222-1 | Paving and asphalting works | FALSE | 2011 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 30-07-2012 | 04-10-2017 | 1892 | 365 | 260000 | 249200 | 1 | 137332.66 | 111867.34 | 181.4572 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the contractor did not carry out the projects within the foreseen period, having requested 2 deadline extensions, which were rejected by the board of directors, in view of the reasons invoked by the contractor. | the contractor did not complete the project within the contract period.
4089 | 329515 | Canalization of the Ribeiro da Corujeira between the Caminho do Cabeço dos Lombos and the Caminho da Corujeira - Monte | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2017 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 25 | 27-10-2011 | 10-10-2017 | 2175 | 150 | 590000 | 387565.76 | 2 | 323468.67 | 64097.09 | 119.8155 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | due to the difference between the value of the project planned and the project actually carried out, and also due to the ordinary revision of prices.
4090 | 191905 | The work includes the construction of a building for the PSP police station, as well as the execution of the respective exterior arrangements. | 45216111-5 | Police station construction work | FALSE | 2010 | 2017 | Portugal | Vila Nova de Gaia | Porto | 13 | 42 | 04-08-2011 | 06-12-2017 | 2316 | 365 | 945082.77 | 797500 | 2 | 825135.02 | -27635.02 | 96.6508 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions to the deadline for carrying out the project were duly approved. | two additions to the contract were duly approved, the existence of underwork and a definitive price review.
4091 | 7003599 | Cp 13/2014 - electrical switchboards for powering and controlling the water collection and lifting pumps, automation and remote management system at the collection center, and the water lifting stations | 45300000-0 | Building installation work | FALSE | 2014 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 15-12-2014 | 15-06-2016 | 548 | 120 | 333742.85 | 302952.14 | 2 | 302952.14 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
4092 | 6431328 | Cp 13/2015 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 17-11-2015 | 19-12-2016 | 398 | 540 | 260000 | 215613.75 | 1 | 214931.92 | 681.83 | 100.3172 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | urgency | works less
4093 | 5957250 | Construction of the S. Cristóvão de Nogueira Sports Complex | 45212220-4 | Multi-purpose sports facilities construction work | FALSE | 2015 | 2016 | Portugal | Cinfães | Viseu | 20 | 20 | 26-10-2015 | 22-07-2016 | 270 | 120 | 184102.28 | 156400 | 1 | 152613.5 | 3786.5 | 102.4811 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | climatic conditions. | over and underwork.
4094 | 4680021 | Restoration and Improvement of the Coverings of the CCC and Franco Dias Pavilion | 45261210-9 | Roof-covering work | FALSE | 2015 | 2016 | Portugal | Lisboa | Lisboa | 11 | 20 | 01-09-2015 | 14-01-2016 | 135 | 120 | 333000 | 329893.48 | 2 | 329893.48 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (70%) and Technical Value of the Proposal (30%) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | there was no change, despite the existence of over and underwork
4095 | 4338581 | Replacement of the roofs of the Marquês de Niza Palace | 45261210-9 | Roof-covering work | FALSE | 2015 | 2016 | Portugal | Lisboa | Lisboa | 11 | 20 | 16-09-2015 | 12-01-2016 | 118 | 120 | 556468.65 | 394349.27 | 2 | 272523.05 | 121826.22 | 144.7031 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Bid price (70%) and Technical Valuation of the Proposal (30%) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
4096 | 4260673 | Construction of the Multiusos do Montemuro | 45211350-7 | Multi-functional buildings construction work | FALSE | 2015 | 2016 | Portugal | Cinfães | Viseu | 20 | 20 | 09-05-2016 | 20-12-2016 | 225 | 180 | 241762.91 | 183929.33 | 1 | 184229.96 | -300.63 | 99.8368 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes. | existence of over and underwork.
4097 | 4256156 | Souselo Social and Sports Development Center - Installation of Synthetic Grass in the Souselo Games Park | 45212220-4 | Multi-purpose sports facilities construction work | FALSE | 2015 | 2016 | Portugal | Cinfães | Viseu | 20 | 20 | 14-01-2016 | 11-10-2016 | 271 | 120 | 232967.64 | 207650 | 1 | 223757.62 | -16107.62 | 92.8013 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension | existence of more works
4098 | 4206054 | Headquarters of the Municipal Associations | 45262700-8 | Building alteration work | FALSE | 2014 | 2016 | Portugal | Mação | Santarém | 16 | 12 | 10-04-2014 | 27-06-2016 | 809 | 300 | 337313.95 | 248579.59 | 1 | 236019.57 | 12560.02 | 105.3216 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension. | underwork.
4099 | 4187546 | Requalification of accesses to the Anadia School and Sports Complex | 45233141-9 | Road-maintenance works | FALSE | 2016 | 2016 | Portugal | Anadia | Aveiro | 1 | 20 | 02-05-2016 | 14-10-2016 | 165 | 120 | 236187.65 | 151492.66 | 1 | 151492.66 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4100 | 3192427 | 5010016277 - Contract for "Anti-Corrosion Protection of Metallic Bridges on the West Line" | 45221112-0 | Railway bridge construction work | FALSE | 2014 | 2016 | Portugal | N/A | N/A | N/A | N/A | 24-02-2015 | 04-02-2016 | 345 | 150 | 350000 | 336969.73 | 2 | 331043.71 | 5926.02 | 101.7901 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A |  | additional hours of service provided by inspection (€): -5,926.02€
4101 | 3152511 | 5010014748 - Replacement of the External Prestressing System on the Soure Bridge, at PK 216+893 of the Alfarelos Branch | 45221112-0 | Railway bridge construction work | FALSE | 2014 | 2016 | Portugal | N/A | N/A | N/A | N/A | 04-08-2014 | 17-11-2016 | 836 | 112 | 350000 | 288361.86 | 2 | 271988.24 | 16373.62 | 106.02 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension 23 days | decreases in the cost of the project (excluding vat): - €1,954.89 (additional hours of service provided by the inspection)
4102 | 3104566 | 5010014185 - Contract for Drainage, Waterproofing and Consolidation of the Vault and Rods between metric points 1635 and 1650 of the Rossio Tunnel on the Sintra Line | 45221000-2 | Construction work for bridges and tunnels, shafts and subways | FALSE | 2014 | 2016 | Portugal | N/A | N/A | N/A | N/A | 20-10-2014 | 19-09-2016 | 700 | 305 | 400000 | 299458.13 | 2 | 299458.13 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A
4103 | 3030075 | AR 2280 - Execution Contract for Gerém Interceptor - Extension - FD9 | 45232411-6 | Foul-water piping construction work | FALSE | 2014 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 41 | 25-06-2015 | 14-12-2016 | 538 | 120 | 240000 | 184647.07 | 1 | 203442.46 | -18795.39 | 90.7613 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work and deadline for the contract due to lack of safety conditions due to adverse weather conditions. | there was a need for further work to be carried out.
4104 | 2969408 | Provere - Environmental Requalification of the banks of the Dão River - Termas de Alcafache - Requalification of the Public Space | 45247220-8 | Weir construction work | FALSE | 2011 | 2015 | Portugal | Viseu | Viseu | 20 | 20 | 05-12-2011 | 31-03-2015 | 1212 | 365 | 964060 | 724648.67 | 2 | 581023 | 143625.67 | 124.7194 | Ad rectification statement | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | N/A | N/A | N/A | N/A | failure of the contractor to comply with binding deadlines | penalty termination of the contract
4105 | 2896892 | Improvement of the 0th floor of the PCM building | 45210000-2 | Building construction work | FALSE | 2015 | 2016 | Portugal | Lisboa | Lisboa | 11 | 24 | 15-07-2015 | 11-08-2016 | 393 | 120 | 319708 | 264900 | 2 | 282528 | -17628 | 93.7606 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change in the execution period. the provisional reception was made at a later date because the final screens and hvac maintenance plan were missing.
4106 | 2863404 | 5010002754 - "Suppression of the level crossings at km 43+433 and 45+244 and reconversion to pedestrian traffic of the level crossing at km 43+806, on the Minho Line, in the municipality of Barcelos - lot 1 | 45221000-2 | Construction work for bridges and tunnels, shafts and subways | FALSE | 2010 | 2016 | Portugal | N/A | N/A | N/A | 32 | 18-03-2011 | 22-07-2016 | 1953 | 180 | 2000000 | 1399312.32 | 3 | 1234325.65 | 164986.67 | 113.3665 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the reasons for the changes to the project execution period are those described in the memorandum attached to the process and the contracting authority requested a graceful extension of 96 days waiving the right to present a claim for any default interest due for the delay in paying the contract invoices, as well as the right to review the final price of the contract, in a global amount of €66,638.66.
4107 | 2853300 | Construction contract for the Caminho da Erva Má, POA BLPDL | 45000000-7 | Construction work | FALSE | 2016 | 2016 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 20 | 25-05-2016 | 22-09-2016 | 120 | 210 | 260000 | 169940 | 1 | 156013 | 13927 | 108.9268 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | underwork | underwork
4108 | 2779138 | 1O0001-2016 Contract for Improvement and Remodeling of the Sterilization Center of CHBM EPE | 45215100-8 | Construction work for buildings relating to health | FALSE | 2015 | 2016 | Portugal | Barreiro | Setúbal | 17 | 30 | 23-03-2016 | 04-11-2016 | 226 | 90 | 595000 | 588500 | 2 | 596143.36 | -7643.36 | 98.7179 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Article 13 of the Procedure Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
4109 | 2719613 | Finishing, furniture, audio and video contract for the OTOC auditorium in Porto | 45212321-2 | Auditorium construction work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 12 | 26-10-2015 | 28-07-2016 | 276 | 60 | 560000 | 517856.04 | 2 | 463426.23 | 54429.81 | 111.7451 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without description | without description
4110 | 2701623 | Construction contract for the new landfill of the Multimunicipal System of the South of Douro - Landfill of Gestal | 45112310-1 | Infill work | FALSE | 2013 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 42 | 08-07-2013 | 17-11-2016 | 1228 | 280 | 16650000 | 10829542.25 | 3 | 12851331.76 | -2021789.51 | 84.2679 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions; more works; objective modifications of the contract for reasons of public interest; errors and omissions supply work. | weather conditions; more work; objective modifications of the contract for reasons of public interest; errors and omissions supply work.
4111 | 2698715 | 100% Quality - Urgent Repairs to Bituminous Paving 2015 – Union of Parishes of Custóias, Leça do Balio and Guifões - contract 116/20015 - EDOC/2014/78154 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2016 | Portugal | Matosinhos | Porto | 13 | 36 | 01-09-2015 | 15-11-2016 | 441 | 183 | 850000 | 677584.47 | 2 | 677584.47 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
4112 | 2520371 | 5010006820 - Contract for the Northern Line - Entroncamento Station - Complete Renovation of Lines 5, 9 and 10. | 45234100-7 | Railway construction works | FALSE | 2014 | 2016 | Portugal | N/A | N/A | N/A | N/A | 08-09-2014 | 13-07-2016 | 674 | 180 | 2705578.78 | 2440791.28 | 3 | 2347312.32 | 93478.96 | 103.9824 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | na
4113 | 2511738 | Sidewalk Repair in the City of Matosinhos - Contract No. 83/2015 | 45233220-7 | Surface work for roads | FALSE | 2014 | 2016 | Portugal | Matosinhos | Porto | 13 | 36 | 27-07-2015 | 20-09-2016 | 421 | 182 | 250000 | 150000 | 1 | 150000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
4114 | 2436052 | Contract for the Reorganization and Enhancement of 7 Lagoon Fishing Centers - Lot 2 Cais das Teixugueiras, Cais do Nacinho, Cais da Tabuada and Cais das Bulhas (Municipality of ESTARREJA) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | Estarreja | Aveiro | 1 | 45 | 05-06-2014 | 23-06-2016 | 749 | 150 | 1230000 | 155626.28 | 1 | 151817.55 | 3808.73 | 102.5088 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | period necessary for the execution that elapses, among others, from adverse weather conditions that arise made to feel and to carry out the 'excess work' (clause three of amendment no. 01 to the contract no. pra/14/cn005. | underwork
4115 | 2339831 | Acquisition of a public works contract for requalification of cafeteria no. 10, located on Av. Viscount Valmor, no. 72 C, in Lisbon. | 45453100-8 | Refurbishment work | FALSE | 2016 | 2016 | Portugal | Lisboa | Lisboa | 11 | 20 | 05-08-2016 | 19-12-2016 | 136 | 100 | 225000 | 220000 | 1 | 220000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the difference in 6 days was due to the delay in the delivery of some materials.
4116 | 2317415 | Implementation of an urban allotment, with the execution of the respective infrastructures | 45111290-7 | Primary works for services | FALSE | 2016 | 2016 | Portugal | Oleiros | Castelo Branco | 5 | 20 | 16-05-2016 | 30-12-2016 | 228 | 90 | 330000 | 191546.22 | 1 | 191546.22 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a change to the execution period of the project due to delays by suppliers of materials to be used in the contract
4117 | 2296856 | Renovation of the Lumiar Campus water distribution network | 45232151-5 | Water-main refurbishment construction work | FALSE | 2016 | 2016 | Portugal | Lisboa | Lisboa | 11 | 21 | 11-07-2016 | 19-12-2016 | 161 | 150 | 350000 | 228523.15 | 1 | 228523.15 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the projects took place within the established maximum period of execution of the project.
4118 | 2270362 | Improvement of the municipal road network in the parish of Quelfes | 45233140-2 | Roadworks | FALSE | 2015 | 2016 | Portugal | Olhão | Faro | 8 | 20 | 11-04-2016 | 31-10-2016 | 203 | 150 | 300000 | 291781.53 | 2 | 283753.61 | 8027.92 | 102.8292 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | approval of dpss and completion of the project ahead of schedule | existence of underwork
4119 | 2254183 | Rehabilitation of Caramila elementary school (EM.004.2016.064) | 45453100-8 | Refurbishment work | FALSE | 2016 | 2016 | Portugal | Porto | Porto | 13 | 20 | 13-06-2016 | 13-12-2016 | 183 | 75 | 800000 | 560000.01 | 2 | 567093.77 | -7093.76 | 98.7491 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work was carried out within the expected time frame | additional work worth €8,830.27, errors and omissions worth €4,046.54 and work not performed worth €5,783.05
4120 | 2236686 | Repair works in the school building and exterior arrangements - E. B. 1st cycle of Requião | 45453100-8 | Refurbishment work | FALSE | 2016 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 02-06-2016 | 13-09-2016 | 103 | 90 | 250000 | 194937.61 | 1 | 192568.31 | 2369.3 | 101.2304 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value of the Proposal: 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork worth €2,369.30.
4121 | 2231546 | Contract for the Construction and Restoration of the exterior stone elements of the Monument to the Discoveries | 45454100-5 | Restoration work | FALSE | 2016 | 2016 | Portugal | Lisboa | Lisboa | 11 | 30 | 04-05-2016 | 31-12-2016 | 241 | 210 | 330000 | 264000.01 | 2 | 271332.01 | -7332 | 97.2978 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Quality - 40% and Price - 60%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | already mentioned | already mentioned
4122 | 2229498 | The works are specified in the documents of the procedure, (Tender Program, Tender Documents and Work Execution Project) | 45231110-9 | Pipelaying construction work | FALSE | 2015 | 2016 | Portugal | Estarreja | Aveiro | 1 | 22 | 22-07-2015 | 22-01-2016 | 184 | 90 | 1135000 | 1134000 | 3 | 1126106.72 | 7893.28 | 100.7009 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4123 | 2206936 | Contract for “General works for installation or replacement of accessories, connection branches and domestic sewage drainage networks - Oeiras 2016" | 45232410-9 | Sewerage work | FALSE | 2016 | 2016 | Portugal | Oeiras | Lisboa | 11 | 20 | 20-05-2016 | 02-12-2016 | 196 | 184 | 462000 | 277200.01 | 2 | 277096.83 | 103.18 | 100.0372 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 50% Technical value of the proposal - 50% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the duration of the contract depended on the number of anomalies and the need for intervention to replace or repair them. | the remaining amount of €103.18 was not enough to carry out further interventions, so provisional acceptance was carried out
4124 | 2206369 | Execution of interior finishing and coating work, assembly of sanitary, kitchen, electrical and air conditioning equipment, construction of covered playground and exterior arrangements | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2016 | Portugal | Amarante | Porto | 13 | 20 | 03-05-2016 | 30-11-2016 | 211 | 120 | 467826.74 | 336094.14 | 2 | 336094.14 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a 62-day extension granted by the developer due to the reassessment of the project and delays in execution
4125 | 2197350 | Fire safety contract | 45343000-3 | Fire-prevention installation works | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 30 | 31-03-2016 | 27-10-2016 | 210 | 90 | 300000 | 209579.58 | 1 | 209579.58 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: PRICE:60%; TECHNICAL VALUES: 30%; EXECUTION TIME: 10% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4126 | 2194441 | Refurbishment and Improvement of the Eng.º Branco Teixeira Municipal Stadium - 1st Phase | 45453000-7 | Overhaul and refurbishment work | FALSE | 2016 | 2016 | Portugal | Chaves | Vila Real | 19 | 20 | 17-05-2016 | 16-09-2016 | 122 | 75 | 760000 | 669900 | 2 | 761850 | -91950 | 87.9307 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | resulting from additional work and supply of errors and omissions | resulting from overwork and supply of errors and omissions and underwork.
4127 | 2183146 | Quality 100% - Installation of Light Flux Regulators in Public Lighting in the Municipality of Matosinhos - EDOC/2015/18028 | 45000000-7 | Construction work | FALSE | 2015 | 2016 | Portugal | Matosinhos | Porto | 13 | 36 | 15-10-2015 | 19-04-2016 | 187 | 91 | 1308051.42 | 1178527.7 | 3 | 1178527.7 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (40% weighting) b) Technical value (60% weighting) The final classification will result from the application of the following equation weighting the classifications obtained in each of the factors: Cf = 0.4 Pi + 0.6 Vt Being: Cf = final classification Pi = Score of each proposal regarding the "Price" factor Vt = Score of each proposal regarding the "Technical value" factor | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
4128 | 2172767 | 2015.054.02.C1 - SF Coimbra - Demolition, modeling and land fencing | 45111200-0 | Site preparation and clearance work | FALSE | 2016 | 2016 | Portugal | Coimbra | Coimbra | 6 | 12 | 18-04-2016 | 16-11-2016 | 212 | 90 | 350000 | 236000 | 1 | 236000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 22 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension term
4129 | 2171723 | Connection of the Mouril roundabout to the Creixomil bypass | 45233226-9 | Access road construction work | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 28-04-2016 | 09-09-2016 | 134 | 75 | 292492.49 | 230731.79 | 1 | 235466.44 | -4734.65 | 97.9892 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | existence of underwork due to the foreseen quantities not being used up. supply of errors and omissions.
4130 | 2170517 | Execution of interior finishing and coating work, assembly of sanitary, kitchen, electrical and air conditioning equipment, construction of covered playground and exterior arrangements | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2016 | Portugal | Amarante | Porto | 13 | 20 | 12-04-2016 | 30-11-2016 | 232 | 120 | 356360.72 | 278500 | 2 | 278500 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
4131 | 2170405 | Execution of interior finishing and coating work, assembly of sanitary, kitchen, electrical and air conditioning equipment, construction of covered playground and exterior arrangements | 45214200-2 | Construction work for school buildings | FALSE | 2016 | 2016 | Portugal | Amarante | Porto | 13 | 20 | 12-04-2016 | 30-11-2016 | 232 | 120 | 388588.32 | 330000 | 2 | 330000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension
4132 | 2170392 | Paving in Adopisco and Ervilhal | 45232451-8 | Drainage and surface works | FALSE | 2016 | 2016 | Portugal | São Pedro do Sul | Viseu | 20 | 20 | 02-05-2016 | 18-11-2016 | 200 | 150 | 218200.5 | 155542.5 | 1 | 155542.5 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | no change
4133 | 2150919 | 2015.054.01.C1 - SFP Coimbra - Installation of the multipurpose space | 45259900-6 | Plant upgrade work | FALSE | 2015 | 2016 | Portugal | Coimbra | Coimbra | 6 | 22 | 08-02-2016 | 22-11-2016 | 288 | 100 | 800000 | 733345.76 | 2 | 733345.76 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension
4134 | 2127006 | Improvement of the municipal road network - CM 516-3- Olhão - Brancanes - Poço Longo | 45233140-2 | Roadworks | FALSE | 2015 | 2016 | Portugal | Olhão | Faro | 8 | 20 | 27-01-2016 | 21-10-2016 | 268 | 90 | 300000 | 289010.98 | 2 | 289010.98 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractor's request for extension
4135 | 2126711 | Improvement of ER 206 - Av.ª 25 de Abril | 45233223-8 | Carriageway resurfacing works | FALSE | 2016 | 2016 | Portugal | Valpaços | Vila Real | 19 | 24 | 07-04-2016 | 27-10-2016 | 203 | 120 | 216767.86 | 151737.51 | 1 | 151737.51 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Provided for in point 17 of the Program of Procedure and Annex VI: 1st - The award will be made to the most economically advantageous proposal, this being dedeadlineined by assessing two factors: Proposal (PP) and Technical Value of the Proposal (VTP). 2nd - The weighting coefficients for the two factors are, respectively, 75% and 25%. 3.º - The classification of proposals is carried out by applying the following formula: CP = PP x 75% + VTP x 25% 4th - Definition of concepts: a) Price of the Proposal under analysis (PPa) - is the algebraic addition of the value contained in the Main Form of the Proposal under analysis with the value assigned to supply the List of Errors and Omissions approved by the competent Body for the decision to hire, if applicable, and, occurring with the correction of account errors; b) Base Price (PB) - is the maximum price that the contracting authority is willing to pay for the execution of all the services that constitute the object of the contract to be signed, article 47 of the Public Contracts Code (CCP); c) Abnormally Low Price (PAB) - is the value set in the tender program, by reference to the base price set in the charges, from which the total price resulting from a proposal is considered abnormally low, article 132 of the CCP. d) Documents with Justification Clarifications - are the documents to be presented by the bidder with a proposal with price abnormally low, either accompanying the proposal or after notification, in writing, to provide clarifications within a suitable period justifications relating to the constituent elements of the proposal that it deems relevant for this purpose, paragraph d) of number 1 of article 57 and number 3 of article 71 of the CCP, respectively; e) Approximation of the score - the score to be assigned to each subfactor and factor is approximated to two decimal places, that is, to the hundredths; 5.º - Scoring of the Proposal Price, is carried out by applying the following formulas and the following rules: a) Formula 1, for proposals with prices within the following limits: less than or equal to the base price and greater than or equal to seventy percent (70%) of the base price: PP = 30 + (PB-PPa)/(0.30xPB) x 70 b) Proposals with an abnormally low total price, whose justifications have been considered under the deadlines of article 71 of the CCP, are punctuated by the application of Formula 2: PP = 100 + (PB-PPa)/(0.70xPB) x 5 c) Being: i) PP - score of the price of the proposal under consideration; ii) PB - base price; iii) PPa - price of the proposal under analysis; d) The scoring scale varies between thirty (30) and one hundred and five (105) points; e) Proposals that present a price are excluded: i) contract higher than the base price, under the deadlines of paragraph d) of number 2 of article 70 and paragraph o) of number 2 of article 146 of the CCP; ii) an abnormally low total, under the deadlines of paragraph e) of number 2 of article 70 and of paragraph d) and o) of number 2 of article 146 of the CCP, after verification pursuant to the provisions of article 71 of the CCP. 6 - The Technical Valuation of the Proposal is scored based on the analysis of the following three sub-factors: Work Plan (PT), Memory Justification and Description of the Work (MO) and Payment Plan (PG), with the respective weighting coefficients of 50%, 30% and 20%, using the following formula: VT = PT x 50% + MO x 30% + PG x 20% 7.º - The score for the Work Plan subfactor is obtained by analyzing the following three elementary subfactors: Work Map (MdT), Manpower Map (MMO) and Equipment Map (MEq), with the following weighting coefficients of 50%, 25% and 25%, using the following formula: PT=MdT x 50%+ MMO x 25%+MEq x 25% 8.º - The scoring scale for these elementary subfactors and subfactors varies between zero (0) and one hundred (100) points, according to the ordered set of different attributes likely to be proposed that allow the attribution of partial scores (descriptors - 9th to 13th of Annex VI of the Procedure Programme). | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | early completion-
4136 | 2122022 | Contract for the repair/conservation of the SIMAS reservoirs of Oeiras and Amadora, in the municipalities of Oeiras and Amadora, for the years 2014 to 2016 | 45259000-7 | Repair and maintenance of plant | FALSE | 2014 | 2016 | Portugal | Oeiras | Lisboa | 11 | 11 | 22-08-2014 | 08-03-2016 | 564 | 730 | 395000 | 237000.01 | 1 | 237000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | the discrepancy verified is related to the fact that the project took place at a higher pace than initially expected, with the contract, as such, having ended before the end of the stipulated period.
4137 | 2104665 | Requalification of Largo de Donães - Oliveira do Castelo | 45233262-3 | Pedestrian zone construction work | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 24-03-2016 | 25-08-2016 | 154 | 90 | 216418.11 | 151852.42 | 1 | 142442.06 | 9410.36 | 106.6064 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Valuation - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline has been met. however, it is clarified that the deadline ended at the weekend, so the provisional reception was carried out on the following working day. | cancellation of works (€5,626.36 + vat) and non-exhaustion of projected quantities (€3,784.00 + vat).
4138 | 2092753 | Requalification and improvement of several streets in the Parishes of Bajouca, Coimbrão, Union of Parishes of Monte Real and Carvide and Union of Parishes of Monte Redondo and Carreira | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Leiria | Leiria | 10 | 20 | 16-03-2016 | 23-12-2016 | 282 | 180 | 457473 | 336728.25 | 2 | 332403.25 | 4325 | 101.3011 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension. | underwork.
4139 | 2077003 | Contract for the Maintenance of Sanitation and Water Supply Networks | 45259000-7 | Repair and maintenance of plant | FALSE | 2015 | 2016 | Portugal | Chamusca | Santarém | 16 | 24 | 15-03-2016 | 14-11-2016 | 244 | 720 | 250000 | 250000 | 2 | 248333.76 | 1666.24 | 100.671 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | all works were carried out within the contract deadline. | the project was carried out in its entirety, not requiring the billing of the entire quantity of all articles.
4140 | 2071193 | Adaptation of the former elementary school in Bairro/Pevidém for a music school | 45454000-4 | Restructuring work | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 09-03-2016 | 28-10-2016 | 233 | 120 | 467603.92 | 370823.22 | 2 | 368992.61 | 1830.61 | 100.4961 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical Valuation - 30% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the approval of the health and safety plan was communicated on 01/04/2016. following the inspection notice for provisional acceptance (02/08/2016), the contractor had to correct defects in the project, so he was granted a period of 30 days. | underwork due to the anticipated quantities not being used up.
4141 | 2069522 | Expansion of the Eb1 da Avenida School | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2016 | Portugal | Viseu | Viseu | 20 | 24 | 13-02-2013 | 11-02-2016 | 1093 | 150 | 249000 | 173869.98 | 1 | 185157.75 | -11287.77 | 93.9037 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | additional work and errors and omissions supply
4142 | 2045264 | Installation of a pavilion for the storage of valuables at the SULDOURO Screening Station | 45213220-1 | Construction work for warehouses | FALSE | 2015 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 42 | 11-02-2016 | 22-09-2016 | 224 | 120 | 223916 | 187390.32 | 1 | 190318.71 | -2928.39 | 98.4613 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
4143 | 2026291 | Adaptation of the "Casa de Donães" building for the headquarters of the ACT | 45453100-8 | Refurbishment work | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 17-02-2016 | 30-09-2016 | 226 | 90 | 300733.85 | 208099.21 | 1 | 207910.26 | 188.95 | 100.0909 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Technical value - 30% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | partial suspension of work for 60 days, to carry out structural reinforcement carried out through a new procedure (direct adjustment). | existence of underwork due to the foreseen quantities not being used up.
4144 | 2019704 | The object of this contract is the remodeling of the reservoir of the Cimo de Vila system in Ovar, including civil construction works, equipment and electrical and instrumentation installations | 50514200-3 | Repair and maintenance services of reservoirs | FALSE | 2015 | 2016 | Portugal | Ovar | Aveiro | 1 | N/A | 20-01-2016 | 31-10-2016 | 285 | 120 | 240000 | 189388.66 | 1 | 189388.66 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value of the proposal - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contractual deadlines due to difficulties resulting from weather conditions
4145 | 2019488 | Execution of the "Contract for the Improvement of a Section of the Rural Path of Espigão da Madeira (Achada/Northeast)" | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 24 | 01-12-2015 | 30-05-2016 | 181 | 180 | 290781.56 | 259998.3 | 2 | 261326.9 | -1328.6 | 99.4916 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Pursuant to Annex IV of the Program of Procedure. | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the deadline for carrying out the project. | carrying out more work
4146 | 2010022 | Refurbishment of the former premises of the Higher School of Education of Viseu - Polo de Lamego | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Lamego | Viseu | 20 | 11 | 10-02-2016 | 16-06-2016 | 127 | 60 | 340504.18 | 309847.78 | 2 | 309847.78 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: P- Price - 40% Technical value of the proposal - 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the arrival of material.
4147 | 1992951 | The objective of this contract is to renew the water supply network in streetPadre Acúrcio, parish and municipality of Oliveira do Bairro. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2015 | 2016 | Portugal | Oliveira do Bairro | Aveiro | 1 | N/A | 14-01-2016 | 29-08-2016 | 228 | 120 | 235000 | 166404.68 | 1 | 149780.68 | 16624 | 111.0989 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work was carried out within the contractual deadlines | contracted works, not performed
4148 | 1986728 | Public tender for the contract to remodel the water supply networks in Queijas. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2013 | 2016 | Portugal | Oeiras | Lisboa | 11 | 11 | 31-07-2014 | 19-01-2016 | 537 | 425 | 571000 | 342600.01 | 2 | 342600.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | since the deadline for the contract in question would end at the weekend, the respective provisional receipt notice was signed on the first working day immediately after (monday – 11/09/2015).
4149 | 1978587 | Contract for the rehabilitation and adaptation of the building, located in Quinta da Alfarrobeira, which will house the new headquarters of the Parish Council of São Domingos de Benfica. | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Lisboa | Lisboa | 11 | 30 | 04-01-2016 | 28-11-2016 | 329 | 150 | 348227.07 | 277370.65 | 2 | 291269.46 | -13898.81 | 95.2282 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the antiquity and historical characteristics of the building, it was necessary to carry out more work than was foreseen in the terms of reference. | extra work
4150 | 1954034 | The object of this contract is the construction of a water supply network with a total length of about 2055 m, 197 branches and 18 fire marks | 45232151-5 | Water-main refurbishment construction work | FALSE | 2015 | 2016 | Portugal | Ovar | Aveiro | 1 | N/A | 15-12-2015 | 19-07-2016 | 217 | 120 | 240000 | 218643.47 | 1 | 218643.47 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contractual deadlines, for reasons of coordinating work on the same site with other entities
4151 | 1950948 | Pavement Repair - The intervention consists of improving and repaving some streets and parking lots, located in the various parishes of the municipality of Vagos. | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Vagos | Aveiro | 1 | 30 | 12-01-2016 | 25-07-2016 | 195 | 180 | 348485.1 | 230478.62 | 1 | 253341.9 | -22863.28 | 90.9753 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | provisional receipt dated 07/06/2016 | existence of additional work, necessary for the correct completion of the project, with a cost of €24,618.20, and existence of underwork (quantities of work not carried out), totaling €1,753.20.
4152 | 1933487 | More efficiency in public lighting in the trough - Amares | 50000000-5 | Repair and maintenance services | FALSE | 2015 | 2016 | Portugal | Amares | Braga | 3 | N/A | 15-12-2015 | 13-01-2016 | 29 | 11 | 251075 | 237697.58 | 1 | 237697.58 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | it was carried out in less time than expected as more work teams were deployed
4153 | 1930426 | Execution of facilities for staff of the lu/djev de almada/cova da piedad/cacilhas (streetd. João de portugal - almada) | 45453100-8 | Refurbishment work | FALSE | 2015 | 2016 | Portugal | Almada | Setúbal | 17 | 24 | 07-12-2015 | 17-11-2016 | 346 | 150 | 221401.78 | 187000 | 1 | 187000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work.
4154 | 1929819 | Construction contract for the Supplementary Passive Treatment of the Mining Water Treatment System in the Mining Area of ​​Cunha Baixa | 45232450-1 | Drainage construction works | FALSE | 2015 | 2016 | Portugal | Mangualde | Viseu | 20 | 20 | 18-12-2015 | 27-05-2016 | 161 | 92 | 250000 | 185939.3 | 1 | 185939.3 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60%; 2. Technical Value of the Proposal - 40%. (As indicated in the Contest Program) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | finished on time
4155 | 1929790 | 2013.180.01.C1 - cefp barlavento - new workshop block - multipurpose workshop | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Portimão | Faro | 8 | 21 | 24-11-2015 | 01-06-2016 | 190 | 120 | 345000 | 343195.21 | 2 | 338417.58 | 4777.63 | 101.4118 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | over and underwork
4156 | 1926153 | Contract for Complementary Works on Safety and Environmental Recovery of the Former Mining Area of ​​Vale da Abrutiga | 45262310-7 | Reinforced-concrete work | FALSE | 2015 | 2016 | Portugal | Tábua | Coimbra | 6 | 20 | 28-12-2015 | 04-08-2016 | 220 | 92 | 320000 | 250404.66 | 2 | 250404.66 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | at the request of the performing entity, the extension of the total execution period of the contract was granted for an additional period of 60 days. the partial provisional reception took place on 03/06, having identified the need to correct some works, so an additional period of 15 days was granted until their completion and provisional reception
4157 | 1922983 | 2014.054.02.C1 - Coimbra Training Services - Remodeling of Pavilion 2 - 1st Phase | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Coimbra | Coimbra | 6 | 21 | 04-09-2015 | 28-07-2016 | 328 | 120 | 565000 | 548280 | 2 | 593204.8 | -44924.8 | 92.4268 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | additional | additional
4158 | 1920205 | Construction of the Malhadas Pontoon | 45221220-0 | Culverts | FALSE | 2013 | 2016 | Portugal | Vagos | Aveiro | 1 | 30 | 28-12-2015 | 12-10-2016 | 289 | 90 | 191107 | 168380 | 1 | 165345.71 | 3034.29 | 101.8351 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work no. 1, due to the unavailability of land needed to widen the pier - period from 28/01/2016 to 08/03/2016. suspension of works n.º 2, due to the lv electric power line not having been changed yet, which prevents the projects - period from 09/03/2016 to 08/05/2016. extension of the deadline for a period of 18 days, based on unforeseen events that occurred during the project, namely the weather conditions that occurred at the beginning of the project, transfer of the pipeline adjacent to the project and the dam made downstream of the project by a private individual. | resulting from the calculated price revision (-3,034.29 €).
4159 | 1918707 | 2015.124.01.C1 - SFP Amadora - Renovation of the Home Pavilion and kitchen facilities | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Amadora | Lisboa | 11 | 23 | 16-07-2015 | 29-09-2016 | 441 | 120 | 600000 | 414344.22 | 2 | 414344.22 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | not included in the process
4160 | 1912282 | IP network requalification - replacement of VSAP luminaires for LED luminaires - 2nd Phase | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2015 | 2016 | Portugal | Tondela | Viseu | 20 | 11 | 18-12-2015 | 21-10-2016 | 308 | 10 | 191000 | 190000 | 1 | 190000 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Those contained in the procedure program | 0 | 0 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4161 | 1898866 | More energy efficiency in public lighting in Cávado - Municipality of Barcelos. | 45310000-3 | Electrical installation work | FALSE | 2015 | 2016 | Portugal | Barcelos | Braga | 3 | 9 | 15-12-2015 | 11-01-2016 | 27 | 30 | 828617.72 | 745755.96 | 2 | 745755.96 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price (50%); b) Technical Valuation of the Proposal (50%): b1) "PT" Work Plan (25%); b2) "PM" Labor Plan (25%); b3) "PE" Equipment Plan (25%); b4) Interconnection/compatibility between Work Plans, Manpower Plan, "IC" Equipment Plan (25%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to complete the execution of the projects before the end of 2015 (community funds).
4162 | 1896973 | Rehabilitation of the Varadouro Ramp in Porto da Ericeira | 45243000-2 | Coastal-defence works | FALSE | 2015 | 2016 | Portugal | Mafra | Lisboa | 11 | N/A | 09-12-2015 | 22-04-2016 | 135 | 120 | 188000 | 173826.44 | 1 | 233263.62 | -59437.18 | 74.5193 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% deadline 5% 20% descriptive memory Work plan 15% Labor and equipment plan 10% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
4163 | 1896264 | Rehabilitation of the breakwater and floating walkways at Porto de Recreio de Olhão | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Olhão | Faro | 8 | N/A | 19-11-2015 | 22-07-2016 | 246 | 98 | 255000 | 169068 | 1 | 174168 | -5100 | 97.0718 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 40% Technical Quality 60% | 1 | 40 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | extra work
4164 | 1880642 | Preparatory works, Demolitions, Foundations, Formwork, Strutting and Constructive Phasing, Steel for Reinforced Concrete, Prefabricated Elements, other works | 45221220-0 | Culverts | FALSE | 2015 | 2016 | Portugal | Figueira da Foz | Coimbra | 6 | 22 | 26-11-2015 | 05-07-2016 | 222 | 110 | 344750 | 312483.07 | 2 | 306798.76 | 5684.31 | 101.8528 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1 - Price K2 - Technical value K3 - Technical value of the Preliminary Study The most economically advantageous proposal will result from the application of the weighting of the factors according to the mathematical expression that the the following is explained: K= 0.8*K1+0.15*K2+0.05*K3 | 1 | 80 | N/A | FALSE | Complete fulfillment of the contract+AE4166 | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the level of the water line of the ditch | price review
4165 | 1871833 | Public Tender for a contract for the replacement of water supply networks and lowering of branches in the streets confluent with Av. Padre Himalaya, in the parish of Águas Livres | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2016 | Portugal | Amadora | Lisboa | 11 | 11 | 25-11-2015 | 16-09-2016 | 296 | 279 | 332000 | 199200.01 | 1 | 169665.25 | 29534.76 | 117.4077 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to clause 28 of the Program of Procedure | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor created conditions for the deadline for completion of the project to be anticipated, | there was no need to carry out all the project initially planned, as only the project carried out was paid
4166 | 1871785 | Public Tender for the contract for the replacement of covers and repair of sanitation branches and manholes in the Municipality of Amadora - Years 2015/2016 | 45232410-9 | Sewerage work | FALSE | 2015 | 2016 | Portugal | Oeiras | Lisboa | 11 | 20 | 25-11-2015 | 27-06-2016 | 215 | 365 | 400000 | 240000.01 | 1 | 234570.01 | 5430 | 102.3149 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to clause 28 of the Program of Procedure | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | the difference between the contracted and invoiced amounts is justified because, on site, there was no need to carry out all the project initially planned, as only the project performed was paid.
4167 | 1863228 | Contract No. 16/2015 - Its purpose is to contract for the construction of the animal waste processing center. | 45210000-2 | Building construction work | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 20 | 19-11-2015 | 30-08-2016 | 285 | 100 | 500000 | 425000 | 2 | 450508.28 | -25508.28 | 94.3379 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (F1) - 70% Work plan quality (F2) - 30% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | this contract was contiguous to other contracts, namely lots 1 and 3 of the infrastructures and due to the suspensions of the same, there were works that were not possible to carry out as they depend on their completion. in addition, in the months of december, january and february, it was impossible to circulate the equipment for this contract on site due to the constant circulation of vehicles and machines to support the energy recovery center. this situation made several concreting impossible. | construction of a shed to cover this structure in order to allow greater comfort for employees who have to work on rainy days
4168 | 1857289 | Intervention contract on the Roof of the Pavilion of the University Stadium | 45261920-9 | Roof maintenance work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 36 | 09-11-2015 | 22-06-2016 | 226 | 120 | 290000 | 288696.5 | 2 | 285689 | 3007.5 | 101.0527 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global price proposed for the Contract - score represented by VP ----- 40%; b) Technical value of the proposal - score represented by VT ----------- 60%. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension. | referred decreases.
4169 | 1855164 | Rehabilitation of the Lóios Pavilion | 45212200-8 | Construction work for sports facilities | FALSE | 2015 | 2016 | Portugal | Lisboa | Lisboa | 11 | 30 | 16-11-2015 | 12-11-2016 | 362 | 120 | 300000 | 299001.9 | 2 | 335015.98 | -36014.08 | 89.25 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the change in the term of the contract is due to more work and errors and omissions | existence of work to supply errors and omissions and additional work
4170 | 1851855 | 2013.517.30.C1 - Xabregas Building - Glazed coverage of the access patio to the Cafeteria | 45261900-3 | Roof repair and maintenance work | FALSE | 2014 | 2016 | Portugal | Lisboa | Lisboa | 11 | 22 | 17-06-2015 | 18-04-2016 | 306 | 57 | 200500 | 157777.77 | 1 | 156737.77 | 1040 | 100.6635 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%, Proposed technical value: 30% and deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completed works
4171 | 1849132 | The object of this contract is the execution of the Contract referring to the "Improvement of Municipal Roads EM555 and EM616 (Assanhas - Prados - county boundary (Videmonte) Guarda" | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Celorico da Beira | Guarda | 9 | 30 | 30-10-2015 | 07-06-2016 | 221 | 90 | 300000 | 261332.56 | 2 | 261332.56 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions forced the suspension of work execution.
4172 | 1848245 | Execution of installations for the staff of lu/djev (urban cleaning/division of gardens and green spaces) in orange tree/feijó - orange market, streetd. duarte | 45454000-4 | Restructuring work | FALSE | 2015 | 2016 | Portugal | Almada | Setúbal | 17 | 24 | 05-10-2015 | 07-12-2016 | 429 | 240 | 491000 | 387890 | 2 | 345535.66 | 42354.34 | 112.2576 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: Factor 1: Technical Value of the Proposal (40%), with subfactors: PT1: Work Execution Plan (30 Points) and PT2: Means of Equipment and Labor to be assigned to the Work (10 Points) Factor 2 - Proposal Price - (60%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | deletion of works.
4173 | 1844551 | EXECUTION OF THE 2014 PARTICIPATORY BUDGET - Project execution contract | 45113000-2 | Siteworks | FALSE | 2015 | 2016 | Portugal | Leiria | Leiria | 10 | 20 | 22-10-2015 | 20-06-2016 | 242 | 120 | 232382.22 | 159296.02 | 1 | 159296.02 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4174 | 1834952 | Requalification of Parque das Hortas and surrounding area | 45233160-8 | Paths and other metalled surfaces | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 16-11-2015 | 09-12-2016 | 389 | 210 | 2599357.85 | 1975096.58 | 3 | 1961116.46 | 13980.12 | 100.7129 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | following the inspection notice for provisional acceptance (19/09/2016), the contractor had to carry out the necessary repairs and was granted a period of 20 days. | existence of underwork corresponding to the non-exhaustion of the quantities of work foreseen in the bill of quantities.
4175 | 1826301 | The contract consists of "Repaving streets in Bairro Alice", | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Albufeira | Faro | 8 | 20 | 13-11-2015 | 11-11-2016 | 364 | 30 | 200000 | 153669.67 | 1 | 153669.67 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change to the execution period of the project, due to delays on the part of the contractor
4176 | 1817084 | Public works contract for the rehabilitation of the Francisco Vieira stream | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 24 | 09-11-2015 | 31-10-2016 | 357 | 180 | 550000 | 467500.01 | 2 | 427320.06 | 40179.95 | 109.4028 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1) Price - 40% K2) Technical quality of proposals - 60% distributed by the following subfactors and weighting coefficients: K2.1) Work plan (70%); K2.2) Descriptive memory and justification of the execution of the work (30%) | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for carrying out the contract has not been changed. | underwork
4177 | 1782978 | Eb 2307 - waste water drainage network in the parish of britelo – municipality of celorico de basto | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Celorico de Basto | Braga | 3 | 41 | 27-01-2015 | 30-06-2016 | 520 | 180 | 1100000 | 798333.39 | 2 | 783084.03 | 15249.36 | 101.9473 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project had layout errors, some of which were in the private domain, which led to corrections during the course of the project. there was also a large amount of buried public and private infrastructure, not registered, which hindered and delayed the projects. | underwork
4178 | 1782774 | Eb 2306 - construction of wastewater drainage networks in the parish of arnóia - municipality of celorico de basto | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Celorico de Basto | Braga | 3 | 41 | 26-02-2015 | 30-05-2016 | 459 | 210 | 1600000 | 1159646.29 | 3 | 1152230.85 | 7415.44 | 100.6436 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project had layout errors, some of which were in the private domain, which led to corrections during the course of the project. there was also a large amount of buried public and private infrastructure, not registered, which hindered and delayed the project. | underwork
4179 | 1782100 | Contract for the execution of the sealing of the dump on the island of Corvo and construction of the inert landfill | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2016 | Portugal | Corvo | Região Autónoma dos Açores | 15 | 30 | 09-11-2015 | 27-12-2016 | 414 | 200 | 345000 | 338500 | 2 | 338500 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: K1) Price - 40% K2) Technical quality of proposals - 60% distributed by the following subfactors and weighting coefficients: K2.1) Work plan (70%); K2.2) Descriptive memory and justification of the execution of the work (30%) | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension 47 days | there were no changes to the value of the project
4180 | 1781572 | Exterior improvement of the neighborhood of S. Roque da Lameira (blocks 21 to 23) (EM.004.2015.129) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 21 | 29-10-2015 | 17-10-2016 | 354 | 210 | 900000 | 797695.18 | 2 | 761585.91 | 36109.27 | 104.7413 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70% and Technical Valuation of Proposal 30%; Subfactors (Technical value): Methodology 50%, Work Program 40% and Safety 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project on the contract proceeded normally, in accordance with the specification in the tender specifications and without incidents worthy of record
4181 | 1780558 | Contract No. 13/2015 - the purpose of contracting the Contract for the Construction of Infrastructure, Support Buildings and Organic Valorization Center (Phase 1). | 45111290-7 | Primary works for services | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 20 | 19-10-2015 | 30-08-2016 | 316 | 60 | 713250.71 | 712425.14 | 2 | 712425.14 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: Price (F1) - 70% Work plan quality (F2) - 25% Characteristics of the materials and equipment to be used (F3) - 5% | 1 | 70 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the reasons were explained in the field "reference dates for the execution of the project"
4182 | 1775087 | More energy efficiency in public lighting in Cávado - municipality of Braga. | 45317000-2 | Other electrical installation work | FALSE | 2015 | 2016 | Portugal | Braga | Braga | 3 | 30 | 05-11-2015 | 17-06-2016 | 225 | 75 | 1066494 | 771034.53 | 2 | 771034.53 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in inspections and laboratory tests to rule out manufacturing defects.
4183 | 1754423 | Execution of the Contract for "Maintenance Dredging in the Vila do Conde Recreation Center and Access Channel" | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2016 | Portugal | Vila do Conde | Porto | 13 | 11 | 29-10-2015 | 29-06-2016 | 244 | 60 | 391000 | 307748.2 | 2 | 307748.2 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1 - The award is carried out according to the criterion of the most economically advantageous tender, taking into account the following factors and sub-factors and respective weighting coefficients: a) Technical suitability of the proposal (50%), assessed taking into account the following subfactors: a1) Proposed constructive processes analyzed based on the detail and coherence of the elements contained in the descriptive memory and justification (10%); a2) Suitability of the work program to the work and local conditions (40%); b) Price (50%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather
4184 | 1738718 | Conservation and Improvement of streets in the Municipality of Almada - 1st Action 2015 | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Almada | Setúbal | 17 | 21 | 10-09-2015 | 21-06-2016 | 285 | 120 | 424528.3 | 328578.8 | 2 | 328578.8 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work.
4185 | 1737950 | Rehabilitation and correction of anomalies in blocks 46 to 52 of Bairro de Santa Luzia (EM.004.2015.105) | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 21 | 22-10-2015 | 25-08-2016 | 308 | 240 | 502000 | 428521.86 | 2 | 428194.26 | 327.6 | 100.0765 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%; Technical Value of the Proposal 30% (Subfactors: Methodology 50%; Affected means 40% and Safety 10%) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract work proceeded normally, with the contractor proceeding with the partial delivery of the blocks within the contractually foreseen completion deadlines. | work not carried out worth €327.60
4186 | 1735383 | Requalification and improvement of streets of the municipal road network | 45233223-8 | Carriageway resurfacing works | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 21-10-2015 | 23-09-2016 | 338 | 180 | 1666216.96 | 1159462.57 | 3 | 1099541.85 | 59920.72 | 105.4496 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 60% Technical Value - 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the works were executed earlier. | existence of underwork due to the foreseen quantities not being used up.
4187 | 1727542 | Contract for "Maintenance Dredging in Portinho de Vila Praia de Âncora" | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2016 | Portugal | Caminha | Viana do Castelo | 18 | 11 | 21-10-2015 | 24-03-2016 | 155 | 45 | 365550 | 329867.1 | 2 | 324264.38 | 5602.72 | 101.7278 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Technical adequacy of the proposal (50%), assessed taking into account the following subfactors: a1) Proposed constructive processes analyzed based on the detail and coherence of the elements contained in the descriptive memory and justification (10%); a2) Suitability of the work program to the work and local conditions (40%); b) Price (50%). | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension by the owner of the project due to lack of safety conditions, due to maritime agitation. | there was no mobilization of all the dredging equipment
4188 | 1702864 | Rehabilitation and correction of anomalies in blocks 32 to 36 of Bairro de Santa Luzia (EM.004.2015.106 | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 21 | 07-10-2015 | 13-07-2016 | 280 | 180 | 345000 | 336917.46 | 2 | 336492.41 | 425.05 | 100.1263 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 70%; Technical Value of the Proposal 30% (Subfactors: Methodology 50%; Affected means 40% and Safety 10%. | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project on the contract proceeded normally and within the contractually established period. | work not carried out worth €425.00
4189 | 1693222 | Installation of an economic canteen in a municipal building - S. Paio | 45454000-4 | Restructuring work | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 12-10-2015 | 11-05-2016 | 212 | 210 | 469674.76 | 305999.72 | 2 | 295507.11 | 10492.61 | 103.5507 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the contractor completed the project early. | underwork due to not carrying out the amounts of work provided for in the bill of quantities.
4190 | 1685134 | Construction of support building/stands - Pinhel football field. | 45000000-7 | Construction work | FALSE | 2015 | 2016 | Portugal | Pinhel | Guarda | 9 | N/A | 14-09-2015 | 30-11-2016 | 443 | 90 | 350019.5 | 339972.16 | 2 | 338388.06 | 1584.1 | 100.4681 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | miscellaneous conditions | underwork
4191 | 1684614 | Refurbishment of the Auction Buildings in Lagos and Sagres | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Vila do Bispo | Faro | 8 | N/A | 08-10-2015 | 15-04-2016 | 190 | 105 | 330000 | 318943 | 2 | 356018.01 | -37075.01 | 89.5862 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 50%; Technical Quality of the Proposal 50% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4192 | 1674317 | Use of the outer net area of ​​the setúbal fishermen's dock | 45244100-0 | Marine installations | FALSE | 2015 | 2016 | Portugal | Setúbal | Setúbal | 17 | 20 | 02-10-2015 | 05-05-2016 | 216 | 90 | 475000 | 473999.96 | 2 | 473999.96 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Price - 40% 2) Technical value of the proposal - 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4193 | 1673461 | Repair of the 1st lagoa Waterproofing System | 45247270-3 | Reservoir construction works | FALSE | 2015 | 2016 | Portugal | Corvo | Região Autónoma dos Açores | 15 | 20 | 13-10-2015 | 30-06-2016 | 261 | 120 | 305174.86 | 279000 | 2 | 279000 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A) Technical Value of the Proposal - 55%, subfactors: Work plan - 70% and Descriptive memory and justification of the way of execution - 30% B) Price - 45% | 1 | 45 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | grace period extension authorization
4194 | 1659621 | Complementary interventions for the reconstruction of the Mouchão de Pernes waterfall, Santarém | 45220000-5 | Engineering works and construction works | FALSE | 2015 | 2016 | Portugal | Santarém | Santarém | 16 | 20 | 02-10-2015 | 25-11-2016 | 420 | 70 | 228894.89 | 174868.49 | 1 | 163923.86 | 10944.63 | 106.6767 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project | underwork
4195 | 1656818 | 2013.122.01.C1 - Olaias Building - Renovation of the 1st and 2nd Floors | 45213150-9 | Office block construction work | FALSE | 2014 | 2016 | Portugal | Lisboa | Lisboa | 11 | 22 | 27-04-2015 | 14-10-2016 | 536 | 135 | 1400000 | 1049995 | 3 | 1100673.8 | -50678.8 | 95.3957 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%, Proposed technical value: 30% and deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional | additional
4196 | 1634929 | Paving of the Municipal Road in Coucinheira - Limit of the Council - Parish of Amor | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Leiria | Leiria | 10 | 20 | 16-09-2015 | 11-04-2016 | 208 | 60 | 215000 | 160462.05 | 1 | 160462.05 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change
4197 | 1630572 | Convent of Christ - Recovery of the north facades | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2016 | Portugal | Tomar | Santarém | 16 | 20 | 15-09-2015 | 21-04-2016 | 219 | 90 | 320000 | 245612.11 | 1 | 245612.11 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Those listed in the tender program | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were two partial suspensions, due to the study related to parietal archeology
4198 | 1619199 | Contract for the construction and improvement of agricultural paths cs4 - sloth and cs8 - serroa - poa west zone of são jorge - island of são jorge | 45233120-6 | Road construction works | FALSE | 2015 | 2016 | Portugal | Velas | Região Autónoma dos Açores | 15 | 36 | 10-08-2015 | 01-09-2016 | 388 | 210 | 435000 | 375250 | 2 | 335423.67 | 39826.33 | 111.8734 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 40% and Technical Quality of proposal 60% Subfactors of the technical quality factor: Work plan 70% and Descriptive memory and justification of the way the work was carried out 30% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work finished ahead of schedule | underwork
4199 | 1618339 | PROVERE - Environmental Requalification of the Dão River Banks - Termas de Alcafache - Requalification of the Public Space - 2nd. Procedure - Completion of Works | 45247220-8 | Weir construction work | FALSE | 2015 | 2016 | Portugal | Viseu | Viseu | 20 | 24 | 10-04-2015 | 10-11-2016 | 580 | 49 | 2018000 | 156751.01 | 1 | 147693.28 | 9057.73 | 106.1328 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | execution of additional work | performing over and underwork
4200 | 1611953 | Public tender for the award of a contract for "infrastructures of the business reception area of ​​Alvarães - Industrial Zone of Alvarães - 2nd phase" | 45113000-2 | Siteworks | FALSE | 2015 | 2016 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 23-09-2015 | 26-10-2016 | 399 | 120 | 399699 | 314630.55 | 2 | 314630.55 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 40%. Technical Value of the Proposal - 60%. The subfactors are those contained in article 18 of the tender program | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
4201 | 1610083 | EB 2308 - Construction of water supply networks in the parish of Bustelo (Amarante) | 45247270-3, 45232150-8 | Reservoir construction works, Works related to water-distribution pipelines | FALSE | 2014 | 2016 | Portugal | Amarante | Porto | 13 | 41 | 24-07-2015 | 15-12-2016 | 510 | 120 | 515000 | 349952.98 | 2 | 306012.01 | 43940.97 | 114.3592 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Overall price 50% 2) Technical value of the proposal 50% | 1 | 50 | Yes (no values) | TRUE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | alteration of the initial project due to the fact that there is a temporary reservoir at the project site | alteration of the initial project due to the fact that there is a temporary reservoir at the project site
4202 | 1589918 | Reinforcement of the Protection of the Douro Estuary Bank | 45246200-5 | Riverbank protection works | FALSE | 2015 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 18-09-2015 | 08-01-2016 | 112 | 90 | 798500 | 573840 | 2 | 573840 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (P) - 50% Technical Quality of the Proposal (QTP) - 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the owner of work was interested in anticipating the terminus of the project, due to the need to meet the application deadline for the contract.
4203 | 1589776 | Construction of the Sintra training ground of the National Firefighters School (ENB) | 45210000-2 | Building construction work | FALSE | 2015 | 2016 | Portugal | Sintra | Lisboa | 11 | 20 | 21-08-2015 | 28-10-2016 | 434 | 150 | 450000 | 366304.68 | 2 | 366304.68 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Award will be made to the proposal economically more advantageous, this being dedeadlineined by assessing the factors listed below 20.1.1 PRICE The weighting of this factor will have the importance of 60%, and its score will result from one of the following formulas: a) If the value of the bid presented by competitor i is in the range: Pc >=0.6 x Pb The formula will apply: Pi = ((Pb-Pc) / (0.4 x Pb)) x 80 b) If the value of the bid presented by competitor i is in the range: Pc < 0.6 x Pb The formula will apply: Pi = 80 + (1-(Pc / (0.6 x Pb)) x 20 if the justification of the abnormally low price is accepted, under the deadlines of paragraph 4 of article 71 of the Public Contracts Code, in which: Pi - Ranking of competitor i's proposal in deadlines of price Pc - Competitor bid price Pb - Base Price 20.1.2 TECHNICAL VALUE OF THE PROPOSAL (VTP) The weighting of this factor will have the importance of 40%, and its score will result from the analysis of four sub-factors, taking into account their decomposition and methodologies provided for and described below, with each proposal being assigned a score depending on the assessment of the integral aspects of each of them: 20.1.2.1 - Work Plan, with a weighting of 25% of the VTP For the evaluation of the sub-factor "Work Plan", the methodologies proposed for the execution of the work will be analyzed, where takes into account the relevant aspects for the correct planning of the contract in its particular and specific aspects duly adapted to and reported to the work in competition. The work plan allows obtaining information on the activities that make up the contract, and be as complete as possible. Thus, in this parameter, the presentation of all the main activities will be evaluated, the respective duration with indication of the start and end dates of the activities, their precedence relationships, the critical path and yield of works. 20.2 GLOBAL EVALUATION OF PROPOSALS For the global evaluation of the proposals and taking into account the above criteria, the following calculation algorithm is established: CF = A1 + A2 + A3 + A4 + Pi x 0.6 | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions.
4204 | 1584541 | Construction contract for the New Headquarters of the Parish Council of Marvila | 45211350-7 | Multi-functional buildings construction work | FALSE | 2013 | 2016 | Portugal | Lisboa | Lisboa | 11 | N/A | 07-11-2014 | 19-11-2016 | 743 | 300 | 928642.15 | 767857.48 | 2 | 866135.14 | -98277.66 | 88.6533 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the term of the contract is due to the suspension at the beginning of the project for the replacement of electrical equipment by edp, and due to the extra work and errors and omissions. | the change in the value of the contract is due to the performance of more work and errors and omissions
4205 | 1572718 | Contract for the rehabilitation of the São Bento stream - Angra do Heroísmo - Terceira Island | 45220000-5 | Engineering works and construction works | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 24 | 07-09-2015 | 14-12-2016 | 464 | 365 | 1400000 | 1190000.01 | 3 | 1062446.32 | 127553.69 | 112.0057 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A - Densification of the "Price" factor (K1) (40%) and respective partial score: The evaluation of the price factor results in a score between a minimum value of 0 (zero) and a maximum of 20 (twenty), of according to the following formula: K1 = ((Pb-Pp))/Pb x 20 On what: Pp = value of the proposal under analysis; Pb = base price of the procedure; The score obtained by applying the formula above is rounded up or down to the nearest hundredth. B - Densification of the factor "technical quality of the proposal" (K2) (60%) and respective partial score: This factor is subdivided into two sub-factors, with the following weighting: K2.1 - Work plan - 70% K2.2 - Descriptive memory and justification of how the work was carried out - 30% The score of this factor (K2) results from the following formula: K2 = (0.70xK2.1) + (0.30xK2.2) On what: K2.1 = score assigned to the "Work plan" subfactor, resulting from the sum of all partial values ​​assigned in each one of the attribute sets of the respective descriptor. K2.2 = score assigned to the subfactor "Descriptive memory and justification of the way the work was carried out" resulting from the sum of all partial values ​​assigned in each of the sets of attributes of the respective descriptor. The score obtained by applying the formula above is rounded up or down to the nearest hundredth. The final score of each proposal is obtained using the following formula: (PF) Final Score = (K1 x 0.4) + (K2 x 0.6) On what: K1 = Score obtained in the bid price factor; K2 = Score obtained in the technical quality factor of the proposal. The application of the aforementioned formula results in a global score between 0 (zero) and 20 (twenty), the proposal being considered economically more advantageous is the one whose score is closest to the maximum value of 20 (twenty). The score obtained by applying the formula above is rounded up or down to the nearest hundredth. In case there is a tie in the overall score of the proposals, the best score obtained in the "technical quality of the proposal" factor and, if the tie persists, the best score obtained in the "price" factor and, if still so the tie persists, the order of reception of the proposals. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project proceeded at a good pace, with a well-linked cadence of works, having finished before the deadline. | underwork.
4206 | 1572529 | The list of the main civil construction works is as follows, among other works: • Discharge chambers, properly speaking. • Ecological flow discharge hydraulic circuit. | 45248000-7 | Construction work for hydro-mechanical structures | FALSE | 2015 | 2016 | Portugal | Bragança | Bragança | 4 | 20 | 17-08-2015 | 13-07-2016 | 331 | 150 | 170000 | 150668.46 | 1 | 150668.61 | -0.15 | 99.9999 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40% Technical value of the proposal: 50% Guarantee of compliance with the Execution Period: 10% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | rounding due to sap billing computer programming (systeme, anwendungen und produkte)
4207 | 1566978 | Repaving work on streets in the municipality | 45000000-7 | Construction work | FALSE | 2015 | 2016 | Portugal | Barreiro | Setúbal | 17 | 20 | 05-08-2015 | 04-08-2016 | 365 | 90 | 349000 | 272349.08 | 2 | 266229.04 | 6120.04 | 102.2988 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: a) Proposal price - 60% b) Quality of the proposal - 40% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension (by the owner) due to lack of safety conditions
4208 | 1558561 | Contract No. 10/2015 - Purpose of contracting the contract for the construction of a piezometric borehole to monitor the water downstream of the Waste Treatment and Recovery Center on Ilha Terceira | 76431400-7 | Rathole well-drilling services | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 18 | 04-09-2015 | 10-05-2016 | 249 | 60 | 289750 | 202825.01 | 1 | 20825.01 | 182000 | 973.9492 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price - 70% Quality of Work Plan - 30% | 1 | 70 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | - delay in starting the contract; - suspension of time due to a fact attributable to the successful tenderer;
4209 | 1556718 | Construction contract for the water supply to the crop in the area of ​​Pico da Bagacina | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 27 | 03-09-2015 | 25-05-2016 | 265 | 150 | 230000 | 195500.01 | 1 | 178810.61 | 16689.4 | 109.3336 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 40% and Technical Quality of proposal 60% Sub-factors of the technical quality factor: Work plan 70% and Descriptive memory and justification of how the work was carried out 30% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work finished ahead of schedule | underwork
4210 | 1550036 | Assembly and disassembly of the support site for the work in general; Milling of the existing pavement; Paving the bituminous concrete layer; Adjustment of lids of manholes and sinks; | 45233200-1 | Various surface works | FALSE | 2015 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 31 | 03-09-2015 | 14-03-2016 | 193 | 90 | 290450 | 228634.75 | 1 | 228634.75 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (P) 60% Technical Quality of the Proposal (QTP) 40% | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was an extension to the contract period
4211 | 1542771 | 0030/DOM/DGEPIM/15 - Refurbishment of the cellar entrance and parking lot at the Marquês de Pombal Palace | 45233200-1 | Various surface works | FALSE | 2015 | 2016 | Portugal | Oeiras | Lisboa | 11 | 30 | 25-08-2015 | 11-10-2016 | 413 | 45 | 428892.01 | 257335.22 | 2 | 201895.42 | 55439.8 | 127.4597 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: F1 - Price (60%); F2 - Value and technical feasibility of the proposal (30%); F3 - Deadline execution (10%) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4212 | 1542688 | Its objective is to replace existing luminaires with more efficient luminaires with savings in terms of energy consumption and a reduction in CO2 emissions. | 45000000-7 | Construction work | FALSE | 2015 | 2016 | Portugal | Esposende | Braga | 3 | 30 | 02-09-2015 | 17-05-2016 | 258 | 90 | 363000 | 304800 | 2 | 304800 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution period of the project
4213 | 1540198 | Contract for the Refurbishment and Expansion of the Nursery and Kindergarten at the Children's Center of Angra do Heroísmo, "O Baloiço" College, paragraph b), article 19, of the CCP | 45262800-9 | Building extension work | FALSE | 2014 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 31 | 03-10-2014 | 02-12-2016 | 791 | 420 | 967000 | 945425.9 | 2 | 945425.9 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4214 | 1533980 | Contract for Construction of Paim Nursery | 45215215-7 | Children's home construction work | FALSE | 2015 | 2016 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 30 | 06-07-2015 | 02-11-2016 | 485 | 420 | 1350000 | 1147500.01 | 3 | 1145430.37 | 2069.64 | 100.1807 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factor K1 - Price 40%; K2 factor - Quality Proposal Technique 60%, with the subfactors K2.1 Work Plan 42% and K2.2 Descriptive Memorandum and justification for execution of the Work 18% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4215 | 1533882 | 1. This Contract comprises the clauses to be included in the contract to be signed within the scope of the public tender for carrying out the Construction Contract, by lots, of Infrastructures, Buildings | 45233140-2 | Roadworks | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 20-08-2015 | 30-08-2016 | 376 | 150 | 2143104.61 | 759000 | 2 | 759000 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (F1) - 70% Work plan quality (F2) - 25% Characteristics of the materials and equipment to be used (F3) - 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the works were suspended due to the lack of security for the execution of works due to weather conditions, as well as for using the site of the mentioned contract for access to the crushing works that are used in the energy recovery center.
4216 | 1533570 | School Center – Pavilion – Construction of Gym | 45212222-8 | Gymnasium construction work | FALSE | 2015 | 2016 | Portugal | Sousel | Portalegre | 12 | 9 | 20-08-2015 | 14-04-2016 | 238 | 60 | 171500 | 162508.83 | 1 | 162508.83 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4217 | 1532196 | 1. This Contract comprises the clauses to be included in the contract to be signed within the scope of the public tender for carrying out the Construction Contract, by lots, of Infrastructures, Buildings | 45210000-2 | Building construction work | FALSE | 2015 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 20-08-2015 | 30-08-2016 | 376 | 150 | 2143104.61 | 709978.59 | 2 | 709978.59 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (F1) - 70% Work plan quality (F2) - 25% Characteristics of the materials and equipment to be used (F3) - 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the works were suspended due to the lack of security for the execution of works due to weather conditions, as well as for using the site of the mentioned contract for access to the crushing works that are used in the energy recovery center.
4218 | 1530605 | Improvement and Paving of municipal roads EM 537 from Santa Comba de Rossas to Pinela | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Bragança | Bragança | 4 | 20 | 24-08-2015 | 05-07-2016 | 316 | 120 | 345000 | 319491 | 2 | 314856 | 4635 | 101.4721 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price (weighting) of 70%) b) Technical value (30% weighting) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions for the application of horizontal painting | underwork
4219 | 1529867 | public works contract for the construction of the water supply system in the path of fornos and ppa | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2015 | 2016 | Portugal | Vila Franca do Campo | Região Autónoma dos Açores | 15 | 27 | 09-07-2015 | 29-02-2016 | 235 | 240 | 310000 | 245039.42 | 1 | 212354.74 | 32684.68 | 115.3915 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Factors: Price 40% and Technical Quality 60% Subfactors of the Technical Quality factor: Work Plan 70% and Justification and descriptive memory of the way the work was carried out 30% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ended ahead of schedule | underwork
4220 | 1529689 | public works contract for the construction of the path of the mine | 45233120-6 | Road construction works | FALSE | 2015 | 2016 | Portugal | Ribeira Grande | Região Autónoma dos Açores | 15 | 21 | 06-07-2015 | 12-02-2016 | 221 | 150 | 215000 | 165972.6 | 1 | 159982.59 | 5990.01 | 103.7442 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work finished ahead of schedule | underwork
4221 | 1527756 | Energy efficiency in public lighting in the municipality of Espinho | 45316000-5 | Installation work of illumination and signalling systems | FALSE | 2015 | 2016 | Portugal | Espinho | Aveiro | 1 | 20 | 20-08-2015 | 11-04-2016 | 235 | 60 | 705275 | 689839.96 | 2 | 689839.96 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Global Price 10% Technical value of the proposal 80% deadline 10% | 1 | 10 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution period.
4222 | 1525872 | The purpose of the Contract is to perform maintenance dredging on the bar, access channel and port of Póvoa de Varzim. | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2016 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 18-08-2015 | 10-11-2016 | 450 | 105 | 1558400 | 1394150 | 3 | 1389150 | 5000 | 100.3599 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award is carried out according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors and respective weighting coefficients a) Technical value of the proposal (50%), evaluated by the methodology contained in Annex IV to the tender program; a1) Proposed constructive processes analyzed based on the detail and coherence of the elements contained in the descriptive memory and justification (10%); a2) Adequacy to the work and local conditions, work plans, labor and equipment to be used (40%); b) Price (50%), scored using the value function graphed in Annex V to the tender schedule. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | alteration of the dredge deposit. | changing the location of the dredge deposit.
4223 | 1520545 | Improvement of streetde Cabeda, in Alfena, as well as a small extension of streetD. Pedro IV, in Valongo, which will include (partial) reprofiling, paving of the aforementioned streets | 45233223-8 | Carriageway resurfacing works | FALSE | 2015 | 2016 | Portugal | Valongo | Porto | 13 | 12 | 05-08-2015 | 14-09-2016 | 406 | 60 | 205000 | 178028.1 | 1 | 168237.07 | 9791.03 | 105.8198 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. the last measurement report was prepared on november 20, 2015, however there was a delay in provisional acceptance, taking into account that there was a negative inspection on january 7, 2016, given the existence of anomalies, with a deadline of 4 months to repair them | approved by order of 22.05.2019 the definitive price revision in the amount of - €9,791.03 + vat (credit in favor of the city council)
4224 | 1520531 | Fetais elementary school - Rehabilitation of Block 3 | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2015 | 2016 | Portugal | Loures | Lisboa | 11 | N/A | 26-06-2015 | 16-02-2016 | 235 | 75 | 299945.61 | 232988 | 1 | 232988 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Proposal price 40% Work plan 30% Execution time 30% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4225 | 1519452 | Assembly of the shipyard to support the work in general; Supply and installation of a luminous flux regulation system; Opening, covering ditches and rebuilding floors; | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2014 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 31-07-2015 | 19-01-2016 | 172 | 240 | 900000 | 862813.09 | 2 | 811862.51 | 50950.58 | 106.2758 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | there is an amendment to the contract, in which the period for carrying out the project is changed. | existence of underworks.
4226 | 1517261 | The object of the contract is the contract for "Navigability of the Guadiana River between Vila Real de Santo António and Alcoutim". | 45252124-3 | Dredging and pumping works | FALSE | 2015 | 2016 | Portugal | Castro Marim | Faro | 8 | 11 | 29-07-2015 | 19-01-2016 | 174 | 90 | 480000 | 383783.75 | 2 | 414582.98 | -30799.23 | 92.571 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award is carried out according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors and respective weighting coefficients: a) Technical value of the proposal (50%), assessed using the methodology set out in Annex IV to the tender program; b) Price (50%) scored using the value function graphed in Annex V to the tender schedule. The subfactors and respective qualitative analysis descriptors, and respective weightings and scores, to be considered for the evaluation of the factor "Technical value of the proposal" are the following: a1) Proposed constructive processes analyzed based on the detail and coherence of the elements contained in the descriptive memory and justification - 20%; a2) Adequacy to the work and local conditions, work plans, labor and equipment to be used - 30%. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | geotechnical conditions of the bottoms which implied an increase in the set of some piles.
4227 | 1515675 | Contract for “Replacement of Floodgates at the Ribeira dos Moinhos WWTP" | 45248100-8 | Canal locks construction work | FALSE | 2014 | 2016 | Portugal | Sines | Setúbal | 17 | 21 | 03-07-2015 | 01-11-2016 | 487 | 120 | 225000 | 151719 | 1 | 151719 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractor's responsibility
4228 | 1515301 | Overpass over the green corridor of Ribeira do Patarro - Tributary of Rio de Vila - Tributary of Cávado | 45233261-6 | Pedestrian overpass construction work | FALSE | 2013 | 2016 | Portugal | Barcelos | Braga | 3 | 24 | 29-07-2015 | 19-12-2016 | 509 | 180 | 348970.01 | 296624.52 | 2 | 277161.8 | 19462.72 | 107.0222 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties in the supply of some specific materials, which conditioned the timely supply of materials by the contractor. suspension due to the need to study possible changes to be introduced to the project, based on article 365 of the pcc. suspension of the projects by the contractor due to lack of safety conditions, verified by the flooding of the place where the projects are carried out, based on article 366 of the "public procurement code". | in light of the joint provisions of paragraph a) of article 297.º, paragraph 3 of article 366.º and paragraph 2 of article 214.º, all of the "public procurement code", it will be up to the co-contractor – for abnormal and unforeseen changes of the circumstances that made it temporarily impossible to fulfill the contract -, an indemnity, latu sensu considered, which will take the form, more precisely, of a financial compensation measured by criteria of equity; (transcription of paragraph 2 of the conclusion of the internal legal opinion in registration 26.691/16). the existence of underwork resulted from the execution of less quantities than those initially foreseen due to the adjustment in the extent of the project carried out.
4229 | 1514711 | 2014.126.03.C1 - SFP Sintra - Rehabilitation of roofs and facades | 45261210-9 | Roof-covering work | FALSE | 2015 | 2016 | Portugal | Sintra | Lisboa | 11 | 20 | 20-07-2015 | 11-07-2016 | 357 | 90 | 294780 | 198000 | 1 | 181465.09 | 16534.91 | 109.1119 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | legal extension of the contract | job supply
4230 | 1514327 | Various Interventions in Street Layouts in the Municipality | 45233200-1 | Various surface works | FALSE | 2015 | 2016 | Portugal | Odivelas | Lisboa | 11 | 20 | 30-07-2015 | 03-06-2016 | 309 | 180 | 187100 | 187100 | 1 | 187099.99 | 0.01 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Point 12 of the Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project. | there was a rounding in the amount of €0.01.
4231 | 1513734 | Corujeira Elementary School Rehabilitation Works (EM.004.2015.072) | 45454100-5 | Restoration work | FALSE | 2015 | 2016 | Portugal | Porto | Porto | 13 | 20 | 29-07-2015 | 05-01-2016 | 160 | 50 | 220000 | 154000.05 | 1 | 154000.05 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 24 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in accordance with the contractual provisions.
4232 | 1512295 | 2013.517.26.C1 - Xabregas Building - Repair and maintenance of facilities | 45261000-4 | Erection and related works of roof frames and coverings | FALSE | 2014 | 2016 | Portugal | Lisboa | Lisboa | 11 | 22 | 16-06-2015 | 14-10-2016 | 486 | 100 | 314000 | 188400.01 | 1 | 188400.01 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%, Proposed technical value: 30% and deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completed works
4233 | 1510106 | The object of this contract is the construction of a water supply network with a total length of about 2,132.47 m, 103 branches and 5 fire marks. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2015 | 2016 | Portugal | Ovar | Aveiro | 1 | N/A | 02-07-2015 | 23-06-2016 | 357 | 150 | 249000 | 198743.72 | 1 | 198743.72 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value of the proposal - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | contractual deadlines were not long, for reasons that the street where the projects took place, had to be managed and consolidated with other entities.
4234 | 1510032 | Requalification of the Road Network in the Municipality, by Contract: Access Road to the Cantanhede School Center - CP-CCP-EMP No. 02/2015 | 45233120-6 | Road construction works | FALSE | 2015 | 2016 | Portugal | Cantanhede | Coimbra | 6 | 20 | 28-07-2015 | 28-07-2016 | 366 | 240 | 385934.88 | 291299.88 | 2 | 292030.71 | -730.83 | 99.7497 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no change | existence of underwork and negative price review
4235 | 1509015 | Contract for the Improvement of the Municipal Road Network - Different Flooring, in the Municipality of Lajes do Pico | 45233251-3 | Resurfacing works | FALSE | 2015 | 2016 | Portugal | Lajes do Pico | Região Autónoma dos Açores | 15 | 20 | 24-07-2015 | 19-01-2016 | 179 | 180 | 323187.5 | 281875 | 2 | 281875.01 | -0.01 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4236 | 1507737 | 2013.005.03.C1 - Services Professional Training Braga - Fire Safety | 45343000-3 | Fire-prevention installation works | FALSE | 2015 | 2016 | Portugal | Braga | Braga | 3 | 21 | 16-06-2015 | 16-04-2016 | 305 | 45 | 275000 | 199651.21 | 1 | 214908.36 | -15257.15 | 92.9006 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%, Proposed technical value: 30%, deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work | additional work
4237 | 1507693 | Baixa Sanitation Network - 2nd Phase - Caramos / Friande (Basin 82A and 89) - Conclusion | 90000000-7 | Sewage-, refuse-, cleaning-, and environmental services | FALSE | 2015 | 2016 | Portugal | Felgueiras | Porto | 13 | 16 | 23-07-2015 | 20-09-2016 | 425 | 120 | 747683.54 | 567165.84 | 2 | 383083.69 | 184082.15 | 148.0527 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some approved deadline extensions | smaller quantities executed
4238 | 1506885 | Requalification of the Castanheira Road | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 15-07-2015 | 31-10-2016 | 474 | 30 | 465849.51 | 323541.66 | 2 | 355902.19 | -32360.53 | 90.9075 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | 7-day deadline extension due to additional work being carried out. | the change in the value of the project is due to the existence of over and underwork
4239 | 1505133 | Public Tender for the Contract for the refurbishment of domestic and unitary networks in streetDiogo Cão, in the parish of Encosta do Sol, in the municipality of Amadora. | 45232410-9 | Sewerage work | FALSE | 2015 | 2016 | Portugal | Amadora | Lisboa | 11 | 20 | 15-07-2015 | 08-02-2016 | 208 | 180 | 370000 | 265482.4 | 2 | 265482.4 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: According to clause 28 of the contest | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the months in question for the execution of the project total more days than the stipulated period
4240 | 1502553 | Civil construction works and exterior arrangements. | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2015 | 2016 | Portugal | Nisa | Portalegre | 12 | 30 | 06-07-2015 | 29-09-2016 | 451 | 120 | 195000 | 176970 | 1 | 168877.19 | 8092.81 | 104.7921 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | only in september 2016 were the necessary indices published to carry out the definitive price review. | notice of underwork carried out in the amount of €8,092.82.
4241 | 1500224 | Contract for: "Enlargement of Avenida das Forças Armadas" | 45233222-1 | Paving and asphalting works | FALSE | 2014 | 2016 | Portugal | Entroncamento | Santarém | 16 | 20 | 23-09-2014 | 02-09-2016 | 710 | 180 | 350000 | 298495 | 2 | 292832.9 | 5662.1 | 101.9336 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | granted 2 grace period extensions. | underwork.
4242 | 1499076 | Requalification of the VIM Intermunicipal Road (5,950 KM - 11,650KM) | 45233223-8 | Carriageway resurfacing works | FALSE | 2015 | 2016 | Portugal | Guimarães | Braga | 3 | 20 | 06-07-2015 | 09-05-2016 | 308 | 150 | 2485669.51 | 2360941.43 | 3 | 2247694.2 | 113247.23 | 105.0384 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value: 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension of work pursuant to paragraph a) of article 365 of the public contracts code. | underwork due to anticipated quantities not being used up.
4243 | 1494234 | Contract for “Bypass to the EN 205 between Lameiros and the Town Hall – 2nd phase”. | 45233120-6 | Road construction works | FALSE | 2015 | 2016 | Portugal | Cabeceiras de Basto | Braga | 3 | 20 | 02-07-2015 | 10-10-2016 | 466 | 60 | 693000 | 594898.78 | 2 | 594898.78 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 80%; Technical Value of the Proposal 20% | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project ended later than expected
4244 | 1491300 | Contract for the requalification and expansion of the "shelter amigo" facilities | 45211200-1 | Sheltered housing construction work | FALSE | 2014 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 02-04-2015 | 08-07-2016 | 463 | 420 | 603000 | 567740.7 | 2 | 567740.7 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price factor (K1) with a weight of 40% Technical quality factor of the proposal with a weight of 60% K2.1 - Work plan - 70% K2.2 - Descriptive memory and justification of how the work was carried out - 30% The score of this factor (K2) results from the following formula: K2 = (0.70xK2.1) + (0.30xK2.2), where: K2.1 - Work plan K2.2 - Descriptive memory and justification of the way of execution of the work | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4245 | 1489799 | Rebuilding a Weir on the Lima River | 45247220-8 | Weir construction work | FALSE | 2015 | 2016 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 18 | 16-06-2015 | 30-03-2016 | 288 | 120 | 480000 | 447250.16 | 2 | 544469.42 | -97219.26 | 82.1442 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Bid price (70%); Technical value of proposal (30%) | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without changes | underwork
4246 | 1489105 | “Execution of the Pipeline to the Quinta Nova Reservoir (Coimbra)” | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2016 | Portugal | Coimbra | Coimbra | 6 | 20 | 20-11-2014 | 22-07-2016 | 610 | 180 | 1200000 | 893070.67 | 2 | 1003398.34 | -110327.67 | 89.0046 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need to bypass an affected service ("downstream" water pipe) that was not correctly identified in the registration; need to set back and build a fence wall, in reinforced concrete, so as to be able to install the pipeline in the only possible lane, taking into account the existing infrastructures. these works also conditioned the start of one of the teams, given the traffic constraints that were caused by the need to carry them out. need to bypass an affected service ("downstream" water pipe) that was not correctly identified in the registration; need to set back and build a fence wall, in reinforced concrete, so as to be able to install the pipeline in the only possible lane, taking into account the existing infrastructures. these works also conditioned the start of one of the teams, given the traffic constraints that were caused by the need to carry them out. need to bypass an affected service ("downstream" water pipe) that was not correctly identified in the registration; need to set back and build a fence wall, in reinforced concrete, so as to be able to install the pipeline in the only possible lane, taking into account the existing infrastructures. these works also conditioned the start of one of the teams, given the traffic constraints that were caused by the need to carry them out. need to carry out a second bypass of an affected service ("downstream" water conduit that was not correctly identified in the register; as a result of the construction of the fence wall, the paving work and sidewalks on this street were conditioned to the completion of the first one; delay in manufacturing parts for one of the nodes, in an alternative solution proposed by ee. | execution of the fence wall, in reinforced concrete. bypass execution and conduct related to affected services; execution of a rainwater network and widening of the road, where the fence wall was built; alteration of the rainwater network next to the 25 de abril node.
4247 | 1488597 | Construction of the Overpass between Pragal (Quinta dos Crastos) and Parque da Paz | 45233144-0 | Overpass construction work | FALSE | 2014 | 2016 | Portugal | Almada | Setúbal | 17 | 30 | 28-04-2015 | 16-06-2016 | 415 | 150 | 693000 | 677589.11 | 2 | 667246.62 | 10342.49 | 101.55 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Factor 1 "Technical Value of the Proposal" - 40%, with subfactors "Descriptive and Justification" - 10 points and "Work Plan" - 30 points. Factor 2 "Bid Price" - 60%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in work. | underwork.
4248 | 1488036 | Contract for the Construction Works of Passive and Active Treatment Systems for Outflows and Tributaries to the Nova Dam Area | 45232420-2 | Sewage work | FALSE | 2015 | 2016 | Portugal | Nelas | Viseu | 20 | 20 | 18-06-2015 | 20-12-2016 | 551 | 250 | 2500000 | 1822620.1 | 3 | 1822620.1 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60%; 2. Technical Value of the Proposal - 40%. (As indicated in the Contest Schedule). | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | two graceful extensions were granted to the execution period of the contract as a result of constraints that occurred in the execution of the project, in which there was a need for the contractor to define exceptional measures for the conclusion of the contract and which resulted in requests for extension of the period of execution, free of charge and without charges of any kind for the owner of work.
4249 | 1486182 | Pe_15041_cue - urgent public tender for the conclusion of the contract for the modernization works of the augusto gomes High school, in matosinhos | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2016 | Portugal | Matosinhos | Porto | 13 | 15 | 22-06-2015 | 25-08-2016 | 430 | 165 | 4955703.82 | 4280000 | 3 | 4181610.09 | 98389.91 | 102.3529 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | the facts that led to the extension of the term of the contract resulted from work to eliminate errors and omissions not attributable to the contractor, which led to the extension of the contractual term for the completion of the contract by 39 days. | changes in the value of the project result from the issuance of execution orders relating to the supply of errors and omissions detected by the contractor in the execution phase.
4250 | 1486175 | Pe_15040_cue - urgent public tender for the conclusion of the contract for the execution of the modernization works of the High school of castêlo da maia, in maia | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2016 | Portugal | Maia | Porto | 13 | 15 | 22-06-2015 | 23-11-2016 | 520 | 165 | 4898319.04 | 3750000 | 3 | 3844068.47 | -94068.47 | 97.5529 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | the facts that led to the extension of the term of the contract resulted from work to eliminate errors and omissions not attributable to the contractor, which led to the extension of the contractual period for the completion of the contract by 94 days, and the suspension of work under subparagraph a) of article 297 of the "public procurement code", which led to the extension of the contract period by 53 days. | changes in the value of the project result from the issuance of execution orders relating to the supply of errors and omissions detected by the contractor in the execution phase.
4251 | 1486046 | "In 392 - Pontoon of Sinks - Replacement of Artwork". | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2016 | Portugal | Serpa | Beja | 2 | 42 | 12-06-2015 | 02-12-2016 | 539 | 80 | 225000 | 169930.71 | 1 | 167920.06 | 2010.65 | 101.1974 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price: 80% -Technical value: 20% | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | free extensions for a total of 28 days, under the responsibility of the contractor for reasons related to the weather and some difficulties in the supply of ready-mixed concrete in the area | the change in the value of the project is related to the clearance of negative errors and omissions supply work in the amount of €2,010.65
4252 | 1486014 | Construction of two synthetic turfs in the sports complexes of Canedo and Vila Maior | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2015 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 24 | 23-06-2015 | 28-07-2016 | 401 | 90 | 251937.4 | 240293.4 | 1 | 238093.4 | 2200 | 100.924 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Price - 60%; and b) Technical Quality of the Proposal - 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | need to rectify slopes in the field in vila maior. | underwork due to the exclusion of two articles referring to the maintenance of the fields that has to be done over time.
4253 | 1483085 | Contract for the Maintenance of Sanitation and Water Supply Networks | 45259000-7 | Repair and maintenance of plant | FALSE | 2015 | 2016 | Portugal | Torres Novas | Santarém | 16 | 24 | 29-05-2015 | 30-05-2016 | 367 | 730 | 205000 | 205000 | 1 | 205000 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | all works were carried out within the contract deadline.
4254 | 1482285 | Construction of the Vilar de Luz aerodrome - rehabilitation of the Vilar de Luz aerodrome tunnel | 45221241-3 | Road tunnel construction work | FALSE | 2014 | 2016 | Portugal | Maia | Porto | 13 | 47 | 15-06-2015 | 21-11-2016 | 525 | 180 | 735436.25 | 588349.01 | 2 | 588349.01 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 24 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the deadline for the contract took place with an extension of 120 days due to the clomateric conditions not allowing the execution of the embankment, and also, the paintings inside the tunnel.
4255 | 1479828 | Execution of the contract for "Requalification of EM - 526-1 between Páteo and Guia. | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Albufeira | Faro | 8 | 20 | 15-06-2015 | 30-05-2016 | 350 | 30 | 424500 | 296530.65 | 2 | 296530.65 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in the execution of the projects by the contractor.
4256 | 1476516 | Pipeline between Petrogal Node and ZILS North - Phase II | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2016 | Portugal | Sines | Setúbal | 17 | 60 | 05-06-2015 | 28-12-2016 | 572 | 150 | 3100000 | 2287585.47 | 3 | 2262189.89 | 25395.58 | 101.1226 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension, no penalties for the contractor | following the increase and supply of works
4257 | 1475586 | Repaving of the Accesses to Cadaveira-Moudo and Moita-Limite do Concelho, in accordance with the attached map of quantities. | 45233141-9 | Road-maintenance works | FALSE | 2015 | 2016 | Portugal | Águeda | Aveiro | 1 | 30 | 04-06-2015 | 23-11-2016 | 538 | 60 | 261663.65 | 176742 | 1 | 149029.28 | 27712.72 | 118.5955 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contractor did not start work at the start of the contract period, there were recurrent delays in carrying out the project, and the project plan was not complied with. extension of deadline for execution of additional works. | execution of the most necessary work during the course of the project.
4258 | 1471228 | Construction of a building for the installation of a mill and packing area | 45000000-7 | Construction work | FALSE | 2015 | 2016 | Portugal | Vila de Rei | Castelo Branco | 5 | 20 | 01-06-2015 | 18-02-2016 | 262 | 90 | 200000 | 179000 | 1 | 174060.3 | 4939.7 | 102.8379 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution deadlines | work unless not performed
4259 | 1471076 | IP3, km 47+588, hydraulic crossing. En229, km 42+380, hydraulic passage rehabilitation and structural reinforcement / replacement of the bridge | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2016 | Portugal | Coimbra | Coimbra | 6 | 31 | 20-05-2015 | 30-12-2016 | 590 | 120 | 340000 | 226748.59 | 1 | 226748.59 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: - Price 80% - Technical value 20% | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4260 | 1466078 | Access to Forte da Graça - Parking and outdoor infrastructure | 45223300-9 | Parking lot construction work | FALSE | 2015 | 2016 | Portugal | Elvas | Portalegre | 12 | 24 | 12-05-2015 | 11-01-2016 | 244 | 90 | 550000 | 387036.55 | 2 | 383151.6 | 3884.95 | 101.0139 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a need to carry out repairs on site in order to be able to carry out the provisional reception. | once the final measurements were taken, it was verified the existence of excessive quantities in the quantity map and works that were not carried out because they were not necessary.
4261 | 1463428 | The contract includes the execution of a WWTP, including the extension of the interceptor of the domestic waste water collector. | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2015 | 2016 | Portugal | Nelas | Viseu | 20 | 22 | 12-05-2015 | 24-02-2016 | 288 | 210 | 700000 | 484910.44 | 2 | 484910.44 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | without changes | without changes
4262 | 1462584 | Contract for the "Strengthening of Margins, through the Recovery of Dikes and Motorbikes with a View to Preventing Risks - Water Gates and Canal de Mira (Mira)". | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2016 | Portugal | Oliveira do Bairro | Aveiro | 1 | 24 | 31-03-2015 | 04-02-2016 | 310 | 180 | 649500 | 573695.37 | 2 | 573695.37 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A
4263 | 1462550 | Contract for the contract for the "2nd Phase of the Protection and Recovery of the Dune System, through the Reinforcement of the Dune Cord between Costa Nova and Mira, within the Scope of the Intervention of the Polis Litoral Ria de Aveiro". | 45243400-6 | Beach-consolidation works | FALSE | 2014 | 2016 | Portugal | Mira | Aveiro | 1 | 24 | 25-03-2015 | 18-03-2016 | 359 | 183 | 1200000 | 915366.96 | 2 | 874473.38 | 40893.58 | 104.6764 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | no information | underwork
4264 | 1461991 | School Center – Pavilion – Refurbishment of the Sousel Gym Pavilion | 45262500-6 | Masonry and bricklaying work | FALSE | 2015 | 2016 | Portugal | Sousel | Portalegre | 12 | 20 | 22-05-2015 | 20-04-2016 | 334 | 60 | 508075.42 | 394766.2 | 2 | 394766.2 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%; Technical value: 30%; deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4265 | 1461898 | Expansion of the downstream roll-on roll-off terminal in the port of setúbal | 45213342-2 | Ro-Ro terminal construction work | FALSE | 2015 | 2016 | Portugal | Setúbal | Setúbal | 17 | 56 | 19-05-2015 | 17-06-2016 | 395 | 150 | 3500000 | 2861664.46 | 3 | 2876615.61 | -14951.15 | 99.4803 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | the projects on the slope of the marginal retention, placing stone, carried out at the tide brought a higher conditioner to the time for execution of the activity. there were also delays in the delivery of materials for the electrical part | materials of the electrical part
4266 | 1459483 | Improvement of VNC 85 (section between Azinhal and Águas Frias) | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Loulé | Faro | 8 | 30 | 04-05-2015 | 26-02-2016 | 298 | 180 | 403454.14 | 289738.63 | 2 | 288738.63 | 1000 | 100.3463 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the stipulated time frame. there were administrative delays in scheduling the inspection. | the anticipated quantities have not been exhausted.
4267 | 1453248 | Bike Route - Albergaria-a-Velha to Valmaior | 45233162-2 | Cycle path construction work | FALSE | 2015 | 2016 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 12 | 20-03-2015 | 21-12-2016 | 642 | 90 | 300263 | 218967.21 | 1 | 218967.21 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4268 | 1452105 | Adaptation of facilities for Balcão Único - Paços do Concelho | 45262700-8 | Building alteration work | FALSE | 2015 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 18 | 12-05-2015 | 02-12-2016 | 570 | 180 | 294500 | 221346.23 | 1 | 214353.23 | 6993 | 103.2624 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 40%; Technical Value of the Proposal: 60%. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork worth €6,993.00.
4269 | 1449441 | Requalification of the quay 3 embankment, in the port of setúbal | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | Setúbal | Setúbal | 17 | 34 | 31-03-2015 | 11-11-2016 | 591 | 90 | 300000 | 225000.01 | 1 | 236075.34 | -11075.33 | 95.3086 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | work carried out in urban areas and work carried out at sea with unforeseen work | unforeseen works
4270 | 1444221 | Improvement of the Old National Road 202 - 2nd Phase - Section 2 - Km 113,400 to Km 117,500. | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Monção | Viana do Castelo | 18 | 20 | 23-03-2015 | 26-04-2016 | 400 | 210 | 294000 | 254223.39 | 2 | 279262.93 | -25039.54 | 91.0337 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | addition of more works. | addition of more works.
4271 | 1442478 | Construction contract for the installation of screening in the Penedrão - Roxo Hydraulic Circuit of the Alqueva Multipurpose Project | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2016 | Portugal | Aljustrel | Beja | 2 | 45 | 12-03-2015 | 06-10-2016 | 574 | 274 | 900000 | 804510 | 2 | 804510 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | power supply for carrying out tests. | there were no changes.
4272 | 1441856 | The aim of carrying out this contract is the requalification of a section of the CM 1109, with a total length of about 3 212 meters, this requalification consisting of the implantation of a new profile | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Alandroal | Évora | 7 | 21 | 22-04-2015 | 13-04-2016 | 357 | 60 | 342900 | 308207.56 | 2 | 320803.95 | -12596.39 | 96.0735 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the deadline for carrying out the project. | ordinary provisional price revision (article 382 of the "public procurement code") - value: €12,596.39 excluding vat.
4273 | 1436756 | Repaving of streets erpa Pinto in Loulé. | 45233251-3 | Resurfacing works | FALSE | 2014 | 2016 | Portugal | Loulé | Faro | 8 | 36 | 26-03-2015 | 13-07-2016 | 475 | 210 | 473378.6 | 316913.27 | 2 | 286737.42 | 30175.85 | 110.5239 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the stipulated period. there were delays in scheduling provisional acceptance. | contract work not performed
4274 | 1428548 | Resettlement of Families in Need- Families of Gypsy Ethnicity in a situation of illegal occupation of public space. | 45212410-3 | Construction work for lodging buildings | FALSE | 2013 | 2016 | Portugal | Campo Maior | Portalegre | 12 | 30 | 03-12-2014 | 05-02-2016 | 429 | 270 | 1242677.77 | 1004085.63 | 3 | 1004085.63 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the execution period of the project was completed within the date. the consignment was a posteriori.
4275 | 1427706 | Construction of the Landfill for Hazardous Waste which will correspond to the 9th Cell of the Intermunicipal Landfill of Terceira Island, henceforth referred to as the 9th AIIT cell. | 45222100-0 | Waste-treatment plant construction work | FALSE | 2014 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 30 | 25-03-2015 | 11-02-2016 | 323 | 180 | 600000 | 510000 | 2 | 510000 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: a) Price (F1) - 70% b) Quality of the work plan (F2) - 30% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4276 | 1426427 | Contract work for the Faro Riverside Park - 1st phase, within the scope of the intervention of Polis Litoral Ria Formosa | 45112700-2 | Landscaping work | FALSE | 2012 | 2016 | Portugal | Faro | Faro | 8 | 30 | 13-07-2012 | 09-05-2016 | 1396 | 665 | 2910000 | 2606275.19 | 3 | 2421637.69 | 184637.5 | 107.6245 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | reasons for changes to the execution period of the project: -difficulties specific to the sector; -difficulties in contracting specialized companies, due to the relocation of equipment in other countries; -state and characteristics of the buried networks, particularly in the area of ​​the old fishing center; -changing discontinued materials. | works less
4277 | 1426360 | Construction contract for the new IVBAM laboratory, IP-RAM | 45262700-8 | Building alteration work | FALSE | 2014 | 2016 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 28 | 01-04-2015 | 16-03-2016 | 350 | 244 | 370000 | 277500.01 | 2 | 277500.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the execution period of the project.
4278 | 1424623 | Recovery from E.M. From Cruzinha- ​​Daires- Souto- Castelo- Corte | 45233220-7 | Surface work for roads | FALSE | 2015 | 2016 | Portugal | Tondela | Viseu | 20 | 11 | 17-03-2015 | 16-12-2016 | 640 | 60 | 418276.77 | 234823.01 | 1 | 234823.01 | 0 | 100 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out within the expected execution time. | existence of more works
4279 | 1424477 | The purpose of the contract is to carry out a contract "port of ericeira - recovery and stabilization of the cliff at praia dos pescadores". | 45243110-6 | Cliff-stabilisation works | FALSE | 2015 | 2016 | Portugal | Mafra | Lisboa | 11 | 15 | 06-04-2015 | 20-01-2016 | 289 | 100 | 620000 | 396600 | 2 | 434651 | -38051 | 91.2456 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: The award is carried out according to the criterion of most economically advantageous proposal, taking into account the following factors and sub-factors and respective weighting coefficients: a) Technical value of the proposal (60%), assessed using the methodology set out in Annex IV to the tender program; b) Price (40%) scored using the value function graphed in Annex V to the tender schedule. The subfactors and respective qualitative analysis descriptors, and respective weightings and scores, to be considered for the evaluation of the factor "Technical value of the proposal" are the following: a1) Proposed constructive processes analyzed based on the detail and coherence of the elements contained in the descriptive memory and justification - 30%; a2) Adequacy to the work and local conditions, work plans, labor and equipment to be used - 30%. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension due to city council charges, due to the use of the beach during the bathing season. more works resulting from unforeseeable geotechnical constraints. | unforeseeable geotechnical constraints - need for greater injection volume, need for more drainage.
4280 | 1422730 | Street layout contract to intervene in the Municipality of Aveiro | 45233142-6 | Road-repair works | FALSE | 2015 | 2016 | Portugal | Aveiro | Aveiro | 1 | 22 | 27-03-2015 | 20-09-2016 | 543 | 120 | 305400.57 | 203426.49 | 1 | 200660.55 | 2765.94 | 101.3784 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | lack of responsiveness to the various works in progress | alteration of the road solution at the intersection of rua engenheiros da celulose. it was verified that it was not necessary to build a ditch and rectify the modification of the pavement
4281 | 1421668 | Work to Reinforce the Protection of the Dune System and Protection of the Coastline at Praia de Ofir - Phase 3 | 45243000-2 | Coastal-defence works | FALSE | 2014 | 2016 | Portugal | Esposende | Braga | 3 | 24 | 20-02-2015 | 20-09-2016 | 578 | 120 | 615000 | 459977.67 | 2 | 459977.67 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The award is made according to the criterion of most economically advantageous tender, taking into account the following factors: a) Price............40% b) Technical Quality of the Proposal............60% b.1) Descriptive Memory and Justification.....30% b.2) Work Plan.....18% b.3) Occupational Health and Safety Management.....12 % | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4282 | 1421500 | The purpose of the contract is to carry out the work defined, regarding the type, quantity and technical conditions of execution, in the proposal presented, in the map of quantities, special ty project | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | Vila do Porto | Região Autónoma dos Açores | 15 | 24 | 13-03-2015 | 19-08-2016 | 525 | 120 | 900000 | 765000.01 | 2 | 847105.28 | -82105.27 | 90.3075 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for carrying out the project has changed due to a graceful extension and the period necessary to carry out additional work. | the value of extra work.
4283 | 1419891 | Urban requalification on en 106 next to the hotel das termas - dosma | 45233220-7 | Surface work for roads | FALSE | 2014 | 2016 | Portugal | Penafiel | Porto | 13 | 20 | 04-12-2014 | 21-06-2016 | 565 | 180 | 262411.77 | 151748.99 | 1 | 151748.99 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 25 | N/A | N/A | N/A | N/A | N/A | N/A
4284 | 1418779 | Improved energy efficiency in public lighting | 45000000-7 | Construction work | FALSE | 2013 | 2016 | Portugal | Fundão | Castelo Branco | 5 | 21 | 12-03-2015 | 14-01-2016 | 308 | 730 | 245520 | 161759.63 | 1 | 161759.63 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change
4285 | 1407069 | From Baixa to Alta by the Botanical Garden: Requalification of the Botanical Garden of Coimbra, including namely slope stabilization, construction of walls and stairs, paving, drainage | 45112700-2 | Landscaping work | FALSE | 2014 | 2016 | Portugal | Coimbra | Coimbra | 6 | 24 | 09-03-2015 | 22-06-2016 | 471 | 150 | 347844.29 | 327317.28 | 2 | 321182.18 | 6135.1 | 101.9102 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | underwork value
4286 | 1403164 | The contract consists of repairing the roof, chipping, plastering and painting the walls, replacing false ceilings as well as remodeling and improving the water and sewage networks in some areas | 45453100-8 | Refurbishment work | FALSE | 2014 | 2016 | Portugal | Nordeste | Região Autónoma dos Açores | 15 | 30 | 23-01-2015 | 10-08-2016 | 565 | 240 | 442600 | 384080.01 | 2 | 449252.47 | -65172.46 | 85.4931 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4287 | 1402787 | The contract for “Rotunda of the North Entrance of Vila Real de Santo António”, consists of the need to requalify the EN122, namely the execution of a roundabout intersection with two traffic lanes | 45233128-2 | Roundabout construction work | FALSE | 2013 | 2016 | Portugal | Vila Real Sto Antonio | Faro | 8 | 30 | 21-01-2015 | 27-04-2016 | 462 | 90 | 200000 | 192299.79 | 1 | 189587.34 | 2712.45 | 101.4307 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the project deadline for determination of the area of ​​intervention by an entity involved;
4288 | 1401035 | In. Mirão - hermitage - completion of works | 45233120-6 | Road construction works | FALSE | 2014 | 2016 | Portugal | Baião | Porto | 13 | 31 | 26-01-2015 | 08-04-2016 | 438 | 150 | 388454.18 | 305989.25 | 2 | 305989.25 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Those contained in no. 14 of the Contest. | 0 | 0 | N/A | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to say. | nothing to say.
4289 | 1399355 | Remodeling of the water distribution network in Canada de Belém and Cruz dos Regatos, to be carried out respectively in the parishes of Terra Chã and São Bartolomeu, municipality of Angra do Heroísmo. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2013 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 9 | 05-03-2015 | 23-08-2016 | 537 | 180 | 420000 | 339442.3 | 2 | 272671.87 | 66770.43 | 124.4875 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - due to the execution of works to supply errors and omissions detected in the execution phase of the project, related to the need to execute a water drainage network, before carrying out the project foreseen in the project. - adverse weather conditions that hampered the progress of the project (material from trenches dragged which led to the repetition of work already carried out). - restrictions on obtaining human and material resources, due to the contractor's financial difficulties. | - underwork due to excess quantities in the project map, not having any impact on the project foreseen in the execution project.
4290 | 1392193 | Renovation of the dr. Rui machado and preparation of the base for the installation of synthetic grass | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2016 | Portugal | Peso da Régua | Vila Real | 19 | N/A | 23-02-2015 | 12-01-2016 | 323 | 180 | 291239.2 | 268610.29 | 2 | 268610.29 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period of the contract. | there was no change in the value of the contract
4291 | 1386923 | Execution of the contract named AR 73.0.10 – construction contract for the execution of the labruge pulping station (fd10), within the scope of the Northwest Multimunicipal Water Supply and Sanitation System. | 45232423-3 | Sewage pumping stations construction work | FALSE | 2010 | 2016 | Portugal | Vila do Conde | Porto | 13 | 47 | 10-12-2012 | 09-09-2016 | 1369 | 180 | 850000 | 687500 | 2 | 674078.22 | 13421.78 | 101.9911 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractor's financial difficulties | removal of the transformer station from the scope of the contract
4292 | 1382927 | Execution of the outfall and installation of the treatment plant in the town of são pedro de serracenos | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Bragança | Bragança | 4 | 20 | 13-02-2015 | 22-04-2016 | 434 | 270 | 255000 | 164677.5 | 1 | 162457.5 | 2220 | 101.3665 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (60% weighting) Technical value (40% weighting) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delays due to the edp branch and download | underwork
4293 | 1379950 | Expansion of the Murtosa Cemetery | 45215400-1 | Cemetery works | FALSE | 2014 | 2016 | Portugal | Murtosa | Aveiro | 1 | 30 | 10-02-2015 | 23-03-2016 | 407 | 150 | 276131.75 | 198604.17 | 1 | 198181.77 | 422.4 | 100.2131 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | difficulties in delivering materials, high water table and difficulties in dialogue with the neighboring neighbor | there was underwork
4294 | 1373304 | This involves improvement, route correction and repaving of the urban section of the EN331 in the surroundings of the Longroiva Thermal Pole | 45112700-2 | Landscaping work | FALSE | 2014 | 2016 | Portugal | Meda | Guarda | 9 | 20 | 03-02-2015 | 21-06-2016 | 504 | 90 | 398000 | 348913.33 | 2 | 335836.64 | 13076.69 | 103.8938 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in making land available due to the publication of the declaration of public utility (dup) | results from small amount of some works that were not performed
4295 | 1373126 | Public tender for the contract for the repair of ruptures in the network and in water supply branches in the municipality of Oeiras, years 2014/2015. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2016 | Portugal | Oeiras | Lisboa | 11 | 11 | 29-01-2015 | 17-05-2016 | 474 | 270 | 374956 | 297387.5 | 2 | 192288 | 105099.5 | 154.6573 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the completion of the contract was imposed by the daily needs of the division's work, until the end of the available period, with the total budget initially foreseen not having been exhausted. | reduction of the object of the contract
4296 | 1369357 | execution of the contract called eb 2286 - wastewater drainage network for part of the parishes of são romão do coronado (trofa), within the scope of the multimunicipal water supply system | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Trofa | Porto | 13 | 42 | 10-11-2014 | 15-12-2016 | 766 | 210 | 1750000 | 1339185.14 | 3 | 1288326.1 | 50859.04 | 103.9477 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - excavations in hard rock with volumes greater than those planned, which conditioned the continuation of the project; - adverse weather conditions (heavy precipitation), in december 2015, january, february, march and april 2016, which conditioned the execution/completion of the final paving works of ditches/roads; - delays under the contractor's responsibility. | underwork, fundamentally the execution of fewer home extensions.
4297 | 1369354 | execution of the public work contract called eb 2284 - drainage network of alvarelhos, bougado, s. romão coronado and covelas (trofa)” – water system of the northwest region | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Trofa | Porto | 13 | 41 | 07-11-2014 | 03-06-2016 | 574 | 210 | 1275000 | 978528.81 | 2 | 904712.02 | 73816.79 | 108.1591 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | - excavations in hard rock with volumes greater than those planned, which conditioned the continuation of the project; - adverse weather conditions (heavy precipitation), in december 2015, january, february, march and april 2016, which conditioned the execution/completion of the final paving works of ditches/roads; - delays under the contractor's responsibility. | underwork, fundamentally the execution of fewer home extensions.
4298 | 1369204 | execution of the public works contract called eb 2285 - são romão do covelas and covelas waste water drainage network (trofa), within the scope of the northwest region water system. | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Trofa | Porto | 13 | 42 | 18-12-2014 | 03-06-2016 | 533 | 180 | 900000 | 597500 | 2 | 574528.65 | 22971.35 | 103.9983 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | - excavations in hard rock with volumes greater than those planned, which conditioned the continuation of the project; - adverse weather conditions (heavy precipitation), in december 2015, january, february, march and april 2016, which conditioned the execution/completion of the final paving works of ditches/roads; - delays under the contractor's responsibility. | - underwork, fundamentally the execution of fewer home extensions.
4299 | 1369013 | execution of the public work contract named ar 2251 – construction contract for execution of the ribeira da granja intercetor – 2nd phase”, within the scope of the multimunicipal water supply and sanitation system | 45232411-6 | Foul-water piping construction work | FALSE | 2013 | 2016 | Portugal | Vila do Conde | Porto | 13 | 42 | 17-11-2014 | 21-06-2016 | 582 | 126 | 230000 | 184542.13 | 1 | 178767.87 | 5774.26 | 103.23 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | the project on the contract and the counting of the respective contractual period were suspended, from the 4th to the 17th of january 2016, under the stipulations in paragraph a), number 3, of article 366 of decree-law 18/2008 , that is, due to the lack of safety conditions for the execution of all the projects of the contract.
4300 | 1367742 | Exterior repairs to the school building, including paving work, walls and fences, drainage networks, irrigation, lighting, water, sewage, telecommunications, green spaces | 45112700-2 | Landscaping work | FALSE | 2014 | 2016 | Portugal | Nisa | Portalegre | 12 | 30 | 21-01-2015 | 02-03-2016 | 406 | 120 | 989412.23 | 858899.76 | 2 | 853795.99 | 5103.77 | 100.5978 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | definitive pricing revision. | underwork proposal.
4301 | 1367625 | The object of this contract is the construction of 10,500 meters of PPc DN 200 piping, 61 meters of FFD DN 200 piping and 279 home extensions. | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Arouca | Aveiro | 1 | 41 | 27-10-2014 | 15-01-2016 | 445 | 240 | 1050000 | 744587.27 | 2 | 750153.54 | -5566.27 | 99.258 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | no change | carrying out more work
4302 | 1359580 | Construction of the Synthetic Field in Gondomar (Gondomar Sport Clube) | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2016 | Portugal | Gondomar | Porto | 13 | 20 | 21-01-2015 | 04-11-2016 | 653 | 210 | 200000 | 153491.28 | 1 | 153491.28 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | 1st suspension notice 5-5-2015 1st auto restart 2015-08-31 2nd suspension notice 09-30-2015 2nd auto restart 11-30-2015 3rd suspension notice 12-17-2015 3rd auto restart 2016-10-17
4303 | 1358355 | This involves the execution of a bicycle path and wooden walkway, including its lighting. | 45000000-7 | Construction work | FALSE | 2014 | 2016 | Portugal | Esposende | Braga | 3 | 30 | 04-12-2014 | 12-01-2016 | 404 | 180 | 790000 | 665823.89 | 2 | 628966.91 | 36856.98 | 105.8599 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period of the project, the last work measurement report is from 06.24.2015 | no work on locksmiths and deck walkways was carried out.
4304 | 1357874 | Public competition for awarding the contract for "requalification of the public space in the historic center of Viana do Castelo - streetde Viana, streetPrior do Crato, Beco do Caxuxo and crossstreet of Vitória" | 45233200-1 | Various surface works | FALSE | 2014 | 2016 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 21-01-2015 | 11-11-2016 | 660 | 120 | 290000 | 287883.09 | 2 | 287883.09 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 11 | N/A | N/A | FALSE | FALSE | FALSE | N/A | weather conditions
4305 | 1351249 | Construction of two gravity domestic wastewater systems and a pumping system in Sobreiro | 45232410-9 | Sewerage work | FALSE | 2014 | 2016 | Portugal | Mafra | Lisboa | 11 | 21 | 09-01-2015 | 11-08-2016 | 580 | 210 | 610000 | 491314.51 | 2 | 455234.42 | 36080.09 | 107.9256 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global Contract Price: 80%; b) Technical value of the proposal: 20%. | 1 | 80 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | adverse weather conditions | work not performed by the contractor
4306 | 1348292 | Remodeling of the Municipal Camping Park. | 45453100-8 | Refurbishment work | FALSE | 2014 | 2016 | Portugal | Bragança | Bragança | 4 | 30 | 29-12-2014 | 14-06-2016 | 533 | 180 | 500000 | 366315.18 | 2 | 366315.18 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | there was a deadline extension
4307 | 1343715 | Water Distribution Network in the Border Areas of Rio Maior - Arco da Memória | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2016 | Portugal | Rio Maior | Santarém | 16 | 9 | 22-12-2014 | 21-11-2016 | 700 | 120 | 279901.04 | 220410.46 | 1 | 208999.71 | 11410.75 | 105.4597 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay in starting work | negative price revision and underwork
4308 | 1334203 | Remodeling and recovery of the arroios market | 45212310-2 | Construction work for buildings relating to exhibitions | FALSE | 2014 | 2016 | Portugal | Lisboa | Lisboa | 11 | 24 | 23-12-2014 | 19-09-2016 | 636 | 365 | 833599.73 | 663929.55 | 2 | 676602.27 | -12672.72 | 98.127 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A
4309 | 1330221 | This is the execution of a contract for the remodeling of existing collectors/outfalls, consisting of three main drainage systems, Monsanto/WWTP, Vila Moreira/WWTP and Gouxaria /WWTP | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Alcanena | Santarém | 16 | 47 | 19-12-2014 | 20-04-2016 | 488 | 300 | 7060000 | 5884351.72 | 3 | 5839594.01 | 44757.71 | 100.7665 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | date of completion of the project 12/14/2015. | underwork.
4310 | 1328849 | Repair and improvement of the headquarters building of Águas do Porto, E.M. | 45450000-6 | Other building completion work | FALSE | 2014 | 2016 | Portugal | Porto | Porto | 13 | 20 | 18-12-2014 | 12-08-2016 | 603 | 150 | 275777.28 | 236149.65 | 1 | 301277.15 | -65127.5 | 78.3829 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the extension of the 78-day period was due to the inclusion of more works, which, due to their size, were not possible to fit within the contractually foreseen initial period. | need to include more works, due to unforeseeable causes at the date of the tender's launch.
4311 | 1327102 | Basic Sanitation in the Parish of Almalaguês - 5th Phase and Remodeling of the Water Network in the Vale de Cântaros System | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2012 | 2016 | Portugal | Coimbra | Coimbra | 6 | 26 | 24-07-2013 | 02-05-2016 | 1013 | 540 | 1400000 | 840074.9 | 2 | 675089.55 | 164985.35 | 124.439 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | it was due to bad weather. | there were many works that weren't done
4312 | 1326291 | "Improvement of E.N. 124 Between Barranco do Velho and the County Limit (Monte da Charneca)" | 45233142-6 | Road-repair works | FALSE | 2014 | 2016 | Portugal | Loulé | Faro | 8 | 30 | 09-10-2014 | 22-01-2016 | 470 | 210 | 1952397.33 | 1442129.24 | 3 | 1442129.24 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the deadline. there were administrative delays in scheduling the inspection. | there were no changes to the value of the project
4313 | 1324759 | Urban Arrangement contract for the junction at Largo da Feira, 1st phase - Reformulation of the junction with the E.R. 326-1 (Alvarenga) | 45233120-6 | Road construction works | FALSE | 2014 | 2016 | Portugal | Arouca | Aveiro | 1 | 20 | 15-12-2014 | 15-09-2016 | 640 | 150 | 279920.56 | 279415.77 | 2 | 246930.4 | 32485.37 | 113.1557 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with the deadline due to a fact attributable to the contractor. | occurrence of overwork and suppression of unnecessary work to complete the project.
4314 | 1322617 | This contract is intended for the drainage of domestic wastewater in the parishes of Repeses, União das Parishes of Vila Chã de Sá and Fail, S. João de Lourosa, Union of Parishes of Repeses | 45232460-4 | Sanitary works | FALSE | 2014 | 2016 | Portugal | Viseu | Viseu | 20 | 30 | 09-12-2014 | 01-02-2016 | 419 | 292 | 1276936.48 | 930060 | 2 | 876571.5 | 53488.5 | 106.102 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Technical value of the proposal ...... 21% 1.1) Compatibility between work plans, labor and equipment... 7% 1.2) Quality of the work plan... 7% 1.3) Quality of materials and equipment... 7% 2) Price ..75% 3) Execution time ... 4% | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | not having made available all the plots of land necessary for the constitution of administrative easements | not all the projects included in the measurement maps and budget of the contract were carried out.
4315 | 1320697 | Contract for the expansion and requalification of the pedagogical building of the Superior School of Technology and Management of Lamego of the Polytechnic Institute of Viseu | 45214410-7 | Polytechnic construction work | FALSE | 2014 | 2016 | Portugal | Lamego | Viseu | 20 | 21 | 15-09-2014 | 31-03-2016 | 563 | 240 | 1044782.05 | 744432.26 | 2 | 740905.06 | 3527.2 | 100.4761 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | several causes: bad weather, inaccessibility to the construction site (commemoration of the day of portugal, others). | underwork and project errors and omissions.
4316 | 1320398 | Construction contract for the 4th Section of the Vale do Gaio Hydraulic Circuit of the Alqueva Multipurpose Development | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2016 | Portugal | Alcácer do Sal | Setúbal | 17 | 43 | 04-12-2014 | 09-02-2016 | 432 | 274 | 4000000 | 2497720 | 3 | 2494947.66 | 2772.34 | 100.1111 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | different amounts of work. | amounts of work less than expected.
4317 | 1319013 | Felgueiras swimming pool complex - Conservation / Repair / Maintenance (Civil Construction and Energy Efficiency Works - conclusion)_x000D_ | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2014 | 2016 | Portugal | Felgueiras | Porto | 13 | 42 | 01-12-2014 | 27-09-2016 | 666 | 120 | 640021.89 | 571985.79 | 2 | 492279 | 79706.79 | 116.1914 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension requests | smaller quantities executed
4318 | 1317755 | Repair and Improvement Works of the Municipal Sports Pavilion and Surrounding Area | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2014 | 2016 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 30 | 28-11-2014 | 18-01-2016 | 416 | 120 | 233100 | 195576.24 | 1 | 195576 | 0.24 | 100.0001 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the need to provide clarification regarding the details of the project | there were no changes to the value of the project
4319 | 1316468 | Contract for the new Health Center in Ponta Delgada, on the island of São Miguel | 45215100-8 | Construction work for buildings relating to health | FALSE | 2012 | 2016 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 48 | 26-11-2012 | 31-03-2016 | 1221 | 540 | 16800000 | 14280000 | 3 | 14261848.11 | 18151.89 | 100.1273 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension | errors and omissions work
4320 | 1316425 | execution of the contract named ar 2235 - construction contract for the execution of the veade-britelo elevatory system, within the scope of the northwest multimunicipal water supply and sanitation system. | 45232411-6 | Foul-water piping construction work | FALSE | 2013 | 2016 | Portugal | Celorico de Basto | Braga | 3 | 42 | 15-07-2014 | 01-07-2016 | 717 | 364 | 1250000 | 788843.52 | 2 | 745350.49 | 43493.03 | 105.8352 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unavailability of the private land connecting to the britelo wwtp and constraints on the part of edp and the company infrastructras de portugal led to the extension of the contract's deadline. | deletion of some works resulted in underwork in the contract.
4321 | 1316194 | execution of the public work contract called ar 2210 - contract for implementation of the elevatory systems for the deactivation of the apúlia wwtp, forjães, antas, curvos and fão (esposende) - phase 1 | 45232411-6, 45232423-3 | Foul-water piping construction work, Sewage pumping stations construction work | FALSE | 2013 | 2016 | Portugal | Esposende | Braga | 3 | 49 | 28-02-2014 | 29-07-2016 | 882 | 546 | 2950000 | 2199921.93 | 3 | 2015349.7 | 184572.23 | 109.1583 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there are some difficulties in carrying out some works, which led the contractor to request a graceful extension of the contract period, which was approved by the owner of work | there were some situations of difficulty in complying with the stipulations in the execution project, so that, for the proper functioning of the system, it was necessary to proceed with the approval of works not foreseen in the initial contract, which were subject to approval by the project client
4322 | 1316013 | Construction of Support Infrastructures for the Municipal Stadium to Replace Installed Temporary Structures | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2016 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 30 | 28-11-2014 | 18-01-2016 | 416 | 120 | 278957.5 | 289968.53 | 2 | 277008.53 | 12960 | 104.6786 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the need to provide clarification regarding the details of the project | underwork
4323 | 1315825 | It consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution, in the project and in the specifications for the procedure | 45315100-9 | Electrical engineering installation works | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 21-11-2014 | 28-07-2016 | 615 | 575 | 247500 | 198000.01 | 1 | 198000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A
4324 | 1314909 | contract for "rehabilitation and improvement of the branch of e.r. nº 1-2ª, in the sections between the junction with street of arrabalde, s. sebastião, and the intersection with estrada de sta. margarida | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 24 | 16-09-2014 | 21-12-2016 | 827 | 180 | 670000 | 644700 | 2 | 617759.8 | 26940.2 | 104.361 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | interventions by the eda | negative price review
4325 | 1313328 | Construction of the seven-a-side football field | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2016 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 30 | 28-11-2014 | 18-01-2016 | 416 | 120 | 204608.04 | 187468.5 | 1 | 187219.5 | 249 | 100.133 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the need to provide clarification regarding the details of the project and the area to be intervened coincides with the area required for the construction of the contract | underwork
4326 | 1312710 | Requalification of the Lavandeira Industrial Zone | 45233200-1 | Various surface works | FALSE | 2014 | 2016 | Portugal | Mangualde | Viseu | 20 | 12 | 25-11-2014 | 19-08-2016 | 633 | 90 | 192000 | 172800.01 | 1 | 165440.19 | 7359.82 | 104.4486 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
4327 | 1310756 | Execution of the Contract - "Alto da Vela Car Park – Mafra” | 45223300-9 | Parking lot construction work | FALSE | 2014 | 2016 | Portugal | Mafra | Lisboa | 11 | N/A | 21-11-2014 | 19-02-2016 | 455 | 140 | 242218.78 | 203932.45 | 1 | 203932.45 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions.
4328 | 1309090 | The works include the execution of the infrastructure necessary for the expansion and extension of the Carvoeiro Regional System, namely the pipeline system, reservoirs, pumping stations | 45247270-3, 45252126-7, 45231112-3 | Reservoir construction works, Drinking-water treatment plant construction work, Installation of pipe system | FALSE | 2012 | 2016 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 48 | 16-04-2013 | 13-06-2016 | 1154 | 400 | 28700000 | 25080238.29 | 3 | 24604867.72 | 475370.57 | 101.932 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project deadline was graciously extended. the circumstances that led to the impossibility of completing the project on time were substantially attributable to the contractor, although there were constraints imposed on the planning and development of the project for reasons beyond his control. the alteration of the term of the project is supported in greater detail in the contractual documentation.
4329 | 1308603 | The objective of the intervention is to pave the carriageway with bituminous asphalt and improve the drainage conditions for rainwater. | 45233200-1 | Various surface works | FALSE | 2014 | 2016 | Portugal | Mangualde | Viseu | 20 | 12 | 25-11-2014 | 19-09-2016 | 664 | 60 | 167906.49 | 151115.85 | 1 | 150198.05 | 917.8 | 100.6111 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | as stated in the final account of the contract
4330 | 1307401 | The works include repairs and improvements to the infrastructures of the Carvoeiro Regional System (SRC), namely in conduits, reservoirs and other buildings supporting | 45247270-3, 45231110-9 | Reservoir construction works, Pipelaying construction work | FALSE | 2013 | 2016 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 47 | 14-02-2014 | 22-01-2016 | 707 | 200 | 2200000 | 1489828.31 | 3 | 1404309.56 | 85518.75 | 106.0897 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | the project was carried out in accordance with the execution project (there were no objective changes to the contract). the project had a total effective cost of €1,404,309.56, with a remaining balance of 5.74% corresponding to work that was not carried out. the project period was legally extended due to constraints imposed on the planning and development of the project for reasons beyond the responsibility of the contractor (essentially constraints imposed by concessionary entities).
4331 | 1307132 | The object of this object is the execution of the connection to the ETA of Cabeça Gorda-Obra 270A | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | Sardoal | Santarém | 16 | 20 | 21-11-2014 | 26-02-2016 | 462 | 180 | 1480000 | 1293472.12 | 3 | 1224205.2 | 69266.92 | 105.6581 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 55-day extension granted. | changes to the value of the project are due to underwork.
4332 | 1302496 | Contract for Consolidation of the Fontaínhas Escarpment - Sections 3.1 and 5.3 | 45243510-0 | Embankment works | FALSE | 2014 | 2016 | Portugal | Porto | Porto | 13 | 24 | 06-10-2014 | 11-04-2016 | 553 | 300 | 2100000 | 1379855.35 | 3 | 1376839.83 | 3015.52 | 100.219 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | 1st extension was due to the delay in authorizing the demolition of buildings in section 3.1 (lack of agreement with owners). 2nd extension was due to more work that had to be carried out. | generically, more work related to the need to replace a wall that had collapsed and which was covered by weeds and contractual work over estimates (quantities not used up – underwork).
4333 | 1302166 | Contract for "Installation/renovation of water networks and lowering of branches in the municipality of Oeiras" | 45232151-5 | Water-main refurbishment construction work | FALSE | 2014 | 2016 | Portugal | Oeiras | Lisboa | 11 | 11 | 31-07-2014 | 17-05-2016 | 656 | 420 | 436000 | 304359.25 | 2 | 273321.6 | 31037.65 | 111.3557 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | 425 days | the board of directors decided to reduce the amount
4334 | 1301631 | Urban Regeneration of the Village of Tábua | 45233160-8 | Paths and other metalled surfaces | FALSE | 2011 | 2016 | Portugal | Tábua | Coimbra | 6 | 36 | 14-11-2014 | 27-07-2016 | 621 | 365 | 978656.82 | 737959.22 | 2 | 565871.86 | 172087.36 | 130.411 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work to supply errors and omissions and changes to the initial project | underwork
4335 | 1301589 | Urban Requalification of Vila de Tábua - street of Indústria | 45233142-6 | Road-repair works | FALSE | 2014 | 2016 | Portugal | Tábua | Coimbra | 6 | 21 | 14-11-2014 | 27-07-2016 | 621 | 270 | 316000 | 271268.84 | 2 | 268346.45 | 2922.39 | 101.089 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the deadline for carrying out the project. | errors and omissions and underwork.
4336 | 1298161 | Matosinhos mar: rehabilitation of the coastline - coastal defense measures - lot 2 - reconstruction of walkways and the like - woodwork and dune protection | 45223000-6 | Structures construction work | FALSE | 2014 | 2016 | Portugal | Matosinhos | Porto | 13 | 11 | 17-10-2014 | 23-02-2016 | 494 | 270 | 971600 | 394302 | 2 | 394302 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change
4337 | 1298137 | Matosinhos mar: requalification of the coastline - coastal defense measures - lot 1 - paradise beach - reinforced concrete works | 45223000-6 | Structures construction work | FALSE | 2014 | 2016 | Portugal | Matosinhos | Porto | 13 | 11 | 09-10-2014 | 23-02-2016 | 502 | 270 | 971600 | 426115.2 | 2 | 426115.2 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change
4338 | 1297656 | Requalification of the public space in the western part of the historic center of Viana do Castelo - streetFrei Bartolomeu dos Mártires and streetCónego Domingos Borlido | 45113000-2 | Siteworks | FALSE | 2013 | 2016 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 27 | 06-11-2014 | 22-07-2016 | 624 | 150 | 478600.35 | 467950.79 | 2 | 467950.79 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions
4339 | 1288948 | It consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution, in the project and in the specifications governing the procedure | 45261420-4 | Waterproofing work | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 28-10-2014 | 06-01-2016 | 435 | 575 | 247500 | 198000.01 | 1 | 198000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | • there was an urgent need to carry out work in several schools and municipal buildings, so that the normal functioning of services was not affected; • several cases were identified that require urgent intervention; • it will be convenient for these works to be carried out before the rainy season, in order to guarantee that there are no serious problems of infiltration, existence of fungi, and other anomalies, which compromise the normal functioning of the buildings;
4340 | 1288715 | It consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution, in the project and in the specifications governing the procedure | 45232450-1 | Drainage construction works | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 28-10-2014 | 07-01-2016 | 436 | 575 | 247485 | 197988.01 | 1 | 197988.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | • there was an urgent need to carry out work in several schools and municipal buildings, so that the normal functioning of services was not affected; • several cases were identified that require urgent intervention; • it would be convenient for these works to be carried out before the rainy season, in order to guarantee that there are no drainage problems, land subsidence in opening ditches, increased flow, sewage problems, and other anomalies;
4341 | 1287700 | Expansion of the Serra 1 primary school - Lousado | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 07-05-2014 | 11-03-2016 | 674 | 365 | 870613.38 | 576999.37 | 2 | 572792.39 | 4206.98 | 100.7345 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work for a period of 25 days. | underwork worth €4,206.98.
4342 | 1287672 | Expansion of theelementary school 1st cycle school in Bairro | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 07-05-2014 | 18-01-2016 | 621 | 365 | 959000 | 716125.32 | 2 | 701106.78 | 15018.54 | 102.1421 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of the project for a period of 25 days. | underwork worth 15,018.54 euros.
4343 | 1284245 | Contract for the construction of the Technological Pole - Matilde Rosa Araujo School | 45223210-1, 45112700-2, 45112000-5, 45351000-2, 45214800-8 | Structural steelworks, Landscaping work, Excavating and earthmoving work, Mechanical engineering installation works, Training facilities building | FALSE | 2013 | 2016 | Portugal | Cascais | Lisboa | 11 | 20 | 07-08-2014 | 10-02-2016 | 552 | 192 | 450000 | 448570.64 | 2 | 448570.64 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | to change the electricity project
4344 | 1284059 | Construction contract for the São Matias Hydraulic Circuit of the Alqueva Multipurpose Project. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Beja | Beja | 2 | N/A | 06-10-2014 | 10-11-2016 | 766 | 515 | 19000000 | 13105619 | 3 | 13105619 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | power connection | pricing review.
4345 | 1284010 | Construction contract for the Caliços - Machados Hydraulic Circuit of the Alqueva Multipurpose Project. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Moura | Beja | 2 | 43 | 06-10-2014 | 14-12-2016 | 800 | 545 | 21200000 | 16952704.35 | 3 | 16951941.72 | 762.63 | 100.0045 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | over and under works and supply works. | over and under works and supply works.
4346 | 1282883 | Rehabilitation and Expansion of Building Destined for Security Forces | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2014 | 2016 | Portugal | Tabuaço | Viseu | 20 | 24 | 28-10-2014 | 19-12-2016 | 783 | 365 | 819655.59 | 598600 | 2 | 592975.3 | 5624.7 | 100.9486 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | temporary impossibility of complying with the initial contract, due to the fact that the project site is still occupied by the previous construction site (section a) of article 297 of the public contracts code). likewise, the adverse weather conditions that conditioned the execution of the exterior repairs and the presence of high humidity inside the building that made it impossible to execute the vinyl and epoxy floors. | suppression of works for not being necessary for the execution of the project.
4347 | 1272375 | Requalification of the rugby field - Construction of changing rooms | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2016 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 16-10-2014 | 11-03-2016 | 512 | 240 | 336885 | 329499.2 | 2 | 328047.53 | 1451.67 | 100.4425 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | price review
4348 | 1271429 | Improvement of en 396 – section between the industrial zone of loulé and the franchised zone – 1st phase | 45233251-3 | Resurfacing works | FALSE | 2014 | 2016 | Portugal | Loulé | Faro | 8 | 36 | 07-08-2014 | 18-07-2016 | 711 | 210 | 654000 | 444545.53 | 2 | 425722.07 | 18823.46 | 104.4215 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | delays in scheduling the provisional reception. | contract work not performed.
4349 | 1271193 | Construction of a promenade along the bank of the Inha River and placement of Decks. | 45246510-1 | Boardwalk construction work | FALSE | 2014 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 15-10-2014 | 05-02-2016 | 478 | 90 | 199419 | 174137.66 | 1 | 174137.66 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | delay attributable to the contractor.
4350 | 1268865 | E.R. REHABILITATION contract Nº 2-1ª, section between streetPadre Rocha Sousa and Cruz do Marco in Santa Cruz, Praia da Vitória - Terceira Island - Azores | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 24 | 28-07-2014 | 16-12-2016 | 872 | 180 | 550000 | 484850 | 2 | 462728.7 | 22121.3 | 104.7806 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | intervention by the eda | negative price review
4351 | 1262119 | It includes the construction work of niches / large drawers in a wired concrete structure in brick masonry, execution of plasters, ceramic coatings, paintings, placement of metallic elements | 45215400-1 | Cemetery works | FALSE | 2014 | 2016 | Portugal | Barreiro | Setúbal | 17 | 20 | 22-09-2014 | 11-03-2016 | 536 | 120 | 214000 | 185713.03 | 1 | 185713.03 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | due to atmospheric conditions | without changes
4352 | 1262058 | Infrastructure and Paving of streets I, J, K, L, M, N, O and P in Vila Nova de Paiva | 45233252-0 | Surface work for streets | FALSE | 2014 | 2016 | Portugal | Vila Nova de Paiva | Viseu | 20 | 12 | 08-07-2014 | 16-09-2016 | 801 | 180 | 345000 | 314308.65 | 2 | 301826.69 | 12481.96 | 104.1355 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | atmosphere conditions
4353 | 1261366 | It consists of carrying out the work defined in terms of its type, quantity and technical conditions of execution in the project and in the specifications governing the procedure | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 01-10-2014 | 15-02-2016 | 502 | 120 | 244820.67 | 201851.83 | 1 | 201851.83 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A
4354 | 1260163 | Porta do Mezio - Center for the Promotion and Enhancement of Local Products | 45212420-6 | Construction work for restaurants and similar facilities | FALSE | 2014 | 2016 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 25-09-2014 | 25-01-2016 | 487 | 240 | 322565.27 | 284861.7 | 2 | 271050.38 | 13811.32 | 105.0955 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | lack of human resources on site and lack of work organization | underwork
4355 | 1259131 | Paving of the road of bicas | 45233200-1 | Various surface works | FALSE | 2014 | 2016 | Portugal | Grandola | Setúbal | 17 | 12 | 26-08-2014 | 11-01-2016 | 503 | 45 | 212243.08 | 164084.03 | 1 | 174881.6 | -10797.57 | 93.8258 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | due to the submission of more works | replacement of the material initially planned to be applied in the construction, tout-venant for hot materials, due to the advanced state of degradation of the pavement in question
4356 | 1257822 | Rehabilitation of the Bus Station - Av.ª Sr.ª do Castelo | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Mangualde | Viseu | 20 | 12 | 26-09-2014 | 23-12-2016 | 819 | 90 | 212000 | 190800.01 | 1 | 181638.75 | 9161.26 | 105.0437 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4357 | 1254286 | Benefit from E.M. 595 | 45233142-6 | Road-repair works | FALSE | 2013 | 2016 | Portugal | Vagos | Aveiro | 1 | 30 | 26-09-2014 | 26-01-2016 | 487 | 60 | 191058.78 | 174800 | 1 | 174673 | 127 | 100.0727 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension for a period of 9 days (from 11/14/2014 to 11/22/2014), based on paragraph a) of number 3 of article 366 of the "public procurement code" | measurements of work actually carried out.
4358 | 1243821 | Contract for the Refurbishment of the Competence Center - Greenhouse Support Building (former museum) and the Training Center of the Agricultural Campus of Vairão. | 45453100-8 | Refurbishment work | FALSE | 2013 | 2016 | Portugal | Vila do Conde | Porto | 13 | 24 | 26-06-2014 | 16-11-2016 | 874 | 365 | 1380000 | 1173722.17 | 3 | 1238203.6 | -64481.43 | 94.7923 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | requests for graceful deadline extensions. | existence of additional works.
4359 | 1241480 | The contract project aims to create a leisure space, pedestrian and cycle circulation, in the northern part of the City, which extends, in a section between street ofmião de Góis and streetJosé Régio; | 45233162-2 | Cycle path construction work | FALSE | 2014 | 2016 | Portugal | Entroncamento | Santarém | 16 | 20 | 19-09-2014 | 27-05-2016 | 616 | 270 | 850000 | 629979.77 | 2 | 622316.53 | 7663.24 | 101.2314 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | granted 2 grace period extensions. | underwork.
4360 | 1232941 | Urban requalification of several arteries in the historic center of the village of Almodôvar - Malpica, Afionso and Arco streets | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Almodovar | Beja | 2 | 30 | 16-09-2014 | 23-03-2016 | 554 | 180 | 560000 | 336000.01 | 2 | 351648.7 | -15648.69 | 95.5499 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | changes to existing infrastructure that were not fully registered. integration of power grid transformer station, project adaptation. | more work and underwork
4361 | 1230187 | Ançã Sports Complex - Support Building and Surrounding Areas | 45210000-2 | Building construction work | FALSE | 2014 | 2016 | Portugal | Cantanhede | Coimbra | 6 | 21 | 29-08-2014 | 15-06-2016 | 656 | 300 | 1185000 | 990000 | 2 | 973702.22 | 16297.78 | 101.6738 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | underwork
4362 | 1229022 | Contract for "Rehabilitation of the Non-stabilized Sludge Cell of Alcanena WWTP" | 45232422-6 | Sludge-treatment works | FALSE | 2010 | 2016 | Portugal | Alcanena | Santarém | 16 | 48 | 15-04-2014 | 07-06-2016 | 784 | 610 | 4500000 | 3844399.53 | 3 | 3882834.6 | -38435.07 | 99.0101 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork; more works; price review.
4363 | 1214787 | Refurbishment of the Portelinha soccer field in Pedras Salgadas | 45236119-7 | Repair work on sports fields | FALSE | 2014 | 2016 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 12 | 09-09-2014 | 23-05-2016 | 622 | 90 | 349521.54 | 314220 | 2 | 306137.07 | 8082.93 | 102.6403 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the delivery of materials by suppliers and adverse weather conditions. | job suppression and price revision.
4364 | 1210206 | “Contract to carry out the sealing of two dumpsters on Graciosa Island” | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | Santa Cruz da Graciosa | Região Autónoma dos Açores | 15 | 24 | 08-09-2014 | 02-03-2016 | 541 | 120 | 800000 | 779000 | 2 | 779000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension
4365 | 1210057 | Contract for the execution of the sealing of two dumpsters on Ilha das Flores | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2016 | Portugal | N/A | Região Autónoma dos Açores | 15 | 24 | 29-08-2014 | 05-05-2016 | 615 | 120 | 1100000 | 1087000 | 3 | 1087000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension. | the project has not changed its value.
4366 | 1207938 | Construction of Multiservice Building | 45211350-7 | Multi-functional buildings construction work | FALSE | 2014 | 2016 | Portugal | Sobral de Monte Agraço | Lisboa | 11 | 12 | 28-08-2014 | 05-01-2016 | 495 | 180 | 350000 | 329396.87 | 2 | 329396.87 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there was an extension of the execution period of the project for another 30 days, requested by the contractor, due to lack of material and adverse weather conditions.
4367 | 1196933 | Requalification of the Zimão - Serra da Falperra route - Phase 2 | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2016 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 12 | 05-09-2014 | 29-03-2016 | 571 | 90 | 349399.63 | 296989.89 | 2 | 296989.89 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions and delay in the delivery of materials by suppliers.
4368 | 1188762 | Microenterprise Support Center | 45210000-2 | Building construction work | FALSE | 2013 | 2016 | Portugal | Sousel | Portalegre | 12 | 20 | 30-06-2014 | 27-01-2016 | 576 | 365 | 527751.49 | 413999.96 | 2 | 413999.96 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4369 | 1186931 | Road marking 2014 - lot 6 | 45233142-6 | Road-repair works | FALSE | 2014 | 2016 | Portugal | N/A | N/A | N/A | 24 | 01-09-2014 | 23-11-2016 | 814 | 180 | 1637500 | 210590.26 | 1 | 196846.89 | 13743.37 | 106.9818 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the legal extension of the contract period for 75 days was requested in order to ensure during this period the management of items with existing balances, in order to make it possible to improve service levels with regard to the road marking of the oc during the period extended until the entry into force of a new homologous contract. | the change in the value of the project resulted from the determination of positive errors and omissions correction work in the amount of €33,915.71 and negative errors and omissions correction work in the amount of €47,659.08
4370 | 1186783 | Drainage networks on street of Vales and Encosta Poente da Pedrulha | 45232400-6 | Sewer construction work | FALSE | 2014 | 2016 | Portugal | Coimbra | Coimbra | 6 | 20 | 28-08-2014 | 03-02-2016 | 524 | 100 | 350000 | 272172.39 | 2 | 246341.07 | 25831.32 | 110.486 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | rise of water table levels in the area of ​​connection to the general collector | there were works that were not carried out
4371 | 1186033 | Construction of Padre Tobias Nursery, in Samora Correia | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2013 | 2016 | Portugal | Benavente | Santarém | 16 | 31 | 08-05-2014 | 23-03-2016 | 685 | 365 | 904500 | 645000 | 2 | 645000 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project took place within the legal deadline for execution, although the provisional reception was made after the deadline.
4372 | 1181262 | execution of the contract called ar 2198 - construction contract for the execution of the veade river interceptor – 1st phase, within the scope of the northwest multimunicipal water supply and sanitation system. | 45232411-6, 45232423-3, 45112500-0 | Foul-water piping construction work, Sewage pumping stations construction work, Earthmoving work | FALSE | 2013 | 2016 | Portugal | Celorico de Basto | Braga | 3 | 50 | 24-03-2014 | 30-05-2016 | 798 | 301 | 1000000 | 678880.19 | 2 | 610884.86 | 67995.33 | 111.1306 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project resulted in a graceful extension being granted to the contractor. | changes to the project allowed for a reduction in the project foreseen in the contract, resulting in underwork.
4373 | 1181219 | execution of the public work contract named ar 2190 - contract for execution of the rio ave interception system (fd10) – 1st phase, within the scope of the multimunicipal water supply | 45112500-0, 45232423-3, 45232411-6 | Earthmoving work, Sewage pumping stations construction work, Foul-water piping construction work | FALSE | 2013 | 2016 | Portugal | Vila do Conde | Porto | 13 | 49 | 06-06-2014 | 23-02-2016 | 627 | 365 | 2500000 | 1801386.02 | 3 | 1510893.31 | 290492.71 | 119.2266 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | as a result of the objective modification of the contract, there was a need to negotiate easements in other lands. | 1) objective modification of contract for reasons of public interest arising from a new weighing of existing circumstances; 2) suppression of the 10.san gravity interceptor and 3) optimization of constructive solutions.
4374 | 1180868 | execution of the contract called ar 2109 – construction contract for the execution of the drainage system of marinhas sul (fd11), within the scope of the multimunicipal system of water supply | 45232411-6 | Foul-water piping construction work | FALSE | 2012 | 2016 | Portugal | Esposende | Braga | 3 | 50 | 19-03-2014 | 12-09-2016 | 908 | 240 | 770000 | 685282.47 | 2 | 509278.34 | 176004.13 | 134.5595 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | there are some difficulties in carrying out some works, which will have led the contractor to delay the execution of the project. | there were some situations of difficulty in complying with the stipulated in the execution project, with works initially foreseen in the contract having been suppressed.
4375 | 1180648 | execution of the contract called ar 2110 – contract for execution of the cávado/esposende intercetors (fd11) – 1st phase, within the scope of the multimunicipal water supply | 45232423-3, 45232411-6, 45112500-0 | Sewage pumping stations construction work, Foul-water piping construction work, Earthmoving work | FALSE | 2012 | 2016 | Portugal | Esposende | Braga | 3 | 49 | 06-06-2014 | 13-09-2016 | 830 | 420 | 2100000 | 1688194.37 | 3 | 1688194.37 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | no change | no change
4376 | 1180506 | execution of the public works contract named ar 2061 - construction contract for the intercetors of ribeira da granja, apple tree da maia and tougues (fd10) | 45232411-6 | Foul-water piping construction work | FALSE | 2011 | 2016 | Portugal | Vila do Conde | Porto | 13 | 50 | 19-12-2012 | 11-04-2016 | 1209 | 180 | 840000 | 468847.04 | 2 | 530221.53 | -61374.49 | 88.4247 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | due to adverse weather conditions, the contract had to be suspended with the consequent extension of the contractual term. due to serious design errors in the farm's riverside interceptor, it was necessary to change the solution initially envisaged, leading to an extension of the deadline and an increase in work to supply errors and omissions. | due to design errors, in the farm's riverside interceptor, it was necessary to change the initially envisaged solution, leading to an increase in work to supply errors and omissions. due to the unavailability of a connection point for the maia da maia interceptor, it was necessary to carry out additional work in order to allow the interceptor to be connected to a compact wwtp. due to the exact measurement on site, the decrease in the number of boxes executed and the replacement of the execution method for crossing the en13 in the farm's interceptor, resulting in underwork in the contract.
4377 | 1180444 | execution of the contract called ar 2108 - construction contract for the execution of the antas elevatory system, within the scope of the northwest multimunicipal water supply and sanitation system. | 45232423-3, 45232411-6, 45112500-0 | Sewage pumping stations construction work, Foul-water piping construction work, Earthmoving work | FALSE | 2011 | 2016 | Portugal | Esposende | Braga | 3 | 48 | 12-03-2014 | 25-02-2016 | 715 | 240 | 840000 | 668394.71 | 2 | 654573.39 | 13821.32 | 102.1115 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | constraints on entering private plots. alterations to the execution project only detectable in the construction phase. delays in connecting the electricity that made it impossible to test the equipment.
4378 | 1172239 | Rehabilitation in the 2nd collapse zone in the structure of Ribeira da Granja on R. D. Pedro de Meneses | 45246200-5 | Riverbank protection works | FALSE | 2014 | 2016 | Portugal | Porto | Porto | 13 | 20 | 19-08-2014 | 19-09-2016 | 762 | 120 | 650000 | 459990.07 | 2 | 447524.3 | 12465.77 | 102.7855 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the conditions of heavy rainfall and spring tides did not allow the flow to be channeled through the bypass created inside the stream and destroyed the cofferdams and shoring necessary for carrying out the rehabilitation works. it also contributes to the delay of the project in the delivery of elements related to the construction methods to be adopted in the projects, the technical difficulties in its execution and the alterations to the construction methods proposed by the contractor. | the constructive solutions of the support structure were changed, which now include lost metallic profiles as an alternative to the provisional shoring foreseen in the proposal. the method of concreting the walls and the slab covering the structure of the stream was also changed, which changed from sprayed concrete to formworked concrete.
4379 | 1169450 | Construction of irrigation, road and drainage infrastructure for the Moura Gravitic Block, with the following main characteristics:  Irrigation networks (1674 ha with an extension of 18.9 km of pipelines | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Moura | Beja | 2 | 50 | 21-08-2014 | 08-04-2016 | 596 | 390 | 6950000 | 5786410 | 3 | 5850177.87 | -63767.87 | 98.91 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | period of inspections for reception. | carrying out procurement work and existence of underwork.
4380 | 1167879 | Conservation and maintenance of the sanitation network in the western and northern zones of the city of lisbon” | 45232460-4 | Sanitary works | FALSE | 2013 | 2016 | Portugal | Lisboa | Lisboa | 11 | 21 | 26-08-2014 | 06-09-2016 | 742 | 365 | 699992.53 | 448345.42 | 2 | 448345.25 | 0.17 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4381 | 1167597 | Rehabilitation and improvement of Avenida de S. Mateus, which includes repair+paving, construction of sidewalks and cycle paths, and electrical, rainwater and telecommunications infrastructure | 45432110-8 | Floor-laying work | FALSE | 2014 | 2016 | Portugal | Murtosa | Aveiro | 1 | 30 | 27-08-2014 | 24-06-2016 | 667 | 180 | 343490.2 | 228692.86 | 1 | 205764.01 | 22928.85 | 111.1433 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | the project ran as normal. | underwork and price revision.
4382 | 1165388 | Construction of irrigation, road and drainage infrastructure for the Barras, Torrão and Baronia Baixo Blocks, with the following main characteristics:  Irrigation networks (2274 ha with an extension of 23 km | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Alvito | Setúbal | 17 | 49 | 21-08-2014 | 01-07-2016 | 680 | 390 | 8000000 | 5589000 | 3 | 5440613.75 | 148386.25 | 102.7274 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | reception inspections. | the executed quantities differed in some works from the initially estimated quantities.
4383 | 1161261 | It consists of the execution of horizontal road signs, softening the northern geographical area of ​​the municipality of Amadora, in places where there is a need to replace the existing signs | 45233221-4 | Road-surface painting work | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 19-08-2014 | 26-07-2016 | 707 | 620 | 207545 | 166036.9 | 1 | 166036.9 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A
4384 | 1159970 | Construction of irrigation, road and drainage infrastructure in the Roxo-Sado Block, with the following main characteristics:  Irrigation networks (4033 ha with an extension of 32 km of pipelines); | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Aljustrel | Beja | 2 | 48 | 29-07-2014 | 14-11-2016 | 839 | 510 | 17950000 | 12998538.77 | 3 | 13566221.02 | -567682.25 | 95.8155 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 25 | N/A | N/A | N/A | N/A | N/A | N/A | need to reformulate the constituent parts of the hydrants and interference with the hydraulic circuit contract that took place simultaneously. | the executed quantities differed in some works from the initially estimated quantities.
4385 | 1153601 | The object of this contract is the remodeling of the reservoir of the Lagoa/Ílhavo system (PAA 010) contemplating the recovery of the structural elements of concrete and existing metalwork | 50000000-5 | Repair and maintenance services | FALSE | 2014 | 2016 | Portugal | Ílhavo | Aveiro | 1 | N/A | 30-07-2014 | 02-03-2016 | 581 | 90 | 175000 | 154890.77 | 1 | 154890.77 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays in the execution of the contract, due to errors in the project, which had to be revised.
4386 | 1150883 | Refurbishment of the car park and bus station in Lamego | 45000000-7 | Construction work | FALSE | 2014 | 2016 | Portugal | Lamego | Viseu | 20 | 15 | 01-08-2014 | 18-01-2016 | 535 | 180 | 708380.42 | 637542.38 | 2 | 622667.06 | 14875.32 | 102.389 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | climatic reasons that hindered the development of the project. | there was a price revision, value in favor of the municipality.
4387 | 1149264 | House of sandpaper culture - construction (completion) | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2014 | 2016 | Portugal | Felgueiras | Porto | 13 | 24 | 04-08-2014 | 15-01-2016 | 529 | 120 | 281959.83 | 197130.93 | 1 | 196670.12 | 460.81 | 100.2343 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some adverse situations during the execution of the project | smaller quantities executed
4388 | 1149059 | Romanas Golf Academy - Pedras Salgadas - (Phase 2 - Golf and Putting Green) | 45112721-5 | Landscaping work for golf courses | FALSE | 2014 | 2016 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 5 | 14-08-2014 | 26-02-2016 | 561 | 110 | 291472.34 | 265000 | 2 | 265000 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | impediment of work on private land and delay in the delivery of materials by suppliers.
4389 | 1147674 | Execution of the contract for the environmental requalification of the Penas quarry. | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2014 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 12-08-2014 | 16-05-2016 | 643 | 270 | 1218817 | 731290.21 | 2 | 743997.06 | -12706.85 | 98.2921 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | deadline due to t+ and errors & omissions (39 days). delay in carrying out the project attributable to the contractor (186 days). period elapsed between the 1st and the last inspection for the purposes of provisional acceptance, to correct deficiencies (121 days). | overwork and underwork and errors & omissions.
4390 | 1143059 | The purpose of the contract is the execution of the water supply and drainage networks and the treatment of domestic and rainwater wastewater in the village of Martinhanes. | 45232460-4 | Sanitary works | FALSE | 2013 | 2016 | Portugal | Mértola | Beja | 2 | 30 | 30-07-2014 | 03-05-2016 | 643 | 365 | 1235000 | 737913.85 | 2 | 655139.07 | 82774.78 | 112.6347 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | completion of the technical compilation and performance of final tests of the equipment installed at the eta | underwork
4391 | 1138590 | Contract for: "Requalification of street lias Garcia (crossing street of Casal Melão to Meia Via)" | 45233200-1 | Various surface works | FALSE | 2014 | 2016 | Portugal | Entroncamento | Santarém | 16 | 30 | 29-07-2014 | 16-05-2016 | 657 | 270 | 600000 | 499886.35 | 2 | 474947.52 | 24938.83 | 105.2509 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | granted 1 grace period extension. | underwork
4392 | 1129317 | Construction of irrigation and road infrastructure for the Baronia and Alvito Altos and Alvito Baixo blocks. | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2016 | Portugal | Alvito | Beja | 2 | 46 | 15-07-2014 | 06-07-2016 | 722 | 545 | 15150000 | 10732117.75 | 3 | 10551839.98 | 180277.77 | 101.7085 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | reception inspections. | the executed quantities differed in some works from the initially estimated quantities.
4393 | 1129302 | Ponte de Sor Municipal Airfield - 2nd Phase - University Campus | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2013 | 2016 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 03-07-2014 | 15-04-2016 | 652 | 270 | 4277278.72 | 4299000 | 3 | 4296705.45 | 2294.55 | 100.0534 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existence of extension of term | underwork
4394 | 1129066 | It consists of the execution of horizontal road signs, covering the geographic area south of the municipality of amadora, in places where there is a need to replace existing signs. | 45233221-4 | Road-surface painting work | FALSE | 2014 | 2016 | Portugal | Amadora | Lisboa | 11 | 21 | 22-07-2014 | 02-02-2016 | 560 | 620 | 207545 | 166036.9 | 1 | 162867.5 | 3169.4 | 101.946 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A |  | due to the decrease of the price revision in the amount of -3,169.40€.
4395 | 1128944 | The purpose of this contract is to expand the wastewater drainage and water supply networks throughout the contract period. These extensions will be requested by the owner of the object. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2014 | 2016 | Portugal | Aveiro | Aveiro | 1 | N/A | 16-07-2014 | 05-07-2016 | 720 | 1095 | 245000 | 234275.79 | 1 | 234275.79 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractual deadline elapsed for less time, because many extensions were requested in a short period of time and the contractor gave a positive response in its execution.
4396 | 1128512 | Refurbishment and expansion of the Oliveira Sta. Maria | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2016 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 21-07-2014 | 13-04-2016 | 632 | 240 | 512000 | 310496.88 | 2 | 287543.37 | 22953.51 | 107.9826 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work for a period of 30 + 30 days. | unbilled initial contract works worth €22,953.51.
4397 | 1128349 | Execution of all the works that are part of the contract to modernize the irrigation block XIV | 45232120-9 | Irrigation works | FALSE | 2013 | 2016 | Portugal | Aljezur | Faro | 8 | 31 | 27-06-2014 | 02-05-2016 | 675 | 275 | 4990000 | 3847748.59 | 3 | 3818407.7 | 29340.89 | 100.7684 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delivery times for equipment and piping in ffd | not doing some work
4398 | 1126445 | Requalification and urban enhancement of the industrial zones of maia - industrial zone of maia i and porvene | 45233142-6 | Road-repair works | FALSE | 2011 | 2016 | Portugal | Maia | Porto | 13 | 45 | 17-07-2014 | 10-02-2016 | 573 | 540 | 4294760 | 2576857 | 3 | 2699724.22 | -122867.22 | 95.4489 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the execution period was thirty days for the execution of the additional works. | the value of the contract was changed due to the execution of more works, in the total amount of €128,367.22 and there was, auto de inspecção and measurement of single works, of that value without vat. on december 30, 2015.
4399 | 1113864 | Requalification of streets in the urban area of ​​vilar formoso - zone c - | 45233252-0 | Surface work for streets | FALSE | 2014 | 2016 | Portugal | Almeida | Guarda | 9 | 19 | 26-06-2014 | 30-03-2016 | 643 | 270 | 390585.38 | 297000 | 2 | 294223.76 | 2776.24 | 100.9436 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | high density of existing infrastructure along rua de s. joão and rua da gnr and weather conditions. | existence of underwork for which it was verified that there was no need to carry it out.
4400 | 1109882 | execution of the contract for construction of the new headquarters of the order of architects - north regional section - north 41º: center for architecture, creativity and sustainability | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2016 | Portugal | Porto | Porto | 13 | 20 | 13-06-2014 | 10-03-2016 | 636 | 450 | 1400000 | 1248627.49 | 3 | 1195586.46 | 53041.03 | 104.4364 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the coexistence of autonomous contracts from the general contract that influenced the normal progress of the projects, as well as some unpredictable difficulties in the supply of materials whose supply was the responsibility of the owner of work, by virtue of signed protocols. | the existence of underwork.
4401 | 1108663 | The object of the contract is the contract for the expansion and alteration of the Santana da Serra Senior Home building | 45215212-6 | Retirement home construction work | FALSE | 2013 | 2016 | Portugal | Ourique | Beja | 2 | 30 | 16-06-2014 | 18-01-2016 | 581 | 450 | 606870 | 497860.29 | 2 | 497860.29 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | conjugation of works with another contract taking place in the same location; adverse weather conditions; current adverse economic conditions, causing delays in the procurement of materials.
4402 | 1107418 | The contract includes work on foundations and structures, masonry, plastering, roofing, insulation, ceramic floors and coatings, sanitary equipment, stonework, window frames, carpentry | 45453100-8 | Refurbishment work | FALSE | 2013 | 2016 | Portugal | Mértola | Beja | 2 | 30 | 20-06-2014 | 19-01-2016 | 578 | 365 | 352435.87 | 252949.42 | 2 | 248334.88 | 4614.54 | 101.8582 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | work completed on time. delay in the delivery of documentation. | underwork
4403 | 1106722 | Construction contract for irrigation, road and drainage infrastructure in the Beja block. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Beja | Beja | 2 | 40 | 23-06-2014 | 09-05-2016 | 686 | 548 | 25575000 | 19002753.97 | 3 | 18664513.55 | 338240.42 | 101.8122 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | execution of supply work and extra work. | execution of procurement works and overworks and not performing underworks
4404 | 1103491 | Dredging work that proves necessary to remove a maximum amount of 980,000 m3 of sediments and respective immersion in the places indicated in the execution project. | 45252124-3 | Dredging and pumping works | FALSE | 2013 | 2016 | Portugal | Ílhavo | Aveiro | 1 | 31 | 18-06-2014 | 03-02-2016 | 595 | 730 | 2980000 | 2871400 | 3 | 2767894.18 | 103505.82 | 103.7395 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the silting that occurred in the areas subject to the contract forced their dredging in advance. | price review
4405 | 1100152 | Construction contract for the irrigation, road and drainage infrastructure in Blocks 3 and 4 of São Matias. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Beja | Beja | 2 | 42 | 13-06-2014 | 12-04-2016 | 669 | 578 | 23485500 | 16885000 | 3 | 15686576.05 | 1198423.95 | 107.6398 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | period necessary to carry out inspections for reception purposes. | the executed quantities differed in some works from the initially estimated quantities.
4406 | 1100108 | Construction contract for the irrigation, road and drainage infrastructure of the Caliços Machados Block. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Beja | Beja | 2 | 50 | 13-06-2014 | 02-11-2016 | 873 | 578 | 16900000 | 13489077 | 3 | 12838928.72 | 650148.28 | 105.0639 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | - difficulties in keeping contracted subcontractors on site, as well as in ensuring the timely supply of materials and equipment essential to the project. | existence of underworks.
4407 | 1099951 | Construction contract for the irrigation, road and drainage infrastructure for the Beringel and Álamo Blocks. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Beja | Beja | 2 | 49 | 13-06-2014 | 31-03-2016 | 657 | 485 | 10200000 | 7142729 | 3 | 7584325.56 | -441596.56 | 94.1775 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | carrying out supply work and additional work. | carrying out supply work and extra work and not performing underwork.
4408 | 1099860 | Construction contract for the irrigation and drainage infrastructure in Blocks 1 and 2 of São Matias. | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2016 | Portugal | Vidigueira | Beja | 2 | 41 | 13-06-2014 | 01-07-2016 | 749 | 485 | 12950000 | 9785000 | 3 | 9560567.03 | 224432.97 | 102.3475 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | on the one hand, there were constraints on the execution of some works caused by the simultaneous execution of another contract, which gave rise to a deadline extension. on the other hand, there was an under-allocation of means on the part of the contractor, who bore, to that extent, the corresponding costs. | the executed quantities differed in some works from the initially estimated quantities.
4409 | 1095241 | Completion of the Execution of the Domestic Wastewater Drainage Network of Fonte Boa dos Nabos and Seixal - Phase II | 45232410-9 | Sewerage work | FALSE | 2013 | 2016 | Portugal | Mafra | Lisboa | 11 | 20 | 27-05-2013 | 11-01-2016 | 959 | 120 | 425000 | 388136.11 | 2 | 320730.24 | 67405.87 | 121.0164 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays by the contractor | works less
4410 | 1095239 | Construction of Gravity System 2 of the Achada/Sobreiro Domestic Wastewater Drainage Network | 45232400-6 | Sewer construction work | FALSE | 2012 | 2016 | Portugal | Mafra | Lisboa | 11 | 20 | 21-02-2013 | 11-01-2016 | 1054 | 150 | 450000 | 393741.75 | 2 | 344216.17 | 49525.58 | 114.3879 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays by the contractor | works less
4411 | 1095236 | Barras Domestic Wastewater Drainage Network | 45232410-9 | Sewerage work | FALSE | 2012 | 2016 | Portugal | Mafra | Lisboa | 11 | 20 | 24-08-2012 | 26-10-2016 | 1524 | 180 | 190000 | 168152.27 | 1 | 168152.27 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | licensing problems for works in em and disputes with contractors
4412 | 1094483 | Restoration contract for the Geophysical Institute in Serra do Pilar | 45453100-8 | Refurbishment work | FALSE | 2013 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 25 | 03-06-2014 | 29-03-2016 | 665 | 180 | 415000 | 373500 | 2 | 399826.16 | -26326.16 | 93.4156 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions mentioned in the "deadline extensions" box. | overwork and supply of errors and omissions mentioned in the table "increases in the cost of the project", as well as underwork and fines for delay in carrying out the projects, mentioned in the table "decreases in the cost of the project".
4413 | 1074128 | "Construction, expansion and improvement of the pre-school education center in alcácer do sal" | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2016 | Portugal | Alcácer do Sal | Setúbal | 17 | 21 | 20-05-2014 | 14-01-2016 | 604 | 365 | 854554 | 776253.72 | 2 | 816877.63 | -40623.91 | 95.0269 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of works (additional contracts 1 and 2) | execution of works (additional contracts 1 and 2)
4414 | 1061638 | Bakery street requalification (phase 1 and phase 3) | 45233140-2 | Roadworks | FALSE | 2014 | 2016 | Portugal | Marinha Grande | Leiria | 10 | 20 | 13-05-2014 | 03-10-2016 | 874 | 150 | 449621.31 | 308000 | 2 | 275245.78 | 32754.22 | 111.9 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | for facts attributable to the owner of the project | for the purpose of deleting works and works from additional works
4415 | 1059099 | Urban rehabilitation of the facilities of the former J. Ferreira custódio factory | 45233140-2 | Roadworks | FALSE | 2014 | 2016 | Portugal | Marinha Grande | Leiria | 10 | 20 | 07-05-2014 | 29-11-2016 | 937 | 150 | 433317.68 | 333665.53 | 2 | 316386.53 | 17279 | 105.4614 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | for facts attributable to the owner of the project | due to price revisions and job suppression
4416 | 1059051 | Refurbishment of street ofs Laranjeiras | 45233140-2 | Roadworks | FALSE | 2013 | 2016 | Portugal | Marinha Grande | Leiria | 10 | 20 | 08-05-2014 | 13-06-2016 | 767 | 180 | 350558.71 | 282000 | 2 | 285807.56 | -3807.56 | 98.6678 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | for a fact attributable to the owner of the project | due to additional work, suppression of work and price revisions
4417 | 1036035 | Contract for “Execution of the ETA of Paúl (Phase 1), of the Pressure Tower and respective connection to the supply duct to the North Sector; Equipment and pipelines for interconnection between holes L6, L7 and L10 | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2016 | Portugal | Pombal | Leiria | 10 | 30 | 15-11-2013 | 29-07-2016 | 987 | 300 | 4900000 | 2940000.01 | 3 | 2862334.71 | 77665.3 | 102.7134 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | lack of electricity in the boreholes of mata do urso and delay in the definitions of integration of the infrastructures by the smas of leiria | underwork
4418 | 1033583 | Reinforcement of the water supply to the northwest sector of the Municipality of Coimbra - Section between Espertina and Antuzede | 45232151-5 | Water-main refurbishment construction work | FALSE | 2013 | 2016 | Portugal | Coimbra | Coimbra | 6 | 40 | 26-03-2014 | 27-01-2016 | 672 | 180 | 470000 | 398643.55 | 2 | 286609.8 | 112033.75 | 139.0893 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | conditions due to estradas de portugal having to study new methods | change to the project, underwork has occurred
4419 | 1029660 | Preliminary works, demolitions, signage, lancing/ paving, drainage, vertical signage, horizontal signage | 45233221-4 | Road-surface painting work | FALSE | 2011 | 2016 | Portugal | Figueira da Foz | Coimbra | 6 | 11 | 17-03-2014 | 29-01-2016 | 683 | 365 | 195033 | 179000 | 1 | 144722.78 | 34277.22 | 123.6847 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline for completion of the project
4420 | 1017014 | Requalification and Defense of the Dune Cord of the Maritime Front between Praia da Vagueira and Praia do Labrego | 45233222-1 | Paving and asphalting works | FALSE | 2013 | 2016 | Portugal | Vagos | Aveiro | 1 | 30 | 19-03-2014 | 15-01-2016 | 667 | 150 | 924114.17 | 708500.58 | 2 | 701421.25 | 7079.33 | 101.0093 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | notice of suspension: dated 05/05/2014 - having verified the lack of approval by the court of auditors and the expected entry into force of the 2014 bathing season, from 06/21/ to 09/07, it was considered convenient to proceed the suspension of execution of works until 15/09/2014. notice of restarting work: dated 09/15/2014, since the causes that led to the suspension of work on 05/05/2014 have ceased. extension of the project deadline, for a total of 119 days: execution of tasks along the coast, with work rhythms less than normal due to adverse weather conditions and due to strong maritime agitation, and also due to the need to study the compatibility of the project with the natural terrain, with regard to the wooden walkways, derived from the natural movements of sand and maritime dynamics, a situation that caused delays in the physical execution of the project. | resulting from the execution of additional work and from the measurements of the quantities of work actually carried out during the course of the project.
4421 | 1016845 | Refurbishment of the central section of the marginal douro interceptor and reformulation of the high/low connections | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2016 | Portugal | Porto | Porto | 13 | 47 | 25-03-2014 | 31-10-2016 | 951 | 300 | 3844840.79 | 3678266.16 | 3 | 4605978.36 | -927712.2 | 79.8585 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | the extension of the 213-day period was due to the inclusion of more works, which, due to their size, were not possible to fit within the contractually foreseen initial period. the remaining extension of the 169-day period was due to the need to, taking into account the great impact that the contract had on the city, it was necessary to reduce the project fronts ensuring harmony between the projects and the impacts that the city felt. | need to include more works, for unforeseen and unforeseen reasons at the date of the tender's launch.
4422 | 1013012 | Execution of the necessary works for access and infrastructure associated with the 3rd phase of the ETRS da Meia Serra landfill, namely construction of road access, execution of a washing system | 45315600-4, 45233123-7, 45315500-3, 45232452-5 | Low-voltage installation work, Secondary road construction work, Medium-voltage installation work, Drainage works | FALSE | 2013 | 2016 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 50 | 20-03-2014 | 18-02-2016 | 700 | 120 | 700000 | 624936.02 | 2 | 624744.48 | 191.54 | 100.0307 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | . | public interest (art.º 312.º b))
4423 | 1010329 | Repair and improvement of sports and leisure spaces - Guilhadezes sports complex | 45212200-8 | Construction work for sports facilities | FALSE | 2013 | 2016 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 16-12-2013 | 11-03-2016 | 816 | 180 | 554600 | 542141.41 | 2 | 536515.87 | 5625.54 | 101.0485 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in meeting the partial deadlines for the project, justified by the contractor with changes to the project, with adverse weather conditions with the difficulty of supplying materials and with the assignment of the contractual position. | over and underwork
4424 | 1007033 | Regularization and Channeling of several streams in the parish of Ribeira da Janela | 45246000-3 | River regulation and flood control works | FALSE | 2013 | 2016 | Portugal | Porto Moniz | Região Autónoma da Madeira | 14 | 23 | 13-03-2014 | 13-05-2016 | 792 | 180 | 886100 | 160000.01 | 1 | 159984.61 | 15.4 | 100.0096 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | difference between planned and executed quantities.
4425 | 1002401 | Construction of the Tourist Office in Peso da Régua | 45210000-2 | Building construction work | FALSE | 2013 | 2016 | Portugal | Peso da Régua | Vila Real | 19 | 20 | 10-03-2014 | 07-01-2016 | 668 | 180 | 194387.26 | 189277.53 | 1 | 189277.53 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for the project was extended by 120 days due to the delay in the supply of specific materials, wood of non-domestic origin. | there was no change in the value of the contract.
4426 | 995505 | Construction of the Santarém Business Innovation Center | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2016 | Portugal | Santarém | Santarém | 16 | 61 | 28-02-2014 | 01-03-2016 | 732 | 90 | 349000 | 244303.61 | 1 | 237388.77 | 6914.84 | 102.9129 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work | errors and omissions supply works and work less
4427 | 989481 | Construction contract for the Abrantes Family Health Unit consists of the construction of a new building, suitable for the installation of services of a collective and/or social nature. | 45215100-8 | Construction work for buildings relating to health | FALSE | 2013 | 2016 | Portugal | Abrantes | Santarém | 16 | 36 | 20-02-2014 | 06-12-2016 | 1020 | 365 | 1381427.81 | 1048918.4 | 3 | 1026696.33 | 22222.07 | 102.1644 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline changes were due to the approval of the removal of asbestos-containing asbestos-cement sheets from the roof of the building, by the act, the current situation related to financial difficulties, or the closure of companies linked to civil construction and motivated by a accident at work that caused two fatal victims. | the alterations were motivated by the revision of prices and the existence of underwork.
4428 | 983416 | execution of the contract for the public work "electrification of a set of agro-forestry farmings", which consists of the electrification of 19 agro | 45315300-1 | Electricity supply installations | FALSE | 2013 | 2016 | Portugal | Alandroal | Évora | 7 | 30 | 11-02-2014 | 24-03-2016 | 772 | 240 | 477310.4 | 401237.09 | 2 | 360558.9 | 40678.19 | 111.282 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project's execution time came about due to the need to adapt the project to the withdrawal of electrification from some farms, a fact that also gave rise to the suppression of contracted works; and, due to the appearance of additional work, errors and omissions and due to a delay in completing the project of about 15 days, the responsibility of which was attributed to the successful tenderer. | supply of errors & omissions work: €19,974.14; additional work: €10,236.58; ordinary price revision (provisional) negative: -1,816.61€; underwork: €69,272.30;
4429 | 979560 | execution of the contract for “reordering the insertion of avenida kopke with the commercial wharf in ponta delgada and the south side of fort de são brás”. | 45233000-9 | Construction, foundation and surface works for highways, roads | FALSE | 2013 | 2016 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 30 | 06-02-2014 | 02-02-2016 | 726 | 150 | 476000 | 439816.45 | 2 | 428327.6 | 11488.85 | 102.6823 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need for supply and delivery of missing materials. | underwork.
4430 | 973403 | Construction, Improvement and Conservation of Other Buildings, by Contract - Rehabilitation and expansion of a building for use by the Security Forces in Praia da Tocha - CP-CCP-EMP n.º 01/2013 | 45262700-8 | Building alteration work | FALSE | 2013 | 2016 | Portugal | Cantanhede | Coimbra | 6 | 27 | 06-02-2014 | 29-12-2016 | 1057 | 240 | 203610.96 | 157325.08 | 1 | 147265.86 | 10059.22 | 106.8307 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | completion of works | existence of underwork and negative price revision
4431 | 971285 | Requalification of the rugby field - construction of stands | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2013 | 2016 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 24 | 31-01-2014 | 25-02-2016 | 755 | 240 | 347500 | 347445.99 | 2 | 347395.69 | 50.3 | 100.0145 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | design adjustments and poor weather conditions | underwork
4432 | 970971 | The contract comprises the completion of the access to Cabanas de Tavira | 45232451-8 | Drainage and surface works | FALSE | 2013 | 2016 | Portugal | Tavira | Faro | 8 | 30 | 31-01-2014 | 22-04-2016 | 812 | 150 | 347669.98 | 228987.66 | 1 | 226139.43 | 2848.23 | 101.2595 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather | underwork and price revision
4433 | 968358 | Execution of the refurbishment and expansion of the school building | 45214210-5 | Primary school construction work | FALSE | 2013 | 2016 | Portugal | Cadaval | Lisboa | 11 | 20 | 28-01-2014 | 28-07-2016 | 912 | 270 | 600861.79 | 402363.47 | 2 | 410099.32 | -7735.85 | 98.1137 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | already justified | already justified
4434 | 968204 | Execution of civil construction work, foundations and structures, water and sewage and fire, electrical installations, structured network, mechanical installations and outdoor spaces | 45215100-8 | Construction work for buildings relating to health | FALSE | 2013 | 2016 | Portugal | Sines | Setúbal | 17 | N/A | 10-01-2014 | 14-10-2016 | 1008 | 426 | 1955000 | 1522000 | 3 | 1488231.59 | 33768.41 | 102.269 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | accumulation of delays in the various stages of the project by the successful tenderer | supply of errors and omissions work and underwork
4435 | 953255 | Execution of work to support interventions to repair or change the Water Distribution and Wastewater Drainage Systems of the A.R.M. | 45232150-8, 45232460-4 | Works related to water-distribution pipelines, Sanitary works | FALSE | 2013 | 2016 | Portugal | Santana | Região Autónoma da Madeira | 14 | 20 | 17-01-2014 | 11-07-2016 | 906 | 365 | 330000 | 289913.72 | 2 | 289407.28 | 506.44 | 100.175 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | addendum of 01/17/2015 to extend the contract for another six months, in order to use the remaining contractual balance on that date. | however, during the execution of the contract, it was verified that there was no need to apply the entire contractual quantity of the aforementioned suction cups in the context of carrying out the projects, thus not having the need to assemble 8 of the 20 proposed units.
4436 | 941564 | Contract for the Protection and Recovery of the Dune System, through the Reinforcement of the Dune Cord between Costa Nova and Mira, within the Scope of the Intervention of the Polis Litoral Ria de Aveiro | 45243400-6 | Beach-consolidation works | FALSE | 2013 | 2016 | Portugal | Ílhavo | Aveiro | 1 | 30 | 12-08-2013 | 21-03-2016 | 952 | 365 | 4300000 | 2948757.61 | 3 | 2893018.38 | 55739.23 | 101.9267 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | on november 19, 2014, the contractor rosas construtores, s.a formalized a request for a 200-day extension of the contract deadline. in a meeting of the plra board of directors, the owner approved the requested extension. with this extension of time, the completion date of the contract was set at may 30, 2014; on may 5, 2015, the contractor rosas construtores, s.a requested that the plantations be postponed so that they could be carried out at a more favorable time for these works, namely, in october and november 2015 so that they could be completed by december 2015 the project owner approved in a meeting of the board of directors of the plra the extension requested by the successful bidder. with this extension of time, the completion date of the contract was set for the end of december 2015
4437 | 941081 | Execution of the contract for the rehabilitation of buildings in the Senhora do Amparo municipal allotment (lots 11, 12 and 13) in Vila do Bispo, in accordance with the specifications described in the specifications | 45454000-4 | Restructuring work | FALSE | 2013 | 2016 | Portugal | Vila do Bispo | Faro | 8 | 30 | 10-12-2013 | 15-11-2016 | 1071 | 180 | 307000 | 184200.01 | 1 | 182807.89 | 1392.12 | 100.7615 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | contractor's speed | ordinary price review
4438 | 937918 | Improvement of the Infrastructures of the Manuel da Mota Industrial Park - Proc. No. 50/2013 | 45233220-7 | Surface work for roads | FALSE | 2013 | 2016 | Portugal | Pombal | Leiria | 10 | 18 | 10-12-2013 | 29-03-2016 | 840 | 120 | 326333.52 | 263000 | 2 | 254601.82 | 8398.18 | 103.2986 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | it was due to the delay in agreeing the measurements with the executing entity. | existence of underwork and revision of prices.
4439 | 923920 | Improvement of the EM 561 from Sequeade to the limit of the county | 45233140-2 | Roadworks | FALSE | 2013 | 2016 | Portugal | Barcelos | Braga | 3 | 24 | 17-12-2013 | 10-02-2016 | 785 | 547 | 1780416.66 | 1513354.17 | 3 | 1446589.72 | 66764.45 | 104.6153 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the existence of adverse weather conditions in january and february 2015, which conditioned the normal execution of the projects. | the existence of works with expected quantities above those actually executed and measured.
4440 | 922738 | The purpose of this contract is to improve the WTP in France, including expanding it from a current capacity of 620 m3/h to a capacity of 755 m3/h | 45252126-7 | Drinking-water treatment plant construction work | FALSE | 2013 | 2016 | Portugal | Bragança | Bragança | 4 | 33 | 17-12-2013 | 17-06-2016 | 913 | 330 | 1100000 | 1078000 | 3 | 1070728.64 | 7271.36 | 100.6791 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | guarantee of uninterrupted operation of the eta | guarantee of uninterrupted operation of the eta
4441 | 907078 | Municipal market - conservation / maintenance | 45213140-6 | Market construction work | FALSE | 2012 | 2016 | Portugal | Felgueiras | Porto | 13 | 24 | 27-11-2013 | 08-01-2016 | 772 | 240 | 677893.13 | 610103.82 | 2 | 474865.33 | 135238.49 | 128.4793 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some adverse situations during the execution of the project | smaller quantities executed.
4442 | 905729 | Contract number 1/dmpo/dcmivp/ds/12 – “preservation and maintenance of the sanitation network in the western part of the city of lisbon” (process n.º 67/cp/deps/n.d./2012) | 45232460-4 | Sanitary works | FALSE | 2013 | 2016 | Portugal | Lisboa | Lisboa | 11 | 21 | 22-11-2013 | 07-04-2016 | 867 | 365 | 618678.74 | 393118.81 | 2 | 393118.67 | 0.14 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A
4443 | 903965 | ETAR Expansion Contract in Évora | 45232420-2 | Sewage work | FALSE | 2013 | 2016 | Portugal | Évora | Évora | 7 | 47 | 21-11-2013 | 18-02-2016 | 819 | 400 | 1650000 | 1550434.78 | 3 | 1657948.39 | -107513.61 | 93.5153 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | as established in clause 53.1.1 of the tender specifications, “the period for carrying out the contract is 400 days (…) plus 180 days for carrying out the start-up, until the provisional acceptance”. during the start-up phase, which has a minimum period of 180 days, the successful tenderer must enforce all the assumptions imposed in the declaration of guarantees. since there was difficulty on the part of the successful tenderer in complying with all the requirements set out in the declaration of guarantees, the start-up phase lasted beyond 180 days, with all the conditions for provisional acceptance only being met in february 2016 . | the increased costs of the contract resulted from the need to perform some works not initially foreseen, resulting from the supply of errors/omissions, or unforeseen works, but strictly necessary for the conclusion of the contract – Extra work.
4444 | 900747 | Refurbishment of the customs building for installation of the cedet / aect, in vilar formoso | 45262700-8 | Building alteration work | FALSE | 2012 | 2016 | Portugal | Almeida | Guarda | 9 | 24 | 04-10-2012 | 22-04-2016 | 1296 | 365 | 1259603.03 | 834469.84 | 2 | 827708.58 | 6761.26 | 100.8169 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | additional work, supply of errors and omissions. | underwork, errors and omissions and price review
4445 | 881301 | Educational Center of Aguada de Cima | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2016 | Portugal | Águeda | Aveiro | 1 | 36 | 06-11-2013 | 11-04-2016 | 887 | 365 | 2252744.01 | 1516406.52 | 3 | 1510874.35 | 5532.17 | 100.3662 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration of the deadline for execution of the project resulted from the approval of the map of additional works and work to correct errors and omissions n. | the value of the project has changed due to the approval of additional work and work to correct errors and omissions identified in map no. 1 and contemplated in additional contract no. 3/2015/cma.
4446 | 877581 | Execution of the contract for the Construction of a Bridge over the Levada grotto, located at ER 1-1ª, in Ajuda da Maravilha - Ponta Delgada - São Miguel Island - Azores | 45221110-6 | Bridge construction work | FALSE | 2013 | 2016 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 36 | 26-09-2013 | 06-10-2016 | 1106 | 90 | 480000 | 478000 | 2 | 446815.55 | 31184.45 | 106.9793 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4447 | 875790 | Adaptation of the building to a tourist office and memory space of the Sephardic presence | 45212313-3 | Museum construction work | FALSE | 2013 | 2016 | Portugal | Bragança | Bragança | 4 | 30 | 30-10-2013 | 08-08-2016 | 1013 | 365 | 940000 | 644992.51 | 2 | 644992.51 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension
4448 | 870025 | Construction of a School Center | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2016 | Portugal | Arronches | Portalegre | 12 | 30 | 02-09-2013 | 19-02-2016 | 900 | 600 | 3171767.82 | 2450000 | 3 | 2601345.68 | -151345.68 | 94.182 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 40 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions due to project doubts and overwork | extra work
4449 | 855623 | EN258-1 – Improvement between Vila Ruiva and Cuba (km 0+000 to km 9+300) and between Cuba and IP2 (km 10+747 to km 16+350) | 45233142-6 | Road-repair works | FALSE | 2012 | 2016 | Portugal | Cuba | Beja | 2 | 42 | 05-07-2013 | 19-05-2016 | 1049 | 120 | 1650000 | 1286873.63 | 3 | 1260699.32 | 26174.31 | 102.0762 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline extension granted was due to adverse weather conditions | clearance during the course of the project of correcting errors and omissions in the amount of €26,437.06 and of correcting negative errors and omissions in the amount of €52,611.37
4450 | 851811 | "Valuing and Boosting Tourism - Route/Aldeia de Várzeas - Luso" | 45262310-7 | Reinforced-concrete work | FALSE | 2013 | 2016 | Portugal | Mealhada | Aveiro | 1 | N/A | 09-10-2013 | 01-04-2016 | 905 | 154 | 254000 | 189909.24 | 1 | 172926.33 | 16982.91 | 109.8209 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension due to new edp requirements regarding the ip network. | overwork, underwork, and errors and omissions supply work.
4451 | 851045 | Rehabilitation and regularization of the São João stream - construction of the A5 to A8 dams | 45247220-8 | Weir construction work | FALSE | 2011 | 2016 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 49 | 04-10-2013 | 30-03-2016 | 908 | 540 | 9450000 | 6836358.69 | 3 | 6830018.51 | 6340.18 | 100.0928 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | difference between planned and executed quantities
4452 | 831585 | Construction contract for the Baixo Alentejo Business Initiatives Center | 45210000-2 | Building construction work | FALSE | 2012 | 2016 | Portugal | Castro Verde | Beja | 2 | 60 | 31-07-2013 | 26-02-2016 | 940 | 365 | 1150000 | 997356.56 | 2 | 1026924.46 | -29567.9 | 97.1207 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | regarding carrying out additional work | with regard to carrying out the project further
4453 | 826285 | 1 SHIPYARD 1.1 Assembly and maintenance of the overall construction site, including fences, accesses, easements, indicative panels of the designer and contract, utilities and provisional access networks | 45233220-7 | Surface work for roads | FALSE | N/A | 2016 | Portugal | Penalva do Castelo | Viseu | 20 | N/A | 08-07-2013 | 18-01-2016 | 924 | 90 | N/A | 285571.45 | 2 | 311114.38 | -25542.93 | 91.7899 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension and suspension of the term | over and underwork and price revision
4454 | 817871 | Refurbishment of the water supply network in various areas of the municipality of coimbra – 7th phase – (ingote/ lordemão/ brasfemes systems, alto 5 reis, ademia, chão do Bispo | 45232151-5 | Water-main refurbishment construction work | FALSE | 2013 | 2016 | Portugal | Coimbra | Coimbra | 6 | 24 | 03-07-2013 | 27-01-2016 | 938 | 450 | 1350000 | 842924.77 | 2 | 809740.6 | 33184.17 | 104.0981 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to weather conditions | there were works that were not performed
4455 | 809251 | Urban Regeneration of the North Quarter of Praça Francisco Barbosa, in the parish of Beduído, in the municipality of Estarreja | 45211360-0 | Urban development construction work | FALSE | 2013 | 2016 | Portugal | Estarreja | Aveiro | 1 | 36 | 02-08-2013 | 29-04-2016 | 1001 | 485 | 669000 | 401400.01 | 2 | 394800.03 | 6599.98 | 101.6717 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of works | underwork and price revision
4456 | 806057 | The contract includes construction work on the domestic wastewater pumping station, including civil construction, electrical and electromechanical installations, involving demolition work | 45232431-2 | Wastewater pumping station | FALSE | 2012 | 2016 | Portugal | Barreiro | Setúbal | 17 | 20 | 26-03-2013 | 06-01-2016 | 1016 | 120 | 260000 | 238500.94 | 1 | 238500.94 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A
4457 | 801419 | “Urban arrangement of Praça d. Afonso III, streetD. Paio peres belt and old spouts square (fountain)” – o.m. 102/2012 | 45233251-3, 45315600-4, 45232460-4 | Resurfacing works, Low-voltage installation work, Sanitary works | FALSE | 2013 | 2016 | Portugal | Loulé | Faro | 8 | 48 | 15-07-2013 | 20-10-2016 | 1193 | 365 | 934758.79 | 699997.23 | 2 | 692119.78 | 7877.45 | 101.1382 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | i have to inform you that effectively the discovery of archaeological structures of a relevant nature conditioned the normal progress of the projects. although its appearance was already foreseen, the archaeological find exceeded initial expectations, and the time that elapsed between the careful excavation, and the lack of decision (independent of these services) about what to do and how the structure would be protected, conditioned the normal course of work. having a work front temporarily discontinued. | contract work not performed.
4458 | 800601 | Access roads to Santa Cristina: E.M. From Ribeira to Santa Cristina and paving the E.M. from Santa Cristina to Vila Boa | 45233120-6 | Road construction works | FALSE | 2013 | 2016 | Portugal | Mortágua | Viseu | 20 | 20 | 18-07-2013 | 17-02-2016 | 944 | 120 | 348108.76 | 208186.92 | 1 | 259259.46 | -51072.54 | 80.3006 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | weather reasons | due to the fact that the project had €52,891.76 more work.
4459 | 800389 | Requalification of the banks of the Avelâmes River | 45112710-5 | Landscaping work for green areas | FALSE | 2013 | 2016 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 20 | 24-07-2013 | 01-03-2016 | 951 | 300 | 914867.09 | 804000.44 | 2 | 804000.44 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | impediment of work on private land, uncertainties and project and weather conditions.
4460 | 790849 | Being close to people: social housing - biquinha housing development - 4th phase | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2011 | 2016 | Portugal | Matosinhos | Porto | 13 | 36 | 02-07-2013 | 19-04-2016 | 1022 | 210 | 256000 | 179903.2 | 1 | 177725.91 | 2177.29 | 101.2251 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | no deadline change | there was less price revision. (-2177.29€)
4461 | 782281 | Construction of the Negrais Reservoir - Maceira Reservoir System/ Pedra Furada ETA | 45247270-3 | Reservoir construction works | FALSE | 2012 | 2016 | Portugal | Sintra | Lisboa | 11 | 30 | 18-06-2013 | 03-03-2016 | 989 | 450 | 450000 | 335031.04 | 2 | 324208.63 | 10822.41 | 103.3381 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions, some delays under the responsibility of the contractor, issues related to the electrical part under the responsibility of the d.o. and connections to existing networks are also the responsibility of the d.o. | being a work paid for by measurement, there were less quantities and some unused items (by pass for example)
4462 | 781196 | As part of the Environmental and Territorial Enhancement and Qualification Program - Actions to Enhance the Coast of Vila Nova de Gaia, the project for the Requalification of the Natural Front of the River | 45233200-1 | Various surface works | FALSE | 2012 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 36 | 01-03-2013 | 15-02-2016 | 1081 | 179 | 1940000 | 1641802.47 | 3 | 1559661.74 | 82140.73 | 105.2666 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | an amendment to the consignment was duly approved, due to the assignment of the contractual position. | negative price revision in the amount of €71,095.39; additional work worth €45,034.83; errors and omissions worth €9,674.01 and underwork worth €65,754.18.
4463 | 776058 | Construction contract for the São Pedro - Baleizão hydraulic circuit at the Alqueva Multipurpose Project. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2016 | Portugal | Beja | Beja | 2 | 45 | 11-06-2013 | 14-06-2016 | 1099 | 517 | 33000000 | 19952550 | 3 | 19981478.3 | -28928.3 | 99.8552 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of additional and supply work. | the changes are essentially due to: - alteration of the quantities foreseen in the treatments of the foundations of dams and gates; - adaptation of the electrical infrastructure of the pumping station substation, in order to comply with edp requirements; - difference between planned and actually executed quantities.
4464 | 775724 | Construction contract for the Amoreira - Caliços hydraulic circuit at the Alqueva Multipurpose Development. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2016 | Portugal | Moura | Beja | 2 | 45 | 21-05-2013 | 14-06-2016 | 1120 | 547 | 26500000 | 19730000 | 3 | 19759877.26 | -29877.26 | 99.8488 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | integration of the supervision system with the ch caliços-pias and ch caliços-machados. | the changes are essentially due to: - amounts of work effectively carried out lower than those initially estimated; - integration of the supervision system with the ch caliços-pias and ch caliços-machados.
4465 | 772366 | Construction contract for the Caliços - Sinks hydraulic circuit at the Alqueva Multipurpose Development. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2016 | Portugal | Serpa | Beja | 2 | 45 | 21-05-2013 | 30-08-2016 | 1197 | 487 | 14415000 | 11194670 | 3 | 11177143.41 | 17526.59 | 100.1568 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the formalization of the provisional acceptance notice was pending the authorization of infraestruturas de portugal, s.a., to proceed with the diversion of traffic from the en 255 for the restoration of that road, over the dam. | the changes are essentially due to differences between the amounts of work planned and carried out.
4466 | 767163 | Construction contract for the Vale do Gaio Hydraulic Circuit of the Alqueva Multipurpose Project. | 45247000-0 | Construction work for dams, canals, irrigation channels and aqueducts | FALSE | 2010 | 2016 | Portugal | Alvito | Setúbal | 17 | 47 | 07-12-2010 | 21-01-2016 | 1871 | 485 | 20000000 | 14571398 | 3 | 13604186.2 | 967211.8 | 107.1097 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the successful tenderer underwent a restructuring process that led to its integration into the elevogrupo group. | non-execution of works that were also considered in another contract, also by edia; failure to supply electricity to some switching chambers; difference between planned and realized quantities of work.
4467 | 764175 | The object of this contract is the construction of the Montezinho Water Reserve Dam and the Hydraulic Circuit to Connect the latter to the Existing System. | 45247000-0, 45231300-8 | Construction work for dams, canals, irrigation channels and aqueducts, Construction work for water and sewage pipelines | FALSE | 2012 | 2016 | Portugal | Bragança | Bragança | 4 | 50 | 23-05-2013 | 11-05-2016 | 1084 | 420 | 8000000 | 5300000 | 3 | 5685323.45 | -385323.45 | 93.2225 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out at a slower pace of work than anticipated, given its specificity versus the contractor's inexperience in carrying out this type of work, difficulties increased by the severe weather conditions that were felt, with heavy snowfall and consequent interruptions to the project. the project was concluded within the foreseen objectives and with appreciable quality, although with significant delay. | they stemmed from the need to carry out more work and the supply of errors and omissions in the terms of reference but which are intended for the project itself and which should have been part of it from the beginning, not being technically and economically separated from the initial contract.
4468 | 760137 | Project for alteration of the former convent of reparation of the santissimo sacramento (ji + eb) | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2012 | 2016 | Portugal | Lisboa | Lisboa | 11 | 47 | 09-05-2013 | 20-01-2016 | 986 | 365 | 5500000 | 3494399.63 | 3 | 3494399.63 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 25 | N/A | N/A | N/A | N/A | N/A | N/A
4469 | 752246 | Path paving | 45233220-7 | Surface work for roads | FALSE | 2012 | 2016 | Portugal | Mértola | Beja | 2 | 30 | 30-04-2013 | 03-02-2016 | 1009 | 180 | 491732 | 311664.12 | 2 | 307476.73 | 4187.39 | 101.3619 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | conditions for non-execution of work within periods defined in an icnb opinion, referring to special protection areas. | underwork
4470 | 749957 | Rehabilitation and expansion of the kindergarten in the neighborhood of Belém | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2012 | 2016 | Portugal | Lisboa | Lisboa | 11 | 21 | 18-04-2013 | 27-05-2016 | 1135 | 150 | 1414604.74 | 1249999.34 | 3 | 1142082.17 | 107917.17 | 109.4492 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A
4471 | 744550 | Execution of the Construction Contract for Colégio Fundação Alentejo - Nursery, Kindergarten, 1st Cycle, in Évora, under the terms and with the specifications | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2016 | Portugal | Évora | Évora | 7 | 20 | 29-12-2010 | 31-03-2016 | 1919 | 240 | 3675000 | 3123750 | 3 | 3198170.33 | -74420.33 | 97.673 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the initial work plan was completed
4472 | 734210 | Rehabilitation of the Sassoeiros Outfall – intermediate and final sections (over a length of 4,185 m) – which runs between chambers CV.21 and CV.143, replacing the current outfall | 45232410-9 | Sewerage work | FALSE | 2010 | 2016 | Portugal | Cascais | Lisboa | 11 | 30 | 08-03-2013 | 17-03-2016 | 1105 | 270 | 3640000 | 2184000.08 | 3 | 2295277.12 | -111277.04 | 95.1519 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions associated with extra work. | changes to the value of the project are due to more and less described works.
4473 | 711334 | Ponte de Sor Municipal Airfield - 2nd Phase - Construction of Hangar | 45213351-8 | Maintenance hangar construction work | FALSE | 2012 | 2016 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 27-02-2013 | 15-04-2016 | 1143 | 150 | 1897214.3 | 1333244.44 | 3 | 1331833.12 | 1411.32 | 100.106 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underworks
4474 | 697613 | Innovation Space of the Municipality of Mealhada | 45210000-2 | Building construction work | FALSE | 2011 | 2016 | Portugal | Mealhada | Aveiro | 1 | 30 | 22-02-2013 | 24-05-2016 | 1187 | 364 | 815000 | 779750 | 2 | 790576.7 | -10826.7 | 98.6305 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions associated with the execution of work to correct errors and omissions and the need to change the electrical project, including the respective approval with certiel | the value of the project resulted from the existence of work to supply errors and omissions and work less
4475 | 678046 | execution of the public works contract remodeling the water supply to sinks, sale and new houses in mares. | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2011 | 2016 | Portugal | Alandroal | Évora | 7 | 30 | 23-01-2013 | 23-05-2016 | 1216 | 300 | 393035.79 | 349994.9 | 2 | 334447.53 | 15547.37 | 104.6487 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | due to the suspension ordered by the developer, motivated by cash flow difficulties / financial unavailability. deadline extension due to delay for which the successful tenderer is responsible, but which were not the subject of sanctions. | elimination of contract works ordered by the d.o., worth €15,640.17, and due to the ordinary price review worth €92.80, carried out on a provisional basis as all the economic indicators were not known.
4476 | 654996 | execution of the public work contract called ar 2018 - contract for execution of the intercetors of the sousa ii subsystem (fd15) - part 1, within the scope of the multimunicipal water supply system | 45232411-6 | Foul-water piping construction work | FALSE | 2010 | 2016 | Portugal | Felgueiras | Porto | 13 | 49 | 10-12-2012 | 15-01-2016 | 1131 | 487 | 3000000 | 1800000.01 | 3 | 1861148.25 | -61148.24 | 96.7145 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | no change | errors and omissions work
4477 | 641636 | Construction of a wooden pedestrian bridge over the Enxarrique stream and enhancement of the landscape in the surrounding area | 45112700-2 | Landscaping work | FALSE | 2012 | 2016 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 18 | 13-12-2012 | 23-02-2016 | 1167 | 180 | 356804.39 | 229796.67 | 1 | 238748.62 | -8951.95 | 96.2505 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty in acquiring materials and performing extra work | execution of additional work
4478 | 732437 | execution of the public work contract called ar 2019 - contract for execution of the intercetors of the sousa ii subsystem (fd15) - part 2, within the scope of the multimunicipal water supply system | 45232411-6 | Foul-water piping construction work | FALSE | 2011 | 2016 | Portugal | Felgueiras | Porto | 13 | 53 | 21-11-2012 | 27-05-2016 | 1283 | 487 | 4250000 | 2421401.12 | 3 | 2334973.51 | 86427.61 | 103.7014 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | an extension of the 159-day period associated with carrying out the remaining works was approved, including sections conditioned by the opinion of the apa. | errors and omissions work
4479 | 623968 | Elaboration of Specialty Execution Projects and the Construction Contract for the Silvalde School Center | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2011 | 2016 | Portugal | Espinho | Aveiro | 1 | 48 | 26-06-2012 | 14-06-2016 | 1449 | 480 | 3917703.75 | 3525933.09 | 3 | 3842615.46 | -316682.37 | 91.7587 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | assignment of the contractual position. | changes to the value of the project were due to the financial balance and price revision.
4480 | 619294 | Regularization and Canalization of Ribeira da Vargem - São Vicente | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2016 | Portugal | São Vicente | Região Autónoma da Madeira | 14 | 46 | 15-11-2012 | 20-04-2016 | 1252 | 360 | 5544800 | 3326883.21 | 3 | 3329865.14 | -2981.93 | 99.9104 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities and price revision.
4481 | 607306 | Chaves Roman Baths Museum | 45212313-3 | Museum construction work | FALSE | 2012 | 2016 | Portugal | Chaves | Vila Real | 19 | 30 | 05-11-2012 | 28-10-2016 | 1453 | 365 | 2325000 | 1800000 | 3 | 1840457.62 | -40457.62 | 97.8018 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of works, rescheduling of works and overwork. | more work and underwork
4482 | 604652 | The object of this contract is the construction of a building intended for residences for the elderly and people with reduced mobility, as well as a Day Center to support residents | 45215214-0 | Residential homes construction work | FALSE | 2012 | 2016 | Portugal | Amadora | Lisboa | 11 | 36 | 25-10-2012 | 15-04-2016 | 1268 | 480 | 2408924 | 2150876.39 | 3 | 2149714.79 | 1161.6 | 100.054 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unpredictable weather conditions and contractor's per | final adjustment of measurements
4483 | 585700 | Stabilization of the Garachico slope - Câmara de Lobos | 45111230-9 | Ground-stabilisation work | FALSE | 2011 | 2016 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 21 | 23-08-2012 | 09-06-2016 | 1386 | 360 | 1900000 | 1478000 | 3 | 1470736.84 | 7263.16 | 100.4938 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the execution period of the project. | difference between planned and actually performed work
4484 | 389922 | Works to adapt and equip the Palacete do Ex-Grémio for installation of the Municipal Archive | 45262700-8 | Building alteration work | FALSE | 2011 | 2016 | Portugal | Fafe | Braga | 3 | 30 | 11-04-2012 | 03-11-2016 | 1667 | 300 | 1931648.74 | 1159365.89 | 3 | 1125828.98 | 33536.91 | 102.9789 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were two deadline extensions | there was less and more work
4485 | 368784 | Regularization and Canalization of Ribeira do Vasco Gil - Santo António | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2016 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 47 | 05-09-2012 | 21-03-2016 | 1293 | 540 | 5300000 | 3180000.01 | 3 | 3216087.82 | -36087.81 | 98.8779 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | difference between forecast and executed quantity plus price revision
4486 | 199525 | Architectural work, structures, installations and electrical equipment, telecommunications, fire safety, air conditioning, installations and equipment for hydraulic networks | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2016 | Portugal | Portalegre | Portalegre | 12 | 60 | 06-08-2012 | 06-12-2016 | 1583 | 300 | 1650000 | 1299385.05 | 3 | 1299385.41 | -0.36 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | one of the companies in the consortium filed a recovery plan with the court; | there were no changes, only roundings to the initial contract value
4487 | 340376 | Intervention in the Terminal Sections of Ribeiras de Santa Luzia and João Gomes | 45240000-1 | Construction work for water projects | FALSE | 2011 | 2016 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 49 | 21-06-2012 | 18-03-2016 | 1366 | 720 | 45000000 | 37500000 | 3 | 37490302.96 | 9697.04 | 100.0259 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the deadline | underwork
4488 | 374880 | Construction of the Luso School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2016 | Portugal | Mealhada | Aveiro | 1 | 30 | 03-05-2012 | 02-06-2016 | 1491 | 363 | 1900000 | 1348097.04 | 3 | 1351440.66 | -3343.62 | 99.7526 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions associated with the need to partially suspend the execution of the contract, due to the need to study changes to be introduced to the project, the execution of additional works and work to correct errors and omissions, and delay in the execution of the projects, of full responsibility of the contractor. | execution of more work, execution of work to supply errors and omissions, underwork and application of contractual sanction, for non-compliance with the deadline for execution of the contract.
4489 | 725563 | The contract consists of executing the extension of the Belinho Interceptor, which will connect to the Marinhas WWTP, including a Pumping Station that will allow for the existing difference in E.N. 13. | 45232440-8, 45232423-3 | Construction work for sewage pipes, Sewage pumping stations construction work | FALSE | 2010 | 2016 | Portugal | Esposende | Braga | 3 | 49 | 08-11-2011 | 12-09-2016 | 1770 | 180 | 1500000 | 1211098.73 | 3 | 1056623.77 | 154474.96 | 114.6197 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension | errors and omissions work
4490 | 131365 | Interceptor of Neiva Piping Ø 200 PP-C over a length of 9 464 meters and Ø250 PP-C over a length of 2 723 meters. | 45232410-9 | Sewerage work | FALSE | 2010 | 2016 | Portugal | Vila Verde | Porto | 13 | 48 | 28-03-2011 | 02-02-2016 | 1772 | 365 | 3200000 | 2297357.11 | 3 | 2792039.42 | -494682.31 | 82.2824 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the partial consignments mentioned above | the change in the value of the project was due to the approval and execution of errors and omissions and additional works.
4491 | 391585 | Requalification of the avenue, creation of parking spaces, good pedestrian accessibility, a cycle path and a space to be landscaped. | 45233160-8 | Paths and other metalled surfaces | FALSE | 2011 | 2016 | Portugal | Mangualde | Viseu | 20 | 25 | 02-02-2012 | 23-12-2016 | 1786 | 365 | 2200000 | 1474584.67 | 3 | 1301231.5 | 173353.17 | 113.3222 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4492 | 304472 | Contract for Reinforcement and Rehabilitation of the Foundations of the Valença International Bridge | 45221119-9 | Bridge renewal construction work | FALSE | 2011 | 2016 | Portugal | Valença | Viana do Castelo | 18 | 39 | 09-12-2011 | 16-06-2016 | 1651 | 365 | 6200000 | 3540000.01 | 3 | 3757282.73 | -217282.72 | 94.217 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A
4493 | 262923 | Conservation and Restoration of the Church of S. Pedro Gonçalves Telmo (Nossa Senhora das Ondas) | 45454100-5, 45453100-8 | Restoration work, Refurbishment work | FALSE | 2011 | 2016 | Portugal | Tavira | Faro | 8 | 90 | 26-10-2011 | 31-05-2016 | 1679 | 720 | 521508.25 | 354638.6 | 2 | 327121.53 | 27517.07 | 108.4119 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | complexity of intervention and restoration of artistic assets. | works not performed.
4494 | 112823 | Construction of the Horta do Carmo School Center (elementary school+JI)- Tavira | 45214200-2 | Construction work for school buildings | FALSE | 2009 | 2016 | Portugal | Tavira | Faro | 8 | 60 | 29-12-2010 | 16-06-2016 | 1996 | 540 | 3535205 | 2474000 | 3 | 2589261.73 | -115261.73 | 95.5485 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extensions. | design and pricing errors and omissions
4495 | 268363 | Construction of the Fiães Sports Pavilion - Phase 2 | 45212225-9 | Sports hall construction work | FALSE | 2011 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 42 | 29-11-2011 | 25-01-2016 | 1518 | 270 | 1633455 | 1523725 | 3 | 1523725 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | readjustment of existing specialty projects (261 days); causes attributable to the contractor (138 days); extension of the period between the 1st provisional reception of the project (18/03/2014) and the final one (22/01/2016) for correction of deficiencies and delivery of documents. | there was no change in the value of the contract.
4496 | 240514 | ETAR Sul/West de Mangualde - Installation of a wastewater treatment plant for 3,000 inhabitants. | 45232421-9 | Sewage treatment works | FALSE | 2010 | 2016 | Portugal | Mangualde | Viseu | 20 | 30 | 16-11-2011 | 08-04-2016 | 1605 | 548 | 444910 | 336120.17 | 2 | 329008.46 | 7111.71 | 102.1616 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | process | process
4497 | 261505 | Environmental Recovery of the Abandoned Quarries of Lourosa | 45453100-8 | Refurbishment work | FALSE | 2011 | 2016 | Portugal | Santa Maria da Feira | Aveiro | 1 | 72 | 28-10-2011 | 22-02-2016 | 1578 | 360 | 2349164.5 | 1554780.51 | 3 | 1453333.25 | 101447.26 | 106.9803 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution time due to more work (60 days); delay in execution attributable to the contractor (959 days); period elapsed between the 1st and the last inspection for the purposes of provisional acceptance, to correct deficiencies (156 days). | more work, underwork and price revision.
4498 | 298525 | Social Housing - Development of 24 apartments in Brangada - Vila Pouca de Aguiar | 45211340-4 | Multi-dwelling buildings construction work | FALSE | 2011 | 2016 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 36 | 02-11-2011 | 26-02-2016 | 1577 | 600 | 1625301.95 | 1398928.99 | 3 | 1398928.99 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions, delays by the entity responsible for the financing program - irhu and delay in the delivery of materials by suppliers.
4499 | 280850 | Construction of the stone pavilion - parish of Mafamude | 45212225-9 | Sports hall construction work | FALSE | 2011 | 2016 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 20-09-2011 | 16-02-2016 | 1610 | 365 | 1250000 | 1242485.32 | 3 | 1243925.41 | -1440.09 | 99.8842 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | in this contract, the contractual position was assigned, as well as several extensions of the term. | additional to the contract for the correction of errors and omissions, and there were works under the responsibility of the client of the project and others of the contractor.
4500 | 265383 | Refurbishment of EN 3-5 - Structuring Axis of Estrada da Estação | 45233140-2 | Roadworks | FALSE | 2011 | 2016 | Portugal | Santarém | Santarém | 16 | 30 | 05-09-2011 | 22-06-2016 | 1752 | 270 | 1484800 | 1199888.43 | 3 | 1178540.09 | 21348.34 | 101.8114 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution of works by other entities, in the same assigned space. | underwork
4501 | 349485 | Public competition for the execution of the “contract for external arrangements, accessory and preparatory work for High school d. Pedro V in Lisbon” | 45112700-2 | Landscaping work | FALSE | N/A | 2016 | Portugal | Lisboa | Lisboa | 11 | N/A | 08-07-2009 | 02-06-2016 | 2521 | 120 | N/A | 648000 | 2 | 764688.55 | -116688.55 | 84.7404 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | changes to the contract value result from errors & omissions and over and underwork
4502 | 291924 | Ponte de Sor Day/Night Center - Home for the Elderly, Avenida do Colégio, Ponte de Sor | 45215212-6 | Retirement home construction work | FALSE | 2010 | 2016 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 30-03-2011 | 29-06-2016 | 1918 | 450 | 2329853.1 | 1903670 | 3 | 1903670 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work extended until june 17, 2013. from that period until june 21, 2016, corrective interventions took place in the project.
4503 | 98904 | Stabilization of the Escarpment Overlooking the Marginal da Calheta - 1st Phase | 45243110-6 | Cliff-stabilisation works | FALSE | 2009 | 2016 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 42 | 16-03-2011 | 25-05-2016 | 1897 | 720 | 7200000 | 4745000 | 3 | 5005556.77 | -260556.77 | 94.7946 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | problems of the judicial forum in the acquisition of a plot of land | difference between the project planned and the project actually carried out and also due to the ordinary revision of prices
4504 | 120417 | A)Construction of a dam with profile type in zoned embankment; maximum height above the foundation 32.50 m; crest length 150 m; labyrinth-type flood spillway, followed by a channel | 45247210-5 | Dam construction work | FALSE | N/A | 2016 | Portugal | Estremoz | Évora | 7 | N/A | 10-11-2009 | 18-04-2016 | 2351 | 810 | N/A | 6573385.22 | 3 | 6553337.36 | 20047.86 | 100.3059 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project execution period resulted from the declaration of insolvency of one of the companies in the consortium and due to the situation provided for in paragraph 2 of article 98 of the "public procurement code". | given the efficient management of the contract and since the project planned for this type of work is mostly estimated quantities, it was found that in reality they were greater than those actually needed.
4505 | 176370 | Construction of the Freixianda School Center | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2016 | Portugal | Ourém | Santarém | 16 | 20 | 24-01-2011 | 21-04-2016 | 1914 | 540 | 1853348.35 | 1460321.18 | 3 | 1340558.13 | 119763.05 | 108.9338 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need to change a medium voltage line. indefinition of the exterior arrangement project | underwork and price revision
4506 | 188469 | P104/2010/CPA - Construction of the Olival School Center | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2016 | Portugal | Ourém | Santarém | 16 | 20 | 29-12-2010 | 21-04-2016 | 1940 | 540 | 1737478.8 | 1266498.64 | 3 | 1203559.32 | 62939.32 | 105.2294 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | project doubts and adverse weather conditions | revision of prices and work to be done
4507 | 221441 | Execution of the Water and Sanitation Networks in the parishes of Batocas and Badamalos. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2010 | 2016 | Portugal | Sabugal | Guarda | 9 | 5 | 17-01-2011 | 20-04-2016 | 1920 | 365 | 672898.68 | 481746.47 | 2 | 514958.05 | -33211.58 | 93.5506 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the contractual term. | there were two positive price revisions worth €33,231.92 and one negative price revision worth €20.34.
4508 | 144092 | The purpose of the contract is the requalification of a set of buildings in a cultural complex | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2010 | 2016 | Portugal | Tomar | Santarém | 16 | 54 | 22-12-2010 | 28-03-2016 | 1923 | 365 | 5955162.57 | 5359646.32 | 3 | 5337971.91 | 21674.41 | 100.406 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need to change the project, due to archaeological finds. | need to change the project, due to archaeological finds.
4509 | 660030 | The contract consists of the construction of a library with 1808 m2 of construction area, based on the demolition of an existing building with preservation of the façade, and includes sitework | 45212330-8 | Library construction work | FALSE | 2010 | 2016 | Portugal | Vagos | Aveiro | 1 | 90 | 30-11-2010 | 15-04-2016 | 1963 | 730 | 1670338.7 | 1100131.71 | 3 | 1124135.94 | -24004.23 | 97.8647 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | special revitalization plan presented by the company, registered at the municipality of vagos on 15/11/2013, under number 6728. | existence of underwork (work not performed), in a total of €7,190.66 and price revision calculation, in a total of €31,194.89
4510 | 136610 | Revitalization of the Central Zone of Knights | 45233222-1 | Paving and asphalting works | FALSE | N/A | 2016 | Portugal | Mealhada | Aveiro | 1 | N/A | 10-07-2009 | 14-01-2016 | 2379 | 100 | N/A | 247702.85 | 1 | 252381.22 | -4678.37 | 98.1463 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report. | pricing review.
4511 | 6855032 | Wastewater Drainage Network and Water Supply to Lugar de Feira Franca and to the Centro Escolar de Nespereira. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2012 | 2015 | Portugal | Cinfães | Viseu | 20 | 30 | 18-09-2012 | 16-03-2015 | 909 | 180 | 344236.66 | 184036.98 | 1 | 189769.47 | -5732.49 | 96.9792 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | existence of works more | more work and underwork
4512 | 5920676 | Bestança Valley Safeguard Plan - Construction of the Environmental Interpretation Center, Resorts and Exterior Arrangements | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Cinfães | Viseu | 20 | 20 | 08-09-2014 | 29-06-2015 | 294 | 180 | 228512.33 | 206884.81 | 1 | 198845.83 | 8038.98 | 104.0428 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions | underwork
4513 | 5908387 | Requalification of the streets "Capitão Salgueiro Maia and Conselheiro Martins de Carvalho" | 45211360-0 | Urban development construction work | FALSE | 2013 | 2015 | Portugal | Cinfães | Viseu | 20 | 30 | 11-09-2014 | 26-11-2015 | 441 | 180 | 262278.51 | 175511.49 | 1 | 162137.79 | 13373.7 | 108.2484 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | existence of over and underwork. | existence of over and underwork.
4514 | 4858933 | Public Works Contract for the Refurbishment of the Facilities in Building 16 of the Parque da Saúde de Lisboa | 45453000-7 | Overhaul and refurbishment work | FALSE | 2014 | 2015 | Portugal | Lisboa | Lisboa | 11 | N/A | 09-12-2014 | 20-10-2015 | 315 | 120 | 1520000 | 1055212 | 3 | 1184311.82 | -129099.82 | 89.0992 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | extra work
4515 | 4558120 | 5010015061 - Contract for "North Line, Subsection 2.3 - Alfarelos / Pampilhosa - Construction of Pedestrian Overpass at km 215.179 at Bencanta Stop" | 45233261-6 | Pedestrian overpass construction work | FALSE | 2014 | 2015 | Portugal | N/A | N/A | 13 | N/A | 28-07-2014 | 12-10-2015 | 441 | 150 | 350000 | 347808.28 | 2 | 299659.83 | 48148.45 | 116.0677 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A
4516 | 4194464 | Refurbishment of the Gymnastics Pavilion of Anadia | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2015 | 2015 | Portugal | Anadia | Aveiro | 1 | 20 | 23-06-2015 | 30-12-2015 | 190 | 150 | 358853.12 | 294374.46 | 2 | 294374.46 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4517 | 3241964 | Contract for the construction and supply of equipment for the filtration station at the Cinco Reis Trindade Irrigation Block. | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2015 | Portugal | Beja | Beja | 2 | 40 | 22-04-2015 | 23-12-2015 | 245 | 221 | 410000 | 320013.99 | 2 | 320013.99 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made according to the criterion of economically most advantageous proposal, by weighting the assessment factors, indicated below, and considering as such the that presents the best classification translated by the expression: V = 0.25 Q + 0.25 G + 0.50 P on what: a) Factor Q: Technical value of the proposal and guarantee of good execution, to be evaluated by the descriptive memory and justification of the execution mode of the work; b) Factor G: Guarantee of compliance with the contractual deadline, which will be evaluated by the work program; c) Factor P: Value of the total cost of the contract. The P factor will be calculated by the expressions: For the Vp/Vb range between 0.8 and 1: P = -20 ( Vp/Vb) + 25 For the Vp/Vb interval equal to or less than 0.8: P = -1.25 ( Vp/Vb) + 10 on what: Vb is the base price of the contract, corrected for the value of errors and omissions in the project recognized and accepted by the Owner of the Work in the design phase contest; Vp is the value of the proposal to be classified. | 1 | 50 | Yes (no values) | TRUE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes in the execution period of the project.
4518 | 2965955 | 5010015053 - Electrification of the Railway Branch Access to the Port of Aveiro | 45234160-5 | Catenary's construction works | FALSE | 2014 | 2015 | Portugal | N/A | N/A | 13 | N/A | 17-10-2014 | 20-11-2015 | 399 | 270 | 2000000 | 1686827 | 3 | 1713213.63 | -26386.63 | 98.4598 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the projects took place according to the planned plan.
4519 | 2955026 | Assembly and disassembly of the shipyard, paving several streets in Mação (pedestrian areas, paving and horizontal signage), paving several streets in Queixoperra | 45233200-1 | Various surface works | FALSE | 2013 | 2015 | Portugal | Mação | Santarém | 16 | 11 | 30-04-2013 | 02-10-2015 | 885 | 60 | 249944.53 | 189996.87 | 1 | 234189.26 | -44192.39 | 81.1296 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension for about 2 years | extra work
4520 | 2719915 | Contract for the execution of installations and electrical equipment for the new installations in the port of the order of official accountants | 45310000-3 | Electrical installation work | FALSE | 2015 | 2015 | Portugal | Porto | Porto | 13 | 20 | 04-08-2015 | 04-10-2015 | 61 | 55 | 499000 | 424150.01 | 2 | 424150.01 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: According to article 20 of the Tender Program | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4521 | 2689518 | Construction contract for the Pedrógão Pipeline - Right Bank and the São Pedro Dam of the Primary Irrigation System of the Alqueva Multi-Purpose Project. | 45247000-0 | Construction work for dams, canals, irrigation channels and aqueducts | FALSE | 2010 | 2015 | Portugal | Beja | Beja | 2 | 25 | 19-05-2011 | 13-10-2015 | 1608 | 455 | 29980000 | 20986000 | 3 | 20560299.64 | 425700.36 | 102.0705 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for the contract was largely exceeded for reasons related to the financial difficulties of one of the companies in the awarded consortium. | the changes are essentially due to: - amounts of work effectively carried out lower than expected; - adaptation of the odearce siphon automation and remote management system; - alteration of the solution for crossing the en 258 by drilling, as required by estradas de portugal s.a.; - compatibility of the channel's drainage outlets with the natural terrain.
4522 | 2453732 | Contract for the remodeling of the chp's orthopedics external consultation building, for the installation of the external consultation of the joaquim urban hospital | 45453000-7 | Overhaul and refurbishment work | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 28 | 06-10-2014 | 30-01-2015 | 116 | 75 | 220000 | 168668.93 | 1 | 168668.93 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4523 | 2436060 | Contract for the Reorganization and Enhancement of 7 Lagoon Fishing Centers - Lot 3 Cais da Malhada (Municipality of ÍLHAVO) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Ílhavo | Aveiro | 1 | 45 | 05-06-2014 | 23-06-2015 | 383 | 210 | 1230000 | 303090.66 | 2 | 302659.95 | 430.71 | 100.1423 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | period necessary for the execution that elapses, among others, from adverse weather conditions that arise made you feel. | underwork
4524 | 2436042 | Contract for Reorganization and Enhancement of 7 Lagoon Fishing Centers - Lot 1 Pier of Ribeira de Esgueira (Municipality of AVEIRO) | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Aveiro | Aveiro | 1 | 45 | 05-06-2014 | 02-11-2015 | 515 | 210 | 1230000 | 389387.15 | 2 | 387345.95 | 2041.2 | 100.527 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | period necessary for the execution that elapses, among others, from adverse weather conditions that arise made you feel. | work unless the nature of the initial contract was stated
4525 | 2391411 | Recovery and enhancement of the Convent of Jesus. | 45453100-8 | Refurbishment work | FALSE | 2012 | 2015 | Portugal | Setúbal | Setúbal | 17 | 15 | 23-10-2012 | 27-04-2015 | 916 | 240 | 3405000 | 2583060.43 | 3 | 3075690.89 | -492630.46 | 83.9831 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution of the project attributable to the contractor and which gave rise to the imposition of a fine for breach of the contractual term. | overwork, errors and omissions, restoring financial balance and underwork.
4526 | 2318291 | Requalification of Avenida 31 de Janeiro and Avenida Gago Coutinho and Sacadura Cabral and Execution of the Bike Path Section from the Municipal Market to Liceu Sá da Bandeira | 45233140-2 | Roadworks | FALSE | 2011 | 2015 | Portugal | Santarém | Santarém | 16 | 30 | 06-10-2011 | 01-01-2015 | 1183 | 300 | 700520.45 | 630570.4 | 2 | 519114.27 | 111456.13 | 121.4704 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existence of design errors in the execution project; the need to make the contract works for águas de santarém and edp compatible with the contract for the municipality. | underwork
4527 | 2286854 | Improvement and Conservation of the Municipal Road Network - street of Colégio, in Campos | 45232451-8 | Drainage and surface works | FALSE | 2010 | 2015 | Portugal | Vila Nova de Cerveira | Viana do Castelo | 18 | 20 | 18-08-2010 | 16-09-2015 | 1855 | 30 | 259000 | 157941.53 | 1 | 157819.48 | 122.05 | 100.0773 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the causes for the change in the execution period of the project were justified by the need to conclude the public lighting works. | the difference in value between the initial contractual price and the effective total price is due to the fact that at the end of the project the projects were measured and the final quantities were smaller than the quantities that were initially foreseen.
4528 | 2218516 | Construction contract for the road network of the São Pedro-Baleizão Irrigation Block - 2nd phase | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2015 | Portugal | Beja | Beja | 2 | 42 | 12-06-2015 | 10-12-2015 | 181 | 150 | 2250000 | 2076667.14 | 3 | 2018930.77 | 57736.37 | 102.8597 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made according to the criterion of economically most advantageous proposal, by weighting the assessment factors, indicated below, and considering as such the that presents the best classification translated by the expression. V = 0.25 Q + 0.25 G + 0.50 P on what: a) Factor Q: Technical value of the proposal and guarantee of good execution, to be evaluated by the descriptive memory and justification of the execution mode of the work; b) Factor G: Guarantee of compliance with the contractual deadline, which will be evaluated by the work program; c) Factor P: Value of the total cost of the contract. The P factor will be calculated by the expressions: For the Vp/Vb range between 0.8 and 1: P = -20 ( Vp/Vb) + 25 For the Vp/Vb interval equal to or less than 0.8: P = -1.25 ( Vp/Vb) + 10 on what: Vb is the base price of the contract, corrected for the value of errors and omissions in the project recognized and accepted by the Owner of the Work in the design phase contest; Vp is the value of the proposal to be classified. | 1 | 50 | Yes (no values) | TRUE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | there was no need to execute the quantities foreseen in the project.
4529 | 2211224 | 5010011974 - “Construction of the Pedestrian Overpass at km 330+924, Coimbrões stop, subsection 3.3 (Ovar/Gaia), on the North Line” | 45233261-6 | Pedestrian overpass construction work | FALSE | 2013 | 2015 | Portugal | N/A | N/A | 13 | N/A | 31-03-2014 | 12-10-2015 | 560 | 120 | 250000 | 237481.49 | 1 | 215142.47 | 22339.02 | 110.3834 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A
4530 | 2054733 | Contract for Artificial Feeding and Reinforcement of the Dune Cord in the Extreme West of Cabanas Island (Tavira) | 45243400-6 | Beach-consolidation works | FALSE | 2014 | 2015 | Portugal | Tavira | Faro | 8 | 11 | 20-06-2014 | 18-05-2015 | 332 | 45 | 281000 | 277947.52 | 2 | 277947.52 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | equipment malfunction. disappearance and search for worker.
4531 | 2030151 | Public Works contract for the 2nd Phase of the recovery and adaptation of the Efficiency of the Occupational Activities Center and Residential Home of Santa Casa da Misericórdia das Velas. | 45215210-2 | Construction work for subsidised residential accommodation | FALSE | 2014 | 2015 | Portugal | Velas | Região Autónoma dos Açores | 15 | 30 | 14-08-2014 | 17-07-2015 | 337 | 210 | 450000 | 400982.94 | 2 | 400982.94 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | article 13, decree-law no. 6/2002, of 6 january.
4532 | 1914868 | 0020/DOM/DEM/13 - elementary school Santo António de Tercena - Refurbishment of the cafeteria, improvement of "Block A" and requalification of outdoor spaces | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Oeiras | Lisboa | 11 | 60 | 19-11-2013 | 03-12-2015 | 744 | 90 | 270000 | 244209.49 | 1 | 244209.49 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A
4533 | 1892927 | Qualification, Reinforcement and Maintenance of the Water Network, Baixa – Construction of Reservoirs to Supply Water to the Parish of Covas | 45247270-3 | Reservoir construction works | FALSE | 2014 | 2015 | Portugal | Vila Nova de Cerveira | Viana do Castelo | 18 | 15 | 26-12-2014 | 25-11-2015 | 334 | 240 | 300000 | 240000.01 | 1 | 220871.51 | 19128.5 | 108.6605 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | changes in the value of the project relate to the non-execution of chapters 1.4 and 2.4 of the project map regarding installations and electrical equipment. the solution presented in the project is currently not the most efficient and adequate.
4534 | 1883362 | Rehabilitation contract for the Gameiro Mini-Hydric Power Plant | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2015 | Portugal | Mora | Évora | 7 | 20 | 10-03-2015 | 16-12-2015 | 281 | 157 | 520000 | 512082 | 2 | 540212.94 | -28130.94 | 94.7926 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value of the proposal - 40% Price - 30% deadline - 30% | 1 | 30 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the delay of 43 days was due to the delay in delivery of the transformation station by the supplier | during the contract, some anomalies were detected in the existing equipment that could not be left unattended in order not to compromise the proper functioning of the central. the additional works that gave rise to the change in the value of the project were not foreseen in the terms of reference, however they were financed by their own means.
4535 | 1824973 | The object of this contract is the execution of the contract for the installation of luminous flux regulators within the scope of the program "More energy efficiency in public lighting in Cávado | 45310000-3 | Electrical installation work | FALSE | 2015 | 2015 | Portugal | Vila Verde | Braga | 3 | 24 | 17-11-2015 | 28-12-2015 | 41 | 60 | 312584.32 | 310948.39 | 2 | 310948.39 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4536 | 1791222 | Enlargement of plot r of the cemetery of vila franca de xira | 45215400-1 | Cemetery works | FALSE | 2013 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 18-09-2013 | 12-10-2015 | 754 | 135 | 237000 | 207708.47 | 1 | 204362.62 | 3345.85 | 101.6372 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work approved in rc of 10/30/2013 | approval of underwork in rc of 10/08/2014
4537 | 1789664 | Execution contract for the Stream Supply Subsystem | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | N/A | 30-09-2013 | 10-08-2015 | 679 | 150 | 1900000 | 1351177.27 | 3 | 1327216 | 23961.27 | 101.8054 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
4538 | 1789244 | Execution contract for the Water Supply Subsystems of Arriça, Malhada Alta, Volta do Vale, Feixe and Semideiro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Coruche | Santarém | 16 | 48 | 08-08-2013 | 05-02-2015 | 546 | 150 | 715000 | 499544.22 | 2 | 499544.22 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements.
4539 | 1789201 | Execution contract for the Torres Novas Sanitation Subsystem | 45232423-3, 45232421-9, 45232410-9 | Sewage pumping stations construction work, Sewage treatment works, Sewerage work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | N/A | 30-09-2013 | 21-12-2015 | 812 | 240 | 3500000 | 3238816.03 | 3 | 3229000.35 | 9815.68 | 100.304 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the term of the project and the provisional acceptance derives from the correction of defects in the project and the delivery of elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
4540 | 1788991 | Execution contract for the Benavente/Samora Correia/Vale Tripeiro Supply Subsystems – Lower Strand - 2nd phase | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Benavente | Santarém | 16 | N/A | 25-11-2013 | 29-05-2015 | 550 | 180 | 1000000 | 600000.01 | 2 | 480766.01 | 119234 | 124.8008 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
4541 | 1788388 | 2014.186.01.C1 - Centro Regional Delegation - Refurbishment of electrical and telecommunications installations | 45310000-3 | Electrical installation work | FALSE | 2015 | 2015 | Portugal | Coimbra | Coimbra | 6 | 20 | 07-08-2015 | 22-12-2015 | 137 | 90 | 250000 | 192681.73 | 1 | 192681.73 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%; Proposed technical value: 30%; deadline: 20% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completed works
4542 | 1782635 | Viseu Estrela school center | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Viseu | Viseu | 20 | 20 | 09-01-2014 | 08-10-2015 | 637 | 274 | 2150000 | 1969945.96 | 3 | 1948404.23 | 21541.73 | 101.1056 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractor delays and overwork | extra work
4543 | 1765249 | Execution contract for the Treatment and Equipment of the new abstractions from Parreira, Riachos, Almeirim and Benfica do Ribatejo | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2015 | Portugal | Almeirim | Santarém | 16 | 15 | 16-04-2015 | 12-10-2015 | 179 | 60 | 325000 | 274145.73 | 2 | 272457.13 | 1688.6 | 100.6198 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
4544 | 1764500 | Eop 40.341.14/15 pm 010 abrantes - branch | 45453100-8 | Refurbishment work | FALSE | 2015 | 2015 | Portugal | Abrantes | Santarém | 16 | 24 | 15-10-2015 | 31-12-2015 | 77 | 60 | 230000 | 188217.35 | 1 | 188217.35 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Price Factor: 60% 2) Technical Quality Factor of the Proposal: 40% 2.1. Subfactor Descriptive Memory and Justification of the Mode of Execution of the Contract: 40%; 2.2. Work Plan subfactor: 30%; 2.3 Technical Means and Equipment Plan subfactor to be allocated to the work: 15% 2.4. Subfactor Labor and Human Resources Plan to be allocated to the work: 15% | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out without incident, the deadline being met and there are no deficiencies in the execution to report.
4545 | 1755428 | Cp 17/2013 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 02-12-2013 | 16-06-2015 | 561 | 365 | 258914.6 | 193296.1 | 1 | 192364.58 | 931.52 | 100.4842 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | execution difficulties related to weather conditions | underwork. it was not necessary to carry out all the planned works
4546 | 1735424 | Construction of the Porto Santo Fire Station | 45216121-8 | Fire station construction work | FALSE | 2013 | 2015 | Portugal | Porto Santo | Região Autónoma da Madeira | 14 | 48 | 30-05-2014 | 26-10-2015 | 514 | 270 | 2300000 | 2074999.98 | 3 | 2074999.98 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | serious damage occurred at the only aggregate and concrete production center on porto santo island and a fire at the wooden beam supplier's factory.
4547 | 1682089 | Refurbishment and replacement work on electrical components in the public lighting network | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2015 | 2015 | Portugal | Amarante | Porto | 13 | 30 | 18-09-2015 | 30-12-2015 | 103 | 90 | 411920 | 314753.49 | 2 | 314753.49 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the contractual period. its provisional reception took place 2 days after the completion of the projects
4548 | 1634350 | Refurbishment of the auction and ice factory buildings - Porto Pesca de Aveiro | 45453100-8 | Refurbishment work | FALSE | 2015 | 2015 | Portugal | Ílhavo | Aveiro | 1 | N/A | 25-09-2015 | 30-12-2015 | 96 | 47 | 260000 | 235000 | 1 | 262751.52 | -27751.52 | 89.4381 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% deadline 5% Descriptive Memory and Justification 20% Work Plan 15% Manpower/Equipment Plan 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4549 | 1627269 | The contract aims to carry out all the finishing work on Building B in Faria Sampaio, and provide it with all the technical facilities necessary for the installation of the Citizen's Store (Ermesinde) | 45400000-1 | Building completion work | FALSE | 2015 | 2015 | Portugal | Valongo | Porto | 13 | 12 | 29-09-2015 | 28-12-2015 | 90 | 60 | 740000 | 712614.59 | 2 | 710881.19 | 1733.4 | 100.2438 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were not | changes to the value of the project resulted from the existence of suppression of works
4550 | 1622127 | Remodeling of the water supply network in several areas of the Municipality of Coimbra - 5th phase - Part B | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Coimbra | Coimbra | 6 | 27 | 11-10-2012 | 21-09-2015 | 1075 | 420 | 1350000 | 801826.3 | 2 | 758294.76 | 43531.54 | 105.7407 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no conditions to continue the project | there were works unless they were not performed
4551 | 1562299 | José de Figueiredo Laboratory, Lisbon - Reinstallation of restoration services in the paper and furniture, archive and library areas | 45453100-8 | Refurbishment work | FALSE | 2015 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 13-08-2015 | 10-12-2015 | 119 | 120 | 230000 | 169467.21 | 1 | 169467.21 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: PR - Price - 50% QTP - Technical Quality of the Proposal - 50% MD - Descriptive memory - 60% Evaluation of the "Methodologies proposed for the execution of the work": detailed description of the proposed solutions, description of the proposed intervention covering all activities, the number of work fronts, methods and techniques to be used, as well as other aspects that guarantee the preservation of the building and the fulfillment of the deadlines of the contract. OT- Organization of work - 40% Work plan consistent with the execution phases of the work, with the manpower and equipment plan, characterization of the interdependencies and linkages of the different phases of the work, suitability of the human resources and equipment to be allocated to the endeavor. The assessment will also focus on the safety and waste plan suitable for the work. | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 3 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule
4552 | 1560562 | Contract for "remodeling/expansion of domestic and storm sewer networks in the Municipality of Amadora - years 2013/2014" | 45232410-9 | Sewerage work | FALSE | 2013 | 2015 | Portugal | Amadora | Lisboa | 11 | 20 | 19-05-2014 | 29-06-2015 | 406 | 365 | 350000 | 210000.01 | 1 | 210000 | 0.01 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the existing difference is due to the fact that the 365 days coincide with the weekend. | vat settlements
4553 | 1559596 | Rehabilitation of the old Lota de Sagres Building, in street ofs Naus, Sagres | 45454000-4 | Restructuring work | FALSE | 2015 | 2015 | Portugal | Vila do Bispo | Faro | 8 | 21 | 31-08-2015 | 30-11-2015 | 91 | 120 | 350000 | 321539.84 | 2 | 321539.86 | -0.02 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price and technical quality of the proposals | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4554 | 1556900 | Public tender for the award of the contract for "replacement of existing lighting fixtures with new ones using LED technology under the POVT program - Illuminate Alto Minho" | 45113000-2 | Siteworks | FALSE | 2015 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 10-09-2015 | 10-12-2015 | 91 | 730 | 576565 | 458797.3 | 2 | 458797.3 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price - 40%. Technical Value of the Proposal - 60%. The subfactors are those contained in article 18 of the tender program | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 22 | N/A | N/A | FALSE | FALSE | FALSE | N/A | a period of 730 days for the execution of the project was indicated, when it was 90 days.
4555 | 1544877 | Contract for the Structural Rehabilitation of the Setúbal Higher Technology School of the Setúbal Polytechnic Institute | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2015 | 2015 | Portugal | Setúbal | Setúbal | 17 | 20 | 31-08-2015 | 13-11-2015 | 74 | 60 | 288000 | 207564.4 | 1 | 207564.4 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Price (weighting 60%) Technical Value (weighting 40%) Technical Valuable Subfactors Descriptive Memory weighting 0.40 Work Plan weighting 0.30 Work Warranty deadline weighting 0.30 | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4556 | 1540854 | Infrastructures to support the practice of sports and adventure on the river paiva – lodeiro – freg. cabril | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2010 | 2015 | Portugal | Castro Daire | Viseu | 20 | 20 | 04-07-2011 | 23-01-2015 | 1299 | 300 | 290538.01 | 294800 | 2 | 297293.76 | -2493.76 | 99.1612 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | approval of the application to mais centro and issuance of opinions | unforeseen works
4557 | 1531362 | Design, construction, supply and assembly of two waste-derived fuel (cdr) preparation plants in the aveiro and coimbra tmbs | 45222100-0 | Waste-treatment plant construction work | FALSE | 2010 | 2015 | Portugal | Coimbra | Aveiro | 1 | 45 | 02-12-2011 | 21-04-2015 | 1236 | 240 | 7300000 | 7580000 | 3 | 7580000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the manufacture of equipment, motivated by the economic and financial crisis in europe
4558 | 1529956 | Public works contract for the CONSTRUCTION OF THE PATH OF JOÃO NATEIRO | 45233120-6 | Road construction works | FALSE | 2015 | 2015 | Portugal | Vila Franca do Campo | Região Autónoma dos Açores | 15 | 21 | 07-07-2015 | 30-11-2015 | 146 | 210 | 200000 | 170000.01 | 1 | 168680.01 | 1320 | 100.7825 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work finished ahead of schedule | underwork
4559 | 1529167 | Square Dr. Bush ax - car park | 45223300-9 | Parking lot construction work | FALSE | 2010 | 2015 | Portugal | Felgueiras | Porto | 13 | 36 | 17-05-2011 | 20-08-2015 | 1556 | 540 | 3505500 | 2315109.31 | 3 | 2301964.54 | 13144.77 | 100.571 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some adverse situations during the execution of the project | smaller quantities executed
4560 | 1525727 | Execution of all the works that make up the Contract for the Medium Voltage Electrical Supply Branches to the Channel Siphon Installations do Sado | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2015 | 2015 | Portugal | Alcácer do Sal | Beja | 2 | 21 | 28-07-2015 | 29-12-2015 | 154 | 90 | 334000 | 279693.44 | 2 | 279693.44 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Factors and possible subfactors accompanied of the respective weighting coefficients: Factors and possible subfactors accompanied by the respective weighting coefficients: V = 0.25 Q + 0.25 G + 0.50 P On what: a) V: Value of the score to be attributed to the competitor b) Factor Q: Technical value of the proposal c) Factor G: Guarantee of compliance with the contractual deadline d) Factor P: Value of the total cost of the contract; The P factor will be calculated by the expressions: If Vp > abnormally low price threshold, we have: P = -13.33 (Vp/Vb) + 20 If Vp <= abnormally low price threshold, we have: P=10.00 | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contract was delayed on the one hand due to the delay in obtaining the license to establish one of the lines issued by the dgeg and on the other hand the start of work on the contract was delayed due to difficulties in supplying the poles, given that some of them are large, which is not frequent, and there is no stock.
4561 | 1523999 | Execution of the Contract for the Construction of an ATL on Avenida D. João III (Adaptation of the Existing Space) - Ponta Delgada | 45262700-8 | Building alteration work | FALSE | 2015 | 2015 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 24 | 19-06-2015 | 28-12-2015 | 192 | 90 | 335000 | 284750.01 | 2 | 279969.42 | 4780.59 | 101.7075 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: A - Densification of the "Price" factor (K1) (40%) and respective partial score: The evaluation of the price factor results in a score between a minimum value of 0 (zero) and a maximum of 20 (twenty), of according to the following formula: K1 = (Pb-Pp)/Pb x 20 On what: Pp = value of the proposal under analysis; Pb = base price of the procedure; The score obtained by applying the formula above is rounded up or down to the nearest hundredth. B - Densification of the factor "technical quality of the proposal" (K2) (60%) and respective partial score: This factor is subdivided into two sub-factors, with the following weighting: K2.1 - Work plan - 70% K2.2 - Descriptive memory and justification of how the work was carried out - 30% The score of this factor (K2) results from the following formula: K2 = (0.70xK2.1) + (0.30xK2.2) On what: K2.1 = score assigned to the "Work plan" subfactor, resulting from the sum of all partial values ​​assigned in each one of the sets of attributes of the respective descriptor. K2.2 = score assigned to the subfactor "Descriptive memory and justification of the way the work was carried out" resulting from the sum of all partial values ​​assigned in each of the sets of attributes of the respective descriptor. The score obtained by applying the formula above is rounded up or down to the nearest hundredth. The final score of each proposal is obtained using the following formula: (PF) Final Score = (K1 x 0.4) + (K2 x 0.6) On what: K1 = Score obtained in the bid price factor; K2 = Score obtained in the technical quality factor of the proposal. The application of the aforementioned formula results in a global score between 0 (zero) and 20 (twenty), the proposal being considered economically more advantageous is the one whose score is closest to the maximum value of 20 (twenty). The score obtained by applying the formula above is rounded up or down to the nearest hundredth. In case there is a tie in the overall score of the proposals, the best score obtained in the "technical quality of the proposal" factor and, if the tie persists, the best score obtained in the "price" factor and, if still if the tie persists, the order of receipt of proposals. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4562 | 1513838 | Rehabilitation works of the Torrinha elementary school (EM.004.2015.069) | 45454100-5 | Restoration work | FALSE | 2015 | 2015 | Portugal | Porto | Porto | 13 | 20 | 29-07-2015 | 27-11-2015 | 121 | 50 | 200000 | 155985.61 | 1 | 156473.61 | -488 | 99.6881 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 20 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was carried out in accordance with the contractual provisions.
4563 | 1505253 | Replacement and improvement of street pavements in the villages of Vale de Mouro, Vale de Borregão and Galhardo, intervened by the wastewater drainage network | 45233140-2 | Roadworks | FALSE | 2015 | 2015 | Portugal | Mortágua | Viseu | 20 | 20 | 19-06-2015 | 20-10-2015 | 123 | 90 | 242682.05 | 199058.03 | 1 | 199058.03 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) price (60%) b) technical quality of the proposal (40%) The intervening subfactors are described in point 18 of the tender program | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4564 | 1503297 | Contract for the Rehabilitation and Renewal of the Roofing of an Industrial Building with Fiber Cement Boards with Asbestos Particles (Campolide) | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Lisboa | Lisboa | 11 | N/A | 29-06-2015 | 15-11-2015 | 139 | 90 | 400000 | 325000 | 2 | 325000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4565 | 1503088 | Contract for Construction of Equipment Warehouses for Vianapesca-OP | 45213220-1 | Construction work for warehouses | FALSE | 2014 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 18-05-2015 | 09-12-2015 | 205 | 270 | 2750000 | 2200000.01 | 3 | 2196552.28 | 3447.73 | 100.157 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical value (70% weighting) Price (30% weighting) | 1 | 30 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | amendment to the deadline for execution of the project in order to comply with the closing deadlines of the application. | consequence of changing the execution period
4566 | 1502705 | Multipurpose Construction Works and General Improvement of EB Augusto Lessa (EM.004.2015.012) | 45262700-8 | Building alteration work | FALSE | 2015 | 2015 | Portugal | Porto | Porto | 13 | 22 | 01-07-2015 | 17-11-2015 | 139 | 60 | 312000 | 248792.7 | 1 | 254371.45 | -5578.75 | 97.8068 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 22 | N/A | N/A | FALSE | FALSE | FALSE | N/A | extra work | additional work worth €5,520.00, errors and omissions worth €3,262.28 and unfinished work worth €3,202.97
4567 | 1502219 | 2013.102.01.C1 - SE Amadora - Replacement of air conditioning system, lighting and telecommunications infrastructure | 45300000-0 | Building installation work | FALSE | 2014 | 2015 | Portugal | Amadora | Lisboa | 11 | 33 | 09-04-2015 | 09-09-2015 | 153 | 90 | 330000 | 295700.3 | 2 | 267783.06 | 27917.24 | 110.4253 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | additional | underwork
4568 | 1500874 | Requalification of EM 521-1 (between EN 258 and Selmes) and EM 521 (between Selmes and IP2) | 45233142-6 | Road-repair works | FALSE | 2015 | 2015 | Portugal | Vidigueira | Beja | 2 | 20 | 13-07-2015 | 30-09-2015 | 79 | 75 | 581000 | 282734.75 | 2 | 282734.75 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global Bid Price (Pg) at 30% b) Technical value of the proposal (Vt) at 70% | 1 | 30 | Yes (no values) | FALSE | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4569 | 1500860 | Requalification of Municipal Road 519 in the section between Vidigueira/Alcaria da Serra | 45233142-6 | Road-repair works | FALSE | 2015 | 2015 | Portugal | Vidigueira | Beja | 2 | 20 | 13-07-2015 | 30-09-2015 | 79 | 75 | 568565.9 | 282024.32 | 2 | 282024.32 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Global Bid Price (Pg) at 30% b) Technical value of the proposal (Vt) at 70% | 1 | 30 | Yes (no values) | FALSE | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4570 | 1498973 | Construction contract for the road network of the Baleizão-Quintos Irrigation Block - 2nd phase | 45233123-7 | Secondary road construction work | FALSE | 2014 | 2015 | Portugal | Beja | Beja | 2 | 42 | 25-06-2015 | 10-12-2015 | 168 | 152 | 575000 | 409945.85 | 2 | 384770.77 | 25175.08 | 106.5429 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: The award will be made according to the criterion of economically most advantageous proposal, by weighting the assessment factors, indicated below, and considering as such the that presents the best classification translated by the expression. V = 0.25 Q + 0.25 G + 0.50 P on what: a) Factor Q: Technical value of the proposal and guarantee of good execution, to be evaluated by the descriptive memory and justification of the execution mode of the work; b) Factor G: Guarantee of compliance with the contractual deadline, which will be evaluated by the work program; c) Factor P: Value of the total cost of the contract. The P factor will be calculated by the expressions: For the Vp/Vb range between 0.8 and 1: P = -20 ( Vp/Vb) + 25 For the Vp/Vb interval equal to or less than 0.8: P = -1.25 ( Vp/Vb) + 10 on what: Vb is the base price of the contract, corrected for the value of errors and omissions in the project recognized and accepted by the Owner of the Work in the design phase contest; Vp is the value of the proposal to be classified. | 1 | 50 | Yes (no values) | TRUE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame. | there was no need to execute the quantities foreseen in the project.
4571 | 1489540 | Implementation of the 1st cycle elementary school in Sobral | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 18-11-2013 | 10-04-2015 | 508 | 270 | 1900000 | 1499155.05 | 3 | 1476217.76 | 22937.29 | 101.5538 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | deadline deviation, date of completion of work. | approval of work unless in board meeting - 11/19/2014 and 02/11/2015
4572 | 1488479 | Construction of a support pavilion for unloading, transferring and packaging fish from Siege, including demolition of the existing shed. | 45210000-2 | Building construction work | FALSE | 2015 | 2015 | Portugal | Matosinhos | Porto | 13 | N/A | 16-06-2015 | 16-12-2015 | 183 | 90 | 424824 | 329487.07 | 2 | 329487.07 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% Descriptive Memory 20% Work Plan 15% Equipment Plan 10% deadline 5% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies
4573 | 1488358 | Coverage, Quay and External Infrastructure Contract - Portimão Fishing Port | 45453100-8 | Refurbishment work | FALSE | 2015 | 2015 | Portugal | Portimão | Faro | 8 | N/A | 15-06-2015 | 22-12-2015 | 190 | 60 | 300000 | 276037.69 | 2 | 277693.93 | -1656.24 | 99.4036 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% deadline 5% Descriptive Memory 20% Work Plan 15% Labor Plan 10% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4574 | 1488226 | Requalification of the Auction Building in the Fishing Port of Portimão | 45453000-7 | Overhaul and refurbishment work | FALSE | 2015 | 2015 | Portugal | Portimão | Faro | 8 | N/A | 15-06-2015 | 30-10-2015 | 137 | 140 | 350000 | 308215.36 | 2 | 343356.56 | -35141.2 | 89.7654 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% Technical Quality 50% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4575 | 1487144 | DIO.PR.15.030 - Contract for the Emergency Repair of the Downsizing and Crane Rolling Path, Organization and Requalification of the Area of ​​Jurisdiction of the Port of Faro | 45241100-9 | Quay construction work | FALSE | 2015 | 2015 | Portugal | Faro | Faro | 8 | 21 | 22-04-2015 | 16-08-2015 | 116 | 70 | 700000 | 420000.01 | 2 | 420000.01 | 0 | 100 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Under the deadlines set out in point 14 of the program of the procedure. | 0 | 0 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | graceful extension, for reasons not attributable to the contractor.
4576 | 1485154 | Contract for the design and execution of the construction and installation works of the Data Center of the Polytechnic Institute of Tomar | 45314000-1 | Installation of telecommunications equipment | FALSE | 2015 | 2015 | Portugal | Tomar | Santarém | 16 | 20 | 11-03-2015 | 10-11-2015 | 244 | 45 | 1330000 | 997500 | 2 | 997498.72 | 1.28 | 100.0001 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Proposed price, with a weighting of 40%; Technical merit and guarantee of quality and adequacy of the proposal, with a weighting of 50%; Deadline for completion of the work, with a 10% weighting. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | work did not start on may 4th due to weather conditions | adjustments due to rounding errors in the awarded proposal.
4577 | 1477651 | Construction of animal experimentation infrastructure, for UC-Biotech - CP-CCP-EMP n.º 01/2015 | 45214600-6 | Construction work for research buildings | FALSE | 2015 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 25 | 12-06-2015 | 25-09-2015 | 105 | 76 | 750000 | 739989.89 | 2 | 792498.55 | -52508.66 | 93.3743 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | change in 25 days, due to the period of execution of the project coinciding with the month of august and several suppliers close in this period. | extra work
4578 | 1477424 | Removal of materials deposited in the basin of the Container Terminal of the Port of Sines (TCS) and subsequent regularization of the rocky bottoms in that basin. | 45241000-8 | Harbour construction works | FALSE | 2014 | 2015 | Portugal | Sines | Setúbal | 17 | 30 | 27-05-2015 | 16-10-2015 | 142 | 53 | 10000000 | 9342400 | 3 | 9564233 | -221833 | 97.6806 | lowest price | 2 | 100 | Yes (no values) | TRUE | Complete fulfillment of the contract | 4 | N/A | N/A | FALSE | FALSE | FALSE | N/A | use of equipment with greater capacity and production. | compensation paid to the contractor to support costs associated with contingencies.
4579 | 1474347 | Public Tender for the contract for the remodeling/expansion of domestic and storm sewer networks in the Municipality of Oeiras - North Zone - Years 2013 / 2014 | 45232410-9 | Sewerage work | FALSE | 2013 | 2015 | Portugal | Oeiras | Lisboa | 11 | 11 | 13-06-2014 | 17-03-2015 | 277 | 365 | 350000 | 210000.01 | 1 | 209999.96 | 0.05 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | in order to reduce the inconvenience to citizens caused by the intervention in question, and in conjunction with the contractor, it was decided to put another work front on the work, which substantially reduced the time of the contract. due to the weather conditions that were always favorable to the intervention in question, it was possible to reduce the duration of the contract. due to the weather conditions, which were always favorable to the intervention in question, it was possible to reduce the duration of the contract | vat rounding
4580 | 1473514 | Transformation/Adaptation of Municipal Building to Citizen's Store | 45262700-8 | Building alteration work | FALSE | 2015 | 2015 | Portugal | Sardoal | Santarém | 16 | 15 | 04-06-2015 | 30-12-2015 | 209 | 90 | 295746.32 | 289871 | 2 | 289871 | 0 | 100 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | unforeseen work during the contract | unforeseen work
4581 | 1471775 | Replacement of fiber-cement roofs with asbestos at Escola Básica nº 2 in Laranjeiro, EB nº 3 in Cova da Piedade and nº 2 in Monte de Caparica | 45261900-3 | Roof repair and maintenance work | FALSE | 2015 | 2015 | Portugal | Almada | Setúbal | 17 | 24 | 25-05-2015 | 03-12-2015 | 192 | 150 | 216697.86 | 159900 | 1 | 144396.96 | 15503.04 | 110.7364 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | anticipation of works | underwork.
4582 | 1464038 | Contract for the refurbishment of the new premises of the Escola Superior de Tecnologia da Saúde do Porto - Building D | 45262700-8 | Building alteration work | FALSE | 2015 | 2015 | Portugal | Porto | Porto | 13 | 20 | 26-05-2015 | 20-11-2015 | 178 | 90 | 300000 | 239130.32 | 1 | 259058.36 | -19928.04 | 92.3075 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 16 | N/A | N/A | FALSE | FALSE | FALSE | N/A | deadline extension in the context of overwork, underwork and errors and omissions | overwork and errors and omissions
4583 | 1460010 | Improvement of the pavement, rainwater network and signaling | 45233220-7 | Surface work for roads | FALSE | 2015 | 2015 | Portugal | Oleiros | Castelo Branco | 5 | 12 | 23-02-2015 | 16-07-2015 | 143 | 90 | 730000 | 528360.73 | 2 | 528360.73 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was a change in the deadline due to delays and difficulties in the earthworks / implementation of the project and the need to remove electrical infrastructure (poles).
4584 | 1459902 | Execution of the contract: "Remodeling of the public lighting network in the municipality of Valpaços". | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2014 | 2015 | Portugal | Valpaços | Vila Real | 19 | 24 | 21-05-2015 | 25-11-2015 | 188 | 180 | 269383 | 252500.19 | 2 | 252500.19 | 0 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: The bidders' proposals will be analyzed according to the following methodology: Price Factor - 75%; Technical Valuation Factor of the Proposal - 25%. The final evaluation will be the result of the comparative analysis of the various proposals, applying the following subfactors: a) Price (P) - 75%; b) Technical value of the proposal (VTP) - 25%. The final evaluation will be the result of the comparative analysis of the various proposals, by applying the following subfactors: a) Price (P) P = 0.75 x Pb / Pp, where Pb is the estimated cost of the works for tender purposes and Pp is the value of the proposal under analysis. (THE score will be the result of the formula, except for values ​​greater than 1, where the score will always be 1.) b) Technical value of the proposal (VTP): b.1) Descriptive memory and justification - 25% (MD); - Proposal of very good quality and globally well prepared - Classification 1.0; - Proposal of good quality and globally well prepared, admitting some deficiencies in detail - Classification - 0.8; - Acceptable proposal, although presenting relevant deficiencies in its preparation and/or gaps in technical information - Classification - 0.6; - Negative proposal containing insufficient technical information and/or non-compliance with the conditions or technical specifications - Classification - 0.4; - Inadequate proposal with absence of any technical information or other element required by the tender process - Rating - 0.2; b.2) Work plan - 25% (PT): -Methodologically well-structured proposal, complying with the requirements of the tender program, showing an in-depth study of the tasks and the specificity of the work, presenting a planning specifically suited to the work - Rating - 1.0; - Methodologically well-structured proposal, complying with the requirements of the tender program, with a detailed description of tasks, relating them to planning in a harmonized way - Rating - 0.8; - Methodologically well-structured proposal, complying with the requirements of the tender program, with a description of the tasks of in general, relating them correctly to the planning - Classification - 0.6; - Proposal complying with the requirements of the tender program with a summary description of the tasks, not listing them specifically with planning - Rating - 0.4; - Proposal that, although complying with the requirements of the tender program, is not minimally substantiated - Classification - 0.2; b.3) Allocated resources - 25% (RA): - Proposal with assignment to the contract of all the necessary human and material resources, carefully proposing other means complementary, adapting them to the specificity of the functions to be performed and clearly demonstrating greater value - Rating - 1.0; - Proposal with allocation to the contract of all the necessary human and material resources, adapting them in a balanced way to the functions and perform, with allocations correctly evaluated and calculated - Rating - 0.8; - Proposal with assignments to the contract of all the necessary human and material resources, demonstrating their suitability for the functions to be play - Rating - 0.6; - Proposal with assignments to the contract of all necessary human and material resources- Rating - 0.4; - Proposal that does not affect all the human and material resources necessary for the full fulfillment of the object of the contract - Rating - 0.2; b.4) Security - 25% (S): - Detailed description of the procedures to be implemented in the security area, showing in-depth knowledge and experience in implementation of these procedures - Rating - 1.0; - Detailed description of the procedures to be implemented in the security area - Rating - 0.8; - General description of the procedures to be implemented in the security area - Classification - 0.6; - It generally indicates the procedures to be implemented in the security area, not describing them or indicating how to implementation - Rating - 0.4; - Does not indicate the procedures it intends to implement in the security area - Rating - 0.2. The value of this parameter will be established according to the following formula: VTP = MD x 25% + PT x 25% + RA x 25% + S x 25% The Final Classification (CF) will be the one resulting from the application of the form: CF = (75% x P) + (25% x VTP) The proposals are sorted in descending order according to the classification obtained. | 1 | 75 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | early completion.
4585 | 1458273 | Remodeling of the water supply network in several areas of the Municipality of Coimbra - 6th Phase - (Pine Forest Systems of Morocco, Santa Clara, Alto dos Barreiros, Cerrnache and Cruz dos Morouços) | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Coimbra | Coimbra | 6 | 22 | 11-10-2012 | 08-05-2015 | 939 | 480 | 1750000 | 1061815.88 | 3 | 827528.33 | 234287.55 | 128.3117 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | postponement of the celebration of provisional acceptance | there were works unless they were not carried out
4586 | 1457251 | Requalification of the area surrounding the Castle | 45233253-7 | Surface work for footpaths | FALSE | 2010 | 2015 | Portugal | Sines | Setúbal | 17 | 10 | 26-11-2010 | 06-03-2015 | 1561 | 366 | 505087.29 | 303052.38 | 2 | 324349.29 | -21296.91 | 93.434 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the execution of works | omissions supply work and price review
4587 | 1457033 | C.p. No. 01/2012 - extensions of water supply and wastewater drainage networks in zone 1 - 2nd phase - fermentations | 45232460-4 | Sanitary works | FALSE | 2012 | 2014 | Portugal | Guimarães | Braga | 3 | 25 | 23-11-2012 | 26-11-2014 | 733 | 210 | 253000 | 179862.8 | 1 | 73751.73 | 106111.07 | 243.876 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Revocation of the Contract) | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contract revocation | contract revocation
4588 | 1451050 | Refurbishment and expansion work on the existing building of the former Primary School for the Headquarters and facilities of the PARISH SOCIAL CENTER OF SÃO PEDRO DA COMPORTA | 45215220-5 | Construction work for social facilities other than subsidised residential accommodation | FALSE | 2014 | 2015 | Portugal | Alcácer do Sal | Setúbal | 17 | 22 | 21-01-2015 | 23-12-2015 | 336 | 300 | 498000 | 498000 | 2 | 497781.68 | 218.32 | 100.0439 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price (Global Price + Justification of the Price) - 30%; Technical Valuation (Work Plans, Manpower, Equipment and Payments and Descriptive and Justification Report) - 40%; deadline - 30% | 1 | 30 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes | there were no changes
4589 | 1450549 | The irrigation network to be built is a pressure network, intended to feed an area of ​​152.5 ha with a length of 6354 m, equipped with | 45232121-6 | Irrigation piping construction work | FALSE | 2015 | 2015 | Portugal | Belmonte | Castelo Branco | 5 | 21 | 08-05-2015 | 04-12-2015 | 210 | 159 | 900000 | 720000.01 | 2 | 669875.09 | 50124.92 | 107.4827 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Factors: F1 - Technical value of the proposal (40%) F2 - Price (60%). b) F1 subfactors - Technical value of the proposal: F 1.1 - Descriptive Memory (20%) F 1.2 - Work Plan (20%). | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 18 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the execution period of the project. | during the execution of the project it was verified that it was not necessary to carry out some works, which resulted in “too little” work.
4590 | 1443287 | Refurbishment of the auction building and visor - Sesimbra Fishing Port | 45453100-8 | Refurbishment work | FALSE | 2015 | 2015 | Portugal | Sesimbra | Setúbal | 17 | N/A | 21-04-2015 | 23-12-2015 | 246 | 75 | 341000 | 331900 | 2 | 342246.27 | -10346.27 | 96.977 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% deadline 5% Descriptive Memory 20% Plato Works 15% Labor and Equipment Plan 10% | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | "additional work" | "additional work"
4591 | 1442618 | Refurbishment ofelementary school 1 E JI do Barracão. | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2015 | Portugal | Amarante | Porto | 13 | 9 | 21-01-2015 | 22-07-2015 | 182 | 180 | 399950 | 299484.54 | 2 | 299484.54 | 0 | 100 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | 1 day due to delay in inspection for provisional acceptance
4592 | 1442599 | Refurbishment ofelementary school 1 from Vila Caiz. | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2015 | Portugal | Amarante | Porto | 13 | 9 | 21-01-2015 | 22-07-2015 | 182 | 180 | 399900 | 299743.42 | 2 | 299743.42 | 0 | 100 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4593 | 1442571 | Refurbishment ofelementary school 1 Deal. | 45214200-2 | Construction work for school buildings | FALSE | 2015 | 2015 | Portugal | Amarante | Porto | 13 | 9 | 21-01-2015 | 22-07-2015 | 182 | 180 | 400000 | 299934.95 | 2 | 299934.95 | 0 | 100 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4594 | 1436204 | Construction of a cycle and pedestrian track. Execution of drainage and road paving in bituminous concrete | 45233220-7 | Surface work for roads | FALSE | 2015 | 2015 | Portugal | Sertã | Castelo Branco | 5 | 9 | 11-03-2015 | 23-12-2015 | 287 | 90 | 254300 | 226390.68 | 1 | 226390.68 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | completed on time | no change
4595 | 1436047 | The contract has as its general characteristics the execution of bituminous paving, demolitions, earthworks, execution of rainwater and electrical infrastructure | 45233223-8 | Carriageway resurfacing works | FALSE | 2015 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 09-04-2015 | 30-11-2015 | 235 | 150 | 1164412.83 | 1086624.18 | 3 | 998315.77 | 88308.41 | 108.8457 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 60%; Technical Value: 40%. | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | suppression of works and non-exhaustion of foreseen quantities.
4596 | 1435724 | Requalification of the Ex-EN 323 Vila Nova de Paiva-Alhais | 45233252-0 | Surface work for streets | FALSE | 2014 | 2015 | Portugal | Vila Nova de Paiva | Viseu | 20 | 12 | 28-10-2014 | 02-10-2015 | 339 | 240 | 785000 | 664275.1 | 2 | 641688.86 | 22586.24 | 103.5198 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | several reasons given by the contractor | underwork
4597 | 1435680 | Connecting road to Rotunda da Praia/Rotunda do Lar | 45233122-0 | Ring road construction work | FALSE | 2014 | 2015 | Portugal | Vila Nova de Paiva | Viseu | 20 | 20 | 18-02-2015 | 02-10-2015 | 226 | 150 | 347000 | 344712.75 | 2 | 330082.25 | 14630.5 | 104.4324 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 5 | N/A | N/A | FALSE | FALSE | FALSE | N/A | occasional adjustments to the project project | underwork
4598 | 1432679 | Business pavilions - industrial pavilion construction | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Cinfães | Viseu | 20 | 20 | 25-11-2014 | 18-06-2015 | 205 | 75 | 238400.3 | 198888 | 1 | 203231.38 | -4343.38 | 97.8628 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 21 | N/A | N/A | FALSE | FALSE | FALSE | N/A | term extension. | existential of Extra work and underwork.
4599 | 1432496 | Business pavilions - industrial pavilion construction | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Cinfães | Viseu | 20 | 30 | 25-11-2014 | 18-06-2015 | 205 | 75 | 238400.3 | 197488 | 1 | 200852.62 | -3364.62 | 98.3248 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | existence of more works. | existence of more work and underwork.
4600 | 1432152 | Rehabilitation of the northern elevated and supported cells of the Cacia reserve system. | 45262330-3 | Concrete repair work | FALSE | 2014 | 2015 | Portugal | Aveiro | Aveiro | 1 | N/A | 24-03-2015 | 20-11-2015 | 241 | 60 | 192000 | 159971.62 | 1 | 158922.05 | 1049.57 | 100.6604 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Technical Value of the Proposal (50%) and Price (50%) | 1 | 50 | N/A | FALSE | Complete fulfillment of the contract | 6 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works that were not necessary to perform
4601 | 1431335 | Reinforcement of the flow of thermal water to the Chaves spa | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2015 | 2015 | Portugal | Chaves | Vila Real | 19 | 15 | 13-04-2015 | 28-07-2015 | 106 | 150 | 340000 | 271999 | 2 | 271999 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | nothing to register
4602 | 1428726 | Urban Regeneration of the City of Pinhel | 45233222-1 | Paving and asphalting works | FALSE | 2013 | 2015 | Portugal | Pinhel | Guarda | 9 | N/A | 19-02-2014 | 10-04-2015 | 415 | 720 | 810556 | 486333.61 | 2 | 445128.15 | 41205.46 | 109.257 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | reduction of the execution period from 720 days to 408 days, by administrative act, under the terms of article 311 of the "public procurement code". | underwork worth €41,205.47
4603 | 1428336 | Preliminary works, demolitions, earthmoving, concrete, Roofing, Masonry, Stonework, Partition walls in phenolic, floors, coating and painting walls, coating and painting | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2013 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 11 | 07-04-2014 | 25-03-2015 | 352 | 120 | 174177.11 | 168432.33 | 1 | 172721.56 | -4289.23 | 97.5167 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | due to deadline extensions | due to the value of additional works and works to be suppressed
4604 | 1424879 | Execution contract for the Lamarosa, Zebrinho, Ameixal, Frazão, Carapuções and Excusa water supply subsystems | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2012 | 2015 | Portugal | Coruche | Santarém | 16 | 48 | 01-08-2013 | 13-07-2015 | 711 | 150 | 1400000 | 1147631.17 | 3 | 1146856.16 | 775.01 | 100.0676 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the simultaneity of works on the same land | the project was carried out in its entirety, not requiring the invoicing of all items.
4605 | 1424822 | Modernization of the tracks at the stations in question, replacing wooden sleepers with concrete and faulty rails and creating long welded bars. | 45234100-7 | Railway construction works | FALSE | 2012 | 2015 | Portugal | Vila Real Sto Antonio | Faro | 8 | N/A | 24-04-2013 | 16-02-2015 | 663 | 100 | 1226000 | 1093289.84 | 3 | 1093289.84 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to say | nothing to say
4606 | 1422985 | Execution of the Alvito ETA Water Pipeline - Monteza Junction | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Alvito | Beja | 2 | N/A | 12-02-2014 | 30-11-2015 | 656 | 240 | 1250000 | 752671.42 | 2 | 751145.4 | 1526.02 | 100.2032 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | delays arising from difficulties in agreements with landlords | underwork
4607 | 1422268 | It involves the improvement and paving of an agricultural road, including earthworks, drainage, bituminous paving, safety signs and accessory works. | 45233123-7 | Secondary road construction work | FALSE | 2015 | 2015 | Portugal | Meda | Guarda | 9 | 20 | 01-04-2015 | 05-06-2015 | 65 | 60 | 333971.11 | 299338.53 | 2 | 299338.56 | -0.03 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price: 50%; Technical Value of the Proposal: 50% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed on the last working day of the end of the project term | it results from the non-execution of small quantities foreseen because, in the course of the project, it was verified that they were not necessary.
4608 | 1421230 | Cultural Center of S. João de Loure | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2010 | 2015 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 36 | 28-06-2012 | 17-06-2015 | 1084 | 545 | 1495957.81 | 1078869.91 | 3 | 1120954.13 | -42084.22 | 96.2457 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | errors and omissions and extra work
4609 | 1420907 | Expansion of the Nursery/ Kindergarten of the Social Welfare Center of the Upper Zone | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Torres Novas | Santarém | 16 | 20 | 04-08-2014 | 20-03-2015 | 228 | 90 | 235657.35 | 183992.74 | 1 | 183992.74 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | due to meteorological issues, the project was delayed in its conclusion.
4610 | 1419631 | RUCI - Platform for the support and appreciation of entrepreneurship and innovation | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Albergaria-a-Velha | Aveiro | 1 | 28 | 23-05-2014 | 20-05-2015 | 362 | 90 | 235800 | 161729.28 | 1 | 161729.28 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions.
4611 | 1418605 | Landscape integration of Vias Paralelas, in the parish of Maia | 45112730-1 | Landscaping work for roads and motorways | FALSE | 2011 | 2015 | Portugal | Maia | Porto | 13 | 45 | 10-03-2015 | 12-08-2015 | 155 | 365 | 319379.04 | 269316.67 | 2 | 224157.7 | 45158.97 | 120.1461 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | it was the time necessary to complete the project | at the end of the project it was the necessary amount for the execution of the project
4612 | 1417384 | Contract for the Reorganization and Enhancement of Fishing Centers Lagunares I: Porto de Abrigo da Torreira, within the scope of the Intervention of the Polis Litoral Ria de Aveiro | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2015 | Portugal | Aveiro | Aveiro | 1 | 30 | 18-02-2014 | 15-10-2015 | 604 | 300 | 1004250 | 1003946.38 | 3 | 745449.38 | 258497 | 134.6767 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | verification of the existence of a bottom near the end of the breakwater head (through the last topo-hydrographic survey) and which required a reinforcement intervention (execution of a rockfill mat at the end of the breakwater). | extra work
4613 | 1417281 | Contract for the Requalification and Enhancement of Pateira de Fermentelos - Requeixo and Carregal Parks, within the scope of the Intervention of Polis Litoral Ria de Aveiro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Aveiro | Aveiro | 1 | 45 | 18-07-2014 | 04-11-2015 | 474 | 180 | 300000 | 299705.11 | 2 | 289951.5 | 9753.61 | 103.3639 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions, which created constraints that led to a rise in the water level of pateira de fermentelos and also difficulties experienced in the supply of materials and in hiring subcontractors. execution of another contract with a view to raising the threshold levels of the support buildings and revising the residual sewage system in the carregal park, works that conditioned the development of the projects in the contract.
4614 | 1417264 | Contract for "Requalification and Enhancement of Pateira de Fermentelos - Parque de Espinhel (Águeda), within the scope of the intervention of Polis Litoral Ria de Aveiro". | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Águeda | Aveiro | 1 | 30 | 20-10-2014 | 04-08-2015 | 288 | 180 | 320000 | 314121.36 | 2 | 307133.77 | 6987.59 | 102.2751 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions that created constraints that led to rising water levels from pateira de fermentelos and also difficulties felt in the supply of materials and in hiring of subcontractors. | underwork
4615 | 1416636 | Contract for the Conception/Construction of the Monte da Rocha ETA | 45252120-5 | Water-treatment plant construction work | FALSE | 2013 | 2015 | Portugal | Ourique | Beja | 2 | 47 | 03-09-2013 | 28-08-2015 | 724 | 385 | 3900000 | 3499993 | 3 | 3627994.34 | -128001.34 | 96.4718 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties of the contractor in articulating the cc and eq specialties. carrying out the projects with the guarantee of the eta remaining in operation. | changes arising from unforeseen situations supplied by errors and omissions and extra work.
4616 | 1414891 | Rehabilitation of the Ribeira da Pega Path | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 06-02-2015 | 24-09-2015 | 230 | 180 | 222008.79 | 187942.86 | 1 | 186856.21 | 1086.65 | 100.5815 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1-Price:70% Subfactors: a) Overall Price: 90% b) Justification of the Proposed Price: 10% 2-Technical Value of the Proposal: 30% Subfactors: a) Work Program: 50% .Work Plan: 50% .Labor Plan: 25% .Equipment Plan: 25% b) Descriptive and Justification: 40% c) Payment Plan: 10% | 1 | 70 | Yes (no values) | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the contracting company carried out the project in a shorter period of time | underwork
4617 | 1412215 | Contract for the Environmental Remediation Works in the Former Mining Area of ​​Freixinho | 45112500-0 | Earthmoving work | FALSE | 2014 | 2015 | Portugal | Pinhel | Guarda | 9 | N/A | 09-03-2015 | 14-07-2015 | 127 | 90 | 350000 | 295000 | 2 | 295000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the stipulated time frame.
4618 | 1411840 | Contract for the Construction of the Headquarters Building of the Association of Veiros Hydro-Agricultural Development of Veiros | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Estremoz | Évora | 7 | 21 | 20-03-2015 | 28-10-2015 | 222 | 120 | 350000 | 280000.01 | 2 | 275235.78 | 4764.23 | 101.731 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there was no change to the execution period of the project | there was no need to carry out all the project foreseen in the bill of quantities of the contract execution project.
4619 | 1411507 | Placement of synthetic grass in the sports parks of the parishes: Navais | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 31-10-2014 | 18-08-2015 | 291 | 60 | 199864.34 | 173011.49 | 1 | 173011.49 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment, to be able to reorganize its activities during the course of the intervention.
4620 | 1411442 | Placement of synthetic grass in the sports parks of the parishes: Argivai | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 31-10-2014 | 18-08-2015 | 291 | 60 | 199841.78 | 176515.2 | 1 | 176515.2 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment to be able to reorganize its activities during the course of the intervention.
4621 | 1411434 | Placement of synthetic grass in the sports parks of the parishes: Amorim | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 31-10-2014 | 12-10-2015 | 346 | 60 | 199667 | 189628 | 1 | 189628 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment, to be able to reorganize its activities during the course of the intervention.
4622 | 1411111 | Rehabilitation of the Municipal Road "Ferreirós - Lageosa" | 45232451-8 | Drainage and surface works | FALSE | 2015 | 2015 | Portugal | Tondela | Viseu | 20 | 11 | 10-03-2015 | 25-09-2015 | 199 | 150 | 295500 | 247000 | 1 | 247000 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed before the deadline.
4623 | 1411063 | Rehabilitation of slopes/water lines and paths - Parish of Silvares | 45112320-4 | Land-reclamation work | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 11 | 26-02-2015 | 11-05-2015 | 74 | 60 | 242743.75 | 194195.01 | 1 | 169785.03 | 24409.98 | 114.377 | lowest price | 2 | 100 | Waive | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the established time frame and the measurement was carried out after its conclusion. | existence of unexecuted works, leading to suppression of works
4624 | 1409631 | Remodeling of the Wastewater Treatment Plant (WWTP) in Estremoz | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2015 | 2015 | Portugal | Estremoz | Évora | 7 | 20 | 19-03-2015 | 30-12-2015 | 286 | 210 | 2601516.57 | 1998900 | 3 | 2030882.41 | -31982.41 | 98.4252 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1 - Price = 50% Sub factors: | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 34 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work | additional work
4625 | 1409131 | Contract for the stabilization of the cliffs of Praia de S. Pedro moel | 45242110-9 | Launchway construction work | FALSE | 2010 | 2015 | Portugal | Leiria | Leiria | 10 | 45 | 01-03-2012 | 04-03-2015 | 1098 | 270 | 2100000 | 1278570 | 3 | 1284445.02 | -5875.02 | 99.5426 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the execution deadline has been met | there were works initially planned that were not necessary
4626 | 1408213 | Contract for Adduction to Ourique | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Ourique | Beja | 2 | 47 | 28-02-2014 | 30-08-2015 | 548 | 365 | 4140000 | 2852643.03 | 3 | 2977079.17 | -124436.14 | 95.8202 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | changes in the layout of ducts due to opinions from various entities | design changes
4627 | 1405574 | Improvement of the EM between Mosteiro and the connection to the EN 238, with the execution of the widening of the carriageway, parking areas, application of bituminous concrete pavement, water drainage | 45233220-7 | Surface work for roads | FALSE | 2015 | 2015 | Portugal | Oleiros | Castelo Branco | 5 | 12 | 10-03-2015 | 02-07-2015 | 114 | 60 | 245000 | 198361.91 | 1 | 198361.91 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the causes of the alterations to the deadline for the execution of the project were due to adverse weather conditions, which, due to the nature of the soils, did not allow the execution of the projects.
4628 | 1405379 | Contract for the refurbishment and recovery of the Academia do CPN building CP 7/2014 PC 45_998 | 45262700-8 | Building alteration work | FALSE | 2014 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 28-07-2014 | 30-01-2015 | 186 | 92 | 698000 | 586540.63 | 2 | 617340.8 | -30800.17 | 95.0108 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions | work not foreseen in the contract due to the fact that several situations were found in the execution of the project that it was not possible to detect previously, in the execution of the project, and that did not constitute errors or omissions, and that were necessary for the execution of the project. - pc 45_2155
4629 | 1405378 | Reinforcement of the Spur at Praia do Sul – Ericeira | 45241300-1 | Pier construction work | FALSE | 2014 | 2015 | Portugal | Mafra | Lisboa | 11 | 24 | 10-03-2015 | 18-11-2015 | 253 | 100 | 286216.44 | 209308.56 | 1 | 209308.56 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: a) Overall price of the proposal (60%); b) Technical quality of the proposal (40%), divided by the following sub-factors: b.1) Descriptive memory and justification of the mode of execution of the contract, including description of the execution planning of the works, according to specifications (45%); b.2) Work Plan (20%); b.3) Labor Plan (17.5%); b.4) Equipment Plan (17.5%). | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | do not exist.
4630 | 1402333 | Replacement of the roof, demolition of the wall delimiting the field with polycarbonate tables and nets suitable for roller hockey, construction of sanitary facilities for the disabled | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2014 | 2015 | Portugal | Valongo | Porto | 13 | 12 | 04-03-2015 | 29-06-2015 | 117 | 60 | 187500 | 150000.01 | 1 | 150000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the project deadline | there were no changes to the value of the project
4631 | 1401508 | Requalification of Municipal Roads | 45233142-6 | Road-repair works | FALSE | 2014 | 2015 | Portugal | Vidigueira | Beja | 2 | 12 | 04-03-2015 | 22-10-2015 | 232 | 150 | 1994683.8 | 945887.38 | 2 | 939455.7 | 6431.68 | 100.6846 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: ) Overall Bid Price (Pg) at 30% b) Technical value of the proposal (Vt) at 70% | 1 | 30 | Yes (no values) | FALSE | Non-fulfilment of the contract (Contract Termination) | 10 | N/A | N/A | FALSE | FALSE | FALSE | N/A |  | underwork
4632 | 1399730 | Construction of small streets in the municipality of Cascais | 45233223-8, 45233294-6, 45111100-9, 45232130-2 | Carriageway resurfacing works, Installation of road signals, Demolition work, Storm-water piping construction work | FALSE | 2013 | 2015 | Portugal | Cascais | Lisboa | 11 | N/A | 11-08-2014 | 27-08-2015 | 381 | 144 | 912600 | 547560 | 2 | 547560 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A
4633 | 1399518 | Infrastructure and sports equipment - Placement of synthetic grass in the sports parks of the parishes: Estela | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 31-10-2014 | 18-08-2015 | 291 | 60 | 199541.11 | 171527.66 | 1 | 171527.66 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment, to be able to reorganize its activities during the course of the intervention and difficulty in the delivery of materials (screen/grass) by the contractor's suppliers.
4634 | 1393192 | Construction of Caminho da Seixinha in the Fundão Irrigation Block, in the Cova da Beira Hydro-Agricultural Development | 45233123-7 | Secondary road construction work | FALSE | 2013 | 2015 | Portugal | Fundão | Castelo Branco | 5 | 11 | 26-02-2015 | 10-08-2015 | 165 | 60 | 290000 | 214568.59 | 1 | 205788.08 | 8780.51 | 104.2668 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project | during the execution of the project it was verified that it was not necessary to carry out some works, which resulted in underwork.
4635 | 1391936 | Contract for the refurbishment of the 0th floor of the Professional Training Center for the Footwear Industry in S. João da Madeira | 45220000-5 | Engineering works and construction works | FALSE | 2014 | 2015 | Portugal | São João da Madeira | Aveiro | 1 | 13 | 16-02-2015 | 03-09-2015 | 199 | 150 | 320000 | 289997.84 | 2 | 289997.82 | 0.02 | 100 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: price - 50% technical value - 50% - see article 7 Tender Program | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | there were no changes to the project schedule. | there were no changes to the value of the project
4636 | 1390631 | Physical rehabilitation of the urban center of Marco de Canaveses - street1º de Maio, streetDr. Alfredo Manso Preto and Av. F.C. Marco | 45233140-2 | Roadworks | FALSE | 2015 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 20-02-2015 | 20-07-2015 | 150 | 92 | 216000 | 191814.59 | 1 | 191814.59 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed on time
4637 | 1389610 | Improvement of municipal road n.º 555 between melo and figueiró da serra | 45233142-6 | Road-repair works | FALSE | 2014 | 2015 | Portugal | Gouveia | Guarda | 9 | N/A | 03-02-2015 | 29-06-2015 | 146 | 150 | 348719.6 | 292960 | 2 | 292960 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4638 | 1388531 | Fresh fish storage, ice manufacturing and storage - Lota de Portimão | 45351000-2 | Mechanical engineering installation works | FALSE | 2014 | 2015 | Portugal | Portimão | Faro | 8 | N/A | 10-02-2015 | 10-06-2015 | 120 | 120 | 302000 | 299972.59 | 2 | 299972.59 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: Price 40% Technical Quality of the Proposal 60% | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies
4639 | 1386228 | Expansion contract in Santiago do Cacém - Supply to Old Furnaces, Tenant Forums and Nozzles | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Odemira | Setúbal | 17 | 47 | 21-01-2015 | 30-11-2015 | 313 | 180 | 1540000 | 1078255.02 | 3 | 1055129.3 | 23125.72 | 102.1917 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | partial consignments | project execution adjustments
4640 | 1385169 | Almodôvar supply contract | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Almodovar | Beja | 2 | 47 | 03-04-2014 | 18-11-2015 | 594 | 365 | 4730000 | 2838000.01 | 3 | 2818274.97 | 19725.04 | 100.6999 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties in accessing the land by the owners. | alterations to the route with consequent increases in the allocation of road pavements.
4641 | 1385043 | Supply contract to Cuba and Alvito - Alvito Reservoir, Faro do Alentejo and Guizo - Supply to Viana | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Viana do Alentejo | Beja | 2 | 47 | 03-04-2014 | 31-12-2015 | 637 | 270 | 3400000 | 2237186.27 | 3 | 2314022.17 | -76835.9 | 96.6796 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties according to owners and design changes. | design changes resulting from agreements with landlords and the municipality.
4642 | 1384601 | Construction of sports equipment for changing rooms and synthetic turf | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Resende | Viseu | 20 | 9 | 04-12-2014 | 06-07-2015 | 214 | 210 | 349990 | 296797.66 | 2 | 296797.66 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | anticipation of completion of the contract. | the change in the value of the project was due exclusively to the price revision
4643 | 1383166 | execution of the contract called eb 2273 - waste water drainage network of lamelas (santo tirso) - water system of the northwest region, within the scope of the water system of the northwest region. | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Santo Tirso | Porto | 13 | 41 | 03-10-2014 | 31-12-2015 | 454 | 240 | 1350000 | 1350000 | 3 | 1350000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 25 | N/A | N/A | N/A | N/A | N/A | N/A | volume of hard rock greater than expected, which led to a rescheduling of the projects in line with the forecast. necessary changes to the execution project can only be detected during the execution of the project. | execution of a smaller number of branches than expected.
4644 | 1383077 | Maintenance Dredging in the Navigation Channels and Maneuvering and Parking Basins in the Port of Setúbal in 2015 | 45252124-3 | Dredging and pumping works | FALSE | 2014 | 2015 | Portugal | Setúbal | Setúbal | 17 | 21 | 13-02-2015 | 25-05-2015 | 101 | 120 | 900000 | 854325 | 2 | 844610.3 | 9714.7 | 101.1502 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: 1) Global Price - 45% 2) Quality of Technique, Work Methodology and Execution Process - 30% 3) deadline - 25% | 1 | 45 | Yes (no values) | FALSE | Complete fulfillment of the contract | 2 | N/A | N/A | FALSE | FALSE | FALSE | N/A | underwork | works less
4645 | 1383072 | execution of the contract called eb 2272 - guimarei waste water drainage network (santo tirso). northwest region water system, within the scope of the northwest region water system. | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Santo Tirso | Porto | 13 | 41 | 03-10-2014 | 31-12-2015 | 454 | 240 | 1000000 | 986549.85 | 2 | 862779.23 | 123770.62 | 114.3456 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | constraints on entering private land and necessary changes to the execution project. need for changes to the execution project, only detectable in the construction phase. volume of hard rock greater than expected, which led to a rescheduling of the projects in line with the forecast. | execution of a smaller number of branches than expected.
4646 | 1380702 | Refurbishment of CM 1166 | 45233142-6 | Road-repair works | FALSE | 2014 | 2015 | Portugal | Guarda | Guarda | 9 | 9 | 02-02-2015 | 29-06-2015 | 147 | 150 | 370000 | 253000.91 | 2 | 253000.91 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time
4647 | 1379961 | Improvement of accessibility in the city of Guarda | 45233142-6 | Road-repair works | FALSE | 2014 | 2015 | Portugal | Guarda | Guarda | 9 | 9 | 02-02-2015 | 29-06-2015 | 147 | 150 | 368300 | 248000.93 | 1 | 248000.93 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time
4648 | 1377894 | execution of the public work contract called eb 2271 - waste water drainage network of s. tiago da carreira (santo tirso), within the scope of the multimunicipal system of water supply | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Santo Tirso | Porto | 13 | 41 | 30-10-2014 | 30-10-2015 | 365 | 240 | 640000 | 604680.04 | 2 | 513371.58 | 91308.46 | 117.786 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | no change | execution of a smaller number of branches than expected.
4649 | 1377778 | Contract for Environmental Remediation Works in the Old Mining Area of ​​Fontinha | 45112500-0 | Earthmoving work | FALSE | 2014 | 2015 | Portugal | Seia | Guarda | 9 | 20 | 09-02-2015 | 02-09-2015 | 205 | 180 | 1500000 | 1073999 | 3 | 1073999 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1. Price - 60%; 2. Technical Value of the Proposal - 40%. (As indicated in the Contest Program) | 1 | 60 | Yes (no values) | FALSE | Complete fulfillment of the contract | 15 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed within the stipulated time frame.
4650 | 1376870 | Construction of the Municipal Stadium - Athletics Track - Public Tender | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 30-01-2015 | 18-11-2015 | 292 | 120 | 599850.73 | 515438.79 | 2 | 515438.79 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the deadline.
4651 | 1375126 | Refurbishment of the Santa Luzia municipal camping site | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Miranda do Douro | Bragança | 4 | 30 | 14-11-2013 | 26-01-2015 | 438 | 365 | 879284 | 848419.85 | 2 | 848419.85 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | favorable climate conditions
4652 | 1374246 | Malhada EE5 refurbishment including civil construction, equipment and electrical installations. | 45232423-3 | Sewage pumping stations construction work | FALSE | 2014 | 2015 | Portugal | Ílhavo | Aveiro | 1 | 23 | 03-02-2015 | 18-12-2015 | 318 | 120 | 207000 | 180510 | 1 | 180510 | 0 | 100 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: 1) Price - 55% 2) Technical value of the proposal - 45% | 1 | 55 | N/A | FALSE | Complete fulfillment of the contract | 7 | N/A | N/A | FALSE | FALSE | FALSE | N/A | non-compliance by the contractor with respect to contractual deadlines | there were no changes to the contract price
4653 | 1371671 | Home extensions - 2014 | 50000000-5 | Repair and maintenance services | FALSE | 2014 | 2015 | Portugal | Caldas da Rainha | Leiria | 10 | 30 | 21-01-2015 | 24-11-2015 | 307 | 365 | 299704.03 | 165599.59 | 1 | 165599.59 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | work progressed more quickly
4654 | 1371390 | Installation of two synthetic lawns | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2015 | 2015 | Portugal | Pinhel | Guarda | 9 | 15 | 29-01-2015 | 29-07-2015 | 181 | 570 | 489000 | 331221 | 2 | 322580.12 | 8640.88 | 102.6787 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | favorable development of the projects by the contractor | suppressed works
4655 | 1369222 | execution of the contract called eb 2270- drainage network of sands, palmeira, roriz, santo tirso and são mamede de negrelos (santo tirso), within the scope of the northwest region water system. | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Santo Tirso | Porto | 13 | 41 | 05-12-2014 | 31-12-2015 | 391 | 180 | 925000 | 734534.86 | 2 | 599213.9 | 135320.96 | 122.5831 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | constraints on entering private land and necessary changes to the execution project. the volume of hard rock was approximately 50% higher than expected, which led to a rescheduling of the project in line with the forecast. | execution of a smaller number of branches than expected.
4656 | 1364456 | Requalification of elementary school n.º 1 in Municipal Archive | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2010 | 2015 | Portugal | Tondela | Viseu | 20 | N/A | 09-02-2011 | 06-01-2015 | 1427 | 270 | 427875 | 350951.38 | 2 | 350951.38 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | assignment of contractual position; corrections to the project performed; delay in supplying equipment | price review and contractual fine
4657 | 1360537 | Construction of a Synthetic Field in Rio Tinto (Rio Tinto Athletic Club) | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Gondomar | Porto | 13 | 20 | 21-01-2015 | 12-10-2015 | 264 | 210 | 300000 | 249951.22 | 1 | 249951.22 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | suspension notice: 01/22/2015_x000d_ auto restart: 4/1/2015
4658 | 1360281 | Adhesive longitudinal defense - paramos beach - Espinho | 45243000-2 | Coastal-defence works | FALSE | 2014 | 2015 | Portugal | Espinho | Aveiro | 1 | 20 | 22-01-2015 | 21-09-2015 | 242 | 120 | 1081196 | 864956.81 | 2 | 864956.81 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period
4659 | 1360251 | This is the work of the 2nd phase of the Adaptation and Expansion of an existing building. The work presupposes the construction of a building corresponding to the auditorium. | 45212320-5 | Construction work for buildings relating to artistic performances | FALSE | 2013 | 2015 | Portugal | Monção | Viana do Castelo | 18 | 30 | 06-02-2014 | 02-04-2015 | 420 | 300 | 370000 | 301780.05 | 2 | 301780.05 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | delay in delivery of acoustic material.
4660 | 1359775 | Construction of a Synthetic Field in Gens (Gens Sport Clube) | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Gondomar | Porto | 13 | 20 | 21-01-2015 | 12-10-2015 | 264 | 210 | 295000 | 207159.4 | 1 | 207159.4 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed before the execution deadline.
4661 | 1358476 | Requalification and expansion of elementary school da Picota - Tuías | 45454000-4 | Restructuring work | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 20-01-2015 | 11-09-2015 | 234 | 150 | 331450.45 | 272735.33 | 2 | 301939.65 | -29204.32 | 90.3278 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 9 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional work | additional work
4662 | 1355638 | Construction of Sports, Recreational and Leisure Infrastructures in the Parishes, by Contract - Laying of synthetic flooring in the Fujanco Sports Park - Rodelo - CP-CCP-EMP No. 02/2014 | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 23 | 19-01-2015 | 22-09-2015 | 246 | 90 | 271961 | 239019.59 | 1 | 244519.59 | -5500 | 97.7507 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | completion of work | existence supply of errors and omissions
4663 | 1354991 | Requalification of the Lota building in the Port of Olhão | 45454000-4 | Restructuring work | FALSE | 2014 | 2015 | Portugal | Olhão | Faro | 8 | 27 | 07-01-2015 | 09-12-2015 | 336 | 120 | 424500 | 416601.49 | 2 | 419912.64 | -3311.15 | 99.2115 | Most economically advantageous proposal Factors and any sub-factors accompanied by the respective weighting coefficients: Price 50% QTP 50% | 1 | 50 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | unspecified contingencies | unspecified contingencies
4664 | 1350462 | Requalification of Baixa network | 45232151-5 | Water-main refurbishment construction work | FALSE | 2012 | 2015 | Portugal | Reguengos de Monsaraz | Évora | 7 | 26 | 29-12-2014 | 02-10-2015 | 277 | 480 | 285816.72 | 208058.15 | 1 | 208058.15 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | when the firm signed the consignment notice for the contract, it presented a declaration that it would carry out the project within a period of 180 days
4665 | 1349814 | Public tender for awarding the contract for "meadela business park - rainwater, wastewater and paving infrastructure" | 45232130-2 | Storm-water piping construction work | FALSE | 2014 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 12-01-2015 | 31-07-2015 | 200 | 90 | 287586.5 | 198845.19 | 1 | 195114.91 | 3730.28 | 101.9118 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions. | underwork was done.
4666 | 1349155 | Urban Requalification of the Center of Penamacor | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Penamacor | Castelo Branco | 5 | 9 | 13-01-2015 | 30-09-2015 | 260 | 120 | 371001 | 155155.2 | 1 | 172725.9 | -17570.7 | 89.8274 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 12 | N/A | N/A | FALSE | FALSE | FALSE | N/A | delay on the part of the contractor. | underwork: €4,570.00.
4667 | 1348577 | Supply and application of synthetic grass, football field irrigation system, reformulation and partial improvement of access to changing rooms | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Valongo | Porto | 13 | 12 | 09-01-2015 | 09-12-2015 | 334 | 60 | 196500 | 156787.55 | 1 | 158310.99 | -1523.44 | 99.0377 | Most economically advantageous proposal Factors and possible sub-factors accompanied by the respective weighting coefficients: The following assessment factors are taken into account of the proposals and their weighting in descending order of importance: 1st most favorable price - 80%; 2nd Technical Valuation 20%. The proposal evaluation model is the one set out in Annex VII - Regulation assessment, which is part of the tender program | 1 | 80 | Waive | FALSE | Complete fulfillment of the contract | 17 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the cause that led to the change to the execution period of the project was the suspension of the projects | the causes that led to the alterations to the value of the project were the price review that resulted in a credit in favor of the city hall in the amount of € - 2,979.07 + vat
4668 | 1346278 | Urban requalification of the northern area of ​​Benquerença | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Penamacor | Castelo Branco | 5 | 9 | 06-01-2015 | 30-09-2015 | 267 | 120 | 345907.72 | 189521.05 | 1 | 233492.06 | -43971.01 | 81.1681 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 8 | N/A | N/A | FALSE | FALSE | FALSE | N/A | additional to the initial contract for another 1 month. | underwork value: €1,891.00.
4669 | 1345988 | Contract for the Rehabilitation Works of the Mine Gallery Below the Access Road to the Vale D'Oca District in Aljustrel | 45221248-2 | Tunnel linings construction work | FALSE | 2014 | 2015 | Portugal | Aljustrel | Beja | 2 | 21 | 26-12-2014 | 25-09-2015 | 273 | 180 | 1000000 | 850362.61 | 2 | 908610.11 | -58247.5 | 93.5894 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | during the contract, there was a need to carry out unpredictable works that could only be detected during the execution of the contract. these works cannot be technically and economically separable from the object of the contract without serious inconvenience for the developer and the public interest. as a result of carrying out these works, the contract execution period was extended for another 43 (forty-three) days | during the contract, there was a need to carry out unpredictable works that could only be detected during the execution of the contract. these works cannot be technically and economically separable from the object of the contract without serious inconvenience for the developer and the public interest.
4670 | 1345112 | Intermunicipal Road Badim/Cousso (Section Badim - Riba de Mouro). Supply and application of bituminous mat, hot technology "Binder" | 45432110-8 | Floor-laying work | FALSE | 2011 | 2015 | Portugal | Monção | Viana do Castelo | 18 | 20 | 30-12-2014 | 07-09-2015 | 251 | 180 | 245000 | 198113.5 | 1 | 198113.5 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climatic conditions.
4671 | 1341065 | Construction of the Faro / Loulé / Olhão Transfer Station Official Pavilion | 45213221-8 | Warehouse stores construction work | FALSE | 2014 | 2015 | Portugal | Loulé | Faro | 8 | 15 | 05-11-2014 | 26-08-2015 | 294 | 60 | 190000 | 184515.7 | 1 | 186042.88 | -1527.18 | 99.1791 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | change in electrical installations, workshop pit and coverage of distribution networks (sewerage network, electricity network and water network). | alteration in electrical installations, workshop ditch and coverage of distribution networks (sewerage network, electricity network and water network).
4672 | 1336154 | Paving and improvement of streets in the parishes of: União de parishes of Leiria, Pousos, Barreira and Cortes | 45233220-7 | Surface work for roads | FALSE | 2014 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 13-08-2014 | 17-02-2015 | 188 | 120 | 1818687 | 323489.46 | 2 | 323489.46 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A
4673 | 1336085 | Paving and improvement of streets in the parishes of: Union of parishes of Santa Eufémia and Boa Vista, Caranguejeira, Arrabal and Union of parishes of Santa Catarina da Serra and Chainça | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 14-08-2014 | 29-07-2015 | 349 | 120 | 1818687 | 337249.64 | 2 | 294028.6 | 43221.04 | 114.6996 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work | underwork
4674 | 1336065 | Paving and improvement of several streets in the parishes of Amor, Bidoeira de Cima, Milagres, Union of Parishes of Souto da Carpalhosa and Ortigosa and Union of Parishes of Colmeias and Memória | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 05-08-2014 | 15-12-2015 | 497 | 120 | 1818687 | 369811.93 | 2 | 356811.93 | 13000 | 103.6434 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | no change | underwork
4675 | 1336004 | This involves improving and paving a rural road, including earthworks, drainage, bituminous paving, safety signs and ancillary works. | 45233123-7 | Secondary road construction work | FALSE | 2014 | 2015 | Portugal | Meda | Guarda | 9 | 30 | 29-12-2014 | 05-06-2015 | 158 | 180 | 315480.58 | 278491.86 | 2 | 278491.86 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | favorable conditions and accesses that allowed the smooth progress of the project, which led to the project being completed before the contracted deadline. | it results from the non-execution of small quantities of some works because, during the project, they were considered unnecessary,
4676 | 1334184 | Wastewater drainage system - Vila Boa de Quires network | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 29-12-2014 | 03-09-2015 | 248 | 60 | 349201 | 242334 | 1 | 242334 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | suspension in accordance with paragraph b) of article 365 of the "public procurement code".
4677 | 1331995 | Public tender for the award of the contract for "Replacement of fiber cement roofing in Basic Education Schools 1 / Municipal Kindergartens" | 45261920-9 | Roof maintenance work | FALSE | 2014 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 18-12-2014 | 12-08-2015 | 237 | 120 | 432269.5 | 323617.8 | 2 | 300751.4 | 22866.4 | 107.6031 | Most economically advantageous proposal Factors and possible subfactors accompanied by the respective weighting coefficients: Bid price - 40%; Technical value of Proposal - 60%. The subfactors are those contained in article 18 of the tender program. | 1 | 40 | Yes (no values) | FALSE | Complete fulfillment of the contract | 34 | N/A | N/A | FALSE | FALSE | FALSE | N/A | bad weather conditions | underwork
4678 | 1329869 | Expansion of the Tailors Water and Sanitation Distribution Network | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Sabugal | Guarda | 9 | 15 | 18-12-2014 | 05-11-2015 | 322 | 150 | 280194.17 | 168116.51 | 1 | 190236.62 | -22120.11 | 88.3723 | Urgent Tender Announcement Without Pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | more work and underwork
4679 | 1329709 | Expansion of the Higher School of Health Technology in Coimbra | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Coimbra | Coimbra | 6 | 20 | 19-12-2014 | 19-11-2015 | 335 | 180 | 1023513.92 | 823999.15 | 2 | 865050.23 | -41051.08 | 95.2545 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 14 | N/A | N/A | FALSE | FALSE | FALSE | N/A | due to the period of school evaluations, they limited the execution of the projects | due to the period of school evaluations, they limited the execution of the projects
4680 | 1327800 | Repair of the Fontainhas Recreational Dock | 45246200-5 | Riverbank protection works | FALSE | 2014 | 2015 | Portugal | Setúbal | Setúbal | 17 | 19 | 09-12-2014 | 11-12-2015 | 367 | 180 | 750000 | 562500.01 | 2 | 562500.01 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | stone laying work on the marginal retention slope (tidal work)
4681 | 1324334 | Contract for "Chafé Sports Field - Synthetic Turf" | 45113000-2 | Siteworks | FALSE | 2014 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 11-12-2014 | 16-06-2015 | 187 | 90 | 360000 | 239729 | 1 | 239729 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions
4682 | 1324278 | Refurbishment of the Auction Building and Ice Factory in the Fishing Port of Figueira da Foz | 45453000-7 | Overhaul and refurbishment work | FALSE | 2014 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 22 | 15-07-2014 | 15-12-2015 | 518 | 180 | 360000 | 310114 | 2 | 348852.16 | -38738.16 | 88.8955 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | additional to the contract: errors and omissions and over and underwork | additional to the contract - charge €38,738.15
4683 | 1324277 | Pier Coverings and External Infrastructures - Requalification of Coverings, Piers and External Infrastructures in the Fishing Port of Figueira da Foz | 45453000-7 | Overhaul and refurbishment work | FALSE | 2014 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 22 | 11-08-2014 | 18-12-2015 | 494 | 180 | 345000 | 297114 | 2 | 341825.49 | -44711.49 | 86.9198 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | additional contract: records of errors and omissions and extra and underwork | additional contract: charges €44,711.50
4684 | 1317029 | Work to Improve the Safety Conditions of the Dam | 45315600-4 | Low-voltage installation work | FALSE | 2014 | 2015 | Portugal | Aljustrel | Beja | 2 | 21 | 09-10-2014 | 01-05-2015 | 204 | 118 | 440000 | 439118.71 | 2 | 439118.71 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the delivery of material to the contractor, with special incidence on the servomotor that was not replaced, but recovered. as the equipment is quite old, its recovery was quite time consuming.
4685 | 1310816 | Construction of the Vila de Aparecida Bypass - 2nd Phase | 45233220-7 | Surface work for roads | FALSE | 2014 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 21-11-2014 | 16-10-2015 | 329 | 120 | 289256.65 | 239687 | 1 | 239687 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | conditioning of earthmoving works and land preparation for project quotas due to adverse weather conditions.
4686 | 1310477 | Supply of a transformer for the interconnection of the Maranhão hydroelectric plant to the Public Service Electrical Network (RESP); | 45317200-4 | Electrical installation work of transformers | FALSE | 2013 | 2015 | Portugal | Avis | Portalegre | 12 | 20 | 16-12-2013 | 06-07-2015 | 567 | 180 | 380000 | 273100 | 2 | 273100 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline change was due to the need to make it compatible with related works
4687 | 1309548 | Infrastructure and sports equipment - Placement of synthetic grass in the sports parks of the parishes: Terroso | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 11-11-2014 | 18-08-2015 | 280 | 60 | 199658.45 | 180987.99 | 1 | 180987.99 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment, to be able to reorganize its activities during the course of the intervention and difficulty in the delivery of materials (screen/grass) by the contractor's suppliers.
4688 | 1309537 | Infrastructure and sports equipment - Placement of synthetic grass in the sports parks of the parishes: Beiriz | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 15 | 11-11-2014 | 18-08-2015 | 280 | 60 | 196716.38 | 165224.13 | 1 | 165224.13 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension - due to the need of the club/association responsible for the equipment, to be able to reorganize its activities during the course of the intervention and difficulty in the delivery of materials (screen/grass) by the contractor's suppliers.
4689 | 1309322 | Constance lift station construction | 45232431-2 | Wastewater pumping station | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 15 | 20-11-2014 | 07-09-2015 | 291 | 90 | 236416 | 183987 | 1 | 183987 | 0 | 100 | lowest price | 2 | 100 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | ip authorization due to intervention in e.n. 211.
4690 | 1308175 | «PIPARU - Priority Investment Program in Urban Rehabilitation Actions Action: Nº 35 - Bairro Dr. Alfredo Bensaúde, Lots A1 to A11, B1 to B12 and C1 to C13 - Lisbon | 45330000-9 | Plumbing and sanitary works | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | N/A | 15-10-2014 | 24-06-2015 | 252 | 120 | 180000 | 154700 | 1 | 101358.78 | 53341.22 | 152.6261 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension due to adverse weather conditions in certain periods of the execution of the project; and delay in the preparation of the contract. | underwork
4691 | 1307892 | The object of the contract is the execution of the contract for the construction of the Mozelos Sports Pavilion | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 21-11-2014 | 06-10-2015 | 319 | 400 | 1485500 | 1261967.56 | 3 | 33728.21 | 1228239.35 | 3741.5788 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work. | contract termination.
4692 | 1305718 | Emergency stabilization after a fire in the county from customs of faith | 77000000-0 | Agricultural, forestry, horticultural, aquacultural and apicultural services | FALSE | 2014 | 2015 | Portugal | Alfandega da Fé | Bragança | 4 | 12 | 30-10-2014 | 26-03-2015 | 147 | 60 | 263769.18 | 220669.96 | 1 | 220669.96 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
4693 | 1304907 | “Improvement of the railway track in the PM of Contumil – Minho and Douro Parks” | 50220000-3 | Repair, maintenance and associated services related to railways and other equipment | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | 30 | 18-11-2014 | 14-09-2015 | 300 | 270 | 500000 | 468764.81 | 2 | 468764.81 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period. | there were no price changes.
4694 | 1302893 | Infrastructure and Paving of Municipal streets | 45232451-8 | Drainage and surface works | FALSE | 2014 | 2015 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 11-11-2014 | 26-10-2015 | 349 | 330 | 391052.3 | 372530.1 | 2 | 372530.1 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | good performance in the development and execution of works
4695 | 1302648 | Conservation of the Clock Tower and surrounding area: Requalification of pedestrian and road accesses in the area surrounding the Torre do Relógio | 45222000-9 | Construction work for engineering works except bridges, tunnels, shafts and subways | FALSE | 2014 | 2015 | Portugal | Alfandega da Fé | Bragança | 4 | 11 | 05-09-2014 | 17-06-2015 | 285 | 240 | 498774.06 | 396186.57 | 2 | 396186.57 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to register | nothing to register
4696 | 1302423 | The object of the contract is the execution of the contract for the Execution of the Urban Variant - Intermunicipal Connections/accesses to the School Center | 45233120-6 | Road construction works | FALSE | 2014 | 2015 | Portugal | Vila Verde | Braga | 3 | 14 | 14-11-2014 | 27-07-2015 | 255 | 120 | 348056.7 | 330073.31 | 2 | 330073.31 | 0 | 100 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A
4697 | 1302311 | Execution of the Synthetic Turf Campo de Jogos do Areal (Raianos). Application of last generation synthetic grass and silica sand and rubber granules. | 45236119-7 | Repair work on sports fields | FALSE | 2014 | 2015 | Portugal | Monção | Viana do Castelo | 18 | 20 | 23-10-2014 | 13-07-2015 | 263 | 150 | 220000 | 179976.33 | 1 | 179976.33 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the period that occurs, in this case 19 days, is due to the date on which the provisional acceptance was drawn up.
4698 | 1298893 | This is the construction of a reinforced concrete bridge over the Ribeira Teja, in Aveloso and respective accesses | 45221111-3 | Road bridge construction work | FALSE | 2014 | 2015 | Portugal | Meda | Guarda | 9 | N/A | 12-11-2014 | 23-09-2015 | 315 | 365 | 440485.9 | 375509.74 | 2 | 375509.73 | 0.01 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | due to the urgency in carrying out the project, an amendment to the contractual term was agreed with the contractor. | difference in hits €0.01
4699 | 1298408 | The object of this contract is the Rehabilitation of the EE of the Marinheiros Post - Vacant | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Vagos | Aveiro | 1 | 32 | 31-10-2014 | 21-09-2015 | 325 | 120 | 165000 | 164031.05 | 1 | 164031.05 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with contractual deadlines, at the expense of the contracting company
4700 | 1296873 | C.p. No. 08/2014 - execution of home and non-domestic water supply and wastewater sanitation connections in the municipalities of guimarães and vizela" | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 30-10-2014 | 08-12-2015 | 404 | 540 | 259000 | 188190.1 | 1 | 188089.81 | 100.29 | 100.0533 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions allowed for faster development than originally anticipated | underwork
4701 | 1295911 | The object of this contract is the execution of the Pico de Regalados Sports Complex | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Vila Verde | Braga | 3 | 12 | 07-11-2014 | 30-06-2015 | 235 | 180 | 299781.8 | 259243.13 | 2 | 258553.13 | 690 | 100.2669 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4702 | 1295870 | The object of this contract is the execution of the Ribeira do Neiva Sports Park | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Vila Verde | Braga | 3 | 12 | 07-11-2014 | 30-06-2015 | 235 | 180 | 348172 | 313350.75 | 2 | 313343.02 | 7.73 | 100.0025 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4703 | 1295652 | Public tender for the Contract for the Remodeling/Expansion of the sanitation networks in the municipality of Oeiras - South Zone - Years 2014/ 2015 | 45232410-9 | Sewerage work | FALSE | 2014 | 2015 | Portugal | Oeiras | Lisboa | 11 | 11 | 16-10-2014 | 13-04-2015 | 179 | 365 | 370000 | 222000.01 | 1 | 222000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the contract indicated was aimed at the remodeling/expansion of domestic and rainwater sewer networks in the municipality of oeiras due to collapses in the collectors, so the duration of the same depends on the number of collapses of the domestic and rainwater wastewater networks.
4704 | 1295147 | Contract for the execution of the exterior arrangements, parking and access to the areas of the 1st phase of the contract for the Terceira Island Exhibition Park | 45233120-6 | Road construction works | FALSE | 2014 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | N/A | 03-11-2014 | 07-08-2015 | 277 | 120 | 346000 | 276800 | 2 | 276800 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | situations related to constructive anomalies in the contract for the 1st phase of the construction of the exhibition park on terceira island that directly interfered with the project to be carried out within the scope of the contract for roads and exterior access.
4705 | 1294460 | Support for the development of sporting infrastructures in the parishes - construction of the synthetic turf in the playground of rio de moinhos - parish of rio de moinhos | 45212200-8 | Construction work for sports facilities | FALSE | 2014 | 2015 | Portugal | Penafiel | Porto | 13 | 9 | 17-10-2014 | 27-05-2015 | 222 | 200 | 205631.2 | 184137.45 | 1 | 184137.45 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work completed within the contracted period.
4706 | 1292723 | Circular Axis to the Lena River and Bus Park, supporting the Historic and Tourist Center of Vila da Batalha | 45233121-3 | Main road construction works | FALSE | 2014 | 2015 | Portugal | Batalha | Leiria | 10 | N/A | 17-10-2014 | 26-06-2015 | 252 | 150 | 600000 | 483000 | 2 | 468293.87 | 14706.13 | 103.1404 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | there were changes to the execution period of the project due to 2 suspensions of the project. one for 49 days due to partial consignments and another for 22 days there was also a 6-day extension to carry out additional work | performing additional work. there was still underwork. the causes of these changes are based on the minutes of the executive meeting of 05/25/2015, in resolution no. 2015/0263/dom(soaa). the suppression of works was also approved by the minutes of the executive meeting of 07/06/2015, in deliberation nº 2015/0349/dom(soaa)
4707 | 1292347 | Environmental Enhancement of the East Bank of the Lena River - Ecological Park and Peripheral Car Park of Intermodal Support to the Historic and Tourist Center of Vila da Batalha | 45112710-5 | Landscaping work for green areas | FALSE | 2014 | 2015 | Portugal | Batalha | Leiria | 10 | N/A | 20-10-2014 | 26-06-2015 | 249 | 120 | 900000 | 749753.09 | 2 | 700968.36 | 48784.73 | 106.9596 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | lack of safety conditions, due to atmospheric instability. need to study the modeling of the land in relation to the ec quotas | reduction of the final value due to underwork in the amount of -48,784.73€
4708 | 1290099 | Requalification of the playground - grass on synthetic floor - sports complex of Alpendorada | 45236119-7 | Repair work on sports fields | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 12 | 29-10-2014 | 03-06-2015 | 217 | 60 | 249722.85 | 237366.8 | 1 | 237366.8 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work due to unfavorable weather conditions.
4709 | 1286525 | Public tender for the contract for the remodeling of the water supply networks in Tercena, in the municipality of Oeiras | 45232151-5 | Water-main refurbishment construction work | FALSE | 2014 | 2015 | Portugal | Oeiras | Lisboa | 11 | 11 | 09-10-2014 | 08-05-2015 | 211 | 181 | 180945.56 | 155209.5 | 1 | 155209.5 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | the project scheduled for the contract in question took place at a good pace, managing to anticipate the expected date for the completion of the contract by a few days
4710 | 1284721 | Requalification of the riverside bank of Peso da Régua | 45233161-5 | Footpath construction work | FALSE | 2014 | 2015 | Portugal | Peso da Régua | Vila Real | 19 | N/A | 29-10-2014 | 30-11-2015 | 397 | 180 | 348729 | 284048.5 | 2 | 284048.5 | 0 | 100 | Most economically advantageous proposal Factors and any subfactors accompanied by the respective weighting coefficients: Factors and any subfactors accompanied of the respective weighting coefficients: 60% Price and 40% Technical Value. | 1 | 60 | N/A | FALSE | Complete fulfillment of the contract | 0 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project deadline is suspended due to electrical and telecommunications infrastructures that collided with the implementation of the project.
4711 | 1284172 | Moorish-Safara conduct | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2010 | 2015 | Portugal | Moura | Beja | 2 | 57 | 19-09-2011 | 30-11-2015 | 1533 | 365 | 6700000 | 4020000.1 | 3 | 3226854.24 | 793145.86 | 124.5795 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | errors & omissions, overwork, underwork and suspensions | errors & omissions, overwork, underwork and suspensions
4712 | 1283355 | Requalification of Auction and Pier of Nazaré | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Nazaré | Leiria | 10 | 31 | 15-09-2014 | 21-08-2015 | 340 | 210 | 344000 | 299578.7 | 2 | 334509.3 | -34930.6 | 89.5577 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unspecified contingencies | unspecified contingencies
4713 | 1280445 | Public Tender for awarding the contract for "Municipal Stadium Manuela Machado - Renovation of the Athletics Track and Sports Area" | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 20 | 23-10-2014 | 24-07-2015 | 274 | 90 | 540000 | 480289.03 | 2 | 480289.03 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions
4714 | 1279935 | Expansion of the 1st floor of an existing building consisting of basement, ground floor and 1st floor, execution of infrastructure and renovations on the ground floor and basement. | 45215212-6 | Retirement home construction work | FALSE | 2014 | 2015 | Portugal | Mação | Santarém | 16 | 15 | 07-08-2014 | 24-02-2015 | 201 | 150 | 405000 | 405000 | 2 | 243000.01 | 161999.99 | 166.6667 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | heavy rainfall, which, combined with the type of terrain (clayey), forced some interruptions on the part of the contractor.
4715 | 1278805 | The contract consists of carrying out the Mobility and Planning contract for the Urban Center of Vila de Prado. | 45112700-2 | Landscaping work | FALSE | 2014 | 2015 | Portugal | Vila Verde | Braga | 3 | 20 | 22-10-2014 | 10-07-2015 | 261 | 180 | 248770.42 | 199016.35 | 1 | 199016.35 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was suspended for reasons concerning community funding
4716 | 1278276 | This involves the improvement and repaving of a municipal road, including earthworks, drainage, bituminous paving, safety signs and accessory works. | 45233121-3 | Main road construction works | FALSE | 2014 | 2015 | Portugal | Meda | Guarda | 9 | 21 | 21-10-2014 | 23-09-2015 | 337 | 365 | 380000 | 336057.51 | 2 | 313856.9 | 22200.61 | 107.0735 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | due to the good progress of the project and favorable weather conditions. | quantities of work that were not fully performed because they were not needed.
4717 | 1277654 | Measures to protect and reinforce the primary dune and the dune ecosystem of Póvoa de Varzim | 45220000-5 | Engineering works and construction works | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 30 | 22-10-2014 | 23-06-2015 | 244 | 210 | 1809329.44 | 1587482.59 | 3 | 1587482.59 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4718 | 1277566 | Rehearsal rooms in the garage of Teatro Jordão - Urzeses | 45212320-5 | Construction work for buildings relating to artistic performances | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 25 | 15-10-2014 | 24-05-2015 | 221 | 150 | 724414.42 | 657044 | 2 | 643815.93 | 13228.07 | 102.0546 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underworks.
4719 | 1277477 | 2013.099.01.C1 - SFP SANTARÉM - Telecommunications Infrastructures | 45310000-3 | Electrical installation work | FALSE | 2013 | 2015 | Portugal | Santarém | Santarém | 16 | 20 | 02-09-2014 | 10-03-2015 | 189 | 100 | 349000 | 278184.75 | 2 | 278184.75 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | materials
4720 | 1277059 | Vila Real International Circuit - Paddock Paving and Pits | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Vila Real | Vila Real | 19 | 20 | 07-10-2014 | 21-08-2015 | 318 | 60 | 336204.5 | 234733.97 | 1 | 234733.97 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions
4721 | 1275456 | Santo Isidoro network and water supply | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 21 | 09-10-2014 | 09-09-2015 | 335 | 120 | 227930 | 158210 | 1 | 158210 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension in accordance with paragraph b) of article 365 of the "public procurement code"
4722 | 1275191 | Implementation of a dune protection system - Construction of dune regenerators and reinforcement of the dune consolidation system | 45243400-6 | Beach-consolidation works | FALSE | 2014 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 17-10-2014 | 30-09-2015 | 348 | 63 | 636000 | 481200 | 2 | 455986.63 | 25213.37 | 105.5294 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions | existence of works to themselves
4723 | 1274037 | Requalification of the public space in the western part of the historic center of Viana do Castelo - Largo Vasco da Gama and Largo da Paz | 45233200-1 | Various surface works | FALSE | 2012 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 60 | 17-10-2014 | 24-08-2015 | 311 | 120 | 259328 | 199973.13 | 1 | 182945.85 | 17027.28 | 109.3073 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork.
4724 | 1273790 | Recovery of Municipal Roads | 45233220-7 | Surface work for roads | FALSE | 2014 | 2015 | Portugal | Ferreira do Zezere | Santarém | 16 | 21 | 07-10-2014 | 02-11-2015 | 391 | 60 | 412944.31 | 338318.07 | 2 | 315158.99 | 23159.08 | 107.3484 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | there was only a delay between the completion of the project and the preparation of the provisional rectification notice due to the fact that tests were carried out. | it is due to the existence of underwork and negative price revision
4725 | 1273477 | 1/DP/2011 - CB1118 – Contract for the Rehabilitation of buildings, landscaping and multi-functional space in the Bairro de Cabo-Mor, V. Nova de Gaia | 45453000-7 | Overhaul and refurbishment work | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 26-05-2011 | 15-12-2015 | 1664 | 300 | 940000 | 785210.99 | 2 | 815538.65 | -30327.66 | 96.2813 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | resettlement of households housed in the basements of buildings | unforeseen works on the water supply network and on the domestic waste water drainage network.
4726 | 1272905 | The object of this contract is the construction of 6 reservoirs, about 25 km of new water mains and the remodeling of the current pipeline between the ETA das Penhas da Saúde and the city council. | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2015 | Portugal | Covilhã | Castelo Branco | 5 | 40 | 16-10-2014 | 15-12-2015 | 425 | 300 | 11000000 | 10687635.95 | 3 | 10199055.61 | 488580.34 | 104.7904 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties experienced by the general contractor in mobilizing human and material resources, resulting from the precarious situation experienced in the civil construction sector. | underwork resulting from non-execution of contractual work
4727 | 1272483 | Urban Arrangement Contract for the Center of Tropeço | 45233120-6 | Road construction works | FALSE | 2014 | 2015 | Portugal | Arouca | Aveiro | 1 | 30 | 17-10-2014 | 27-10-2015 | 375 | 210 | 287154.71 | 264808.3 | 2 | 248008.14 | 16800.16 | 106.774 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the presentation of the final screens. | underwork and price revision.
4728 | 1272320 | Exterior intervention works in block 1 of the S. Vicente paulo neighborhood | 45454100-5 | Restoration work | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | 20 | 07-07-2014 | 30-10-2015 | 480 | 120 | 389600 | 294750.23 | 2 | 267953.98 | 26796.25 | 110.0003 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | the project on the contract proceeded normally, in accordance with the specification in the tender specifications and without incidents worthy of note. | work not carried out worth €26,796.03
4729 | 1271835 | The contract has as general characteristics the rehabilitation of a bridge, through the construction of a walkway in metallic structure, reinforcement of the foundations by micropiles, reinforcement of the remaining structure | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 07-10-2014 | 22-05-2015 | 227 | 90 | 250008.53 | 227903.39 | 1 | 268357.96 | -40454.57 | 84.9251 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the approval of the pss was communicated on 10/27/2014. term extension for 30 days. term extension: 29 days. | existence of less and more works.
4730 | 1271772 | Requalification of the center of Vila de Mira - 1st Phase | 45233140-2 | Roadworks | FALSE | 2014 | 2015 | Portugal | Mira | Coimbra | 6 | 20 | 14-10-2014 | 26-06-2015 | 255 | 210 | 283018 | 244000 | 1 | 236351.08 | 7648.92 | 103.2363 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | revision of prices and work to be done
4731 | 1270309 | The object of the contract is the execution of the contract for "Maintenance Dredging in Barra do Porto da Póvoa de Varzim" . | 45252124-3 | Dredging and pumping works | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 11 | 25-09-2014 | 05-08-2015 | 314 | 75 | 940000 | 742500 | 2 | 798900 | -56400 | 92.9403 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A
4732 | 1268452 | Implementation of a floating cover for the wastewater ponds at the Sotavento sanitary landfill | 45261420-4 | Waterproofing work | FALSE | 2014 | 2015 | Portugal | Loulé | Faro | 8 | N/A | 17-09-2014 | 16-02-2015 | 152 | 41 | 182000 | 166650.9 | 1 | 180836.5 | -14185.6 | 92.1556 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions. | alteration of the location on the anchoring beam of the screen, implying an addition to the geomembrane of the roof of 992m2, not foreseen in the initial tender process.
4733 | 1267763 | 64/ABS/2014 - Leak Repair Contract in Baixo Vouga Lagunar | 45246200-5 | Riverbank protection works | FALSE | 2014 | 2015 | Portugal | Aveiro | Aveiro | 1 | 20 | 29-09-2014 | 21-12-2015 | 448 | 90 | 320332.35 | 192199.42 | 1 | 192199.42 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | lack of security conditions, water level due to winter rains
4734 | 1266542 | Construction of Warehouse for Waste Storage | 45213221-8 | Warehouse stores construction work | FALSE | 2014 | 2015 | Portugal | Portimão | Faro | 8 | 20 | 13-08-2014 | 30-04-2015 | 260 | 90 | 240000 | 184940 | 1 | 184940 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays imputed to the contractor due to financial difficulties.
4735 | 1266074 | 2013.185.01.C1 - C-EF COIMBRA - Remodeling and modernization of the Employment Services service area | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Coimbra | Coimbra | 6 | 20 | 19-09-2014 | 22-01-2015 | 125 | 90 | 340000 | 241283 | 1 | 241283 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | completed works
4736 | 1265388 | Urgent public tender for the contract for emergency intervention in municipal streets damaged by bad weather in March 2013 - Grota do carpet | 45233252-0 | Surface work for streets | FALSE | 2013 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 15 | 12-12-2013 | 17-07-2015 | 582 | 120 | 1281255.7 | 1069100 | 3 | 1060666.66 | 8433.34 | 100.7951 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | article 369 of the "public procurement code".
4737 | 1265346 | Recovery and adaptation of Forte da Graça for the development of cultural activities | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Elvas | Portalegre | 12 | 48 | 03-10-2014 | 02-12-2015 | 425 | 330 | 5440000 | 4623605.95 | 3 | 4610163.09 | 13442.86 | 100.2916 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | * necessity and performance of mortar and whitewash tests to define the materials to be used; * the specificity of the materials to be used, which requires curing times and weather conditions that are different from the materials used in current construction; * the rupture of stocks of materials and the inability of suppliers to produce in a timely manner; * appearance of unidentified elements in the project, namely the wall paintings, making it necessary to adopt measures to preserve them. | there was underwork for the contract worth €13,442.86.
4738 | 1265253 | Construction Pole II and III of CIMO | 45214620-2 | Research and testing facilities construction work | FALSE | 2012 | 2015 | Portugal | Bragança | Bragança | 4 | 24 | 22-02-2013 | 14-12-2015 | 1025 | 300 | 630000 | 545067.84 | 2 | 585462.3 | -40394.46 | 93.1004 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties in supplying materials due to lack of stocks | overwork, errors and omissions
4739 | 1263766 | Contract for the Implementation of the Supply Pipeline for Zibreira | 45231100-6 | General construction work for pipelines | FALSE | 2014 | 2015 | Portugal | Torres Novas | Santarém | 16 | 24 | 19-09-2014 | 27-07-2015 | 311 | 90 | 750000 | 525000.01 | 2 | 525000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements.
4740 | 1260576 | Promotion of energy-environmental efficiency in the indoor pool | 45300000-0 | Building installation work | FALSE | 2014 | 2015 | Portugal | Miranda do Douro | Bragança | 4 | 24 | 25-09-2014 | 20-04-2015 | 207 | 90 | 231000 | 177920.2 | 1 | 177920.2 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather reasons
4741 | 1260153 | Domestic Wastewater Drainage Network in Outeiro da Lagoa | 45232460-4 | Sanitary works | FALSE | 2010 | 2015 | Portugal | Sertã | Castelo Branco | 5 | 15 | 16-01-2014 | 13-03-2015 | 421 | 365 | 1000000 | 856471.75 | 2 | 856471.75 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | safety conditions - climatic | no change
4742 | 1259390 | Urban arrangement of the area surrounding the Cine-Teatro Garrett | 45233161-5 | Footpath construction work | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 30 | 29-09-2014 | 15-07-2015 | 289 | 90 | 304000 | 197803.88 | 1 | 188805.69 | 8998.19 | 104.7658 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4743 | 1258597 | Construction of the Multipurpose Sports Pavilion - Multipurpose Sports Complex | 45212220-4 | Multi-purpose sports facilities construction work | FALSE | 2014 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 01-10-2014 | 21-12-2015 | 446 | 180 | 726387.17 | 631086.93 | 2 | 613119.53 | 17967.4 | 102.9305 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | cessation of the contractual position, alteration of the project and delay in the delivery of materials | changes to the project
4744 | 1258019 | Contract for replacement of water supply networks and lowering of branches, in the Municipality of Amadora - Years 2014/2015". | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Amadora | Lisboa | 11 | 11 | 02-07-2014 | 05-06-2015 | 338 | 300 | 332995 | 199797.01 | 1 | 199797.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the scheduled works were delayed, as a result of constraints found during the course of the project, so the scheduled date for the completion of the contract was extended.
4745 | 1257945 | public tender for the contract for the rehabilitation of the amadora zona media reservoir and the amadora zona alta reservoir. | 45261420-4 | Waterproofing work | FALSE | 2014 | 2015 | Portugal | Oeiras | Lisboa | 11 | 11 | 22-08-2014 | 21-05-2015 | 272 | 240 | 311000 | 177484.02 | 1 | 177484.02 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the project scheduled for the contract in question took place at a good pace, managing to anticipate the expected date for the completion of the contract by a few days
4746 | 1257764 | Hydraulic and paidagistic intervention of the river of hides - S. Sebastião | 45246000-3 | River regulation and flood control works | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 19-09-2014 | 21-05-2015 | 244 | 90 | 938879.75 | 850005.55 | 2 | 845949.05 | 4056.5 | 100.4795 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work - 83 days. following the inspection notice for provisional acceptance (03/18/2015), the contractor had to carry out the necessary repairs, so he was granted a period of 30 days. | existence of underwork corresponding to the non-exhaustion of the quantities of work foreseen in the bill of quantities.
4747 | 1254971 | The main objectives of this contract will be to provide the Bypass chamber with isolating valves and replace the existing ARPOL joint upstream. | 45232460-4 | Sanitary works | FALSE | 2014 | 2015 | Portugal | Aveiro | Aveiro | 1 | 31 | 29-09-2014 | 16-10-2015 | 382 | 240 | 187000 | 174732 | 1 | 182732.02 | -8000.02 | 95.622 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | temporary impossibility of fulfilling the contract due to differences between the diameters of the existing pipe and the flanges planned to be welded on this pipe. | financial rebalancing due to work suspension.
4748 | 1254253 | Execution of all works that are part of the contract to automate modules of the hydro-agricultural exploitation of Mira | 45248000-7 | Construction work for hydro-mechanical structures | FALSE | 2014 | 2015 | Portugal | Aljezur | Beja | 2 | 30 | 16-09-2014 | 08-06-2015 | 265 | 93 | 1454665 | 1299955.49 | 3 | 1299955.49 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | supply of electricity and incompatibility with the management of the irrigation work and provision of vpn mobile communications.
4749 | 1253671 | Expansion of the current Sewer Network - Allotment of Crasto - Ribeira - Ponte de Lima | 45232400-6 | Sewer construction work | FALSE | 2014 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 12 | 25-09-2014 | 28-05-2015 | 245 | 180 | 412000 | 288622.9 | 2 | 288622.9 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | the value of the contract is wrong. the value of the award is 288,622.90
4750 | 1250373 | Construction of the Home for the Elderly and Day Center of São Sebastião | 45215200-9 | Construction work for social services buildings | FALSE | 2014 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 48 | 23-09-2014 | 28-11-2015 | 431 | 330 | 1311235.68 | 1140000 | 3 | 1217402.48 | -77402.48 | 93.642 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4751 | 1250267 | Adaptation and expansion of the Marco de Canaveses elementary school - (school center in Fornos) | 45262800-9 | Building extension work | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 20 | 23-09-2014 | 11-09-2015 | 353 | 240 | 747846 | 624448.37 | 2 | 624448.37 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension in accordance with paragraph b) of article 365 of the "public procurement code".
4752 | 1248212 | Construction of the Palhaça Fair - 2nd Phase | 45213141-3 | Covered market construction work | FALSE | 2012 | 2015 | Portugal | Oliveira do Bairro | Aveiro | 1 | 24 | 25-07-2013 | 26-03-2015 | 609 | 240 | 500000 | 496736.15 | 2 | 488511.36 | 8224.79 | 101.6836 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | there were some suspensions and some extensions in the contract | there was a place for works more and works less
4753 | 1246173 | Contract for the Rehabilitation and Structural Reinforcement of the D. Maria Bridge, in Lagos | 45221119-9 | Bridge renewal construction work | FALSE | 2014 | 2015 | Portugal | Lagos | Faro | 8 | N/A | 21-08-2014 | 06-10-2015 | 411 | 240 | 950000 | 870044.27 | 2 | 1028079.91 | -158035.64 | 84.6281 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | execution of urgent and unpredictable works that required the revision of the execution methodology and the consequent alteration of the contractual term
4754 | 1246072 | Construction of the Business Reception Area in an Urban Environment - Business Incubator in Oliveira do Bairro | 45213150-9 | Office block construction work | FALSE | 2013 | 2015 | Portugal | Oliveira do Bairro | Aveiro | 1 | 15 | 22-01-2014 | 26-03-2015 | 428 | 181 | 280000 | 208999.99 | 1 | 218995.36 | -9995.37 | 95.4358 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | need to change the exterior arrangements, namely the access to the 1st floor and consequently the garden platform of the building, with the need to redo the envisaged solution. | additional work at contractual prices - €3,277.83_x000d_ additional work at agreed prices - €13,869.96_x000d_ underwork - €7,152.42
4755 | 1244136 | construction work number 33/dmpo/dcme/dpe/12 – “geotechnical stabilization of the escarpment located at the back of nos. 112 to 129 of streetinácio pardelhas sanches - bairro da liberdade” | 45111230-9 | Ground-stabilisation work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 03-09-2014 | 29-06-2015 | 299 | 75 | 580209.4 | 324077.25 | 2 | 32199.88 | 291877.37 | 1006.4548 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4756 | 1237945 | Contract for the supply and assembly of cogeneration groups for the S. João da Talha WWTP - CP/O 28/13 | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Loures | Lisboa | 11 | 50 | 30-07-2014 | 19-03-2015 | 232 | 180 | 240000 | 223000 | 1 | 223000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change.
4757 | 1236249 | Alteration and Construction of Annex to the National Guard Post in Castelo de Vide | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2013 | 2015 | Portugal | Castelo de Vide | Portalegre | 12 | 30 | 17-09-2014 | 11-11-2015 | 420 | 240 | 300588 | 224888.19 | 1 | 237110.4 | -12222.21 | 94.8454 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of additional works | execution of additional works
4758 | 1232503 | Rural Village and Campsite of Alvão, Phase II - Requalification of Surroundings - Falperra Dam | 45112710-5 | Landscaping work for green areas | FALSE | 2014 | 2015 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 6 | 16-09-2014 | 07-09-2015 | 356 | 90 | 349177.67 | 296801.43 | 2 | 296801.43 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climatic conditions.
4759 | 1230987 | Baguim do Monte Municipal Pools - Installation of Energy Efficiency Equipment. | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Gondomar | Porto | 13 | 25 | 11-09-2014 | 03-03-2015 | 173 | 90 | 216020 | 173290.62 | 1 | 173290.62 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | according to information filed in the process.
4760 | 1230867 | Rio Tinto Municipal Swimming Pools - Installation of Energy Efficiency Equipment. | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Gondomar | Porto | 13 | 25 | 11-09-2014 | 24-02-2015 | 166 | 90 | 247468 | 170688.58 | 1 | 170688.58 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | following the physical completion of the contract in question, the respective self-measurement of work performed managed to obtain the due dates for the completion of those corresponding physical executions. it happened, however, that the dates relating to the provisional acceptances and the final quotas had to suffer delays, due to vicissitudes.
4761 | 1223489 | Fânzeres Municipal Swimming Pools - Installation of Energy Efficiency Equipment | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Gondomar | Porto | 13 | 25 | 11-09-2014 | 24-02-2015 | 166 | 90 | 217790 | 168819.95 | 1 | 168819.95 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | according to information, filed in the respective process.
4762 | 1222792 | S.Cosme Municipal Swimming Pools - Installation of Energy Efficiency Equipment | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Gondomar | Porto | 13 | 25 | 11-09-2014 | 24-02-2015 | 166 | 90 | 234943 | 181746.37 | 1 | 181746.37 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | according to information filed in the process.
4763 | 1222421 | Medas Municipal Swimming Pools - Installation of Energy Efficiency Equipment | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Gondomar | Porto | 13 | 25 | 11-09-2014 | 03-03-2015 | 173 | 90 | 217715 | 159788.63 | 1 | 159788.63 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | under the terms of the information according to information provided, filed in the procedure.
4764 | 1214265 | Contract for the Execution of Measures for the Rational Use of Energy and Energy-Environmental Efficiency in Municipal Sports Equipment – ​​Covered Municipal Swimming Pool and Gymnasium | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Alijó | Vila Real | 19 | 10 | 03-07-2014 | 02-02-2015 | 214 | 184 | 197573.58 | 178420.5 | 1 | 177631.4 | 789.1 | 100.4442 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed 3 days before its contractual deadline | no speed bumps were fitted.
4765 | 1213056 | Carrying out the contract for the Requalification of Communication Routes in Macinhata do Vouga and Valongo do Vouga, as described in the Tender Documents | 45233251-3 | Resurfacing works | FALSE | 2014 | 2015 | Portugal | Águeda | Aveiro | 1 | 36 | 09-09-2014 | 20-10-2015 | 406 | 60 | 241116.21 | 183881.26 | 1 | 159574.37 | 24306.89 | 115.2323 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the counting of the execution period of the project began with the approval of the pss; suspension of work; the project was provisionally received after correction of work defects detected during the inspection for the purposes of provisional acceptance. | execution of additional work; existence of underworks.
4766 | 1212911 | Contract for the expansion of floor -1 of the professional training center for the footwear industry – s. John of the wood | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | São João da Madeira | Aveiro | 1 | 14 | 01-08-2014 | 17-04-2015 | 259 | 195 | 300000 | 299817.32 | 2 | 344383.75 | -44566.43 | 87.0591 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension - 39 days - to carry out additional work | execution of additional work
4767 | 1207510 | Miuzela Market Square and Civic Center | 45000000-7 | Construction work | FALSE | N/A | 2015 | Portugal | Almeida | Guarda | 9 | N/A | 25-01-2010 | 05-06-2015 | 1957 | 730 | N/A | 793334.14 | 2 | 749227.28 | 44106.86 | 105.887 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the process of termination of the contractual position, difficulties in acquiring materials and the lack of electrical power necessary for testing hvac equipment | existence of underworks
4768 | 1204210 | Construction of the Fire Station building. | 45216121-8 | Fire station construction work | FALSE | 2014 | 2015 | Portugal | Barcelos | Braga | 3 | 30 | 09-09-2014 | 30-09-2015 | 386 | 240 | 1249728 | 1197922.07 | 3 | 1176683.35 | 21238.72 | 101.805 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the deadline granted by the owner of work due to adverse weather conditions and the difficulty of the successful tenderer in supplying some materials, given that the contract foresaw the application of some less conventional materials. | works suppressed due to the almost simultaneous construction of the 2nd phase of the barracks.
4769 | 1204150 | Execution of work to improve access to Casais Formigos and Casal Vidigal, as well as providing them with adequate infrastructure, promoting quality of life and upgrading the urban space. | 45233200-1 | Various surface works | FALSE | 2014 | 2015 | Portugal | Entroncamento | Santarém | 16 | 24 | 08-08-2014 | 30-09-2015 | 418 | 180 | 450000 | 342138.51 | 2 | 326903.65 | 15234.86 | 104.6604 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | execution work on the roundabout provided for in the contract by indication of the owner of the project, a fact that inevitably postponed the deadline for completion of the project
4770 | 1202721 | Execution of the infrastructures of the Business and Industrial Park of Vidigueira (phase 1) and creation of a nest of companies | 45111290-7 | Primary works for services | FALSE | 2010 | 2015 | Portugal | Vidigueira | Beja | 2 | 40 | 15-06-2011 | 01-06-2015 | 1447 | 300 | 885757.5 | 785549.14 | 2 | 649020.67 | 136528.47 | 121.0361 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | there was underwork
4771 | 1201041 | Qualification contract in Rural Space at street of Centro Social - Azervadinha | 45233200-1 | Various surface works | FALSE | 2013 | 2015 | Portugal | Coruche | Santarém | 16 | 24 | 08-07-2013 | 26-05-2015 | 687 | 150 | 206757.84 | 154659.37 | 1 | 154659.37 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of works - 50 days (works to replace the water pipe by the intermunicipal company "águas do ribatejo") and suspension of works - 52 days (climate conditions)
4772 | 1197242 | Amieira Road repaving contract | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Coruche | Santarém | 16 | 24 | 20-09-2013 | 26-05-2015 | 613 | 90 | 252348.39 | 159644.56 | 1 | 159644.56 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of works - weather conditions.
4773 | 1188500 | Water supply, collection and treatment of wastewater and rainwater in Bairro Mouzinho de Albuquerque, Angústias, in the city of Horta | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Horta | Região Autónoma dos Açores | 15 | 30 | 17-03-2014 | 13-08-2015 | 514 | 365 | 1224984.27 | 699000 | 2 | 699000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period of the project
4774 | 1185488 | The purpose of the contract is to fully implement the layout and infrastructure of the designated industrial zone of Queirã. | 45211360-0 | Urban development construction work | FALSE | 2014 | 2015 | Portugal | Vouzela | Viseu | 20 | 15 | 22-08-2014 | 02-10-2015 | 406 | 180 | 350000 | 245000.01 | 1 | 166627.41 | 78372.6 | 147.0346 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | the contract was executed within the established contractual period. | the change in the value of the project is the result of one less set of works.
4775 | 1175251 | Execution contract for the collection and treatment equipment at Gaviãozinho | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Chamusca | Santarém | 16 | 24 | 14-08-2014 | 02-09-2015 | 384 | 90 | 225000 | 195938.81 | 1 | 187749.51 | 8189.3 | 104.3618 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items
4776 | 1175077 | Different tours in the city - Mobility for all - South Entrance | 45432110-8 | Floor-laying work | FALSE | 2014 | 2015 | Portugal | Bragança | Bragança | 4 | 20 | 27-08-2014 | 18-09-2015 | 387 | 180 | 215000 | 183795.72 | 1 | 183795.72 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions
4777 | 1166651 | Construction of the sports space in Vila da Ponte | 45000000-7 | Construction work | FALSE | 2011 | 2015 | Portugal | Sernancelhe | Viseu | 20 | 42 | 09-08-2014 | 27-05-2015 | 291 | 180 | 306560.59 | 258455.22 | 2 | 254621.94 | 3833.28 | 101.5055 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | final cleaning of the project | more work and underwork
4778 | 1166389 | Construction of the Ferreirim riverside bridge and footpath | 45221113-7 | Footbridge construction work | FALSE | 2013 | 2015 | Portugal | Sernancelhe | Viseu | 20 | 23 | 08-08-2014 | 25-06-2015 | 321 | 300 | 538076.85 | 322846.12 | 2 | 310096.12 | 12750 | 104.1116 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | work cleaning | underwork
4779 | 1164780 | Construction of Access Path to the Bird Observatory | 45233200-1 | Various surface works | FALSE | 2013 | 2015 | Portugal | Sernancelhe | Viseu | 20 | 23 | 08-08-2014 | 25-06-2015 | 321 | 240 | 361948.07 | 256726.77 | 2 | 223539.04 | 33187.73 | 114.8465 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | cleaning of the project | underwork
4780 | 1162059 | Reconversion of the Industrial Park into the Carameleiro Business Park" along the former EN 236-1, located in Carameleiro, parish and municipality of Figueiró dos Vinhos | 45111290-7 | Primary works for services | FALSE | 2014 | 2015 | Portugal | Figueiró dos Vinhos | Leiria | 10 | 20 | 30-07-2014 | 05-11-2015 | 463 | 150 | 433000 | 349857.9 | 2 | 346687.55 | 3170.35 | 100.9145 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4781 | 1160743 | Execution, under the terms of the specifications and the awarded proposal, of the contract for “Improvement of the southern section of Tornos – 3rd Phase” | 45247110-4 | Canal construction | FALSE | 2014 | 2015 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 50 | 25-08-2014 | 25-03-2015 | 212 | 90 | 235000 | 176595.61 | 1 | 174531.75 | 2063.86 | 101.1825 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | part of the project on the canal only started on october 15th due to issues associated with the need for irrigation in accordance with clause 9 of the tender specifications.
4782 | 1160544 | Execution, under the terms of the specifications and the awarded proposal, of the contract for “Recovery of the Levada Calheta-Ponta do Sol – 2nd Phase” | 45247110-4 | Canal construction | FALSE | 2014 | 2015 | Portugal | Ponta do Sol | Região Autónoma da Madeira | 14 | 50 | 25-08-2014 | 05-06-2015 | 284 | 120 | 500000 | 388171.27 | 2 | 388171.27 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | part of the project on the canal only started on october 15th due to issues associated with the need for irrigation in accordance with clause 9 of the tender specifications. occasionally the need to pass water for irrigation conditioned the yield.
4783 | 1156723 | Completion of the works to improve the Side Corridors and the South Body of the Setúbal 2nd Seafood Market Building | 45213141-3 | Covered market construction work | FALSE | 2013 | 2015 | Portugal | Setúbal | Setúbal | 17 | 20 | 06-08-2014 | 24-04-2015 | 261 | 150 | 220000 | 165000.01 | 1 | 166830.01 | -1830 | 98.9031 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | due to more works | due to more works
4784 | 1156032 | Realization of the contract "Allotment adjacent to the business park of Figueiró dos Vinhos", located in Carameleiro, Parish and Municipality of Figueiró dos Vinhos | 45111290-7 | Primary works for services | FALSE | 2014 | 2015 | Portugal | Figueiró dos Vinhos | Leiria | 10 | 24 | 23-07-2014 | 05-11-2015 | 470 | 180 | 301000 | 228003.04 | 1 | 226936.07 | 1066.97 | 100.4702 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4785 | 1154928 | Execution of the Contract for New Broadband Technological Networks | 45232332-8 | Ancillary works for telecommunications | FALSE | 2014 | 2015 | Portugal | Vila Real | Vila Real | 19 | 30 | 21-07-2014 | 15-06-2015 | 329 | 180 | 318051.54 | 211111.11 | 1 | 198882.98 | 12228.13 | 106.1484 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | atmosphere conditions. | underwork.
4786 | 1150380 | Execution of the contract for the “Improvement of the EN17 – EM554 (Mesquitela)”, located in the parish of Mesquitela, in the municipality of Celorico da Beira. | 45233220-7 | Surface work for roads | FALSE | 2014 | 2015 | Portugal | Celorico da Beira | Guarda | 9 | 10 | 14-08-2014 | 22-04-2015 | 251 | 90 | 215000 | 189004.8 | 1 | 187338.1 | 1666.7 | 100.8897 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with the contractual term by the contractor. | there was underwork.
4787 | 1150188 | "Expansion of the Home for the Elderly and SAD of the Social and Parish Center of S. Mamede de Agrochão" | 45215212-6 | Retirement home construction work | FALSE | 2014 | 2015 | Portugal | Vinhais | Bragança | 4 | 20 | 01-07-2014 | 06-10-2015 | 462 | 180 | 432000 | 378914.06 | 2 | 378914.06 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | change of work plan due to weather conditions.
4788 | 1149205 | Barrosas Culture House - Construction | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2014 | 2015 | Portugal | Felgueiras | Porto | 13 | 24 | 12-08-2014 | 13-11-2015 | 458 | 120 | 199994.4 | 198647.8 | 1 | 190984.25 | 7663.55 | 104.0127 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some adverse situations during the execution of the project | smaller quantities executed.
4789 | 1147960 | Pe_14011_cne - national public tender for the execution of the contract for the reconstruction of the sports cover of the High school of martins sarmento, in guimarães | 45214200-2 | Construction work for school buildings | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 35 | 06-08-2014 | 06-05-2015 | 273 | 150 | 335600 | 310000 | 2 | 306726.4 | 3273.6 | 101.0673 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A
4790 | 1147813 | Execution of the design and construction works for the Contract designated as "Operational Building in Modular Construction at the WWTP of Olhalvas" | 45223810-7 | Prefabricated constructions | FALSE | 2014 | 2015 | Portugal | Leiria | Leiria | 10 | 29 | 24-07-2014 | 26-06-2015 | 337 | 180 | 240000 | 228391.81 | 1 | 224503.24 | 3888.57 | 101.7321 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | conciliation with work related to another endeavor | works not performed
4791 | 1147760 | Network of urban cycle paths - ecocaminho - section between the peripheral road and the parallel roads, with a length of 2.8 km. | 45233162-2 | Cycle path construction work | FALSE | 2014 | 2015 | Portugal | Maia | Porto | 13 | 32 | 12-08-2014 | 29-06-2015 | 321 | 150 | 331287 | 231379.08 | 1 | 225379.07 | 6000.01 | 102.6622 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | it had a graceful extension of the deadline for another 30 days, due to the unfavorable weather conditions that made it impossible for the normal evolution of the projects in the months of september, october and november. the date of the last inspection and measurement notice was march 10, 2015, with the provisional receipt being made on april 30, 2015, at the initiative of this city council. | the value of the contract was the result of the measurements carried out.
4792 | 1146613 | Adaptation of building for National Guard post - Alpendorada e Matos - Marco de Canaveses | 45216110-8 | Construction work for buildings relating to law and order | FALSE | 2014 | 2015 | Portugal | Marco de Canaveses | Porto | 13 | 30 | 07-08-2014 | 21-12-2015 | 501 | 365 | 595403.75 | 413958.18 | 2 | 408328.49 | 5629.69 | 101.3787 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the end of the undertaking was anticipated.
4793 | 1145545 | Construction of a Rural Park in Cepães | 45233260-9 | Pedestrian ways construction work | FALSE | 2014 | 2015 | Portugal | Fafe | Braga | 3 | 30 | 07-08-2014 | 13-04-2015 | 249 | 90 | 222855.7 | 208896.41 | 1 | 208895.8 | 0.61 | 100.0003 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change to the deadline was due to the suspension of the contract, due to weather conditions | there were no changes to the value of the project
4794 | 1145155 | The contract includes the remodeling of the existing school building, including the execution of demolitions, structures. | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Mértola | Beja | 2 | 30 | 07-08-2014 | 29-10-2015 | 448 | 270 | 488829.05 | 338376.02 | 2 | 338260.55 | 115.47 | 100.0341 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | no change | underwork
4795 | 1142737 | Execution, under the terms of the specifications and the awarded proposal, of the contract for “Recovery of the Levada Machico-Caniçal – 2nd Phase” | 45247110-4, 45262310-7 | Canal construction, Reinforced-concrete work | FALSE | 2014 | 2015 | Portugal | Machico | Região Autónoma da Madeira | 14 | 50 | 07-08-2014 | 07-04-2015 | 243 | 120 | 347000 | 252791.6 | 2 | 227226.24 | 25565.36 | 111.2511 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | the rainfall recorded in the months of september, october, november and december made it impossible for the contractor to proceed with waterproofing work inside the manholes, carrying out welding of the hdpe pipes and carrying out excavations/filling in the ditches. | underwork worth €25,565.36 under paragraph 2 of article 379
4796 | 1142136 | National public tender for the execution of the contract for the rehabilitation of the air conditioning system of the building of the department of services in the Alentejo region, in Évora | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2014 | 2015 | Portugal | Évora | Évora | 7 | 31 | 30-07-2014 | 01-07-2015 | 336 | 182 | 324000 | 298953.44 | 2 | 304993.14 | -6039.7 | 98.0197 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the term contractually stipulated for the contract. | there was a need to issue 3 execution orders to carry out work classified as detectable errors and omissions in the contract formation phase, with 50% responsibility for the project client. the issuance of the execution orders complied with the legal procedures, also complying with the legally established limits.
4797 | 1142103 | Contract work for the New E-Learning Café in the Porto Botanical Garden (Casa Salabert) | 45453100-8 | Refurbishment work | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | 24 | 04-08-2014 | 04-06-2015 | 304 | 150 | 375000 | 346465.82 | 2 | 370685.72 | -24219.9 | 93.4662 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | free term extensions, approved by order of the management board, on 12/30/2014 and 03/06/2015. | existence of additional work, supply of errors and omissions and less referenced work.
4798 | 1142068 | Execution of all works that are part of the construction contract for the Samouqueiro reservoir | 45247270-3 | Reservoir construction works | FALSE | 2013 | 2015 | Portugal | Odemira | Beja | 2 | 31 | 21-04-2014 | 14-05-2015 | 388 | 172 | 157500 | 154541.64 | 1 | 154541.64 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | constraints caused by the irrigation campaign
4799 | 1139616 | Alter do Chão archaeological site - Coverage of Casa da Medusa | 45223110-0 | Installation of metal structures | FALSE | 2014 | 2015 | Portugal | Alter do Chão | Portalegre | 12 | 12 | 01-08-2014 | 14-07-2015 | 347 | 80 | 346876.47 | 336632.05 | 2 | 333972.66 | 2659.39 | 100.7963 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to weather conditions. | underwork.
4800 | 1137623 | Requalification of the Installations of the Training Center Specialized in forest fires of the Lousã National Firefighters School | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Lousã | Coimbra | 6 | 20 | 30-07-2014 | 02-02-2015 | 187 | 150 | 230000 | 203684.78 | 1 | 203684.78 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | no changes were made to the execution period of the project.
4801 | 1136997 | Contract for the Restoration of the FBAUP Exhibition Pavilion | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 24 | 24-07-2014 | 26-03-2015 | 245 | 150 | 315000 | 299492.65 | 2 | 284708.4 | 14784.25 | 105.1928 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | referenced deadline extensions. | existence of underwork.
4802 | 1135981 | Contract for the interior remodeling of spaces intended for postgraduate studies at FMUP | 45454000-4 | Restructuring work | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | 24 | 23-07-2014 | 27-03-2015 | 247 | 140 | 402700 | 395701.54 | 2 | 412598.74 | -16897.2 | 95.9047 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | referenced deadline extension. | existence of more works.
4803 | 1135373 | Rehabilitation of 3 properties, 6 dwellings under the Pró-Habita program in Portalegre - Contract nº. two | 45211340-4 | Multi-dwelling buildings construction work | FALSE | 2014 | 2015 | Portugal | Portalegre | Portalegre | 12 | 20 | 29-07-2014 | 06-11-2015 | 465 | 300 | 399000 | 316958.82 | 2 | 316958.73 | 0.09 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension | rounding value
4804 | 1134054 | Construction of the Sports Zone of Vila Meã (1st Phase) - Secondary Field Zone and Consolidation of Slopes. | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2013 | 2015 | Portugal | Amarante | Porto | 13 | 30 | 21-07-2014 | 21-07-2015 | 365 | 270 | 812495.79 | 704489.29 | 2 | 553128.84 | 151360.45 | 127.3644 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed 64 days ahead of the contractual execution period | work not carried out because they were considered unnecessary in the amount of €151,241.46
4805 | 1133842 | Rural electrification contract in the parishes of Ourique and Panoias | 45310000-3 | Electrical installation work | FALSE | 2014 | 2015 | Portugal | Ourique | Beja | 2 | N/A | 24-07-2014 | 02-11-2015 | 466 | 180 | 250366.75 | 213767.63 | 1 | 213767.63 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | reasons not attributable to the contractor, "the contract has been concluded, only the assembly of the transformers is pending to proceed with the connection of the installations, they are in the phase of handing over the infrastructures, to edp" (provisional delivery notice that affected or prevented determine the progress of the project) | alteration of the layout of the lamt, so that the project would not stop and that power could be supplied to the transformer station. instead of having a straight route, two curves were made so that the crossing of the ic1 was in the same place, due to the authorizations obtained by edp. this resulted in the need for a number of different posts, as well as their type, which were larger due to the new angles.
4806 | 1130821 | Reorganization of the space where the Arganil weekly fair currently takes place. | 45213142-0 | Open-air market construction work | FALSE | 2012 | 2015 | Portugal | Arganil | Coimbra | 6 | 24 | 29-05-2014 | 17-06-2015 | 384 | 150 | 224000 | 206244.37 | 1 | 202488.9 | 3755.47 | 101.8547 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | a) of article 366 of the "public procurement code" due to weather conditions | according to the progress of the projects and the final measurements, it was verified that it was not necessary to carry out and/or complete the execution of works foreseen in articles 1.21; article 2.9, article 3.1.4., article 3.5.1, article 3.6, article 3.15 and article 5.10.5 making a total value of €3,755.47 underwork, fulfilling the purpose of the contract.
4807 | 1128546 | Floor Rehabilitation | 45233142-6 | Road-repair works | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 11 | 27-05-2014 | 09-10-2015 | 500 | 60 | 349200 | 261900.01 | 2 | 243918.01 | 17982 | 107.3721 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | an inspection of the project was carried out on 23/11/2014 in which it was considered in conditions to be provisionally received. the respective provisional acceptance notice was drawn up on 05/12/2014. | existence of underworks
4808 | 1128042 | Rehabilitation of distribution ducts and residential branches - Póvoa da Lomba ZMC, Lemede ZMC, Tocha ZMC and Praia da Tocha ZMC | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 20 | 22-07-2014 | 18-12-2015 | 514 | 180 | 520000 | 378975.7 | 2 | 378975.7 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | extension due to weather conditions
4809 | 1127786 | Requalification and expansion of the water and sanitation network - 2014 | 50000000-5 | Repair and maintenance services | FALSE | 2014 | 2015 | Portugal | Caldas da Rainha | Leiria | 10 | N/A | 14-07-2014 | 21-12-2015 | 525 | 365 | 388298.64 | 209931.96 | 1 | 197352.12 | 12579.84 | 106.3743 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | wait for povt application approval | there was no need to carry out all the planned work
4810 | 1127274 | Intervention project on the coast of Marinha Grande | 45243000-2 | Coastal-defence works | FALSE | 2014 | 2015 | Portugal | Marinha Grande | Leiria | 10 | 20 | 14-07-2014 | 28-10-2015 | 471 | 45 | 219150 | 180747.94 | 1 | 171935.62 | 8812.32 | 105.1254 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | facts attributable to the owner of the project | due to job suppression
4811 | 1120968 | Execution of construction work on a building on crossstreet of Boa-Hora à Ajuda, n.ºs 25-25A | 45211000-9 | Construction work for multi-dwelling buildings and individual houses | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 16-11-2012 | 08-05-2015 | 903 | 540 | 450000 | 398180.8 | 2 | 405632.54 | -7451.74 | 98.1629 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the causes of alterations to the execution period of the project are related, essentially, to unforeseen events that resulted in delays in the execution of the projects not attributable to the owner of the project. | more work and underwork.
4812 | 1120912 | Execution of works for the rehabilitation of Elementary School No. 19, Urban Rehabilitation Area of ​​West Lisbon, parish of Ajuda | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 07-02-2013 | 14-05-2015 | 826 | 240 | 1000000 | 747404.83 | 2 | 1069245.34 | -321840.51 | 69.9002 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | the causes of alterations to the execution period of the project are essentially related to unforeseen circumstances that resulted in delays in the execution of the projects not attributable to the owner of the project due to unforeseen alterations to the structural project and even others that are the responsibility of the infrastructure concessionaires, not included in the undertaking, but conditions for its progression. | overwork, underwork, and errors and omissions supply work.
4813 | 1119781 | 2013.086.02.C1 - SF Alverca - Facade and Roof Remodeling | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 21 | 25-03-2014 | 25-03-2015 | 365 | 60 | 270000 | 214256.18 | 1 | 221942.94 | -7686.76 | 96.5366 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | extra work
4814 | 1117539 | Execution of the contract for Environmental Enhancement and Improvement of Citizens' Quality of Life | 45232130-2 | Storm-water piping construction work | FALSE | 2009 | 2015 | Portugal | Freixo Espada a Cinta | Bragança | 4 | 30 | 03-03-2010 | 24-03-2015 | 1847 | 530 | 2900000 | 2446714.37 | 3 | 2606616.28 | -159901.91 | 93.8655 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension documents | more work, underwork and price revisions
4815 | 1116990 | Requalification of CM 1038, Section from Barracão to the limit of the Municipality of Leiria | 45233140-2 | Roadworks | FALSE | 2011 | 2015 | Portugal | Leiria | Leiria | 10 | 35 | 01-07-2014 | 28-04-2015 | 301 | 270 | 1676782 | 1245000 | 3 | 1194986.3 | 50013.7 | 104.1853 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no deadline changes | underwork
4816 | 1116773 | Execution of works to remodel and expand the WWTP of Benquerença in the municipality of Penamacor | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2014 | 2015 | Portugal | Penamacor | Castelo Branco | 5 | 24 | 17-06-2014 | 27-02-2015 | 255 | 210 | 750000 | 594933.88 | 2 | 594933.88 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2015-02-28 - (2015-02-08 + 20 days)
4817 | 1114613 | Asmal house construction contract - socio-occupational forum for teenagers (13-17 years old) (cao) | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Loulé | Faro | 8 | 20 | 25-06-2014 | 16-02-2015 | 236 | 180 | 271500 | 199905.4 | 1 | 210767.66 | -10862.26 | 94.8463 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of extra work and correction of errors and omissions | execution of extra work and correction of errors and omissions
4818 | 1111703 | Refurbishment of building for installation of Kindergarten | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2012 | 2015 | Portugal | Montijo | Setúbal | 17 | 40 | 12-05-2014 | 21-07-2015 | 435 | 270 | 310084.04 | 255410 | 2 | 255410 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A | the reason for the delay in completing the project was the delay in the delivery of some specific materials by the manufacturers, namely aluminum frames and laminated double glazing, which prevented the building from being closed (windows and exterior doors).
4819 | 1111085 | Contract for the Repaving of streetNossa Senhora do Pilar - Parish of Fajã de Cima and Requalification of a Section of streetde São Gonçalo - Parish of São Pedro/Fajã de Baixo - Ponta Delgada | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 48 | 02-07-2014 | 21-05-2015 | 323 | 180 | 600000 | 450000.01 | 2 | 444800 | 5200.01 | 101.1691 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | underwork.
4820 | 1110487 | Contract for the Remodeling of the Cold Water Production System - HVAC at the Belém Cultural Center | 45331230-7 | Installation work of cooling equipment | FALSE | 2014 | 2015 | Portugal | Lisboa | Lisboa | 11 | 48 | 02-06-2014 | 18-05-2015 | 350 | 140 | 900000 | 796000 | 2 | 796000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | for reasons of operating the events held at the meeting center and show centre, it was not possible to put the previous equipment out of service on the scheduled date, forcing it to be carried out at a later date.
4821 | 1109169 | Execution of the pedestrian overpass of Fort da Casa | 45233261-6 | Pedestrian overpass construction work | FALSE | 2013 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 15 | 14-06-2013 | 12-01-2015 | 577 | 120 | 1100000 | 1092879.22 | 3 | 1088103.22 | 4776 | 100.4389 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | deadline deviation from the date of completion of the project | approval of underwork to the awarded contract
4822 | 1105917 | Contract for the rehabilitation and automation of the water intake from the Odivelas dam | 45240000-1 | Construction work for water projects | FALSE | 2014 | 2015 | Portugal | Ferreira do Alentejo | Beja | 2 | 30 | 16-06-2014 | 20-05-2015 | 338 | 150 | 630000 | 607000 | 2 | 600996.57 | 6003.43 | 100.9989 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for carrying out the project was longer than contractually established due to the occurrence of rains that greatly conditioned the execution of the projects, as well as the unforeseen delay in the supply of some equipment. | bearing in mind that, in accordance with the provisions of the specifications, the contractor is remunerated according to the application of the unit prices, established in the contract for each type of work to be carried out, to the quantities of these works actually carried out, it was verified that the measurement of the projects executed proved to be lower than expected in the patented project in the competition.
4823 | 1104525 | Execution of the Urban Park of Quinta da Flamenga - Phase A - Vialonga | 45112711-2 | Landscaping work for parks | FALSE | 2014 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 23-06-2014 | 09-03-2015 | 259 | 150 | 286000 | 224561.16 | 1 | 224561.16 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | deviation of 30 days for completion of the contract.
4824 | 1104462 | Reconversion of the sports field in Bairro Novo de Nandufe | 45236119-7 | Repair work on sports fields | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 11 | 25-06-2014 | 06-07-2015 | 376 | 60 | 330000 | 307064.96 | 2 | 292797.26 | 14267.7 | 104.8729 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | there was a change in the execution period, due to the fact that the road outside the project, accessing the playground, was damaged due to the passage of equipment for the execution of the project | existence of works
4825 | 1103496 | Dredging work that proves necessary to remove the maximum amount of 450,000 m3 of sediments and respective immersion in the places indicated in the execution project | 45252124-3 | Dredging and pumping works | FALSE | 2013 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 31 | 18-06-2014 | 27-10-2015 | 496 | 730 | 1350000 | 1273500 | 3 | 1235478.68 | 38021.32 | 103.0775 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | partially transcribing the fourth clause of the contract in question: “the effectiveness of this contract is subordinated … and it remains in force until the maximum number of dredged items to be removed set out in the body of the first clause above is satisfied, or after it is the maximum period of 24 months from the assignment or approval of the pss.” | due to price revision.
4826 | 1102553 | Replacement of the pavement of the paths on the side where the irrigation network ditch was made, with reinforcement across the entire width of the platform with a wearing course in bituminous concrete | 45233220-7 | Surface work for roads | FALSE | 2014 | 2015 | Portugal | Alfandega da Fé | Bragança | 4 | 15 | 19-06-2014 | 03-02-2015 | 229 | 30 | 250000 | 189999 | 1 | 189999 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the project deadline | there were no changes to the project deadline
4827 | 1101277 | Contract for the Requalification of the Areas Surrounding the Monastery of Arouca - Cafeteria in the Park and Urban Arrangement of the Area Surrounding Pombal | 45212423-7 | Cafeteria construction work | FALSE | 2013 | 2015 | Portugal | Arouca | Aveiro | 1 | 30 | 20-06-2014 | 23-09-2015 | 460 | 90 | 369854.7 | 331044.53 | 2 | 329988.57 | 1055.96 | 100.32 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay attributable to the contractor. | existence of deleted works.
4828 | 1099126 | The object of this contract is the execution, by the second parties to the first party, of the contract for the «Conclusion of the Urban Arrangement of the streets Adjacent to the Center of the Village | 45211360-0 | Urban development construction work | FALSE | 2014 | 2015 | Portugal | Carregal do Sal | Viseu | 20 | 20 | 22-05-2014 | 15-09-2015 | 481 | 240 | 650000 | 583521.03 | 2 | 553820.44 | 29700.59 | 105.3629 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | extensions requested by the contractor | correct measurements
4829 | 1098030 | Improvement of street layouts in several parishes of the municipality | 45233223-8 | Carriageway resurfacing works | FALSE | 2014 | 2015 | Portugal | Guimarães | Braga | 3 | 20 | 13-06-2014 | 16-01-2015 | 217 | 120 | 1310828.07 | 991513.35 | 2 | 936993.54 | 54519.81 | 105.8186 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underwork due to the foreseen quantities not being used up.
4830 | 1097807 | Energy Contract – Rational Use of Energy and Energy-Environmental Efficiency in Municipal Sports Facilities - Covered Swimming Pool and Sports Pavilion in Tabuaço. | 45315000-8 | Electrical installation work of heating and other electrical building-equipment | FALSE | 2014 | 2015 | Portugal | Tabuaço | Viseu | 20 | 12 | 11-06-2014 | 30-12-2015 | 567 | 120 | 211532.4 | 191695.82 | 1 | 191329.44 | 366.38 | 100.1915 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the lack of planning by the contractor in the acquisition of the different equipment to be installed on site, as well as the lack of definition by the municipality and the design team of the initial project of the project in defining the type and model of coverage of the water plan to be installed, whether fixed or mobile, taking into account their impact on the property's architecture, as well as on the technical and aesthetic definition of the chimney flue layout, they caused delays in the project that deserved extensions. | excess measurement in the quantity map of the contract for a circulatory pump, that is, circulatory pump not necessary for the installation because it is too much.
4831 | 1097011 | Construction of the Headquarters of the L’Atitudes Association and the Europe Direct Office | 45262700-8 | Building alteration work | FALSE | 2014 | 2015 | Portugal | Castelo Branco | Castelo Branco | 5 | 14 | 30-05-2014 | 05-03-2015 | 279 | 120 | 358817.65 | 282156.11 | 2 | 282024.11 | 132 | 100.0468 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | - demolition works lasted much longer than expected, as they did not obtain the initially expected yields, given their complexity; - difficulties in carrying out the project due to the atypical climate; - execution of partition work in an integrated system with a much longer duration than expected, due to their complexity. | underwork result from article 1.9.1, €117.00 and article 1.9.4, €15.00, which had a measurement error on the competition map. article 1.9.1, "supply and execution of painting with plastic paint, in the colors chosen by the developer, in the necessary coats, on interior walls...", will be equal to the total area of ​​interior wall covering to be painted , that is, the sum of article 1.6.1.1, 720 m2 and article 1.6.1.2, 46 m2, being the total 766.00 m2. article 1.9.4, "supply and execution of painting with plastic paint suitable for exteriors, in the colors to be chosen by the client of the project, in the necessary coats, on exterior walls over plaster,...", will be equal to the total area of ​​coating of exterior walls to be painted, being the same as article 1.6.2.1 with an area of ​​325.00m2.
4832 | 1096128 | contract for "rehabilitation and improvement of the branch of e.r. nº 1-2ª, in the sections between the junction with street of arrabalde, s. sebastião, and the intersection with estrada de sta. margarida | 45232451-8 | Drainage and surface works | FALSE | 2013 | 2015 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 24 | 28-04-2014 | 30-10-2015 | 550 | 150 | 450000 | 444750 | 2 | 449502.4 | -4752.4 | 98.9427 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4833 | 1095240 | Completion of the Domestic Wastewater Drainage Network in Vila Franca do Rosário | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Mafra | Lisboa | 11 | N/A | 06-01-2014 | 09-02-2015 | 399 | 90 | 265000 | 197119.61 | 1 | 197119.61 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions
4834 | 1095214 | It foresees the construction of 6.8 km of gravity flow collectors and two elevating pipelines of approximately 0.5 km in length. | 45232400-6 | Sewer construction work | FALSE | 2014 | 2015 | Portugal | Mafra | Lisboa | 11 | 20 | 29-05-2014 | 07-08-2015 | 435 | 210 | 620000 | 517056.87 | 2 | 512391.26 | 4665.61 | 100.9106 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | some conditions relating to the availability of land | works less
4835 | 1094482 | Execution of the construction contract for the Seda Museum Nucleus of Freixo de Espada à Cinta | 45212320-5 | Construction work for buildings relating to artistic performances | FALSE | 2011 | 2015 | Portugal | Freixo Espada a Cinta | Bragança | 4 | 20 | 12-09-2011 | 06-10-2015 | 1485 | 540 | 928000 | 556930.05 | 2 | 556049.32 | 880.73 | 100.1584 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | approved by the court of auditors; change of aedpa premises; climatic conditions. | underwork
4836 | 1094116 | Urban Arrangement Contract at the Asprela Pole | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | 30 | 04-06-2014 | 05-05-2015 | 335 | 210 | 900000 | 798473.45 | 2 | 787321.46 | 11151.99 | 101.4164 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | said deadline extensions. | existence of extra or underwork and supply of errors and omissions. maintenance work on green and paved spaces, provided for in the project plan, will not be carried out.
4837 | 1088811 | Energy Efficiency Contract at Municipal Swimming Pools in Lousada | 45331200-8 | Ventilation and air-conditioning installation work | FALSE | 2014 | 2015 | Portugal | Lousada | Porto | 13 | 21 | 03-06-2014 | 23-02-2015 | 265 | 90 | 295815 | 179289.01 | 1 | 179289.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | in centralized technical management, it was necessary to obtain clarifications and agreements with the supplier. the programming of the entire management had to be adjusted in order to include more technical points that were not foreseen.
4838 | 1086894 | E201401 - Construction of the Malhada de Cambarinho Dam | 45247220-8 | Weir construction work | FALSE | 2014 | 2015 | Portugal | Vouzela | Viseu | 20 | 12 | 29-05-2014 | 30-07-2015 | 427 | 120 | 250300 | 175000.01 | 1 | 167725.9 | 7274.11 | 104.3369 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the extension referred to above is essentially the result of the dry period, atypical in 2014, which led to the asnelo stream maintaining a remarkable flow for this period of the year, which resulted in several temporary interruptions to the project and that the present extension aimed to reset. | the decrease in the value of the project results from the following: "since the initially proposed solution was not considered, aimed at maintaining the usufruct of water for irrigation in two plots downstream from the dam, the project on laying the pipes, valves and maneuvering boxes referred to in headings 2.2 was suppressed. 5.4, ​​2.2.5.6 and 2.2.6.7, respectively. regarding the non-execution of the remaining works, this is due to the physical impossibility of carrying them out, as defined in the initial part of article 379.º of the pcc, approved by decree-law no. 18/2008, of 29 january, in your current wording."
4839 | 1085168 | It consists of the coercive demolition of buildings, PER buildings and other annexed structures, as well as the execution of cleanings and demolitions in municipal spaces, in the municipality of Amadora | 45110000-1 | Building demolition and wrecking work and earthmoving work | FALSE | 2014 | 2015 | Portugal | Amadora | Lisboa | 11 | 21 | 28-05-2014 | 20-04-2015 | 327 | 540 | 349850 | 209911 | 1 | 209911 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A
4840 | 1085048 | building renovation | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 11 | 26-05-2014 | 22-04-2015 | 331 | 210 | 250000 | 187500.01 | 1 | 187500.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the deadline.
4841 | 1083297 | Refurbishment and Expansion of the elementary school of Vila das Velas, São Jorge Island | 45113000-2 | Siteworks | FALSE | 2014 | 2015 | Portugal | Velas | Região Autónoma dos Açores | 15 | 20 | 30-05-2014 | 16-07-2015 | 412 | 365 | 349593.41 | 289014.78 | 2 | 289014.78 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the last invoice was presented together with measurement notice no. 10 for a total of 12 notices foreseen at the start of the contract.
4842 | 1083200 | Execution of the contract for "Construction of the Porto Municipal Emergency Operations Center for Civil Protection" | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 11 | 14-08-2013 | 23-02-2015 | 558 | 240 | 190000 | 153102.98 | 1 | 35863.23 | 117239.75 | 426.908 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 14 | N/A | N/A | N/A | N/A | N/A | N/A |  | errors and omissions
4843 | 1082137 | "Remodeling and Conservation of the Municipal Auditorium, Avenida da Conceição in Vila das Velas, São Jorge Island" | 45113000-2 | Siteworks | FALSE | 2014 | 2015 | Portugal | Velas | Região Autónoma dos Açores | 15 | 20 | 29-05-2014 | 16-07-2015 | 413 | 365 | 407398.68 | 392920.26 | 2 | 392920.26 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the last invoice was presented together with measurement notice no. 7 for a total estimated at the beginning of the 12-month contract.
4844 | 1080710 | “Execution of Works to Improve the Quality of Water Distributed by ARM”, in accordance with the provisions of the Specifications and respective annexes, based briefly on the following works: | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2014 | 2015 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 52 | 28-05-2014 | 03-07-2015 | 401 | 120 | 320000 | 258931.16 | 2 | 240565.56 | 18365.6 | 107.6343 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | delay on the part of the contractor. | underwork worth €18,365.60 under article 379
4845 | 1078673 | Shipyard and work Preliminaries, cleaning and deforesting of walls and bastions surfaces, reconstruction, consolidation and reinforcement of unstable areas of walls and bastions | 45454100-5 | Restoration work | FALSE | 2014 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 11 | 12-05-2014 | 24-03-2015 | 316 | 270 | 330000 | 198000.01 | 1 | 191603.03 | 6396.98 | 103.3387 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | deadline for completion of the project | works to be suppressed worth €6396.98
4846 | 1078311 | Seafront Requalification Contract - 3rd Phase | 45233120-6 | Road construction works | FALSE | 2014 | 2015 | Portugal | Mira | Coimbra | 6 | 20 | 07-05-2014 | 10-07-2015 | 429 | 305 | 240000 | 196249.72 | 1 | 200194.62 | -3944.9 | 98.0295 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | Extra work - underwork - price review
4847 | 1078074 | Construction of the Tondela Mortuary House | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 20-05-2014 | 26-05-2015 | 371 | 180 | 245000 | 202000 | 1 | 198259.7 | 3740.3 | 101.8866 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | for causes supervening the contract.
4848 | 1072526 | Execution of the construction works of a Municipal Building in crossstreet ofs Dores, nºs 9 to 15, in Lisbon, in the place where there are currently three Municipal Buildings – crossstreet ofs Dores, nº 9; | 45211000-9 | Construction work for multi-dwelling buildings and individual houses | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 11-05-2012 | 05-06-2015 | 1120 | 540 | 1200000 | 976072.69 | 2 | 1029425.33 | -53352.64 | 94.8172 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the causes of the alterations to the execution period of the project are essentially related to archaeological prospecting work not initially foreseen and others under the responsibility of the infrastructure concessionaires, not included in the contract, but conditioning its progression. | overwork, underwork and compensation
4849 | 1070285 | This is the improvement and paving of an agricultural road, including earthworks, drainage, bituminous paving and hub paving, safety signs and road works. | 45233123-7 | Secondary road construction work | FALSE | 2014 | 2015 | Portugal | Meda | Guarda | 9 | N/A | 20-05-2014 | 05-06-2015 | 381 | 365 | 287673.88 | 232989.39 | 1 | 214948.94 | 18040.45 | 108.3929 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the contractual period and at a good pace. | small quantities of some works that, in the course of the project, it was found not to be necessary.
4850 | 1068975 | construction of bike path | 45233162-2 | Cycle path construction work | FALSE | 2011 | 2015 | Portugal | Almeida | Guarda | 9 | 24 | 14-09-2011 | 12-06-2015 | 1367 | 480 | 996397.88 | 849599.86 | 2 | 782298.4 | 67301.46 | 108.603 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to labor difficulties and also due to the fact that the awarded company is going through a restructuring phase | existence of underworks
4851 | 1068302 | Alteration of the ventilation duct network (inflation of fresh air), including additions, connections, repositioning of sections, creation of collars for mounting grilles and diffusers | 45331210-1 | Ventilation installation work | FALSE | 2013 | 2015 | Portugal | Cascais | Lisboa | 11 | 30 | 24-03-2014 | 05-06-2015 | 438 | 300 | 1300000 | 889760.11 | 2 | 889760.11 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period. due to the need for corrections, tests and adjustments to operation, the provisional acceptance was only carried out a few months after the completion of the project.
4852 | 1068263 | Improvement of the Ark Workshop - Energy and Environmental Upgrade | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2014 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 18 | 02-05-2014 | 06-02-2015 | 280 | 120 | 282000 | 281556.06 | 2 | 281556.06 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | without changes
4853 | 1063266 | Contract for the Supply and Assembly of a "Fine Bubble" Air Diffusion System for the Chelas and Frielas WWTP - CP/O 15/13 | 45259100-8 | Wastewater-plant repair and maintenance work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 36 | 14-04-2014 | 12-03-2015 | 332 | 180 | 230000 | 229990 | 1 | 229990 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period.
4854 | 1062141 | Remodeling contract for the Surgical Inpatient Service at HDJMG - ULSNA, EPE | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Portalegre | Portalegre | 12 | 48 | 28-04-2014 | 23-04-2015 | 360 | 180 | 1493000 | 983426.94 | 2 | 879901.78 | 103525.16 | 111.7655 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extra work | additional work and contract termination
4855 | 1060999 | Implementation of EE in Carvalhal, parish of Silva Escura and municipality of Sever do Vouga | 45000000-7 | Construction work | FALSE | 2014 | 2015 | Portugal | Sever do Vouga | Aveiro | 1 | N/A | 17-04-2014 | 28-09-2015 | 529 | 90 | 200000 | 192692.32 | 1 | 192171.36 | 520.96 | 100.2711 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with contractual deadlines due to the need to acquire a plot of land for the installation of the ee | contracted amounts that, due to the location of the project, were not necessary to execute
4856 | 1059427 | Baroque axis building - Interactive tourism shop | 45211350-7 | Multi-functional buildings construction work | FALSE | 2013 | 2015 | Portugal | Lamego | Viseu | 20 | 11 | 27-02-2014 | 23-07-2015 | 511 | 270 | 544679.03 | 479793.14 | 2 | 479793.14 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | there were deadline extensions due to changes arising in the project
4857 | 1059272 | Refurbishment and expansion of building for residential home, center for occupational activities and home support service called Nossa Senhora de Espadanedo | 45215200-9 | Construction work for social services buildings | FALSE | 2011 | 2015 | Portugal | Cinfães | Viseu | 20 | 30 | 04-12-2011 | 13-03-2015 | 1195 | 730 | 2431393.65 | 1776851.55 | 3 | 1776851.55 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | lack of access to land, change of contractor
4858 | 1057741 | Construction of a flow regulation reservoir and execution of complementary works | 45247270-3 | Reservoir construction works | FALSE | 2013 | 2015 | Portugal | Odemira | Beja | 2 | 31 | 15-04-2014 | 17-12-2015 | 611 | 154 | 982326.62 | 973982.14 | 2 | 973982.14 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension due to impossibility of connection to the irrigation channel
4859 | 1055971 | Contract number 8/dmpo/dcme/dpc/2013 – “Rehabilitation of the Gaivotas school, located at street ofs Gaivotas nº 2 to 8 - Piparu financing” process nº 25/cp/deps/n.d./2013) | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 02-05-2014 | 10-02-2015 | 284 | 90 | 300000 | 205386.18 | 1 | 300000 | -94613.82 | 68.4621 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4860 | 1054659 | Improvement of streetFeliciano Moreira - Rana | 45112000-5, 45232130-2, 45232151-5, 45233000-9, 45316110-9 | Excavating and earthmoving work, Storm-water piping construction work, Water-main refurbishment construction work, Construction, foundation and surface works for highways, roads, Installation of road lighting equipment | FALSE | 2013 | 2015 | Portugal | Cascais | Lisboa | 11 | 30 | 23-04-2014 | 22-01-2015 | 274 | 180 | 575554.47 | 345332.68 | 2 | 345332.68 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4861 | 1053346 | Fever Sports Park, by Contract - Changing Rooms (Finishing) - CP-CCP-EMP No. 01/2014 | 45212221-1 | Construction work in connection with structures for sports ground | FALSE | 2014 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 27 | 06-05-2014 | 25-09-2015 | 507 | 180 | 325261.8 | 265889.32 | 2 | 262234.36 | 3654.96 | 101.3938 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | completion of work | existence of more/underwork and errors and omissions
4862 | 1050380 | RUCI PROJECT - Business Incubator, 2nd Phase, at streetDr. Pereira de Melo, in the Parish of Beduído, in the Municipality of Estarreja | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Estarreja | Aveiro | 1 | 21 | 22-04-2014 | 02-07-2015 | 436 | 180 | 251000 | 248517.73 | 1 | 244638.51 | 3879.22 | 101.5857 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 2 | N/A | N/A | N/A | N/A | N/A | N/A | term extension | price review
4863 | 1047894 | Contract for the Construction of the "Centre for the Promotion of Interculturality and Community Support" - future installation (headquarters) of the Cape Verdean Association of Sines and Santiago do Cacém. | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Sines | Setúbal | 17 | 24 | 22-04-2014 | 06-03-2015 | 318 | 150 | 261605.87 | 237761.01 | 1 | 260350.4 | -22589.39 | 91.3235 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a delay in the execution of the project due to the delay in carrying out the projects by the contractor. | the contractor claimed the existence of additional work, which led to an increase in the contractual value of the project.
4864 | 1045455 | REC- creative workshops- work to convert and equip the old Cine-Têja into an incubation center and residence for creativity | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 07-04-2014 | 14-09-2015 | 525 | 210 | 526140.39 | 394605.3 | 2 | 390443.01 | 4162.29 | 101.066 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the formalization of additional works | existence of overwork and underwork
4865 | 1045267 | The contract aims to improve trafficability conditions, reinforce the pedestrian traffic component and simultaneously the comfort and safety of all users | 45211360-0 | Urban development construction work | FALSE | 2014 | 2015 | Portugal | Vouzela | Viseu | 20 | 12 | 10-04-2014 | 30-07-2015 | 476 | 120 | 350000 | 306637.88 | 2 | 288982.11 | 17655.77 | 106.1096 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project term result from the extensions granted. | the decrease in the value of the project essentially results from the project actually carried out and measured and those initially planned.
4866 | 1043118 | Campo de Besteiros School Center - Requalification of Sports and Covered Equipment | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 16-04-2014 | 07-01-2015 | 266 | 150 | 345456.44 | 241819.52 | 1 | 216354.69 | 25464.83 | 111.7699 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions, due to lack of safety conditions | existence of works
4867 | 1042610 | Accessibility to the Convent of S. Francisco / Requalification of Av. João das Regras | 45233120-6 | Road construction works | FALSE | 2013 | 2015 | Portugal | Coimbra | Coimbra | 6 | 20 | 28-03-2014 | 28-10-2015 | 579 | 150 | 341400 | 309127.21 | 2 | 340606.92 | -31479.71 | 90.7578 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extensions | more work value
4868 | 1042007 | Refurbishment and expansion of the interceptor system between Aver-o-Mar and ETAR PV/VC: Work - Agro Velho Elevator System | 45232431-2 | Wastewater pumping station | FALSE | 2014 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 30 | 16-04-2014 | 01-09-2015 | 503 | 365 | 495000 | 461853.72 | 2 | 459599.04 | 2254.68 | 100.4906 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4869 | 1041676 | contract contract for “rehabilitation of degraded houses in the historical center – building on streets á da bandeira”. | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Elvas | Portalegre | 12 | 24 | 16-04-2014 | 13-01-2015 | 272 | 180 | 240000 | 199410.53 | 1 | 192405.66 | 7004.87 | 103.6407 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | it was necessary to make some corrections in the project in order to be able to carry out the provisional acceptance. | there was a supply of works
4870 | 1041507 | This is an urban rehabilitation work focusing on the completion and requalification of some existing streets in the urban agglomeration of Torreira, reinforcing the safety conditions | 45432110-8 | Floor-laying work | FALSE | 2014 | 2015 | Portugal | Murtosa | Aveiro | 1 | 30 | 17-04-2014 | 29-07-2015 | 468 | 360 | 550515.42 | 467846.84 | 2 | 463591.84 | 4255 | 100.9178 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | the project was delayed due to weather conditions | the project had underwork
4871 | 1038215 | Environmental requalification of the banks of the Sousa River (Senhora do Salto) - Aguiar de Sousa | 45112700-2 | Landscaping work | FALSE | 2013 | 2015 | Portugal | Paredes | Porto | 13 | 20 | 10-04-2014 | 04-05-2015 | 389 | 365 | 342000 | 205200.01 | 1 | 205200.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions
4872 | 1038077 | The Work will consist of reinforcing the Picoto subsystem, including the construction of a reservoir in Picoto de Cima, replacing the existing one, which is obsolete in view of current needs | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Braga | Braga | 3 | 30 | 09-04-2014 | 29-12-2015 | 629 | 365 | 1476530 | 1471864.94 | 3 | 1462022.63 | 9842.31 | 100.6732 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no deadline change | adequacy on site of some planned works
4873 | 1037207 | Construction of an Incubator Pavilion for Workshops and Industry | 45213250-0 | Construction work for industrial buildings | FALSE | 2013 | 2015 | Portugal | Fig. Castelo Rodrigo | Guarda | 9 | 15 | 02-04-2014 | 02-06-2015 | 426 | 200 | 222064.31 | 186900.07 | 1 | 191597.38 | -4697.31 | 97.5483 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | work of an unforeseen nature: execution of a retaining wall | works of an unforeseen nature
4874 | 1036925 | Construction of the Fevers Sports Pavilion - CP-CCP-EMP No. 10/2013 | 45212225-9 | Sports hall construction work | FALSE | 2013 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 34 | 11-04-2014 | 25-09-2015 | 532 | 365 | 1570000 | 1334737.52 | 3 | 1326875.37 | 7862.15 | 100.5925 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | conclusion work | existence of underwork and revision of prices
4875 | 1036594 | Execution of the infrastructures of the Business and Industrial Park of Vidigueira - phase 2 - creation of a nest of companies | 45111290-7 | Primary works for services | FALSE | 2013 | 2015 | Portugal | Vidigueira | Beja | 2 | 20 | 07-03-2014 | 03-06-2015 | 453 | 180 | 589793.59 | 561948.31 | 2 | 531903.92 | 30044.39 | 105.6485 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | the value of the project results from the difference between the contracted value and the value of the extra work and underwork.
4876 | 1036243 | Refurbishment of the WWTPs in Vila Verde and Aldeia das Dez. Construction of two EEAR and respective outfalls and lifts in Aldeia das Dez. | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2013 | 2015 | Portugal | Oliveira do Hospital | Guarda | 9 | 25 | 07-04-2014 | 27-02-2015 | 326 | 300 | 720000 | 615587 | 2 | 613355.84 | 2231.16 | 100.3638 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the project deadline. | underwork
4877 | 1033880 | Construction of irrigation networks, paths and drainage, leveling and landscape restoration of the Bolão block. | 45232120-9 | Irrigation works | FALSE | 2013 | 2015 | Portugal | Coimbra | Coimbra | 6 | 30 | 08-04-2014 | 04-12-2015 | 605 | 360 | 4400000 | 3520000.01 | 3 | 3445846.21 | 74153.8 | 102.152 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period. | the project included the planting of a green structure, to be executed at the end of the contract. plantings to be effective have to be carried out between october and february. the development of the project would only allow planting between may and june (out of season), so they were withdrawn from the contract.
4878 | 1033062 | Improvement of street of Barreiro, in Sarnadas - Execution of exterior pavements, rainwater drainage, electrical and telecommunications infrastructure, plantings and irrigation | 45211360-0 | Urban development construction work | FALSE | 2014 | 2015 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 12 | 07-04-2014 | 19-08-2015 | 499 | 90 | 353659 | 297148.45 | 2 | 269735.49 | 27412.96 | 110.1629 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | complexity found in the adjustment between infrastructure found underground and new ones to be installed | non-completion of work
4879 | 1033015 | Rehabilitation of the Municipal Pavilion of Santa Cruz das Flores | 45212200-8 | Construction work for sports facilities | FALSE | 2013 | 2015 | Portugal | Santa Cruz das Flores | Região Autónoma dos Açores | 15 | 21 | 07-03-2014 | 09-11-2015 | 612 | 180 | 399862.25 | 348707.38 | 2 | 348707.39 | -0.01 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no application. | no application.
4880 | 1031051 | The object of this contract is the construction of the artisan dynamization center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2013 | 2015 | Portugal | Vila Verde | Braga | 3 | 30 | 04-04-2014 | 20-04-2015 | 381 | 365 | 283464.9 | 234649.56 | 1 | 229680.98 | 4968.58 | 102.1633 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4881 | 1030851 | Requalification of the Fratel Public Swimming Pools - Expansion of the swimming pool and support buildings, structural elements, basic infrastructure, HVAC, sanitary hot water, plantings, irrigation and paving | 45210000-2, 45112700-2, 45212212-5 | Building construction work, Landscaping work, Construction work for swimming pool | FALSE | 2014 | 2015 | Portugal | Vila Velha de Ródão | Castelo Branco | 5 | 12 | 04-04-2014 | 16-09-2015 | 530 | 90 | 338848.4 | 246661.93 | 1 | 245941.93 | 720 | 100.2928 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | delay in carrying out the provisional acceptance | non-performance of contractual works
4882 | 1030302 | Execution contract for Espaço Guadiana (Party Room) | 45210000-2 | Building construction work | FALSE | 2014 | 2015 | Portugal | Alcoutim | Faro | 8 | 20 | 01-04-2014 | 20-07-2015 | 475 | 90 | 286573.64 | 228873.33 | 1 | 224875.84 | 3997.49 | 101.7776 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | due to provisional acceptance | underwork worth €3,997.48
4883 | 1028201 | Refurbishment of the Old Town Hall Building | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2013 | 2015 | Portugal | Murtosa | Aveiro | 1 | 30 | 02-04-2014 | 12-10-2015 | 558 | 365 | 474373.45 | 421978.98 | 2 | 420522.09 | 1456.89 | 100.3464 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was delayed by a month, due to a delay in the delivery of some equipment | the project had underwork
4884 | 1026120 | 2013.041.03.C1 - SF Porto - Auditorium Remodeling | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2014 | 2015 | Portugal | Porto | Porto | 13 | N/A | 12-03-2014 | 09-06-2015 | 454 | 40 | 320000 | 310013.54 | 2 | 340115.51 | -30101.97 | 91.1495 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | additional | additional
4885 | 1024700 | Contract for the Construction of the Sports Pavilion of the elementary school of Posto Santo | 45212225-9 | Sports hall construction work | FALSE | 2013 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 31 | 26-02-2014 | 14-12-2015 | 656 | 270 | 691066.5 | 625569.37 | 2 | 619103.53 | 6465.84 | 101.0444 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A
4886 | 1023553 | En10 - 24+200 - construction of roundabout - elimination of black spot. | 45233128-2 | Roundabout construction work | FALSE | 2011 | 2015 | Portugal | Setúbal | Setúbal | 17 | 48 | 14-03-2014 | 18-12-2015 | 644 | 90 | 310000 | 299881.53 | 2 | 231964.42 | 67917.11 | 129.2791 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | resulting from the elaboration of bill of quantities
4887 | 1023011 | Requalification of the public space of the Baroque Axis | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Lamego | Viseu | 20 | 20 | 30-11-2012 | 20-04-2015 | 871 | 300 | 2847009.06 | 2562308.15 | 3 | 2490493 | 71815.15 | 102.8836 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climatic conditions and archaeological works. | there were works that were found not to be necessary (underwork)
4888 | 1021940 | Construction of the Cantanhede School Center - CP-CCP-EMP No. 08/2013 | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2013 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 32 | 28-03-2014 | 24-09-2015 | 545 | 540 | 1997055.69 | 1677079.23 | 3 | 1591987.48 | 85091.75 | 105.345 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 23 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the project deadline | existence of more, underwork and negative price revision
4889 | 1017134 | Installation of a sieving system to treat thickened sludge at the Solid Phase Treatment Station (ETFS), involving civil construction work and equipment assembly. | 45232422-6 | Sludge-treatment works | FALSE | 2013 | 2015 | Portugal | Cascais | Lisboa | 11 | 30 | 22-01-2014 | 25-06-2015 | 519 | 180 | 750000 | 559453.96 | 2 | 564561.52 | -5107.56 | 99.0953 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | in addition to the contractual modification already published, due to delay in the delivery of equipment by suppliers (attached), there was no other extension of the execution period. provisional acceptance was carried out on a more convenient date for sanest, taking into account the company's current activities
4890 | 1014549 | The object of this contract is the construction of two wastewater pumping stations, lift pipes and gravity interceptors. | 45112500-0, 45232411-6, 45232423-3 | Earthmoving work, Foul-water piping construction work, Sewage pumping stations construction work | FALSE | 2013 | 2015 | Portugal | Vila do Conde | Porto | 13 | 50 | 03-03-2014 | 27-12-2015 | 664 | 304 | 2200000 | 1716362.59 | 3 | 1818161.42 | -101798.83 | 94.401 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | as a result of additional work and errors and omissions in the execution project | 1) additional work: 2) errors and omissions; 3) underwork; 4) indemnities for extension of the legal term and 5) price review
4891 | 1013277 | Reuse of Building for Interpretive Center | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2013 | 2015 | Portugal | Vinhais | Bragança | 4 | 36 | 13-03-2014 | 13-07-2015 | 487 | 275 | 349776.16 | 308882.47 | 2 | 308882.47 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | occurrence of unforeseen situations during the course of the project, whose clarifications were requested by the contractor.
4892 | 1012278 | Construction of a reservoir supported by the station's supply zone | 45247270-3 | Reservoir construction works | FALSE | 2013 | 2015 | Portugal | Marinha Grande | Leiria | 10 | 20 | 20-03-2014 | 17-04-2015 | 393 | 150 | 329864.47 | 259993.33 | 2 | 259766.43 | 226.9 | 100.0873 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes in the period of execution of the project | for the purpose of suppressing work and supplying errors and omissions
4893 | 1009592 | The object of this contract is the execution of the Cervães Educational Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Vila Verde | Braga | 3 | 45 | 24-10-2013 | 30-06-2015 | 614 | 300 | 856247.71 | 729221 | 2 | 725871 | 3350 | 100.4615 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
4894 | 1009581 | The object of this contract is the execution of the Soutelo Educational Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 45 | 24-10-2013 | 30-06-2015 | 614 | 300 | 893187.17 | 683862.73 | 2 | 683375.02 | 487.71 | 100.0714 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4895 | 1009561 | The object of this contract is the construction of the Lage Educational Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Vila Verde | Braga | 3 | 45 | 24-10-2013 | 30-06-2015 | 614 | 300 | 1173273.24 | 919402.2 | 2 | 914749.52 | 4652.68 | 100.5086 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4896 | 1007627 | Construction of the Casais School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 13-03-2014 | 30-10-2015 | 596 | 360 | 813481.13 | 792185.31 | 2 | 768165.28 | 24020.03 | 103.1269 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions; lack of definitions in terms of exterior arrangements; definition of the power supply in the hvac system | adaptation of the project to real conditions on the ground
4897 | 1007512 | Construction of the Nespereira School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 13-03-2014 | 30-10-2015 | 596 | 420 | 1291768.19 | 1085366.11 | 3 | 1083387.1 | 1979.01 | 100.1827 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions; lack of definitions in terms of exterior arrangements; definition of the power supply in the hvac system | adaptation of the project to the conditions necessary for installing the hvac equipment
4898 | 1007431 | Contract work for the Arouca School Center - Phase 4 | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Arouca | Aveiro | 1 | 30 | 17-03-2014 | 03-06-2015 | 443 | 240 | 899025.15 | 675971.82 | 2 | 638917.8 | 37054.02 | 105.7995 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A | delay of work attributable to the contractor. | suppressed works and additional works necessary for the completion of the project.
4899 | 999198 | Contract work for the South Street of Quinta de Santo António, in Santa Maria da Feira. | 45230000-8 | Construction work for pipelines, communication and power lines, for highways, roads, airfields and railways; flatwork | FALSE | 2013 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 60 | 03-03-2014 | 08-07-2015 | 492 | 120 | 305337 | 263649 | 2 | 246780.35 | 16868.65 | 106.8355 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | additional work (2 days) ;execution delay attributable to the contractor (191 days) ;extension of the period elapsed between the 1st provisional reception and the final one for correction of deficiencies (142 days). | additional work resulting from other infrastructures that required superior protection of the rainwater pipe. underwork.
4900 | 998972 | Urban Arrangement Contract for Praça Sá Carneiro and Surroundings of the Arouca Pole | 45233120-6 | Road construction works | FALSE | 2013 | 2015 | Portugal | Arouca | Aveiro | 1 | 30 | 06-03-2014 | 02-07-2015 | 483 | 240 | 263179.22 | 226650 | 1 | 202580.75 | 24069.25 | 111.8813 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of the contract for an indefinite period due to the temporary impossibility of carrying out some works, in accordance with article 297 of the "public procurement code" and delay attributed to the contractor. | existence of more work and underwork.
4901 | 994655 | Contract for UP Museums – Atrium and Access Center | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 25 | 20-02-2014 | 16-10-2015 | 603 | 180 | 448845.63 | 366329.52 | 2 | 395807 | -29477.48 | 92.5526 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | existence of term extensions totaling 163 days.
4902 | 993723 | Demolitions/earth movements; flooring; execution of electrical infrastructure and public lighting; telecommunications infrastructure; infrastructure for EDP Gas | 45233252-0 | Surface work for streets | FALSE | 2013 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 11-02-2014 | 02-11-2015 | 629 | 210 | 300000 | 253918.54 | 2 | 253918.54 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 6 | N/A | N/A | N/A | N/A | N/A | N/A | the last measurement report was prepared on october 28, 2014, as such the provisional acceptance was prepared on the same date.
4903 | 991719 | Execution contract for the Benavente/Samora Correia/Vale Tripeiro Supply Subsystems – Low slope – Completion of the 2nd phase | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Benavente | Santarém | 16 | 48 | 26-02-2014 | 09-05-2015 | 437 | 90 | 350000 | 226562.43 | 1 | 226562.43 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements.
4904 | 988480 | Paving of the Municipal Road Network | 45232451-8 | Drainage and surface works | FALSE | 2013 | 2015 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 19-02-2014 | 10-09-2015 | 568 | 150 | 464264.5 | 409768.96 | 2 | 409768.96 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather, delay in transportation of some essential materials for the project
4905 | 986635 | Rehabilitation of the Family Health Unit "AS GÂNDRAS" - CP-CCP-EMP n.º 07/2013 | 45215100-8 | Construction work for buildings relating to health | FALSE | 2013 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 47 | 20-02-2014 | 23-09-2015 | 580 | 240 | 333357.5 | 246170.82 | 1 | 221649.37 | 24521.45 | 111.0632 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | completion of the remaining work | existence of works
4906 | 985042 | Execution contract for the Wastewater Pumping Station of Matadouro in Torres Novas | 45232431-2 | Wastewater pumping station | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | N/A | 04-10-2013 | 15-12-2015 | 802 | 120 | 600000 | 450025 | 2 | 449917.03 | 107.97 | 100.024 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the term of the contract and the provisional acceptance derives from delays in the execution of the projects, in the correction of defects and in the delivery of elements.
4907 | 985018 | Execution contract for the Water Supply Network in Pé-de-Cão | 45231110-9 | Pipelaying construction work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | 24 | 24-01-2014 | 26-06-2015 | 518 | 120 | 370000 | 222000.01 | 1 | 180196.19 | 41803.82 | 123.1991 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the term of the contract and the provisional acceptance was derived from suspension, repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
4908 | 985008 | Contract for execution of the supply pipeline to Granho | 45231100-6 | General construction work for pipelines | FALSE | 2013 | 2015 | Portugal | Salvaterra de Magos | Santarém | 16 | 48 | 24-01-2014 | 29-04-2015 | 460 | 120 | 400000 | 240000.01 | 1 | 235460.01 | 4540 | 101.9281 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 26 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements | the project was carried out in its entirety, not requiring the invoicing of all items.
4909 | 984955 | Contract for Execution of Equipment for Collection and Treatment of the Chamusca/Vale de Cavalos and Ulme Supply Subsystem | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Chamusca | Santarém | 16 | 48 | 14-02-2014 | 23-10-2015 | 616 | 120 | 350000 | 281688.45 | 2 | 281489.08 | 199.37 | 100.0708 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was due to repairs, correction of defects and delivery of missing elements.
4910 | 984940 | Rehabilitation contract for the Riachos WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | 48 | 05-12-2013 | 10-08-2015 | 613 | 180 | 2700000 | 1890000.01 | 3 | 1890000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 34 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the term of the contract and the provisional acceptance derives from delays in the execution of the project, in the correction of defects and in the delivery of elements.
4911 | 982611 | Contract for the 2nd Recovery Phase of the Lousal Mining Area | 45112500-0 | Earthmoving work | FALSE | 2013 | 2015 | Portugal | Grandola | Setúbal | 17 | 29 | 05-02-2014 | 09-07-2015 | 519 | 365 | 2350000 | 1803959.81 | 3 | 1803959.81 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed within the stipulated time frame.
4912 | 981662 | Rehabilitation of the Tourism and Culture building - Santa Maria da Feira | 45210000-2 | Building construction work | FALSE | 2013 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 36 | 11-02-2014 | 07-09-2015 | 573 | 360 | 423307 | 352830.94 | 2 | 359922.95 | -7092.01 | 98.0296 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | additional works of various kinds, which only became visible when the contractor entered the project and which stem from the recognized unpredictability inherent in interventions to rehabilitate buildings and works unless they resulted from lags between the measurements in the project and the measurements of the projects in progress work, or that proved to be expendable.
4913 | 980625 | Construction of the Telheiro school center, Barreira | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Leiria | Leiria | 10 | 35 | 13-12-2013 | 01-06-2015 | 535 | 425 | 1626875.4 | 1334000 | 3 | 1334000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | incomplete works
4914 | 978170 | Construction of the Lodares School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 10-02-2014 | 30-10-2015 | 627 | 420 | 1290887.41 | 1054478.78 | 3 | 1052438.77 | 2040.01 | 100.1938 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions; lack of definitions in terms of external arrangements: definition of the power supply in the hvac system | adaptation of the project to the conditions necessary for installing the hvac equipment
4915 | 978050 | Major repair and adaptation of buildings - refurbishment of the municipal market | 45259000-7 | Repair and maintenance of plant | FALSE | 2013 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 03-02-2014 | 29-07-2015 | 541 | 180 | 295318.14 | 208261.82 | 1 | 208261.82 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were 1 extension and 2 suspensions in the project. extension: due to the presence of commerce and services in the facilities that do not allow the start of the project. 1st suspension: reasons beyond the control of the successful tenderer (change in the layout of the edp and zon infrastructures). 2nd suspension: reasons beyond the control of the successful tenderer (request by the architect responsible for the project to make aesthetic adaptations to the project.
4916 | 977991 | Construction of the Caíde de Rei School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 10-02-2014 | 30-10-2015 | 627 | 480 | 1556603.77 | 1331302.23 | 3 | 1328354.85 | 2947.38 | 100.2219 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | delays occurred in the preparatory work and earthmoving phase. | adaptation of the project to the conditions necessary for installing the hvac equipment
4917 | 976644 | Work to Duplicate Ribeira da Falagueira - CP/O 04/13. | 45232400-6 | Sewer construction work | FALSE | 2013 | 2015 | Portugal | Amadora | Lisboa | 11 | 63 | 31-01-2014 | 29-06-2015 | 514 | 365 | 3800000 | 3024755.89 | 3 | 2980113.67 | 44642.22 | 101.498 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions for the execution of the type of work. | affected unforeseen services with adaptation of the constructive method and need to carry out exterior repair works that were not foreseen.
4918 | 976185 | Repaving of C.M 1167 from Aldeia dos Fernandes to EN2 | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Almodovar | Beja | 2 | N/A | 06-02-2014 | 26-10-2015 | 627 | 180 | 597000 | 477155.35 | 2 | 473421.95 | 3733.4 | 100.7886 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions | underwork
4919 | 975629 | Ronfe School Center | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Guimarães | Braga | 3 | 30 | 06-02-2014 | 16-01-2015 | 344 | 240 | 3257585.25 | 2105207.2 | 3 | 2089792.76 | 15414.44 | 100.7376 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underwork due to the non-exhaustion of the measurement of some items foreseen in the project.
4920 | 974525 | Contract for the Remodeling of the General Conductor Channel 2nd Section 2nd Phase | 45232120-9 | Irrigation works | FALSE | 2013 | 2015 | Portugal | Aljustrel | Beja | 2 | 40 | 19-12-2013 | 27-03-2015 | 463 | 240 | 2500000 | 2262617.01 | 3 | 2262179.03 | 437.98 | 100.0194 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | survey of around 80 mts of dn 1800 piping after a night of heavy rain, unforeseen in the demolition of er0, only in january did it obtain proder approval to change the irrigation sockets | changes in irrigation sockets
4921 | 973263 | Construction of the Maceira school center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Leiria | Leiria | 10 | 35 | 04-12-2013 | 31-07-2015 | 604 | 365 | 1478663.62 | 1116126.22 | 3 | 1114193.72 | 1932.5 | 100.1734 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension | underwork
4922 | 964782 | Contract for the execution of the supply pipeline for Raposa | 45231100-6 | General construction work for pipelines | FALSE | 2013 | 2015 | Portugal | Almeirim | Santarém | 16 | 48 | 23-12-2013 | 06-05-2015 | 499 | 120 | 380000 | 228000.01 | 1 | 195190.04 | 32809.97 | 116.8092 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements | the project was carried out in its entirety, not requiring the invoicing of all items.
4923 | 964358 | Refurbishment and Refurbishment Works for the Palace of Vila Pouca as described in the specifications of the tender process | 45211350-7 | Multi-functional buildings construction work | FALSE | 2013 | 2015 | Portugal | Mondim de Basto | Vila Real | 19 | 15 | 17-01-2014 | 13-03-2015 | 420 | 365 | 175762 | 174900 | 1 | 174900 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes in the execution period of the project. | there were no changes in the value of the project
4924 | 963084 | This is a work to be carried out by the Municipality of Calheta, which aims to objective is the implementation of communication infrastructures, capable of streamlining and boost agricultural activity | 45233123-7 | Secondary road construction work | FALSE | 2013 | 2015 | Portugal | Calheta | Região Autónoma da Madeira | 14 | 21 | 30-12-2013 | 08-06-2015 | 525 | 360 | 619619.49 | 448000 | 2 | 450102 | -2102 | 99.533 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | the project took place as described in the respective measurement records. | the balance results from the measurements of work on site as described in the measurement records and in the accounts closing maps, and additional contract whose works are specified in the said contract and annex i thereto.
4925 | 961001 | Work to adapt Casa Andresen to the Biodiversity Gallery | 50000000-5 | Repair and maintenance services | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 60 | 20-01-2014 | 22-09-2015 | 610 | 270 | 926500 | 833850 | 2 | 855391.1 | -21541.1 | 97.4817 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful term extensions referred to, authorized on 08/13/2014 and 01/06/2015. | existence of increases in the cost of the project resulting from additional work (art.º 373.º "public procurement code") and works to correct errors and omissions not included in the initial contract (art. the final value also includes a decrease due to ordinary price revisions (art.º 383º "public procurement code").
4926 | 955154 | Refurbishment of the road between Bemposta and Vale das Mós -Consists in particular of regularization and widening work on the carriageway, execution of new verges and cleaning and regularization | 45233141-9 | Road-maintenance works | FALSE | 2013 | 2015 | Portugal | Abrantes | Santarém | 16 | 36 | 15-01-2014 | 28-06-2015 | 529 | 120 | 399915.29 | 382800 | 2 | 375845.33 | 6954.67 | 101.8504 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | the change in the value of the project was due to the price revision.
4927 | 951782 | The object of this contract is the Expansion of the Turiz Educational Center - Completion | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Vila Verde | Braga | 3 | 24 | 15-07-2013 | 30-06-2015 | 715 | 150 | 527262 | 526640 | 2 | 522570 | 4070 | 100.7788 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A
4928 | 951664 | The purpose of the procedure is to contract the contract for: COMPLETION OF THE CONTRACT FOR “REQUALIFICATION OF EN 4 – 2nd PHASE: BETWEEN THE POOL ROUNDABOUT TO THE AMOREIRA AQUEDUCT – 1ST SECTION”. | 45233200-1 | Various surface works | FALSE | 2013 | 2015 | Portugal | Elvas | Portalegre | 12 | 24 | 15-01-2014 | 22-01-2015 | 372 | 150 | 1600000 | 1394076.31 | 3 | 1295108.04 | 98968.27 | 107.6417 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a need to make some corrections in the project and in order to be able to carry out the provisional acceptance.
4929 | 951531 | Execution of the works for the Water Supply to Amarante - Left Bank - Phase 1 | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Amarante | Porto | 13 | 47 | 09-01-2014 | 09-01-2015 | 365 | 300 | 2500000 | 1870475.15 | 3 | 1834029.01 | 36446.14 | 101.9872 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in deadline. reception was made on the business day following the contractual deadline. | improve project efficiency
4930 | 951197 | "En 2 - Pontoon at km 654+420 / En 263 - Barranco da Venda pontoon / er 266 - Overpass to the railway - rehabilitation and reinforcement of the works of art". | 45262330-3 | Concrete repair work | FALSE | 2013 | 2015 | Portugal | Almodovar | Beja | 2 | 36 | 26-12-2013 | 07-08-2015 | 589 | 150 | 325000 | 249998.09 | 1 | 236123.36 | 13874.73 | 105.8761 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the final work report makes no reference causes of changes to the project execution period | the final work report does not mention causes of changes in the value of the project
4931 | 950519 | Construction contract for the Secondary Irrigation Network and Drainage Networks in Block IV of the Lezíria Grande Hydro-Agricultural Development in Vila Franca de Xira, with the following main characteristics: | 45232120-9 | Irrigation works | FALSE | 2013 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 21 | 20-12-2013 | 01-04-2015 | 467 | 350 | 4500000 | 4427069.94 | 3 | 4426265.79 | 804.15 | 100.0182 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed within the stipulated time. | the project had a lower cost in the amount of 804 euros that derived from the change of air tickets to buried tickets.
4932 | 950378 | Contract work for the 3rd phase of repair of the Alcântara Caneiro - Braço de Sete Rios/Twin Towers - CP/O 11/12 | 45220000-5 | Engineering works and construction works | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 44 | 23-09-2013 | 24-04-2015 | 578 | 300 | 1770000 | 1055306.65 | 3 | 1016264.05 | 39042.6 | 103.8418 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period. | underwork because it was found that the length of the piles executed was shorter than expected, as firm ground was found at a higher elevation. pricing review.
4933 | 947212 | Construction of the ETAR and Pumping Station of Póvoa de Penela and Forwarding of Effluents from the ZI of Penela da Beira - Gravity Drainage and Pumping Stations and WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2013 | 2015 | Portugal | Penedono | Viseu | 20 | 30 | 13-01-2014 | 07-09-2015 | 602 | 365 | 690000 | 414000.01 | 2 | 414000.01 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | weather changes
4934 | 944785 | Execution of the domestic waste water drainage network. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2011 | 2015 | Portugal | Monção | Viana do Castelo | 18 | 25 | 20-12-2013 | 05-10-2015 | 654 | 365 | 200000 | 153277.98 | 1 | 153277.98 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work due to lack of safety conditions and need to change the project. | there were no changes to the value of the project
4935 | 941861 | Contract for the Reorganization and Qualification of the Lagoon Front of Ovar: Praia do Areínho, Cais da Ribeira and Mouth of the river Cáster, within the Scope of the Intervention of the Polis Litoral Ria de Aveiro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Ovar | Aveiro | 1 | 30 | 12-08-2013 | 14-05-2015 | 640 | 120 | 492000 | 439501.59 | 2 | 433677.64 | 5823.95 | 101.3429 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions, which created constraints on the movement of vehicles, handling of materials and the operability of workers; spring tides and heavy rains.
4936 | 941659 | Refurbishment \\ Expansion of the Pombal WWTP - Proc. No. 35/2012 | 45232420-2 | Sewage work | FALSE | 2012 | 2015 | Portugal | Leiria | Leiria | 10 | 40 | 14-01-2013 | 22-07-2015 | 919 | 365 | 8300000 | 5939143.2 | 3 | 5852437.63 | 86705.57 | 101.4815 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions; delay in the delivery of certain equipment; execution of the power branch in medium voltage | non-execution of work (underwork).
4937 | 941392 | Contract for the Reorganization, Requalification and Enhancement of Barrinha and Lagoa de Mira and Lago do Mar, within the scope of the Intervention of the Polis Litoral Ria de Aveiro | 45220000-5 | Engineering works and construction works | FALSE | 2013 | 2015 | Portugal | Aveiro | Aveiro | 1 | 30 | 12-08-2013 | 23-02-2015 | 560 | 210 | 960000 | 837233.55 | 2 | 818402.51 | 18831.04 | 102.301 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | for the first alteration, reasons related to the high and continuous rainfall that has been felt since the beginning of the project period, which made it difficult to carry out the projects, mainly on the dam and lagoa de mira. for the second amendment, reasons related to access difficulties and local conditions, as well as issues related to the economic crisis and difficulties that, as a direct or indirect consequence, are reflected in the management of the contracts. | underwork
4938 | 937805 | Refurbishment of the Headquarters Building of Lar D. Pedro v | 45259900-6 | Plant upgrade work | FALSE | 2013 | 2015 | Portugal | Praia da Vitória | Região Autónoma dos Açores | 15 | 30 | 18-12-2013 | 02-07-2015 | 561 | 240 | 1346454.74 | 1095073.58 | 3 | 1163696.55 | -68622.97 | 94.103 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | article 370, "public procurement code".
4939 | 935676 | Changes introduced in the market construction project regarding floor -3 | 45213141-3 | Covered market construction work | FALSE | 2013 | 2015 | Portugal | Abrantes | Santarém | 16 | 36 | 23-12-2013 | 28-07-2015 | 582 | 120 | 1067323.04 | 703602.42 | 2 | 661249.95 | 42352.47 | 106.4049 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | economic difficulties of the contractor. | the existence of underwork.
4940 | 935315 | 2013.517.07.C1 - Xabregas Building - HVAC and lighting installations - East and West Wings | 45331000-6 | Heating, ventilation and air-conditioning installation work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 30 | 05-09-2013 | 10-04-2015 | 582 | 180 | 1000000 | 896981.64 | 2 | 896981.64 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | undetermined
4941 | 934470 | Construction of the Corgo School Centre, Meinedo. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 18-12-2013 | 30-10-2015 | 681 | 480 | 1411320.76 | 1102084.07 | 3 | 1077987.31 | 24096.76 | 102.2353 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | failure by the successful tenderer to respond to all contractual aspects | underwork: adaptation of the project to real conditions on the ground
4942 | 934443 | Construction of the Cristelos School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 18-12-2013 | 30-10-2015 | 681 | 480 | 1653242.92 | 1251599.72 | 3 | 1230867.58 | 20732.14 | 101.6844 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | failure by the successful tenderer to respond to all contractual aspects | underwork: adaptation of the project to real conditions on the ground
4943 | 933351 | “Rehabilitation of the Bustos reservation system” | 45232100-3 | Ancillary works for water pipelines | FALSE | 2013 | 2015 | Portugal | Oliveira do Bairro | Aveiro | 1 | 15 | 11-11-2013 | 30-01-2015 | 445 | 120 | 222500 | 179859.12 | 1 | 179859.12 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays under the responsibility of the contracting company, so there was no right to an extension of the deadline/suspension. there was also no penalty due to not having losses for the contracting authority
4944 | 929767 | Construction of the Mechanical and Biological Treatment Center for urban waste from the GESAMB, RESIALENTEJO and AMCAL Systems in Beja | 45222100-0 | Waste-treatment plant construction work | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 50 | 27-02-2013 | 02-06-2015 | 825 | 420 | 3450000 | 2463327.49 | 3 | 2461257.68 | 2069.81 | 100.0841 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 28 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project | changes to the project
4945 | 926460 | Roman Equestrian Center - Pedras Salgadas | 45454100-5 | Restoration work | FALSE | 2013 | 2015 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 14 | 20-12-2013 | 04-09-2015 | 623 | 300 | 1979663.77 | 1524341 | 3 | 1524340.99 | 0.01 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climatic conditions.
4946 | 926203 | Requalification to safeguard the public spaces surrounding the church of Aveleda, Porto, Lousada, Aveleda | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 16-12-2013 | 10-07-2015 | 571 | 120 | 331940 | 323328.09 | 2 | 316935.43 | 6392.66 | 102.017 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | occurrence of adverse climatic constraints that implied a reduction in the pace of execution of the project | underwork and negative price revision check
4947 | 926154 | Construction of the Sousela School Center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lousada | Porto | 13 | 20 | 10-12-2013 | 30-10-2015 | 689 | 480 | 1295094.34 | 1104239.44 | 3 | 1099808.52 | 4430.92 | 100.4029 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | failure by the successful tenderer to respond to all contractual aspects | underwork: adaptation of the project to real conditions on the ground
4948 | 925146 | Protection of the slope of Sotamar do Molhe Norte and Reinforcement of the Maritime Signaling of the Port of Aveiro | 45243510-0 | Embankment works | FALSE | 2013 | 2015 | Portugal | Ílhavo | Aveiro | 1 | 20 | 13-12-2013 | 05-02-2015 | 419 | 60 | 823000 | 598127.1 | 2 | 598089.62 | 37.48 | 100.0063 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather and sea conditions. | quantity less in an article of the chart of quantities of contractual works.
4949 | 922969 | Completion of the reconversion works of the convent of Santo Agostinho - Leiria | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 13-11-2013 | 22-04-2015 | 525 | 210 | 1576400 | 1358000 | 3 | 1305203.31 | 52796.69 | 104.0451 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions | underwork
4950 | 922627 | Construction of the Romanesque Interpretation Center - Lousada | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2013 | 2015 | Portugal | Lousada | Porto | 13 | 30 | 16-12-2013 | 12-11-2015 | 696 | 540 | 1036708.1 | 912929.55 | 2 | 912929.55 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the existence of a contract for the assignment of contractual position to the current contractor conditioned the pace of execution of the contract.
4951 | 915335 | Rural Village and Rural Campsite | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2013 | 2015 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 14 | 11-12-2013 | 07-09-2015 | 635 | 300 | 2880631.73 | 2448537.53 | 3 | 2448537.53 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | climatic conditions.
4952 | 913654 | With the present project, it is intended to implement a new section of the priority road from the A24 that allows an alternative road to access the Hospital Distrital de Chaves, since the current network | 45233227-6 | Slip road construction work | FALSE | 2013 | 2015 | Portugal | Chaves | Vila Real | 19 | 30 | 09-12-2013 | 28-07-2015 | 596 | 365 | 1717962.67 | 1374300 | 3 | 1348933.47 | 25366.53 | 101.8805 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extension approved in r.c. on 11/17/2014, under proposal no. 251/2014 by technician vítor pereira | supply of errors and omissions approved in r.c. on 12/19/2014, under proposal no. 251/2014 by technician vítor pereira. and price revision in the negative amount of €44,495.47.
4953 | 913206 | Museum of santo antónio - requalification work of the museum space | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 29-11-2013 | 22-01-2015 | 419 | 90 | 326322.23 | 259539.56 | 2 | 259539.38 | 0.18 | 100.0001 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4954 | 912649 | Construction contract for a water reservoir and remodeling/construction of water supply pipes for human consumption, in Fonte Faneca - Terra Chã. | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 24 | 29-11-2013 | 15-05-2015 | 532 | 360 | 800000 | 797356.13 | 2 | 797356.13 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the execution period of the project. the inspection for the purposes of provisional acceptance was carried out only on 18-02-2015 because only on this date was it possible to reconcile the simultaneous visit of the inspection and the contractor.
4955 | 908227 | Contract number 2/dmau/dhu/2013 – “construction of eco-center and surrounding area - operation feder 778 - eco-neighborhood Ambiente+: - eco-center / lot-1 (component 1.13); - infrastructure and public space | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 27-11-2013 | 28-05-2015 | 547 | 100 | 329874.77 | 296000 | 2 | 296000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4956 | 907602 | Passal Infrastructures - Casal Comba | 45233228-3 | Surface coating construction work | FALSE | 2013 | 2015 | Portugal | Mealhada | Aveiro | 1 | 30 | 03-12-2013 | 10-11-2015 | 707 | 60 | 195000 | 153904.86 | 1 | 157960.84 | -4055.98 | 97.4323 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the project suffered delays due to its suspension due to particularly adverse weather conditions, carrying out additional works and the supply of errors and omissions. | more work, underwork and errors and omissions supply.
4957 | 904231 | Refurbishment and extension of streetPedro Homem de Melo | 45233200-1 | Various surface works | FALSE | 2012 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 60 | 28-11-2013 | 07-10-2015 | 678 | 150 | 344153 | 280449.02 | 2 | 274614.02 | 5835 | 102.1248 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions | underwork
4958 | 902016 | Environmental Restoration of the Aljustrel Mining Area - 4th Contract, includes interventions in the mining areas of Algares, Pedras Brancas and S. João, in the Municipality of Aljustrel | 45112500-0 | Earthmoving work | FALSE | 2013 | 2015 | Portugal | Aljustrel | Beja | 2 | 48 | 28-11-2013 | 30-09-2015 | 671 | 406 | 5300000 | 3342357.14 | 3 | 3342357.14 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the owner of the project granted 2 requests made by the contractor to extend the execution period of the contract.
4959 | 898796 | Forest fire defense - fuel management tracks in primary and secondary networks | 77000000-0 | Agricultural, forestry, horticultural, aquacultural and apicultural services | FALSE | 2013 | 2015 | Portugal | Fundão | Castelo Branco | 5 | 20 | 19-11-2013 | 23-12-2015 | 764 | 540 | 508840 | 406999 | 2 | 406999 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change
4960 | 897264 | The contract comprises two works:_x000D_ _x000D_ Work 2 will consist of the expansion of the Montariol / Sete Fontes subsystem, including the construction of a new reservoir in Gualtar, at a higher elevation | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Braga | Braga | 3 | 30 | 12-11-2013 | 08-11-2015 | 726 | 360 | 2066641.75 | 2060956.24 | 3 | 2022507.7 | 38448.54 | 101.901 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay of licenses | project quantities error
4961 | 892706 | The object of this contract comprises the contract works for the realization of "Urban Requalification of Algoceira", to be developed in accordance with the parameters defined in the invitation and notebook | 45211360-0 | Urban development construction work | FALSE | 2012 | 2015 | Portugal | Odemira | Beja | 2 | 45 | 05-06-2013 | 21-12-2015 | 929 | 300 | 900137.3 | 678888.76 | 2 | 680471.34 | -1582.58 | 99.7674 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in removing electricity and telephone poles, unforeseen situations and improper weather | errors and omissions and unforeseen situations
4962 | 886958 | The execution project will consist of a set of buildings that integrate the remodeling of some of the buildings of the old Vidago station, to be recovered, a pivotal element of the access roads | 45215110-1 | Spa construction work | FALSE | 2012 | 2015 | Portugal | Chaves | Vila Real | 19 | 30 | 13-11-2013 | 30-06-2015 | 594 | 365 | 3380000 | 2654776.57 | 3 | 2664357.41 | -9580.84 | 99.6404 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension, work rescheduling and overwork | more works - €23,633.43, underwork - €8,437.64 and price review - €5,614.95 less.
4963 | 883883 | Design, Construction, Supply and Assembly of the Mechanical Treatment Unit for Urban Solid Waste at the Barlavento landfill | 45213270-6 | Construction works for recycling station | FALSE | 2013 | 2015 | Portugal | Portimão | Faro | 8 | 40 | 27-09-2013 | 29-05-2015 | 609 | 240 | 1800000 | 1789544.97 | 3 | 1983744.97 | -194200 | 90.2104 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | carrying out more work.
4964 | 883787 | The object of the contract is to increase the storage capacity of the Sete Fontes reservoir and increase the lifting capacity of Montariol/Sete Fontes. | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Braga | Braga | 3 | 30 | 06-11-2013 | 19-10-2015 | 712 | 540 | 3642550.84 | 3632972.93 | 3 | 3692436.08 | -59463.15 | 98.3896 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline for the project has been met. | these were works carried out within the framework of paragraph 1 of article 370 of the "public procurement code"
4965 | 883729 | Ic1, km 629+850 to km 639+120. Weather Improvement 2012-2013 | 45233142-6 | Road-repair works | FALSE | 2013 | 2015 | Portugal | Santiago do Cacém | Setúbal | 17 | 26 | 07-10-2013 | 07-08-2015 | 669 | 60 | 935000 | 860738.55 | 2 | 915918.89 | -55180.34 | 93.9754 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | periods of heavy and continuous rainfall that prevented the normal progress of paving work with hot bituminous masses, in order to guarantee the quality standards stipulated in the ec. | the projects succinctly respect the project of supplying errors and omissions
4966 | 883728 | En121, km 0+000 to km 10+650. En390, km 17+000 to km 26+946. Improvement. Weather 2012-2013 | 45233142-6 | Road-repair works | FALSE | 2013 | 2015 | Portugal | Santiago do Cacém | Setúbal | 17 | 24 | 30-09-2013 | 07-08-2015 | 676 | 60 | 715000 | 638963.84 | 2 | 636045.09 | 2918.75 | 100.4589 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather from december 2013 prevented paving and road marking work from being carried out while maintaining the quality levels stipulated in the ec. | an additional fee was submitted with the aim of contracting the projects due to the correction of initially contracted quantities.
4967 | 877702 | Execution contract for the Pedrógão/Vale da Serra/Casal João Dias Supply Subsystem | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | N/A | 17-09-2013 | 07-09-2015 | 720 | 150 | 800000 | 676373.98 | 2 | 604228.06 | 72145.92 | 111.9402 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | there was a partial suspension of work and two deadline extensions. | not all the project originally planned was carried out.
4968 | 877672 | Recovery, adaptation and expansion of existing school buildings - Construction of the Mandim School Center | 45214210-5 | Primary school construction work | FALSE | 2011 | 2015 | Portugal | Maia | Porto | 13 | 20 | 01-11-2013 | 24-08-2015 | 661 | 365 | 1650000 | 1358004.9 | 3 | 1357365.59 | 639.31 | 100.0471 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | the project started on january 27, 2015, there were 14 inspection and work measurement reports,. from the 1st to the 14th, they relate to contract no. 132/2013 of november 1, 2013. a deliberation was made that went to the board meeting on 02/5/2015, to extend the term of the contract for 30 days, and also the deliberation that was passed at the board meeting of june 4, 2015, regarding over and underwork. the last rectification measurement self of 06/25/2015. the provisional reception was drawn up on 06/25/2015, at the initiative of this city council. | the value of the project was the result of the project carried out on it.
4969 | 876763 | Construction of the school center of folgosa - eb1 and ji - nucleus of the church in the parish of folgosa | 45214210-5 | Primary school construction work | FALSE | 2011 | 2015 | Portugal | Maia | Porto | 13 | 20 | 31-10-2013 | 27-05-2015 | 573 | 365 | 1464000 | 1244400 | 3 | 1244225.82 | 174.18 | 100.014 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project began on january 29, 2014, there were 12 work inspection and measurement notices, relating to contract no. of march 2015, which corresponds to unforeseen works of the same type that implied an extension of the deadline. | the value of the contract is the result of the projects carried out in it.
4970 | 873765 | streetAntónio Vinhas - Vilarinho das Cambas | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 12 | 28-10-2013 | 20-05-2015 | 569 | 250 | 355500 | 320503.29 | 2 | 320503.2 | 0.09 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed ahead of schedule. | rounding: €0.09
4971 | 873341 | En261, km 10+530 to km 27+275. Improvement. Weather 2012-2013 | 45233142-6 | Road-repair works | FALSE | 2013 | 2015 | Portugal | Grandola | Setúbal | 17 | 25 | 30-09-2013 | 07-08-2015 | 676 | 60 | 675000 | 637072.42 | 2 | 625963.12 | 11109.3 | 101.7748 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather from december 2013 prevented paving and road marking work from being carried out while maintaining the quality level stipulated in the ec. | the additional map was submitted due to the correction of initially contracted quantities.
4972 | 872399 | Contract n.º 3/DP/2012 - Rehabilitation of the Creixomil Neighborhood - Guimarães | 45453000-7 | Overhaul and refurbishment work | FALSE | 2012 | 2015 | Portugal | Guimarães | Braga | 3 | 30 | 29-07-2013 | 30-06-2015 | 701 | 270 | 1628549 | 1103880.09 | 3 | 1103880.09 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | difficulty in articulating with the tenants in the execution of some tasks, namely the application of the frames.
4973 | 871089 | Requalification of the health unit of Santa Catarina da Serra, Leiria | 45215100-8 | Construction work for buildings relating to health | FALSE | 2013 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 25-10-2013 | 05-01-2015 | 437 | 150 | 280000 | 212400 | 1 | 212400 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | delay in work
4974 | 867565 | Construction of the "Silva Escura/Dornelas and Talhadas wastewater drainage network – Sever do Vouga - 2nd Phase – Talhadas – Water and Sanitation". | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2013 | 2015 | Portugal | Sever do Vouga | Aveiro | 1 | N/A | 02-10-2013 | 17-09-2015 | 715 | 365 | 2500000 | 2050000 | 3 | 1686898.61 | 363101.39 | 121.5248 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
4975 | 866689 | Trofa Educational Center | 45214200-2 | Construction work for school buildings | FALSE | 2013 | 2015 | Portugal | Águeda | Aveiro | 1 | 36 | 21-10-2013 | 16-11-2015 | 756 | 365 | 2327462.48 | 1587870.59 | 3 | 907254.92 | 680615.67 | 175.0192 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration of the execution period of the project resulted from the approval of the map of works amis and works of correction of errors and omissions n.º 1. | the value of the project has changed due to the approval of additional work and work to correct errors and omissions identified in map no. 1 and contemplated in additional contract no. 4/2015/cma.
4976 | 866549 | Requalification of the health unit of Caranguejeira, Leiria | 45215100-8 | Construction work for buildings relating to health | FALSE | 2013 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 21-10-2013 | 27-01-2015 | 463 | 150 | 280000 | 249900 | 1 | 249900 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions
4977 | 864057 | Replace the current natural lawn with a synthetic lawn, including the implementation of an irrigation system and peripheral drainage network | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Esposende | Braga | 3 | 22 | 17-10-2013 | 01-07-2015 | 622 | 60 | 275000 | 269874.07 | 2 | 269874.07 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project the last work measurement report is from december 2013
4978 | 861491 | Safeguarding and enhancing the Torre dos Alcoforados Monument - Phase 1, Paredes | 45262690-4 | Refurbishment of run-down buildings | FALSE | 2013 | 2015 | Portugal | Paredes | Porto | 13 | 30 | 07-10-2013 | 31-07-2015 | 662 | 270 | 306531.64 | 241545.12 | 1 | 239593.8 | 1951.32 | 100.8144 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the strong weather that was felt in the region forced to reduce the pace of execution of the contract | execution of works
4979 | 858299 | EN255-1 - Paving between Moura and Sobral da Adiça (km 0+600 to 21+400) | 45233220-7 | Surface work for roads | FALSE | 2010 | 2015 | Portugal | Beja | Beja | 2 | 48 | 11-07-2013 | 02-10-2015 | 813 | 180 | 1160000 | 964366.46 | 2 | 864507.64 | 99858.82 | 111.5509 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | total of 67 days relating to two extensions of time granted gracefully by the developer, mainly due to the market situation in the public works sector, and also due to adverse weather conditions that occurred at a certain stage of the project | clearance of additional work in the amount of €4,991.50, work to correct errors and omissions in the amount of €639,881.21 and work to correct errors and omissions in the amount of €744,731.53
4980 | 855510 | Improvement of Av.ª Vale do Caima, from the Roundabout of the Market to the Roundabout of Entre Pontes | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Vale de Cambra | Aveiro | 1 | 36 | 27-06-2013 | 20-10-2015 | 845 | 75 | 345500 | 253874.55 | 2 | 229125.55 | 24749 | 110.8015 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the alteration to the execution period of the project is due to changes in the horizontal signage, which were requested by the municipalities during the course of the project. | no work was carried out on the hydraulic networks.
4981 | 855107 | Construction of the Interpretation Center of the Route of the Romanesque in Abragão | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2013 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 02-09-2013 | 14-04-2015 | 589 | 540 | 349980.04 | 313605.61 | 2 | 222826.66 | 90778.95 | 140.7397 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Revocation of the Contract) | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contract revocation | execution of works
4982 | 846117 | Construction of the Gondifelos Kindergarten | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 26-09-2013 | 13-05-2015 | 594 | 365 | 387000 | 348096.06 | 2 | 281570.25 | 66525.81 | 123.6267 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work within a period of 55 days, under paragraph a) of article 297 of the "public procurement code". | contractual work not carried out in the amount of €66,525.81.
4983 | 845933 | Construction of the irivo school center | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 27-09-2013 | 30-07-2015 | 671 | 400 | 1972117.38 | 1317408.33 | 3 | 1317408.33 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions leading to suspension and extensions.
4984 | 843530 | Construction of the boelhe school center | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 27-09-2013 | 28-09-2015 | 731 | 360 | 1703950.65 | 1250895.59 | 3 | 1250895.59 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A | there were 4 extensions in the project.
4985 | 843516 | Rehabilitation of the CM: 1480 (1st phase) - Gavião | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 26-09-2013 | 20-05-2015 | 601 | 365 | 377000 | 339750 | 2 | 339750 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed ahead of schedule. | decrease in the value of the project, in the amount of €1,332.10, due to the price review.
4986 | 843487 | Construction of the pine school center | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 27-09-2013 | 28-09-2015 | 731 | 360 | 2145792.47 | 1550802.26 | 3 | 1550802.26 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 33 | N/A | N/A | N/A | N/A | N/A | N/A | different soil than expected, adverse weather conditions, late expropriation agreement and lack of definition of a specialized exterior street layout project.
4987 | 843458 | Construction of the two church school center | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Penafiel | Porto | 13 | 30 | 27-09-2013 | 29-07-2015 | 670 | 360 | 1800957.78 | 1266836.62 | 3 | 1266836.62 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 30 | N/A | N/A | N/A | N/A | N/A | N/A | climate difficulties, geological difficulties.
4988 | 842489 | Public tender for the execution of the contract "Requalification for the enhancement of the public spaces surrounding the Marmoiral de Sobrado, Aveiro, Castelo de Paiva, Sobrado" | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Castelo de Paiva | Aveiro | 1 | 30 | 02-09-2013 | 12-11-2015 | 801 | 300 | 539512.1 | 397706.58 | 2 | 394477.7 | 3228.88 | 100.8185 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions conditioned the pace of work execution. | negative price review
4989 | 841005 | In addition to preparatory work (site, signage, safety and health plans and construction and demolition waste), the intervention on the road includes earthworks, drainage | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Penacova | Coimbra | 6 | 24 | 09-09-2013 | 11-11-2015 | 793 | 180 | 1100000 | 726329.37 | 2 | 666985.64 | 59343.73 | 108.8973 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | although the project was completed on 06/30/2014, it was only provisionally received on 11/11/2015 essentially for the following reasons: (1) delay in the preparation and delivery of the final screens; (2) need to correct some anomalies regarding vertical signage; (3) delay in submitting test results for some of the bituminous material. | existence of underworks.
4990 | 838749 | Rehabilitation of Cineteatro António Lamoso/CCTAR - Theater and Street Arts Creation Center - Pole 2 | 45210000-2 | Building construction work | FALSE | 2013 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 30 | 24-09-2013 | 13-05-2015 | 596 | 270 | 1000000 | 952642.9 | 2 | 986538.16 | -33895.26 | 96.5642 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the development of the projects for reasons imputed to the owner of the project for the elaboration of the hvac project. | increased costs arising from the execution of unforeseen work and to supply errors and omissions. cost reduction motivated by fewer seats in the auditorium and not revising the existing hvac.
4991 | 836578 | Requalification of the Municipal Road Network - Carpet Plan 2013 | 45233252-0 | Surface work for streets | FALSE | 2013 | 2015 | Portugal | Coimbra | Coimbra | 6 | 24 | 31-05-2013 | 29-05-2015 | 728 | 180 | 700000 | 489092.94 | 2 | 484842.33 | 4250.61 | 100.8767 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions | price review
4992 | 832748 | Refurbishment contract for the 6th floor of the Neoclassical Building | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Porto | Porto | 13 | 23 | 06-09-2013 | 30-09-2015 | 754 | 150 | 1521000 | 1129991.3 | 3 | 1129991.3 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
4993 | 832443 | Improvement of Accesses and Tours | 45233252-0 | Surface work for streets | FALSE | 2013 | 2015 | Portugal | Vila Nova de Paiva | Viseu | 20 | 9 | 11-09-2013 | 29-09-2015 | 748 | 90 | 169000 | 150682.31 | 1 | 130943.64 | 19738.67 | 115.0742 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions and delay in the diversion of edp and pt infrastructures | over and underwork
4994 | 832054 | Iberian nature, tourism and adventure park - Mirandês donkey complex | 45212120-3 | Theme park construction work | FALSE | 2012 | 2015 | Portugal | Vimioso | Bragança | 4 | 30 | 12-09-2013 | 19-05-2015 | 614 | 300 | 340750.03 | 277418.62 | 2 | 277418.62 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A | extension
4995 | 831066 | Construction of a cycle path and improvement of the Atlantic road over a length of 900 meters | 45233140-2 | Roadworks | FALSE | 2013 | 2015 | Portugal | Marinha Grande | Leiria | 10 | 20 | 29-08-2013 | 13-03-2015 | 561 | 120 | 301146.03 | 243999.98 | 1 | 235708.7 | 8291.28 | 103.5176 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes in the period of execution of the project | due to price revisions, errors and omissions supply work, extra work and work suppression
4996 | 830587 | "Urban Requalification of the Surrounding Area of ​​Nas Quatro Estradas Station" | 45315600-4, 45233251-3 | Low-voltage installation work, Resurfacing works | FALSE | 2013 | 2015 | Portugal | Loulé | Faro | 8 | 36 | 05-09-2013 | 13-02-2015 | 526 | 180 | 366705 | 257777.51 | 2 | 247982.64 | 9794.87 | 103.9498 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension, as the projectloads and equipment associated with the contract work plan were not complied with. | work not carried out by order of the representative of the client of the project, paragraph 1 of article 379 of the "public procurement code".
4997 | 829519 | Construction of the interpretive center of the argoselo mines | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2012 | 2015 | Portugal | Vimioso | Bragança | 4 | 30 | 03-09-2013 | 21-04-2015 | 595 | 365 | 284850 | 249105.84 | 1 | 249105.84 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension request
4998 | 827325 | Integrated Center for Valuing Manhose Pebble Resources | 45212110-0 | Leisure centre construction work | FALSE | 2013 | 2015 | Portugal | Vila Flor | Bragança | 4 | 23 | 03-09-2013 | 31-08-2015 | 727 | 240 | 193129.69 | 171980 | 1 | 171979.98 | 0.02 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extension of time | additional works amounting to 8565.80 + vat.
4999 | 826495 | Refurbishment of the water supply network and branches of the Outil ZMC | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2013 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 20 | 04-09-2013 | 09-02-2015 | 523 | 150 | 370000 | 328727.9 | 2 | 328727.9 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions
5000 | 826430 | The present project intends to restore the structural axis between the station building and the entrance to the Vidago Palace, proposing the leveling of the track and sidewalks | 45232451-8 | Drainage and surface works | FALSE | 2012 | 2015 | Portugal | Chaves | Vila Real | 19 | 30 | 09-09-2013 | 29-06-2015 | 658 | 365 | 2495700 | 1920530.34 | 3 | 1928295.45 | -7765.11 | 99.5973 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extensions and correction of errors and omissions | supply of errors and omissions in the amount of €7,765.11
5001 | 826192 | Contract for the modernization of the infrastructures of block 4 of the odivelas hydro-agricultural development | 45240000-1 | Construction work for water projects | FALSE | 2013 | 2015 | Portugal | Ferreira do Alentejo | Beja | 2 | 30 | 23-08-2013 | 21-05-2015 | 636 | 480 | 9724000 | 8349819.75 | 3 | 8075567.07 | 274252.68 | 103.3961 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions, insufficient workload, difficulties in the supply of some materials. | the quantities measured in the project, in some items, proved to be higher than the quantities executed on site.
5002 | 823669 | Refurbishment work on the kitchen eb1 nº 14 - o Leão de arroios, located in Largo do Leão | 45212422-0 | Canteen construction work | FALSE | 2013 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 26-08-2013 | 18-06-2015 | 661 | 120 | 301226.33 | 183982.55 | 1 | 166213.11 | 17769.44 | 110.6908 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A
5003 | 823363 | 1. The object of this tender is the construction of a landfill for ordinary waste that will correspond to cell no. | 45222100-0 | Waste-treatment plant construction work | FALSE | 2013 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | 35 | 28-08-2013 | 19-03-2015 | 568 | 120 | 1250000 | 875000 | 2 | 875000 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were two requests for a deadline extension, one for 37 days and the other for 21 days due to the impossibility of transporting explosive substances by sea. impossibility of proceeding with the application of waterproofing screens due to atmospheric constraints in the period from 3/31/14 to 4/6/14.
5004 | 822110 | Rehabilitate the Market by providing it with better functional conditions and improving the provision of services to its users | 45213141-3 | Covered market construction work | FALSE | 2011 | 2015 | Portugal | Montijo | Setúbal | 17 | 49 | 15-06-2012 | 27-05-2015 | 1076 | 365 | 862004.08 | 643396.82 | 2 | 643396.82 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 22 | N/A | N/A | N/A | N/A | N/A | N/A | a contractual position was assigned and compliance with all legal formalities determined the verification of delays in the project plan, so it was necessary to provide the contract with a new work plan adapted to the current circumstances of the project. the contractor complied with the new plan presented.
5005 | 816105 | Expansion of Salir elementary school | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Loulé | Faro | 8 | 30 | 28-03-2013 | 24-08-2015 | 879 | 360 | 598000 | 398001.99 | 2 | 392739.09 | 5262.9 | 101.34 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to difficulties in the delivery of materials in some phases of the project | replacement of construction methods and techniques and/or materials provided for in the terms of reference and in the project by others that it deems more appropriate, without prejudice to obtaining the final characteristics specified for the project
5006 | 812882 | School of the 1st CEB of Santa Cruz - Remodeling and Expansion | 45210000-2 | Building construction work | FALSE | 2012 | 2015 | Portugal | Coimbra | Coimbra | 6 | 24 | 24-07-2013 | 16-06-2015 | 692 | 270 | 705940 | 599624.15 | 2 | 597639.94 | 1984.21 | 100.332 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions and acquisition of materials | value of over and under works.
5007 | 810624 | Roundabout on streetDr. Joaquim Carlos Wedge Cerqueira | 45233128-2 | Roundabout construction work | FALSE | 2013 | 2015 | Portugal | Arcos de Valdevez | Viana do Castelo | 18 | 20 | 06-08-2013 | 11-09-2015 | 766 | 90 | 340000 | 255001.08 | 2 | 245853.1 | 9147.98 | 103.7209 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in meeting partial deadlines for the project, justified by the contractor with changes to the project, adverse weather conditions, the volume of traffic on site and the difficulty in supplying directional signs. | over and underwork resulting from design changes and price revisions.
5008 | 805109 | Alvega Canoe Station | 45212170-8 | Entertainment building construction work | FALSE | 2012 | 2015 | Portugal | Abrantes | Santarém | 16 | 36 | 30-07-2013 | 07-04-2015 | 616 | 210 | 332342.92 | 258819.77 | 2 | 253424.86 | 5394.91 | 102.1288 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline changes were due to the fact that the project was isolated and in a flood-prone area and to weather conditions aggravated by a severe winter. | the change in the value of the project came about as a result of the existence of underwork due to a superior decision, taken by deliberation of the chamber.
5009 | 805047 | Construction and Improvement of Sections of the Municipal Road Network - Improvement of CM 1300-1, Connection Casal da Velha/Valteira | 45233140-2 | Roadworks | FALSE | 2012 | 2015 | Portugal | Rio Maior | Santarém | 16 | 24 | 24-06-2013 | 13-07-2015 | 749 | 180 | 419068.52 | 336575.36 | 2 | 325260.42 | 11314.94 | 103.4787 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | free extension - 30 days | underwork and negative price revision
5010 | 801796 | Iberian Nature and Adventure Park - Gateway to the Terra Frio Route | 45212120-3 | Theme park construction work | FALSE | 2012 | 2015 | Portugal | Vimioso | Bragança | 4 | 30 | 22-07-2013 | 19-05-2015 | 666 | 365 | 776114.2 | 647464.77 | 2 | 647464.77 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | term extension
5011 | 800258 | Execution contract for the Stream Sanitation Subsystem | 45232410-9, 45232423-3 | Sewerage work, Sewage pumping stations construction work | FALSE | 2013 | 2015 | Portugal | Torres Novas | Santarém | 16 | N/A | 17-07-2013 | 28-08-2015 | 772 | 180 | 1800000 | 1698338.53 | 3 | 1696956.59 | 1381.94 | 100.0814 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was due to repairs, correction of defects and delivery of missing elements.
5012 | 799771 | Urban Requalification of the Municipality Headquarters (Between Praça 25 de Abril and Paços do Concelho) | 45211360-0 | Urban development construction work | FALSE | 2013 | 2015 | Portugal | Cinfães | Viseu | 20 | 30 | 18-07-2013 | 18-12-2015 | 883 | 365 | 1637473.59 | 987834.23 | 2 | 981067.67 | 6766.56 | 100.6897 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline suspension and extensions | presentation of overwork and underwork
5013 | 798894 | The contract essentially includes the rehabilitation/construction of a building located in Bobadela. A new function is foreseen for the space, transforming it into an Ethnographic Museum. | 45212313-3 | Museum construction work | FALSE | 2013 | 2015 | Portugal | Boticas | Vila Real | 19 | 21 | 26-06-2013 | 12-01-2015 | 565 | 635 | 346078.14 | 241429.29 | 1 | 241427.42 | 1.87 | 100.0008 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a change in the term of the project because of the extra work | the value has added because of the extra work
5014 | 798733 | Santa Justa Barracks - Center for the Interpretation and Active Experience of Nature - Rehabilitation of the Santa Justa Barracks | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 18 | 18-07-2013 | 06-02-2015 | 568 | 240 | 306000 | 227726.15 | 1 | 181039.14 | 46687.01 | 125.7884 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | underwork
5015 | 798680 | Cussena Valley Bridge, at em10-2 at km 0+600; ph on er379-1 at km 19+152; ph on en10 at km 14+250; ph on en378 at km 3+620 - rehabilitation/enlargement/replacement of works of art | 45262330-3 | Concrete repair work | FALSE | 2013 | 2015 | Portugal | Seixal | Setúbal | 17 | 42 | 16-07-2013 | 30-10-2015 | 836 | 150 | 435000 | 346379.3 | 2 | 385436.75 | -39057.45 | 89.8667 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | resulting from the elaboration of bill of quantities | resulting from the elaboration of bill of quantities
5016 | 798562 | North Circular - Phase 3.1 | 45233122-0 | Ring road construction work | FALSE | 2013 | 2015 | Portugal | São Brás de Alportel | Faro | 8 | 40 | 19-07-2013 | 06-03-2015 | 595 | 420 | 900000 | 669269.11 | 2 | 669269.11 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
5017 | 798132 | The purpose of the contract is to pave the streets in Moreanes. Integrates the paving of squares, parking spaces, public spaces adjoining the streets | 45233252-0 | Surface work for streets | FALSE | 2013 | 2015 | Portugal | Mértola | Beja | 2 | 30 | 17-07-2013 | 27-07-2015 | 740 | 270 | 672300 | 433436.48 | 2 | 406206.35 | 27230.13 | 106.7035 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions and specific circumstances of the execution | underwork
5018 | 795599 | Requalification of Municipal Path 1101 - Landim | 45233251-3 | Resurfacing works | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 15-07-2013 | 20-05-2015 | 674 | 365 | 406000 | 364998.1 | 2 | 364988.1 | 10 | 100.0027 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed ahead of schedule. | underwork worth €10.00
5019 | 789635 | Caminho da Carvalhosa - Lousado | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 12 | 04-07-2013 | 20-05-2015 | 685 | 365 | 536000 | 482202.3 | 2 | 475223.92 | 6978.38 | 101.4684 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the project was completed ahead of schedule. | underwork worth €6,978.38
5020 | 789467 | Restoration of the Fortress for future use as a Museum of the Sea, structural consolidation work is planned, interior and exterior coatings, carpentry, metalwork, water supply | 45453100-8 | Refurbishment work | FALSE | 2012 | 2015 | Portugal | Sesimbra | Setúbal | 17 | 20 | 12-04-2013 | 26-05-2015 | 774 | 210 | 986630.49 | 735876.25 | 2 | 810930.6 | -75054.35 | 90.7447 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | paragraph a) art.312.º and paragraph a) paragraph 1 art. 311 of the "public procurement code" | n.º 1 point c) n.º 2 art. 370.º and nº 3 art. 376.º, paragraph d) nº 2 art. 377.º and nº 1 art. 378 of the "public procurement code" amended by dl 149/2012 of 12/27/2012
5021 | 788583 | Refurbishment/Expansion of the Murtede WWTP | 45232420-2 | Sewage work | FALSE | 2012 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 20 | 01-07-2013 | 27-04-2015 | 665 | 365 | 800000 | 598676.13 | 2 | 589101.86 | 9574.27 | 101.6252 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
5022 | 788287 | Connecting street between Carvalhosa and E. N. 14 - Lousado | 45233120-6 | Road construction works | FALSE | 2013 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 12 | 04-07-2013 | 20-05-2015 | 685 | 365 | 1056500 | 948460.49 | 2 | 943960.49 | 4500 | 100.4767 | lowest price | 2 | 100 | Yes (no values) | FALSE | Complete fulfillment of the contract | 13 | N/A | N/A | FALSE | FALSE | FALSE | N/A | the project was completed ahead of schedule. | underwork worth €4,500.00
5023 | 787781 | This is the requalification of several streets in order to promote the sustainable development of the municipality and increase the quality of life of the citizens, creating good accessibility | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Esposende | Braga | 3 | 22 | 03-07-2013 | 13-10-2015 | 832 | 119 | 343000 | 299780.06 | 2 | 299780.06 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the execution period of the project
5024 | 786165 | Modernization, maintenance and conservation of municipal buildings - Siza works in Leça da Palmeira - Rehabilitation of the Tea House in Boa Nova | 45453100-8 | Refurbishment work | FALSE | 2013 | 2015 | Portugal | Matosinhos | Porto | 13 | 36 | 17-06-2013 | 05-08-2015 | 779 | 180 | 414000 | 350005.15 | 2 | 350005.15 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties in obtaining details and approval of some materials, considering the specificity of the project and the architectural solutions to be carried out, and taking into account that it is a building with unique characteristics.
5025 | 785845 | Extension of Avenida PACOPAR in the Business Eco-Park of Estarreja | 45211360-0 | Urban development construction work | FALSE | 2012 | 2015 | Portugal | Estarreja | Aveiro | 1 | 45 | 21-06-2013 | 17-06-2015 | 726 | 180 | 865108.61 | 650876.47 | 2 | 558834.5 | 92041.97 | 116.4703 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions and extensions | underwork and price revision
5026 | 784713 | Conservation of the municipal road network - Improvement of the paving of the municipal road 503-1 access to Donai, Paving of the municipal road 1186 between Formil and Fontes Barrosas | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Bragança | Bragança | 4 | 20 | 17-06-2013 | 26-02-2015 | 619 | 120 | 199278.58 | 169752.24 | 1 | 169752.24 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | non-attendance of the contractor's representative for the purposes of producing the administrative acts corresponding to the formalization of the provisional acceptance of the contract.
5027 | 784426 | Execution of 68.42 km of wastewater drainage network, 40 km of lift pipes, 11 lift stations and 2800 branches. | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Ovar | Aveiro | 1 | 40 | 05-06-2013 | 01-09-2015 | 818 | 540 | 6693642 | 4016185.21 | 3 | 3995719.34 | 20465.87 | 100.5122 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | nothing to report | nothing to report
5028 | 784403 | Tresminas Interpretive Center - Polo II | 45210000-2 | Building construction work | FALSE | 2013 | 2015 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | 30 | 26-06-2013 | 14-07-2015 | 748 | 300 | 548066.37 | 447670.21 | 2 | 444670.22 | 2999.99 | 100.6747 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 21 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | job suppression
5029 | 784265 | contract work number 43/dmpo/dcme/dpe/12 - "general improvement of elementary da luz + ji do largo da luz - financing of piparu" (process no. 55/cp/deps /n.d./2012) | 45262800-9 | Building extension work | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 19-06-2013 | 09-02-2015 | 600 | 270 | 1374701.51 | 952133.53 | 2 | 1012620.06 | -60486.53 | 94.0267 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 27 | N/A | N/A | N/A | N/A | N/A | N/A
5030 | 781074 | Reorganization and Qualification Contract for the Lagoon Front of Vagos: Banks of the Boco River and Moliceiros Wharf / Folsas Novas, in the Scope of the Intervention of the Polis Litoral Ria de Aveiro | 45200000-9 | Works for complete or part construction and civil engineering work | FALSE | 2013 | 2015 | Portugal | Vagos | Aveiro | 1 | 30 | 31-05-2013 | 15-12-2015 | 928 | 210 | 515000 | 514937.04 | 2 | 571366.33 | -56429.29 | 90.1238 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions prevented work on the ground; situation of unpredictability in the foundation of the wall of cais dos moliceiros/folsas novas; out of stock in the supply of materials, | extra work
5031 | 780754 | The object of this contract is the "Gafanha da Gafanha da Nazaré and Z. I. Da Mota (PAR 004, PAR 005 and PAR 016)”. | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Ílhavo | Aveiro | 1 | 40 | 19-06-2013 | 25-09-2015 | 828 | 365 | 13247000 | 9769182.66 | 3 | 9764182.67 | 4999.99 | 100.0512 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with contracted deadlines under the responsibility of the contracting company | contracted works, not performed
5032 | 780306 | Requalification of the Training Fields of the Municipal Stadium of Amarante. | 45212290-5 | Repair and maintenance work in connection with sports facilities | FALSE | 2012 | 2015 | Portugal | Amarante | Porto | 13 | 30 | 19-06-2013 | 01-06-2015 | 712 | 180 | 1329733.59 | 926999.71 | 2 | 905972.4 | 21027.31 | 102.321 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work suspensions for 2 periods totaling 125 due to project adjustments and a 21-day delay in provisional acceptance | non-execution of works worth 21027.31 euros that proved to be unnecessary.
5033 | 780015 | Repaving of the streets Dr. Manuel Monterroso, Poet Alfredo Brochado, Acácio Lino, Archaeologist José Pinho, Alto das Murtas, Ilídio Sardoeira, Mota Alves; Pracetas Archaeologist José Pinho | 45211360-0 | Urban development construction work | FALSE | 2013 | 2015 | Portugal | Amarante | Porto | 13 | 30 | 17-06-2013 | 23-11-2015 | 889 | 180 | 905000 | 617362.87 | 2 | 611352.11 | 6010.76 | 100.9832 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work for a total of 251 days due to unfavorable weather conditions. | negative price revision worth €6,010.76
5034 | 779787 | Access to the Nadir Afonso Foundation | 45233250-6 | Surfacing work except for roads | FALSE | 2012 | 2015 | Portugal | Chaves | Vila Real | 19 | 30 | 18-06-2013 | 16-03-2015 | 636 | 150 | 770000 | 623535.4 | 2 | 639830.9 | -16295.5 | 97.4532 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extension, correction of errors and omissions and suspension of execution term.
5035 | 778109 | Construction of a water distribution network for irrigation, which consists of installing underground pipelines and supplying and assembling the respective control and protection devices | 45232121-6 | Irrigation piping construction work | FALSE | 2012 | 2015 | Portugal | Alfandega da Fé | Bragança | 4 | 30 | 05-06-2013 | 13-04-2015 | 677 | 210 | 1700000 | 1020000.01 | 3 | 992512.51 | 27487.5 | 102.7695 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 25 | N/A | N/A | N/A | N/A | N/A | N/A | decrease in income initially forecast for work due to heavy rainfall in the autumn-winter period. | in addition to some quantities estimated in excess in the project, it was also possible to optimize part of the layout of the irrigation network which, while still benefiting the entire area foreseen in the project, led to the reduction of some amounts of work.
5036 | 776627 | This involves the requalification of several streets in the parishes of Gandra, Fão, Fonte Boa and Rio Tinto, improving circulation and parking accessibility and increasing the quality of life | 45000000-7 | Construction work | FALSE | 2013 | 2015 | Portugal | Esposende | Braga | 3 | 22 | 11-06-2013 | 13-10-2015 | 854 | 150 | 345000 | 284731.43 | 2 | 283859.3 | 872.13 | 100.3072 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change to the deadline for execution of the project, in terms of the tender, the deadline presented by the contractor was 119 days, which was complied with
5037 | 775544 | Construction contract for the Baleizão-Quintos hydraulic circuit of the Foins Múltiplos do Alqueva development. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 45 | 21-05-2013 | 24-04-2015 | 703 | 426 | 22400000 | 17808719.79 | 3 | 17525676.81 | 283042.98 | 101.615 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need for a new electrical line to carry out tests. | the changes are essentially due to differences between the amounts of work planned and carried out.
5038 | 774251 | Rehabilitation of the National Guard Territorial Post in Ferreira do Alentejo | 45216000-4 | Construction work for buildings relating to law and order or emergency services and for military buildings | FALSE | 2013 | 2015 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 06-06-2013 | 15-01-2015 | 588 | 240 | 500000 | 348876.82 | 2 | 350611.25 | -1734.43 | 99.5053 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 12 | N/A | N/A | N/A | N/A | N/A | N/A | unforeseen work on the structure and adverse weather conditions | reconstruction of the pre-existing wall, which collapsed onto the public road and unforeseen work on the pre-existing building.
5039 | 774177 | The intervention consists of the functional requalification of the spa building and the surrounding area, providing it with a better adaptation to the physical and functional requirements, better security conditions | 45215110-1 | Spa construction work | FALSE | 2013 | 2015 | Portugal | Chaves | Vila Real | 19 | 30 | 06-06-2013 | 29-06-2015 | 753 | 365 | 3302000 | 2948039.84 | 3 | 2781831.19 | 166208.65 | 105.9748 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extension for 85 days approved in r.c. of 08/01/2014, + 72 days approved in r.c. of 11/21/2014, + 122 days approved in r.c. of 04/10/2015 | underwork in the amount of €155,234.15 and negative price revision in the amount of €10,974.49
5040 | 772069 | Construction contract for the irrigation, road and drainage infrastructure for blocks 1, 2 and 3 of Baleizão - Quintos. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 45 | 21-05-2013 | 06-07-2015 | 776 | 517 | 21900000 | 16887999.99 | 3 | 16470604.5 | 417395.49 | 102.5342 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the contractual period is less than the maximum execution period specified in the tender in the procedure documents, as proposed by the successful bidder who submitted a proposal for execution with a shorter period (450 days). | it results from the sum of the value of the errors and omissions supply work and the deduction of the value of the underwork from the contract price.
5041 | 771371 | Construction contract for the irrigation, road and drainage infrastructure for blocks 4 and 5 of Baleizão-Quintos. | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 45 | 21-05-2013 | 06-10-2015 | 868 | 608 | 32100000 | 22498250.53 | 3 | 22087718.15 | 410532.38 | 101.8586 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in deadline was due to an untimely supply of materials, which had repercussions on the development of the project. | the executed quantities differed in some works from the initially estimated quantities.
5042 | 771247 | Construction contract for the irrigation, road and drainage infrastructure of the Cinco Reis Trindade Block | 45240000-1 | Construction work for water projects | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 45 | 21-05-2013 | 02-06-2015 | 742 | 547 | 26900000 | 17497878 | 3 | 17736613.13 | -238735.13 | 98.654 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension resulting from the execution of work to correct errors and omissions. | carrying out work to correct errors and omissions and not carrying out underwork, namely quantities less than those estimated in the execution project.
5043 | 769661 | Construction contract for the irrigation, road and drainage infrastructure of the São Pedro Block – Baleizão. | 45232120-9 | Irrigation works | FALSE | 2012 | 2015 | Portugal | Beja | Beja | 2 | 40 | 21-05-2013 | 16-09-2015 | 848 | 540 | 25500000 | 20391675.24 | 3 | 19377939 | 1013736.24 | 105.2314 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | emergence of archaeological sites and spatial limitations of intervention not included in the initial contract | quantities of work less compared to contractual estimates.
5044 | 769455 | Interventions in the Flow Sections in Ponte do Campo, Ponte de Óis da Ribeira and in the Secondary Channel of the River Águeda "By-Pass" in Águeda - Ponte do Campo and Ponte de Óis da Ribeira. | 45221100-3 | Construction work for bridges | FALSE | 2011 | 2015 | Portugal | Águeda | Aveiro | 1 | 42 | 02-05-2013 | 08-09-2015 | 859 | 450 | 2236192.91 | 1340000 | 3 | 265706.33 | 1074293.67 | 504.3162 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Revocation of the Contract) | 17 | N/A | N/A | N/A | N/A | N/A | N/A | due to work suspensions, motivated by the construction of pillar piles with a diameter of 1500mm which, during the soil drilling phase, when passing through the muddy layer, the presence of water with high pressure and flow, dissolves the bentonite sludge. and also the floods that flooded the site of the construction works of the e1 meeting. | construction of an alternative diversion to the temporary diversion in order to minimize the inconvenience caused to populations wishing to move between óis da ribeira and travassô. carrying out tests in order to characterize the geology and hydrology at the site where the piles are installed. existence of underwork as a result of the signature of the contract revocation agreement.
5045 | 768249 | Conservation and improvement of CM 1064 to Sr.ª da Serra and EM 506 to Petisqueira | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Bragança | Bragança | 4 | 30 | 24-05-2013 | 26-02-2015 | 643 | 180 | 224145 | 162799.85 | 1 | 162799.85 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | non-attendance of the contractor's representative for the purposes of producing the administrative acts corresponding to the formalization of the provisional acceptance of the contract.
5046 | 768185 | Conservation of the municipal road network - paving of municipal road 501-1 Baçal to national road 218-3 and paving of municipal road 501 and municipal road 504 access to Varge | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Bragança | Bragança | 4 | 20 | 24-05-2013 | 19-03-2015 | 664 | 120 | 296428.95 | 247698.43 | 1 | 235950.88 | 11747.55 | 104.9788 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions. | underwork
5047 | 767509 | Several paving, alteration and improvement works of several streets in the municipality of Leiria (Lot 6) | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 24-05-2013 | 20-01-2015 | 606 | 75 | 2779294.32 | 379662.5 | 2 | 340535 | 39127.5 | 111.49 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension | underwork
5048 | 767454 | Several paving works, alteration works and improvement of several streets in the municipality of Leiria (Lot 3) | 45233220-7 | Surface work for roads | FALSE | 2013 | 2015 | Portugal | Leiria | Leiria | 10 | 20 | 24-05-2013 | 20-01-2015 | 606 | 75 | 2779294.32 | 421999.36 | 2 | 421999.36 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | elaboration of a technical study for av. sá carneiro
5049 | 766324 | Restoration of the Cine Teatro Mouzinho da Silveira | 45212322-9 | Theatre construction work | FALSE | 2011 | 2015 | Portugal | Castelo de Vide | Portalegre | 12 | 22 | 24-05-2013 | 16-03-2015 | 661 | 366 | 1250000 | 943174.1 | 2 | 960317.85 | -17143.75 | 98.2148 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | execution of additional work | performing over and underwork
5050 | 759972 | Paving streets in Corte Gafo de Cima . Integrates paving of streets , squares, parking spaces, public spaces bordering the streets , exterior arrangements, landscaping | 45233252-0 | Surface work for streets | FALSE | 2012 | 2015 | Portugal | Mértola | Beja | 2 | 30 | 10-05-2013 | 15-12-2015 | 949 | 310 | 910000 | 590890.97 | 2 | 534090.88 | 56800.09 | 110.6349 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions | underwork
5051 | 756751 | Construction of the Fenais da Luz Cultural Center - Ponta Delgada | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2012 | 2015 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 48 | 30-04-2013 | 29-01-2015 | 639 | 245 | 400000 | 365402.18 | 2 | 351237.12 | 14165.06 | 104.0329 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension. | underwork.
5052 | 756665 | Construction of the Santo António Cultural Center - Ponta Delgada | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2012 | 2015 | Portugal | Ponta Delgada | Região Autónoma dos Açores | 15 | 48 | 30-04-2013 | 23-02-2015 | 664 | 245 | 400000 | 371888.23 | 2 | 347405.37 | 24482.86 | 107.0473 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension
5053 | 755966 | Accessibility of the Riverside Villages of the Municipality of Reguengos de Monsaraz | 45233140-2 | Roadworks | FALSE | 2010 | 2015 | Portugal | Reguengos de Monsaraz | Évora | 7 | 30 | 10-04-2013 | 02-02-2015 | 663 | 270 | 1425531.35 | 1187656 | 3 | 1272248.58 | -84592.58 | 93.3509 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | need for suspension of work | price review presentation
5054 | 753390 | The works essentially consist of the construction of a pumping station consisting of a building measuring 61 X 23 m, equipped with 5 variable speed electric pump sets on a vertical axis | 45232152-2 | Pumping station construction work | FALSE | 2010 | 2015 | Portugal | Estremoz | Évora | 7 | 60 | 29-04-2013 | 17-08-2015 | 840 | 390 | 2500000 | 2028672.16 | 3 | 2028672.16 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | bad weather conditions and difficulty in delivering equipment | there were no changes to the uncivilly predicted value
5055 | 751140 | Rainwater drainage networks in streets of the parishes of arzila, assafarge, s. Martinho do Bispo, Souselas and Trazmil | 45232451-8 | Drainage and surface works | FALSE | 2012 | 2015 | Portugal | Coimbra | Coimbra | 6 | 20 | 01-04-2013 | 22-01-2015 | 661 | 150 | 550000 | 330000.01 | 2 | 308844.61 | 21155.4 | 106.8499 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties on pavements due to rainy weather. | there were works left undone
5056 | 750155 | Completion of the Refurbishment and Expansion Works of the Former Fiscal Guard Building for the Municipal Library of Ponte da Barca | 45212330-8 | Library construction work | FALSE | 2012 | 2015 | Portugal | Ponte da Barca | Viana do Castelo | 18 | 30 | 29-04-2013 | 28-07-2015 | 820 | 305 | 1072417.3 | 698999.8 | 2 | 698347.38 | 652.42 | 100.0934 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 37 | N/A | N/A | N/A | N/A | N/A | N/A | due to delays in the delivery of necessary elements by the project team | underwork
5057 | 749733 | The works consist essentially of:_x000D_ - IRRIGATION NETWORK – under pressure, for an area of ​​1 114 ha, with 7.1 km of ductile cast iron (FFd) piping for diameters equal to or greater than 450 mm and 9 | 45232120-9 | Irrigation works | FALSE | 2010 | 2015 | Portugal | Monforte | Évora | 7 | 60 | 29-04-2013 | 10-09-2015 | 864 | 540 | 6150000 | 5093041.58 | 3 | 5093041.58 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were changes to the execution period of the project due to the difficulty of access to some plots. | there were no changes to the value of the project
5058 | 746879 | Miscellaneous Paving Repairs in the Municipality of Mealhada | 45233142-6 | Road-repair works | FALSE | 2013 | 2015 | Portugal | Mealhada | Aveiro | 1 | N/A | 26-03-2013 | 06-07-2015 | 832 | 90 | 165000 | 152693.4 | 1 | 143127.15 | 9566.25 | 106.6837 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work completed beyond the contractual term, plus the extensions granted | overwork, underwork and errors and omissions supply
5059 | 745946 | construction work number 9/dmpo/dcme/dpc/2012 – “work of recovery and enhancement of the 2nd phase of the roman theater museum” (process no. 20/cp/deps/n.d./2012) | 45212313-3 | Museum construction work | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 16-04-2013 | 02-12-2015 | 960 | 250 | 654285.18 | 392571.18 | 2 | 539354.2 | -146783.02 | 72.7854 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A
5060 | 745626 | Construction of the Municipal Museum of Santa Cruz das Flores | 45212313-3 | Museum construction work | FALSE | 2013 | 2015 | Portugal | Santa Cruz das Flores | Região Autónoma dos Açores | 15 | 20 | 11-04-2013 | 09-02-2015 | 669 | 365 | 1777905.57 | 1772000 | 3 | 1694271.04 | 77728.96 | 104.5878 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the deadline for carrying out additional work.
5061 | 743816 | Refurbishment of the water supply networks for human consumption and the drainage networks for waste and rainwater, on the section between Chafariz Velho and Ladeira Branca. | 45232151-5 | Water-main refurbishment construction work | FALSE | 2012 | 2015 | Portugal | Angra do Heroismo | Região Autónoma dos Açores | 15 | N/A | 30-01-2013 | 11-05-2015 | 831 | 360 | 1022000 | 952447.06 | 2 | 952447.06 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | serious financial difficulties for the contractor, which resulted in difficulties in acquiring the materials necessary for the execution of the project and consequent failure to meet the execution deadline, which led to the assignment of the contractual position, as the contractor did not meet the conditions to proceed with the contract.
5062 | 743640 | Requalification of the Public Lighting Network of the Urban Center of Vila de Odemira | 45316100-6 | Installation of outdoor illumination equipment | FALSE | 2012 | 2015 | Portugal | Odemira | Beja | 2 | 40 | 28-01-2013 | 12-01-2015 | 714 | 120 | 430448.72 | 284956.2 | 2 | 284956.2 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | underworks left to finish
5063 | 742038 | Requalification of the coastline - Boa Nova beach car park | 45223300-9 | Parking lot construction work | FALSE | 2013 | 2015 | Portugal | Matosinhos | Porto | 13 | 12 | 11-04-2013 | 28-07-2015 | 838 | 45 | 329300 | 197580 | 1 | 197580 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | no change
5064 | 739042 | contract no. 5/dmpo/dcme/dce/2012 – “miscellaneous works for the installation of the information center of the integrated project cerca velha, casa dos bicos, floor 0 - financing of piparu” | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 27-03-2013 | 16-04-2015 | 750 | 120 | 470409.91 | 263900.01 | 2 | 242363.73 | 21536.28 | 108.8859 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A
5065 | 738520 | Er 385 – Pontoon on the ravine of Sobral da Adiça. En 255 – Penknives Pontoon. Replacement of works of art | 45221100-3 | Construction work for bridges | FALSE | 2012 | 2015 | Portugal | Serpa | Beja | 2 | 36 | 11-03-2013 | 20-02-2015 | 711 | 120 | 360000 | 294148 | 2 | 290645.7 | 3502.3 | 101.205 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | difficulties related to the mobilization of equipment for the execution of piles, with the market given the deactivation of the nearest concrete plant and with the complexity in terms of assembling reinforcements and formwork for the abutments, in view of the solution designed in a pronounced bias of the project of art - sobral da adiça bridge | underwork (-17,513.58 €) relating to the adjustment of the lining of ribeira da ponte do barranco do sobral da adiça to the existing one, upstream and downstream. additional works at agreed prices (17,509.50 €) relating to the adjustment of the cladding of the ribeira da ponte do barranco do sobral da adiça to the existing one, upstream and downstream. work to supply errors and omissions resulting from the adjustment of the drainage of the track at pontão dos canivetes and modeling of wing walls, the replacement of carp tail terminals by output terminals for dpm and the final measurement of the project.
5066 | 738027 | construction/rehabilitation | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 08-04-2013 | 06-11-2015 | 942 | 300 | 1298500 | 1058741.99 | 3 | 1033397.3 | 25344.69 | 102.4526 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather changes
5067 | 737183 | Construction of Gimnodesportivo da Ribeira | 45212225-9 | Sports hall construction work | FALSE | 2012 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 21 | 06-02-2013 | 30-10-2015 | 996 | 240 | 665000 | 573079.61 | 2 | 560888.18 | 12191.43 | 102.1736 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | over and underwork
5068 | 737162 | Construction of the Facha Gymnasium | 45212225-9 | Sports hall construction work | FALSE | 2012 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 21 | 11-01-2013 | 29-10-2015 | 1021 | 240 | 630000 | 526651.98 | 2 | 516833.78 | 9818.2 | 101.8997 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
5069 | 734040 | Roundabouts on the EN 234, in Canas de Senhorim - Paving | 45233220-7, 45000000-7 | Surface work for roads, Construction work | FALSE | 2012 | 2015 | Portugal | Nelas | Viseu | 20 | 22 | 15-03-2013 | 19-05-2015 | 795 | 180 | 370000 | 333000 | 2 | 309331.4 | 23668.6 | 107.6515 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | successive extensions. | underwork
5070 | 732397 | The purpose of the contract is the rehabilitation of the water supply network, the execution of the domestic wastewater and rainwater drainage networks, and the paving of streetRei Ramiro. | 45232130-2 | Storm-water piping construction work | FALSE | 2012 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 24 | 19-03-2013 | 01-06-2015 | 804 | 120 | 550000 | 349968.23 | 2 | 349649.63 | 318.6 | 100.0911 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extensions for the contract for 150+60 days, as decided by the board of directors, due to weather conditions and also due to other city council works that interfered with the contract. | the total effective price of the contract includes the value of €-317.93, related to the price revision, in accordance with paragraph 1 of article 382. of the "public procurement code"
5071 | 716629 | Requalification of streetVisconde Moreira de Rei and street of Combatentes da Grande Guerra | 45211360-0 | Urban development construction work | FALSE | 2012 | 2015 | Portugal | Fafe | Braga | 3 | 30 | 14-03-2013 | 18-05-2015 | 795 | 180 | 717186.11 | 511827.46 | 2 | 458244.5 | 53582.96 | 111.6931 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a partial suspension of work for 60 days | there was underwork
5072 | 716007 | Renovation of Primary Schools of the Século - Póvoa de Varzim - ref. CP011/11 | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 30 | 06-03-2013 | 23-04-2015 | 778 | 426 | 2160000 | 1598000 | 3 | 1572014.84 | 25985.16 | 101.653 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
5073 | 714702 | Requalification and networks in the Z.I. From Cavadas, streetde Cavadas, streetand Praceta José Manuel Costa | 45232451-8 | Drainage and surface works | FALSE | 2012 | 2015 | Portugal | Fafe | Braga | 3 | 30 | 15-03-2013 | 26-02-2015 | 713 | 180 | 387623.14 | 288474.36 | 2 | 288473.6 | 0.76 | 100.0003 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period | there were no changes to the value of the project
5074 | 711834 | Containment of banks and placement of removable platforms over the river. | 45242000-5 | Waterside leisure facilities construction work | FALSE | 2012 | 2015 | Portugal | Resende | Viseu | 20 | 30 | 12-12-2012 | 20-07-2015 | 950 | 300 | 320000 | 298562.34 | 2 | 298562.34 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension of work for safety reasons | underwork
5075 | 709536 | Widening and paving of street of Junqueira, in Várzea. | 45233220-7 | Surface work for roads | FALSE | 2011 | 2015 | Portugal | Barcelos | Braga | 3 | 60 | 01-03-2013 | 12-03-2015 | 741 | 365 | 318271 | 257000.05 | 2 | 257000.05 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | security conditions in execution.
5076 | 709132 | Construction of the elementary school of the Northeast of the Municipality - Fráguas (School Center No. 4) | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Rio Maior | Santarém | 16 | 30 | 21-12-2012 | 23-01-2015 | 763 | 365 | 1096991.81 | 959059.78 | 2 | 945652.25 | 13407.53 | 101.4178 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the contractual term | underwork
5077 | 705560 | The contract refers to the expansion and requalification of an existing equipment (elementary school nº 1 of Benavente), which will include 11 rooms for the 1st Cycle of Basic Education with the respective areas of fine arts. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Benavente | Santarém | 16 | 30 | 14-01-2013 | 08-07-2015 | 905 | 300 | 1223750 | 993851.26 | 2 | 990397.47 | 3453.79 | 100.3487 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the execution period was mainly due to atmospheric conditions and the financial condition of the company (approval of the per requested by the company). | the change in the value of the project was due to the decrease in underwork (3,505.47 €) and the increase due to the revision of prices in the amount of €51.68
5078 | 687822 | Requalification Project for the Forest Park and Mata da Carvalhada. | 45233200-1 | Various surface works | FALSE | 2012 | 2015 | Portugal | Vila Pouca de Aguiar | Vila Real | 19 | N/A | 07-02-2013 | 04-09-2015 | 939 | 300 | 346792.68 | 277434.14 | 2 | 277434.16 | -0.02 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in delivery of materials by suppliers. | rounding.
5079 | 657490 | Contract refers to the expansion and requalification of the elementary school Fonte dos Escudeiros, in Samora Correia, comprising 7 rooms for the 1st cycle of basic education with the respective areas of plastic arts | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Benavente | Santarém | 16 | 30 | 08-11-2012 | 16-06-2015 | 950 | 300 | 800800 | 729982.2 | 2 | 712675 | 17307.2 | 102.4285 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | vandalism and thefts occurred in the contract; lack of project definitions, extended delivery times for materials, due to the current situation and lack of stock by manufacturers. the moisture content did not allow the application of vinyl floors; the competent authorities failed to carry out the connections to the existing infrastructures. | underwork worth €16,816.00, whose implementation, by decision of the project client and with the agreement of the contractor, turned out to be unnecessary. it should be noted that there is still maintenance to be invoiced, worth € 491.20.
5080 | 651396 | Conservation and Maintenance of the Sanitation Network in the Central Area of ​​the City of Lisbon | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 21 | 20-12-2012 | 21-05-2015 | 882 | 365 | 690044.24 | 415572.44 | 2 | 415572.44 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A
5081 | 648921 | The object of this contract is the construction of a wastewater drainage network with a total length of around 34,233m in PPc (2,512m DN160, 30,944m DN200, 649m DN250 and 127m DN315) | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2011 | 2015 | Portugal | Murtosa | Aveiro | 1 | 41 | 16-11-2012 | 31-03-2015 | 865 | 480 | 5900000 | 4325824.07 | 3 | 4294212.01 | 31612.06 | 100.7362 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | contractual deadlines not met by the contracting company, due to technical difficulties. | works not performed.
5082 | 648485 | Basic Infrastructures and Environmental Protection of the Parish of Ponte de Sor - Basic Infrastructures South/West | 45231110-9 | Pipelaying construction work | FALSE | 2012 | 2015 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 13-11-2012 | 16-10-2015 | 1067 | 180 | 1213202.08 | 1037407.51 | 3 | 1037407.51 | 0 | 100 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
5083 | 647471 | Ponte de Sor Municipal Airfield - 2nd Phase - ILS/DME- Aircraft Landing Assistance System | 45317000-2 | Other electrical installation work | FALSE | 2011 | 2015 | Portugal | Ponte de Sor | Portalegre | 12 | 50 | 19-12-2012 | 17-04-2015 | 849 | 180 | 620000 | 581870 | 2 | 581870 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | deadline extension
5084 | 732419 | Contract for Execution of Supply and Sanitation Infrastructures in Almeirim and Alpiarça | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Almeirim | Santarém | 16 | 48 | 30-07-2012 | 22-06-2015 | 1057 | 150 | 3100000 | 2167702.09 | 3 | 2149062.2 | 18639.89 | 100.8673 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was derived from repairs, correction of defects and delivery of missing elements. | the project was carried out in its entirety, not requiring the invoicing of all items.
5085 | 732432 | The object of the contract is the execution of the connection of the drainage networks of domestic wastewater and rainwater from AUGI – Área Urbana de Génese Ilegal da Serra do Pilar to the Quebrantões Wharf | 45233140-2 | Roadworks | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 40 | 27-12-2012 | 20-01-2015 | 754 | 90 | 320000 | 243993.49 | 1 | 235083.02 | 8910.47 | 103.7904 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the siphon equipment had to be made to measure and it was only on this date that it was supplied and installed. | there were works that were not necessary to perform.
5086 | 645894 | Execution contract for the Chamusca, Vale de Cavalos and Ulme Supply Subsystem | 45220000-5 | Engineering works and construction works | FALSE | 2012 | 2015 | Portugal | Chamusca | Santarém | 16 | 48 | 21-12-2012 | 23-10-2015 | 1036 | 150 | 2500000 | 1986985.08 | 3 | 1951218.22 | 35766.86 | 101.8331 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the time that elapsed between the end of the contract period and the provisional acceptance was due to repairs, correction of defects and delivery of missing elements.
5087 | 645547 | Contract for the refurbishment, expansion and reinforcement of the water supply flow of the municipality's agglomerations - UPLET HOLE (Electrical installations and equipment) AND RESERVOIR RR4-A - RESERVOIR | 45247270-3 | Reservoir construction works | FALSE | 2012 | 2015 | Portugal | Lajes do Pico | Região Autónoma dos Açores | 15 | 30 | 05-12-2012 | 15-10-2015 | 1044 | 180 | 374847 | 360366.46 | 2 | 360366.46 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions and suspension of the term of execution of the project.
5088 | 643196 | Mobility in Matosinhos streets surrounding the EB of Matosinhos | 45233142-6 | Road-repair works | FALSE | 2011 | 2015 | Portugal | Matosinhos | Porto | 13 | 36 | 09-07-2012 | 15-09-2015 | 1163 | 122 | 301000 | 238541.7 | 1 | 226882.37 | 11659.33 | 105.1389 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change | the total value of the projects carried out was €240,495.31, of which: - €223,756.39, related to the invoicing of normal work; - €14,785.31, for underwork; - €3,125.98, for price revisions; - €13,612.94, with respect to vat.
5089 | 640099 | Construction of drainage networks at Vale Figueiras and Aiana, with delivery of effluents to the existing Alta da Simarsul System. | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Sesimbra | Setúbal | 17 | 30 | 11-09-2012 | 04-09-2015 | 1088 | 300 | 1680000 | 1144825.44 | 3 | 1200950.19 | -56124.75 | 95.3266 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | unforeseeable circumstances, with the existence of local constraints, making it necessary to make specific changes in the nature of the project to be carried out. | unforeseeable circumstances, with the existence of local constraints, making it necessary to make specific changes in the nature of the project to be carried out.
5090 | 640096 | Complement of the drainage networks of the places between Cabedal/Carrasqueira and Almoinha/Cotovia, with delivery of the effluents in the already existing System in Alta da Simarsul. | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Sesimbra | Setúbal | 17 | 30 | 22-10-2012 | 06-01-2015 | 806 | 270 | 880000 | 790573.43 | 2 | 823701.22 | -33127.79 | 95.9782 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A | unforeseeable circumstances, with the existence of local constraints, making it necessary to make specific changes in the nature of the project to be carried out. | unforeseeable circumstances, with the existence of local constraints, making it necessary to make specific changes in the nature of the project to be carried out.
5091 | 634954 | ER393 - Vila Nova de Milfontes Bridge. Rehabilitation and Reinforcement of the Work of Art. | 45221119-9 | Bridge renewal construction work | FALSE | 2011 | 2015 | Portugal | Odemira | Beja | 2 | 48 | 22-11-2012 | 28-08-2015 | 1009 | 365 | 1790000 | 1397529.42 | 3 | 1211531.65 | 185997.77 | 115.3523 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | total of 302 days relating to 4 extensions of time granted gracefully by the developer, mainly due to the situation of the company (per), also taking into account the difficult market situation in the public works sector, and also due to weather conditions adverse events that occurred in a certain phase of the project. | the change in the value of the project was due to the calculation of additional works worth €226,117.44, positive errors and omissions repair work worth €39,387.72, negative errors and omissions repair work in the €131,098.07 and underwork worth €320,404.86
5092 | 632315 | The object of this contract concerns the execution of the sewage, paving and paving network. | 45232410-9 | Sewerage work | FALSE | 2012 | 2015 | Portugal | Cadaval | Lisboa | 11 | 20 | 05-12-2012 | 21-01-2015 | 777 | 180 | 618979.26 | 372283.32 | 2 | 363791.41 | 8491.91 | 102.3343 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions and appearance of aqueducts and other unknown ancient infrastructures | work that was not carried out because during the course of the project it was verified that they were not necessary
5093 | 625871 | Execution of the contract “Sanitation of the Parish of Castelo - Execution of the drainage networks of the Municipality of Sesimbra – Lagoa de Albufeira – 2nd. Phase - North Interceptor and Sachola and Avenidas Casalão | 45232460-4 | Sanitary works | FALSE | 2012 | 2015 | Portugal | Sesimbra | Setúbal | 17 | 30 | 10-10-2012 | 05-05-2015 | 937 | 270 | 1416960 | 912658.51 | 2 | 785849.08 | 126809.43 | 116.1366 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 15 | N/A | N/A | N/A | N/A | N/A | N/A | review of the eear3 project, as well as the exact definition of their implementation | due to underwork
5094 | 625274 | As part of the Environmental and Territorial Enhancement and Qualification Program - Actions to Enhance the Coast of Vila Nova de Gaia, the Recovery of the Ecological Corridor of Ribeira de Atiâ | 45233200-1 | Various surface works | FALSE | 2012 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 22-11-2012 | 26-05-2015 | 915 | 90 | 165000 | 151155.1 | 1 | 149857.75 | 1297.35 | 100.8657 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | situations that prevented the normal development of the projects, namely agreements with the owners of the land affected by the project, felling of trees that were the responsibility of the land owners and the drainage to be carried out on site by the municipal company apbg | underwork
5095 | 623964 | Elaboration of Specialty Execution Projects and the Contract for the Construction of the Anta School Center | 45214000-0 | Construction work for buildings relating to education and research | FALSE | 2011 | 2015 | Portugal | Espinho | Aveiro | 1 | 48 | 26-06-2012 | 09-03-2015 | 986 | 480 | 3629931 | 3266805.52 | 3 | 3266805.52 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | term extension totaling 178 days to the contract.
5096 | 618646 | Preliminary Works, Demolitions, Earthworks, Drainage System, Irrigation System, Paving, Fences, Sports Equipment, Electric Network. | 45112720-8 | Landscaping work for sports grounds and recreational areas | FALSE | 2011 | 2015 | Portugal | Figueira da Foz | Coimbra | 6 | 25 | 19-11-2012 | 26-03-2015 | 857 | 180 | 534207.38 | 485423.54 | 2 | 495958.43 | -10534.89 | 97.8759 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the suspension of work | due to the execution of works more
5097 | 611888 | The object of this contract is the construction of a wastewater drainage network with a total length of 68.42 km and about 2800 home branches with the respective manholes | 45232400-6 | Sewer construction work | FALSE | 2011 | 2015 | Portugal | Ovar | Aveiro | 1 | 41 | 04-10-2012 | 13-02-2015 | 862 | 365 | 7000000 | 4577769 | 3 | 4476082.31 | 101686.69 | 102.2718 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 20 | N/A | N/A | N/A | N/A | N/A | N/A | non-compliance with contractual deadlines, responsibility of the awarding company | contracted works, not performed
5098 | 608317 | Construction of an auditorium, car park and arrangement of the surrounding area | 45212321-2 | Auditorium construction work | FALSE | 2012 | 2015 | Portugal | Peso da Régua | Vila Real | 19 | 20 | 30-10-2012 | 03-08-2015 | 1007 | 540 | 4626109.12 | 3594918.53 | 3 | 3553776.59 | 41141.94 | 101.1577 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project deadline was extended 3 times, due to uncertainties about the project, delay in the delivery of materials and execution elements, as well as delay in starting work on the part of subcontractors of some specialties. | the change in the value of the project was due to underwork, not carried out.
5099 | 606412 | Contract for repaving streets , construction of a bridge and two car parks, in the Municipality of Lajes do Pico | 45233222-1 | Paving and asphalting works | FALSE | 2012 | 2015 | Portugal | Lajes do Pico | Região Autónoma dos Açores | 15 | 30 | 05-11-2012 | 12-06-2015 | 949 | 240 | 2802628.91 | 2769900 | 3 | 2800573.49 | -30673.49 | 98.9047 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions and suspension of the execution period | ordinary price review
5100 | 606369 | Construction of the New Etar de Tondela | 45232421-9 | Sewage treatment works | FALSE | 2012 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 31-10-2012 | 21-10-2015 | 1085 | 540 | 792000 | 612142.82 | 2 | 591753.89 | 20388.93 | 103.4455 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays attributable to the contractor | existence of over and underwork in the contract
5101 | 587650 | Requalification of the former EN2 and confluent Municipal Roads in Canas de Santa Maria | 45233142-6 | Road-repair works | FALSE | 2010 | 2015 | Portugal | Tondela | Viseu | 20 | 8 | 11-10-2011 | 08-01-2015 | 1185 | 365 | 1818011.55 | 1137120.31 | 3 | 1192840.93 | -55720.62 | 95.3287 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were changes to the execution period due to two objective modifications of the contract. | the value of the project was changed due to underwork and price revisions.
5102 | 584612 | execution of the contract called ar 71.0.09 – construction contract for the execution of the intercetors of the cávado-homem subsystem – 2nd phase (fd 12), within the scope of the multimunicipal water supply | 45232411-6 | Foul-water piping construction work | FALSE | 2009 | 2015 | Portugal | Terras de Bouro | Braga | 3 | 51 | 19-09-2012 | 19-02-2015 | 883 | 600 | 6300000 | 4797571.97 | 3 | 2972621.03 | 1824950.94 | 161.392 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | increased difficulties in view of the expected volume of work, caused by the higher percentage of muddy soils, by the bad weather that hit the contract, by the contractor's inability to mobilize and provide the contract with the necessary means and materials in view of the assumed deadline. | this was due to the supply of works, as part of the contract for the pico de regalados system was withdrawn from the project, due to the delay that occurred in the execution of the downstream networks.
5103 | 584753 | In the 1st phase, excavation work, foundries, support walls and structures below the ground floor have already been carried out. | 45211350-7 | Multi-functional buildings construction work | FALSE | 2012 | 2015 | Portugal | Lagoa | Região Autónoma dos Açores | 15 | 60 | 24-09-2012 | 24-02-2015 | 883 | 400 | 9072000 | 7711200.01 | 3 | 7467711.75 | 243488.26 | 103.2605 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the 1st, 3rd and 4th deadline extensions were due to delays by the contractor. the 2nd extension was due to the existence of more work. | the change in the value of the project resulted from more work, underwork and supplies of errors and omissions.
5104 | 581271 | Conservation of the West Wing of the Old Cloister of the Monastery of S. Bento de Avis and adjacent spaces | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2012 | 2015 | Portugal | Avis | Portalegre | 12 | 20 | 12-06-2012 | 16-02-2015 | 979 | 120 | 210000 | 174658.54 | 1 | 156732.71 | 17925.83 | 111.4372 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | assignment of the contractual position due to the fact that the company initially does not currently have the financial means to complete the project within the expected deadlines | need to delete works
5105 | 732418 | Breakwater (this breakwater), rooted in the eastern embankment; an inner breakwater to, in conjunction with the breakwater, improve the conditions of shelter for the wet basin | 45243200-4 | Breakwater construction work | FALSE | 2012 | 2015 | Portugal | Povoação | Região Autónoma dos Açores | 15 | 30 | 17-10-2012 | 26-03-2015 | 890 | 540 | 4100000 | 3485000.01 | 3 | 3505363.97 | -20363.96 | 99.4191 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the changes that took place in the execution period resulted, in essence, from the constraints imposed by the above-mentioned maritime agitation. with a much smaller but still noteworthy implication, some increased difficulties in the execution of certain contracted works, particularly some dredging, which were critical in the planning, also had implications for the contracted period. | changes in the value of the project compared to the initially contracted resulted from two situations: i. over and underwork associated with the reformulation of the diversion project for the ribeira do purgar, namely its cross-section; ii. underwork related to the suppression of existing rockfill removal work in the marginal retention.
5106 | 579489 | Installation of a Geothermal Power Station and a Substation on the left bank of the River Minho, in Monção. | 45251141-1 | Geothermal power station construction work | FALSE | 2012 | 2015 | Portugal | Monção | Viana do Castelo | 18 | N/A | 22-08-2012 | 20-04-2015 | 971 | 210 | 330500 | 313197.75 | 2 | 328988.31 | -15790.56 | 95.2003 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 3 | N/A | N/A | N/A | N/A | N/A | N/A | floods in the river minho, preventing access to the project site as well as the recovery of damaged material. dgeg impositions relating to the computer system and carrying out tests until obtaining favorable conditions for the normal operation of the central. | unforeseen circumstances.
5107 | 579492 | Lagares School Center (Expansion) | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Felgueiras | Porto | 13 | 24 | 15-10-2012 | 06-02-2015 | 844 | 270 | 2183500 | 1965150 | 3 | 1953350.34 | 11799.66 | 100.6041 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the execution period of the project | smaller quantities executed
5108 | 579097 | Urban requalification in the Jewish churchyard and 25 de Abril neighborhood | 45233252-0 | Surface work for streets | FALSE | 2011 | 2015 | Portugal | Almodovar | Beja | 2 | 60 | 14-12-2011 | 09-01-2015 | 1122 | 365 | 837401.64 | 568040.01 | 2 | 568286.2 | -246.19 | 99.9567 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions | price revisions and work less
5109 | 576683 | Corporate Nest - Ponte de Sor Business Reception Area | 45213000-3 | Construction work for commercial buildings, warehouses and industrial buildings, buildings relating to transport | FALSE | 2012 | 2015 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 11-10-2012 | 20-04-2015 | 921 | 180 | 1999731.63 | 1534986.85 | 3 | 1534606.85 | 380 | 100.0248 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | existence of underworks
5110 | 576239 | Requalification of Vasco da Gama Avenue - Cliff Consolidation (2nd phase) | 45243110-6 | Cliff-stabilisation works | FALSE | 2011 | 2015 | Portugal | Sines | Setúbal | 17 | 36 | 06-02-2012 | 15-09-2015 | 1317 | 450 | 895514.86 | 758123.52 | 2 | 784996.82 | -26873.3 | 96.5766 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | there was no change in the execution period | additional work under article 311 and sgs of the "public procurement code" (€3,064.94 + vat)
5111 | 679428 | Stephens Heritage Redevelopment - Phase 1, Educational Services, Municipal Gallery and Cafeteria | 45262700-8 | Building alteration work | FALSE | 2011 | 2015 | Portugal | Marinha Grande | Leiria | 10 | 20 | 21-12-2011 | 11-12-2015 | 1451 | 150 | 348649.01 | 318472.41 | 2 | 385591.37 | -67118.96 | 82.5932 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions and additional contracts | for the purposes of price revisions, errors and omissions supply work, overwork and underwork
5112 | 575657 | River regularization work carried out at the cost of widening the flow section, in a length of 2530 meters, from about 250 m downstream of the Couraça bridge, on the EN1 | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2015 | Portugal | Vila Franca de Xira | Lisboa | 11 | 24 | 24-10-2011 | 30-09-2015 | 1437 | 630 | 4450000 | 4390000 | 3 | 4156482.12 | 233517.88 | 105.6182 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | approval of an extension of 365 days, corresponding to suspensions of the project for various reasons during its execution. deadline deviations for completion of the project of 258 days without the application of article 403 of the "public procurement code" | short work approval and price review
5113 | 575526 | Reinforcement of the water supply in the municipality of Horta | 45232150-8 | Works related to water-distribution pipelines | FALSE | 2010 | 2015 | Portugal | Horta | Região Autónoma dos Açores | 15 | 30 | 18-09-2012 | 28-04-2015 | 952 | 150 | 880614.34 | 755000 | 2 | 755000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | alteration of the circumstances of execution of the projects constituting the contract, namely significant degradation of the boxes and tanks at the date of execution of the contract and discontinuity of manufacture and commercialization of some equipment. | there were no changes in the value of the project
5114 | 575687 | Qualification of the Public Space in the Araucária District | 45000000-7 | Construction work | FALSE | 2011 | 2015 | Portugal | Vila Real | Vila Real | 19 | 59 | 11-04-2012 | 28-05-2015 | 1142 | 365 | 318188.44 | 310096.68 | 2 | 301146.16 | 8950.52 | 102.9722 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 11 | N/A | N/A | N/A | N/A | N/A | N/A | the contractor requested a graceful extension of the contract period for a period of 30 days, alleging that the delay in completing the contract for the construction of the semi-covered sports complex in araucária interfered with the projects for the qualification of the public space in the araucária neighborhood, having the extension was authorized by resolution of 09/23/2013 | authorized to carry out additional work by resolution of 12-17-2012
5115 | 576117 | Requalification of the ZIM da Adiça WWTP | 45232421-9 | Sewage treatment works | FALSE | 2011 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 06-03-2012 | 14-10-2015 | 1317 | 540 | 1173000 | 1073194.66 | 3 | 978650.36 | 94544.3 | 109.6607 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in carrying out the project | existence of underworks
5116 | 315492 | Wastewater drainage network and water supply in steps - sedielos and wastewater drainage network in place of sleepers - poiares | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2011 | 2015 | Portugal | Peso da Régua | Vila Real | 19 | 11 | 25-07-2011 | 25-11-2015 | 1584 | 180 | 311374.3 | 222613.89 | 1 | 185253.72 | 37360.17 | 120.167 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project period was suspended due to the following situations being pending: execution of the collector of passos' part in the private land, due to the current unavailability of the same due to the fact that they are cultivated; start-up of the pumping station installed in lugar de poiares due to the contracting of electric energy for the respective delivery point and, replacement of approximately 77.11 m2 of cube flooring for reasons totally attributable to the awarded company. | the change in the value of the project was due to underwork.
5117 | 227517 | The object of this contract is the award of the contract for Horta - Rehabilitation of the Road Network and Water Network | 45233120-6 | Road construction works | FALSE | 2010 | 2015 | Portugal | Horta | Região Autónoma dos Açores | 15 | 30 | 19-12-2011 | 23-04-2015 | 1221 | 720 | 2916318.28 | 2296800 | 3 | 2296800 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | update of technology and materials of led panels. | price review
5118 | 573414 | execution of the contract named ar 58.0.09 - contract for execution of the interceptors of poriço and freiriz, within the scope of the multimunicipal water supply and sanitation system of vale do ave. | 45232411-6 | Foul-water piping construction work | FALSE | N/A | 2015 | Portugal | Vila Verde | Braga | 3 | N/A | 28-10-2009 | 15-12-2015 | 2239 | 180 | N/A | 498828.78 | 2 | 587422.9 | -88594.12 | 84.9182 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the amount of flooring in ditches (due to high water levels) has doubled compared to what was initially foreseen. in addition, there are unfavorable weather conditions, difficulties in accessing private plots and damage caused by flooding in completed sections. | process of errors and omissions, resulting from the increase of flooring in ditches
5119 | 603604 | Construction of a Mountain Botanical Garden - Covilhã | 45112711-2 | Landscaping work for parks | FALSE | 2010 | 2015 | Portugal | Covilhã | Castelo Branco | 5 | 5 | 17-12-2010 | 23-02-2015 | 1529 | 365 | 500000 | 396131.97 | 2 | 396131.97 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | no
5120 | 375005 | Construction of the agricultural path of Luzirão – Jardim da Serra | 45233120-6 | Road construction works | FALSE | 2011 | 2015 | Portugal | Câmara de Lobos | Região Autónoma da Madeira | 14 | 21 | 27-06-2012 | 31-08-2015 | 1160 | 900 | 2340000 | 1985000 | 3 | 1860604.93 | 124395.07 | 106.6857 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | project change. | contract by price series, so the projects paid were those that were actually measured on site.
5121 | 464507 | The purpose of this contract is to carry out work defined as to its type, quantity and technical conditions of execution, in the Project and in the Tender Documents | 45112710-5 | Landscaping work for green areas | FALSE | 2012 | 2015 | Portugal | Amadora | Lisboa | 11 | 30 | 14-09-2012 | 11-06-2015 | 1000 | 945 | 310490 | 239257.47 | 1 | 243272.49 | -4015.02 | 98.3496 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | price review
5122 | 449466 | The object of this contract is to carry out the work defined, as to its type, quantity and technical conditions of execution, in the Project and in the Specifications | 45112710-5 | Landscaping work for green areas | FALSE | 2012 | 2015 | Portugal | Amadora | Lisboa | 11 | 30 | 14-09-2012 | 11-06-2015 | 1000 | 945 | 310490 | 269928 | 2 | 274326.89 | -4398.89 | 98.3965 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | price revisions
5123 | 225667 | Implementation of a signposted route equipped for pedestrian or bicycle use on a route that crosses ten counties Pampilhosa da Serra, Guarda, Oleiros, Sertã, Pedrógão Grande, Figueiró | 45233260-9 | Pedestrian ways construction work | FALSE | 2010 | 2015 | Portugal | Ferreira do Zezere | Castelo Branco | 5 | 20 | 12-10-2011 | 28-10-2015 | 1477 | 730 | 475000 | 439216.72 | 2 | 435774 | 3442.72 | 100.79 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extensions and suspensions | underwork
5124 | 428707 | 1 - Carry out the CONTRACT under the terms required by the Tender Specifications, which include the General Clauses, the Special Technical Clauses | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Lourinhã | Lisboa | 11 | 40 | 14-09-2012 | 29-09-2015 | 1110 | 540 | 6271770.15 | 4700000 | 3 | 4745169.38 | -45169.38 | 99.0481 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | despite the fact that there were three partial consignment notices, it did not give rise to a change in the execution period of the project (september 18, 2015) | verification of errors and omissions in the execution of the contract.
5125 | 354568 | The work includes the following earthworks; drainage; paving the carriageway in bituminous concrete and sidewalks in granite brick. | 45233120-6 | Road construction works | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 03-04-2012 | 15-04-2015 | 1107 | 180 | 1568638.13 | 1199950.48 | 3 | 1363549.71 | -163599.23 | 88.002 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were two partial assignments, resulting from the total availability of land; during the contract, there was also a modification of the contractual position (assignment of the contractual position of the initial contractor) as announced on 21-05-2014; more works. | underwork, resulting from the change to the type of foundations foreseen in the project; work to correct errors resulting from changing the type of foundations, including work on the gabion wall; omission supply works resulting from the existence of the mine; works to supply the omission of the "gusset" plate
5126 | 506450 | Contract work on Ribeira da Pantanha and Final Sealing of the Nova Dam, which includes interventions in the Urgeiriça area | 45112500-0 | Earthmoving work | FALSE | 2012 | 2015 | Portugal | Nelas | Viseu | 20 | 48 | 06-09-2012 | 26-02-2015 | 903 | 457 | 6100000 | 3876321.87 | 3 | 3828497.68 | 47824.19 | 101.2492 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 32 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extensions requested by the contractor and term extensions due to the contractor's need to make adjustments and corrections of defects in the project | deletion of works because it was verified that their execution was not necessary
5127 | 268180 | Municipal archive / adaptation of the municipal library - construction / expansion | 45212330-8 | Library construction work | FALSE | 2011 | 2015 | Portugal | Felgueiras | Porto | 13 | 48 | 20-06-2011 | 27-05-2015 | 1437 | 540 | 2760000 | 2058000.01 | 3 | 1919080.82 | 138919.19 | 107.2388 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | some adverse situations during the execution of the project | smaller quantities executed
5128 | 481007 | Rehabilitation and qualification of a municipal building (Edifício da Comur), for a museum. | 45212313-3 | Museum construction work | FALSE | 2012 | 2015 | Portugal | Murtosa | Aveiro | 1 | 30 | 13-09-2012 | 04-02-2015 | 874 | 365 | 940000 | 678497.23 | 2 | 646235.64 | 32261.59 | 104.9922 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | weather issues | there was underwork
5129 | 518848 | The purpose of the contract is to carry out major repair and adaptation works to the secondary education of Primary school in Velas | 45000000-7 | Construction work | FALSE | 2012 | 2015 | Portugal | Velas | Região Autónoma dos Açores | 15 | 47 | 17-09-2012 | 31-10-2015 | 1139 | 730 | 14200000 | 14120055.53 | 3 | 13760649.98 | 359405.55 | 102.6118 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful deadline extension | supply of errors and omissions whose works are included in additional to the contract and works unless removed from the contract also referred to in additional to the contract.
5130 | 725594 | The purpose of the contract is to carry out the work defined in terms of its type, quantity and technical conditions of execution, in the solution elements of the work that are part of the Specifications. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Óbidos | Leiria | 10 | 90 | 14-09-2012 | 11-12-2015 | 1183 | 330 | 6200000 | 5936000 | 3 | 5899290.33 | 36709.67 | 100.6223 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 31 | N/A | N/A | N/A | N/A | N/A | N/A
5131 | 446050 | Construction of a 2-storey building for a school center with 3 activity rooms for pre-primary and 6 classrooms for the 1st cycle of basic education, library, multipurpose room, canteen | 45214200-2 | Construction work for school buildings | FALSE | 2012 | 2015 | Portugal | Amarante | Porto | 13 | 30 | 07-09-2012 | 05-06-2015 | 1001 | 365 | 2838000 | 1890038.22 | 3 | 1890038.22 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | after the effective completion of the projects, there was a period of 94 days until the provisional acceptance, since it was not possible to do so because there were no effective conditions, namely electricity.
5132 | 367534 | Channeling and Regularization of Ribeiro das Eiras (1st Phase) - Caniço | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2015 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 43 | 05-09-2012 | 25-11-2015 | 1176 | 360 | 1454000 | 872400.01 | 2 | 883191.79 | -10791.78 | 98.7781 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities and the ordinary revision of prices.
5133 | 465330 | The object of the contract is the repair and requalification of the streets and respective surrounding areas, such as parking lots and sidewalks in the southern area of ​​the council | 45233200-1 | Various surface works | FALSE | 2012 | 2015 | Portugal | Amadora | Lisboa | 11 | 30 | 05-09-2012 | 27-05-2015 | 994 | 945 | 309954 | 268954.77 | 2 | 270607.63 | -1652.86 | 99.3892 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | public interest (article 312, paragraph b) of the "public procurement code"), agreement between the parties, the period for carrying out the project was extended to 480 days. addendum to the contract on 03/14/2013. | due to the price revision addition.
5134 | 648404 | Intervention in the Terminal Section of Ribeira de São João | 45240000-1 | Construction work for water projects | FALSE | 2011 | 2015 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 49 | 03-09-2012 | 29-06-2015 | 1029 | 720 | 27900000 | 19669500 | 3 | 18870253.59 | 799246.41 | 104.2355 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities.
5135 | 398499 | Construction of the Canedo School Center. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 60 | 29-08-2012 | 13-11-2015 | 1171 | 365 | 1478468.28 | 1249391.36 | 3 | 1325100.66 | -75709.3 | 94.2865 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A | 130 days (pl) - arising from the assignment of the contractual position; 282 days (pl) - requested by the contractor, taking into account the need to revise the project and switch on definitive electricity; extension of the period between the 1st provisional acceptance (18/06/2015) and the final one (05/11/2015) for resolution of technical details and correction of deficiencies. | work to correct errors and omissions resulting from discrepancies between measurements in the project and measurements in work on site; additional works resulting from the revision of the project and security reinforcement; minor works resulting from lags between the measurements of the project and those of the project, or that proved to be unnecessary.
5136 | 289977 | Requalification of the elementary s and primary chool Dr. Francisco sanches. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Braga | Braga | 3 | 60 | 06-08-2012 | 17-08-2015 | 1106 | 430 | 6475832.38 | 6651311.67 | 3 | 6651311.67 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 14 | N/A | N/A | N/A | N/A | N/A | N/A
5137 | 376592 | Expansion of the Wastewater Drainage and Water Supply Networks in AdRA's 10 municipalities. | 45231300-8 | Construction work for water and sewage pipelines | FALSE | 2011 | 2015 | Portugal | Murtosa | Aveiro | 1 | 20 | 23-01-2012 | 12-02-2015 | 1116 | 1095 | 300000 | 299809.77 | 2 | 299806.99 | 2.78 | 100.0009 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | work was carried out within the contracted period.
5138 | 447643 | Construction of the Vale do Forno Civic and Community Center | 45214100-1 | Construction work for kindergarten buildings | FALSE | 2012 | 2015 | Portugal | Odivelas | Lisboa | 11 | 20 | 31-07-2012 | 29-04-2015 | 1002 | 150 | 957021.76 | 763765.41 | 2 | 767278.63 | -3513.22 | 99.5421 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | term extension | additional work and price revision
5139 | 480885 | Remodeling of the Fruit and Vegetable Sectors for Allocation to New Uses/Gourmet Gastronomy | 45213141-3 | Covered market construction work | FALSE | 2012 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 12-07-2012 | 04-12-2015 | 1240 | 116 | 457178.53 | 365052.36 | 2 | 365052.38 | -0.02 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A
5140 | 375989 | Architectural work, stability and even installations, equipment and systems for water and sewage, electrical, communications, HVAC, gas, fire safety and people transport systems. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Nisa | Portalegre | 12 | 30 | 13-07-2012 | 12-08-2015 | 1125 | 540 | 4840000 | 3839144.98 | 3 | 3839144.87 | 0.11 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension of the project term by 213 days. | underwork and interim price revisions
5141 | 419294 | flood control in águeda-interventions in the flow sections of ponte do campo, ponte de óis da ribeira and in the secondary channel of the river águeda by pass in águeda-secondary channel of the river agueda by-pass | 45246400-7 | Flood-prevention works | FALSE | 2011 | 2015 | Portugal | Águeda | Aveiro | 1 | 42 | 19-06-2012 | 05-10-2015 | 1203 | 480 | 1956875.72 | 1298097.37 | 3 | 1329686.46 | -31589.09 | 97.6243 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | due to suspensions (adverse weather conditions: floods and rain). special request for revitalization requested by the contractor. deadline extension for carrying out work to correct errors and omissions. | execution of extra work at contract and agreed prices, and errors and omissions supply work and existence of underwork.
5142 | 458077 | Requalification of road infrastructures, drainage, paving, signaling, domestic and rainwater wastewater network. | 45233142-6 | Road-repair works | FALSE | 2012 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 21-06-2012 | 20-05-2015 | 1063 | 450 | 3615683.07 | 2610923.33 | 3 | 2539473.91 | 71449.42 | 102.8136 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to the existence of the suspension. | existence of underworks.
5143 | 362166 | Reconstruction of the PH and canalization walls of the 1st Ribeiro do Lazareto - São Gonçalo | 45246000-3 | River regulation and flood control works | FALSE | 2011 | 2015 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 23 | 25-06-2012 | 02-12-2015 | 1255 | 180 | 560000 | 336000.8 | 2 | 337221 | -1220.2 | 99.6382 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 7 | N/A | N/A | N/A | N/A | N/A | N/A | there were no changes to the execution period of the project. | difference between planned and executed quantities and the ordinary revision of prices.
5144 | 365161 | The object of this contract is the execution of the contract for the museum convent of Lóios - 2nd phase, according to the works described in article 1, chapter I, of the specifications and contract program. | 45212313-3 | Museum construction work | FALSE | 2011 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 60 | 25-06-2012 | 19-01-2015 | 938 | 365 | 646123.38 | 639947.46 | 2 | 638781.91 | 1165.55 | 100.1825 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 5 | N/A | N/A | N/A | N/A | N/A | N/A | slowness in the execution of works. | underwork and errors and omissions.
5145 | 449224 | Alvarães industrial zone - 1st phase - process no. 06/a1/2012 | 45232451-8 | Drainage and surface works | FALSE | 2012 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 25 | 15-06-2012 | 25-02-2015 | 985 | 274 | 2499492.13 | 1790000 | 3 | 1790000 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | economic difficulties of the contractor
5146 | 368938 | Refurbishment of the Town Hall Building | 45210000-2 | Building construction work | FALSE | 2011 | 2015 | Portugal | Alcoutim | Faro | 8 | 30 | 17-05-2012 | 14-07-2015 | 1153 | 420 | 785398.06 | 612808.2 | 2 | 600498.3 | 12309.9 | 102.0499 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | due to work to be carried out after inspection | due to underwork worth €12,309.91.
5147 | 459721 | Execution of Roundabout at street of Campa in Lordelo | 45233128-2 | Roundabout construction work | FALSE | 2012 | 2015 | Portugal | Paredes | Porto | 13 | 20 | 31-05-2012 | 17-09-2015 | 1204 | 545 | 395000 | 289291.97 | 2 | 288483.53 | 808.44 | 100.2802 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | execution project change | 2 items of the project map were not executed.
5148 | 321870 | Construction contract for a Creche, Kindergarten and Occupational Activities Center for the disabled, Funchais path, Rebentão, Santa Cruz da Graciosa, Azores | 45000000-7 | Construction work | FALSE | 2011 | 2015 | Portugal | Santa Cruz da Graciosa | Região Autónoma dos Açores | 15 | 48 | 02-03-2012 | 07-05-2015 | 1161 | 540 | 2375000 | 1885000 | 3 | 1885407.44 | -407.44 | 99.9784 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | price review
5149 | 435180 | Construction of the Youth House in Vila Nova de Famalicão. | 45262700-8 | Building alteration work | FALSE | 2011 | 2015 | Portugal | Vila Nova de Famalicão | Braga | 3 | 24 | 29-05-2012 | 27-07-2015 | 1154 | 365 | 800000 | 720660.87 | 2 | 720660.87 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | total suspension of the project for a period of 30 days. | there was only an increase of 776.63 euros to the award value relating to the price review.
5150 | 404052 | Requalification of E.M. 1519 E of the Municipal Roads Connecting to E.R.228 | 45233220-7 | Surface work for roads | FALSE | 2011 | 2015 | Portugal | Tondela | Viseu | 20 | 20 | 15-03-2012 | 08-01-2015 | 1029 | 240 | 1237552 | 771364.54 | 2 | 748491.54 | 22873 | 103.0559 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | objective modification of the contract in accordance with articles 311 to 315 of the "public procurement code" | lack of works
5151 | 289800 | Requalification of the elementary and primary school André Soares. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Braga | Braga | 3 | 60 | 17-05-2012 | 28-07-2015 | 1167 | 600 | 9631710 | 7223782.51 | 3 | 7414561.5 | -190778.99 | 97.427 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 17 | N/A | N/A | N/A | N/A | N/A | N/A |  | the successful tenderer filed a lawsuit with the administrative and tax court of braga (proc. n.º 1508/13.3bebrg) claiming additional work worth €660,073.93, with an agreement in the amount of €186,665.85 having been accepted. the amount is 2.58% of the contractual price, which is lower than the limit defined in point 4 of article 376 of the "public procurement code". to that amount was added the amount of €4,113.14 corresponding to the ordinary price review.
5152 | 432862 | Construction of the School Center of São Pedro do Sul with the following services: School of the 1st CEB, Kindergarten, Sports Gym, Dining Hall, Auditorium, Library, Children's Park, Playground | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | São Pedro do Sul | Viseu | 20 | 24 | 15-05-2012 | 16-02-2015 | 1007 | 540 | 3150000 | 2394000 | 3 | 2367205.5 | 26794.5 | 101.1319 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | no change | there were works that were not performed.
5153 | 336564 | Summary of work1 shipyard and preliminary work2 earthworks and demolitions3 foundations and structures4 roofing/waterproofing5 interior floors | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2015 | Portugal | Águeda | Aveiro | 1 | 42 | 09-05-2012 | 30-03-2015 | 1055 | 365 | 1563432.19 | 1295312.37 | 3 | 1152552.66 | 142759.71 | 112.3864 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 24 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline changes were motivated by suspensions and deadline extensions due to the approval of too many works. | changes in the value of the project are due to the need to carry out unforeseen work and the fact that it is not necessary to provide all the didactic material foreseen in the project.
5154 | 407738 | Improvement of the Municipal Road Network in the village of Ponte de Lima - Requalification of Avenida 5 de Outubro | 45232451-8 | Drainage and surface works | FALSE | 2011 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 25 | 05-03-2012 | 04-09-2015 | 1278 | 150 | 462000 | 430885.99 | 2 | 361149.38 | 69736.61 | 119.3096 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | without changes | underwork
5155 | 310387 | Refurbishment of the Municipal Market of Almodôvar | 45453100-8 | Refurbishment work | FALSE | 2011 | 2015 | Portugal | Almodovar | Beja | 2 | 30 | 06-10-2011 | 24-04-2015 | 1296 | 335 | 375104.76 | 318812.37 | 2 | 328178.81 | -9366.44 | 97.1459 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the reasons for the changes to the deadline are due to the fact that the 1st contractor (conspronel) assigned the contractual position to the company jasfec, and during the execution of the project there were extensions of the deadline due to some lack of definition of the project. | the change in value is due to more work (€11,547.90) underwork (€5,661.94) and price revision (€3,479.73).
5156 | 289948 | Rehabilitation / refurbishment of the schoolelementary school 2,3 E vimioso sports hall | 45262700-8 | Building alteration work | FALSE | 2011 | 2015 | Portugal | Vimioso | Bragança | 4 | 30 | 24-01-2012 | 12-06-2015 | 1235 | 180 | 1170235.04 | 792665.53 | 2 | 792665.53 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extensions
5157 | 222187 | The interceptor runs along the Tâmega River, in a total length of 6,100m, corresponding to 4,033m to Ø630 PP-C / Ø600 FFD gravity collectors and 2,067 meters to three Ø400 PE | 45232423-3, 45112500-0, 45232411-6 | Sewage pumping stations construction work, Earthmoving work, Foul-water piping construction work | FALSE | 2010 | 2015 | Portugal | Amarante | Porto | 13 | 52 | 01-03-2012 | 30-01-2015 | 1065 | 365 | 4850000 | 3495844.58 | 3 | 3395065.94 | 100778.64 | 102.9684 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions and floods on the tâmega river. (extensions free of charge for the owner of work). | alteration of the execution project mainly due to situations detected during the construction phase and difficult to detect during the elaboration phase of the execution project – unstable granite batholiths, which, when disturbed, could cause serious accidents and which forced adjustments to the layout, without compromising the purpose and quality of the project.
5158 | 423744 | Requalification of Av. Captain Gaspar de Castro - Proc. No. 175/A1/2011 | 45233200-1 | Various surface works | FALSE | 2011 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 20-03-2012 | 08-05-2015 | 1144 | 180 | 1800000 | 1392382.04 | 3 | 418208.59 | 974173.45 | 332.9396 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the court of accounts visa was on may 3, 2012, adverse weather conditions and project remodeling | underwork due to project remodeling by decision of the executive
5159 | 243665 | Restoration and enhancement of Cine-Teatro Garrett Completion of the work - ref. 018/10 | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2010 | 2015 | Portugal | Póvoa de Varzim | Porto | 13 | 40 | 06-03-2012 | 11-11-2015 | 1345 | 425 | 5230000 | 4680000 | 3 | 4502794.22 | 177205.78 | 103.9355 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 19 | N/A | N/A | N/A | N/A | N/A | N/A | unavailability of the entire land at the beginning of the project and fragility of the neighboring foundations, which led to the use of less efficient equipment, implying a delay in the execution of the project. | incompatibility of some specialties with regard to maps of quantities and projects and work adjustments.
5160 | 299239 | The present work concerns the execution project of the Access road to the Wastewater Treatment Station of Viseu Sul. | 45233120-6 | Road construction works | FALSE | 2011 | 2015 | Portugal | Viseu | Viseu | 20 | 42 | 07-11-2011 | 22-12-2015 | 1506 | 96 | 1335145.44 | 801154.29 | 2 | 754335.07 | 46819.22 | 106.2067 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the alterations to the execution period of the project, was the fact that not all the administrative easements necessary for the execution of the project were constituted.
5161 | 403211 | Reconstruction of the manor house at Porta dos Figos for the installation of the traditional arts and crafts center - center for welcoming artists. | 45211200-1 | Sheltered housing construction work | FALSE | 2011 | 2015 | Portugal | Lamego | Viseu | 20 | 30 | 05-03-2012 | 09-04-2015 | 1130 | 210 | 778424.65 | 700586.41 | 2 | 674791.9 | 25794.51 | 103.8226 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions and nature of the project. | there was underwork
5162 | 394326 | Requalification of the square of the fair. | 45112711-2 | Landscaping work for parks | FALSE | 2011 | 2015 | Portugal | Lamego | Viseu | 20 | 30 | 05-03-2012 | 22-06-2015 | 1204 | 180 | 1350777.04 | 1289801.7 | 3 | 1253696.68 | 36105.02 | 102.8799 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | partial suspension of work | underwork and price revision
5163 | 348864 | Rehabilitation of the surface of Campo das Hortas and streetAndrade Corvo. | 45233228-3 | Surface coating construction work | FALSE | 2011 | 2015 | Portugal | Braga | Braga | 3 | 30 | 28-02-2012 | 12-01-2015 | 1049 | 120 | 593477.65 | 415434.37 | 2 | 686523.44 | -271089.07 | 60.5128 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 16 | N/A | N/A | N/A | N/A | N/A | N/A
5164 | 344844 | Requalification of the public space in the western part of the historic center of Viana do Castelo - streetMonsenhor Daniel Machado and street of Loureiro - Proc.º n.º 85/A1/2011 | 45233252-0 | Surface work for streets | FALSE | 2011 | 2015 | Portugal | Viana do Castelo | Viana do Castelo | 18 | 30 | 28-02-2012 | 07-10-2015 | 1317 | 180 | 509953.7 | 473994.02 | 2 | 404914.58 | 69079.44 | 117.0603 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
5165 | 339630 | Construction of the primary school for the 2nd and 3rd cycles of Santa Maria da Feira and the sports pavilion. | 45210000-2 | Building construction work | FALSE | 2011 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 40 | 22-02-2012 | 18-03-2015 | 1120 | 450 | 6757673.96 | 4955703.91 | 3 | 4955703.91 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 26 | N/A | N/A | N/A | N/A | N/A | N/A | 12d arising from overwork and errors and omissions; 95d arising from the existence of local constraints that prevented the normal development of the projects by the contractor;57d on a free basis, for reasons beyond the control of the projects owner and the responsibility of the contractor;289d extension of the period elapsed between the 1st inspection for the purpose of provisional acceptance and the final one, to correct deficiencies. | addition of quantities due to errors and omissions in the contract quantities map and the need for more essential works for the execution of the project, namely, the foundations by piles and reinforcement of the reinforced concrete structure and electrical installation associated with the sports pavilion.
5166 | 330005 | Execution of the public works contract Construction of the Creche de Pias. | 45215215-7 | Children's home construction work | FALSE | 2011 | 2015 | Portugal | Alandroal | Évora | 7 | 30 | 03-02-2012 | 04-02-2015 | 1097 | 365 | 447438.92 | 398017.61 | 2 | 396261.44 | 1756.17 | 100.4432 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 9 | N/A | N/A | N/A | N/A | N/A | N/A | due to the suspension ordered by the developer, due to adverse weather conditions. deadline extensions for delays for which the successful tenderer is responsible, but which have not been subject to sanctions. | withdrawal of work from the contract and due to the ordinary revision of prices.
5167 | 323138 | Reconstruction of Casa dos Bordalos for a Center for Design and Silver Studies | 45453100-8 | Refurbishment work | FALSE | 2011 | 2015 | Portugal | Lamego | Viseu | 20 | 30 | 15-12-2011 | 25-03-2015 | 1196 | 300 | 415161.11 | 414611.17 | 2 | 368416.74 | 46194.43 | 112.5386 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there were work suspensions and deadline extensions due to archaeological work and the need to change the project. | there were works that proved not to be necessary.
5168 | 362041 | Urban renewal of Largo da Senhora a Branca | 45233228-3 | Surface coating construction work | FALSE | 2011 | 2015 | Portugal | Braga | Braga | 3 | 45 | 01-02-2012 | 12-01-2015 | 1076 | 120 | 691647.73 | 484153.42 | 2 | 841300.77 | -357147.35 | 57.5482 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A | the delay in the provisional acceptance of the contract was due to a delay in the reception of the electrical infrastructures by edp | the successful tenderer filed a lawsuit at the administrative and judicial court of braga claiming a work value of more than €958,140.52, with an agreement worth €355,400.91 having been accepted by superiors. to this is added the amount relating to the legal revision of prices of €1,746.44.
5169 | 353902 | The object of the contract is the execution of the public works contract for the construction of an industrial zone equipped with the respective infrastructures. | 45211360-0 | Urban development construction work | FALSE | 2011 | 2015 | Portugal | Vouzela | Viseu | 20 | 30 | 11-01-2012 | 02-10-2015 | 1360 | 450 | 1300000 | 804105.87 | 2 | 671326.01 | 132779.86 | 119.7787 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | changes to the project deadline result from several factors, which appear in the municipality's deliberations and accompanying documents. | the change in the value of the project results from one less set of works.
5170 | 323067 | Rehabilitation of building - towered house of barbosa Aranha - municipal services and cultural space | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2011 | 2015 | Portugal | Ponte de Lima | Viana do Castelo | 18 | 20 | 27-09-2011 | 06-02-2015 | 1228 | 300 | 585000 | 467973.24 | 2 | 365723.5 | 102249.74 | 127.9582 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | atmosphere conditions | underwork
5171 | 284238 | Extension of the pier for a length of 200m, according to the alignment of the final section of the existing work and dredging of the navigation channel. | 45243200-4 | Breakwater construction work | FALSE | 2011 | 2015 | Portugal | Ílhavo | Aveiro | 1 | 49 | 24-11-2011 | 05-02-2015 | 1169 | 730 | 33000000 | 24687000 | 3 | 24679006.05 | 7993.95 | 100.0324 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | delay of the authorization of the maritime authority regarding maritime signaling. | quantities less in some articles of the map of contractual works.
5172 | 365168 | As part of the Program for the enhancement and reorganization of the public space on the coast of Vila Nova de Gaia, a project for the Requalification of the Public Space was developed | 45233200-1 | Various surface works | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 20 | 16-12-2011 | 19-03-2015 | 1189 | 210 | 3831839.85 | 2343892.81 | 3 | 2361290.52 | -17397.71 | 99.2632 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | unfavorable weather conditions, which conditioned the normal development of the projects, given their nature, namely the bituminous paving work, painting the streets and sidewalks. | work was carried out to regularize and fill the pavements, due to the reprofiling of the transverse rail, the installation of sidewalk curbs and the misalignment of the existing threshold levels, which were uneven between adjacent or continuous entrances and the runoff of surface water, resulting from this being a consolidated streets, namely in terms of alignments and longitudinal and transversal profile.
5173 | 357311 | Execution of all contract work necessary to carry out the requalification and regeneration of spaces in Bairro da Nazaré, parish of São Martinho, municipality of Funchal. | 45112700-2 | Landscaping work | FALSE | 2011 | 2015 | Portugal | Funchal | Região Autónoma da Madeira | 14 | 47 | 30-11-2011 | 18-11-2015 | 1449 | 540 | 1200000 | 849995.42 | 2 | 849995.42 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the project was carried out within the deadline
5174 | 366191 | Circular Road Construction | 45233122-0 | Ring road construction work | FALSE | 2011 | 2015 | Portugal | Vila Nova de Paiva | Viseu | 20 | 24 | 22-11-2011 | 02-10-2015 | 1410 | 300 | 322000 | 285659.9 | 2 | 303451.07 | -17791.17 | 94.1371 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | Extra work, lack of weather conditions | unforeseen circumstances
5175 | 346639 | The object of this contract is the milling and replacement of pavements in interventions by Águas e Parque Biológico de Gaia, EEM | 45233222-1 | Paving and asphalting works | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 21 | 19-10-2011 | 02-06-2015 | 1322 | 365 | 260000 | 249200 | 1 | 168823.31 | 80376.69 | 147.6099 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | it was not carried out within the deadline due to the weather conditions verified within the estimated period, considering the specific conditions of application of hot bituminous masses. | the expected amounts for milling and replacing floors did not materialize as there was a low number of breakdowns. the total effective price of the contract includes the amount of €2,719.78 related to the price revision, in accordance with no. 1 of article 382. of the "public procurement code".
5176 | 302687 | It is the construction of a school center with valences for pre-school and 1st cycle of basic education. | 45214200-2 | Construction work for school buildings | FALSE | 2011 | 2013 | Portugal | Esposende | Braga | 3 | 20 | 08-09-2011 | 04-07-2013 | 665 | 540 | 2160000 | 2095420.48 | 3 | 1411590.3 | 683830.18 | 148.444 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Non-fulfilment of the contract (Contract Termination) | 0 | N/A | N/A | N/A | N/A | N/A | N/A | upon termination of the contract | the tender quantity map had excess quantities
5177 | 334640 | Urban arrangement of the square of the monastery of s. Martin of tibães. | 45112723-9 | Landscaping work for playgrounds | FALSE | 2011 | 2015 | Portugal | Braga | Braga | 3 | 30 | 18-10-2011 | 12-01-2015 | 1182 | 90 | 540667 | 497835 | 2 | 629928.12 | -132093.12 | 79.0304 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 18 | N/A | N/A | N/A | N/A | N/A | N/A | the delay in the provisional acceptance of the contract was due to a delay in the reception\ of the electrical infrastructures by edp. | the successful tenderer filed a lawsuit with the administrative court claiming that the project amounted to more than €167,882.69, with an agreement worth €132,093.12 having been accepted by superiors.
5178 | 289507 | Execution of the contract for the Construction of the Cultural Incubator of Águeda and MARCA | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2011 | 2015 | Portugal | Águeda | Aveiro | 1 | 42 | 13-10-2011 | 24-03-2015 | 1258 | 455 | 1149730.25 | 927622.21 | 2 | 907254.92 | 20367.29 | 102.2449 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 8 | N/A | N/A | N/A | N/A | N/A | N/A | suspensions due to design changes and extensions due to overwork. | the existence of underwork, more work and supply of errors and omissions.
5179 | 206079 | Recovery of the Cine-Oriental of Aljustrel | 45453100-8 | Refurbishment work | FALSE | 2010 | 2015 | Portugal | Aljustrel | Beja | 2 | 61 | 15-06-2011 | 25-06-2015 | 1471 | 540 | 1291000 | 906359.87 | 2 | 902031.16 | 4328.71 | 100.4799 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | adverse weather conditions at various stages of the project; several delays in the delivery of materials, difficulties in the acquisition and supply of materials and equipment by the contractor; characteristics of the enterprise, such as its implantation in an urban area, characteristics of the existing building, given that it involved rehabilitation works. | existence of less tasks totalling €18500.00 and final calculation of the price revision in the amount of €14171.29 + vat
5180 | 370201 | Village Park | 45112723-9 | Landscaping work for playgrounds | FALSE | 2010 | 2015 | Portugal | Aljustrel | Beja | 2 | 97 | 10-08-2011 | 18-11-2015 | 1561 | 510 | 720000 | 598110.54 | 2 | 566297.38 | 31813.16 | 105.6177 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | graceful extensions of the contract term for a total of 240 days. | underwork €39,704.31 and provisional price revision calculations in the total amount of €7,891.15.
5181 | 249031 | Construction of a New Cafeteria in the Backyard of Casa Fernando Pessoa | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2011 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 07-09-2011 | 04-08-2015 | 1427 | 200 | 320000 | 267251.23 | 2 | 267236.19 | 15.04 | 100.0056 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
5182 | 176523 | Construction of the New Home for the 3rd Age of Aljustrel | 45215212-6 | Retirement home construction work | FALSE | 2010 | 2015 | Portugal | Aljustrel | Beja | 2 | 60 | 09-08-2011 | 10-03-2015 | 1309 | 450 | 3055733.02 | 2750159.73 | 3 | 2869584.39 | -119424.66 | 95.8383 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 1st extension of 90 days ending on 01/03/2013; 2nd extension of 120 days ending on 30/06/2013, 3rd extension of 61 days ending on 31/08/2013, 4th extension of 61 days ending on 31/10/2013, 5th extension term of 60 days ending on 12/31/2013, 6th extension of term with 58 days ending on 2/28/2014. the causes of the changes to the execution period of the project were due to reasons of the economic environment of the civil construction market and the current severe economic recession. | the causes of the alterations in the value of the project were due to additional works in the amount of €34,114.15 and price revisions in the amount of €85,310.51
5183 | 296445 | The purpose of this Contract is the execution of the works of the contract designated as “Contract for the Construction of a Residential Home and Center for Occupational Activities”. | 45215000-7 | Construction work for buildings relating to health and social services, for crematoriums and public conveniences | FALSE | 2011 | 2015 | Portugal | Matosinhos | Porto | 13 | 15 | 03-09-2011 | 14-04-2015 | 1319 | 360 | 1615000 | 1212865 | 3 | 1263168.43 | -50303.43 | 96.0177 | Ad rectification statement | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 4 | N/A | N/A | N/A | N/A | N/A | N/A | need to evaluate proposals for additional work to address errors and omissions in the project. | the existence of gaps in some specialty projects with regard to the compatibility of existing and new structures.
5184 | 270185 | The object of this contract is the milling and replacement of pavements in AGEEM interventions, including the supply of the necessary materials and the removal of leftovers. | 45233222-1 | Paving and asphalting works | FALSE | 2011 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 30 | 24-08-2011 | 28-05-2015 | 1373 | 365 | 345000 | 248075 | 1 | 258530.2 | -10455.2 | 95.9559 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | it was not carried out within the foreseen period due to the weather conditions verified within the estimated period, considering the specific conditions of application of the hot bituminous masses. | the total effective price of the contract includes the amount of €10,455.20, related to the price revision, in accordance with no. 1 of article 382. of the "public procurement code"
5185 | 193170 | Paving with granite brick of 67 000m2 of streets in parishes | 45233252-0 | Surface work for streets | FALSE | 2010 | 2015 | Portugal | Sernancelhe | Viseu | 20 | 30 | 16-06-2011 | 11-09-2015 | 1548 | 1080 | 1112500 | 881100 | 2 | 884203.25 | -3103.25 | 99.649 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension - weather conditions | underwork
5186 | 277469 | Construction of the Cultural Center of Odivelas - 2nd phase | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2011 | 2015 | Portugal | Ferreira do Alentejo | Beja | 2 | 20 | 11-08-2011 | 31-08-2015 | 1481 | 300 | 550000 | 496534.46 | 2 | 500586.8 | -4052.34 | 99.1905 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 10 | N/A | N/A | N/A | N/A | N/A | N/A | in addition to the extensions granted, there were unjustified delays that led to the application of contractual fines. | existence of over and underwork, default interest and contractual fines.
5187 | 259480 | Execution of the contract called “Execution of Pumping Station No. 2 of the Wastewater Interceptor System of the Parish of Santo António da Serra” | 45232431-2 | Wastewater pumping station | FALSE | 2011 | 2015 | Portugal | Santa Cruz | Região Autónoma da Madeira | 14 | 51 | 15-07-2011 | 23-04-2015 | 1378 | 150 | 220000 | 179952.49 | 1 | 159882.96 | 20069.53 | 112.5526 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | time of suspension (by the contractor) due to lack of safety conditions (art.º 366º, n.º 1 of the "public procurement code") | essentiality of previously detected errors and omissions correction work (art.º 376.º, n.º5 of the "public procurement code")
5188 | 188663 | WWTP with capacity for 1000 inhabitants in a biological process of activated sludge in prolonged aeration | 45232421-9 | Sewage treatment works | FALSE | 2010 | 2015 | Portugal | Mangualde | Viseu | 20 | 30 | 12-07-2011 | 10-02-2015 | 1309 | 540 | 242000 | 184254.93 | 1 | 179574.93 | 4680 | 102.6062 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | according to the project book | according to the description of the final account of the contract
5189 | 303803 | The object of this contract is to carry out the contract for the construction of the Pavilhão Gimnodesportivo do Vade | 45212225-9 | Sports hall construction work | FALSE | 2011 | 2015 | Portugal | Vila Verde | Braga | 3 | 20 | 24-06-2011 | 30-06-2015 | 1467 | 300 | 1137667.28 | 948000 | 2 | 937144.5 | 10855.5 | 101.1584 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A
5190 | 303802 | The object of this contract is to carry out the contract for the Construction of the Cervães Gimnodesportivo Pavilion, located in the parish of Cervães, Municipality of Vila Verde | 45212225-9 | Sports hall construction work | FALSE | 2011 | 2015 | Portugal | Vila Verde | Braga | 3 | 20 | 24-06-2011 | 30-06-2015 | 1467 | 300 | 1095218.94 | 918000 | 2 | 907258.31 | 10741.69 | 101.184 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 13 | N/A | N/A | N/A | N/A | N/A | N/A
5191 | 277251 | Rehabilitation of Building for the Family Health Unit. | 45215100-8 | Construction work for buildings relating to health | FALSE | 2011 | 2015 | Portugal | Mangualde | Viseu | 20 | 20 | 27-06-2011 | 12-05-2015 | 1415 | 180 | 471398.12 | 441659.69 | 2 | 427300.76 | 14358.93 | 103.3604 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | works | underwork
5192 | 245551 | Construction of the Ançã Sports Complex | 45212200-8 | Construction work for sports facilities | FALSE | 2010 | 2015 | Portugal | Cantanhede | Coimbra | 6 | 30 | 16-06-2011 | 23-03-2015 | 1376 | 540 | 1920000 | 1747620.85 | 3 | 896170.73 | 851450.12 | 195.0098 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions | underwork
5193 | 250652 | nadir afonso foundation | 45212300-9 | Construction work for art and cultural buildings | FALSE | 2011 | 2015 | Portugal | Chaves | Vila Real | 19 | 60 | 16-06-2011 | 30-06-2015 | 1475 | 540 | 7100000 | 4771380.52 | 3 | 4927440.67 | -156060.15 | 96.8328 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 33 | N/A | N/A | N/A | N/A | N/A | N/A | term extensions approved at the board meeting of 04/02/2012 - 60 days + r.c. from 07/04/2014 120 days +r.c. 10/24/2014 - 60 days +r.c. from 11/21/2014 - 30 days + r.c. 01/29/2015 - 60 days + r.c. 04/10/2015 - 30 days | most approved works in r.c. of 02/27/2015, in the amount of €156,060.15
5194 | 182690 | Expansion of the Sampaio Industrial Park Roads / Sewerage Network / Water Network / Rainwater Network / Energy / Telecommunications | 45111290-7 | Primary works for services | FALSE | 2010 | 2015 | Portugal | Carregal do Sal | Viseu | 20 | 30 | 26-05-2011 | 11-09-2015 | 1569 | 365 | 830000 | 659087.06 | 2 | 680879.05 | -21791.99 | 96.7994 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | requests for extension by the contractor. adverse weather conditions (suspension) | measurement hits
5195 | 660032 | Gafanha da Boa Hora School Center | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2015 | Portugal | Vagos | Aveiro | 1 | 72 | 20-05-2011 | 16-10-2015 | 1610 | 720 | 3875988.05 | 2809905.11 | 3 | 2901076.19 | -91171.08 | 96.8573 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays in carrying out work that depended on favorable weather conditions and, also, in carrying out work with errors and omissions that depended on the order of execution by the owner of the project. | carrying out work to correct errors and omissions, in a total of €9,532.92, underwork (work not performed), in a total of €3,765.30 and calculation of price revisions, in a total of €85,404.15 .
5196 | 160942 | Requalification of the Santa Maria Sugar Cane Treatment Plant including physical-chemical treatment | 45252100-9 | Sewage-treatment plant construction work | FALSE | 2010 | 2015 | Portugal | Tondela | Viseu | 20 | 35 | 12-05-2011 | 23-12-2015 | 1686 | 150 | 160000 | 150858 | 1 | 169803.87 | -18945.87 | 88.8425 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the change in the deadline was due to the various existing suspensions | existence of mail works and price revision
5197 | 144194 | Acquisition of Services for the elaboration of special projects and execution of all the works necessary for the construction of the School Center | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2015 | Portugal | Vila Nova de Gaia | Porto | 13 | 90 | 29-04-2011 | 16-06-2015 | 1509 | 720 | 4586000 | 4267611.75 | 3 | 3977135.31 | 290476.44 | 107.3037 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there is a work suspension auto. subsequently, a grace period extension was approved at no cost to the municipality until september 8, 2014 | existence of underworks
5198 | 183326 | Urban arrangement of the central and adjacent streets of the village of Carregal do Sal | 45211360-0 | Urban development construction work | FALSE | 2010 | 2015 | Portugal | Carregal do Sal | Viseu | 20 | 30 | 14-04-2011 | 25-09-2015 | 1625 | 365 | 1400000 | 1198856.4 | 3 | 1084455.82 | 114400.58 | 110.5491 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | extension requests by the contractor | measurement hits
5199 | 217149 | The object of the contract is the execution of the contract for the refurbishment and expansion of the Centro Escolar da Igreja - 2nd phase - Lourosa. | 45214210-5 | Primary school construction work | FALSE | 2010 | 2015 | Portugal | Santa Maria da Feira | Aveiro | 1 | 42 | 05-04-2011 | 20-10-2015 | 1659 | 210 | 822221 | 771412.89 | 2 | 766492.89 | 4920 | 100.6419 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 122 days (pg) + 82 days (pg) - correction of work situations in the 1st phase and adaptations to the architectural project; 55 days (pg) + 30 days (pg) - overriding need and public interest in completing the projects; extension of the period between the 1st provisional acceptance (6/11/2012) and the final one (12/10/2015 for the resolution of deficiencies. | underwork resulting from a delay between the measurements of the project and those of the project, or that proved to be unnecessary.
5200 | 584533 | Amphitheater of Montargil | 45212321-2 | Auditorium construction work | FALSE | 2010 | 2015 | Portugal | Ponte de Sor | Portalegre | 12 | 24 | 30-03-2011 | 14-04-2015 | 1476 | 300 | 459897.75 | 433333.33 | 2 | 433333.33 | 0 | 100 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
5201 | 207727 | The design and joint execution of the public work for the rehabilitation of a set of buildings for the installation of the Space for the Promotion of Creativity and Innovation (EPIC) | 45212350-4 | Buildings of particular historical or architectural interest | FALSE | 2010 | 2015 | Portugal | Óbidos | Leiria | 10 | 13 | 25-03-2011 | 14-09-2015 | 1634 | 178 | 340000 | 329245 | 2 | 331804.65 | -2559.65 | 99.2286 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | granting of additional deadlines, pursuant to art. 325 of the "public procurement code" | the change in value comes from the fact that there are underworks and price revisions
5202 | 174188 | Improvement of the EM610 of the EN207 to Vilarelho - Serafão | 45232451-8 | Drainage and surface works | FALSE | 2010 | 2015 | Portugal | Fafe | Braga | 3 | 30 | 10-03-2011 | 13-05-2015 | 1525 | 300 | 1125010.42 | 824232.46 | 2 | 824231.02 | 1.44 | 100.0002 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | there was a suspension of work | there were no changes to the value of the project
5203 | 664353 | The contract consists of the construction of a school center with 2848 m2 of construction area | 45214200-2 | Construction work for school buildings | FALSE | 2010 | 2015 | Portugal | Vagos | Aveiro | 1 | 72 | 17-02-2011 | 27-02-2015 | 1471 | 720 | 3311023.94 | 2389000 | 3 | 2462044.57 | -73044.57 | 97.0332 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | during the contract, two work suspensions were carried out due to the delay in the delivery of technical elements for the execution of the project and, for reasons of lack of payments by the owner of the project. when the contract was resumed, during the course of the projects, it was verified that there was a need to study and produce changes to projects of various specialities, for which reason clarifications were continually requested from the designer and solutions were studied, causing delays in carrying out works, which led to the existence of several extensions of the execution period. | execution of errors and omissions supply works, in a total of €85,556.23. underwork (work not carried out), totaling €84,396.16. price review, totaling €71,884.46.
5204 | 204416 | Construction of the Tagus Reception Center - Aquapolis Margem Sul - Abrantes. Demolition of existing buildings and structures. Building construction work and outdoor spaces. | 45212000-6 | Construction work for buildings relating to leisure, sports, culture, lodging and restaurants | FALSE | 2010 | 2015 | Portugal | Abrantes | Santarém | 16 | 9 | 13-12-2010 | 05-05-2015 | 1604 | 365 | 1269276.57 | 948313.78 | 2 | 931978.2 | 16335.58 | 101.7528 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline changes were due to major financial difficulties on the part of the contractor, and there was even a need for a contractual position assignment, on 7/17/2013. | the change in the value of the project came about as a result of the existence of underwork due to a superior decision, taken by decision of the chamber, as well as the calculation of price revisions, in accordance with the legislation.
5205 | 134915 | Current conservation by contract – 2010/2013. South Operational Center - District of Beja | 45233140-2 | Roadworks | FALSE | 2010 | 2015 | Portugal | Beja | Beja | 13 | 48 | 04-08-2010 | 14-08-2015 | 1836 | 1092 | 16000000 | 10547759.03 | 3 | 11166439.18 | -618680.15 | 94.4595 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the deadline extensions were granted in view of the delay in the 2013/2016 current conservation tenders, in order to ensure the public interest (safety of road traffic), while it was not possible to start the new current conservation contract. | calculation during the course of the contract of additional works in the amount of €2,113,143.35, positive errors and omissions supply work in the amount of €1,623,147.74, negative errors and omissions supply work in the amount of €171,628, €71 and underwork amounting to €2,945,982.24
5206 | 134913 | Current conservation by contract - 2010/2013. South Operational Center - District of Faro. | 45233140-2 | Roadworks | FALSE | 2010 | 2015 | Portugal | Faro | Faro | 13 | 48 | 04-08-2010 | 04-05-2015 | 1734 | 1092 | 8000000 | 4800000.1 | 3 | 4638127.5 | 161872.6 | 103.49 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the term extensions were granted in view of the delay in tendering for the 2013/2016 current conservation contracts. in order to ensure the public interest (road traffic safety), while it was not possible to start the new current conservation contract | the value indicated in underwork (art. 379.º, n.º 2 of the "public procurement code") corresponds to negative values ​​of "works to correct errors and omissions, not included in the initial contract (art. 377.º, n.º 1 of the "public procurement code")" 159,372.61 € plus underwork in the amount of -2,500.00 €.
5207 | 206756 | Business Reception Area of ​​Esmolfe - Sezures | 45213251-7 | Industrial units construction work | FALSE | 2010 | 2015 | Portugal | Penalva do Castelo | Viseu | 20 | 5 | 13-12-2010 | 07-10-2015 | 1759 | 550 | 996309.18 | 672704.61 | 2 | 667238.46 | 5466.15 | 100.8192 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | suspension and extensions of the term | underwork
5208 | 194945 | Urban Requalification of the West Entrance of Grândola and Reconstruction/Expansion of the Cine-Teatro Grandolense/SMFOG - Alterations | 45262700-8 | Building alteration work | FALSE | 2010 | 2015 | Portugal | Grandola | Setúbal | 17 | 5 | 14-10-2010 | 16-04-2015 | 1645 | 210 | 1730374.67 | 1279699.92 | 3 | 1514793.34 | -235093.42 | 84.4802 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | the contract was suspended for 10 days, due to the adverse weather conditions that occurred, thus preventing the execution of the projects with the necessary technical and safety conditions. | during the contract, errors and omissions were detected in the project, whose supply led to the execution of non-contractual works.
5209 | 127711 | The object of this contract is to carry out the contract called the House of Knowledge. | 45210000-2 | Building construction work | FALSE | 2010 | 2015 | Portugal | Vila Verde | Braga | 3 | 30 | 20-10-2010 | 30-04-2015 | 1653 | 350 | 1442272.82 | 995000 | 2 | 968424.8 | 26575.2 | 102.7442 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | underwork
5210 | 136794 | The aim is to organize Largo 25 de Abril, with all the reception space, as well as dignifying the accesses to the aforementioned square and consequently to the interior of the Walls of the Fortress of Almeida | 45233250-6 | Surfacing work except for roads | FALSE | 2010 | 2015 | Portugal | Almeida | Guarda | 9 | 24 | 15-10-2010 | 20-01-2015 | 1558 | 365 | 1008286.53 | 660124.39 | 2 | 625106.3 | 35018.09 | 105.6019 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | weather conditions, among others | existence of underworks
5211 | 132712 | Exterior spaces of the eb1 school + ji das galinheiras | 45112700-2 | Landscaping work | FALSE | 2010 | 2015 | Portugal | Lisboa | Lisboa | 11 | 20 | 01-07-2010 | 09-03-2015 | 1712 | 455 | 745000 | 490132.6 | 2 | 495584.98 | -5452.38 | 98.8998 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A
5212 | 102351 | Remodeling of the Amieira do Tejo and Montalvão WWTP and Execution of the Pé da Serra WWTP | 45252127-4 | Wastewater treatment plant construction work | FALSE | 2009 | 2015 | Portugal | Nisa | Portalegre | 12 | 57 | 01-06-2010 | 27-03-2015 | 1760 | 210 | 720000 | 591671.18 | 2 | 498642.64 | 93028.54 | 118.6564 | Wrong ad link \ failed to download pdf | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delay in the approval of equipment attributable to the owner of work. | there was withdrawal of work during the course of the contract.
5213 | 134832 | Execution contract for the Interceptor Systems of Some SAR of AT and DN | 71300000-1 | Engineering services | FALSE | N/A | 2015 | Portugal | Peso da Régua | Vila Real | 19 | N/A | 18-02-2010 | 30-04-2015 | 1897 | 365 | N/A | 3645228.71 | 3 | 4061634.12 | -416405.41 | 89.7478 | Contract without details about the ad | 0 | 0 | N/A | N/A | Complete fulfillment of the contract | 0 | N/A | N/A | N/A | N/A | N/A | N/A | delays in the execution of works | additional work and errors and omissions